## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-085-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0085 - SUP INSTALLATION (HCC)
section | Lot Information
checkpoint | 1.0 Lot Information
textbox | Lot Created On
textbox | Lot Opened On
textbox | Work Commenced On
dropdown | Lot Type | CIL - Civil Lot
textbox | From and To Chainage
dropdown | Construction Element | PAVI - Paving
dropdown | Activity | SHUP – Shared User Path
dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
textbox | Engineer Responsible
textbox | comments
section | 1 - Preliminary Works
checkpoint | 1.1 - Check that current revision drawings are being used
note | Frequency: Prior to Commencing
note | - - - - - - - - -
note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
note | - - - - - - - - -
note | Reference Documents: Project Drawings / Drawing Register
note | - - - - - - - - -
note | Inspection / Test Method: Document review
note | - - - - - - - - -
note | Record of conformity: Latest Revision Drawings
note | - - - - - - - - -
note | AP
note | - - - - - - - - -
note | Responsibility: Site Engineer / Site Foreman
checkpoint | 1.2 - Bedding Material / Base Layer
note | Frequency: Once, for each mix design, prior to placement of material
note | - - - - - - - - -
note | Acceptance Criteria: 20mm Class 3 bedding material conforms to specified requirements applicable to the class of product as detailed on the drawings.
note | • Material is registered with VicRoads in accordance with Code of Practice RC500.02.
textbox | Enter: Teambinder Material Approval number
note | - - - - - - - - -
note | Reference Documents: IFC Drawings 703.21 812.04
note | - - - - - - - - -
note | Inspection / Test Method: Document Review
note | - - - - - - - - -
note | Record of conformity: Teambinder reference number
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Site Engineer Superintendent
checkpoint | 1.3 - Concrete Mix
note | Frequency: Once, for each mix design, prior to placement of concrete
note | - - - - - - - - -
note | Acceptance Criteria: Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings.
note | • Paving concrete mix conforms to AS1379. SUP concrete mix is registered with VicRoads.
note | • No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
note | • Concrete mix designs shall remain valid for 12 months from the date of registration, unless constituent materials and material proportions cease to comply with the specified requirements.
textbox | Enter: Teambinder Material Approval number
note | - - - - - - - - -
note | Reference Documents: IFC Drawings 703.05 (a) 703.07
note | - - - - - - - - -
note | Inspection / Test Method: Document Review
note | - - - - - - - - -
note | Record of conformity: Teambinder reference number
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Site Engineer
checkpoint | 1.4 - Evaporative Retardant
note | Frequency: Once, for each product, prior to placement of concrete
note | - - - - - - - - -
note | Acceptance Criteria: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
note | - - - - - - - - -
note | Reference Documents: 703.09
note | - - - - - - - - -
note | Inspection / Test Method: Document Review
note | - - - - - - - - -
note | Record of conformity: Teambinder reference number
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Site Engineer
checkpoint | 1.5 - Curing Compound
note | Frequency: Once, for each product, prior to placement of concrete
note | - - - - - - - - -
note | Acceptance Criteria: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
note | - - - - - - - - -
note | Reference Documents: 703.10 (a)
note | - - - - - - - - -
note | Inspection / Test Method: Document Review
note | - - - - - - - - -
note | Record of conformity: Teambinder reference number
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Site Engineer
section | 2 - Construction Works
checkpoint | 2.2 - Temporary Drainage Provisions (if required)
note | Frequency: Prior to Commencing
note | - - - - - - - - -
note | Acceptance Criteria: Before obstructing any waterway, channel or culvert, the Contractor shall make appropriate provision for its temporary diversion, and obtain prior written approval from the relevant waterway authority.
note | • The Contractor shall make provision for the safe discharge of drainage and stormwater at all times during construction.
note | - - - - - - - - -
note | Reference Documents: IFC Drawings, VicRoads Spec Cl.703.18
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: Written approval from relevant waterway authority, ITP Signed
note | - - - - - - - - -
note | AP
note | - - - - - - - - -
note | Responsibility: Supervisor / Site Engineer
checkpoint | 2.3 - Pavement Thickness Increases for Crossings
note | Frequency: Prior to Commencing
note | - - - - - - - - -
note | Acceptance Criteria: Where applicable, excavation to allow for increase in the bedding and slab thicknesses at:
note | i. Pram crossings
note | ii. Vehicle crossings (residential and/or commercial)
note | iii. Established / existing mature trees
note | • Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths.
note | - - - - - - - - -
note | Reference Documents: IFC Drawings
note | • VicRoads Spec 703.16 703.24 EDCM 401
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: ITP Signed
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Superintendent/ Supervisor / Site Engineer
checkpoint | 2.4 - Subgrade Preparation
note | Frequency: Each Lot
note | - - - - - - - - -
note | Acceptance Criteria: Subgrade to be test rolled to ensure the substrate is adequate for bedding and concrete placement
note | - - - - - - - - -
note | Reference Documents: WP 011
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: ITP Signed
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
note | Responsibility: Supervisor / Site Engineer
checkpoint | 2.5 - Bedding Preparation
note | Frequency: Each Lot
note | - - - - - - - - -
note | Acceptance Criteria: All bedding material shall be as specified on design drawings.
note | • Where not specified, bedding material used for cast in place concrete paving works shall be compacted size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
note | • Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface. Bedding to be compacted to 98% standard.
note | - - - - - - - - -
note | Reference Documents: VicRoads Spec Cl.703.21 812, 820
note | • IFC Drawings
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: ITP Signed
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Supervisor / Site Engineer
checkpoint | 2.6 - Formwork
note | Frequency: Prior to Commencing
note | - - - - - - - - -
note | Acceptance Criteria: Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
note | - - - - - - - - -
note | Reference Documents: VicRoads Spec Cl.703.12
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: ITP Signed
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Supervisor / Site Engineer
checkpoint | 2.7 - Steel Reinforcement
note | Frequency: Prior to Commencing
note | - - - - - - - - -
note | Acceptance Criteria: Steel reinforcement shall be placed in accordance with drawings and AS/NZS 4671. If not specified, mesh shall be placed as per VicRoads Spec Cl. 703.16.
note | • The minimum cover of any steel reinforcement to the nearest concrete surface shall be 50 mm unless shown on the drawings.
note | • Reinforcement shall be supported using either concrete or plastic chairs.
note | - - - - - - - - -
note | Reference Documents: VicRoads Spec Cl.703.13 & Cl.703.13 AS/NZS 4671
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: ITP Signed
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Supervisor / Site Engineer
checkpoint | 2.8 - Pre-pour inspection
note | Frequency: Each Lot
note | - - - - - - - - -
note | Acceptance Criteria: Inspection to ensure that forms, reinforcement dowels and other embedments conform to the requirements of the specifications and drawings.
note | - - - - - - - - -
note | Reference Documents: VicRoads Spec Cl.703.05, Cl.703.09, Cl.610.17 (a)(b)(c)(d), AS 1379
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: ITP Signed
note | - - - - - - - - -
note | HP
note | - - - - - - - - -
note | Responsibility: Project Engineer, Superintendent/Council & Surveyor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.9 - Concrete Testing
note | Frequency: Each Lot
note | - - - - - - - - -
note | Acceptance Criteria:
note | ○ Concrete Testing Frequency:
note | • 0m³ to 50m³ = 1 sample
note | • Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
note | • Compressive strength cylinders = 2 no. 28 day strength.
note | ○ Slump Testing Tolerances:
note | • <60mm = ±10mm
note | • ≥60mm to ≤80mm = ±15mm
note | • >80mm to ≤110mm = ±20mm
note | • >110mm to ≤150mm = ±30mm
note | • >150mm = ±40mm
note | - - - - - - - - -
note | Reference Documents: VicRoads Spec 703.11
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: Concrete Pour Record, ITP Signed
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Supervisor / Site Engineer
checkpoint | 2.10 - Curing
note | Frequency: Each Lot
note | - - - - - - - - -
note | Acceptance Criteria: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed and shall continue uninterrupted for a period of not less than 7 days after placing the concrete
note | • Concrete shall be cured either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these
note | - - - - - - - - -
note | Reference Documents: VicRoads Spec Cl. 703.10
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: ITP Signed
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Supervisor / Site Engineer
checkpoint | 2.11 - Tolerances
note | Frequency: Each Lot
note | - - - - - - - - -
note | Acceptance Criteria: Concrete paving to match existing fixtures (e.g. pit covers, edgings and vehicle crossings) within 5mm.
note | • Deviation of finished work shall not exceed; 10mm from line or level; or 5mm from a 3m straightedge for curves and shaped areas.
note | • Deviation of section dimensions shall not exceed 5mm (except for overall width); 25mm for the overall width; and +/- 3mm for dimensions less than 25mm.
note | - - - - - - - - -
note | Reference Documents: VicRoads Spec. Cl 703.15
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: ITP Signed
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Supervisor / Site Engineer
checkpoint | 2.12 - Joints
note | Frequency: Each Lot
note | - - - - - - - - -
note | Acceptance Criteria: Expansion Joints: shall be placed at intervals as specified by the drawings.
note | • Control Joints: at least 25% of the paving thickness deep and 5 mm wide shall be formed with a cutting tool at 2.5 m intervals along the full width of footpaths, other surfacings and shared use paths.
note | • Between Concrete Paving and Shared Use Path: Except for medians <2.0m wide, bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt (ableflex).
note | - - - - - - - - -
note | Reference Documents: VicRoads Spec Cl. 703.26 (b)
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: ITP Signed
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Supervisor / Site Engineer
checkpoint | 2.13 - Stripping Formwork
note | Frequency: Each Lot
note | - - - - - - - - -
note | Acceptance Criteria: Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
note | i. 2 days for vertical formwork on external surfaces; and
note | ii. 1 day for vertical forms on permanently hidden surfaces
note | - - - - - - - - -
note | Reference Documents: VicRoads Spec 703.12, AS3610 Table C2
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: ITP Signed
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Supervisor / Site Engineer
checkpoint | 2.14 - Protection of Newly Poured Concrete
note | Frequency: Each Lot
note | - - - - - - - - -
note | Acceptance Criteria: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
note | • Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
note | - - - - - - - - -
note | Reference Documents: VicRoads Spec 703.27
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: ITP Signed
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Supervisor / Site Engineer
section | 3 - Post-Construction
checkpoint | 3.1 - Survey data captured for as-built purposes
note | Frequency: Completion of each lot
note | - - - - - - - - -
note | Acceptance Criteria: Survey to ensure and validate that all works meet level and location requirements.
note | • Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design.
note | • As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
note | - - - - - - - - -
note | Reference Documents: IFC Drawings / survey records
note | - - - - - - - - -
note | Inspection / Test Method: Document review
note | - - - - - - - - -
note | Record of conformity: As-built survey records
note | - - - - - - - - -
note | SCP
note | - - - - - - - - -
note | Responsibility: Project Engineer
checkpoint | 3.2 - Cracking of Concrete
note | Frequency: Each Lot
note | - - - - - - - - -
note | Acceptance Criteria: The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
note | • Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
note | - - - - - - - - -
note | Reference Documents: VicRoads Spec. Cl. 703.30 687
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: ITP Signed
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Supervisor / Site Engineer
checkpoint | 3.2 - Compressive Strength Test Results
note | Frequency: Completion of each lot
note | - - - - - - - - -
note | Acceptance Criteria: 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
note | - - - - - - - - -
note | Reference Documents: IFC Drawings, Relevant Council Drawings 703.11, Table 703.111
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: Attach: Compressive Strength Test Results
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Supervisor / Site Engineer
checkpoint | 3.3 - Backfilling
note | Frequency: Completion of each lot
note | - - - - - - - - -
note | Acceptance Criteria: Where required, as soon as concrete has cured sufficiently and not earlier than three days after placing, topsoil shall be placed and firmly compacted in layers not exceeding 150mm and to a width not less than 300mm behind the edging to the top of the edging.
note | - - - - - - - - -
note | Reference Documents: VicRoads Spec. Cl 703.29
note | - - - - - - - - -
note | Inspection / Test Method: Site Inspection
note | - - - - - - - - -
note | Record of conformity: ITP Signed
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Supervisor / Site Engineer
section | 4 - Completion
checkpoint | 4.1 - As-built Survey
note | Frequency: Completion of each lot
note | - - - - - - - - -
note | Acceptance Criteria: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
note | • Departure from RL = ±10mm
note | • Departure from alignment = ±10mm
note | • Rate of change of deviation from RL or alignment = 10mm in 10m
note | • Irregularities in alignment = 5mm in 3m
note | • Section dimensions = ±5mm
note | • Section dimensions (less than 25mm) = ±3mm
note | • Width of pavement = -5mm, +15mm
note | • Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges.
note | Attach: Survey As-builts / Survey Report
note | - - - - - - - - -
note | Reference Documents: IFC Drawings, VicRoads Spec 703.15
note | - - - - - - - - -
note | Inspection / Test Method: Document Review
note | - - - - - - - - -
note | Record of conformity: ITP Signed
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Site Engineer
checkpoint | 4.2 - Red-Line Markup
note | Frequency: Completion of each lot
note | - - - - - - - - -
note | Acceptance Criteria: Capture any changes in design or RFI's as per approved red-line markup procedure
note | - - - - - - - - -
note | Reference Documents: Quality Management Plan
note | - - - - - - - - -
note | Inspection / Test Method: Document Review
note | - - - - - - - - -
note | Record of conformity: ITP Signed
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Site Engineer
checkpoint | 4.3 - Non-conformance Report (NCR) Closure
note | Frequency: Completion of each lot
note | - - - - - - - - -
note | Acceptance Criteria: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
note | - - - - - - - - -
note | Reference Documents: Quality Management Plan
note | - - - - - - - - -
note | Inspection / Test Method: Document Review
note | - - - - - - - - -
note | Record of conformity: ITP Signed
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Site Engineer
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Name:
textbox | Position:
textbox | Date:
textbox | Work Completed On:
signoff | Add Signature
section | Lot Verification
checkpoint | Lot Verification.
dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
dropdown | Lot verified By | Babak Rudd (Quality Manager),Abid Hameed (Area 1 Manager),Nicola Lodo (Area 2 Manager),Nicholas Terpstra (Delivery Manager),Other:
textbox | Other:
dropdown | Lot Status | OUTSTANDING, CLOSED
textbox | Lot Closed On
textbox | comments