## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Plant Room - Second Fix - Checklist |  |  |  |  | Yes | Plant Room - Second Fix - Checklist | 02a25917-edaf-4833-a4d4-3fc80978a0e1
checkpoint-status |  |  | checkpoint | Thermal insulation stalled
checkpoint-status |  |  | checkpoint | Plant room commissioned correctly
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checklist-flat |  |  | checklist | Corridor DHW/DCW Ke Kelit Checklist |  |  |  |  | Yes | Corridor DHW/DCW Ke Kelit Checklist | 224e1b1e-b779-4d0d-b2dc-adcc477cb13d
checkpoint-status |  |  | checkpoint | TMV Installed to RCP plan
checkpoint-status |  |  | checkpoint | Isolation valves installed to valve set & tested to 1500 kpa
checkpoint-status |  |  | checkpoint | Thermal Insulation installed to DHW
checkpoint-status |  |  | checkpoint | Ke Kelit pressed and witness marks visible
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checklist-flat |  |  | checklist | Plant Room - First Fix - Checklist |  |  |  |  | Yes | Plant Room - First Fix - Checklist | 3f9a7b6c-2874-42b8-8b37-ebbd7c380c5c
checkpoint-status |  |  | checkpoint | Ke kelit pipework pressed and witness mark visible
checkpoint-status |  |  | checkpoint | Pressure tested to 1500kpa and passed by council
checkpoint-status |  |  | checkpoint | Plant room installed as per engineer schematic (valves installed, gauges, control valves)
checkpoint-status |  |  | checkpoint | Seismic restraints installed
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checklist-flat |  |  | checklist | Basement Checklist |  |  |  |  | Yes | Basement Checklist | 44327d9a-c802-4aed-af20-b7fd0d43b4e1
checkpoint-status |  |  | checkpoint | Main drainage installed as per plan
checkpoint-status |  |  | checkpoint | Drainage risers installed as per drawings
checkpoint-status |  |  | checkpoint | Clips at correct spacing
checkpoint-status |  |  | checkpoint | Flood tested and passed by council
checkpoint-status |  |  | checkpoint | Seismic restraints installed
checkpoint-status |  |  | checkpoint | Floor Isolation Valves installed
checkpoint-status |  |  | checkpoint | Thermal insulation (DHW Only)
checkpoint-status |  |  | checkpoint | Ke Kelit pressed and witness mark visible
checkpoint-status |  |  | checkpoint | Tested to 1500kpa and passed by council
checkpoint-status |  |  | checkpoint | RPZ installed to DCW and tested
checkpoint-status |  |  | checkpoint | Riser installed as per plan
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checklist-flat |  |  | checklist | Substration Checklist |  |  |  |  | Yes | Substration Checklist | 5a54e37e-8b5c-4f8d-b367-4a7d77ca6ea6
checkpoint-status |  |  | checkpoint | Flanges installed
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checklist-flat |  |  | checklist | Water Risers Checklist |  |  |  |  | Yes | Water Risers Checklist | 688a552a-9e65-403d-88e5-8ae74eec3039
checkpoint-status |  |  | checkpoint | Floor Isolation Valves installed
checkpoint-status |  |  | checkpoint | Thermal insulation to DHW
checkpoint-status |  |  | checkpoint | Ke Kelit pressed and witness mark visible
checkpoint-status |  |  | checkpoint | Tested to 1500kpa and passed
checkpoint-status |  |  | checkpoint | Clips installed at correct spacing
checkpoint-status |  |  | checkpoint | Riser installed as per plan
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checklist-flat |  |  | checklist | First Fix Checklist |  |  |  |  | Yes | First Fix Checklist | 6d91708b-1074-4ac5-8b1b-ca33279a18f0
checkpoint-status |  |  | checkpoint | Correct set out for all fixtures
checkpoint-status |  |  | checkpoint | Checked for crossovers
checkpoint-status |  |  | checkpoint | All pipes clipped securely
checkpoint-status |  |  | checkpoint | All pipework pressure tested
checkpoint-status |  |  | checkpoint | All waste pipes flood tested
checkpoint-status |  |  | checkpoint | Fixing for all fixtures
checkpoint-status |  |  | checkpoint | Hot water supply lagged
checkpoint-status |  |  | checkpoint | FWG flanges installed and construction capped fitted
checkpoint-status |  |  | checkpoint | Shower tray and mixer installed to manufacturers instruction
checkpoint-status |  |  | checkpoint | Acoustic Insulation Installed as per specification
checkpoint-status |  |  | checkpoint | Area Left clean and tidy
checklist-flat |  |  | checklist | Balcony Drainage/External Stormwater Drainage - Second Fix - Checklist |  |  |  |  | Yes | Balcony Drainage/External Stormwater Drainage - Second Fix - Checklist | bc2c3bfe-c831-4e83-bbce-2f09023fdc7c
checkpoint-status |  |  | checkpoint | Balconies overflow terminated to underside of soffit
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checklist-flat |  |  | checklist | Balcony Drainage/External Stormwater Drainage - First Fix - Checklist |  |  |  |  | Yes | Balcony Drainage/External Stormwater Drainage - First Fix - Checklist | bf8ae3bf-c978-4db0-abc6-3bd4546bd5b6
checkpoint-status |  |  | checkpoint | Setout and position checked and confirmed
checkpoint-status |  |  | checkpoint | Trench width and lid level (attach photos)
checkpoint-status |  |  | checkpoint | Gaps measured and ordered
checkpoint-status |  |  | checkpoint | Stockpiles & cart out confirmed
checkpoint-status |  |  | checkpoint | Pipework installed as per specification
checkpoint-status |  |  | checkpoint | Pipe test booked and test ready
checkpoint-status |  |  | checkpoint | As built plans complete
checkpoint-status |  |  | checkpoint | Clegg test on hardfill (results recorded)
checkpoint-status |  |  | checkpoint | Clamp ring and dome installed to outlet and overflow
checkpoint-status |  |  | checkpoint | Clamp ring and allthrough flange installed to outlet
checkpoint-status |  |  | checkpoint | Stormwater riser installed to allthrough outlet
checkpoint-status |  |  | checkpoint | Pipework complete & ready for sign off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checklist-flat |  |  | checklist | Second Fix Checklist |  |  |  |  | Yes | Second Fix Checklist | f765593c-af7f-4d1f-a8ec-e9126d86ab63
checkpoint-status |  |  | checkpoint | Backflow installed on showers (RPZ at main)
checkpoint-status |  |  | checkpoint | Escutcheons/flanges installed to all fixtures
checkpoint-status |  |  | checkpoint | Heights checked as per plan for all fixtures
checkpoint-status |  |  | checkpoint | Testing of all installed fixtures (flood test)
checkpoint-status |  |  | checkpoint | Silicone applied is neat and tidy
checkpoint-status |  |  | checkpoint | Fixtures installed are to spec/clean and tidy
checkpoint-status |  |  | checkpoint | Kitchen has univalve installed for dishwasher
checkpoint-status |  |  | checkpoint | Laundry box is ready for washing machine installation
checkpoint-status |  |  | checkpoint | Temperature test to sanitary fixtures/kitchen
checkpoint-status |  |  | checkpoint | Aerator to basin mixer/kitchen sink checked and cleaned
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checklist-flat |  |  | checklist | Underslab Checklist |  |  |  |  | Yes | Underslab Checklist | f8d78e46-838c-4868-912a-19607e06e8c5
checkpoint-status |  |  | checkpoint | Pipework Material as specified/scheduled/drawn
checkpoint-status |  |  | checkpoint | Grid lines and fitting dimensions confirmed
checkpoint-status |  |  | checkpoint | Drain invert checked
checkpoint-status |  |  | checkpoint | Gully position checked
checkpoint-status |  |  | checkpoint | Floor levels established
checkpoint-status |  |  | checkpoint | Falls checked
checkpoint-status |  |  | checkpoint | Drainlayer/Plumber interface Points established
checkpoint-status |  |  | checkpoint | Penetrations co-ordinated with main contractor
checkpoint-status |  |  | checkpoint | Pipework backfilled correctly
checkpoint-status |  |  | checkpoint | Identification strip installed if required
checkpoint-status |  |  | checkpoint | Open ends of pipework capped off to prevent dirt ingress
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checkpoint-status |  |  | checkpoint | Area left clean and tidy