## Project Structure
Folder Structure |  |  |  |  | Checklists
Site QA
Basement 1
|  | Lifts 1-3 Pit |  |  | Lift Pits Waterproofing
|  | Lifts 4-6 Pit |  |  | Lift Pits Waterproofing
|  | Lifts 7-9 Pit |  |  | Lift Pits Waterproofing
|  | Lift 10 Pit |  |  | Lift Pits Waterproofing
|  | Lift 11 Pit |  |  | Lift Pits Waterproofing
|  | Skybar Waste Room |  |  | Waste/bin rooms
|  | Hotel Bin Room |  |  | Waste/bin rooms
|  | Residential Bin Room |  |  | Waste/bin rooms
|  | Dirty Linen |  |  | Waste/bin rooms
|  | Clean Linen |  |  | Waste/bin rooms
|  | Cleaners Room |  |  | Waste/bin rooms
|  | Stormwater Tank |  |  | Stormwater Tanks Waterproofing
|  | Rainwater Tank |  |  | Stormwater Tanks Waterproofing
|  | OSD Tank |  |  | Stormwater Tanks Waterproofing
Ground
|  | Fire Pump Room |  |  | Fire Sprinkler Tanks Waterproofing
|  | Waste Room |  |  | Waste/bin rooms
|  | Pub Bin Room |  |  | Waste/bin rooms
|  | Fire Pump Room/Tank |  |  | Fire Sprinkler Tanks Waterproofing
|  | Bulky Waste 1 |  |  | Waste/bin rooms
|  | Bulky Waste 2 |  |  | Waste/bin rooms
|  | Hotel Staff Locker Room |  |  | Internal wet areas
|  | Hotel Lobby Toilets |  |  | Internal wet areas
|  | Pub Kitchen |  |  | Internal wet areas
|  | Pub Toilets |  |  | Internal wet areas
|  | Planterboxes |  |  | Planter Box Waterproofing
Level 1
|  | Planterboxes |  |  | Planter Box Waterproofing
Level 2
|  | Planterboxes |  |  | Planter Box Waterproofing
Level 3
|  | Planterboxes |  |  | Planter Box Waterproofing
Level 4
|  | Planterboxes |  |  | Planter Box Waterproofing
Level 5
|  | Planterboxes |  |  | Planter Box Waterproofing
Swimming Pool
|  | Courtyard/Common Area |  |  | Roof, Terraces & Walkways Waterproofing
West Tower
Level 5
501
|  |  |  | Slab Edge | Slab Edges Waterproofing
|  |  |  | Hobs | Hobs
|  |  |  | Bathrooms | Internal wet areas
|  |  |  | Balcony | Balcony Waterproofing
502
503
504
505
506
507
508
509
Level 6
601
602
603
604
605
606
607
608
609
Level 7
701
702
703
704
705
706
707
708
709
Level 8
801
802
803
804
805
806
807
808
809
Level 9
901
902
903
904
905
906
907
908
909
Level 10
1001
1001
1001
1001
1001
1001
1001
1001
1001
Level 11
1101
1102
1103
1104
1105
1106
1107
1108
1109
Level 12
1201
1202
1203
1204
1205
1206
1207
1208
1209
Level 13
1301
1302
1303
1304
1305
1306
1307
1308
1309
Level 14
1401
1402
1403
1404
1405
1406
1407
1408
1409
Level 15
1501
1502
1503
1504
1505
1506
1507
1508
1509
Level 16
1601
1602
1603
1604
1605
1606
1607
1608
1609
Level 17
1701
1702
1703
1705
1706
1707
1708
1709
Level 18
1801
1802
1803
1805
1806
1807
1808
1809
Level 19
1901
1902
1903
1905
1906
1907
1908
1909
Level 20
2001
2002
2003
2004
2005
2006
2007
2008
2009
Level 21
2101
2102
2103
2104
2105
2106
2107
2108
2109
Level 22
2201
2202
2203
2204
2205
2206
2207
2208
2209
Level 23
2301
2302
2303
2304
2305
2306
2307
2308
2309
Level 24
2401
2402
2403
2404
2405
2406
2407
2408
2409
Level 25
2501
2502
2503
2504
2505
2506
2507
2508
2509
Level 26
2601
2602
2603
2604
2605
Level 27
2701
2702
2703
2704
2705
Level 27
|  |  | Roof |  | Roof, Terraces & Walkways Waterproofing
East Tower
Level 5
|  |  | Restaurant |  | Internal wet areas
|  |  | Outdoor Gym |  | Roof, Terraces & Walkways Waterproofing
|  |  | Male, Female, and Accessible EC & Change |  | Internal wet areas
Hotel Room 501
|  |  |  | Slab Edge | Slab Edges Waterproofing
|  |  |  | Hobs | Hobs
|  |  |  | Bathrooms | Internal wet areas
|  |  |  | Balcony | Balcony Waterproofing
Hotel Room 502
Hotel Room 503
Hotel Room 504
Hotel Room 505
Hotel Room 506
Hotel Room 507
Hotel Room 508
Hotel Room 509
Hotel Room 510
Hotel Room 511
Hotel Room 512
Hotel Room 513
Level 6
|  |  | Hotel Kitchen |  | Internal wet areas
|  |  | Hotel BOH |  | Internal wet areas
|  |  | Male, Female, DDS Bathroom |  | Internal wet areas
|  |  | Pre-Function (Winter Garden) |  | Roof, Terraces & Walkways Waterproofing
Hotel Room 601
Hotel Room 602
Hotel Room 603
Hotel Room 604
Hotel Room 605
Hotel Room 606
Hotel Room 607
Hotel Room 608
Hotel Room 609
Hotel Room 610
Hotel Room 611
Hotel Room 612
Hotel Room 613
Hotel Room 614
Level 7
|  |  | Conference Room Roof |  | Roof, Terraces & Walkways Waterproofing
Hotel Room 701
Hotel Room 702
Hotel Room 703
Hotel Room 704
Hotel Room 705
Hotel Room 706
Hotel Room 707
Hotel Room 708
Hotel Room 709
Hotel Room 710
Hotel Room 711
Hotel Room 712
Hotel Room 713
Hotel Room 714
Hotel Room 715
Hotel Room 716
Hotel Room 717
Hotel Room 718
Hotel Room 719
Hotel Room 720
Hotel Room 721
Hotel Room 722
Hotel Room 723
Level 8
Hotel Room 801
Hotel Room 802
Hotel Room 803
Hotel Room 804
Hotel Room 805
Hotel Room 806
Hotel Room 807
Hotel Room 808
Hotel Room 809
Hotel Room 810
Hotel Room 811
Hotel Room 812
Hotel Room 813
Hotel Room 814
Hotel Room 815
Hotel Room 816
Hotel Room 817
Hotel Room 818
Hotel Room 819
Hotel Room 820
Hotel Room 821
Hotel Room 822
Hotel Room 823
Level 9
|  |  | Non-Trafficable Roof |  | Roof, Terraces & Walkways Waterproofing
Hotel Room 901
Hotel Room 902
Hotel Room 903
Hotel Room 904
Hotel Room 905
Hotel Room 906
Hotel Room 907
Hotel Room 908
Hotel Room 909
Hotel Room 910
Hotel Room 911
Hotel Room 912
Hotel Room 913
Hotel Room 914
Hotel Room 915
Hotel Room 916
Hotel Room 917
Hotel Room 918
Hotel Room 919
Level 10
Hotel Room 1001
Hotel Room 1002
Hotel Room 1003
Hotel Room 1004
Hotel Room 1005
Hotel Room 1006
Hotel Room 1007
Hotel Room 1008
Hotel Room 1009
Hotel Room 1010
Hotel Room 1011
Hotel Room 1012
Hotel Room 1013
Hotel Room 1014
Hotel Room 1015
Hotel Room 1016
Hotel Room 1017
Hotel Room 1018
Hotel Room 1019
Level 11
Hotel Room 1101
Hotel Room 1102
Hotel Room 1103
Hotel Room 1104
Hotel Room 1105
Hotel Room 1106
Hotel Room 1107
Hotel Room 1108
Hotel Room 1109
Hotel Room 1110
Hotel Room 1111
Hotel Room 1112
Hotel Room 1113
Hotel Room 1114
Hotel Room 1115
Hotel Room 1116
Hotel Room 1117
Hotel Room 1118
Hotel Room 1119
Level 12
1201
|  |  |  | Slab Edge | Slab Edges Waterproofing
|  |  |  | Hobs | Hobs
|  |  |  | Bathrooms | Internal wet areas
|  |  |  | Balcony | Balcony Waterproofing
1202
1203
1204
1205
1206
1207
Level 13
1301
1302
1303
1304
1305
1306
1307
1308
1309
Level 14
1401
1402
1403
1404
1405
1406
1407
1408
1409
Level 15
1501
1502
1503
1504
1505
1506
1507
1508
1509
Level 16
1601
1602
1603
1604
1605
1606
1607
1608
Level 17
1701
1702
1703
1704
1705
1706
1707
1708
Level 18
1801
1802
1803
1804
1805
1806
1807
1808
Level 19
1901
1902
1903
1904
1905
1906
1907
1908
Level 20
2001
2002
2003
2004
2005
2006
2007
2008
Level 21
2101
2102
2103
2104
2105
2106
2107
2108
Level 22
2201
2202
2203
2204
2205
2206
2207
2208
Level 23
2301
2302
2303
2304
2305
2306
2307
2308
Level 24
2401
2402
2403
2404
2405
2406
2407
2408
Level 25
2501
2502
2503
2504
2505
2506
2507
2508
Level 26
2601
2602
2603
2604
2605
Level 27
2701
2702
2703
2704
2705
Level 28
|  |  | Skybar Bathroom |  | Internal wet areas
|  |  | Skybar Outdoor Areas |  | Roof, Terraces & Walkways Waterproofing
Level 29
|  |  | Roof |  | Roof, Terraces & Walkways Waterproofing

## Checklist
type | name
checklist | Slab Edges Waterproofing
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
label | Attach relevant photos
button | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
button | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
button | Ensure no high points or crevices are in the substrate
button | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Dampen the surface to ensure the highest level of adhesion as required
label | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines & ensure WPM to be extened and terminated inside the drip groove.
label | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines & ensure WPM to be extened and terminated inside the drip groove.
label | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
label | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
label | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
label | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Balcony Waterproofing
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
label | Attach relevant photos
checkpoint | WP details listed at architectural drawings for clarifications are followed.
button | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
button | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
button | Ensure no high points or crevices are in the substrate
button | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Prime substrate with Polybit Hydrapoxy or PU primer - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Seal all corners, joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant - Apply selected sealant as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Balustrade base i.e shoe base or angle base installed & grouted with structural grout (as required)
label | Joint between bttom of base & substrate to be no greater than 10mm with continuous bead of caulking
checkpoint | Overflow at the ends of balustrades in place
label | Approximate width of over floor to be 50mm
label | Height of overflow must be lower than the bttom of subsill
label | Angle to be installed between end of base & wall with top of angle to be at FFL
checkpoint | Apply 1st coat of Polybit Hydraguard PU on floors with a turnup of 100mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
checkpoint | The WPM must be terminated at the specified height outlined in the wind classification report, also the WPM must be employ at the water stop angles for doors and wondow (if Applicable)
label | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydraguard PU on floors with a turnup of 100mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
checkpoint | The WPM must be terminated at the specified height outlined in the wind classification report, also the WPM must be employ at the water stop angles for doors and wondow (if Applicable)
label | Attach relevant photos
checkpoint | Dry day for second coat (if required).
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
label | Attach relevant photos
checkpoint | Attatch photos for the drainage conduit.
label | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
label | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
label | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Internal Wet Area (Bathrooms & Laundries) Waterproofing
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
label | Attach relevant photos
button | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
button | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
button | Ensure no high points or crevices are in the substrate
button | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
label | Attach relevant photos
button | Ensure all floor wastes & pipes have been primed in accordance with manufacturer's recommendations
button | Shower Angles in correct position & level
button | Door Angle is in correct position & level
button | Door & Shower Angle are 3mm guage aluminium
button | Ensure humidity, temperature & moisture are in accordance with manufactuer's recommendations
checkpoint | Primer substrate (walls and floors) with Polybit Hydrapoxy - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Apply angles to builders FFL as required.
label | Attach relevant photos
checkpoint | Seal all joints and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydraguard PU on floors with a turnup of 250mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
label | All floor wastes membranes to be turned down into floor waste
checkpoint | Waterproof walls of shower section up to ceiling. Seal taps & the like. 2x coats required.
button | Min 150mm kicker has been waterproofed (do width of roller 230mm)
button | Min 1500mm past shower screen has been waterproofed.
button | Waterproof all shower & adjacent walls
button | Ensure humidity, temperature & moisture are in accordance with manufactuer's recommendations
label | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydraguard PU on floors with a turnup of 250mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Dry day for second coat (if required).
label | Attach relevant photos
checkpoint | Apply 2 coats of Polybit Hybrid 150 waterbased polyurethane membrane on walls as required. - Apply selected membrane at a rate of 1.0 litres/m2 per coat as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
label | Attach relevant photos
checkpoint | Conduct a flood test to internal wet area.
label | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
label | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
label | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Roof, Terraces & Walkways Waterproofing
checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
label | Attach relevant photos
checkpoint | WP details listed at architectural drawings for clarifications are followed.
checkpoint | All floor should be with proper falls towards the floor waste with a min. 1:100 slope.
label | Attach relevant photos
checkpoint | WPM must be applied around the linear drains (grated drains) before adding the leveling screed.
label | Attach relevant photos
button | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
button | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
button | Ensure no high points or crevices are in the substrate
button | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Primer substrate with Polybit Hydrapoxy or PU primer - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydraguard PU on floors with a turnup up and over external hobs. - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydraguard PU on floors with a turnup up and over external hobs - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Dry day for second coat (if required).
label | Attach relevant photos
checkpoint | Apply PolyGuard protective UV top coat. - Apply selected top coat at a rate of 0.2-0.6 kg/m2 in one or two coats, depending on traffic conditions as per datasheet & application guidelines
checkpoint | the WPM must be terminated at the specified height outlined in the wind classification report Via saw cut reglet or other WPM termination method specified at AS 4654.2, or can be overlap by approved elastomeric weather-resist coating by min. 150mm.
label | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
label | Attach relevant photos
checkpoint | Attatch photos for the drainage conduit.
label | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
label | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
label | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Garbage Chutes Waterproofing
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
label | Attach relevant photos
button | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
button | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
button | Ensure no high points or crevices are in the substrate
button | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Primer substrate (walls and floors) with Polybit Hydrapoxy - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Apply angles to builders FFL as required.
label | Attach relevant photos
checkpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydraguard PU on floors with a turnup of 250mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydraguard PU on floors with a turnup of 250mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Dry day for second coat (if required).
label | Attach relevant photos
checkpoint | Apply 2 coats of Polybit Hybrid 150 waterbased polyurethane membrane on walls as required. - Apply selected membrane at a rate of 1.0 litres/m2 per coat as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
label | Attach relevant photos
checkpoint | Conduct a flood test to garbage chute area.
label | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
label | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
label | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Garbage Rooms Waterproofing
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
label | Attach relevant photos
button | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
button | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
button | Ensure no high points or crevices are in the substrate
button | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply 1st coat of Duromix Hibuild WBE epoxy primer to walls and floors - Apply selected primer at a rate of 1.5m2/L as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Apply 2nd coat of Duromix Hibuild WBE epoxy primer to walls and floors - Apply selected primer at a rate of 1.5m2/L as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Apply 1st coat of Duropoxy SLR100 epoxy top coat to walls and floors - Apply selected top coat a a rate of 6.6m2/L as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Apply 2nd coat of Duropoxy SLR100 epoxy top coat to walls and floors - Apply selected top coat a a rate of 6.6m2/L as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
label | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
label | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
label | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Planter Box Waterproofing
checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
label | Attach relevant photos
checkpoint | WP details listed at architectural drawings for clarifications are followed.
checkpoint | All floor should be with proper falls towards the floor waste with a min. 1:100 slope.
label | Attach relevant photos
button | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
button | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
button | Ensure no high points or crevices are in the substrate
button | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Primer substrate with Polybit Hydrapoxy - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydraguard AR100 on floors and walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydraguard AR100 on floors and walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Dry day for second coat (if required).
checkpoint | Attatch photos for the drainage conduit.
label | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
label | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
label | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Stormwater Tanks Waterproofing
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
label | Attach relevant photos
button | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
button | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
button | Ensure no high points or crevices are in the substrate
button | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Seal all joints and penetrations with Polybit HydraFlex FC polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Dampen the surface to ensure the highest level of adhesion as required
label | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
label | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
label | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
label | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Lift Pits Waterproofing
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
label | Attach relevant photos
button | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
button | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
button | Ensure no high points or crevices are in the substrate
button | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Dampen the surface to ensure the highest level of adhesion
label | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Inspect for any remaining leaks and treat with HydraPlug - Apply selected sealant as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
label | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
label | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
label | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Fire Sprinkler Tanks Waterproofing
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
label | Attach relevant photos
button | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
button | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
button | Ensure no high points or crevices are in the substrate
button | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Fatra Fatrafol 807 PVC membrane to be used. - Apply selected membrane as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Inspect for any remaining leaks and treat with HydraPlug - Apply selected sealant as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
label | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
label | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
label | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Internal wet areas
checkpoint | Area barricaded off to allow no access to internal wet areas with signs posted/ visible to include date of application, "No access waterproofing work in progress"
label | Attach relevant photos
button | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
button | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
button | Ensure no high points or crevices are in the substrate
button | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Primer substrate with Polybit Hydrapoxy/polyprime - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
checpoint | Install alluminium waterstops to door entries and showers as per builder's FFL.
label | Attach relevant photos
checpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydraguard on floors - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydraguard on floors - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Dry day for second coat (if required).
label | Apply Polybit Hybrid 150 to walls where required as per data sheet and application guidelines.
checkpoint | Flood test for a minimum of 24 hours.
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
label | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
label | HOLDPOINT - Once all above items have been signed off work may proceed
checkpoint
label
checklist | Stormwater Tanks Waterproofing
checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
label | Attach relevant photos
button | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
button | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system. | please remove
button | Ensure no high points or crevices are in the substrate
button | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Seal all joints and penetrations with Polybit HydraFlex FC polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Dampen the surface to ensure the highest level of adhesion as required
label | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
label | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
label | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
label | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Lift Pits Waterproofing
checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
label | Attach relevant photos
button | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
button | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
button | Ensure no high points or crevices are in the substrate
button | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Dampen the surface to ensure the highest level of adhesion
label | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Inspect for any remaining leaks and treat with HydraPlug - Apply selected sealant as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
label | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
label | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
label | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Fire Sprinkler Tanks Waterproofing
checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
label | Attach relevant photos
button | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
button | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
button | Ensure no high points or crevices are in the substrate
button | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Fatra Fatrafol 807 PVC membrane to be used. - Apply selected membrane as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Inspect for any remaining leaks and treat with HydraPlug - Apply selected sealant as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
label | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
label | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
label | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Hobs
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
label | Attach relevant photos
button | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
button | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Primer substrate with Polybit Hydrapoxy/polyprime - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
label | Attach relevant photos
checpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydraguard - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydraguard - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Dry day for second coat (if required).
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
label | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
label | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Waste/bin rooms | Hobs
checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
label | Attach relevant photos
button | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
button | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Primer substrate with Polybit Hydrapoxy- Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
label | Attach relevant photos
label | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydrapoxy flooring on floors and walls as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydrapoxy flooring on walls and floors - Apply selected membrane as per datasheet & application guidelines
label | Attach relevant photos
checkpoint | Dry day for second coat (if required).
label | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
label | HOLDPOINT - Once all above items have been signed off work may proceed