## Fill 14 ITP
Inspection and Test Plan Te Ara o Te Ata MMA-QA-ITP-Z07-EW-FL014 Fill 14 ITP
| This ITP has been prepared by |  |  | Reviewed by Quality Manager |  |  | Reviewed by DSR |  |  | Approved by Construction Manager
Rev # | Name | Signature | Date | Name | Signature | Date | Name | Signature | Date | Name |  | Signature |  | Date
Rev 01 | William McCracken |  | 2022-08-25
Rev 02 | William McCracken | WM | 2024-03-20 | Ramy Faragalla | R Faragalla | 2024-03-20 | Danny Beasant | D.Beasant | 2024-04-04 | Hardus Pieters |  |  |  | 2024-04-05
Rev 03 | William McCracken | WM | 2024-04-17 | Ramy Faragalla | R Faragalla | 2024-04-23 | Danny Beasant | D.Beasant | 2024-04-29 | Hardus Pieters |  |  |  | 2024-04-30
Rev 04
ITP NO: MMA-QA-ITP-Z07-EW-FL014 |  | Project: Te Ara o Te Ata | [5 empty] | Method Statement Ref:
Verification Method: Hold [H] – work will not proceed past Hold Point until released by organisation imposing hold; Inspection [I] – formal inspection activity to be undertaken and recorded; ensure correct verifying records are in place; Witness [W] – an inspection that may be witnessed by organisation imposing hold; allow reasonable notification period; Review [R] – review of reports, records or other evidence of compliance. | [7 empty] | Responsibilities PE = MTM Alliance Construction TWD = Temporary Design Team
Activity/Specification: Structural Fill | [7 empty] | Area Location / Work Breakdown: Zone 7 (Fill 14)
Item | Construction Step or Material |  | Specifications and Standards |  | Acceptance criteria and testing |  |  |  | Responsible |  |  |  | Verifying Records Checklists, Test and Supplier Certificates
[5 empty] | Method/ Description | Test frequency |  | Conformance Criteria | Contractor | Designer | Client | Lab
1.0 Pre-Construction
1.01 | CWP |  |  |  | Document Review | Prior to personal starting |  | Ensure all crew members are briefed on the CWP | H |  |  |  | Signed off CWP
1.03 | IFC's specification |  | MMA-GES-GEO-E1-SPC-3859 MMA-DES-GEO-E1-SPC-8804 |  | Document Review | Prior to works commencing |  | Obtain copy of the earthworks and Vertical Drains PVD specifications | H | H |  |  | IFC Technical Specifications
1.04 | IFC drawings |  | IFC drawings |  | Document Review | Prior to works commencing |  | Ensure all drawings are approved and of the latest revision, or written approval from PAB | H | H |  |  | IFC Drawings upload into InEight
1.05 | Approved earthworks model |  |  |  | Document Review | Every new Earthworks Model and prior to work commencing |  | Designer to confirm and approve models to be loaded on the equipment | H | H |  |  | Earthworks model approval
1.06 | Approval of stockpile location |  | MMA-DES-GEO-E1-SPC-3859 |  | Document Review & Approval | Prior to works commencing |  | Approved stockpile location | H | H |  |  | RFI of Approval of stockpile location
1.07 | Installation of prefabricated vertical drains sequence and method |  | MMA-DES-GEO-E1-SPC-8804 Clause 9 Table 2 & Table 3 |  | Document Review & Approval | At least 4 weeks prior to commencement of PVD installation |  | Design Lead Approval | H | H |  |  | CWP approval
1.08 | PVD sample |  | MMA-DES-GEO-E1-SPC-8804 Clause 9 Table 2 & Table 3 |  | Approval | At least 4 weeks prior to commencement of PVD installation |  | Design Lead Approval | H | H |  |  | PVD sample approval
2.0 Material Compliance
2.01 | Determination of the dry density/water content relationship (Heavy Compaction) for Structural Fill Material |  | MMA-DES-GEO-E1-SPC-3859 Table 4.2, 7.1 & 7.2 |  | NZS 4402:1986, Test 4.1.2 | 1 Per 20,000m3 (Structural Fill) |  | N/A | H | R |  | I | MDD Test Report
2.02 | Atterberg limits test for Structural Fill Material |  | MMA-DES-GEO-E1-SPC-3859 Table 4.2, 7.1 & 7.2 |  | NZS 4402:1986, Test 2.2, 2.3 & 2.4 | 2 Per 20,000m3 (Structural Fill) |  | N/A | H | R |  | I | Test Report
2.03 | Determination of the dry density/water content relationship (Heavy Compaction) for Buttress Fill Material |  | MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 & 7.2 |  | NZS 4402:1986, Test 4.1.2 | 1 test per 20,000m3 |  | Report Only | H | R |  | I | MDD Test Report
2.04 | Atterberg limits test for Buttress Fill Material |  | MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 & 7.2 |  | NZS 4402:1986, Test 2.2, 2.3 & 2.4 | 1 test per 20,000m3 |  | Report Only | H | H |  | I | Atterberg limits Test Report
2.05 | Drainage blanket |  | MMA-DES-GEO-E1-SPC-3859 Clause 4.7 |  | Designer Approval | Once Prior to commence |  | Defines graded, coarse fill used as a high permeability layer through which the Prefabricated Vertical Drains (PVDs) will be installed. It shall comprise either imported suitable material or site-won rock fill. | H | R |  |  | Material Compliance Certificate
2.06 | 40/20 drainage material |  | RFI-00068 |  | Designer Approval | Once Prior to commence |  | Test reports | H | R |  |  | Material Compliance Certificate
2.07 | High Strength Geo Cloth |  | MMA-DES-GEO-E1-SPC-3859 Clause 4.17 |  | Designer Approval | Once Prior to commence |  | Use the Specific high strength Geotextiles as per IFC Drawings, RFI to be submitted to designers for use of alternative | H | R |  |  | Material Compliance Certificate
2.08 | Determination of the dry density/water content relationship (Heavy Compaction) GAP 65 Material |  | MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 & 7.2 |  | NZS 4402:1986, Test 4.1.2 | Source approval 3 no. tests |  | Report Only | H | R |  | I | MDD Test Report
2.09 | Particle size distribution (PSD) Test for GAP 65 material |  | MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 & 7.2 |  | NZS 4402:1986, Test 2.8 | Source approval 3 no. tests then every 2000m3. |  |  | H | H |  | I | PSD Test Report
2.1 | Permeability test for GAP 65 material |  | MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 & 7.2 |  | ASTM D5084 - 16a | Source approval 3 no. tests |  | > 5x10-5 m/s | H | H |  | I | Permeability Test Report
2.11 | Material approval of prefabricated vertical drains (PVD). The PVDs shall consist of a continuous plastic drainage core wrapped in a non-woven geotextile material. The geotextile wrap shall be tight around the core and shall be securely seamed in a manner that will not introduce any new materials nor present an obstruction that will impede flow in the channels of the core. PVDs shall be produced by a manufacturer with an in-place quality control program which is monitored by an independent third party testing organization. |  | MMA-DES-GEO-E1-SPC-8804 Clause 5 |  | Document Review & Approval | At least 4 weeks prior to commencement of PVD installation |  |  | H | H |  |  | Material approval, Material test certificates
2.12 | Delivery of prefabricated vertical drains (PVD) |  | MMA-DES-GEO-E1-SPC-8804 Clause 4.3 |  | Inspection | Each delivery |  | The Constructor shall check and record all materials upon delivery to assure that the proper type, grade, colour and certification have been received and has been stored and labelled such that there is no ambiguity as to the provenance and material specification of any individual roll. | H | R |  |  | • Product name and identification • Date of manufacture • Lot or control numbers • Name and address of producer/supplier • Manufacturer’s certificate • Material Delivery Inspection Checklist
2.13 | Visual inspection - separation geotextiles, basal reinforcement |  | MMA-DES-GEO-E1-SPC-3859 |  | To inspect geotextile and basal reinforcement is the proper type and no tears, rips or other signs of deterioration. | Check each lot (1 roll) |  | Report Only | H | H |  |  | Material Delivery Inspection Checklist
3.0 During Construction
3.1 Pre-filling
3.1.1 | The installation trail of prefabricated vertical drains (PVD) shall be conducted. |  | MMA-DES-GEO-E1-SPC-8804 Clause 7 |  | Inspection | Prior to Commencement |  | The trial of PVD installation should demonstrate satisfaction (e.g., ensuring that the design depths of PVDs are reached and that the anchorage system is suitable for the encountered soil type)." | H | H |  |  | PVD installation trial approval
3.1.2 | Set out extents of fill and check against design |  |  |  | Survey/visual | Prior to Commencement |  | Consistency with Construction Drawings | W
3.1.3 | Ensure GPS plant have the correct model set up in machine and that a datum is available for checking |  |  |  | Survey/visual | Prior to Commencement |  | Consistency with Construction Drawings | W
3.1.4 | Ensure the complete removal of all organics, topsoil, Vegetation, and roots. The depth of topsoil stripping should be adequate to eliminate all organic material, turf, and significant plant roots. |  | MMA-DES-GEO-E1-SPC-3859 Clause 6.3 |  | Survey/visual | Immediately prior to earthworks beginning in all Fill areas |  | Construction team shall coordinate with the Designer ahead of and during clearing and stripping operations to determine the stripping depth. | H | H |  |  | Daily Site Report by Design Lead
3.1.5 | Designer witness of in-situ subgrade prior to filling |  | MMA-DES-GEO-E1-SPC-3859 Clause 7.2 |  | Inspection | 100% subgrade inspection |  | Before fill is placed in any area, the Constructor shall notify the Designer that the fill foundation has been stripped and drained, including construction of subsoil drains and prepared as required by the Drawings and Specification, and is ready for the Designer’s inspection and approval. | H | H |  |  | Daily Site Report by Design Site Representative
3.1.6 | Undercuts Inspection |  | MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3 |  | Visual inspection | 100% of works area |  | • Where shown on the drawings. • The Designer will specify the depth of the undercut in materials. • The Constructor shall treat any excavated undercut material as landscape fill or unsuitable. • Backfill the undercut as per the designer's instruction. | H | H |  |  | Daily Site Report by Design Site Representative
3.1.7 | When required Undercuts (cut-to-fill operations) |  | MMA-DES-GEO-E1-SPC-3859 Clauses 6.7 & 6.8 |  | Visual inspection | Prior to Filling |  | Unsuitable material shall be undercut and tested as per specification or designers instruction | H | H |  |  | Daily Site Report by Design Site Representative
3.1.8 | Piles |  | Separate ITP for Fill 14 Bored Piles ITP # MMA-QA-ITP-Z07-EW-GE006 |  | Inspection | Ongoing |  | Signed ITP | W | R |  |  | Separate Signed ITP
3.1.9 | Installation of prefabricated vertical drains (PVD) PVDs shall be installed after the sand blanket is placed and before the installation of high strength geotextile (basal reinforcement) and the embankment fill. The proposed locations of the PVDs shall be marked out in accordance with the Drawings. |  | MMA-DES-GEO-E1-SPC-8804 Clause 7 |  | Inspection | Each installation of vertical drains |  | Installation tolerances: • 150 mm from the intended location • Verticality: 1 in 50 | I | I |  |  | Vertical drains Installation Checklist
3.1.10 | Basal reinforcement installation |  | IFC drawings and MMA-DES-GEO-E1-SPC-3859 |  | Visual inspection of directional placement, panel length, laps, and damage | During basal reinforcement installation and every 100m² of geotextile installed. |  | Ensure geotextile used is the correct type, and directional placement, tensioning, laps, and spacing are correct | H | H
3.1.11 | Drainage blanket installation |  | IFC drawings and MMA-DES-GEO-E1-SPC-3859 |  | Visual inspection | Prior to filling, and every 100m2 of geotextile installed. |  | Ensure drainage blanket has the correct thickness, geotextile type and laps are correct | H | H
3.1.12 | Monitoring Instrumentation |  | All monitoring requirements will be covered by a separate ITP. |  | Survey/ data logging | Ongoing |  | Signed ITP | W | R |  |  | Separate Signed ITP
3.2 Fill construction
3.2.1 | Filling for the first 5m of Fill |  | MMA-DES-GEO-E1-SPC-3859 Clause 7.2 IFC Drawings |  | Visual inspection | Daily |  | Check embankment slopes for location should be placed against sloping surfaces steeper than 1V:3H. The sloping surface shall be excavated or "benched" so that horizontal benches at no greater than 1.0-meter height intervals are formed. Line and level the benches as the fill progresses, ensuring that batter faces are overfilled and trimmed back so that the fill is well compacted to the edge. | H |  |  |  | As-Built Survey Report/ UAV Scan
3.2.2 | Hold filling operations for a period of two months |  | MMA-DES-GEO-E1-SPC-3859 Clause 7.2 IFC Drawings |  | Monitoring data records | Daily |  | Review of instrumentation data readings. | H | H |  |  | Monitoring data records
3.2.3 | Filling for an additional 3 meters of fill |  | MMA-DES-GEO-E1-SPC-3859 Clause 7.2 IFC Drawings |  | Visual inspection | Daily |  | Check embankment slopes for location should be placed against sloping surfaces steeper than 1V:3H. The sloping surface shall be excavated or "benched" so that horizontal benches at no greater than 1.0-meter height intervals are formed. Line and level the benches as the fill progresses, ensuring that batter faces are overfilled and trimmed back so that the fill is well compacted to the edge. | H |  |  |  | As-Built Survey Report/ UAV Scan
3.2.4 | Hold filling operations for a period of three months |  | MMA-DES-GEO-E1-SPC-3859 Clause 7.2 IFC Drawings |  | Monitoring data records | Daily |  | Review of instrumentation data readings. | H | H |  |  | Monitoring data records
3.2.5 | Final Filling for an additional 2 meters of fill including Surcharge Fill |  | MMA-DES-GEO-E1-SPC-3859 Clause 7.2 IFC Drawings |  | Visual inspection | Daily |  | Check embankment slopes for location should be placed against sloping surfaces steeper than 1V:3H. The sloping surface shall be excavated or "benched" so that horizontal benches at no greater than 1.0-meter height intervals are formed. Line and level the benches as the fill progresses, ensuring that batter faces are overfilled and trimmed back so that the fill is well compacted to the edge. The final fill surface shall be trimmed back to match the required design profile. | H |  |  |  | As-Built Survey Report
3.2.6 | Final Hold filling operations for a period of four months |  | MMA-DES-GEO-E1-SPC-3859 Clause 7.2 IFC Drawings |  | Monitoring data records | Daily |  | Review of instrumentation data readings. | H | H |  |  | Monitoring data records
3.2.7 | insitu fill testing-Plateau Test |  | MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3 |  | Plateau Test | Structural Fill - 1 test per material type per earthworks zone, except where outlined in RFI0057 Buttress Fill - 1 test per material type per earthworks zone GAP65 - 1 test per material type per structure / location Cement Stabilised GAP65/ Structural Fill - 1 Test per material type per structure/ location |  | Reviewed by designer | W | R |  | I | Test report
3.2.8 | insitu fill testing-In situ moisture content and density |  | MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3 |  | In situ moisture content and density | Structural Fill - 1 test per 1 m lift per 100m length, Heavy compaction and standard compaction areas outlined in RFI00057 Buttress fill - 1 test per 200m length Average GAP65 - 4 tests per lift per structure Subsoil Drainage Back fill - 1 test per 500m3 , Cement Stabilised GAP65 - 4 Tests per 0.5m lift per structure Cement Stabilised Structural fill - 1 test per 0.5m lift per 100m length |  | Structural Fill - average > 95% MDD All tests > 92%, Buttress fill - Average > 92 MDD All tests > 90%, GAP65 - Average > 98% MDD All tests > 95%, Subsoil Drainage Back fill - 1 Average > 92 MDD All tests > 90%, Cement Stabilised GAP65 - Average > 98% MDD All tests > 95%, Cement Stabilised Structural fill - average > 95% MDD All tests > 92% | W | R |  | I | Test report
3.2.9 | insitu fill testing- Undrained shear Strength |  | MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3 |  | Undrained shear Strength | Structural fill - 1 test per layer per 1000m2 Buttress Fill - 1 Test per layer per 2000m2 Cement Stabilised Structural Fill - 1 test per layer per 500m2 | Structural fill - 1 test per layer per 1000m2 Average > 150kPa all tests > 120kPa Buttress Fill - 1 Test per layer per 2000m2 Average > 120kPa all tests > 80kPa Cement Stabilised Structural Fill - 1 test per layer per 500m2 Average > 150kPa all tests > 120kPa | Structural fill - Average > 150kPa all tests > 120kPa Buttress Fill - Average > 120kPa all tests > 80kPa Cement Stabilised Structural Fill - Average > 150kPa all tests > 120kPa | W | R |  | I | test report
3.2.10 | Scala Penetrometer Surcharged Fills |  | MMA-DES-GEO-E1-SPC-3859 Clause 10.5 |  | Scala Penetrometer Surcharged Fills | 435mm above Subgrade formation level to 1.5m depth. 3 tests per 20m chainage evenly across formation pavement width |  |  | W | R |  | I | Scala Test results
3.2.11 | In-situ moisture content and density (and/ or air voids) testing of compacted for fill material Subgrade |  | MMA-DES-GEO-E1-SPC-3859 Clause 10.5 |  | in situ moisture content and density (and/ or air voids) testing of compacted fill material | Surcharged Fills - 1 test at subgrade formation level per 50m length, Cut Fill Transitions - 1 Test per 0.5m lift per 50m length for 1.0m subgrade depth |  | Average > 95% MDD All tests > 92% MDD | W | R |  | I | NDM Test results
3.2.12 | Carry out deflection testing (either Benkelman Beam or FWD) at the subgrade |  | MMA-DES-GEO-E1-SPC-3859 Clause 10.4 & 10.5 |  | Benkelman beam or FWD Testing | Surcharged Fills - At subgrade formation level 10m interval in each wheel path Cut Fill Transitions - at three heights: 1.0m, 0.5m and 0m below subgrade formation level 10m interval in each wheel path |  | Benkelman beam, 90th percentile D0 target :1.2mm No D0 deflection exceeding 1.40mm. FWD, 90th percentile D0 target:2.0mm No D0 deflection exceeding 2.2mm | W | R |  | I | Benkelman Beam or FWD Test results
3.2.13 | Laboratory Soaked CBR testing for Subgrade Fill |  | MMA-DES-GEO-E1-SPC-3859 Clause 10.5 |  | Laboratory Soaked CBR | Test per 5000m2 at subgrade formation level |  | ≥ CBR 7% | W | R |  | I | Laboratory Soaked CBR Test results
3.3 Preload/Surcharge (for embankments requiring preload)
3.3.1 | Visual inspection for rate of filling |  | IFC drawings and MMA-DES-GEO-E1-SPC-3859 |  | Inspection of fill height, rate of filling as per IFC drawing | To be monitored daily |  | Ensure maximum rate of filling is adhered to | H | W |  |  | PVD installation trial approval
3.3.2 | After 1m of fill placement. Await approval from Designer before placing more fill. |  | Instrumentation spec MMA-DES-GEO-E1-SPC-8510 Trigger action response plan Doc. MMA-DES-GEO-E1-ITP-31384 |  | Review data and TARP levels before releasing HOLD. | Before releasing hold periods and allowing filling to continue. |  | In accordance with design | H | H |  |  | Designer site diary
3.3.3 | Removal of preload/surcharge |  | IFC drawings and ground instrumentation plan |  | Assessment of monitoring and instrumentation data | After completion of proposed hold period |  | Hold period of preload or surcharge should not be released until monitoring data has been reviewed and confirmed by Designer. | H | H
3.3.4 | Removal of preload/surcharge |  | IFC drawings and ground instrumentation plan |  | Preparation of preload/surcharge report | Every four weeks during earthworks operations and at the end and commencement of each earthworks season |  | Acceptance of report | H
4.0 Post Construction
4.01 | Survey As-builts |  |  |  | Survey As-built | During construction and at end |  | Ensure all features and buried items are captured. | H |  |  |  | CAD files
4.02 | As-builts |  |  |  | Red Pen Mark up | End of Construction |  | All variances captured | H | H |  |  | Red pen mark ups