## zres_siteapp
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP-014 - Fill 14 Rev 3 | itp |  |  |  | Yes | ITP-014 - Fill 14 Rev 3 | 4c6f4dd4-7e6b-43b4-8142-d2c861e040ad
checkpoint-group |  |  | section | 1.0 Pre-Construction
checkpoint-status |  |  | checkpoint | 1.01 - CWP
label | e089dd61-1536-5853-b386-da5ac012a822 |  | note | Method/Description - Document Review
label | 39acd8e3-3204-52a1-8063-8a84de727505 |  | note | Test frequency - Prior to personal starting
label | fb74a4ec-b970-5a82-9438-0371ff2c4f60 |  | note | Contractor - H
label | 24e19b5d-b714-51a0-871e-2fc4077a520b |  | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
checkpoint-status |  |  | checkpoint | 1.03 - IFC's specification
label | 4257e64a-85d4-58d9-ac5c-ff666a5cfb32 |  | note | Method/Description - Document Review
label | 5230702f-d278-5658-a1d3-b49fa06541f8 |  | note | Test frequency - Prior to works commencing
label | 7f1cfa8a-1324-5bbe-8e81-b61f3faa9861 |  | note | Contractor - H
label | 29646630-3fb9-533d-b171-9e4cf8f44811 |  | note | Designer - H
label | a31745d4-ff53-5865-bb8f-f5113a7501f3 |  | note | Verifying Records Checklists, Test and Supplier Certificates - IFC Technical Specifications
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.04 - IFC drawings
label | 306054e1-5f7e-5a9e-9293-a2d5c4f460ea |  | note | Method/Description - Document Review
label | 9fef44a4-1c56-50e4-bd9c-758c6a3e91de |  | note | Test frequency - Prior to works commencing
label | ede6e919-9c31-590b-a63f-de014264a326 |  | note | Contractor - H
label | 17e771b9-78be-537c-9d0f-a2ce791868cf |  | note | Designer - H
label | 815c58e5-413d-52ba-841c-7c25c85b51cc |  | note | Verifying Records Checklists, Test and Supplier Certificates - IFC Drawings upload into InEight
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.05 - Approved earthworks model
label | 01ed7ab8-e726-5289-baf1-a02abb6ed932 |  | note | Method/Description - Document Review
label | 14c5379d-7ee1-5304-9c5b-3f018a80d31d |  | note | Test frequency - Every new Earthworks Model and prior to work commencing
label | dbbf0570-b9dd-5c71-832a-19a7885904a3 |  | note | Contractor - H
label | 36c8e97f-e357-50b5-b7a8-7c1a3cc5021a |  | note | Designer - H
label | 20908a2c-eb88-5181-b450-52efe7c43b5a |  | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks model approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.06 - Approval of stockpile location
label | 9b76d029-9a17-5010-a234-f64302f8b71f |  | note | Method/Description - Document Review & Approval
label | 197af4fe-a59b-500d-8df5-16c49792cc02 |  | note | Test frequency - Prior to works commencing
label | ca87598a-5c60-504a-b9b2-2a1df578b983 |  | note | Contractor - H
label | cd0c588b-b973-51b0-a4b7-2e2e82094b69 |  | note | Designer - H
label | 170dea46-b59b-5c8f-8531-5e621947838d |  | note | Verifying Records Checklists, Test and Supplier Certificates - RFI of Approval of stockpile location
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.07 - Installation of prefabricated vertical drains sequence and method
label | 85400be2-a428-5805-98bc-800258186bf2 |  | note | Method/Description - Document Review & Approval
label | 8c3e6ade-519a-5f6a-a625-19f8909ed9ab |  | note | Test frequency - At least 4 weeks prior to commencement of PVD installation
label | 847212ec-70ca-50f2-9431-e056b4149ae6 |  | note | Contractor - H
label | 4aae23c8-b4ce-5f8a-bfcf-369ed9d8b142 |  | note | Designer - H
label | 1dc449ba-d1b8-5c9f-82b2-fd308a2413d4 |  | note | Verifying Records Checklists, Test and Supplier Certificates - CWP approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.08 - PVD sample
label | 0eee56b4-55ac-5546-b040-654ba8683847 |  | note | Method/Description - Approval
label | 80081bcd-1079-5c4a-8387-329e87e5628a |  | note | Test frequency - At least 4 weeks prior to commencement of PVD installation
label | c611e8e2-079a-55d5-988e-8cd0d0803aa6 |  | note | Contractor - H
label | a7cf3122-eea5-5164-aabe-66226997eb8a |  | note | Designer - H
label | 638c7a7f-872e-50ac-a2d3-e8032f4695e4 |  | note | Verifying Records Checklists, Test and Supplier Certificates - PVD sample approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.0 Material Compliance
checkpoint-status |  |  | checkpoint | 2.01 - Determination of the dry density/water content relationship (Heavy Compaction) for Structural Fill Material
label | fe3d3893-9b75-5b64-a04e-1d86acb4c29b |  | note | Method/Description - NZS 4402:1986, Test 4.1.2
label | 3495b883-135d-5188-a0d3-d10d9d52de1d |  | note | Test frequency - 1 Per 20,000m3 (Structural Fill)
label | 67342cb9-e379-5628-a679-ce5a8db057c2 |  | note | Contractor - H
label | a28c4d46-5800-5e2f-874f-026ddf166bf7 |  | note | Designer - R
label | 43f46eb8-2a53-5e14-bb91-3c6e4f968bc8 |  | note | Lab - I
label | 08e9d96a-e0bb-5542-8746-18d30c8a2f2d |  | note | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
checkpoint-status |  |  | checkpoint | 2.02 - Atterberg limits test for Structural Fill Material
label | 8efac5e3-3f65-5738-b1ef-ec1292709d9b |  | note | Method/Description - NZS 4402:1986, Test 2.2, 2.3 & 2.4
label | 69535725-4c0e-5f33-8524-84264d367b24 |  | note | Test frequency - 2 Per 20,000m3 (Structural Fill)
label | a7c3cdf6-e207-5b7c-94c0-021fa86c896c |  | note | Contractor - H
label | 589c06d6-31ed-5107-8627-2f07da1e5e18 |  | note | Designer - R
label | 5a220030-7b33-59f4-a579-fbbdf4a7dcc2 |  | note | Lab - I
label | 0ffef775-f465-53b4-a18c-cb1c8b8f6766 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint-status |  |  | checkpoint | 2.03 - Determination of the dry density/water content relationship (Heavy Compaction) for Buttress Fill Material
label | 69d19818-b469-529b-9ef7-aff4c821fe86 |  | note | Method/Description - NZS 4402:1986, Test 4.1.2
label | b785a442-961b-5b94-8af8-151734794fbd |  | note | Test frequency - 1 test per 20,000m3
label | 9dc921ba-1c25-579d-91bb-dc10a63c0afb |  | note | Contractor - H
label | 8c71261a-99b2-5147-b6ef-5ae27e292320 |  | note | Designer - R
label | 84d35f5f-7d9c-5a6e-8f30-54288b08faf8 |  | note | Lab - I
label | 7a182bf3-cccc-5a7c-8f91-8121237d9a3c |  | note | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
checkpoint-status |  |  | checkpoint | 2.04 - Atterberg limits test for Buttress Fill Material
label | c59817c9-50be-57fa-8a32-5c7c76032d5e |  | note | Method/Description - NZS 4402:1986, Test 2.2, 2.3 & 2.4
label | 76ac39ed-9b7a-59a0-b5ac-3bb48e1f216e |  | note | Test frequency - 1 test per 20,000m3
label | 6933c107-6455-5372-9895-8562ca47e33a |  | note | Contractor - H
label | 75fb34ac-acdf-5390-bec7-ea6b8ccb8b3e |  | note | Designer - H
label | b84d75df-09d6-5625-82b4-5dcc25d460ea |  | note | Lab - I
label | bf3fd3b6-0a3a-54e8-82d2-93b93a3b84bb |  | note | Verifying Records Checklists, Test and Supplier Certificates - Atterberg limits Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.05 - Drainage blanket
label | 5f61ab54-103f-57e4-b3d5-36ed0ad1c60e |  | note | Method/Description - Designer Approval
label | 05a674f2-7e45-5ea9-bc15-ba0ac76a05cf |  | note | Test frequency - Once Prior to commence
label | decef77c-f13e-5384-af72-010f0e562add |  | note | Contractor - H
label | 550c5d7f-12c3-57f0-8220-b741f2afe396 |  | note | Designer - R
label | eed25f06-ee66-51fe-8fcd-4c2230e42877 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Compliance Certificate
checkpoint-status |  |  | checkpoint | 2.06 - 40/20 drainage material
label | 2aad36c5-3178-5d0c-b563-cea580cd6ca9 |  | note | Method/Description - Designer Approval
label | 1bb11428-cc48-5cb8-9500-5416e5d302a9 |  | note | Test frequency - Once Prior to commence
label | 70f7244d-d97b-57fa-ba1f-11ca991144e6 |  | note | Contractor - H
label | 93dcab24-a726-5715-a574-d685ab37c873 |  | note | Designer - R
label | 69f55381-5238-5045-8214-2b52b33454b8 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Compliance Certificate
checkpoint-status |  |  | checkpoint | 2.07 - High Strength Geo Cloth
label | cc42d98a-b6e1-545c-a3e8-a8f0711fb4d7 |  | note | Method/Description - Designer Approval
label | ba53d346-cff1-5f5f-9c68-4435402ee6e1 |  | note | Test frequency - Once Prior to commence
label | 1811fe65-9427-59db-889b-58dc829be190 |  | note | Contractor - H
label | d39fbbec-30d7-5c3f-8345-7aca5985147a |  | note | Designer - R
label | de6d87a0-7015-588a-ae4a-9848e89f27f4 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Compliance Certificate
checkpoint-status |  |  | checkpoint | 2.08 - Determination of the dry density/water content relationship (Heavy Compaction) GAP 65 Material
label | 4fe0414f-4239-55ef-a22c-522af0dbe57a |  | note | Method/Description - NZS 4402:1986, Test 4.1.2
label | 9af2b779-18d4-5639-b763-35fc911342e9 |  | note | Test frequency - Source approval 3 no. tests
label | 84bc0c4c-e53d-5bdd-8ea2-8e0f713d599f |  | note | Contractor - H
label | be7c19d5-d59b-577a-b17e-1340b30702ae |  | note | Designer - R
label | 92b1ceab-f0f3-5745-9dd7-568ee317fc8f |  | note | Lab - I
label | ed72e9b7-06b2-5fef-8081-5fd20bbf7445 |  | note | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
checkpoint-status |  |  | checkpoint | 2.09 - Particle size distribution (PSD) Test for GAP 65 material
label | 6df844d5-c6e5-5b50-bc97-f066190d8d5f |  | note | Method/Description - NZS 4402:1986, Test 2.8
label | 2024b29f-6e6e-5046-a5b1-d068b202c155 |  | note | Test frequency - Source approval 3 no. tests then every 2000m3.
label | 81dd4ea6-c9f3-535b-b8a4-e25de9ca5bc7 |  | note | Contractor - H
label | da3423e1-4912-559a-a70a-22c67be079e6 |  | note | Designer - H
label | 34e401da-14b0-5355-909b-1fab55def249 |  | note | Lab - I
label | ffc35911-fefb-5f3c-81d9-9f1138519e2a |  | note | Verifying Records Checklists, Test and Supplier Certificates - PSD Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.10 - Permeability test for GAP 65 material
label | abb288ed-94c4-565a-bcbe-80a7a9498f05 |  | note | Method/Description - ASTM D5084 - 16a
label | 667c33d2-16ea-59ad-b248-0140ab162dae |  | note | Test frequency - Source approval 3 no. tests
label | 8a353e9d-0b0c-5277-bc4c-19a6ae765ccd |  | note | Contractor - H
label | 3461238d-3066-5158-86e0-f70bf1338b73 |  | note | Designer - H
label | e5afa4ec-f602-5c85-b1f6-4e9dc54888f5 |  | note | Lab - I
label | ccbdcac9-77d7-502c-b0c6-8af78eb7f154 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Permeability Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.11 - Material approval of prefabricated vertical drains (PVD). The PVDs shall consist of a continuous plastic drainage core wrapped in a non-woven geotextile material. The geotextile wrap shall be tight around the core and shall be securely seamed in a manner that will not introduce any new materials nor present an obstruction that will impede flow in the channels of the core. PVDs shall be produced by a manufacturer with an in-place quality control program which is monitored by an independent third party testing organization.
label | 3e8c1bb0-c1ab-5fb5-89b8-3ef7172e6251 |  | note | Method/Description - Document Review & Approval
label | fd487ad6-02d2-5418-bd50-438713622a49 |  | note | Test frequency - At least 4 weeks prior to commencement of PVD installation
label | 22746887-54ff-51c8-82f9-880c730c907a |  | note | Contractor - H
label | e094b828-fa6e-514d-9556-53061f6e13e2 |  | note | Designer - H
label | 983be9dc-0e75-51d3-9080-11838c3f6709 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material approval, Material test certificates
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.12 - Delivery of prefabricated vertical drains (PVD)
label | c4d0f25b-c01c-55f0-ac5d-da60e709be1c |  | note | Method/Description - Inspection
label | e91f0f77-e1e1-5a3e-b754-e0fd3b4c509c |  | note | Test frequency - Each delivery
label | 37198f97-9691-5687-98f1-5de475b20e13 |  | note | Contractor - H
label | d3b190cb-bdc8-58a7-94dc-e8757bfd86a6 |  | note | Designer - R
label | def2bcb4-5b54-58c2-bd1e-b67895b50ca0 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Product name and identification
label | 69194214-b8dd-5492-a6fd-adf96ae38b13 |  | note | ○ Date of manufacture
label | 39120593-16c7-526d-a9c0-756e3d8a250e |  | note | ○ Lot or control numbers
label | b68aedef-2480-53fc-a83c-ba6abb04e1da |  | note | ○ Name and address of producer/supplier
label | 210d1a1d-b0d4-511c-9de2-9ca121ad46ab |  | note | ○ Manufacturer’s certificate
label | 202807af-e5b8-5897-89f7-974afbafb89a |  | note | ○ Material Delivery Inspection Checklist
checkpoint-status |  |  | checkpoint | 2.13 - Visual inspection - separation geotextiles, basal reinforcement
label | 1bd88497-d9fb-5902-84bb-cfdc5803aee2 |  | note | Method/Description - To inspect geotextile and basal reinforcement is the proper type and no tears, rips or other signs of deterioration.
label | 71eb19da-0af6-507b-98b1-2e074189508e |  | note | Test frequency - Check each lot (1 roll)
label | d2cc6a8e-ea17-5dd1-81ee-362bb5e76a6d |  | note | Contractor - H
label | e39e4363-a496-551a-9b40-bb8b6c8098b8 |  | note | Designer - H
label | 3ab53a30-a262-5f5d-99ad-0793e7430328 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Delivery Inspection Checklist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.1 Pre-filling
checkpoint-status |  |  | checkpoint | 3.1.1 - The installation trail of prefabricated vertical drains (PVD) shall be conducted.
label | 97f9bb0b-efa0-5e7e-9a39-524fca722d8e |  | note | Method/Description - Inspection
label | e775fc77-3d94-5aba-bd13-e6f88a90f925 |  | note | Test frequency - Prior to Commencement
label | 1661fe29-029e-5561-bc4e-c6cbcc706096 |  | note | Contractor - H
label | e6cebe15-0755-5252-bb65-539748cf44ec |  | note | Designer - H
label | 6dcf5206-64ff-5c45-bdad-5893da52433e |  | note | Verifying Records Checklists, Test and Supplier Certificates - PVD installation trial approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.2 - Set out extents of fill and check against design
label | 25cac1dc-aace-5742-9749-f1f60709f72b |  | note | Method/Description - Survey/visual
label | 325250a9-1fea-53ba-a6fd-3f9cc2992dcb |  | note | Test frequency - Prior to Commencement
label | 3e4fec7a-f0c0-5fef-84b4-d44b36b4a27c |  | note | Contractor - W
label | c69a12d2-db03-5683-9bc5-9bc4c008074f |  | note | Verifying Records Checklists, Test and Supplier Certificates -
checkpoint-status |  |  | checkpoint | 3.1.3 - Ensure GPS plant have the correct model set up in machine and that a datum is available for checking
label | 361d3fcd-5761-5969-b127-8f78ac70eec6 |  | note | Method/Description - Survey/visual
label | 32a28ac9-03ff-5114-a365-62d5b468379f |  | note | Test frequency - Prior to Commencement
label | 94fb3fe3-284e-5f1f-b1b3-c7a605682912 |  | note | Contractor - W
label | 19deee23-2985-533c-91d5-1b2ba15f919a |  | note | Verifying Records Checklists, Test and Supplier Certificates -
checkpoint-status |  |  | checkpoint | 3.1.4 - Ensure the complete removal of all organics, topsoil, Vegetation, and roots. The depth of topsoil stripping should be adequate to eliminate all organic material, turf, and significant plant roots.
label | 1a348236-b66a-5bd4-8e38-49fb771503d0 |  | note | Method/Description - Survey/visual
label | dd07b0db-1b64-5554-996c-13f88aeb70ce |  | note | Test frequency - Immediately prior to earthworks beginning in all Fill areas
label | 4cefef70-d70b-5f2f-bd0a-9dd8aaf9a7af |  | note | Contractor - H
label | 434a115a-1bb4-50fa-b482-55f18e55ab9e |  | note | Designer - H
label | 2300c56a-cfa5-5688-8427-01c065d552f5 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Daily Site Report by Design Lead
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.5 - Designer witness of in-situ subgrade prior to filling
label | bd8a8c5f-6389-5d13-8c98-1be5295a12aa |  | note | Method/Description - Inspection
label | 33e3c142-ebd8-576e-b307-69c7f771e120 |  | note | Test frequency - 100% subgrade inspection
label | 79406ac8-c103-5021-a391-bcd811ea7178 |  | note | Contractor - H
label | 9706c16a-b806-557f-b718-5a5485afc829 |  | note | Designer - H
label | 1c2b0ef5-892e-57c8-bcdd-b0cb4f179983 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Daily Site Report by Design Site Representative
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.6 - Undercuts Inspection
label | 1c92114b-c3a2-5ff5-bf14-380ce17efb4e |  | note | Method/Description - Visual inspection
label | 8cc3f98a-7992-5c34-a970-aa9b90fd9d6c |  | note | Test frequency - 100% of works area
label | 9d38d27f-ca7d-590b-8db5-af470db6d917 |  | note | Contractor - H
label | 80624815-64ab-54b6-b308-94b8f8f55539 |  | note | Designer - H
label | dba31996-79a8-5d7d-bd7e-c377ccdaa919 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Daily Site Report by Design Site Representative
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.7 - When required Undercuts (cut-to-fill operations)
label | 573f101f-9c92-5dd6-9ac1-23ee73f3074d |  | note | Method/Description - Visual inspection
label | ebc841ad-eda4-51ef-9e98-314cc1ecac4e |  | note | Test frequency - Prior to Filling
label | 631ebf2c-da87-5e05-bb1c-8398efa8f066 |  | note | Contractor - H
label | d751f6fa-d6dc-5441-b9f7-98fd09470c69 |  | note | Designer - H
label | 816cda5f-7d1d-5433-ac80-6adf6a0a143f |  | note | Verifying Records Checklists, Test and Supplier Certificates - Daily Site Report by Design Site Representative
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.8 - Piles
label | 9e292be0-218c-5ad6-83fc-39a460da28ec |  | note | Method/Description - Inspection
label | 89558d2d-a6af-598b-afac-4fd569abfea0 |  | note | Test frequency - Ongoing
label | bb1043b4-a984-5987-9ffb-3b2344f37241 |  | note | Contractor - W
label | 812ce363-a49f-5498-88ac-1455a3fd3dfa |  | note | Designer - R
label | f4e19a1d-9781-59ef-990b-14e71c021e0b |  | note | Verifying Records Checklists, Test and Supplier Certificates - Separate Signed ITP
checkpoint-status |  |  | checkpoint | 3.1.9 - Installation of prefabricated vertical drains (PVD). PVDs shall be installed after the sand blanket is placed and before the installation of high strength geotextile (basal reinforcement) and the embankment fill. The proposed locations of the PVDs shall be marked out in accordance with the Drawings.
label | 02772269-8cd9-5812-8490-49c9fb5ea26c |  | note | Method/Description - Inspection
label | fcaa78c8-eaec-5af0-8068-8694c820285b |  | note | Test frequency - Each installation of vertical drains
label | 064360f2-54db-57e9-a4aa-8667c2c68884 |  | note | Contractor - I
label | 920d3cd9-9abb-5771-bb1d-9879caee64c9 |  | note | Designer - I
label | a828426c-18b1-5d81-bc8e-0ef079211b3a |  | note | Verifying Records Checklists, Test and Supplier Certificates - Vertical drains Installation Checklist
checkpoint-status |  |  | checkpoint | 3.1.10 - Basal reinforcement installation
label | 22501e99-b98a-533e-bab5-2dec0e3e01c4 |  | note | Method/Description - Visual inspection of directional placement, panel length, laps, and damage
label | b9f3449b-b28c-52de-9d81-d6feb598e690 |  | note | Test frequency - During basal reinforcement installation and every 100m² of geotextile installed.
label | 78056acd-72a3-5086-ad48-99da7b326ea6 |  | note | Contractor - H
label | 5fd9e1e3-4c81-584e-a6df-82f98dacffa5 |  | note | Designer - H
label | 8d7c27b1-582a-5788-9d77-b4341a49eb13 |  | note | Verifying Records Checklists, Test and Supplier Certificates -
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.11 - Drainage blanket installation
label | e66d49e0-6a2c-5dba-86c0-571245b0190e |  | note | Method/Description - Visual inspection
label | 468681a3-e2b8-5559-9dcc-66c5968da39a |  | note | Test frequency - Prior to filling, and every 100m2 of geotextile installed.
label | 3101edb3-e15e-5a0e-a8cf-2ef9b2b70ee0 |  | note | Contractor - H
label | 29893417-818a-5baa-ac98-58662688a3fa |  | note | Designer - H
label | 32daacef-533c-5bd3-9312-0d9c1ac5f204 |  | note | Verifying Records Checklists, Test and Supplier Certificates -
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.12 - Monitoring Instrumentation
label | e2a4e63a-4b09-5aad-aed8-1a1637c9a195 |  | note | Method/Description - Survey/ data logging
label | beb620e3-0d13-5345-aa39-e51abca915bd |  | note | Test frequency - Ongoing
label | 7414e67b-d4c9-5f2c-b4d3-7c1f33df2da0 |  | note | Contractor - W
label | a5ad977e-4b9c-5ca9-bdc7-db37e3b8fd20 |  | note | Designer - R
label | 07952f33-9b11-5337-b4e0-37461539d0f9 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Separate Signed ITP
checkpoint-group |  |  | section | 3.2 Fill construction
checkpoint-status |  |  | checkpoint | 3.2.1 - Filling for the first 5m of Fill
label | 0d8da633-65bb-599a-b6c0-b002435afb62 |  | note | Method/Description - Visual inspection
label | 58eb5e2e-840a-56ce-a71b-42f823542139 |  | note | Test frequency - Daily
label | ede1dd0c-957e-5d6e-97ee-f9f01f364642 |  | note | Contractor - H
label | 9d95cad0-2ece-5f3c-b427-9aa1b730f5ce |  | note | Verifying Records Checklists, Test and Supplier Certificates - As-Built Survey Report/ UAV Scan
checkpoint-status |  |  | checkpoint | 3.2.2 - Hold filling operations for a period of two months
label | ff990dcf-077e-5fb4-ac6f-76f0372a01fa |  | note | Method/Description - Monitoring data records
label | 1b93eb8f-b083-5cdf-bd41-030dfd2360cf |  | note | Test frequency - Daily
label | 6f94c824-74cd-5099-8ca0-cdefa294f20b |  | note | Contractor - H
label | dea990f0-55b6-5065-9874-9039d72c47df |  | note | Designer - H
label | 1e53fcf8-4ab0-5c2a-8d99-45583015dbd8 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Monitoring data records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2.3 - Filling for an additional 3 meters of fill
label |  |  | note | Method/Description - Visual inspection
label |  |  | note | Test frequency - Daily
label |  |  | note | Contractor - H
label |  |  | note | Verifying Records Checklists, Test and Supplier Certificates - As-Built Survey Report/ UAV Scan
checkpoint-status |  |  | checkpoint | 3.2.4 - Hold filling operations for a period of three months
label |  |  | note | Method/Description - Monitoring data records
label |  |  | note | Test frequency - Daily
label |  |  | note | Contractor - H
label |  |  | note | Designer - H
label |  |  | note | Verifying Records Checklists, Test and Supplier Certificates - Monitoring data records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2.5 - Final Filling for an additional 2 meters of fill including Surcharge Fill
label |  |  | note | Method/Description - Visual inspection
label |  |  | note | Test frequency - Daily
label |  |  | note | Contractor - H
label |  |  | note | Verifying Records Checklists, Test and Supplier Certificates - As-Built Survey Report
checkpoint-status |  |  | checkpoint | 3.2.6 - Final Hold filling operations for a period of four months
label |  |  | note | Method/Description - Monitoring data records
label |  |  | note | Test frequency - Daily
label |  |  | note | Contractor - H
label |  |  | note | Designer - H
label |  |  | note | Client -
label |  |  | note | Lab -
label |  |  | note | Verifying Records Checklists, Test and Supplier Certificates - Monitoring data records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2.7 - insitu fill testing-Plateau Test
label |  |  | note | Method/Description - Plateau Test
label |  |  | note | Test frequency - Structural Fill - 1 test per material type per earthworks zone, except where outlined in RFI0057
label |  |  | note | ○ Buttress Fill - 1 test per material type per earthworks zone
label |  |  | note | ○ GAP65 - 1 test per material type per structure / location
label |  |  | note | ○ Cement Stabilised GAP65/ Structural Fill - 1 Test per material type per structure/ location
label |  |  | note | Contractor - W
label |  |  | note | Designer - R
label |  |  | note | Lab - I
label |  |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 3.2.8 - insitu fill testing-In situ moisture content and density
label |  |  | note | Method/Description - In situ moisture content and density
label |  |  | note | Test frequency - Structural Fill - 1 test per 1 m lift per 100m length, Heavy compaction and standard compaction areas outlined in RFI00057
label |  |  | note | ○ Buttress fill - 1 test per 200m length Average
label |  |  | note | ○ GAP65 - 4 tests per lift per structure
label |  |  | note | ○ Subsoil Drainage Back fill - 1 test per 500m3 ,
label |  |  | note | ○ Cement Stabilised GAP65 - 4 Tests per 0.5m lift per structure
label |  |  | note | ○ Cement Stabilised Structural fill - 1 test per 0.5m lift per 100m length
label |  |  | note | Contractor - W
label |  |  | note | Designer - R
label |  |  | note | Lab - I
label |  |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 3.2.9 - insitu fill testing- Undrained shear Strength
label |  |  | note | Method/Description - Undrained shear Strength
label |  |  | note | Test frequency - Structural fill - 1 test per layer per 1000m2
label |  |  | note | ○ Buttress Fill - 1 Test per layer per 2000m2
label |  |  | note | ○ Cement Stabilised Structural Fill - 1 test per layer per 500m2
label |  |  | note | Contractor - W
label |  |  | note | Designer - R
label |  |  | note | Lab - I
label |  |  | note | Verifying Records Checklists, Test and Supplier Certificates - test report
checkpoint-status |  |  | checkpoint | 3.2.10 - Scala Penetrometer Surcharged Fills
label |  |  | note | Method/Description - Scala Penetrometer Surcharged Fills
label |  |  | note | Test frequency - 435mm above Subgrade formation level to 1.5m depth. 3 tests per 20m chainage evenly across formation pavement width
label |  |  | note | Contractor - W
label |  |  | note | Designer - R
label |  |  | note | Lab - I
label |  |  | note | Verifying Records Checklists, Test and Supplier Certificates - Scala Test results
checkpoint-status |  |  | checkpoint | 3.2.11 - In-situ moisture content and density (and/ or air voids) testing of compacted for fill material Subgrade
label |  |  | note | Method/Description - in situ moisture content and density (and/ or air voids) testing of compacted fill material
label |  |  | note | Test frequency - Surcharged Fills - 1 test at subgrade formation level per 50m length, Cut Fill Transitions - 1 Test per 0.5m lift per 50m length for 1.0m subgrade depth
label |  |  | note | Contractor - W
label |  |  | note | Designer - R
label |  |  | note | Lab - I
label |  |  | note | Verifying Records Checklists, Test and Supplier Certificates - NDM Test results
checkpoint-status |  |  | checkpoint | 3.2.12 - Carry out deflection testing (either Benkelman Beam or FWD) at the subgrade
label |  |  | note | Method/Description - Benkelman beam or FWD Testing
label |  |  | note | Test frequency - Surcharged Fills - At subgrade formation level 10m interval in each wheel path
label |  |  | note | ○ Cut Fill Transitions - at three heights: 1.0m, 0.5m and 0m below subgrade formation level 10m interval in each wheel path
label |  |  | note | Contractor - W
label |  |  | note | Designer - R
label |  |  | note | Lab - I
label |  |  | note | Verifying Records Checklists, Test and Supplier Certificates - Benkelman Beam or FWD Test results
checkpoint-status |  |  | checkpoint | 3.2.13 - Laboratory Soaked CBR testing for Subgrade Fill
label |  |  | note | Method/Description - Laboratory Soaked CBR
label |  |  | note | Test frequency - Test per 5000m2 at subgrade formation level
label |  |  | note | Contractor - W
label |  |  | note | Designer - R
label |  |  | note | Lab - I
label |  |  | note | Verifying Records Checklists, Test and Supplier Certificates - Laboratory Soaked CBR Test results
checkpoint-group |  |  | section | 3.3 Preload/Surcharge (for embankments requiring preload)
checkpoint-status |  |  | checkpoint | 3.3.1 - Visual inspection for rate of filling
label |  |  | note | Method/Description - Inspection of fill height, rate of filling as per IFC drawing
label |  |  | note | Test frequency - To be monitored daily
label |  |  | note | Contractor - H
label |  |  | note | Designer - W
label |  |  | note | Verifying Records Checklists, Test and Supplier Certificates - PVD installation trial approval
checkpoint-status |  |  | checkpoint | 3.3.2 - After 1m of fill placement. Await approval from Designer before placing more fill.
label |  |  | note | Method/Description - Review data and TARP levels before releasing HOLD.
label |  |  | note | Test frequency - Before releasing hold periods and allowing filling to continue.
label |  |  | note | Contractor - H
label |  |  | note | Designer - H
label |  |  | note | Verifying Records Checklists, Test and Supplier Certificates - Designer site diary
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3.3 - Removal of preload/surcharge
label |  |  | note | Method/Description - Assessment of monitoring and instrumentation data
label |  |  | note | Test frequency - After completion of proposed hold period
label |  |  | note | Contractor - H
label |  |  | note | Designer - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3.4 - Removal of preload/surcharge
label |  |  | note | Method/Description - Preparation of preload/surcharge report
label |  |  | note | Test frequency - Every four weeks during earthworks operations and at the end and commencement of each earthworks season
label |  |  | note | Contractor - H
checkpoint-group |  |  | section | 4.0 Post Construction
checkpoint-status |  |  | checkpoint | 4.01 - Survey As-builts
label |  |  | note | Method/Description - Survey As-built
label |  |  | note | Test frequency - During construction and at end
label |  |  | note | Contractor - H
label |  |  | note | Verifying Records Checklists, Test and Supplier Certificates - CAD files
checkpoint-status |  |  | checkpoint | 4.02 - As-builts
label |  |  | note | Method/Description - Red Pen Mark up
label |  |  | note | Test frequency - End of Construction
label |  |  | note | Contractor - H
label |  |  | note | Designer - H
label |  |  | note | Verifying Records Checklists, Test and Supplier Certificates - Red pen mark ups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT