## Entec__Contact Energy - Te Huka
Step Id | Warnings | Rich Type | State | resource | type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4
3ae0b124-9397-4a5b-9606-e020a2ce7bda |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-006 TH14 Tie-In
ebcdb7ac-bad0-4f32-b940-9cfd0c060b36 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Instrument
71d6e4b1-0511-4667-b45d-f87405d9b174 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK
f5aa4b89-e752-4816-806f-215b45e5eacd |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-123 Instrument Pre-Commissioning
e829ce54-023a-5a9f-947e-bc32ec8494e3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
d2a42f02-6012-5606-89c8-0faa01ea565a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
89a080c2-ab4b-5bd9-b55b-b4d3e1731519 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
f8a242e8-1d12-5a24-8801-1f5722b2a5d0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
8c163d6d-0936-5633-9cd8-63528098cfcc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
e7a02c68-3346-5e67-a402-445c00543c1b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
d954f588-32ac-5bd3-96f8-a3504b9695f4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
94f7d6bb-dbf5-584e-a53a-66b8a836147b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
5be9c758-2017-5862-afe5-64f2028717ae |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
2bb17de3-cf03-53b7-ae35-bca6c76eb1dc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
8711f855-7003-5343-9856-f3e96ebdc48e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
a4f4fcb7-b201-5cd1-8f5d-fce7d7099b92 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
396e6cef-df9c-55fa-9c54-00c5eaf9b5d4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
450fb691-6534-58ce-aab7-89ba59b74a39 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
63fe650b-a640-534c-84d6-8e88a9dd97f3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
471fcb1c-59ba-513b-98f1-7a4758bffa20 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
ea756cfa-75d9-5858-b6e9-69bd913a12bc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
a0276c82-da23-5592-be04-22094118c703 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
9e4891d5-a0b5-582d-9fbf-39e67e847894 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
649d20ea-2bac-571d-887a-beece14f5983 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
b7766542-ad49-5883-a912-e11d0fbecd74 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
53787acb-a128-4b41-b8ae-f4b177bf2bb1 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-124 Commissioning Instruments
f3d3acf0-7582-5bae-a639-b1e9cbce3e76 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-124 Commissioning Instruments | Required Data
4a973a1e-66aa-5216-ac22-a3fd6b296862 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
e82e830a-f44c-5101-ae12-e2d7f21e7bdd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
fd0c4c7b-7135-57fd-9495-3dc3066aa050 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
25acc1a6-951a-57e5-8281-23da2bd4bf25 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
40ca851f-a0d9-5232-b52a-a23c7e5739f7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
eb1fc64d-6dbc-59a1-8b3c-cc235f39b749 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-124 Commissioning Instruments | Set Point 1
b595746c-1eb9-555d-8983-079df8f31364 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-124 Commissioning Instruments | Set Point 2
74c0449f-d9f6-522a-a9de-305ce7296ebe |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-124 Commissioning Instruments | Set Point 3
d9da97f0-bd85-5eb4-a58e-986add52ad20 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-124 Commissioning Instruments | Set Point 4
6a1c352f-bf1b-52e1-a0d5-32518c7b2c35 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-124 Commissioning Instruments | Calibration settings
88a40578-eed0-5a88-8245-17b3c59e1015 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
02f5110e-9add-4f17-bce7-452c16594738 |  | checklist-flat | not-started | ITR-CL-1-121 Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-121 Instrument Installation
6da065d3-e387-582f-a0df-5ff85ed96c0b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-121 Instrument Installation | Instrument Installation (Mandatory Photo)
27f2005f-3569-517b-be71-d194325e036a |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-OPEN AND CLOSE FEED BACK | ITR-CL-1-121 Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
4bfc1853-f294-49d6-9344-4a839fb99d32 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-FEEDBACK AND SETPOINT
a4bc37b9-2b5a-4b71-a916-ef5c366331db |  | checklist-flat | not-started | ITR-CL-1-121 Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-FEEDBACK AND SETPOINT | TH13/14 Control Valve-FEEDBACK AND SETPOINT
c0b8554f-549b-5457-bdd4-70eb88c19d88 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-FEEDBACK AND SETPOINT | TH13/14 Control Valve-FEEDBACK AND SETPOINT | Instrument Installation (Mandatory Photo)
6d9f307d-1629-5cf5-9edd-a12cbe5d47f5 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH13/14 Control Valve-FEEDBACK AND SETPOINT | TH13/14 Control Valve-FEEDBACK AND SETPOINT | All relevant signatures (Installed by, Approved by, Client Representative)
07969bc8-6218-49f1-9489-634f04810e04 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER
a1e6a951-7da7-4202-ada3-f503fc49af83 |  | checklist-flat | not-started | ITR-CL-1-130 Pressure Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER
d4c1e317-ed2d-54d2-9c70-042a3627dd53 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | Pressure Instrument Installation
b57c26fa-50f7-54a4-a9c8-e9429a36745e |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | All relevant signatures (Installed by, Approved by, Client Representative)
ee763689-ee3c-48e6-8530-10d806cd7454 |  | checklist-sectioned | not-started | ITP-I05B ENTEC - Instrument Loop Check | checklist | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITP-I05B ENTEC - Instrument Loop Check
ee87b263-4606-57f2-9d4c-851a4ac1d2eb |  | checkpoint-group | not-started |  |  | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITP-I05B ENTEC - Instrument Loop Check | Details
440cb445-b69b-5ef4-aed0-7af922014e8c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITP-I05B ENTEC - Instrument Loop Check | Details | Please upload ITP here when complete
5468d20d-5615-4653-81dc-b62f05d3c5c9 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-122 Instrument Calibration
43ab3b45-3c35-504e-9f32-49956c9de2d5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-122 Instrument Calibration | Required Data
c50fee20-8d89-59f9-9012-3a4f1976b8b2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
876a68e5-51d9-511f-bf7f-bf311d22314c |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
43947135-1507-4810-aeee-99099e447ae5 |  | checklist-flat | not-started | ITR-CL-1-130 Pressure Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-130 Pressure Instrument Installation
78c734e5-925d-5f29-914d-996158bfd86d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-130 Pressure Instrument Installation | Pressure Instrument Installation
88d06968-1bfc-5785-8531-5c6eaf9a2a3d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-130 Pressure Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
71bc2e41-ab95-4559-b200-df2cca347a8d |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning
5f31f47b-c962-5d84-8267-95dc28dbad86 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
e5b15235-68fd-5174-bb2b-f1cee15168a0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
c6413aca-92c1-58eb-8b7d-9d8b3a449593 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
0be5aa4c-bc75-5975-8017-5142fc1626e3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
db06b2fb-edcf-5a3f-9ae5-23abf835e89d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
0e9b54f0-516c-5046-84e4-7cba7608e38a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
c6a5536f-5926-5b96-a063-6fd1e038dc12 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
a52ca252-7243-5547-9cfa-129f0b9cb081 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
596bcfcb-413f-58fb-a6c9-003abbd01081 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
d7a5b2da-abb3-5454-aaa5-f244093fbe9b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
e0885458-0e7f-5779-bd8d-f61ba04f0f6a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
8c557b6c-ee9d-5d7c-a2cc-52810f99590f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
24a710de-8797-5c80-84d2-89c4b15ecb03 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
b23fde4d-4575-52d1-8b4c-2a00c423990d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
8df7efb5-000c-5148-99ad-ca63014265c9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
b9a4c1aa-0a54-5d04-b70e-30df21ff627a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
6cdc54bd-57b4-54b9-808f-4a41f0d4b483 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
04a5c546-57cf-504f-8818-c405e44cb930 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
763282b3-7a01-5ebe-9f96-89c2e53b729e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
a69e7663-733e-50c4-befa-30d404e3200c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
da446848-85c0-557c-8642-ef06f2dbe163 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
942ad7e7-accf-414c-89b8-fd8dd1aafe8f |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments
ec190c1c-0c82-5f22-9d98-07e2fd7ae457 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments | Required Data
1c1898cc-bb83-5ff9-aa37-d3ec55ba82b1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
b1dc108f-e71a-5f4a-b4b0-6bf71ebf4f34 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
269dba12-d4fe-5f33-95f6-53422b14aef6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
dc347d82-e43d-5e96-bf44-768f421f278a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
6d4196cd-f005-5d2d-aee2-afe9b048da82 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
9203d2b2-e671-5edc-b3d3-89fbb6284d6c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments | Set Point 1
f99417c8-7abd-581c-80a7-581cba0652cf |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments | Set Point 2
9e3a3bea-b1af-56c8-9463-ccaea22ef11d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments | Set Point 3
dd957047-ff22-5bed-9980-ae5a770819f9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments | Set Point 4
dc211df4-d4ef-5f22-bada-a14360c17039 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments | Calibration settings
cc150ebc-484d-57c6-83f5-43335486a449 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | TH32 2-PH SEPARATOR, PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
a45536b4-9250-4d77-a400-f4ec41102fb9 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter
f39683eb-83d8-4949-bdd4-1ed10bd9692d |  | checklist-flat | not-started | ITR-CL-1-130 Pressure Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-130 Pressure Instrument Installation
5eb34259-0a2f-55b9-8f82-7dcceeebb91c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-130 Pressure Instrument Installation | Pressure Instrument Installation
33a74c7b-56a1-582a-a2ca-ef1ac34e04ca |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-130 Pressure Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
2614eecb-bdba-4616-9aac-d6caf50ef379 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-122 Instrument Calibration
9ad6ec99-eb70-5d8a-9298-6af3246745b4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-122 Instrument Calibration | Required Data
009a3fad-9e4d-57a8-ad8f-0a7de2688689 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
7db2fb12-8b14-541a-a0a8-1e8219e089af |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
c3007da2-5cb0-4e9f-aaa8-0455d29b6f20 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning
56f584bf-647a-50ef-93fc-78017278a3ff |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
f36656bb-8284-5962-8199-db109989190b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
a2d7ba54-ba65-582f-946f-abc4e9ac6db0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
475daf34-fa0f-5452-ba0a-48d3d6d6c9f0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
7569c234-7c33-5f53-a60c-e4d6f32e59aa |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
b203d073-84ae-51e2-a86e-f36f4e0e03c2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
2d4d31f0-a7e1-5d24-b8fa-5036887df747 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
090b49a6-ab93-54bd-892a-b6f707cdc72a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
ff379773-15fa-5d0d-90a4-aa2ea3e0e894 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
a2fdd762-cac2-53bd-81f1-82988778d5a2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
1a752900-6681-54ed-88c1-fa2b096844f3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
9f556d24-31e8-5fbc-8d0f-7a59c5615572 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
92bbfa00-a446-5531-af12-8051cbf4bcb1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
09c4583b-7252-5aaf-a509-f6770c538919 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
93929ed4-baad-5c55-98c5-977c860dcc5c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
aeb49a1f-2394-57af-ac2f-3cda68686553 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
67904ba9-cade-5909-97a4-6136bd81a794 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
04f89a1c-2178-5459-804b-411c096e9645 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
7b84538c-c90e-5f3d-8162-ba684ccc76a4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
3cbd09e9-b02e-5613-91ab-a513a7aa73f2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
d41272c5-c486-5023-a8d2-f3bd91a749dd |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
9b5a9ca9-324d-481e-822a-782b63b12378 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments
d53fcbe5-6c3d-5a89-afed-8fd7e7c34c37 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Required Data
d60b5192-699a-5c9d-aef6-784dad6649fc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
7567ffeb-803a-5a08-99ab-be5c25032412 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
d2fc0b68-832c-5156-9329-13e427567e18 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
54a8e108-168a-5bed-86bc-84e00910e72d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
a87ba206-222f-513d-942b-c46b3f066032 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
de8af387-608e-578f-8916-e86929cede9a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 1
848bb7cb-ccd3-5623-bc56-bffbec1ce880 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 2
3217df91-0485-5da1-9390-516b497e54ad |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 3
09ab480f-c68d-51ff-877d-47c2d7f5c1bc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 4
e2472273-b334-57bf-acd5-35e5652a199c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Calibration settings
72509c4b-32cf-5caf-80d8-5284656e85e7 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Instrument | U3 Separator Inlet Header , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
6914f326-e077-431a-8e5c-5015f29b2c08 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Cables
c3eb2a5a-4f2f-4b03-b8e1-d75552df52f0 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH00S030BHx10GY103-A01
74518e52-3cf6-4498-8028-ce699fa15221 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH00S030BHx10GY103-A01 | 1.5mm 6pr Multicore to JB03
bb6a6ccf-f134-5005-82a5-700b226381e3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH00S030BHx10GY103-A01 | 1.5mm 6pr Multicore to JB03 | Instrument Cable
fabda7d6-0370-5031-b5d9-dcfd5020b069 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH00S030BHx10GY103-A01 | 1.5mm 6pr Multicore to JB03 | Electrical Checks
ba26ebf0-6c1b-4cc7-aaa9-6f731c9df4c7 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH00L030NDA10AA110 -C01
d20e7b20-9ca2-4f6a-a6c2-4fabb55d6443 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH00L030NDA10AA110 -C01 | 1.5mm 4C CuSn PVC/PVC
0f7cdb7e-265c-5713-b9a0-6f0c7254dfee |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH00L030NDA10AA110 -C01 | 1.5mm 4C CuSn PVC/PVC | Instrument Cable
ef8820e2-878d-50c5-9b8e-e155d63db067 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH00L030NDA10AA110 -C01 | 1.5mm 4C CuSn PVC/PVC | Electrical Checks
5fb869bc-5a63-47ff-9f6a-cb2d96bc2c88 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH00L030NDA10AA110 -A01
40e6b18e-3085-45dd-8409-50e4d780bd7b |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH00L030NDA10AA110 -A01 | 1.5mm 2pr CUSN ESCS
023e4931-2f8e-5b46-b192-c7b11ccd308f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH00L030NDA10AA110 -A01 | 1.5mm 2pr CUSN ESCS | Instrument Cable
4f6afb75-d87f-5da8-a41c-f7dcff1806a0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH00L030NDA10AA110 -A01 | 1.5mm 2pr CUSN ESCS | Electrical Checks
97bacc08-760a-4ee0-aba8-9d3692f42a02 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH00L040NDA10CP010-A01
c2dfa1bb-3042-4d47-bf43-d09aabaf988c |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH00L040NDA10CP010-A01 | 1.5mm2 1pr CuSn CS
778d4f95-6e86-58d6-8e5d-1b0323d6a9d1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH00L040NDA10CP010-A01 | 1.5mm2 1pr CuSn CS | Instrument Cable
b2da62e2-f35a-5093-bd2c-d2abe4bca3e5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH00L040NDA10CP010-A01 | 1.5mm2 1pr CuSn CS | Electrical Checks
0361512a-f7cb-4835-b8dc-fb469bb4bb46 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH00S030NDA10CP010-A01
781bf0be-1f9a-484b-b9f3-405e55d5bf50 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH00S030NDA10CP010-A01 | 1.5mm2 1pr CuSn CS
a8e17c7c-3db0-583a-aaa2-2c1f3de26762 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH00S030NDA10CP010-A01 | 1.5mm2 1pr CuSn CS | Instrument Cable
b9b81a99-33e1-5c7c-9861-6edd9ac5dc11 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH00S030NDA10CP010-A01 | 1.5mm2 1pr CuSn CS | Electrical Checks
28d4ffa0-b661-4a18-b260-317f1b1df7a9 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH000140NDA10AA080-P01
3fcedec0-3da3-46a7-959f-08324d1251e8 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH000140NDA10AA080-P01 | 16mm2 3C+E CUsN XLPE/PVC
7d3f3d82-4c73-5322-a81a-9f5eb6b5c1f7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH000140NDA10AA080-P01 | 16mm2 3C+E CUsN XLPE/PVC | Low Voltage Cable
3461879c-7d02-56a7-9784-fe1a5f067491 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH000140NDA10AA080-P01 | 16mm2 3C+E CUsN XLPE/PVC | Electrical Checks
c80c1ebe-f4a3-51a6-807c-92b3c41dcf18 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH000140NDA10AA080-P01 | 16mm2 3C+E CUsN XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
37714a9b-d435-49fa-8cc6-7a7b42c2f37a |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH000140NDA10AA072-P01
97a5b360-3676-4c78-ac34-9c751aae175c |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH000140NDA10AA072-P01 | 16mm2 3C+E CUsN XLPE/PVC
d5c65f70-843e-535a-816d-25cd7d4de989 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH000140NDA10AA072-P01 | 16mm2 3C+E CUsN XLPE/PVC | Low Voltage Cable
bfe44972-0e88-560b-bb8d-01b8888109d0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH000140NDA10AA072-P01 | 16mm2 3C+E CUsN XLPE/PVC | Electrical Checks
9bad547f-1b5a-5854-9e53-44b61c64ec15 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH000140NDA10AA072-P01 | 16mm2 3C+E CUsN XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
4badd7db-d60b-4498-a85f-01dee026e946 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH000140NDA10AA080-S01
b315053c-a362-4839-aaae-9b9781ccee28 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH000140NDA10AA080-S01 | Profibus DP - Grey Sheath
5508e412-092a-58f2-8f5a-388b32b4ca2c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH000140NDA10AA080-S01 | Profibus DP - Grey Sheath | Instrument Cable
a3028b80-4917-5c2b-9c70-340524b694c7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH000140NDA10AA080-S01 | Profibus DP - Grey Sheath | Electrical Checks
c89626d3-9e12-4b7b-b5ab-afbd5f3cb836 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH000140NDA10AA072-S01
699c3afd-51f3-4b19-a983-499bbe01cc36 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH000140NDA10AA072-S01 | Profibus DP - Grey Sheath
11e23c1d-9e9a-572e-9c72-a2c7c29a2e4a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH000140NDA10AA072-S01 | Profibus DP - Grey Sheath | Instrument Cable
4a356177-427f-57a8-8707-1cd36ace9fe1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH000140NDA10AA072-S01 | Profibus DP - Grey Sheath | Electrical Checks
ef0d5bc3-b6f1-47b3-a3e6-527b1179c283 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH00S030BJA10GS010_BOND12
79808148-15f2-4536-918f-9badcd86935e |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH00S030BJA10GS010_BOND12 | 120mm2 1C Earth
7c8ef5a4-6d2c-5d58-a3a5-64740725b2a3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH00S030BJA10GS010_BOND12 | 120mm2 1C Earth | Electrical earthing system installation
6b2ef4e1-6e87-593f-b0fc-2020d892256c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Cables | TH00S030BJA10GS010_BOND12 | 120mm2 1C Earth | Test Results
a086bd02-282f-4b52-9cce-0841827799e4 |  | checklist-flat | not-started | Cable Test Record | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Cables | Cable Test Record
6be67759-62df-5161-aaf3-6c49c347aa41 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Cables | Cable Test Record | Upload completed ITR scans
f73f3308-2060-44fc-8c6f-9460ae8a4f0d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Junction Box 3
5c51ea09-ef2c-49cc-9e25-bb1102e89e88 |  | checklist-flat | not-started | ITR-CL-1-106 - Junction Box | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Junction Box 3 | ITR-CL-1-106 - Junction Box
2fb1d5ed-de89-50bf-9d32-b97247ae4f88 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Junction Box 3 | ITR-CL-1-106 - Junction Box | Junction Box
499aab6b-8d5d-4be3-84ef-4434ae664fe0 |  | checklist-flat | not-started | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP-SEP-E-006 TH14 Tie-In | Certificate of compliance (COC)
9b6c95a6-4665-5a3b-ba53-b73b1a6339b8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-006 TH14 Tie-In | Certificate of compliance (COC) | Please upload Certificate of Compliance here when complete (COC)
1d10cbcc-c63f-46bd-882a-1834dfab397e |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-003 TH32 Field Lighting & Power
d214cbf6-3a83-4d5d-8605-6eabd0794ca1 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-003 TH32 Field Lighting & Power | Cables
e8217f76-30c8-423e-a5d6-700aaf3913d3 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-003 TH32 Field Lighting & Power | Cables | TH000320BFA10GS010_-F52-P01
9a5a4059-4b10-4634-97d5-233ff92423bb |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-003 TH32 Field Lighting & Power | Cables | TH000320BFA10GS010_-F52-P01 | 4mm2 2C+E CUSN PVC/PVC
d279b470-1578-546c-84ab-c5a9db780058 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-003 TH32 Field Lighting & Power | Cables | TH000320BFA10GS010_-F52-P01 | 4mm2 2C+E CUSN PVC/PVC | Low Voltage Cable
d7070db4-0186-5505-a158-85ce65426b68 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-003 TH32 Field Lighting & Power | Cables | TH000320BFA10GS010_-F52-P01 | 4mm2 2C+E CUSN PVC/PVC | Electrical Checks
7e77cd64-2ad1-5888-bd81-a033ff22aae9 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-003 TH32 Field Lighting & Power | Cables | TH000320BFA10GS010_-F52-P01 | 4mm2 2C+E CUSN PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
9ee65f87-69e1-4f7d-b3e1-7ab8aa0d40bf |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-003 TH32 Field Lighting & Power | General Electrical Equipment
f4c8ca2b-352e-4035-9c41-7422a1841abf |  | checklist-flat | not-started | ITR-CL-1-100 General Electrical Equipment | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-003 TH32 Field Lighting & Power | General Electrical Equipment | ITR-CL-1-100 General Electrical Equipment
63aa8efe-2e33-53c6-b4ce-fce5619e70c1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-003 TH32 Field Lighting & Power | General Electrical Equipment | ITR-CL-1-100 General Electrical Equipment | General Electrical Equipment
fc2cc1bc-410a-5c16-b9b0-b7fa29882631 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-003 TH32 Field Lighting & Power | General Electrical Equipment | ITR-CL-1-100 General Electrical Equipment | Electrical Checks
ac4eace6-835a-566e-a4f3-bba6e6a4581c |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-003 TH32 Field Lighting & Power | General Electrical Equipment | ITR-CL-1-100 General Electrical Equipment | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
735cc54a-50b9-4d6f-98b8-8098358b0f74 |  | checklist-flat | not-started | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-003 TH32 Field Lighting & Power | Certificate of compliance (COC)
694e6bf2-1973-5613-aed8-9adfc41ac129 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-003 TH32 Field Lighting & Power | Certificate of compliance (COC) | Please upload Certificate of Compliance here when complete (COC)
da64e710-1320-4f22-83c0-9ed1c9f77e01 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power
a2383b65-f99e-4a7f-85cd-205cfdccdf26 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds
1914de19-b0df-4fec-a24a-11f5e9d92d1e |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND01
4fbb8bde-7e1c-4f67-9628-3e3e69b1c1a2 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND01 | 240mm2 1C Cu PVC/PVC GE/YE
a39f55ea-f995-5481-b557-4a7cd816b009 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND01 | 240mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
23df5187-2d08-5d55-ae55-cf59049759c9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND01 | 240mm2 1C Cu PVC/PVC GE/YE | Test Results
da306b03-22b9-4cb8-a87e-97cf734c6314 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND02
67c9c794-f66f-4ff0-9130-a5ad74bb4ea1 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND02 | 240mm2 1C Cu PVC/PVC GE/YE
49cbdae0-8136-590e-8298-b32c0f0c8417 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND02 | 240mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
19de42cc-a720-568b-bdf0-5639011d96fc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND02 | 240mm2 1C Cu PVC/PVC GE/YE | Test Results
cdc2a462-056f-490f-9558-dfe764e0c263 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND03
590a8349-8f87-4821-95a7-3852cf87bad2 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND03 | 70mm2 1C Cu PVC/PVC GE/YE
a07733a4-bc6c-5707-b1fa-47a2036a3f5e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND03 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
592a4d5e-c8d9-548e-8536-fafabc9b9464 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND03 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
c59c9931-eaf2-434d-a88c-932a1fabf343 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND05
c334afdc-45e8-403e-8616-eb6886aea093 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND05 | 70mm2 1C Cu PVC/PVC GE/YE
d5bd3c09-8a74-5e85-802d-1607becd5b0a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND05 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
f278acef-1e4d-5de5-91a3-c5be90a1b41c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND05 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
7c40c5df-458c-42a7-bc6e-95989fb20b6f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND06
3aa4fc7d-2a0c-45fe-8433-cb6ea4d790e1 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND06 | 70mm2 1C Cu PVC/PVC GE/YE
1e054832-7b95-5a32-b17b-bf9f6afcc955 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND06 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
9ea468c5-40af-58b8-bddb-e2a0f6341eff |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND06 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
134adb17-04d9-44d9-ac9b-544f7bfb8649 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND07
40f34c59-acb5-4381-a67e-f1b3bf66c734 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND07 | 70mm2 1C Cu PVC/PVC GE/YE
0b5e8ce0-2901-559f-9e4d-49479d6fc03b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND07 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
8a99c8d6-a4cc-59db-b7ba-264e41c2fdf3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND07 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
c52a16e9-3c8a-4234-98fb-cb9637530405 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND08-1
571c48ea-c6cd-47f6-a1f1-c21338a14527 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND08-1 | 240mm2 1C Cu PVC/PVC GE/YE
9173389f-50f9-50b3-9153-6db3c3f66ed1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND08-1 | 240mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
39680db3-b49e-51f6-97c2-c73c6eded913 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND08-1 | 240mm2 1C Cu PVC/PVC GE/YE | Test Results
57712fd6-7663-4d34-bc9d-4f627e4c1c97 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND08-2
4ad2270b-8f0c-4c0a-82c2-48c9fc0e1de5 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND08-2 | 240mm2 1C Cu PVC/PVC GE/YE
6dd0a724-9722-575c-9622-fb31e7bcf26b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND08-2 | 240mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
e8124bee-3e37-53bf-8b42-b0b1cba19928 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND08-2 | 240mm2 1C Cu PVC/PVC GE/YE | Test Results
a5a73e8c-2b6c-4c8e-8301-e8896ae24b08 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND11
a82acaf1-3a00-4f6c-b258-1d687e7f602d |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND11 | 240mm2 1C CuSn(BAR CABLE)
f4dcdd55-0406-5cc3-9111-3c7c9f4c1f45 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND11 | 240mm2 1C CuSn(BAR CABLE) | Electrical earthing system installation
3519d3ae-ed31-5b96-85ea-b4aea00d282c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Earth Bonds | TH000320BFA10GS010_BOND11 | 240mm2 1C CuSn(BAR CABLE) | Test Results
3c9abce4-43e3-4c5d-98d0-1f6327dfba57 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut
58c55a96-7cc4-40ca-8a21-e7b0725ec7df |  | checklist-flat | not-started | Cable Pre-installation | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | Cable Pre-installation
de7c8e05-61b2-5937-93a6-b4232cd714d9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | Cable Pre-installation | Cable Pre-Installation
b39f4417-3d9c-4f65-86ac-ab6057373333 |  | checklist-flat | not-started | ITR-CL-1-114 UPS Installation | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-114 Entec - UPS Installation
86e21426-5c5e-532f-ae5b-4023a6ff281e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-114 Entec - UPS Installation | UPS Installation (Mandatory Photo)
d871b130-3e3a-5d81-8d3e-378fc0c8fcc2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-114 Entec - UPS Installation | Test results
5a9069ab-e4b3-4391-8e91-1dbebe617377 |  | checklist-flat | not-started | ITR-CL-1-101B Cable Supports Above Ground | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-101B Cable Supports Above Ground
f7ba33ee-61fc-5048-a85c-b43a6cbdb4c9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-101B Cable Supports Above Ground | Cable Supports Above Ground
5ccf34de-f47d-4d47-b104-fe567973cc8a |  | checklist-flat | not-started | ITR-CL-1-101A Conduit/Ducting Below Ground | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-101A Conduit/Ducting Below Ground
000d3a29-d5b8-544d-999d-ee591a6a8157 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-101A Conduit/Ducting Below Ground | Conduit/Ducting Installation Below Ground
d34a8963-7754-4830-ba7f-6c99b9bdb23b |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-111 Electrical earthing
b7c585bb-261c-54ad-8df8-87e34a588272 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-111 Electrical earthing | Electrical earthing system installation
cd2ef025-5f4a-5b89-9cc9-c93a18281da4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-111 Electrical earthing | Test Results
276b9b0c-d09d-4289-bbe1-929fb55a5f14 |  | checklist-flat | not-started | ITR-CL-1-108 Electrical Switch Rooms | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-108 - Electrical Switch Room
1e0846a5-3354-5f88-9679-946588f832e3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-108 - Electrical Switch Room | Electrical Switchroom (Mandatory Photo)
10684867-fbed-4643-8908-8c2f197d7b08 |  | checklist-flat | not-started | ITR-CL-1-102 Entec - Distribution Board Installation | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-102 - Distribution Board Installation
2084b098-e986-5514-bd1d-4f35ff2b99cd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-102 - Distribution Board Installation | Distribution Board Installation (Mandatory Photo)
c4b389ea-6042-5278-a3bf-75a2d3b43f9a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-102 - Distribution Board Installation | Test Results
5bda193f-eec7-5fb7-91d4-b0ce2647f11e |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-102 - Distribution Board Installation | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
e9e5daa2-af0d-476c-8790-97b7e60298dc |  | checklist-flat | not-started | Cable Test Record | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-103 - Schedule of Test Results DB
b23519c9-1ecb-53ed-a225-a3a29e434a8f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-103 - Schedule of Test Results DB | Upload completed ITR scans
4b753c11-3bf1-40b6-8b4b-7e0a6a0c5aea |  | checklist-flat | not-started | ITR-CL-1-109 Electrical Equipment Package | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-109 Electrical Equipment Package
85806b25-7168-57f2-ac05-32faaa358068 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-109 Electrical Equipment Package | Electrical Equipment Package
b67f4b3b-16d4-4d2d-87b4-8fce2d7a5c99 |  | checklist-flat | not-started | ITR-CL-1-100 General Electrical Equipment | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-100 General Electrical Equipment Install
419f8711-d5fb-5974-b28d-63980848f6ae |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-100 General Electrical Equipment Install | General Electrical Equipment
5fc4a9d3-1845-5b4a-aaf6-7fe09637afdc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-100 General Electrical Equipment Install | Electrical Checks
538f972a-48eb-57ae-ae73-2b2b6cc16e67 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-100 General Electrical Equipment Install | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
2f9756f9-4356-4fc9-85f5-64ac0457bb33 |  | checklist-flat | not-started | ITR-CL-1-101C Cable Transits | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-E-51A Entec - Cable tray and transits
b7f668ef-fc22-55d8-a9e1-27e0ae4c03eb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-E-51A Entec - Cable tray and transits | Cable Transits
898680db-3316-42da-93eb-bca1e386e358 |  | checklist-flat | not-started | ITR-CL-1-106 - Junction Box | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-106 - Junction Box
b40558fc-abc3-581e-bbf9-8e6dca0abede |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-106 - Junction Box | Junction Box
f6541870-ee73-4465-b88c-6ee8252d4933 |  | checklist-flat | not-started | ITR-CL-1-105 Control Panel | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-105 Control Panel
c1fa82d9-2006-5bf9-93b5-f2f7b43b99f3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-105 Control Panel | Control Panel
323588b7-eb47-55ce-8600-35bba9132c9e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-105 Control Panel | Electrical Checks
1b48645b-63ae-589e-9a3c-5a7e10ceb89d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-105 Control Panel | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
784fa606-b305-47ef-86f9-ee4bd3a308ad |  | checklist-flat | not-started | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | Certificate of Compliance
a8dd4b26-c58b-5086-b1d1-fc37d9325f7d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | Certificate of Compliance | Please upload Certificate of Compliance here when complete (COC)
9f657db6-e62d-4847-9983-e18d57b06615 |  | checklist-flat | not-started | ITR-CL-1-110 Generator Package (LV) | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-110 Generator Package (LV)
d039ecb6-8d7e-5cdc-a222-ebcdbacfb7a9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-110 Generator Package (LV) | Generator Package (LV)
362d8e74-1327-5ac3-a37a-d9363ef753ec |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-110 Generator Package (LV) | Electrical Checks
efdc71bb-e8a9-5ade-bad0-ddb25f55a605 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Well Hut | ITR-CL-1-110 Generator Package (LV) | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
38140178-f8e0-44db-a95d-0ba442deacdf |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables
245c4c8f-6b84-420d-839b-0490af25b500 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F01-P01
0e76d82a-23f3-4442-beaf-bcb4a8cd5d39 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F01-P01 | 95mm2 + 25mm2 4C+E CuSn XLPE/PVC
0ea7cd0f-44b2-518b-a9b8-d70fee45816c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F01-P01 | 95mm2 + 25mm2 4C+E CuSn XLPE/PVC | Low Voltage Cable
8c67989c-4648-5940-9658-79e16bbd5081 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F01-P01 | 95mm2 + 25mm2 4C+E CuSn XLPE/PVC | Electrical Checks
7665e1e6-0db0-5db0-8c79-1a9291b8bcdc |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F01-P01 | 95mm2 + 25mm2 4C+E CuSn XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
7230f750-4745-4d52-a202-f86e23389e4a |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F05-P01
8f96647a-5d51-4353-af5a-ebee06aa3fb2 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F05-P01 | 95mm2 + 25mm2 4C+E CuSn XLPE/PVC
66c45015-69d3-5ab7-9451-ebe93d805684 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F05-P01 | 95mm2 + 25mm2 4C+E CuSn XLPE/PVC | Low Voltage Cable
731ae226-f5c7-588f-bf8f-30deed7c88b2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F05-P01 | 95mm2 + 25mm2 4C+E CuSn XLPE/PVC | Electrical Checks
d64460bf-25e7-5f39-a9e2-5065ad3af4a9 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F05-P01 | 95mm2 + 25mm2 4C+E CuSn XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
a4a646ff-3f58-4e2e-ae97-64e5912e1c45 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010-C01
7ca3a7db-42ff-435f-8809-d2c82627574e |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010-C01 | 1.5mm2 2C CuSn PVC/PVC
24c025fc-c761-5c00-96b0-acee067736bc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010-C01 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
c1661d07-1462-5b94-89e3-d9cbe2151919 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010-C01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
e236afde-b6e9-49e3-b0a4-22cff98c1232 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010-C02
4c9aecf3-5155-4f1d-bdd5-baf6fdadc667 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010-C02 | 1.5mm2 2C CuSn PVC/PVC
d3aa6561-2ee3-5dea-938e-67b86f1ff649 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010-C02 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
19e57d47-856c-59e2-94dc-7a70b6c3709f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010-C02 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
10a4aa3b-f4aa-4379-ba5d-674055240d5a |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F01-C01
8a757302-b3cc-4c90-ba1e-7306d896b989 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F01-C01 | 1.5mm2 12C CuSn PVC/PVC
58bf2d3f-a7c6-5401-a122-bfc4d3002ca0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F01-C01 | 1.5mm2 12C CuSn PVC/PVC | Instrument Cable
93c084b5-7efe-5a54-9a2c-0a2c64dd8e7d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F01-C01 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
d7e29251-86fd-4440-951f-af7d93be6257 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F05-C01
13495c72-c71d-4519-9037-cf50e87bb035 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F05-C01 | 1.5mm2 12C CuSn PVC/PVC
811399be-dd1a-5c7f-8a3e-da80402cc8e2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F05-C01 | 1.5mm2 12C CuSn PVC/PVC | Instrument Cable
059d22b4-0e21-56ea-b21f-a14bb1e424be |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F05-C01 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
256f64b3-89b5-46de-a23c-367ddee0d82d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F37-P01
17f2eefb-6d7c-47cc-8247-fbf2813632b5 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F37-P01 | 4mm2 4C+E CuSn PVC/PVC
7738d826-360a-5df7-a6ad-232bab3eea2a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F37-P01 | 4mm2 4C+E CuSn PVC/PVC | Low Voltage Cable
fafd8116-8f94-5cae-9914-ed020b4e6c57 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F37-P01 | 4mm2 4C+E CuSn PVC/PVC | Electrical Checks
c13f8921-eba9-5a17-a9d4-5901b4a8a520 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F37-P01 | 4mm2 4C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
11bf1fb5-ae1b-4114-97bf-e5796bc87ee8 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F40-P01
040c1e80-1fa8-4aa5-a4e9-8012b967c5c3 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F40-P01 | 6mm2 4C+E CuSn PVC/PVC
57cfe8ba-5530-5ba7-8960-bb28c2c5f9ee |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F40-P01 | 6mm2 4C+E CuSn PVC/PVC | Low Voltage Cable
b525efd7-6ab7-51ff-992e-a8f7d4685271 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F40-P01 | 6mm2 4C+E CuSn PVC/PVC | Electrical Checks
93618d72-e1bb-5da9-9795-aed11743447b |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F40-P01 | 6mm2 4C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
a2e8d374-a462-4e20-a25d-e9ae02ddef7e |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F44-P01
784e2a27-7f78-4193-a984-9915ce37d7e2 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F44-P01 | 2.5mm2 2C+E CuSn PVC/PVC
35c270a6-2ac7-5c9a-bacf-98cda1ba6c7c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F44-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Low Voltage Cable
8c87e70b-2541-5ecf-938c-c6c3700eec71 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F44-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Electrical Checks
e1804031-fab2-5178-88ac-b1b86e2793fb |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F44-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
7beba28b-6e7b-42d4-85d7-9bb649413831 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F46-P01
210fe967-c860-4279-bafd-e82192e92018 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F46-P01 | 2.5mm2 2C+E CuSn PVC/PVC
92301ae2-1f38-5ce6-a8db-d9f129006aa9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F46-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Low Voltage Cable
e5ac8c01-cbe4-54fd-b446-3506e12a3d5c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F46-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Electrical Checks
69c0309f-0e69-5175-8b35-edf5f9342694 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F46-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
fa7a4a4f-a015-4b72-9d70-7a641d8b5ea7 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F53-P01
d33bbcce-b654-4377-9f9e-2d055b953580 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F53-P01 | 4mm2 4C+E CuSn PVC/PVC
0223840f-4cc1-5535-97fb-e7ccd4bd4fa7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F53-P01 | 4mm2 4C+E CuSn PVC/PVC | Low Voltage Cable
a9f00d0f-e25b-5290-af14-e78c17c66cfa |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F53-P01 | 4mm2 4C+E CuSn PVC/PVC | Electrical Checks
fa61d1f5-88ad-5f81-82cd-7959bc625f2f |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F53-P01 | 4mm2 4C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
bcf1ef9b-ca98-4597-8c6a-80ecbb445c2e |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F47-P01
e758158c-473c-4026-95bc-a87e7e0021aa |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F47-P01 | 2.5mm2 2C+E CuSn PVC/PVC
1357ac5d-a5e9-5786-97bd-b2b6ad4e25da |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F47-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Low Voltage Cable
dc44764a-7f71-5cbc-9ed5-277b8114019f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F47-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Electrical Checks
5ee440d2-4253-5f90-a2ef-337ccbe4656e |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F47-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
06f20783-c2ba-4d18-9fb1-8d8418d40f48 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F54-P01
4744af5c-e436-4fe4-a5a5-caef20a59333 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F54-P01 | 2.5mm2 2C+E CuSn PVC/PVC
f76cceb2-95e7-55c3-8f0c-52068f5b2223 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F54-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Low Voltage Cable
b8f3b2b4-6d73-59ff-bb8b-24cf92f1f730 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F54-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Electrical Checks
ea7bf330-2315-5927-990f-06b13d841407 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | TH000320BFA10GS010_-F54-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
28e64fac-5da3-417b-ada2-8b6f5396796c |  | checklist-flat | not-started | Cable Test Record | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | Cable Test Record
19921480-fe4f-5836-a5e9-76ce04b2078d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-001 TH32 LV Power & Light Small Power | Cables | Cable Test Record | Upload completed ITR scans
796c0455-2a2d-4879-b7f3-a679d9f4c242 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment
a2baf984-3d0b-46c1-8837-5381559fd5b0 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Earth Bonds
a581bee5-da2a-4b8e-97f5-3b6eb9dffe32 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Earth Bonds | TH000320BFA10GS010_BOND04
3a7bab02-fb3a-42f2-b67b-13bae5a00d0e |  | checklist-flat | work-in-progress | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Earth Bonds | TH000320BFA10GS010_BOND04 | 70mm2 1C Cu PVC/PVC GE/YE
e06aa0e0-f4a1-5522-97da-8f6131b9cea0 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Earth Bonds | TH000320BFA10GS010_BOND04 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
79a94305-8b89-5570-9a17-1e772fa83bd0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Earth Bonds | TH000320BFA10GS010_BOND04 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
e1b5d487-0465-4aaa-971b-6ce5d1ce6638 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Earth Bonds | TH000320BFA10GS010_BOND09
cec2b76d-1ac0-452c-a3c5-e5610e1fc988 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Earth Bonds | TH000320BFA10GS010_BOND09 | 120mm2 1C Cu PVC/PVC GE/YE
83c05ac6-da43-5a25-a5fc-7b186e00b9fb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Earth Bonds | TH000320BFA10GS010_BOND09 | 120mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
0063af55-cf76-5450-8c84-a573bb7b071f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Earth Bonds | TH000320BFA10GS010_BOND09 | 120mm2 1C Cu PVC/PVC GE/YE | Test Results
571dca16-0c00-4738-8934-83a38595e191 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Earth Bonds | TH000320BFA10GS010_BOND10
455424b6-728d-4260-803c-5a1f9e015d5b |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Earth Bonds | TH000320BFA10GS010_BOND10 | 70mm2 1C Cu PVC/PVC GE/YE
07eaefee-bb9b-5d28-8889-6c7d9e25b310 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Earth Bonds | TH000320BFA10GS010_BOND10 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
4f265e83-8177-515f-b3cc-f4868770173e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Earth Bonds | TH000320BFA10GS010_BOND10 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
4c361d7e-d04f-41e3-a828-8176fde01f26 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Earth Bonds | TH000320BHx10GY101-E01
e7cccd0b-20b2-44aa-8a3b-06117176a607 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Earth Bonds | TH000320BHx10GY101-E01 | 120mm2 1C Cu PVC/PVC GE/YE
fa0e7735-34df-5151-9851-75c52bce97fa |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Earth Bonds | TH000320BHx10GY101-E01 | 120mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
6d330769-376e-50f9-b554-3840581d3094 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Earth Bonds | TH000320BHx10GY101-E01 | 120mm2 1C Cu PVC/PVC GE/YE | Test Results
d55feb05-151f-40e0-9c97-06537fb46740 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument
11be20b4-23a1-4fa3-b85d-58d0c6a06ee6 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter
b2919e39-364b-4e5d-9c99-63b5900edb20 |  | checklist-flat | not-started | ITR-CL-1-128 Temperature Instrument Installation | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-128 Temperature Instrument Installation
f658887e-0dd8-5c70-bc76-ce22a5ccd874 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-128 Temperature Instrument Installation | Temperature Instrument Installation
3d957370-803d-502d-9d36-9f7581c71511 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-128 Temperature Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
71bbcdbf-a2df-49f6-84b0-03001c00b913 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-122 Instrument Calibration
b7a748e6-0f10-53fc-a80f-a39368405e6b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-122 Instrument Calibration | Required Data
ba233e20-7461-5225-a742-fbb9464f831b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
72638c34-adf9-5aaf-9537-a0221f531bee |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
34470290-6b69-4846-8fc4-0701ab0e0f74 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning
acce95ae-ff6e-5925-b429-94fcd7de90d3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
2bdca142-b5fc-5eb5-80fc-63287b2df8ae |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
8aa8a9e6-0313-5fe5-be86-9334ebb7f54d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
f1a0b5f5-94ab-5cb4-b875-a4191850933e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
e7a1a399-249c-529c-b9bd-b839c7fec065 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
8a37c2dd-06a8-5e72-92bc-c0ee474c784d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
72f3a0d8-b17c-5d65-a7c8-d169eb631918 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
92d20762-e31f-56ce-8b58-3bd9ca1f7bdc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
3bb8efd6-1a7d-5a57-b56f-4bf520191a1b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
700ce8f5-dee3-5b24-ae8d-2f3eda345283 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
75f2c3bc-ebb5-5481-af84-b9708156754e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
10b8e443-4536-547d-aa8c-4a2fbd5c97a4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
1195f9dc-2416-5726-9f13-2ee776a729a5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
920394c2-907e-5f5d-a853-4531aa4cd28f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
2c7f242d-b8dc-5571-8754-27ea8e25959c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
a44e8e24-5fa7-5b85-8135-c5f37ad9c4c6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
d8356258-7d09-502d-818b-f080426232e6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
df019d8e-e81b-58ad-8a48-7800c7c9982a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
4b4ed9f6-ab33-5a60-a62e-6c5ebd6edb38 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
fe69d860-a0bb-5906-9018-c046e10c2697 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
9bc34e59-dbda-5cee-bfc3-19bdfad70291 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
78083719-0a6e-4a40-ba9f-835ee90b52fa |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments
39ea497b-675a-55f2-998d-aad0035de2fe |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Required Data
59c08c87-90f7-5c2b-a38c-74d1a76b59cf |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
d5f64f16-b7a7-50b4-ab3c-0747f267723e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
8f1c3d97-fc1f-506e-acb4-c5e1a584ae19 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
3fcfc9c7-167e-57c7-a2a7-050034ce0b94 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
03a466cc-e47b-5a2d-9731-f038258d03f3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
bb6c1721-85af-5df9-bd84-79caa07afaab |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 1
262e22aa-4b95-570e-925d-fe0dc23a54e6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 2
463f81a7-5249-55e7-9faa-0657186db71b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 3
c9e9c8ab-44c0-5fe1-82d0-3dd1353413ba |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 4
1b921a65-cd6e-5189-9784-fe1affb44888 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Calibration settings
25f14e26-f2d3-5e81-9006-785b8b5405ba |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00L040NDA10CT010 - TH32 Wellpad Header - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
4b32c3c0-b7d2-4843-b425-9e58df77e9a2 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter
6d02fb99-00c7-41cd-9b0c-f9fe14a8ce5f |  | checklist-flat | not-started | ITR-CL-1-130 Pressure Instrument Installation | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-130 Pressure Instrument Installation
7552115d-f506-5e41-a09e-50daaafbe4f3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-130 Pressure Instrument Installation | Pressure Instrument Installation
15d8f289-6f85-5587-b3a5-b5b010afafaf |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-130 Pressure Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
a15cb731-0e5d-408d-80a0-2778a937b71d |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-122 Instrument Calibration
f3441d87-5b5b-5ca7-b988-7e146a04d9b9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-122 Instrument Calibration | Required Data
3787711e-7b52-5f35-8289-d857d63e0d82 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
7ce7d0a7-b303-53be-8468-9730132d3ce6 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
38a0a3ad-2c84-433c-89e0-561d877cb46f |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning
77b716a3-3f26-59bb-b0f8-9f9097785dd7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
0fa99fe9-ba93-519e-9715-9fe958ce6459 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
b9348876-dd87-5c5f-aaa8-4294adf40cd5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
4af5fa5a-b3c1-56c8-b0c7-7d67392f6f2d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
b5a23a56-1138-5b9a-bfe2-beaeb4143ede |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
748e5f14-2b36-51f2-8315-ae1c51c2e529 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
70090745-15e9-5a31-a049-2e6f59d68622 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
f8ebaa28-ea4a-543c-8cf7-5be1431abf4f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
49fbccc5-7574-52d4-b97f-956df4fe9d14 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
29ff5abc-39ef-5a72-b924-00df1cbd8f58 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
4e372dae-9e47-5ca6-a79d-aca8977fb8e7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
14e3d220-066f-59f9-bd8b-1a7bb1ed8fea |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
e5444dc3-179d-56a7-93e6-07ff39f2ea99 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
26ebc18f-910e-5f83-a35a-d46e0f1d2465 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
54ec49a2-8587-5712-815e-d4a037785409 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
b0a97782-331a-5df5-b95a-a6f781ad3bd9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
4af2d85b-7177-5342-aa5a-05b8d830607d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
d64c21f4-9d8e-55c5-baf8-2a232faf3cdf |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
b20d3a97-b02e-55c0-9a9a-f7117a56e49b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
74fcf07e-2c6f-5665-8010-b65345e45a1f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
b539c9f8-99bc-584e-befd-ebc948277107 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
e2014e79-0dd4-4d40-9558-6df14a38bbb8 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments
023f7dde-3865-5a99-bfc0-d917cef55dc9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Required Data
d5a6a3d8-b9a4-5afa-bd60-3fc399dfdd2e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
55ee3c23-8d53-52a4-8af5-46fe45d5b230 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
540ef280-f134-5a56-8567-e680ff23018a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
a144cc2c-f72d-50d0-943b-eb55b1e4b04e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
c6e1905d-708c-5e09-aa48-71567da99785 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
eaa798ec-84bb-5014-97af-c7ff479865ae |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 1
a7107fef-4166-5268-8b8e-6fe170768748 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 2
e8cf22de-f3b5-560c-895d-dde91f2a83e5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 3
a59e2fc0-8077-5c40-a15c-0be143de9299 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 4
f7e7bc51-e4fa-5e71-9cc8-37e6c5a5757f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Calibration settings
4a671aa4-042b-5e53-a880-c37d2876b310 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP010 - TH32 Wellpad - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
2359218d-3d33-41a3-a17a-4e3749e205c1 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter
fb43b2c6-d0ee-4ed9-8645-f98bdbaaf4b6 |  | checklist-flat | not-started | ITR-CL-1-129 Flow Meter Installation | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-129 Flow Meter Installation
eca8a706-fed4-5168-8f6b-4b0ae68618d2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-129 Flow Meter Installation | Flow Meter Installation
23b63de3-bd6d-5c37-8536-6a332914d6ae |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-129 Flow Meter Installation | All relevant signatures (Installed by, Approved by, Client Representative)
f1b6dec5-44bd-49cf-a188-815022a2ef95 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-122 Instrument Calibration
7ba58cb8-d605-5c68-9231-d181507e009e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-122 Instrument Calibration | Required Data
91ab14ad-7846-5db4-a650-ba970cdbe570 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
5cc2479b-4c2f-5250-a45a-f8f6c696484e |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
6ad4fef0-6263-4c13-b3be-399323bf482a |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning
91b817ad-27a7-52a1-9ea1-86d69967d134 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
235a28e4-d90c-563f-adee-dd45cb515e60 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
1ff62979-f87a-5f9b-8ecb-f424e9d9db43 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
9621468b-500c-5a9e-b9f7-8b1a83b73b29 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
378407b2-9f34-5016-8a42-abcd4f502895 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
158ce40c-16a5-5f6d-8319-c5dde86f7214 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
8d92c4e5-4452-5670-8196-61c7d8beb9cf |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
0dddd12f-3925-513b-a8a2-4f7f2b42ed32 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
8777d919-8ac5-5c2b-b046-ffef07d1bedb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
43bb2b1d-82b3-5e0e-8145-6e4360e20c45 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
52f795e7-ff25-5166-b2b1-ba55ddfc247b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
578148c2-17f3-574a-aa9d-027bae61d3ce |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
03ede8c9-0e2d-50ba-9008-4106b506168d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
88ef4dff-500e-591f-8de6-87fbfcc584c4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
9999aa55-c5c8-5bd3-b0ea-96ebba1cbe9f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
1a51959c-bcd8-5c1f-93b8-1131f9576735 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
15dc1889-543d-5cec-bf28-4358e936d20a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
88089c91-0588-5c4b-9f95-8b63fe00d159 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
e1b87025-1399-5e1c-83be-3717b92acff4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
ddb3deba-1f3b-5675-ba05-9df59f10f9af |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
11f00e7e-7c81-5958-b971-d23fa1c97dcf |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
54e2e6f5-372f-44e4-8911-9b458f0fb276 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments
07d2c6aa-cdfb-5290-b817-0866a662cb71 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Required Data
36f8c470-e7fa-5d3c-a6af-04c7b9db24b7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
9372d82a-633e-58cd-a99b-19ee57701f18 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
1edfd212-f8d6-53e8-a7d4-637beae6f993 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
600e2d75-8b3e-5f41-9826-c5edc1f3310a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
b7c1fc64-eafd-5a13-adc4-44e4041bd733 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
4e13247e-8945-53fa-a90e-629f53e2ff15 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 1
9f61a7aa-683e-57f1-a1c6-c5049df62bfc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 2
0aae0af6-73f8-5f28-8fcb-5473c2316d44 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 3
6342d761-6f93-50b9-93c1-f0e5f8b9057e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 4
cc9360b3-109d-5658-9d8f-66de47eecd4d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Calibration settings
fdbda4f4-4ff1-5370-833d-2bb946759dd2 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | H000320NDA10CF010 - TH32 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
f0918851-8944-4fb7-a902-87fe974a059f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter
e7b021b4-2c6d-41bc-ac36-dbcf7d8c7a9a |  | checklist-flat | not-started | ITR-CL-1-128 Temperature Instrument Installation | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-128 Temperature Instrument Installation
deb5b393-6910-5ba8-a696-d846373f3239 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-128 Temperature Instrument Installation | Temperature Instrument Installation
039e3707-c60a-5bac-8b4f-f7c855b8eaeb |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-128 Temperature Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
d47c5bc7-0441-4437-91b5-e088b8c53bcf |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-122 Instrument Calibration
8327a1f2-2f04-5ed2-8a3c-c1180ed2530e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-122 Instrument Calibration | Required Data
a0d0add7-c7fb-5295-98ee-7d363755cd46 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
16b54d5b-1149-5628-be4c-0e96f6833ad2 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
79ee1ec8-d2a7-4f7f-b990-ed442f78a09c |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning
f97934f9-c531-5ac1-82a3-8d85e5834c2f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
09e550c7-7e17-58c2-afdc-d8dea262f8cf |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
3229792f-4be2-5a0e-9807-173f6ae42c98 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
8c859c69-1ed8-5615-9651-a76f2f39b250 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
2b7ad7c6-826f-5fa2-8eec-ed6c85c1dff7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
af3aebc1-4b25-5dd2-9534-e23dd76612ce |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
42509843-4ba1-549b-82df-c6badc9efb60 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
fdbab941-5e81-5684-91a0-ff5c2dcae581 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
e5107cbb-8450-5d11-8918-bd31db55d06c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
80e5899a-3560-55af-b510-91bf0b557c76 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
6c819dea-6042-53a9-899e-2de6418c6b0c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
d75ce5eb-51b2-5551-8f01-af3ec317ecda |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
3acfd9f2-8114-5813-9ae4-c070ad3a48b4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
90d84511-da0d-578a-aa9b-bd6025879ae3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
d15500cc-4945-5aef-9222-8bf529e3e0a3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
e68e9bca-8f15-5b3b-9a4a-2390f522c59a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
2b59ae95-bcb3-59ee-99c8-a4beb7827a1f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
8b53fc94-8b96-5fc7-8392-cc316cc07618 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
6817f194-551b-59ce-b3fc-e6c6bb113371 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
83c9d5e2-eef6-54bf-b543-3c705fc5cdb1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
12eecf99-5e40-5fd5-ad52-1db16e9859e6 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
4c7911dd-8c1d-46b5-a4b6-7394aee13706 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments
ae9b4ab3-e635-58fb-8c37-a49d3f9c56bb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Required Data
8dfeb100-9967-50b8-88a1-7d8bef0a5d4f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
5ffd1393-be0e-5738-aed4-a0371b28a820 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
9e879268-1df1-5c27-a56e-6c9fa82f679c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
b67726d2-8412-533a-a6b1-53bb76ef33fd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
2730a293-1e6e-5381-99d9-2e537b0fadff |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
6385e18f-0d49-5ee7-ad97-2f2389fe4ff5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 1
6f2faf99-23a4-54e2-acbb-9ac8076de3c7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 2
8b13f520-2f5e-5750-8bda-69efea985096 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 3
1f4b7c2e-efb3-5f34-8e5f-583cffb5d7ca |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 4
9b7f17c6-da7c-5a80-a4bf-2e196cdea84b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Calibration settings
069ccab8-d8ae-5899-974d-ea9d18b67b31 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CT010 - TH32 Branch Line - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
a6be1bcb-c057-4258-9678-1655d92d291b |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter
dd5f7827-c1b8-4334-bb35-a4733232cb70 |  | checklist-flat | not-started | ITR-CL-1-131 Level Instrument Installation | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-131 Level Instrument Installation
3872a4ae-7b9c-5bd1-8e27-52e968d32221 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-131 Level Instrument Installation | Level Instrument Installation
334247d9-93c0-5c72-8772-e2753ed82310 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-131 Level Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
a7f72e4d-2466-4069-946e-c9078dafc1f2 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-122 Instrument Calibration
6d23c02b-01d7-5b9c-a213-e247f18de81d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-122 Instrument Calibration | Required Data
71d5543c-14e8-5f26-85d2-717ecf17c13d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
f76b2d98-80d1-5bcd-8d0a-c948bbc7f24d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
ef414dd8-4919-4f24-a5d7-e4fb6732e7c7 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning
2d993202-b6e1-5d18-a70e-286b2c5b73fb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
f8336a02-6524-5419-8ba3-147e59703f91 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
6acda3a7-ee07-548b-80ff-6fadec3e4f7c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
0f983579-c106-5371-9340-1a3fbf399cc0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
6b552087-e05c-5e72-8e8b-6a78c8cdf650 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
71cbe55a-ffb4-5e57-9e33-f1a64b225024 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
a13be800-638a-5943-b792-44d18fd9560d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
5c6befca-f3c2-52c5-8306-ed60624335de |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
db3e7807-94a6-58b1-a439-d747f060e594 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
ae9ddddf-f1e2-56d8-9b9a-9023a1f654a4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
1fdd249a-8e03-5b2d-83ea-f4b65796818e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
cb757e44-f438-5c8a-a0e2-0267abc4bd18 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
ecc5bbed-53f1-57cf-b748-4ad290c59dad |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
07eea303-3006-576a-b736-36ad50970af8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
7c198037-1395-5c46-93bd-f567bffbcec3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
07fbcf84-d7c2-5401-97c8-8404347c7278 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
9c2bc699-464e-5853-ba09-f53e688b6db9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
2f033eed-4317-5fe8-b846-dfdd37dfe391 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
b3789b89-ad86-51b0-a2cc-a08d4e7fff54 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
c7e120e1-1cb7-59ce-bcbb-1c7e659e5b1f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
9d110083-d011-5b3f-9974-ea33b843e8de |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
1b3d101b-ba95-4c65-b555-2796649b4926 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments
5fabb9f6-bc50-5119-9437-8b6948fbb54e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Required Data
9e680854-20f9-557b-a28d-1b6bc0de1983 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
bb6ead69-961e-5186-8341-46124771fb88 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
32100e57-f1b9-50f0-844d-ac3c1a2c9095 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
1df4d4e6-517a-53ef-96d7-83c806de921b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
5b5678d5-2144-5210-8f82-2edce84c61fd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
45928475-f335-57ed-9f5f-3b6a73b2ea41 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 1
42f285f3-babb-578d-ada7-728191756261 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 2
bf29c661-1b56-56a8-bdf8-039033c47007 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 3
7f2a57de-3e1e-5e47-8f8c-cda2537d9987 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 4
bd9cbc40-7669-52ab-89ee-a3e03ffc79ee |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Calibration settings
5ed5c3db-bd8b-5403-986d-d302b7d2ce4d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320LFC10CL010 - TH32 Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
02b205e0-5965-4ec0-bd5e-262d2f7401e7 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter
1ff69f11-eb2c-45ed-ba0a-a23716b06f03 |  | checklist-flat | not-started | ITR-CL-1-130 Pressure Instrument Installation | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-130 Pressure Instrument Installation
cee1c2b4-b497-5ee4-8849-b1126d99a4f2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-130 Pressure Instrument Installation | Pressure Instrument Installation
0d9eb715-eda5-554f-a0b4-61500d747f26 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-130 Pressure Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
f89fe4e6-30d3-4b7f-8137-e0f8947bda96 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-122 Instrument Calibration
eade6e90-bde6-5795-8449-943c42b9f836 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-122 Instrument Calibration | Required Data
f73c3226-7d87-52b0-86f8-b6cbe0a8aa5e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
7f80f72d-729d-5999-8ea2-0d7885373954 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
d04edc1b-70f5-4719-b135-b1019512fb03 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning
7abe2586-0248-5df4-a64d-cafadf7319ce |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
a72ed1b9-6d97-544e-896a-2dca9b305e15 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
6e0b7724-885d-5323-840e-0454b9296229 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
006dfb14-606c-512a-abdd-6322b86c3584 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
bfe637ed-22f0-5899-abd1-baaa3145749a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
d804e951-6167-5822-8cce-c53e558ea156 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
d5b9a4d1-53e7-56e4-be95-9df51f42733f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
dd7f75f9-60d5-5d90-828c-29749b48510f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
e51115ec-154c-5bf4-a1be-86debe65f2b2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
7c44fe08-11ef-549b-b5eb-86eb4dbad4d4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
8d7d9323-c90c-5f0a-8b6d-0f1da52759c9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
9351a6ff-e276-5735-a9d1-0aecc6fa9746 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
23e3acd4-700d-520b-ab21-4ef44e452937 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
822ee7e1-f862-5593-b300-9b6da73e4ccc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
8eb33892-54d3-5c86-9467-675bf68debb6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
d7f48576-e5b9-5318-9e06-6b944357c43b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
1ed11fca-16d4-5d95-bac1-cf690afe9abd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
22ffaff8-2df8-5485-8670-8b35cda71920 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
ec0e361f-ebf2-51e8-9eb3-ef6eeeee5a16 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
5d129ddc-4a12-5fa2-ae5b-4d021d409531 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
7c8c39a4-a1af-5a5b-bdf1-a2aac3def3bc |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
92687a89-3177-4836-bb75-559abcdd8054 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-124 Commissioning Instruments
7a5efa92-d599-5900-9a55-c87e5b401145 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-124 Commissioning Instruments | Required Data
77d6d060-8dc2-597c-aa3e-268f214bfe16 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
acad7452-447e-57bc-b97a-8f765863fe32 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
50a3350e-c28f-50ee-816e-fb54a08e3241 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
d22d1402-c250-5d79-8308-c3579aded994 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
6bd160e2-998f-53ed-87fc-0603d39df74f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
a5227004-3fbc-5942-8cee-f394b948a15c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 1
574f363e-b59c-55d1-8182-03c7646b084f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 2
37609813-23c2-5653-bb8c-070c79ace6a6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 3
51d23681-b99d-537e-a8a2-18e85d9dbd9a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 4
81954adc-f6d7-50f6-824b-e2c60c89ae26 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-124 Commissioning Instruments | Calibration settings
eb5d1796-1f2b-556a-ab8a-e16c317b4cfc |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH000320NDA10CP020 - TH32 Pressure Indicating Transmitter | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
4e95894b-440a-4435-9573-6480fef15f5a |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve
2aa925a0-4a54-4e2b-847a-78b19de5f7c9 |  | checklist-flat | not-started | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation)
618cce67-e483-5bc3-938a-0496462fdec7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Equipment
4e990106-251d-54e5-b225-04f69ed5a68c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Valve
57e0ce09-e705-5c4d-b216-b98946b4ac46 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Actuator
21ffeb1a-e367-5a9f-a946-dbec18868301 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Positioner
a13b973c-b843-5228-96ac-63c7c74aa09e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | I/P Converter
a9399be7-c93c-5bfb-a9a5-5b7607ffac43 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Filter/Regulator/On-Off Valve
0dbbb69b-4734-502a-8ecb-fcb3978c222a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Fail Action
59313a19-d6c7-5525-9d75-eb7475c19c09 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Valve Field Calibration and Hysteresis Check
3e4fb214-22de-578d-84e8-e004f953e543 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Proximity Detectors
343605c8-b85e-59bb-bde8-9d51be3bcba7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Solenoid Valve
2adeff34-fa7a-58cb-8267-ec1bdd884241 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Pilot Valve
80700dbf-2953-580a-bc0e-76d046ca72d7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Hydraulic Actuator
fc8e5adb-7ca7-567d-a891-29db7ff5039c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Accumulator
fa56c702-792c-58eb-a121-1275f6c1589a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Electric Actuator
6925b79d-c4f0-587c-89f2-47c368a768c0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Miscellaneous Equipment
0ef9c9b8-ae80-5c0c-82db-29cee33cc2fe |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | All relevant signatures (Installed by, Approved by, Client Representative)
37251622-c9a6-46c8-92f9-33834e3efc0e |  | checklist-flat | not-started | ITR-CL-1-121 Instrument Installation | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-121 Instrument Installation
51e10a88-248c-58e7-84a1-117983170ad9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-121 Instrument Installation | Instrument Installation (Mandatory Photo)
477d420c-1014-5b29-af21-9b30d4db6b54 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-121 Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
c67077c6-e226-47b6-8add-73e2d3360756 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-123 Instrument Pre-Commissioning
5ab11cb3-9d2e-5bf0-8e78-96049534998d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
ff5bd6b1-0be7-5376-97b8-3d11c9cb6481 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
998e8b93-c711-5994-9cc3-fa116219b250 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
bab3f0ce-cd8b-5e4d-b59e-23cfb58def61 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
58de513e-8716-5947-b164-5a00da9e25a6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
787b28a2-97c1-524e-beed-1419fcc71eb9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
0dca68b7-f1e4-5446-b168-6c431540552c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
7e029d64-071e-5603-bb4f-d10eef674bdb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
bc27f2cb-b273-53bb-b5cb-41016f823322 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
be10cffd-05df-5ca0-a4b3-8bcd1ac02710 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
df7b9c48-86d4-5536-8921-60a8699c3851 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
69312a18-fe34-5cc7-a66d-a81877e8f868 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
3fc1318b-2984-5043-9200-e1094d5d11e5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
1c2b226d-f7d0-5f7a-84f4-3883a6496749 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
79c58dc1-f046-571f-8eae-0473e5abca6d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
f4cb875d-a0c8-5552-8236-a43d21716d72 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
5ee90ecd-7def-50c7-9289-db4b55cfd6f0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
16b99a62-c814-50b8-9175-4a9d71a40c4f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
bd479c63-76c3-5b6e-8447-39b79a629831 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
73701fda-15dc-5858-9d7f-1e53cf66b73d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
86d0f9e3-5c56-5e91-80ac-68dc07dd0040 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
6b4213fc-2069-42a1-8e27-e079853de96a |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-124 Commissioning Instruments
b9debdf9-59a0-5e64-8ba0-2288a40ace9f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-124 Commissioning Instruments | Required Data
b43951f7-c1b4-5151-9af7-2a41e71ed95f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
2808298e-2e2b-5af9-b33e-9ed9aa3e35cb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
f67d6710-ad2b-50f4-97e2-7987a60fe696 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
22e71a5e-6ffd-5418-806d-e22c9b980100 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
1a4c374d-79f7-55f4-8cce-8252532301e9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
6b88a265-1d5f-5a69-a6b3-7d3dde63453b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-124 Commissioning Instruments | Set Point 1
a00b7012-4f75-5a9b-9b47-26041947fd85 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-124 Commissioning Instruments | Set Point 2
b4c7db78-98d8-5e5e-af5d-bb9e3d19ca33 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-124 Commissioning Instruments | Set Point 3
10922548-ee8b-577c-a675-947a442ff56f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-124 Commissioning Instruments | Set Point 4
222ad7a0-0097-57c9-b6a2-496d93139447 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-124 Commissioning Instruments | Calibration settings
5205f5c5-1970-57d7-81cb-994dc546069c |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Instrument | TH00LO40NDA10AA010 - TH32 Low Point Silencer Purge Valve | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
520c8bf7-aaa9-4f60-a2c5-f729d7913ab0 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables
73bc32c5-2191-484f-9d6e-9feeb0791ed1 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | Junction Box 6
81da135a-bdbb-4b4f-b6fd-1f39c1ffad8c |  | checklist-flat | not-started | ITR-CL-1-106 - Junction Box | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | Junction Box 6 | Junction Box 6
dfbd087b-7e0f-52a2-8b8f-354fde472063 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | Junction Box 6 | Junction Box 6 | Junction Box
c5ef1698-f60d-4056-8e6c-c49572c652a6 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320BHx10GY101-A01
fc0bd975-7ecb-4c3a-9d96-4cca601c2185 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320BHx10GY101-A01 | 1.5mm2 12Pr CuSn ESCS
8e53bd13-0727-54dd-b133-3635986a1061 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320BHx10GY101-A01 | 1.5mm2 12Pr CuSn ESCS | Instrument Cable
e7d7fe71-c850-5e6c-92b5-ddc7a093c1f2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320BHx10GY101-A01 | 1.5mm2 12Pr CuSn ESCS | Electrical Checks
ab6fa00a-0af8-4860-a956-b3f882103d17 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320LFC10CL010-A01
000525d1-4d40-4662-a1bd-37aacc59e952 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320LFC10CL010-A01 | 1.5mm2 1Pr CuSn CS
845f3f3d-f097-5b65-8cc9-13074d307eca |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320LFC10CL010-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
58ba255d-c6e5-5027-bc14-ed853f26cdd2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320LFC10CL010-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
52a64719-c872-4de4-9e24-ac614d73a590 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10CF010-A01
58dc3183-ef01-4e29-b7c4-75aba4eb870c |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10CF010-A01 | 1.5mm2 1Pr CuSn CS
abf16e3e-28da-509c-8737-3225e65bf868 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10CF010-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
4c0e1488-6633-5d57-9d6f-d00624cce648 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10CF010-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
c252bb0a-a749-415b-befd-ad6168d32528 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10CP010-A01
cce94fe1-9594-42a4-b4b1-67f6ee51ee9c |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10CP010-A01 | 1.5mm2 1Pr CuSn CS
497db728-1f54-5d12-a2a6-3fcef5e11323 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10CP010-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
7707448c-2ba3-54fb-aeaa-0ec2ffa49e0c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10CP010-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
16f49f3c-3854-429a-985e-095b6a55bed4 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10CT010-A01
1c86a840-7b12-4987-9b9b-ae65c032426a |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10CT010-A01 | 1.5mm2 1Pr CuSn CS
4d97e670-06a6-5dfd-8dd6-a8c3d51dea69 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10CT010-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
bcada088-5fbe-56fd-83ff-b25b8ba0f53c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10CT010-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
9a15accc-0dfd-43d0-a745-8f07025bc1db |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH00L040NDA10CT010-A01
5d6ebcc8-50f0-4067-8c19-e469b4ff0394 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH00L040NDA10CT010-A01 | 1.5mm2 1Pr CuSn CS
d2d7af94-e55b-5f95-88c8-3b73cf2d4696 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH00L040NDA10CT010-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
78c7d43e-34e6-50e0-997e-1fe27d804acd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH00L040NDA10CT010-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
048ef90a-334b-42b6-8ffa-4c7ff01e2118 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10AA011-P01
d5c61ce7-d87d-45a2-88f9-22ae38ba4f2a |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10AA011-P01 | 6mm2 3C+E CuSn XLPE/PVC
37b3e964-1227-5551-8aa0-bdd8add81b71 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10AA011-P01 | 6mm2 3C+E CuSn XLPE/PVC | Low Voltage Cable
378d4999-bb7d-5a42-9ea8-1b7b27f92702 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10AA011-P01 | 6mm2 3C+E CuSn XLPE/PVC | Electrical Checks
76dacff7-9ec7-5f2a-a372-a6915c5e7fa9 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10AA011-P01 | 6mm2 3C+E CuSn XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
839f7a80-64b3-43a7-bdfd-d95d48f66b9b |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10AA110_-P01
22c2fd81-8471-448c-91dd-2d7dea9fdda0 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10AA110_-P01 | 10mm2 3C+E CuSn XLPE/PVC
b70cf023-cf2d-57c3-8dbc-dd61d753846a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10AA110_-P01 | 10mm2 3C+E CuSn XLPE/PVC | Low Voltage Cable
540c2c2a-6363-57f5-87af-6b07e01a7085 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10AA110_-P01 | 10mm2 3C+E CuSn XLPE/PVC | Electrical Checks
24aebdd2-ad7d-514b-b8c2-965ad250c107 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10AA110_-P01 | 10mm2 3C+E CuSn XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
5272f000-1df3-4ea6-885a-c7aefe1baba9 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10AA011-S01
0a037fff-bcbf-490a-8519-c904d58d96d1 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10AA011-S01 | Profibus DP - Grey Sheath
27e12a5b-9835-533e-9477-61672361e3c3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10AA011-S01 | Profibus DP - Grey Sheath | Instrument Cable
e993c84d-b63f-51f3-a8dc-4067a9b8ad9e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10AA011-S01 | Profibus DP - Grey Sheath | Electrical Checks
0c8c64bc-9f29-428b-98aa-6fc738c63cf8 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10AA110_-S01
f785ba69-fa81-4171-9b18-9c09a06e04ff |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10AA110_-S01 | Profibus DP - Grey Sheath
b95ac920-3dfb-57e7-97ef-844de80582f7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10AA110_-S01 | Profibus DP - Grey Sheath | Instrument Cable
7ffdbb5d-e887-58a0-8b74-6c61d68a5776 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Cables | TH000320NDA10AA110_-S01 | Profibus DP - Grey Sheath | Electrical Checks
6d599bd9-294f-4e3e-b388-adcf71118cc1 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Fibre & Comms
096338f8-d670-4542-aeb4-e0ce4e01e586 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Fibre & Comms | TH000320CRA10GH010-F01
199abe37-4ec5-4df0-b7a4-fca74798d432 |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Fibre & Comms | TH000320CRA10GH010-F01 | 24C OS2 Cable External Armoured L/Tube Gel PE/Nylon
5950d7d7-1db9-5b63-b8e8-03ce9549a7da |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Fibre & Comms | TH000320CRA10GH010-F01 | 24C OS2 Cable External Armoured L/Tube Gel PE/Nylon | Fibre Optic Cable
d3b914d7-cd64-4cec-af16-b497b1ef9bfc |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Fibre & Comms | TH000320CRA10GH010-F02
92223562-9405-4080-96a2-9e757493a029 |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Fibre & Comms | TH000320CRA10GH010-F02 | 24C OS2 Cable External Armoured L/Tube Gel PE/Nylon
6f21da6b-d943-5461-aebf-f2d3dc107a5d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Fibre & Comms | TH000320CRA10GH010-F02 | 24C OS2 Cable External Armoured L/Tube Gel PE/Nylon | Fibre Optic Cable
a428e19e-4d76-48cb-9950-7409ae069532 |  | checklist-flat | not-started | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP-PTH32 -E-002 TH32 Process Equipment | Certificate of compliance (COC)
0dc65fbf-0cca-5dbd-b516-ec0a481cfb44 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-PTH32 -E-002 TH32 Process Equipment | Certificate of compliance (COC) | Please upload Certificate of Compliance here when complete (COC)
21c26744-4aef-46fe-9384-54a656417623 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-003 TH39 Field Lighting & Power
9ba192d8-8a39-4d42-b2b3-b166196272b5 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-003 TH39 Field Lighting & Power | Cables
861067b3-c178-4613-95df-3dd76c0a5223 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-003 TH39 Field Lighting & Power | Cables | TH000390BFA10GS010_-F53-P01
11cfb7b2-2548-4080-b899-6bb29d72b4eb |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-003 TH39 Field Lighting & Power | Cables | TH000390BFA10GS010_-F53-P01 | 2.5mm2 2C+E CuSn PVC/PVC
8d35f791-5f1b-5061-959d-6801f608f08e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-003 TH39 Field Lighting & Power | Cables | TH000390BFA10GS010_-F53-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Low Voltage Cable
b8c9f310-c7f6-5505-8e6f-dba4621319e2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-003 TH39 Field Lighting & Power | Cables | TH000390BFA10GS010_-F53-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Electrical Checks
ac9e3417-83af-51b9-bc9a-54280f70adfe |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-003 TH39 Field Lighting & Power | Cables | TH000390BFA10GS010_-F53-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
7a0389cc-9e76-4cfd-8a32-d7f48ecd9ce5 |  | checklist-flat | not-started | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-003 TH39 Field Lighting & Power | Certificate of compliance (COC)
6385b08c-a553-579f-96b4-a666f110e573 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-003 TH39 Field Lighting & Power | Certificate of compliance (COC) | Please upload Certificate of Compliance here when complete (COC)
127002e7-17d5-43a1-a9d9-c6ac44ea2c47 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power
869d7f13-699f-4b5f-aaf9-584722a164de |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut
9ea5b745-d01d-4b71-885d-7eda56ba2eff |  | checklist-flat | not-started | Cable Pre-installation | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | Cable Pre-installation
c79d1f69-ca7b-5802-a17f-4f844a0c4ab6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | Cable Pre-installation | Cable Pre-Installation
35287d1b-15ba-42f0-b975-e91f29589aa2 |  | checklist-flat | not-started | ITR-CL-1-101B Cable Supports Above Ground | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | ITR-CL-1-101B Cable Supports Above Ground
56cbdfeb-cdc2-55f2-82e6-dbdca00bf517 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | ITR-CL-1-101B Cable Supports Above Ground | Cable Supports Above Ground
17af9712-a217-49c0-b95f-867040859594 |  | checklist-flat | not-started | ITR-CL-1-101A Conduit/Ducting Below Ground | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | ITR-CL-1-101A Conduit/Ducting Below Ground
ea84e968-6894-5917-847e-0d59abe32087 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | ITR-CL-1-101A Conduit/Ducting Below Ground | Conduit/Ducting Installation Below Ground
ffa31711-87a5-40d8-bb4b-4e91cc1197af |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | ITR-CL-1-111 Electrical earthing
7e0ba13f-5597-5d8a-b596-5b653f2b7985 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | ITR-CL-1-111 Electrical earthing | Electrical earthing system installation
0038798b-cc0f-56e8-8f56-a5098ae3a74e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | ITR-CL-1-111 Electrical earthing | Test Results
a5f7eee4-2400-460c-9962-04008cdbe4b6 |  | checklist-flat | not-started | ITR-CL-1-108 Electrical Switch Rooms | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | ITR-CL-1-108 - Electrical Switch Room
14bf2b71-e9be-5405-8af0-f5879556a241 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | ITR-CL-1-108 - Electrical Switch Room | Electrical Switchroom (Mandatory Photo)
35325023-f554-4638-8048-f2d0a1573272 |  | checklist-flat | not-started | ITR-CL-1-102 Entec - Distribution Board Installation | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | ITR-CL-1-102 - Distribution Board Installation
cf5602ed-0d1a-59e1-bc6b-89ffb11d406f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | ITR-CL-1-102 - Distribution Board Installation | Distribution Board Installation (Mandatory Photo)
9296bc6f-2ce2-58e3-bc08-1c3e99fe0352 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | ITR-CL-1-102 - Distribution Board Installation | Test Results
94ce37b4-4e94-5f19-ba34-b80ce9121118 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | ITR-CL-1-102 - Distribution Board Installation | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
9f52e55a-72a0-4d41-861e-b4b67f4c7a7b |  | checklist-flat | not-started | Cable Test Record | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | ITR-CL-1-103 - Schedule of Test Results DB
b1e6c6f0-4d0e-5b01-bc2b-ff1e39367a71 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | ITR-CL-1-103 - Schedule of Test Results DB | Upload completed ITR scans
7ff56b9e-2674-4ada-9f3e-ea345c1917c3 |  | checklist-flat | not-started | ITR-CL-1-109 Electrical Equipment Package | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | ITR-CL-1-109 Electrical Equipment Package
586a13d7-e290-53f9-906f-c2fca4eaabdb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | ITR-CL-1-109 Electrical Equipment Package | Electrical Equipment Package
cf56f942-9651-4ad6-b8e4-7b64522c7c52 |  | checklist-flat | not-started | ITR-CL-1-100 General Electrical Equipment | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | ITR-CL-1-100 General Electrical Equipment Install
35b17183-433f-577e-ba69-8683639b9948 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | ITR-CL-1-100 General Electrical Equipment Install | General Electrical Equipment
997aba78-5802-57f0-bbd4-59e490f17708 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | ITR-CL-1-100 General Electrical Equipment Install | Electrical Checks
39979eb7-ae3c-507f-b6bf-8ddcf92fda24 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | ITR-CL-1-100 General Electrical Equipment Install | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
197455fb-35f3-4db4-a996-d083fbb76dca |  | checklist-flat | not-started | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | Certificate of Compliance
327d56cd-5c4d-5377-b317-5b2db8f97f67 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Well Hut | Certificate of Compliance | Please upload Certificate of Compliance here when complete (COC)
9ac4218f-eca2-4830-a34c-32b5e44462d4 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables
7cb6ea02-5f57-47a0-a720-cdfee7106c66 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F01-P01
d77ef772-2e72-4bc8-8312-9576514d38f9 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F01-P01 | 95mm2 + 25mm2 4C+E CuSn XLPE/PVC- TH39 400V Main Incomer
2906606c-78b1-52e6-941d-e58b9076f6f0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F01-P01 | 95mm2 + 25mm2 4C+E CuSn XLPE/PVC- TH39 400V Main Incomer | Low Voltage Cable
a6b16462-1d73-5d96-9154-312daef5e6ea |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F01-P01 | 95mm2 + 25mm2 4C+E CuSn XLPE/PVC- TH39 400V Main Incomer | Electrical Checks
59b4ba32-4599-5ca6-94cd-0bfe7f9be803 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F01-P01 | 95mm2 + 25mm2 4C+E CuSn XLPE/PVC- TH39 400V Main Incomer | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
300cfd6d-1099-401e-88c3-2d3febb32d4f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F05-P01
f7692801-8a66-4a1e-a4c1-1f570642402b |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F05-P01 | 95mm2 + 25mm2 4C+E CuSn XLPE/PVC- TH39 400V Generator Incomer
4c4f8260-97d4-5d36-87b8-a86829e18fe3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F05-P01 | 95mm2 + 25mm2 4C+E CuSn XLPE/PVC- TH39 400V Generator Incomer | Low Voltage Cable
5ddacb0d-3341-5b43-82f6-2e4df51acbfe |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F05-P01 | 95mm2 + 25mm2 4C+E CuSn XLPE/PVC- TH39 400V Generator Incomer | Electrical Checks
e0693b3d-0d1a-5c1f-baf4-b29b47a1e8db |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F05-P01 | 95mm2 + 25mm2 4C+E CuSn XLPE/PVC- TH39 400V Generator Incomer | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
d1e97100-f415-40ed-a253-1060f5c190d2 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010-C01
c88fa0d8-0524-4e67-8b48-3b6ffb44f545 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010-C01 | 1.5mm2 2C CuSn PVC/PVC-TH39 Switchboard Surge Protection Healthy
7149d90a-adbd-5775-8a2a-eecb6828e982 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010-C01 | 1.5mm2 2C CuSn PVC/PVC-TH39 Switchboard Surge Protection Healthy | Instrument Cable
f974181b-bbe5-5aed-bf6c-102414934abf |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010-C01 | 1.5mm2 2C CuSn PVC/PVC-TH39 Switchboard Surge Protection Healthy | Electrical Checks
f4963573-d31d-43c3-94c8-646c5499d8eb |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010-C02
c39518dd-648d-47fc-8ff4-7ea0ed836ab4 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010-C02 | 1.5mm2 2C CuSn PVC/PVC-TH39 Phase Failure Relay Supply Healthy
002e9ffb-f774-556d-a614-82726c8d50e3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010-C02 | 1.5mm2 2C CuSn PVC/PVC-TH39 Phase Failure Relay Supply Healthy | Instrument Cable
e34023c1-fc62-5eaf-bbff-e34bb7a6af1d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010-C02 | 1.5mm2 2C CuSn PVC/PVC-TH39 Phase Failure Relay Supply Healthy | Electrical Checks
bc2beb78-04c7-440c-ad81-0eaa65e2b15c |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F01-C01
b937ae5d-33d4-447a-b119-6a61e19c6f25 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F01-C01 | 1.5mm2 4C CuSn PVC/PVC- TH39 MCCB F01 Opened, Closed, Tripped Feedback
7a0e1904-d1ac-59a5-97dc-cd6112bcbafe |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F01-C01 | 1.5mm2 4C CuSn PVC/PVC- TH39 MCCB F01 Opened, Closed, Tripped Feedback | Instrument Cable
197f6a22-48ce-5af2-87eb-ecce77ee5465 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F01-C01 | 1.5mm2 4C CuSn PVC/PVC- TH39 MCCB F01 Opened, Closed, Tripped Feedback | Electrical Checks
02ee4db7-009c-4cd3-88cd-d562c0f58018 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F05-C01
c63e5a82-3623-4bb3-8f57-0bfe2b8d1991 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F05-C01 | 1.5mm2 4C CuSn PVC/PVC- TH39 MCCB F05 Opened, Closed, Tripped Feedback
ac2964fc-a792-5d4e-8132-751e9663f048 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F05-C01 | 1.5mm2 4C CuSn PVC/PVC- TH39 MCCB F05 Opened, Closed, Tripped Feedback | Instrument Cable
51e9da37-3c5f-55a4-afb0-048554654b0e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F05-C01 | 1.5mm2 4C CuSn PVC/PVC- TH39 MCCB F05 Opened, Closed, Tripped Feedback | Electrical Checks
625dba19-58f6-4af0-b5a7-44f6a4150fab |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F37-P01
96af8e67-99c7-469c-86ae-8ceeb3f3d520 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F37-P01 | 4mm2 4C+E CuSn PVC/PVC- TH39 H2S Scrubber Supply
52cd768e-5411-5dc5-9816-e807221bc331 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F37-P01 | 4mm2 4C+E CuSn PVC/PVC- TH39 H2S Scrubber Supply | Low Voltage Cable
01089e73-30a7-5895-b1ee-d47d903b02e3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F37-P01 | 4mm2 4C+E CuSn PVC/PVC- TH39 H2S Scrubber Supply | Electrical Checks
9cb72b63-5a80-506e-a941-0f353099bd16 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F37-P01 | 4mm2 4C+E CuSn PVC/PVC- TH39 H2S Scrubber Supply | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
258c3dec-1c63-4f2a-a8a7-4992dfb22c9b |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F40-P01
a1e0f26b-704a-4043-a910-d890ed3e835a |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F40-P01 | 2.5mm2 2C+E CuSn PVC/PVC- TH39 3 Phase Socket Outlet Supply
a339f1bf-1fb2-5d22-bf2a-89f5427704ed |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F40-P01 | 2.5mm2 2C+E CuSn PVC/PVC- TH39 3 Phase Socket Outlet Supply | Low Voltage Cable
af1613e9-7e59-596c-92af-8feb70f1529c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F40-P01 | 2.5mm2 2C+E CuSn PVC/PVC- TH39 3 Phase Socket Outlet Supply | Electrical Checks
7e1987e1-e389-5268-b120-ca2e39461f87 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F40-P01 | 2.5mm2 2C+E CuSn PVC/PVC- TH39 3 Phase Socket Outlet Supply | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
b07e0d3e-7732-4d8f-a745-27061c27aa84 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TBC (TH39Lighting (Inside/Outside) Supply)
cd59006e-0f7d-4761-8031-70bae95ed561 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TBC (TH39Lighting (Inside/Outside) Supply) | 2.5mm2 2C+E CuSn PVC/PVC- TH39 Lighting (Inside/Outside) Supply
2b0a02ea-1d12-5f5f-a6b8-488ef71b3c19 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TBC (TH39Lighting (Inside/Outside) Supply) | 2.5mm2 2C+E CuSn PVC/PVC- TH39 Lighting (Inside/Outside) Supply | Low Voltage Cable
263b4e45-bd52-544b-b7e3-502cdc98a4d1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TBC (TH39Lighting (Inside/Outside) Supply) | 2.5mm2 2C+E CuSn PVC/PVC- TH39 Lighting (Inside/Outside) Supply | Electrical Checks
e033b42a-b4a1-5232-9860-756cfef6bd83 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TBC (TH39Lighting (Inside/Outside) Supply) | 2.5mm2 2C+E CuSn PVC/PVC- TH39 Lighting (Inside/Outside) Supply | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
6fa3a137-6fae-4c10-8d57-d135b8ea0839 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F44-P01
dc5c1391-f0c9-4aec-b4de-df6f35cbb87c |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F44-P01 | 2.5mm2 2C+E CuSn PVC/PVC-TH39 Single Phase Socket Outlet Supply
11e26e94-7212-5f42-9ab4-6bfd1ae35190 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F44-P01 | 2.5mm2 2C+E CuSn PVC/PVC-TH39 Single Phase Socket Outlet Supply | Low Voltage Cable
bf2578e6-0316-564a-ba67-08071ce18b9d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F44-P01 | 2.5mm2 2C+E CuSn PVC/PVC-TH39 Single Phase Socket Outlet Supply | Electrical Checks
cc009827-f6c9-56b4-8569-e0a5cbff5ecb |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F44-P01 | 2.5mm2 2C+E CuSn PVC/PVC-TH39 Single Phase Socket Outlet Supply | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
c06ad68b-5fb0-4e51-97b7-9030ab067695 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F46-P01
8e0f7bc7-94e5-4d11-9f4a-b168c3cc513f |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F46-P01 | 2.5mm2 2C+E CuSn PVC/PVC- TH39 Anti-Condenstation Heater Supply
34ff77b4-588e-5173-8fd4-8d916bb59125 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F46-P01 | 2.5mm2 2C+E CuSn PVC/PVC- TH39 Anti-Condenstation Heater Supply | Low Voltage Cable
c01fecf6-bf2f-52cd-a564-36ee8206b350 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F46-P01 | 2.5mm2 2C+E CuSn PVC/PVC- TH39 Anti-Condenstation Heater Supply | Electrical Checks
b783cf67-7e2b-5f44-9ee2-8d84c0b26a0d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F46-P01 | 2.5mm2 2C+E CuSn PVC/PVC- TH39 Anti-Condenstation Heater Supply | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
4eca95c6-327b-417f-bf2f-deeecefcf91a |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F54-P01
de5d7427-1b4c-464b-8e4c-e8d18d784106 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F54-P01 | 4mm2 4C+E CuSn PVC/PVC- TH39 Wellpad Lightning Control Panel Supply
a3513b90-2ca5-5596-8381-97011e460871 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F54-P01 | 4mm2 4C+E CuSn PVC/PVC- TH39 Wellpad Lightning Control Panel Supply | Low Voltage Cable
bf51312b-25f0-55ed-9f39-ab70c0263179 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F54-P01 | 4mm2 4C+E CuSn PVC/PVC- TH39 Wellpad Lightning Control Panel Supply | Electrical Checks
1990293e-9702-5e92-93d6-4bd6685f7b4d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F54-P01 | 4mm2 4C+E CuSn PVC/PVC- TH39 Wellpad Lightning Control Panel Supply | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
6eea2f5f-6856-4a4e-85b2-2e99d09b227f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F47-P01
b1ce83ad-105e-47f0-a9ba-f2e637f45f3b |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F47-P01 | 2.5mm2 2C+E CuSn PVC/PVC- TH39 Wellpad Lighting Inside
51197435-89a9-5570-9886-8646a140b780 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F47-P01 | 2.5mm2 2C+E CuSn PVC/PVC- TH39 Wellpad Lighting Inside | Low Voltage Cable
176736dc-a53f-50fc-a447-80715917d086 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F47-P01 | 2.5mm2 2C+E CuSn PVC/PVC- TH39 Wellpad Lighting Inside | Electrical Checks
6acf37eb-fb54-56d9-b070-c4b9cf6977e4 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F47-P01 | 2.5mm2 2C+E CuSn PVC/PVC- TH39 Wellpad Lighting Inside | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
40e487f7-c291-4c8f-a6f9-5033b515f2c7 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F52-P01
318a2b4b-612d-48f6-9c30-e94a78832cab |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F52-P01 | 2.5mm2 2C+E CuSn PVC/PVC-TH39 Lighting Field
aa58b099-77d6-5e0c-8447-613d69cbe6a8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F52-P01 | 2.5mm2 2C+E CuSn PVC/PVC-TH39 Lighting Field | Low Voltage Cable
741aae4e-8b53-5e9d-acf2-d84d6313d16c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F52-P01 | 2.5mm2 2C+E CuSn PVC/PVC-TH39 Lighting Field | Electrical Checks
e25af107-c588-5911-85f4-81023e9936de |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F52-P01 | 2.5mm2 2C+E CuSn PVC/PVC-TH39 Lighting Field | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
e4d8906a-1e6a-49b6-b63d-74341cfa7415 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F40-C01
165c872d-25d2-4efc-99c8-b0612716a51e |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F40-C01 | 1.5mm2 12C CuSn PVC/PVC-TH39 H2S Scrubber Running, Healthy, Fault Feedback
2f758ccc-8cd1-5f42-b322-719c5ec295dc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F40-C01 | 1.5mm2 12C CuSn PVC/PVC-TH39 H2S Scrubber Running, Healthy, Fault Feedback | Instrument Cable
abf9f8c0-e2de-5555-aa0c-a3b0153482ea |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390BFA10GS010_-F40-C01 | 1.5mm2 12C CuSn PVC/PVC-TH39 H2S Scrubber Running, Healthy, Fault Feedback | Electrical Checks
749abebe-f623-4f34-8b5c-57291a807db3 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390CFx10CT010-C01
6e01e87c-b016-44fd-8a59-4c4fae706b71 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390CFx10CT010-C01 | 1.5mm2 1pr CuSn CS- TH39 Switchroom Temperature Feedback
1522a4a5-4253-5f17-bc59-b1cbcc263a7f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390CFx10CT010-C01 | 1.5mm2 1pr CuSn CS- TH39 Switchroom Temperature Feedback | Instrument Cable
fe6fbb16-fc92-58f3-ac2b-8b493d1603f3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390CFx10CT010-C01 | 1.5mm2 1pr CuSn CS- TH39 Switchroom Temperature Feedback | Electrical Checks
8279ade3-e5c1-4cab-805e-51c833888575 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390SGY10EH010-C01
eea0d904-17df-4364-be24-8c8a9eb8c9f3 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390SGY10EH010-C01 | 1.5mm2 2C CuSn PVC/PVC- TH39 Switchroom Smoke Alarm Feedback
4f8fa48c-fbb7-5066-bd01-24cadb1727e3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390SGY10EH010-C01 | 1.5mm2 2C CuSn PVC/PVC- TH39 Switchroom Smoke Alarm Feedback | Instrument Cable
65f0053b-c3e2-5126-b78c-bb38d57e62d8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390SGY10EH010-C01 | 1.5mm2 2C CuSn PVC/PVC- TH39 Switchroom Smoke Alarm Feedback | Electrical Checks
98d6be13-cb1e-44d1-96e8-95d710bde123 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390CYP10EM010_QH01-C01
ef6f1938-f591-43e6-a1e7-1a6e2240b2d0 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390CYP10EM010_QH01-C01 | 1.5mm2 2C CuSn PVC/PVC- TH39 Sitchroom Security Feedback
1a7cf376-aca6-5a34-bb4d-706577f3b96a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390CYP10EM010_QH01-C01 | 1.5mm2 2C CuSn PVC/PVC- TH39 Sitchroom Security Feedback | Instrument Cable
42738dae-79cc-5fb6-b90b-9cee8274f572 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Cables | TH000390CYP10EM010_QH01-C01 | 1.5mm2 2C CuSn PVC/PVC- TH39 Sitchroom Security Feedback | Electrical Checks
a3a660f4-c0e3-4f42-9b53-cddd92e6d112 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing
178990ae-1521-443b-985b-66b729ed7b02 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND01
97bdb3f5-1fc9-45fb-b255-3d55bd6a3f02 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND01 | 240mm2 1C Cu PVC/PVC GE/YE
c836cefd-0d70-5b5e-b64c-6996a87453fe |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND01 | 240mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
0b910343-55d2-5578-8514-7ef652517cf9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND01 | 240mm2 1C Cu PVC/PVC GE/YE | Test Results
cb7bd22a-0f6e-45c4-af3d-0f2366bf2900 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND02
2fa99b0d-b21e-4697-acee-bff57a0e5669 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND02 | 240mm2 1C Cu PVC/PVC GE/YE
3e5f1f3c-8d2b-52f0-89ea-c990624e5116 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND02 | 240mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
47e7087e-1528-5746-99e1-f52b4e3b2edd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND02 | 240mm2 1C Cu PVC/PVC GE/YE | Test Results
e47314f5-cf30-4fca-b526-bdc81e84a041 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND03
e9b65e9f-f996-4d37-b717-3b8c32816918 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND03 | 70mm2 1C Cu PVC/PVC GE/YE
a9e145a8-5334-5f4a-8cfa-a652db6701dc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND03 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
5cc2c661-3af6-57cd-84e3-f6b42783bbcf |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND03 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
1fc67c69-89c5-4a95-81bd-ad1cfb298c7f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND05
3d805ef9-3fa1-4f7d-8041-dc783485f91c |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND05 | 70mm2 1C Cu PVC/PVC GE/YE
572dc193-0741-5ac1-bc28-90927848bca4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND05 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
c001c16d-f7e5-583b-9b32-b4a21f686074 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND05 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
579533b2-19be-475c-b9ff-860f2ad9fb6b |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND06
c15047ca-46dc-4d44-9791-c29b1b184a6c |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND06 | 70mm2 1C Cu PVC/PVC GE/YE
769bc04b-1c39-55b7-81c3-ea3f6e15bd99 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND06 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
642aa1b3-0601-5c0e-af8e-9b95b34c7146 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND06 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
d38fd060-6703-4d24-a04f-1874d234a073 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND07
5f69c597-debd-4fae-a15f-94e074009b87 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND07 | 70mm2 1C Cu PVC/PVC GE/YE
73ed6f58-20ba-5b06-9f5a-6e0a00fb9437 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND07 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
964d798b-1ee3-52bc-bc4f-d6789ca19747 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND07 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
62e2f71a-6ffb-46f8-9d11-b37a3a4e170e |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND08-1
3439294e-0968-48e9-bae8-da8fed1e8bd5 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND08-1 | 240mm2 1C Cu PVC/PVC GE/YE
f9745333-ebf4-5b77-9cb2-ebbf6dfdefb5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND08-1 | 240mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
7e4810ba-2cf4-599b-9417-f09ddbd4ccdf |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND08-1 | 240mm2 1C Cu PVC/PVC GE/YE | Test Results
baaff106-306b-4ecd-8b4a-b8f216869edc |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND08-2
88890158-20ad-4c90-92c3-528f1a5285e8 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND08-2 | 240mm2 1C Cu PVC/PVC GE/YE
5b5499fe-8e62-570f-babc-f074bda45762 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND08-2 | 240mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
27f12d58-d218-5dd3-abcc-7e969c40eb5f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND08-2 | 240mm2 1C Cu PVC/PVC GE/YE | Test Results
0b327a57-d977-43bd-9b8e-e8972ce20edf |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND11
ffaa0fe8-c347-42ae-89c5-7c62d50bd113 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND11 | 240mm2 1C CuSn(BAR CABLE)
9d6ca186-721c-5082-ab00-7d955aeeba67 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND11 | 240mm2 1C CuSn(BAR CABLE) | Electrical earthing system installation
33070332-a542-5e0c-918f-c9834a0c3932 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Earthing | TH0003290BFA10GS010_BOND11 | 240mm2 1C CuSn(BAR CABLE) | Test Results
201392c2-ad87-400a-a4ef-843900b18bff |  | checklist-flat | not-started | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Certificate of compliance (COC)
7dea60b5-1b8e-56e2-8c9d-5994a154e087 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-001 TH39 LV Power & Light Small Power | Certificate of compliance (COC) | Please upload Certificate of Compliance here when complete (COC)
8a0fb89c-d478-4bce-9f06-d93aee1327f6 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment
e16e36fc-fbe2-426f-9e82-62f87bad0e07 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument
f17e4d6f-f0c6-4905-be4a-e7ace6daa41a |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter
7f1ab24d-e623-47e7-b5b0-52d07bc599a6 |  | checklist-flat | not-started | ITR-CL-1-131 Level Instrument Installation | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-131 Level Instrument Installation
92648710-164b-53e7-9cd5-81d4af134923 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-131 Level Instrument Installation | Level Instrument Installation
4a5c88c9-88c2-5437-b089-d3f83a355103 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-131 Level Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
943d7344-3d63-4269-ae44-93411b6cabce |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-122 Instrument Calibration
432180d0-0475-5413-867a-f2e474ec3565 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-122 Instrument Calibration | Required Data
f54505d7-dde1-5e14-96a4-31d5ba3e9bd8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
f84c4780-d40f-5ffc-b2a7-3d141fa77927 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
6e2cfd94-4574-4bb1-a60b-91c2a4d3912d |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning
576df2c4-fd8d-5f8d-b8c3-637187169063 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
5b58af90-92ca-51e6-873c-360ad7533816 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
37aafd4c-5605-5875-b774-c511691efa4d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
dc8eb26f-926d-57db-acef-912b0a55cfc3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
1b249e23-c2be-5bab-b1de-a1790565535e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
5995ac25-81b4-5aa6-a250-cd34262879c3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
53c5cef5-5d7b-584f-a375-0811ea47c048 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
a31e476f-6813-52fd-86f5-9a10892396be |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
13c68a39-b9b7-526b-9cd6-9cae8c7125d4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
09be3cf2-13c4-5787-bcef-2adc9898c7ac |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
027678b9-cda4-5c54-861f-b1fbd3643236 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
363936cd-6330-5e75-be62-0c0d6276d285 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
a046b811-f81c-56f9-a970-5f002a7b558a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
95c44182-0ab1-59b3-b3d2-3dfca1912266 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
f945f6a1-552e-5cbd-8297-40fdd2c3112e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
7dcb8aa2-956b-509e-ad1e-dbc1eb78abb2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
b0179f1b-a2fa-5cfa-a18c-d3a03e370494 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
dac3d469-f795-5702-8376-d4f2a51c86ec |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
f8dcebcf-a50b-5521-b64f-1e3d275cd1dd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
752bfb4e-a103-568a-b762-b040dae4d469 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
1dc070ce-7831-56aa-a322-9b2d36e3083f |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
8c7a351e-49c8-4f3b-b721-44b035ce1a9f |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments
16e69676-43f3-5ad0-9218-b5aa57418039 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Required Data
0e8dcf02-4c39-5936-bf76-9b95ad5ef93e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
8583abf6-7e67-5f45-a40c-ceabcd36af10 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
7cbd6bc3-24f9-573e-a6a8-2639cc2d95ae |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
1072a308-cc59-53e8-b8c3-07f70175063b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
fbf1cfe9-a144-5b46-95a2-23a20becf36b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
555d77a1-6e40-56a4-8707-81dc4d854f92 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 1
197703ef-6338-5aab-96bd-0e4c09170e9d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 2
9f45f6ac-4d8f-5d75-9ff0-4a6ef0cdf017 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 3
0a2e34fa-9770-5b10-8ce3-c16977cff689 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 4
b60dc441-c963-5c66-b97b-1ddb8fbfa2e3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Calibration settings
e62672de-93b3-5ffb-ae07-903239148fc9 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00XXXLFC10CL010 - TH39 Well Pad Pond - Level Transmitter | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
e00e8ada-ae81-4f7b-956d-51a4e5421c12 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter
81b087ad-79e6-47ed-a718-cfa4d5bdcde7 |  | checklist-flat | not-started | ITR-CL-1-129 Flow Meter Installation | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-129 Flow Meter Installation
e6d81d01-1cff-5d36-8ef2-8f54b84bf856 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-129 Flow Meter Installation | Flow Meter Installation
24d71c53-63ba-5aad-9383-e8e877edc66d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-129 Flow Meter Installation | All relevant signatures (Installed by, Approved by, Client Representative)
70d630b4-d4e2-4124-84ea-46a18efd8ba1 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-122 Instrument Calibration
12e1ad1a-3df5-51db-913f-63f382cd39b5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-122 Instrument Calibration | Required Data
6065922d-7102-55be-8cc8-24697f9c32ae |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
1e484240-7b7c-5c1c-b9c3-2fb7fb87eeec |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
f254fee5-2c09-4932-ae5f-60116eaf70a5 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning
9b513db4-a66b-57d1-baf7-295a94d50892 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
aecacf08-c439-5fd5-8563-cbe9dff7a79f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
cf0bc8e4-719e-50f6-9552-783151bcab91 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
8abc63fc-50db-5e4a-9045-e38332e40e54 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
070f9fb4-5199-50f2-b6a6-bc7b62e4b815 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
f52da94e-cd6c-5b3f-95a8-4ce83d72c614 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
f50961e0-dab5-5059-bd35-be197f03db36 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
96d96f61-dd85-569c-863d-061038afbd73 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
a6e2798a-90c6-538a-9ef4-e028d0e214b3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
42a4fc7f-8382-55d8-a443-026a29a7c64b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
1fba2451-8339-5c58-b122-a672d5f52ee2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
204c54fb-2bf7-5c5e-8f57-53dc2c5278c4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
5f5a7883-5ad4-5a82-b98e-d37c6f749322 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
63686f64-a2a2-5572-b5ed-05dd6d43293f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
2904667a-e47b-524a-b346-3a39fa64e53f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
a5311df2-5297-5a82-9ede-842dd72922bf |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
8b91721f-0f43-596d-a3b2-fa1f2b2b7c5d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
9f590ae1-0900-5d86-968d-6f761a3120a1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
465f2f44-9b93-5070-9b37-6b86d9f0526d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
f48279fb-a487-5be3-8755-b76229e482e7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
7b5dcbae-1cf9-5795-b14c-001607cdae0d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
1f24d0b5-20cc-4e71-9ed5-5cf8601d8970 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments
5c6e027d-d39c-5c62-89be-9d1f59b90353 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Required Data
2ab5c4ce-ab26-511c-9706-5802ab1c8875 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
a5835ee8-5a7c-511d-bbb7-278ef7cfe0c8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
4a5f30a7-56af-5d87-8765-cdc66783193c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
19eb351f-66b6-5672-8abd-33362ecae4b5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
6b2ed2ee-c326-5c07-b064-c06238baf305 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
e43c2ef9-1700-5d3e-9c9a-9690b637e9cc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 1
a216bc09-c730-548a-85a5-1de5608df6c8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 2
87e90db3-8ede-5c01-bfe2-7471ced8d824 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 3
b7ad34f5-0961-5b07-abc0-2a7ab9e22a9a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 4
7d3134f3-5ceb-58e3-bbb6-9a4fc4819eab |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Calibration settings
052601cb-a827-5b3b-9754-ed79db28f636 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH000390NDB10CF010 - TH39 Branch Line - Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
ac94a854-6cb3-49da-ac31-00ac6c61e8b8 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter
10951b3b-c27c-4cd3-9bca-0058b911f383 |  | checklist-flat | not-started | ITR-CL-1-130 Pressure Instrument Installation | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-130 Pressure Instrument Installation
aadd0571-68d9-5569-b9c1-b7422d630f7a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-130 Pressure Instrument Installation | Pressure Instrument Installation
78b9829d-f3e1-5ab5-8967-09dad33d6cc5 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-130 Pressure Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
37fca3e0-5981-454f-9c27-e9ef9017f848 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-122 Instrument Calibration
08b5473e-e105-56c5-bfc4-0fa6ceaa1761 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-122 Instrument Calibration | Required Data
f945bb12-d720-558c-89bd-9e1310c1dfae |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
75b363cb-eab9-5c9e-b305-fa0038fe7622 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
10c399db-3a05-4ee4-99e3-4684c1d84f4d |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning
dc8cc8b9-7672-5cf3-970c-89330e59b6bc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
bf610ff2-5c0f-5bf2-a92d-c7a299e9fa7e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
43dd0411-3524-5407-88c5-c6bbf11d6c03 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
6122508f-3498-5afd-aca5-304cb816434d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
58d5102c-bde7-52b6-be66-a702207f89cc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
28ddc32b-1fc5-527e-abf2-de2d3f407a4b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
7ee66d05-d1cb-5d84-a7e9-9d0b2cab9c8b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
75544840-3dbd-532b-a35a-0268a8952cf1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
328e1a96-1800-5d72-80a3-a02fbd574f06 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
d0891a31-240f-5453-9293-f1a4b0b0b242 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
4a57726c-cfd6-5d55-a6af-c46165d29366 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
1d83d0e9-302b-5c13-896b-d0e37b1a53e5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
1844aead-0bcf-5ede-9b06-2887addab824 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
ba0915a2-4eca-5eba-baf8-a3c6fd2ef1da |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
bf3688ca-2ab3-5927-9e74-028cbe202df9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
3bc2410f-ec61-57ab-a71f-96874b4179d6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
c0ee149c-563f-53bc-83c5-45bc614250fc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
45343192-80d4-5335-b28b-02300dd807ef |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
6f49daf0-7b62-5c12-ae29-a47eb69e6bc8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
2e57a7e8-ed02-5869-a99e-d9c04c88bd10 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
c9817076-1e7f-5518-9da5-46050992e2ce |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
b172e696-5531-4662-9bbf-50af301677ee |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments
c5e887cd-087b-5d5e-bf25-230f63c06501 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Required Data
96ef90bf-cd08-54ca-973f-171710c00bb1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
e7ddc3b7-d769-5a51-bcc0-66b14ff64b05 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
f9de6095-7209-5295-8ee6-5b973a3f060e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
868bdcfa-115c-5d7f-a49b-e2e79759a632 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
2d589aaf-5576-5887-ad30-66afd1208ef2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
afc45a1c-7f64-5f68-8539-d8d5cc4b5323 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 1
4afec89e-fb12-5a38-bae3-90b0c54fc72b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 2
2c4b5994-d0b8-52cf-8c95-da46199453a6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 3
0c8603ca-d458-5215-a1ab-2eb142027cea |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 4
1a4b45f0-a260-5486-89ad-80f14d68ee96 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Calibration settings
a0f68b69-b3fa-516d-9a38-ce595fc88216 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10CP010 - TH39 Wellhead - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
6758699e-a51b-40e8-b125-987085661dbc |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter
2abebb1e-fc0c-4a4c-b3fc-c74c6e06c962 |  | checklist-flat | not-started | ITR-CL-1-128 Temperature Instrument Installation | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-128 Temperature Instrument Installation
f3cb7c30-6605-5f9c-9266-9c553651e9a7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-128 Temperature Instrument Installation | Temperature Instrument Installation
24df1d15-82bb-512a-ae84-86f80804a689 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-128 Temperature Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
619bf94c-26bc-4206-bdca-4fd2bbfaca37 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-122 Instrument Calibration
a2279d0c-5fe1-5559-a847-3f4b7fcf69d9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-122 Instrument Calibration | Required Data
6f04ecf2-80c2-5190-b8c7-0ab4f977736d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
6df24959-b222-5ba1-bc1b-8995c20c832d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
6334cf48-6ff9-4b4b-a44c-66ceb3822091 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning
bfbd82df-9e3c-57bd-b52c-aa471b6f8aa2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
91517953-5d9d-56cb-ae03-751e77bc2d1e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
acd5b378-976b-5636-ba8a-0675f9637590 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
f8d13ad9-e3a4-5ff9-bbfe-531b20527d3a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
b5084a3a-7c7c-53fc-96d4-1d15251b6efe |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
bff3b0d1-977b-58ea-8cb7-966eb726e62c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
e4c132a3-dcdd-511f-a0cb-3195fa0dcc95 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
a0b56c8e-361e-5b77-b7e1-aaa6b2f7a1fa |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
48ce7a25-f9f8-55ff-85bd-21c675908cde |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
1c51d9fe-1043-5293-b5ce-a4f02a4b392f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
e85e2d34-86e6-5111-aab0-cf6510fac6e7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
6dabf245-5b4f-5a62-a3af-2706578a0789 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
3118e54d-c20c-5360-9e9a-569b82799381 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
48aaa08c-a900-5d92-acfe-84d31c6d6a28 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
3dea7f6e-7fa7-5409-b045-63639ea759b5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
64e30787-3fda-594d-a98f-e1e53010a7b8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
1a480f37-06dd-5276-beb1-c686430d457b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
98108985-2359-556c-87d5-20b2a5101957 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
5387548b-68d0-5ba9-a5bc-5c4eff814d69 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
ad4bb433-05b0-5e9e-bdd8-fbe5a11a04a9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
ad4015ae-c3ed-5054-8fb5-6c492ba38c1b |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
c10fdaee-8b66-4d3f-b307-943d3a270e61 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments
d6084747-cb00-5c2a-b144-8625757a9e3a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Required Data
f0ea1aee-a2a0-5a8b-9af8-f3d8d09a3185 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
ba533afb-81f0-52d7-a4ba-bc07876ebab0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
d4e81edc-09ea-562a-a0dd-85f40f9f6032 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
0ba58ab1-a626-5e08-9ee6-d41e3eda2d57 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
9eb4c460-773c-5031-a875-0fc11cb15c0e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
0afd9a06-292a-5673-b4e8-03a58e938d6c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 1
f9f6fdc1-cb1c-5467-8122-b1d495f09ad3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 2
c37d26f1-9dac-5cdf-9d93-45852762323f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 3
f1d41307-95bd-591f-875e-425f832c5475 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 4
b4d3953b-87d9-5b28-b3aa-f068f4a47148 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Calibration settings
7672c273-6c27-5cf1-9168-f5f83289878d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CT030 - TH39 Well Pad Reinjection - Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
1fac718d-7dc5-42e0-933e-72f79375b704 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve
a3df742d-4463-4881-b7d9-18fd0d46742b |  | checklist-flat | not-started | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation)
db66db17-e033-5a1a-9f12-e7de9620d8f2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Equipment
c821f2bd-f640-5730-90f8-05f40b6fe950 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Valve
15475a16-2f4a-5961-b8cf-5378c5264a98 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Actuator
ca4e2819-a8d8-5537-9118-69baf788202d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Positioner
328b7ab7-00cf-5cb2-b40d-0c8e0afe7f5b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | I/P Converter
279dbf95-151d-5226-ac73-929a1c13f2a4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Filter/Regulator
e14f79fb-1f66-5420-9f53-6649caab6c84 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Fail Action
3388ef3e-fe65-55ee-a2b0-ac9a49229961 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Proximity Detectors
a3d57ccc-ba65-5adb-9ee8-85e7bfcfffca |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Solenoid Valve
f35c54c4-4d92-56dd-9afb-0c34d92620d9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Pilot Valve
cba5290a-f707-5e18-9832-e4864ad5fab3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Hydraulic Actuator
f773003a-b04a-5640-97bf-ca03b68b31de |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Accumulator
be5f6a6b-1f4b-51b2-8068-f46cd05e6ec7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Electric Actuator
b86cb160-1ffe-5fa7-a165-53c7b5b66141 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Miscellaneous Equipment
eeb3582b-75a7-51f8-8ff7-ebe5927ab946 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | All relevant signatures (Installed by, Approved by, Client Representative)
1f2b1d68-2f91-4379-8f92-6ccea224f4d0 |  | checklist-flat | not-started | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation)
07520637-2aa5-5f94-8c1b-20206bf4fcb8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Equipment
453263df-bb26-5865-a2ec-786c78c97837 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Valve
e0255d16-85c0-5792-89e3-208864daf21b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Actuator
4ca2b910-8678-55f5-ab14-109dc0d33acb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Positioner
dcf55e4f-55a2-50a6-9f8c-4fc782a35f6c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | I/P Converter
00aa921a-7a5c-5d0a-92d7-75530fd86af3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Filter/Regulator/On-Off Valve
4ef5ff37-af8e-51a1-b515-a00563de0fc8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Fail Action
e754f936-e560-5d1b-8faa-2430f08da4b7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Valve Field Calibration and Hysteresis Check
920acee2-6f4e-5d58-a188-f87fda42890a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Proximity Detectors
d1a382de-d7f8-5097-833c-17ff6372505b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Solenoid Valve
e884e442-65e9-5b36-8207-9a89ce9ad78f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Pilot Valve
e73bf603-22bf-5beb-94db-1f942ec8d4bb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Hydraulic Actuator
00e4777b-1a56-5219-b0c1-6078b8489f96 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Accumulator
3a26b5a2-d080-57ee-9fdb-fb54d623b301 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Electric Actuator
8aab68ad-ea9a-526f-aed2-b9c8d703dea9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Miscellaneous Equipment
78b32500-bf12-5905-88ec-955e8defd1b2 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | All relevant signatures (Installed by, Approved by, Client Representative)
ffdf9d18-7bad-42f3-b10b-d5cb546ca004 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-122 Instrument Calibration
aec3f004-a62c-56c8-b40f-592c7bced5b3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-122 Instrument Calibration | Required Data
2d0b9df1-94eb-5287-b4a5-f5e3bcc02b37 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
687c81b3-653d-505a-8fd1-a9fa7d130ff4 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
a59d293d-e4f8-4065-923a-12cba3d8985f |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning
c07d1282-0adc-5ba2-94e3-de7052486415 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
404e9747-34e1-582a-9535-3fa6e0e5edf0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
d2ada60a-9745-523d-9d65-b84a1e668eb6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
c4a8a5da-fe58-5db1-aaf0-be52e46bf537 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
7b0eed44-e481-5c2b-b03c-178582b4c3f0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
323979ea-601f-5cea-96ed-de2565ac69ba |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
eb22589f-17c1-54da-88ce-c14b992e86ec |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
589dd2d3-5510-56e8-a741-9931b3218b06 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
9b9002ef-f4d3-590b-a550-a8c63a304d5b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
797e37af-caff-5998-bdf4-bd8269a050e9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
c7fa92e2-0c98-57b7-b236-2e928465b26c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
cdfd041c-07c1-5f71-99d0-f9d3c1bea20f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
46a78aed-ab56-5ac4-9aa7-5a6323221124 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
9096a603-fbd5-5fef-8f01-4362e974c7c6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
993c97f2-564c-5fe8-a15e-62262e8ab393 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
63dbb823-6586-59b1-b663-defd8ebb0eb4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
94e20075-730c-58b3-8540-6adb7c5425c2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
8a006ee8-e614-5c28-b43f-c1de7f5ec5f1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
e72b8a44-93a5-5f0d-a1d0-80bf24037b72 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
75b6d75b-e1d4-506e-949a-93301d903985 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
d4ab3846-cb3e-58d3-9f16-9a9d9e734c30 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
49e3d893-5a08-48dd-b0b2-c198951f8fed |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-124 Commissioning Instruments
1f8e0a2b-7604-587c-b426-2dba0669d1ce |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-124 Commissioning Instruments | Required Data
e6ec6bd7-c011-598b-a41e-27db5ab53467 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
71fda4e0-113b-5bca-a889-b61db3865543 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
16cab802-242e-53a0-becd-45cb160cc9d5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
d566e3e0-eafc-5db5-9d2a-a77c4453a542 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
fd0eba91-1fc3-5bfc-a6d5-46c4f01bea52 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
ce2e44b3-62d7-5963-b1cc-bc80d48b3a1c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-124 Commissioning Instruments | Set Point 1
7a022fa3-d9e8-518f-810a-965fbb2c58b2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-124 Commissioning Instruments | Set Point 2
c0f59266-e221-5bc5-87c1-4860c64032c5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-124 Commissioning Instruments | Set Point 3
3539aedb-db57-582e-aa32-216dbbc0d281 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-124 Commissioning Instruments | Set Point 4
560a5d64-857e-5f16-b278-a2bbf79a34bb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-124 Commissioning Instruments | Calibration settings
e36af016-77b0-500c-a8cc-d36d05b70b52 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00390NDB10AA110 - TH39 Control Valve | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
8682b11a-1ea1-4a05-89fa-5fae91ac10e0 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter
4d7089be-761c-4be1-a261-12c82d44d25c |  | checklist-flat | not-started | ITR-CL-1-130 Pressure Instrument Installation | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-130 Pressure Instrument Installation
1c8fad90-33e9-5808-9da4-a5420bd63d96 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-130 Pressure Instrument Installation | Pressure Instrument Installation
3ff458ea-9e10-5ca5-9571-7cdf22731c2f |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-130 Pressure Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
8708f594-b1d0-40d0-bafc-72aee10bc0e9 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-122 Instrument Calibration
99500247-6e00-5394-9d8b-77c1ccdf50f3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-122 Instrument Calibration | Required Data
3e2b7e81-bf42-5592-a746-6a3bbb20643b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
8ed26c06-99fe-517f-a625-fc6c2a314431 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
8fb42471-9b39-4045-b465-c68b118e9e76 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning
cff9f593-c492-56aa-85ac-a8f1cd981e19 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
6759f711-f2e6-5fce-b60e-4a8a195de8f3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
abe2399b-ac6a-500a-a51b-9c2f6d9ebce2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
9855dbdb-364e-5f2d-8289-2a6c7bf49c61 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
dc913863-1425-5744-be9e-ec2bb698f47c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
2656b764-45ef-508c-bf49-c0501288d35e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
1f508fc1-b9c5-5e2e-857a-6e18de2e9125 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
7a039723-4f20-5912-be2e-118d30af2d33 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
01e94cae-848d-513a-a722-d7cdb37bcdb1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
cfc354e3-d911-5ca0-b05a-7796969222f0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
1e4f79b3-5144-59aa-bc41-07cd9dd3d298 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
87c2dd0c-8154-5e81-98a4-d7c0cdf61933 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
09162ae6-975d-5a08-af0d-dafc497d6645 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
fee075b7-4375-546a-a4ce-da537cdeeaa1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
26ae960c-dfcf-5c70-b859-bcb3bb104125 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
60c50727-850f-584d-b29a-728398f2249a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
519d5b96-ef09-5827-8c24-5921e3e54993 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
78c8a155-d0a4-572a-83e0-0ab5580e2af1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
161cb926-83f5-5ed8-8215-a2cc3598413e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
f7e1760f-0ead-5595-9743-ae48c33affb2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
a09ae8a5-ff27-5077-bf49-03aca32d1738 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
fc1b624c-8aa9-437d-8859-b3d953ec8970 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments
90d03f2e-4ba6-5090-b6b0-6b496b78f2ef |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Required Data
4382aacb-f524-5a2a-9d66-b65a6beaba10 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
1d704814-3075-5fb0-984f-948845d505ab |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
b7f94e87-f056-54d5-85a4-d1e15e4c70e2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
c9d7b11c-8782-5340-b3c7-df0c56f265e6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
8f6de236-fed1-5340-bdb6-6320c4ef73be |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
decce2af-9ca2-55b6-9bde-549b041aa957 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 1
33a40a29-342d-52e3-becd-efb5c782948e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 2
126eb6fe-5d95-55af-b914-cae5a7bbfbf7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 3
7698267e-7fde-513a-be41-3d090735b6c0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 4
e05be7a6-5d30-5b67-8d2c-c9cfbcccf82a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Calibration settings
be3e33d5-64f5-5e8d-bed7-78a903260849 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Instrument | TH00L260NDB10CP010 - TH39 Well Pad Reinjection - Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
8ba862c4-4263-490a-89f6-bf8b00e907d0 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables
3fb4d194-673e-4738-bd7f-74b15ad7c598 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | Junction Box 7
9aa1f234-93bd-4564-88c6-f05dccfdd785 |  | checklist-flat | not-started | ITR-CL-1-106 - Junction Box | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | Junction Box 7 | Junction Box 7
88984505-eb28-5383-8afe-735f4d867754 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | Junction Box 7 | Junction Box 7 | Junction Box
0f07e795-d86a-4051-8cc0-f6d69760a1ba |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH000390BHx10GY101-A01
4f933af9-39fa-49c2-b536-6beebf096090 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH000390BHx10GY101-A01 | 1.5mm2 12pr CuSn ESCS- Twisted Pair Multicore to Junction Box 07
6d80b3b1-db4b-5d20-a6f2-bb194cf9f187 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH000390BHx10GY101-A01 | 1.5mm2 12pr CuSn ESCS- Twisted Pair Multicore to Junction Box 07 | Instrument Cable
75d130ca-0013-5bde-b625-7beb8217c7be |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH000390BHx10GY101-A01 | 1.5mm2 12pr CuSn ESCS- Twisted Pair Multicore to Junction Box 07 | Electrical Checks
cb198a95-f3c4-4b7a-8c49-44fbde94956c |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH000390BHx10GY101-E01
7dcccd36-3391-44c7-80e1-65350cd0d52c |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH000390BHx10GY101-E01 | 120mm2 1C Cu PVC/PVC GE/YE- Feild Earth Bonding
7c9c86d9-3c7f-5ffc-ab6d-6dc2fecc2f20 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH000390BHx10GY101-E01 | 120mm2 1C Cu PVC/PVC GE/YE- Feild Earth Bonding | Electrical earthing system installation
ab9c8f2c-f4e9-5a5f-b9f1-2402567ca984 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH000390BHx10GY101-E01 | 120mm2 1C Cu PVC/PVC GE/YE- Feild Earth Bonding | Test Results
ebab67cc-d972-41c8-af20-a71589d988e6 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH000390NDB10CF010-A01
52d3cc46-93e4-459c-9ced-239e5ac2ab17 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH000390NDB10CF010-A01 | 1.5mm2 1pr CuSn CS- TH39 Pond, Level Transmitter
97e9b664-5960-58a4-89bf-3c2f80af7a93 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH000390NDB10CF010-A01 | 1.5mm2 1pr CuSn CS- TH39 Pond, Level Transmitter | Instrument Cable
4e28b5b0-f822-56ee-8b43-27ea6da5acf9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH000390NDB10CF010-A01 | 1.5mm2 1pr CuSn CS- TH39 Pond, Level Transmitter | Electrical Checks
3b9547c5-ab5b-41a1-9bd0-cd65e1e82806 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH00XXX0LFC10CL010-A01
17668867-3cce-419f-b5ff-d73f02767f77 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH00XXX0LFC10CL010-A01 | 1.5mm2 1pr CuSn CS- TH39 Branch Line, Pressure Transmitter
aebc6cfc-103b-532e-8fa9-95cb87ae7515 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH00XXX0LFC10CL010-A01 | 1.5mm2 1pr CuSn CS- TH39 Branch Line, Pressure Transmitter | Instrument Cable
ae8e954e-2fac-5dd1-8c1c-125164ae8dcb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH00XXX0LFC10CL010-A01 | 1.5mm2 1pr CuSn CS- TH39 Branch Line, Pressure Transmitter | Electrical Checks
54d08071-8ff8-4c30-aed4-914f3fd44589 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH00L260NDB10CT030-A01
84330063-ec8d-4e9a-b899-a059f404fd88 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH00L260NDB10CT030-A01 | 1.5mm2 1pr CuSn CS- TH39 Wellhead, Pressure Transmitter
750866df-f740-5792-9339-2decf62ca57d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH00L260NDB10CT030-A01 | 1.5mm2 1pr CuSn CS- TH39 Wellhead, Pressure Transmitter | Instrument Cable
ad43c053-ea28-555d-9321-d71ee0a1f74a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH00L260NDB10CT030-A01 | 1.5mm2 1pr CuSn CS- TH39 Wellhead, Pressure Transmitter | Electrical Checks
e475c694-268a-4924-8eeb-980bca59ac56 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH00L260NDB10CP020-A01
2ad2e13c-6983-4e94-8aad-db7edb57e012 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH00L260NDB10CP020-A01 | 1.5mm2 1pr CuSn CS- TH39 Branch Line, Temperature Transmitter
298fe815-fcf2-55bd-851d-a231485cf85d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH00L260NDB10CP020-A01 | 1.5mm2 1pr CuSn CS- TH39 Branch Line, Temperature Transmitter | Instrument Cable
121c8b81-a611-5a80-b7e5-513546b75036 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH00L260NDB10CP020-A01 | 1.5mm2 1pr CuSn CS- TH39 Branch Line, Temperature Transmitter | Electrical Checks
7b2710d4-a3cb-4e8b-ae5b-05344849647c |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH000390NDB10CP010-A01
83cc0282-89ab-4cad-a637-8f1f460c0832 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH000390NDB10CP010-A01 | 1.5mm2 1pr CuSn CS- Wellpad Header Temperature Transmitter
2c2be7bb-1824-529a-be66-06d884a272ab |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH000390NDB10CP010-A01 | 1.5mm2 1pr CuSn CS- Wellpad Header Temperature Transmitter | Instrument Cable
73de822e-2a36-5776-a31d-6a2fe0f3cac3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH000390NDB10CP010-A01 | 1.5mm2 1pr CuSn CS- Wellpad Header Temperature Transmitter | Electrical Checks
49caa5df-8911-436b-ba0e-6befc31de78d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH000390NDB10AA110_-P01
aa1d584e-3c70-4f88-a56a-3d780e457bfa |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH000390NDB10AA110_-P01 | 10mm2 3C+E CuSn XLPE/PVC- Reinjeection Wellhead TH39 Control Valve
28c2d66e-630a-55b6-b864-0fc1c1b1a452 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH000390NDB10AA110_-P01 | 10mm2 3C+E CuSn XLPE/PVC- Reinjeection Wellhead TH39 Control Valve | Instrument Cable
463512f3-f979-5ddf-96d0-c7f0df503242 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH000390NDB10AA110_-P01 | 10mm2 3C+E CuSn XLPE/PVC- Reinjeection Wellhead TH39 Control Valve | Electrical Checks
cce24d6e-325c-4c82-ae20-5f8945f4a1d1 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH000390NDB10AA110_-S01
82721134-07b5-490a-8527-24dc38a6a9a1 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH000390NDB10AA110_-S01 | Profibus DP - Grey Sheath- Production Wellhead TH39 Control Valve
016020fb-0158-5e94-b368-94f6a0295ff5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH000390NDB10AA110_-S01 | Profibus DP - Grey Sheath- Production Wellhead TH39 Control Valve | Instrument Cable
9b5f92fa-6351-58bd-b80d-ba8f2c3df938 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Cables | TH000390NDB10AA110_-S01 | Profibus DP - Grey Sheath- Production Wellhead TH39 Control Valve | Electrical Checks
d347ad2c-9e9c-4088-b155-ac9357fd4a03 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms
b350661a-bb78-4b2d-b265-cc342072a153 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH000320CRS20GN011-S01
766a93b3-64eb-42e7-ad31-47998bf70a40 |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH000320CRS20GN011-S01 | Single Mode Fibre Patch Lead- Internal Panel Wiring
25f00920-1dd6-5548-8435-3d5fc4e493f1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH000320CRS20GN011-S01 | Single Mode Fibre Patch Lead- Internal Panel Wiring | Fibre Optic Cable
d27b4161-acf7-440a-b2aa-a27301ec9081 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH000320CRS20GN011-S02
53351e28-9669-4427-bf51-4ab537288274 |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH000320CRS20GN011-S02 | Single Mode Fibre Patch Lead- Internal Panel Wiring
ffc03a12-b3a6-5fef-b733-1ea026ed19c1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH000320CRS20GN011-S02 | Single Mode Fibre Patch Lead- Internal Panel Wiring | Fibre Optic Cable
5e94e2ec-18e7-4459-8393-dddedcc52e70 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH000320CRS20GN011-S03
5bd9b83f-1a27-451a-9d78-97774b0e53ce |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH000320CRS20GN011-S03 | Single Mode Fibre Patch Lead- Internal Panel Wiring
1d5a160c-d0de-56c3-ab3b-fe4b85d6dfd9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH000320CRS20GN011-S03 | Single Mode Fibre Patch Lead- Internal Panel Wiring | Fibre Optic Cable
5632c356-d061-4968-ba8d-5fa13d050020 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH000320CRS20GN011-S04
dd55a6ae-4ad0-4723-959b-d4c92f780aa6 |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH000320CRS20GN011-S04 | Single Mode Fibre Patch Lead- Internal Panel Wiring
cbed5df1-e811-58ce-b01e-4e39c8819d10 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH000320CRS20GN011-S04 | Single Mode Fibre Patch Lead- Internal Panel Wiring | Fibre Optic Cable
7d67f091-18c9-4b0b-8dae-82f45df237ba |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH000390CRA20GU003-S01
1c7159b2-3223-4c95-82ee-69e2cc0ffa86 |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH000390CRA20GU003-S01 | Single Mode Fibre Patch Lead- Internal Panel Wiring
ba53b138-ed5d-5670-a67f-d387736bd7d8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH000390CRA20GU003-S01 | Single Mode Fibre Patch Lead- Internal Panel Wiring | Fibre Optic Cable
0c2e1fa9-b89c-42ba-9c25-a332860830d3 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH000390CRA20GU003-S02
8ee81181-350e-42ca-b706-9dc61e57bc7d |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH000390CRA20GU003-S02 | Profibus DP - Grey Sheath- Internal Wiring
2ce01b10-6211-5f5e-ab2d-cb84c39230da |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH000390CRA20GU003-S02 | Profibus DP - Grey Sheath- Internal Wiring | Fibre Optic Cable
267c6a4d-8727-47fa-a480-fed4a03b5c92 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH000390CRA20GU009-S01
93a06b0b-d11d-4d9b-92a4-b4cf505d2338 |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH000390CRA20GU009-S01 | Single Mode Fibre Patch Lead- Internal Panel Wiring
4b4185f5-809d-5b86-b11e-0bde5bb4198b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH000390CRA20GU009-S01 | Single Mode Fibre Patch Lead- Internal Panel Wiring | Fibre Optic Cable
cb62ffc3-16ac-4219-84b9-c512cb069f7f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH000390CRA20GU009-S02
63053804-dee2-420b-a266-b216f27a6487 |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH000390CRA20GU009-S02 | Profibus DP - Grey Sheath- Internal Wiring
0c59c10d-473b-5afb-bcb9-0ea1358a0878 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH000390CRA20GU009-S02 | Profibus DP - Grey Sheath- Internal Wiring | Fibre Optic Cable
7960e597-9d80-4f52-a405-164ccc636fc7 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH39-RLM01-S01
6a78ca46-d09f-48c2-a1f5-95aa82f7a9e8 |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH39-RLM01-S01 | Profibus DP - Grey Sheath- Internal Wiring
86d1bf33-e8a6-5417-b9f1-0cca00506f01 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH39-RLM01-S01 | Profibus DP - Grey Sheath- Internal Wiring | Fibre Optic Cable
33c035a4-5620-4e66-9829-e6fde2fc5224 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH39-RLM01-S02
58a11242-aaef-401d-9e78-41fd99fb9d61 |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH39-RLM01-S02 | Profibus DP - Grey Sheath- Internal Wiring
3b23990b-7876-5816-9de2-036aee47ce77 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Fibre & Comms | TH39-RLM01-S02 | Profibus DP - Grey Sheath- Internal Wiring | Fibre Optic Cable
d5ba06b0-ec16-4ade-907f-5e9700fc243d |  | checklist-flat | not-started | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP-ITH39 -E-002 TH39 Process Equipment | Certificate of compliance (COC)
7ae561e8-7824-5603-b8ce-b17281de8936 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ITH39 -E-002 TH39 Process Equipment | Certificate of compliance (COC) | Please upload Certificate of Compliance here when complete (COC)
1e26d944-9ae8-42f4-a48e-e1d9726734d6 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-007 Seperation Field Light & Power
be0bb1f8-791f-4a80-9c59-ab8b19e9b088 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-007 Seperation Field Light & Power | Cables
3bb8a6fa-2409-42d4-bd06-904cca9a9c3d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | TH00S030BJB30GS010_-F01-P01
1a25364c-2e53-41f7-8513-887d3d8c71cf |  | checklist-flat | not-started | ITR-CL-1-106 - Junction Box | checklist-flat | FALSE | FALSE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | TH00S030BJB30GS010_-F01-P01 | 4mm2 4C+E CuSn PVC/PVC
dad23334-3716-5130-8d34-967d87e26862 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | TH00S030BJB30GS010_-F01-P01 | 4mm2 4C+E CuSn PVC/PVC | Junction Box
ca3a8dda-70ed-4912-933b-04652efe0751 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | TH00S030BJB30GS010_-F12-P01
fbaff439-611a-4eac-83e0-708e75886c17 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | TH00S030BJB30GS010_-F12-P01 | 2.5mm2 2C+E CuSn PVC/PVC
0f4dee38-a71f-508b-ba0b-73c130a35119 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | TH00S030BJB30GS010_-F12-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Instrument Cable
dc3b451f-0cc8-5e3b-8d75-fa40ef48adb5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | TH00S030BJB30GS010_-F12-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Electrical Checks
cf259614-2023-4533-b5ea-0e30f68ecf88 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | SEPARATOR TASK LIGHITNG SUPPLY SECTION 2 - DUMP STATION
46885f6d-6570-4ab9-af1f-78e4b08e04eb |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | SEPARATOR TASK LIGHITNG SUPPLY SECTION 2 - DUMP STATION | 2.5mm2 2C+E CuSn PVC/PVC
a457d934-e0f2-51a0-85a4-a83eb512cf22 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | SEPARATOR TASK LIGHITNG SUPPLY SECTION 2 - DUMP STATION | 2.5mm2 2C+E CuSn PVC/PVC | Instrument Cable
300214df-cf2d-5a3a-b609-1c9d65466251 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | SEPARATOR TASK LIGHITNG SUPPLY SECTION 2 - DUMP STATION | 2.5mm2 2C+E CuSn PVC/PVC | Electrical Checks
8aaea5d3-bd31-4437-aefa-6614b99b48fe |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | SEPARATOR TASK LIGHITNG SUPPLY SECTION 3 - TH14
f13b4afb-bdcf-45a2-9716-d2d9e974176f |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | SEPARATOR TASK LIGHITNG SUPPLY SECTION 3 - TH14 | 35mm2 2C+E CuSn PVC/PVC
08f4ee50-47b9-58cd-a1a1-669ed3a432b0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | SEPARATOR TASK LIGHITNG SUPPLY SECTION 3 - TH14 | 35mm2 2C+E CuSn PVC/PVC | Instrument Cable
86425724-3960-5aca-b9d0-a02a66a73406 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | SEPARATOR TASK LIGHITNG SUPPLY SECTION 3 - TH14 | 35mm2 2C+E CuSn PVC/PVC | Electrical Checks
b7808c6f-a0cc-49ee-a974-0f35398e1e21 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | TH00S030BJB30GS010_-F03-P01
a30e2113-3359-4124-a886-a40053f780bd |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | TH00S030BJB30GS010_-F03-P01 | 2.5mm2 2C+E CuSn PVC/PVC
dba69bb9-0349-53d0-a99a-76e8ed15bb0a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | TH00S030BJB30GS010_-F03-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Instrument Cable
4457e038-f900-5d88-89b2-21540fea0373 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | TH00S030BJB30GS010_-F03-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Electrical Checks
6a58c7e7-4b02-4d13-9b40-090d47eee7e9 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | TH00S030BJB30GS010_-F14-P01
a0266193-2fa0-49a3-9e7d-52c43a227245 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | TH00S030BJB30GS010_-F14-P01 | 2.5mm2 2C+E CuSn PVC/PVC
490dfc00-83b9-587b-a4d7-7c6e50010d6c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | TH00S030BJB30GS010_-F14-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Instrument Cable
f7ecb3a5-8b2f-5b1c-83a2-d8e33e02adfd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | TH00S030BJB30GS010_-F14-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Electrical Checks
3fe03793-8aed-483a-b85a-73d38367e626 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | SEPARATOR LIGHTING REMOTE SWITCHING Section 1
b1e3b200-e61d-4572-8304-6b2bd211ea36 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | SEPARATOR LIGHTING REMOTE SWITCHING Section 1 | 1.5mm2 2C CuSn PVC/PVC
d324d4f0-5f4f-5908-bde6-ad237bd27999 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | SEPARATOR LIGHTING REMOTE SWITCHING Section 1 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
56859a7f-48c4-59cd-912e-00a70cd24ced |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | SEPARATOR LIGHTING REMOTE SWITCHING Section 1 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
5125bd51-0ade-455a-a11c-15ac68a5213a |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | SEPARATOR LIGHTING REMOTE SWITCHING Section 2
521e3515-43f6-489b-ab5a-e9fa425c47df |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | SEPARATOR LIGHTING REMOTE SWITCHING Section 2 | 1.5mm2 2C CuSn PVC/PVC
65b82395-5676-5816-823f-611dfce76a15 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | SEPARATOR LIGHTING REMOTE SWITCHING Section 2 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
bd5b6150-fcbf-56e2-9980-2b366b660dd7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | SEPARATOR LIGHTING REMOTE SWITCHING Section 2 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
5c2251ad-ada3-434f-a3da-0f3deedaff9f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | SEPARATOR LIGHTING REMOTE SWITCHING Section 3
2c3e8cf9-4854-431d-9be6-2dd47cfc3a3d |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | SEPARATOR LIGHTING REMOTE SWITCHING Section 3 | 2.5mm2 2C CuSn PVC/PVC
5139fc34-24f3-59c0-a0ce-5fef4fe2c065 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | SEPARATOR LIGHTING REMOTE SWITCHING Section 3 | 2.5mm2 2C CuSn PVC/PVC | Instrument Cable
9a472dbf-cbc6-51b3-9fae-dced1d456cc2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-007 Seperation Field Light & Power | Cables | SEPARATOR LIGHTING REMOTE SWITCHING Section 3 | 2.5mm2 2C CuSn PVC/PVC | Electrical Checks
9c23404d-aeb0-4f00-9055-7d3c86851107 |  | checklist-flat | not-started | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP-SEP-E-007 Seperation Field Light & Power | Certificate of compliance (COC)
aef02c72-edd2-51d9-ba70-1d9858736983 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-007 Seperation Field Light & Power | Certificate of compliance (COC) | Please upload Certificate of Compliance here when complete (COC)
82d23815-5976-461e-bff8-b531cefc064c |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power
829c89a7-1211-4456-a3ec-7957cb056da0 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Electrical Installations
1ded4fed-adf8-4fad-8dfb-7f304d4b2491 |  | checklist-flat | not-started | Cable Pre-installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Electrical Installations | Cable Pre-installation
f390522f-4a33-5a6e-b58d-94c004baedbd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Electrical Installations | Cable Pre-installation | Cable Pre-Installation
6d87b23c-d2ca-464a-9e74-b52f0e696049 |  | checklist-flat | not-started | ITR-CL-1-101B Cable Supports Above Ground | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Electrical Installations | ITR-CL-1-101B Cable Supports Above Ground
6fcde06f-290e-5c23-999e-6bf900dacc9b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Electrical Installations | ITR-CL-1-101B Cable Supports Above Ground | Cable Supports Above Ground
fdd188bc-d89c-4f8a-95ed-9280ebc09317 |  | checklist-flat | not-started | ITR-CL-1-101A Conduit/Ducting Below Ground | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Electrical Installations | ITR-CL-1-101A Conduit/Ducting Below Ground
d5e6d556-ce05-58f9-a6e7-faf89f648841 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Electrical Installations | ITR-CL-1-101A Conduit/Ducting Below Ground | Conduit/Ducting Installation Below Ground
657c3e6b-b642-4b7b-88e8-4127a7af90ff |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Electrical Installations | ITR-CL-1-111 Electrical earthing
a2802bdf-beae-539e-911e-6b7ef459084d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Electrical Installations | ITR-CL-1-111 Electrical earthing | Electrical earthing system installation
ecfa54b4-07f6-5e03-9a71-328fbd0fc757 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Electrical Installations | ITR-CL-1-111 Electrical earthing | Test Results
afc8a46d-4834-4621-a9db-bfe47bd147fe |  | checklist-flat | not-started | ITR-CL-1-108 Electrical Switch Rooms | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Electrical Installations | ITR-CL-1-108 - Electrical Switch Room
3718c3ae-fa12-56e8-b901-9185d88d3ae5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Electrical Installations | ITR-CL-1-108 - Electrical Switch Room | Electrical Switchroom (Mandatory Photo)
acc857b9-5060-4307-8379-0b9ebd1c2918 |  | checklist-flat | not-started | ITR-CL-1-102 Entec - Distribution Board Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Electrical Installations | ITR-CL-1-102 - Distribution Board Installation
ebefb702-b80c-5f3d-aa32-af6bc4744a22 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Electrical Installations | ITR-CL-1-102 - Distribution Board Installation | Distribution Board Installation (Mandatory Photo)
963d166b-a547-5bae-8f93-5409b8bee639 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Electrical Installations | ITR-CL-1-102 - Distribution Board Installation | Test Results
f65a1c51-960a-5838-8bdd-3f243d091a31 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Electrical Installations | ITR-CL-1-102 - Distribution Board Installation | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
e4305c50-7268-4c21-8846-1a79555f8d64 |  | checklist-flat | not-started | Cable Test Record | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Electrical Installations | ITR-CL-1-103 - Schedule of Test Results DB
24ef1d9e-e60b-572f-b0b8-4c2f741d2bdd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Electrical Installations | ITR-CL-1-103 - Schedule of Test Results DB | Upload completed ITR scans
e17d103c-6d92-4d17-8839-49e1429a12ad |  | checklist-flat | not-started | ITR-CL-1-109 Electrical Equipment Package | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Electrical Installations | ITR-CL-1-109 Electrical Equipment Package
db6307b8-2376-5658-93e5-f3a90303b867 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Electrical Installations | ITR-CL-1-109 Electrical Equipment Package | Electrical Equipment Package
adba6b81-7de1-4564-a42c-1f7c523f3d01 |  | checklist-flat | not-started | ITR-CL-1-100 General Electrical Equipment | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Electrical Installations | ITR-CL-1-100 General Electrical Equipment Install
e6325613-d264-5018-a248-fced5633d259 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Electrical Installations | ITR-CL-1-100 General Electrical Equipment Install | General Electrical Equipment
cc2a6cfa-48de-5183-899d-4a6d3b75ae20 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Electrical Installations | ITR-CL-1-100 General Electrical Equipment Install | Electrical Checks
2a74a344-8f8e-5e8a-bf97-ce2888f5f11d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Electrical Installations | ITR-CL-1-100 General Electrical Equipment Install | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
ea250bae-761b-411b-8f5f-aef0a731cf06 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables
aad10b75-7fd4-47a4-9df5-956520c0615c |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F01-R01
804168d4-5a5b-483f-8b60-3c6c1d9d08f0 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F01-R01 | 500mm2 1C AL XLPE/PVC
f9f5a255-f9cc-52f1-8c66-fda4e6ee47a8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F01-R01 | 500mm2 1C AL XLPE/PVC | Low Voltage Cable
99f9485c-5b2a-5221-afe6-0a0ed1a6a34b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F01-R01 | 500mm2 1C AL XLPE/PVC | Electrical Checks
fe241ad4-8e55-588c-94cd-cc4fe759eb3f |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F01-R01 | 500mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
7810e078-4f46-495b-84fb-c6b8e3b548c2 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F01-W01
20e6d964-9344-403a-80d4-c47d2c4dfd7e |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F01-W01 | 500mm2 1C AL XLPE/PVC
54826ad8-5bd6-5b93-ba88-3d2b10366a4c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F01-W01 | 500mm2 1C AL XLPE/PVC | Low Voltage Cable
578e0295-6ff3-5f81-b30e-c87b700a9cc9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F01-W01 | 500mm2 1C AL XLPE/PVC | Electrical Checks
d9e1a793-fb21-5a1d-b149-1c53d208c59c |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F01-W01 | 500mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
b058662c-22af-4453-9c83-64d862d134d6 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F01-B01
2e3e8984-fd92-42d4-a526-af4550ccfc15 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F01-B01 | 500mm2 1C AL XLPE/PVC
4cde58dc-f268-5437-b7a4-78aef6933c43 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F01-B01 | 500mm2 1C AL XLPE/PVC | Low Voltage Cable
e1eb7f24-626a-509c-8050-2bdb9807b3d2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F01-B01 | 500mm2 1C AL XLPE/PVC | Electrical Checks
4e496dd2-e819-5074-8743-c60107d06b62 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F01-B01 | 500mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
26bec50e-3981-4a47-b541-a5604952aeba |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F01-N01
ff472215-634d-437b-9a4c-4aa0d52801fa |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F01-N01 | 500mm2 1C AL XLPE/PVC
50fa37ae-df28-567e-91bc-f15e49b8ce57 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F01-N01 | 500mm2 1C AL XLPE/PVC | Low Voltage Cable
bb6287a4-f45b-534a-b1ec-be5252424e1c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F01-N01 | 500mm2 1C AL XLPE/PVC | Electrical Checks
728455c5-b652-5da1-8993-de71302fa0da |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F01-N01 | 500mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
ae32dfb9-1bb9-4bdc-94f2-d3ada3cc9b1f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_F01_E01
984986c5-dfa6-4b70-aff3-9a54b6af79e7 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_F01_E01 | 120mm2 1C Cu PVC/PVC GE/YE
88b878a3-c644-5fcd-9518-6a113d6a1b00 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_F01_E01 | 120mm2 1C Cu PVC/PVC GE/YE | Low Voltage Cable
4e11706a-28af-53bb-97af-46a56cd3364e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_F01_E01 | 120mm2 1C Cu PVC/PVC GE/YE | Electrical Checks
32939084-fb40-5de8-87dc-152f10cc0d4c |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_F01_E01 | 120mm2 1C Cu PVC/PVC GE/YE | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
034687bd-9dd4-4957-ae2d-355270a9ab15 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-R01
1efef2d3-f218-41d4-87cb-8f424e38f230 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-R01 | 240mm2 1C AL XLPE/PVC
70c955f0-79b6-53ad-86dc-4035953a122c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-R01 | 240mm2 1C AL XLPE/PVC | Low Voltage Cable
8391d7df-5e12-5d3a-b736-4c7055e5eb32 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-R01 | 240mm2 1C AL XLPE/PVC | Electrical Checks
69b569eb-4d9b-5584-9ce5-a7460f7af4ce |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-R01 | 240mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
53b47123-4718-4e45-b722-c3188e9915ec |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-W01
faf4c2ef-c33c-46e2-b6fb-3c2dee5e41c3 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-W01 | 240mm2 1C AL XLPE/PVC
5f102b1c-9598-52d0-b3a0-057e0fdde91d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-W01 | 240mm2 1C AL XLPE/PVC | Low Voltage Cable
6869f7c2-0814-50d4-b101-90200644dee8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-W01 | 240mm2 1C AL XLPE/PVC | Electrical Checks
45d4b5cd-c07a-5328-a66f-4204314b0c76 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-W01 | 240mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
0477a26f-957a-47e3-ba63-3e20e461d462 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-B01
307d1b00-66ee-4003-a94d-3ab0201b9a7e |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-B01 | 240mm2 1C AL XLPE/PVC
3c846415-432d-52b1-85de-fec750e1b8bc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-B01 | 240mm2 1C AL XLPE/PVC | Low Voltage Cable
3dede515-b322-5720-aea2-a3f56bd4962d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-B01 | 240mm2 1C AL XLPE/PVC | Electrical Checks
646b3c05-a80b-558e-96f8-ebbfa284fa0b |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-B01 | 240mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
1c8476af-28a3-4a00-8f87-d1708c452747 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-N01
ec70baa5-6302-426e-91a1-2d942c57729c |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-N01 | 240mm2 1C AL XLPE/PVC
f427e6e6-23f6-5a82-a47f-06d930632541 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-N01 | 240mm2 1C AL XLPE/PVC | Low Voltage Cable
f67c2e33-d1af-5ea8-8450-ee357703f6ca |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-N01 | 240mm2 1C AL XLPE/PVC | Electrical Checks
1a7bc550-8149-57ae-8f20-0d7a690f1f8f |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-N01 | 240mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
2d1f6c2f-008e-4fd5-a56a-85af1863cceb |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-E01
b023840e-2f31-437a-a37e-723772931f96 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-E01 | 120mm2 1C Cu PVC/PVC GE/YE
84cea5f3-0ff2-511d-810b-6f453e419a67 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-E01 | 120mm2 1C Cu PVC/PVC GE/YE | Low Voltage Cable
5ef8e7dc-6662-508d-a860-e956a7c7e89e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-E01 | 120mm2 1C Cu PVC/PVC GE/YE | Electrical Checks
c039c42a-da8c-54e4-9f62-1e6c3fc8d7ba |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB10GS010_-F05-E01 | 120mm2 1C Cu PVC/PVC GE/YE | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
a7765625-7e23-48a7-8d31-b857e71acce5 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB30GS010_-F04-P01
f48a71c0-caea-4dec-be9b-9e2c9c544ca0 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB30GS010_-F04-P01 | 2.5mm2 2C+E CuSn PVC/PVC
0e08a622-6947-5f00-ae6a-424dceccfddf |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB30GS010_-F04-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Low Voltage Cable
5a657416-ab18-5ad4-bb35-e2485b14954c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB30GS010_-F04-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Electrical Checks
afa15229-06f1-5e94-8124-272f9ba27463 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB30GS010_-F04-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
ac369544-bbe3-4415-86aa-3c723140588a |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB30GS010_-F06-P01
459aa96f-2e2c-4fc7-8626-c7e856af272f |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB30GS010_-F06-P01 | 2.5mm2 2C+E CuSn PVC/PVC
c6593a86-ce5d-548c-be22-75e43948a468 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB30GS010_-F06-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Low Voltage Cable
7518f16d-21e4-5679-98fc-efbfe89cb5ee |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB30GS010_-F06-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Electrical Checks
324e27d4-31fa-5891-b25b-0e4561dbce02 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB30GS010_-F06-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
448061dd-15cd-4fb5-b37b-6410f33df7d2 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB30GS010_-F07-P01
c81a80d1-0a82-4b38-bf53-85ed0e6133d8 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB30GS010_-F07-P01 | 4mm2 4C+E CuSn PVC/PVC
c15c32dc-4de3-57dd-94d8-59a79ccec753 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB30GS010_-F07-P01 | 4mm2 4C+E CuSn PVC/PVC | Low Voltage Cable
74c80930-176a-5e48-9548-147ea2446a39 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB30GS010_-F07-P01 | 4mm2 4C+E CuSn PVC/PVC | Electrical Checks
220c0faa-02e9-5234-9c12-fec52decdc43 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB30GS010_-F07-P01 | 4mm2 4C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
f13f1311-8de5-4a2f-b250-f406e2f77d3e |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB30GS010_-F10-P01
a5bc10b9-45fa-463b-a8e5-6fe271815fed |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB30GS010_-F10-P01 | 6mm2 4C+E CuSn PVC/PVC
2f16174a-3793-5e6f-824d-15e0777b4515 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB30GS010_-F10-P01 | 6mm2 4C+E CuSn PVC/PVC | Low Voltage Cable
5635a3f5-3eac-5ab6-9a0b-0beb23f6825a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB30GS010_-F10-P01 | 6mm2 4C+E CuSn PVC/PVC | Electrical Checks
f40c715c-c977-5579-b102-bada336fb09f |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Cables | TH00S030BJB30GS010_-F10-P01 | 6mm2 4C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
21a7885d-0533-4c70-b674-bb962b641498 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Earthing
74a9325c-133f-48de-8b74-d69e5df34155 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND01
fe746b53-631e-4c70-a33c-470c86a39874 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND01 | 240mm2 1C Cu PVC/PVC GE/YE
181060b1-2f49-5ec3-a4d0-08d22117e0d0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND01 | 240mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
fbe41536-915a-5018-8be6-5644839ad6a1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND01 | 240mm2 1C Cu PVC/PVC GE/YE | Test Results
298ce043-8669-4dd1-bf26-abb0abd06be8 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND02
4ce17c50-79b4-49cf-94c7-b0ad50618cf7 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND02 | 240mm2 1C Cu PVC/PVC GE/YE
09d4623e-1086-520d-9030-43a7537a9c3f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND02 | 240mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
d85a06a4-051b-5757-99f3-d2a336b38633 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND02 | 240mm2 1C Cu PVC/PVC GE/YE | Test Results
b3047009-782d-4695-b971-3d848ae039d2 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND03
4e364796-c477-4595-a8b8-fe1f9fd1f920 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND03 | 70mm2 1C Cu PVC/PVC GE/YE
2bd05d90-d12f-5280-a282-f335b874ed51 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND03 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
43697b27-2def-5e6a-bdc4-19493909c4b1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND03 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
4e76cba7-b039-468f-9273-a9247241e679 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND04
17ccf0c3-4048-48ca-8c8a-1388fbfb2eae |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND04 | 70mm2 1C Cu PVC/PVC GE/YE
31b60679-4737-555c-a723-1571efab0352 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND04 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
38dee4ec-76d0-57c4-a1c6-efd97ca94c92 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND04 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
3c2f9291-5fb7-405f-ad4c-d8d6327f37e6 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND05
b75b6e2d-97bb-4308-b8f4-44415b9b58b5 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND05 | 70mm2 1C Cu PVC/PVC GE/YE
5bbbd2bb-5177-5579-bb77-65032371c1dd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND05 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
c94f3ff5-cf10-52f2-abd7-88edbb0af2c4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND05 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
b8721bb3-7f9f-4cc7-9758-8e2afd4f612b |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND08-1
3b7a7dce-1cd4-46d5-9412-dbbd01263742 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND08-1 | 70mm2 1C Cu PVC/PVC GE/YE
c7fbbf41-a5e9-5e16-a45b-96857bb54060 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND08-1 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
db231ac2-72f5-5a6d-b250-5fc6d35a188c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND08-1 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
6c364cc3-3dc9-483f-91bc-00a116c7c798 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND08-2
d8a4cae6-96d3-4d42-8cdf-06f7c3244ccb |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND08-2 | 240mm2 1C Cu PVC/PVC GE/YE
c9d765e8-8cd7-506f-80d8-fcf4aa53fa59 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND08-2 | 240mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
d14bc964-472b-52b0-acfc-9dbe27fd3559 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND08-2 | 240mm2 1C Cu PVC/PVC GE/YE | Test Results
ca566a90-961d-4764-9e8a-c4be8b530714 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND13
6512d8e2-51bc-479e-9950-42f1af6d19a4 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND13 | 240mm2 1C Cu PVC/PVC GE/YE
326af4a0-bfcb-581a-a8c9-3c92147543a0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND13 | 240mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
c068a6cf-e9cf-508a-916f-95565269b962 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Earthing | TH00S030BJA10GS010_BOND13 | 240mm2 1C Cu PVC/PVC GE/YE | Test Results
7c5c412b-6af1-49ab-9fd5-6e34d37b387b |  | checklist-flat | not-started | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP-SEP-E-001 SEP LV Power | Certificate of compliance (COC)
ba36e224-0524-5d99-b4a8-8c73eeb5bce8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-001 SEP LV Power | Certificate of compliance (COC) | Please upload Certificate of Compliance here when complete (COC)
a1c3c75e-53ce-4838-9604-e1cc7ac13201 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station
47562427-afc8-488e-ad1f-24165ff93223 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Earthing
43210b99-d669-42fd-aee0-0dd66efc5611 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Earthing | TH00S030BJA10GS010_BOND09
b559cb6c-013b-4ab3-9612-2ba69ca00907 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Earthing | TH00S030BJA10GS010_BOND09 | 120mm2 1C Cu PVC/PVC GE/YE
d53bb620-34b2-578a-9e46-4c960156d660 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Earthing | TH00S030BJA10GS010_BOND09 | 120mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
67b4c69d-dadb-5508-a57a-1e4ba2234826 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Earthing | TH00S030BJA10GS010_BOND09 | 120mm2 1C Cu PVC/PVC GE/YE | Test Results
915d8111-b725-484f-9e72-113a56e86768 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Earthing | TH00S030BJA10GS010_BOND10
be122496-aa34-4cd9-9a58-e97f2e024bc3 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Earthing | TH00S030BJA10GS010_BOND10 | 70mm2 1C Cu PVC/PVC GE/YE
e7be410e-ab08-5333-b150-213e17db08e1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Earthing | TH00S030BJA10GS010_BOND10 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
23c8f97e-bfdc-5168-93e9-a64a82ce3243 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Earthing | TH00S030BJA10GS010_BOND10 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
62471e1d-7f71-40cf-8f6d-3f1ad69b61e0 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Earthing | TH00S030BHX10GY101-E01
bb9b5f9d-c18b-4c21-97de-aca8c55e82ab |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Earthing | TH00S030BHX10GY101-E01 | 120mm2 1C Cu PVC/PVC GE/YE
d285930a-0d90-54a0-becf-9929b58e1088 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Earthing | TH00S030BHX10GY101-E01 | 120mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
4217d6f6-f928-5013-93e2-4600209049dc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Earthing | TH00S030BHX10GY101-E01 | 120mm2 1C Cu PVC/PVC GE/YE | Test Results
7a6c1ccb-87e4-4e5f-b3b3-eb4e044a2c21 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Earthing | TH00S030BHx10GY104-E01
3c7c7d45-c404-441e-9176-c899c3ce8eaa |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Earthing | TH00S030BHx10GY104-E01 | 120mm2 1C Cu PVC/PVC GE/YE
fbffc795-8b8b-5ce8-bda7-bbaa0c60a2fe |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Earthing | TH00S030BHx10GY104-E01 | 120mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
434f7ee9-1476-5b0b-810e-f6fa3a53a61c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Earthing | TH00S030BHx10GY104-E01 | 120mm2 1C Cu PVC/PVC GE/YE | Test Results
7c3d5ab3-681c-44d2-bef4-c574be1a354b |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument
530e2af4-f345-4ad6-a143-c25d2c6c4597 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter
4d8a72b0-96ef-4faa-a015-b1aa194ca1ae |  | checklist-flat | not-started | ITR-CL-1-131 Level Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-131 Level Instrument Installation
92b8ad2d-ccb8-5d9b-a3be-7700ff229ae5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-131 Level Instrument Installation | Level Instrument Installation
154686b6-0a59-5cd2-bd8e-b5f765849f8d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-131 Level Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
e2e85a4b-ed81-4d21-be3f-5a3388607f99 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-122 Instrument Calibration
03221af5-d609-50bf-a7be-9e493fb4ddaa |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-122 Instrument Calibration | Required Data
4fce212d-adb0-510c-9859-5266b951f825 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
c5537c53-eb29-51ef-88ba-f47e333367a5 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
dc16025d-f9f9-4915-aac5-986e3d08341c |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning
31ee732c-8731-5f3f-9e74-e0bc316c1db0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
c9a2c38e-c5be-57fc-9d46-eb70e25d0b84 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
c31b6418-a417-5266-b4bf-59eb794ba293 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
56d3a391-ff21-56bd-9b40-bbd5cb6030b0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
ce32bc66-0765-5550-97cf-689ebf202f74 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
59296677-64fa-5d4c-bdb7-00df9ffcbe21 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
ce94b315-95c7-58bf-bcbb-6e8a46821d7b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
bfe88cfc-e7d8-5ff7-b0e5-c6830feaeb22 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
a0ccd09a-cfea-522d-ae38-30823a12f915 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
262f00de-d778-5e28-a58e-b013ca5ec6ac |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
38526a13-dec6-505e-ae56-8a0213fc9e5a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
c5d921cf-8241-5d47-b616-336755302de7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
d6fd299c-6734-5504-80d3-fc872f7f527f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
6533b933-3015-5e57-b9e7-c7644d94e1d6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
b6e91f76-3851-59c0-ac6a-d1ee1833023b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
5cb4c915-5711-56a0-a4cb-172b30a88402 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
04bf4e34-089d-59aa-9588-291a16893e1d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
f81ab0bd-d685-5b6d-9eff-ba2488044d8a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
fff3d89b-ac8d-5e64-97dd-b759f124db1c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
a04124f3-7cbe-5800-bd04-0059949ef5c1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
1013a52f-3173-5a5e-9d09-2423f7daa789 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
6a1c9815-a2bc-4092-a779-3a811ab9d3d7 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-124 Commissioning Instruments
c708d4c2-499a-540c-8210-f9da21e1f77b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Required Data
666cc01c-3dfc-57d2-8b93-fe9b7408c610 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
394f9f45-6829-50fe-bd6b-2a153e3888fb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
e656e09e-d264-5249-9419-b39cbca89cc4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
93c49cbb-8084-5464-8f21-4bdf45b16bae |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
0b62b7b7-2e37-57ed-9043-64959ce760d1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
a4a0ea7d-5dda-5095-a590-0d6bb68fe8bd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 1
aebf0a7d-5ea3-5abe-829d-7e36a9a948d0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 2
411ca47f-32aa-54d0-9ab7-b9a90f74468a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 3
f69056e2-603c-5138-8cb7-c4bd8f317a73 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 4
5d8736e7-0f18-5d2a-82c8-bf4b19c75708 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Calibration settings
9b490d33-605d-5e24-9684-b93a2521d399 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC20CL040 - Separator Station Silencer Weirbox, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
846ae096-29de-432d-baac-efdd7e13682d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1
a3a3dc9e-07b8-45af-9da5-ee5b0a63d0e3 |  | checklist-flat | not-started | ITR-CL-1-128 Temperature Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-128 Temperature Instrument Installation
318ccf81-37f3-5cad-82fb-db3dca0f2b19 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-128 Temperature Instrument Installation | Temperature Instrument Installation
37c60310-6689-5a10-832b-79697303bb65 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-128 Temperature Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
9df79388-548c-476e-a9ea-b0fb04da83de |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-122 Instrument Calibration
d801c985-a5ad-5d4d-b778-3a36506cbb9c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-122 Instrument Calibration | Required Data
0915ba89-c0eb-585a-9468-89a13ef6db12 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
9240ba4e-2c38-50c1-8be5-67dc5984d321 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
00200c33-5c9f-4a74-8b46-c0fc9a7c9062 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-123 Instrument Pre-Commissioning
085319e3-dcf4-59f1-af9a-d9499b686241 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
f40fedd3-79ca-590c-a1fc-36b0d6583c47 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
07f7c8ef-ed7f-5dd5-aa9f-fedfc4ee46e5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
9bc7e06a-631f-5bf4-832b-b0579d6e1460 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
9b8eae96-d280-597c-b23e-b60d6bd8bcbb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
01dd4281-d284-54d2-bf84-9db7c30ee428 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
fdc12a18-7cb1-57a7-9ccf-d38cc4ad65a4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
ab898234-5a36-50ae-ba98-eaa84bb978c0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
c783a6b5-9004-5745-938f-909569d196f6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
2bb986e9-042b-510c-a044-0b9899d49ddf |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
4b927da7-161e-5b03-9036-60662d2cea9d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
e09dda9f-1ff4-549f-99ee-6a35de6a5270 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
5cf8174e-6959-502c-b625-295fdb5f1e66 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
61f88dae-467c-5dba-9125-bc735e5cee88 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
092ba74e-3c55-55eb-b003-d871b4642687 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
b55f646f-33c1-5f6c-884a-33e7d9cb3a82 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
759ae37b-22dd-5bcd-bb98-2aefb75c454b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
c6028294-6b59-5460-9646-c3198bcaa1c7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
cef1785c-e7d8-5f56-9b47-e8a4c7590a7e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
7286e793-10dd-5ff3-84af-da82baac38c1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
185e7f1d-2cbd-59b2-8775-aec6be4891c5 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
22688ef5-e1c1-4291-83f3-00f4d95ccd09 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-124 Commissioning Instruments
b693103f-d6a6-5e3d-8c21-2b811c04b185 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-124 Commissioning Instruments | Required Data
5e8fa111-7f74-5765-b429-111606a39c63 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
fec30394-8ab9-5362-8494-dd49db4830e0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
058c9197-ea3a-58b0-86e1-c8da937932a5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
ea44a9fe-c743-50ff-8e51-a977892defb5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
6deafc29-26b8-575b-a268-a47100892cc5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
1572a2df-7b64-520d-9621-69bd773469d0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
72f4aca8-ea52-51ed-95ab-58778d50b4c9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
8f4312bb-f4cd-523e-9736-05636f27f796 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
8c0c2d27-2b3d-525b-83f9-13e0b8082876 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
ee1c1707-e9c3-5451-aed0-67c5d61e5f0e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
1d2bfb83-f21a-5eb4-8392-eaea4348053a |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT051 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 1 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
71f3ac47-63f8-4159-8612-f828aabcf406 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2
18c01230-4ac1-4f71-b1f9-cd3a41100fa2 |  | checklist-flat | not-started | ITR-CL-1-128 Temperature Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-128 Temperature Instrument Installation
ff41078b-7b29-5d01-8ec9-d40fc9aec6de |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-128 Temperature Instrument Installation | Temperature Instrument Installation
e2d57ff5-ac71-5c69-857e-5504e508910e |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-128 Temperature Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
80a924c7-60c5-4021-b40e-afc226e69bdc |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-122 Instrument Calibration
ce146e8a-7833-5f67-9c9a-5dc2f19c1de4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-122 Instrument Calibration | Required Data
d62a3acd-f9b7-5f1b-a935-858854d60ac2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
08fe7312-763b-5bc7-8b86-993e87b69385 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
cb02769c-da8d-4006-983e-e59074f7f746 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-123 Instrument Pre-Commissioning
688b136c-cb60-5bd4-997a-1f0ca5f8ce08 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
dec84ad2-8bc7-5158-862b-8729b1d9027a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
95fc722f-8a34-53ae-856c-5de67c14de3a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
03553039-d297-5eab-ae4f-887a821a4436 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
86528320-1336-5fa5-904c-695517684516 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
0231968d-52db-531c-93ce-b1875f5ad5b2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
b26fb352-29a3-52b7-83a3-1e209bb72653 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
154a651a-3215-5804-86ef-d1183e23ab4f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
edf0e6c4-bbe3-53ac-8352-f8da6c97d3e4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
eb50c48b-ee0a-5547-aba8-f8cdce1d9db9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
5c6e7358-369d-5e74-b4e4-a12183c1fc3f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
6ec8c3ba-e893-5cb3-8af8-5c12b5711b73 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
754e3243-3287-5c23-8335-5e47b1eb11ff |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
57e7a400-d9bc-5213-95cd-6d72eaecf392 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
94594668-6718-50b4-b362-dfa03da10719 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
b96e5f19-1866-5f54-a693-fe883449b6dc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
fd27365e-c2b1-50d0-9dc8-d96a2eed2ec0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
f722113b-c067-5c7c-937a-54f75262b50a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
146c1fde-d67b-5823-8ee9-8e7d4ef57488 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
065a215b-94cd-5493-a387-0c2a976aaea5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
d37934f7-3831-55ef-8551-54e47963a74f |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
d1f587fb-2ad2-42a5-b56b-fb7b6a1168a1 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-124 Commissioning Instruments
7152b796-09c4-5f71-a7b2-b419ade6db65 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-124 Commissioning Instruments | Required Data
32134588-3c12-55ad-a96f-c7b286c15f3e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
d6ded5d8-e201-54b0-952c-8db319f40259 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
cd1e0467-19d8-52f1-87fb-0ab129c0f809 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
a2bf9c9f-dbcd-5b5e-94ac-31b687268564 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
d50414fd-43f0-5420-ac10-62a85d474650 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
a4154200-3d6d-5b14-ab46-7aa5b0b3d4a1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
59a70dc2-5418-5bf6-b506-ec928ed83c5a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
75e7cf47-b6a8-5a2c-8d85-bba84772bd94 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
2b306f85-7dba-500d-8212-6db9a261a287 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
f1d3b35b-f849-5d9c-82df-07c98efbc131 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
9e5e5ba6-232e-5f13-8a14-01c3330e066e |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT052 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 2 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
9d74e43e-af9f-4783-b88e-0867fd5d62c3 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3
bf42b6ab-0a98-485d-9dfa-435f161bfa2f |  | checklist-flat | not-started | ITR-CL-1-128 Temperature Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-128 Temperature Instrument Installation
0b7474d3-20b0-57f4-875b-9ba8e450f509 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-128 Temperature Instrument Installation | Temperature Instrument Installation
6d1d77a0-668b-548c-835d-e2a6b65a0f54 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-128 Temperature Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
5164b3b2-331f-4296-9bdd-267437d04fd2 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-122 Instrument Calibration
f7e97c3b-26f7-5946-83f4-446c7196eb69 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-122 Instrument Calibration | Required Data
3c03ef62-b908-59f4-90b6-f7b5ceee698b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
cd8a5016-b99f-5836-bf02-22bef5a5820e |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
784910f8-4bc7-447c-8223-c4a19b8ee917 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-123 Instrument Pre-Commissioning
b3f90bd9-05b1-5aab-b137-22f023804eef |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
d82bce4e-e542-5f98-9fcb-31b2719d4e4a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
ff0bea0c-d45e-5a03-b22e-6993e706aff4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
c69ed8af-9f40-5ccd-9e38-2e1077e12be7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
4ff4d32d-62e7-5d79-ac84-e3b1b775d047 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
54665b9e-2f16-5fb2-a8e4-1ab8945d35dc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
b9d79950-97f8-5315-8ca3-82d549a16716 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
81c7b411-0ac9-5a89-b352-256e101f5ed4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
ca09afe6-7bee-5db1-b836-0e8d0776269f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
e2ae9ca3-414f-510f-8868-5921161603d7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
c5430f86-03c3-53f3-acbb-5b7e7c69488e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
403ec331-e254-5418-82d6-0aec7f4a008c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
f49371a1-4685-5c2e-9c15-d9f1841eb4cf |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
e689571b-5acb-5b2a-9715-f229430d721c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
9e73dfe8-29a8-5f8b-af70-f079a13ff563 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
7a56c634-5b4f-5685-aaac-9f83bd9f3a5e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
73fe0087-b93f-566b-ba61-d09a58f03626 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
7760cb11-d822-5b39-92f7-208fbe63c311 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
c0929a72-adb4-51f7-a667-4f38a7b42243 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
e6070e7f-b69e-5ea8-88f3-f8a82ec1d42e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
562e8fd1-fb0e-56be-8392-13b16ce65c90 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
32b29f09-86f1-4769-a31e-dbfb2d26e3ad |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-124 Commissioning Instruments
16db232a-40b7-5ef4-8672-3047f8cc4d5a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-124 Commissioning Instruments | Required Data
00b75092-12bd-5373-a24b-7c9a16315bd4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
c7379aaa-1813-544e-b5e3-597a2eeb2e1d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
76c9de6a-1149-5ad0-83e7-16a34bd8fe90 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
8a374f60-72cd-56fa-9f97-5bd524ef6a16 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
293da74c-6bb1-554d-87c6-c169bb752a3b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
a3467f3f-b6d0-598c-93ec-7aefd642fe0b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
e41255bf-f14f-5842-88d5-5ce0403c7905 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
d5db5944-d736-5545-a083-53041b275552 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
61adacc3-6562-5a0b-8e4c-f9445cb55b93 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
75eeacf3-6d7e-5072-8166-3b7123a04267 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
dcbce390-fd73-5d82-8f35-da0a8c7db68f |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT053 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 3 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
da9d4f1c-6238-4ac9-8c68-9da930837372 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4
4e81834f-f8ca-4c28-86a7-44f8e63ec671 |  | checklist-flat | not-started | ITR-CL-1-128 Temperature Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-128 Temperature Instrument Installation
996e18f5-0184-5113-be0f-2216e806d4da |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-128 Temperature Instrument Installation | Temperature Instrument Installation
4644f657-71d9-543e-9ebf-74dac659d7bf |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-128 Temperature Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
ce256e8a-fe1f-4fc2-8a4c-9ca989d47839 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-122 Instrument Calibration
a93c7a79-837a-536d-9449-4b7f88c5ac37 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-122 Instrument Calibration | Required Data
385917d6-f657-5fcb-a869-cb41307f6680 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
d5c8c1b3-475f-54b1-8202-0e737ce5b637 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
6a3edc35-f3ce-4a0d-ab90-67963eb2b021 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-123 Instrument Pre-Commissioning
917b0c0a-0427-54f3-8f52-151bb0906cd2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
806512c3-8851-5dbf-9cfe-6d4f1871dfa2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
1549fae4-8de7-5365-abe6-e765e6f7a5f2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
7fe4494e-51d5-576d-9d43-bc6a6af5a0a1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
fda463d6-62f0-5f09-9336-727098fd574b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
c2e686ab-511b-5b11-ada9-b539b532bc3d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
ec86c405-464f-5434-91b6-591b73663d2b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
5e78699f-576a-5a82-95f6-b0cd532de3fc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
6a49c579-f98d-53f7-aa2e-30c9e53ff4ab |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
776b0f5b-9dcf-5500-9b6a-b5996c377a39 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
3dbd17f1-9eb2-5c0d-94b7-f3fffb443a10 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
4d215228-c869-5763-855f-273440c3176f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
998272f3-6edd-52d5-9722-656619a92fa6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
1ab51f4e-e4ae-59bb-ae84-8a54317c8f62 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
1667034c-efd7-5ac8-b4da-597ffedb3cb2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
0ba47b9c-52d8-59f6-8509-07c5c97ab483 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
b048d4fb-e3de-5e7b-b790-5d44576e4e52 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
fd6fbd8a-43e4-53a9-b118-ff1210144405 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
0f352e28-ae23-5b80-9dd2-cabfdb621b40 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
a09949f9-901b-5053-9693-5df0dc41b51c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
3e375897-28e5-5e43-96b2-9f886f2b32ab |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
00a5fe0c-2dba-4770-a36d-c13ebfec3e5e |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-124 Commissioning Instruments
bb7b27c0-cd96-5243-8e73-de4af2af9790 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-124 Commissioning Instruments | Required Data
f6b758b2-3236-5d8b-8161-92d5f6a8599c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
93b939cd-724f-5c54-b58e-6cbcf7ae79c7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
333d05c2-828f-5d5c-961e-b02ffa233205 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
62169838-9641-53f0-8b61-e608c8c6a857 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
3c1392c3-9c5c-50e6-a8ee-821e1cab3c7f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
581846fe-4c40-525c-a94a-0a6ac36aa0e2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
8115c4bc-078e-5d81-95f2-ed125c6ab739 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
4cc6fd80-5071-5501-88a0-ed0effeb6718 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
2cf4baf9-9490-55c0-ab0a-a684b6a4b07e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
b5f89b2d-5c4e-5879-8a01-1666f08f5d8d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
47135e3d-cb37-51ca-8bb0-66cea48a71fc |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT054 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 4 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
eafc17db-d2f4-4496-89df-f70c68110c8e |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5
b218a9ef-8e88-4391-8189-320eacf7a7ac |  | checklist-flat | not-started | ITR-CL-1-128 Temperature Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-128 Temperature Instrument Installation
19c788a3-aa2c-56f1-960f-9ef8a886a81c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-128 Temperature Instrument Installation | Temperature Instrument Installation
0e5a8aa4-0482-5922-aa62-5608f7884a27 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-128 Temperature Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
767c5cb1-d445-4366-aa7c-ed5fc941b4ba |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-122 Instrument Calibration
ed378ac4-a639-543c-ab69-8cdc624fdfd6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-122 Instrument Calibration | Required Data
3d2aa563-5288-56e0-af20-2fc806e34cb6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
ee943ee3-e883-518b-84d2-5980ab96a5c7 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
a87bf103-cbfc-4866-b843-6849c5098227 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-123 Instrument Pre-Commissioning
bc6fa1bd-0a55-5080-a898-b254d6646720 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
7c05f1b8-e4fa-59af-ad46-06bb687af23d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
2e62ff7c-8079-5f6a-b24d-a4804eaa225e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
ddfdf13e-a111-5069-9ac7-6c9b4f03a450 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
e67a0903-05f0-57e9-ac24-a8fcba7b8b03 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
33d5b571-02d0-5ddb-95e2-e017204ed599 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
e7201d04-30ac-5f23-a50d-d34add42fd49 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
4cf12cee-6c31-545e-97e4-440126298f58 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
ca1fd127-6209-581d-bbd8-2b02d32e2f65 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
4c281167-305c-55b0-9ea4-e1442b5a96ba |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
b8c86022-dd7c-50d6-b1b9-d6bb097fc98b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
167cd245-6e6b-5652-86e1-cf4388cc397b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
5b9a6b89-bc3b-556a-b203-033eba3de1b7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
93f15b52-e8f7-5862-bf07-182f096bcf64 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
cba43989-647c-59fd-a226-ce91158ba76d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
d5c606cd-0005-5fab-98dc-eeb02b7bc3f5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
5bd55edd-2974-5b9e-919c-f684328bb444 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
f2f34bb3-9c4a-5a01-b746-15c772dce4cb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
b3e9be95-60c4-50fe-bac8-3352a49b0079 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
fb53cc95-2652-5fbf-bcdb-28017e408f23 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
dafadde4-413d-5ff1-8dd6-9ef664bf3c35 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
9df7d366-d428-4cdd-9e2d-3082981ab1b7 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-124 Commissioning Instruments
a936914f-0c6c-55ac-a869-d8eeb627aafe |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-124 Commissioning Instruments | Required Data
b7276eb2-f555-5768-bdf3-9ed61d372573 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
1a54b585-b483-5694-9e5c-909a94ed606f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
01d3dff7-ad03-5cec-9cb8-60a19f090adf |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
0f8d1d15-2974-53ae-b4a9-c8c718d586c2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
fc5b9cc7-1289-5ba2-8dc2-27f91263f952 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
921ee476-f130-5883-a98d-e2a81c4f0ed0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
343eedd6-8922-54c2-80c4-4ac5768ae715 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
5a39abff-b4be-5f60-a4cd-65bc5eecb596 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
cf89fec4-bf2d-5668-8bfb-7a6fe6554962 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
70456794-0455-5625-af34-8fddc7e140e8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
bfa65203-6372-56a8-ac1b-577f636a24c7 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT055 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 5 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
6914865b-e45d-4dca-814c-a3d68a9e3eaa |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6
9572d54f-42f3-4c77-afa9-ba3c5fa9d1d8 |  | checklist-flat | not-started | ITR-CL-1-128 Temperature Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-128 Temperature Instrument Installation
219f8abe-cf9d-5776-8e75-f183643b981b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-128 Temperature Instrument Installation | Temperature Instrument Installation
eef869bf-c939-5c16-9a17-66df95250e5a |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-128 Temperature Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
08938566-5316-46e7-a88b-696cce41c8a8 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-122 Instrument Calibration
f62abb6b-35b8-58df-b186-4233d2b8173e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-122 Instrument Calibration | Required Data
8888e64b-fc56-5b34-82c0-4dfb9476e0fd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
0c29ae49-ff96-52cd-adf7-c990e32dbe67 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
a20f8bc0-156f-4a5b-8a44-dbc7510dab7e |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-123 Instrument Pre-Commissioning
a426bb93-0083-5a08-b77e-37801b2b280a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
c5618548-ac31-5a4f-ad1b-e8b9394e324c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
a015ca2c-a4c4-540d-9588-25990db2fd4b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
21c0a8b4-bdf1-5729-915e-4f979b294d0d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
616269ae-1ccd-52cc-99c7-b70f11b44e98 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
cdef08d6-3294-58c7-8dde-e3d481b8abbb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
63ecba73-f477-5b79-8e39-57a292a818f5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
55e653e2-9383-50c3-9938-db9a29d31136 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
20793206-aef0-55b9-8cf5-e8b2dc725cfa |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
4b88e3ea-0bba-58ca-a246-f2f011c99340 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
63cfab2d-c517-5821-a0f4-62102cc45b90 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
9db3a16a-95e4-514e-b792-f46aeff7e7f2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
007ce59c-8d1c-59ff-8de9-5befa0e71614 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
d6d3908e-5f70-5b63-bda6-322455b5b15e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
1ee721f7-ef5b-5877-a0a4-b4046a672c51 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
721d88b2-c683-534d-9567-1835585d7ebf |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
edfd0b75-2008-5816-a73a-66e40f869538 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
cf1db05e-20bf-53be-9852-349d7efab0a0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
9d309e78-950a-5b84-96cd-9f7954ae8bd8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
6589e53e-47a5-5ccc-bfbd-1c3f5429607c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
b0527163-fa52-516e-bf83-540618876f90 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
cd17e9fa-d55f-4695-a497-b8ba77e120c6 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-124 Commissioning Instruments
7cbf79f9-60b5-5eb2-9681-3f879904c73b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-124 Commissioning Instruments | Required Data
32ea8056-64f9-5cf8-a219-29c2551d0385 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
839773fb-dca4-5285-967f-347dc8101812 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
193a27ff-12df-5d08-b45b-4f38d7e64883 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
4268b716-34a0-5065-87b6-2452479f6c03 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
32b1cdca-15e2-5e26-8c87-2dfa36ef9c01 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
4bbb9747-807f-5362-8037-b81e0f190d70 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
af67ee34-1a3f-527f-8440-f2094f65cdfc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
4d7e08f9-a3a3-5602-b2c5-8a99f60b22cf |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
207b87bd-a821-5d40-b928-9f96456a44fd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
47e0ae9f-0793-519e-ae7d-74429d97a2f6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
70445d4c-8d52-5287-b932-972df8e8053c |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT056 - U3 Steam Supply Rupture Disc Burst, Temperature Sensor 6 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
f02fde6e-3dd5-4c79-a6c2-d0e9a9d0c570 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint
7e28cb52-e245-44ce-8f9e-8c0f98c98831 |  | checklist-flat | not-started | ITR-CL-1-121 Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-121 - Instrument Installation
d000efb3-d49c-5ce3-87c1-733ca5d4bb61 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-121 - Instrument Installation | Instrument Installation (Mandatory Photo)
865d09cd-e5c1-5e37-b3fa-5377c6a98e72 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-121 - Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
75f2112c-9188-4c53-9e86-0c8ad18c9658 |  | checklist-flat | not-started | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation)
46a30795-8a6d-5184-a66e-395ea15cb3f1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Equipment
91f0bd6b-97da-5965-96e9-4115aa5ea0d2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Valve
335e9a58-4b09-584a-849e-b97be0142c8b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Actuator
5824b39a-cbd4-5c6f-9439-41b19b1b1920 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Positioner
67c427bd-32e3-59a3-9f13-1d363c1535fd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | I/P Converter
1ad405ec-11c7-5613-82cb-64eeb0b74c3a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Filter/Regulator
f41d2eb1-55df-586e-b608-564e32cc2e9a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Fail Action
af77162c-8fbb-59a2-b946-b208f7faceca |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Proximity Detectors
e1dab7b4-d3d0-5e40-bd16-502778454d41 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Solenoid Valve
001110c7-f4d5-5e63-9b55-538af181c38d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Pilot Valve
364f2cc0-10c0-5aef-81b4-6f526a1013ac |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Hydraulic Actuator
4142fab6-325f-5253-926d-2a1722d6c40c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Accumulator
5f12a066-9372-5624-8ad1-329efb13e1e8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Electric Actuator
f7a25a4f-efca-5a65-877d-5ce6ac7b4db2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Miscellaneous Equipment
c60d6363-0259-5bb6-acf2-73bd8e424e56 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | All relevant signatures (Installed by, Approved by, Client Representative)
eca53618-f1ff-4cef-ad43-fd277b3a19a9 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-122 Instrument Calibration
e5588ceb-cd60-5976-91d9-b7b3dbaf78b5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-122 Instrument Calibration | Required Data
2a87246b-1714-5e38-a776-acc715b97951 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
4ebb089f-5af2-5050-879c-37afd419ab32 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
aed40274-6f42-4522-bca7-3e83e0bafe9e |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning
4c071e6b-8f6a-51fc-b7b4-345f632ef744 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
29b12d70-4eab-5be8-a111-90b7b696c916 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
feecd539-69e2-5050-821f-cf6dfb44d98c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
3b4397c4-fa70-5a0d-9889-52a38edd0147 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
e0b3fa05-0d2f-5d51-be4a-0290231f2a65 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
83c38c61-37cd-55b4-848d-7476c4302659 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
35daf3d5-0b96-5325-8cc7-052bee307509 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
c8230fd3-2543-573a-a129-49f73f413db2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
e12f20a1-7785-5d45-81cc-b332ec31d95c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
33dc3fbf-f47e-5503-b9cf-afe9564f3845 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
20a16c4c-cbd8-5ba0-a0bb-a384cef874da |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
ce6cf9f4-b30b-5ab3-9667-dcdc5b714237 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
e0abf90b-854e-5114-bc0d-f6a6df79d647 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
2a1e83be-4092-5459-8c30-87f5779560bc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
2ed3367e-d099-54e8-ba1a-3f2a47781e29 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
60d4a449-ddde-5a8b-a208-83fae878ab2e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
5c8ec469-50b1-563c-9692-551ae7e177a3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
d57fa331-a0e0-5fe4-9d93-1d43d4ed6081 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
886ad8bf-6fe2-5157-b69e-f6d42ac581a7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
b4598f8c-59ef-512b-88c6-e0936e0ae6e8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
d9078b87-e47c-5b01-896e-9f29f5ef31d0 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
6d1bc232-65ea-4490-a114-c7060a370be5 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments
286a1c02-38ac-5298-8d6a-2a2f693f40f1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Required Data
bd569f9f-2008-5203-865e-11873772e0d8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
efc27831-59fc-523c-b57b-a9903fabc6bd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
feb57844-c091-5f8d-89bb-39172485f772 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
f8515ca5-d3b8-5b17-9d9a-fad2e32e4351 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
803ebc58-5338-5887-9bf1-839f3173f360 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
792d1219-554b-5839-b279-795f8f86b504 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Set Point 1
efe64479-7606-543a-99e9-c29caeb065f2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Set Point 2
6aefb60a-ae61-5dbf-a566-037fa62e9936 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Set Point 3
fa85c5c4-b679-51d4-8194-29931fdef0f4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Set Point 4
e9c710fd-9a86-5a29-b2a3-584100a280a8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Calibration settings
41bc8960-6b6f-5399-b13e-e7e00faa6c24 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
f3250c25-871e-4647-97a4-6c78131f6308 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint
132bf510-27a6-4c27-a70c-2c0d0d8b2e78 |  | checklist-flat | not-started | ITR-CL-1-121 Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-121 - Instrument Installation
8a2bf56d-c053-5035-8105-a76af81d9a5c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-121 - Instrument Installation | Instrument Installation (Mandatory Photo)
0c2e0f6f-9ddb-541e-a2eb-74f7d198950f |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-121 - Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
57f46ef4-a2fb-4e38-80cd-b4b306890210 |  | checklist-flat | not-started | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation)
c351df39-4a1c-54e4-bf3e-b0e526f33273 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Equipment
fa691754-9240-5273-8451-d22f55465f2a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Valve
62137b6a-aeaa-5b7b-bd0b-cec02c3cca10 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Actuator
e14c1867-a6ea-5a42-a04c-63bcf7fc4957 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Positioner
f5e30f7c-3af0-5fda-bc19-582b22c8f850 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | I/P Converter
996f3854-03fe-587c-b88c-4798e6afe5a4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Filter/Regulator
03fb6bf8-91f3-52f8-9118-32eb693c34dd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Fail Action
c96e05a6-431b-5fb3-8d53-d7c5eb9b7226 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Proximity Detectors
0f2ecd76-e33e-5a60-9e9b-1939589a0983 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Solenoid Valve
58fc1662-cd86-512d-bf30-abf356d18c5b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Pilot Valve
e3942d6d-0508-5ff8-b14a-581a9f6952f5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Hydraulic Actuator
76f28d81-0110-5126-96e5-9572e1afe681 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Accumulator
0ff8138f-a558-586a-9b4d-6afe62c79a4b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Electric Actuator
356897f4-04cc-5191-b46a-a3fb5226e31b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Miscellaneous Equipment
37fe4f3b-2e53-54ab-85bb-be7b086c7b2c |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | All relevant signatures (Installed by, Approved by, Client Representative)
d518d526-bfa7-4a61-a05a-5e05be112bf8 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-122 Instrument Calibration
02ec8d59-5bae-5d56-b793-ff2d65b743b4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-122 Instrument Calibration | Required Data
ed90bca0-5973-5015-9cdb-6460618a6d17 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
a1e7641d-0b84-5f2a-98b2-129ecd27960a |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
b47d2b82-af6e-4412-84a5-89d0f1a4007f |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning
542c3a2e-d391-556f-87d5-196c20816b49 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
704cd93a-8ef3-556e-9e66-43c3db0d42a0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
bbfa3d06-ac96-5026-8335-6eec48fb3992 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
5e3a5f0b-d43b-53e5-8533-fd8bd7608c86 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
0cc6a50f-6681-51d7-9786-687f96e06d07 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
e1eb1cdd-7977-5682-880f-0072c8c5e1c7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
ff42a82f-2fa7-549d-96fb-f834a55d56a6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
fd8ad8a5-d98b-533f-9046-51cd3d49cdac |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
bb492847-ba75-5598-a57f-71376937d172 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
199625ce-d804-54f9-904a-1f7777a6deea |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
6184db08-5996-5fb9-8582-e6f41e13593f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
4e08e9f7-5ac7-5428-9528-f163fdf69f24 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
b41579c1-96fb-5198-8c1b-e63363917b19 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
96a2e316-6a48-5a00-86c3-1a489c439bf9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
a9174d47-9eca-5638-9a70-3f1f1f38af7a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
7cab1ad7-7bd7-5dc6-b330-ff5e3ee6cf21 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
74f56f2c-2b78-520a-9538-b867bc944937 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
4f085126-6946-5aae-b24a-a750f938dae3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
bfbef397-ded8-5d97-9bcd-681ed3cefc62 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
fb7900a5-9ccc-57e6-a894-fff1e37b49bb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
cf3976e9-d932-5ec5-9063-8a3dc61ffabb |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
2367e255-8d73-48c0-8b21-c010d72a3920 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments
a3b475fe-9850-5fac-9748-50e79dd7865e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Required Data
3366e457-08f8-52e4-82bb-5ffa7af3ff79 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
ff07d358-2997-5d38-b588-f806e31a0183 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
4b2ecd88-7019-51fa-9cc7-61c44493cce7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
6f9899bc-37bb-51d4-a327-5a6c20f9c019 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
c976d845-e254-57d2-9376-376f7f1d93eb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
4cda3031-e82a-5fcc-a216-59aa07e869e8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Set Point 1
afc7c168-08f9-55b2-bf61-0e6ebbfcc82e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Set Point 2
0a939c84-790f-507c-aefd-0300d716e533 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Set Point 3
3713115d-5230-54f6-8226-a2e1275755e4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Set Point 4
d880cdf7-d69f-59a5-8466-91ba2b2a79bb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Calibration settings
6958bd4a-6764-588e-aee6-192096a903c8 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
0a9306d5-d445-45fe-9517-9b83c02f0142 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint
6166286a-1bc0-4446-9a43-961d8923b44f |  | checklist-flat | not-started | ITR-CL-1-121 Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-121 - Instrument Installation
9fe7da5f-9e2a-5cd9-a37d-20b291348c29 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-121 - Instrument Installation | Instrument Installation (Mandatory Photo)
6ac6d573-663a-5885-b526-d5b8ceeebf2b |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-121 - Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
066ceffd-fa8b-4dcd-884e-f88431f69943 |  | checklist-flat | not-started | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation)
86b5905f-db8f-595c-8a9b-157988a8ef94 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Equipment
3d4428b3-27fd-51ea-9532-e475a827b2a8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Valve
9de589bc-1de6-5d5f-b143-5ec7e83d7b93 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Actuator
9c096623-3d62-58d4-8a5d-6d90fb41f2cc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Positioner
db5019ca-cfbf-513b-bdd1-ff8149c26f8d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | I/P Converter
845ed50c-0571-5b67-94a6-deeda73db612 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Filter/Regulator
4f6396cf-90b2-551e-9e5c-38e893713da9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Fail Action
5cead445-e00e-5736-b3b9-ed7e04e92d9f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Proximity Detectors
fab982e0-7b03-540c-84b3-04b8ab813156 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Solenoid Valve
d463689e-eae2-59a5-b3a1-d52f090b34f4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Pilot Valve
86a802bf-41ff-5f20-bc7c-a555e5cf8fb1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Hydraulic Actuator
9549eece-5740-5328-899d-63366f68eaf9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Accumulator
a325d7c9-4543-5953-8289-0f4f13c0c87f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Electric Actuator
357dde77-9a55-5f86-86ad-2fcfd9e175d1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Miscellaneous Equipment
e61fd7c6-81c7-563d-aa40-4622a02247bc |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | All relevant signatures (Installed by, Approved by, Client Representative)
ebe6b7f8-9996-4597-820b-929dbd5cddff |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-122 Instrument Calibration
113fac3c-ef67-5829-b58f-386752d83cbb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-122 Instrument Calibration | Required Data
56210ba7-de1c-5397-a353-ce953c5e3e32 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
bf55e2c4-7bf4-5993-b69f-cfb92718c0c2 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
0a4471ad-7f08-4a8b-ae99-6b20fd56cdc0 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning
b4a6a6b0-08a2-5496-b26f-863d9629755b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
39262eb1-a1ab-5eec-a4e7-e7832780d4c9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
c5d17ff8-5555-5f62-b56b-245c6a60b423 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
7d4e1347-126f-5bf8-86f1-667d96ae6a9a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
d631750f-b8dd-54b0-8d25-9a22771b134e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
218c4509-b6b3-5d3c-8138-43c841283d53 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
d735ea33-bf6d-591c-8abc-8fb88f9db459 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
850029ff-7e44-50c8-b9b6-0b5d1b291e25 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
ceb6c81f-58de-586e-8401-6b2885267f79 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
774579b7-b72f-5997-88e9-48f8b861b29c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
261530fb-b26f-5390-84a1-d55f1ef72f65 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
c24384dd-e587-5838-a01e-a10b1845de02 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
cc9b6417-7ffd-5cd6-a6bf-3f128c53782e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
52a0e37a-59aa-55ce-ac9a-94163e4497d8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
ec1b7002-11e0-5647-9e33-2e7aed17a7cd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
8656aa99-1a2c-5113-a3d9-7284dba931e5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
be7cb25e-b7cd-5cbc-bcb1-b53552067070 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
70f508e6-80de-5f6d-bdfb-ae4760d916b0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
c707790e-3b79-5910-8bca-10c0eb1bb596 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
712491ac-9f12-5101-9579-f070170dfa86 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
4169a67a-f2c8-5de4-a36d-7a7995cd013b |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
36c64a6e-8964-4f80-a7e2-1eac6d8ef86b |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments
0d273fcd-f131-524e-aeaa-7866641aa112 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Required Data
8099b2de-468f-5366-bb71-b585e35efe87 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
b5e086a9-5c89-569e-b9c7-9577051be0e9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
a1c24b9f-4507-5893-9d1c-7893c3165ced |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
84ab36a0-21ee-576a-b686-0d85668091b1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
841db455-f84d-5779-b57d-b08e15385e70 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
12b97098-e5b9-50e6-b763-18cc23af49a9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Set Point 1
46d24559-d7da-5ed6-bc0e-cfc6a29d2fac |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Set Point 2
e1e720f3-918d-5636-a50f-ab4f1387a083 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Set Point 3
a2208b5a-8d04-5af1-90ca-26bc46d25f8b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Set Point 4
1cb51840-a336-55ef-a799-d2d3d04d3e71 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Calibration settings
d2beb726-42b9-54ca-93f8-fb8c84ab70e6 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-FEED BACK AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
9302cd82-2dc9-4bc6-b97b-aac9569ec641 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP)
b272bd79-e114-4606-b3e0-b346ad03fa3a |  | checklist-flat | not-started | ITR-CL-1-129 Flow Meter Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-129 Flow Meter Installation
28f111a5-dcab-5f3f-858e-bf1a06e5d0c4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-129 Flow Meter Installation | Flow Meter Installation
64890cbf-a33e-5a16-a3b4-027ad56e376a |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-129 Flow Meter Installation | All relevant signatures (Installed by, Approved by, Client Representative)
11fc4569-dbbf-44ca-8303-aa708d7a4321 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-122 Instrument Calibration
af3650da-e88b-5a83-bed2-1e95495c1af0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-122 Instrument Calibration | Required Data
3400a0f6-adba-5ef7-8eee-3b2d7e053324 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
a03db5e2-451e-56c0-a36f-48313023f34b |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
02b2559a-dcc4-4b64-b168-89f2fae3ca7b |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning
d9fa20ac-796e-539a-9b83-bd31f93129b8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
0ebaad35-9335-5e0c-9688-18f78dc5dc45 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
e447e69a-60aa-5eb3-b873-cfeabf22a7a0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
bbe7fba9-f38c-5c40-9205-8129061c64fe |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
7f4a961a-86de-5739-99d9-082ffad8aacd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
3da8bd19-cfb4-5cac-a1ae-3f1cf59b6810 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
165d9403-a44b-5c8a-85bf-2b120494ad12 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
169fc582-0f7c-5db6-be39-ae924e522a38 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
24adfce2-1706-54d1-97d6-0db93fa16b61 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
c006228d-8f32-5bfb-91d0-4b865e034fcd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
54e794ee-d5d2-51fe-8507-1a158778866e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
ba45ed64-6661-5a4d-b67c-e594c14b5840 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
49ca1280-b44d-5e9f-b836-940866de55db |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
0472159a-3958-57ea-b857-aace429ee544 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
b749b3af-718d-5e4e-8d5a-32962b32de69 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
72bd9bf8-7e33-5247-b553-a6ff22a70cae |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
c9a92c19-dff4-56fb-81d6-8e40300e60a0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
a80f3d42-6c14-5eb7-9a5e-e996729a0f15 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
72159891-083a-5651-b4d8-54fe6de34d15 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
010c64ff-c61b-5e1b-a0d2-09b5ec9b5dab |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
dbfd9785-26e9-57ff-b016-42dab8638e38 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
25cae203-980a-4c3d-8681-74f41c6b3436 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments
109617fe-35d9-5d60-abc2-f3efe6e86aa8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments | Required Data
480f9a93-fd68-5d17-8d06-b9eeff0c40fd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
d92a5749-754e-5434-a4c9-c7de9816601c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
cd1672b1-4b88-543b-a08c-322dda4c228b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
35eead95-f738-5bcb-8b77-03c13ee45213 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
51923a1c-d45b-57a9-bb21-d73ee424552d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
8193989e-b3a2-5b97-b319-76f8d5d8d1e8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments | Set Point 1
2a199a5a-6ce1-5e0b-8f15-a563f4d8d8de |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments | Set Point 2
ef45ec1f-2b8d-51f6-a4e4-fbf47e97ebe4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments | Set Point 3
857f25df-edb7-59de-b94c-a4e0b5707158 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments | Set Point 4
78d8c367-07f3-53d2-85f4-ba2b79d97f31 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments | Calibration settings
c150c2e8-eabc-57ae-a3b1-7c3b350bde25 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF010 - U3 ORC SGW Supply, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
3311447e-57bc-46cd-8247-2a6afc28ac43 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure
e6fe7bd4-eaef-475b-96de-0e4369261b46 |  | checklist-flat | not-started | ITR-CL-1-130 Pressure Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-130 Pressure Instrument Installation
99e637bd-967c-5b15-8eb4-0016d89acfc3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-130 Pressure Instrument Installation | Pressure Instrument Installation
5863f53b-19f9-5d8a-be9c-42dd3149c16a |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-130 Pressure Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
817bcf1c-eed0-4549-a16c-0eb6b61f3596 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-122 Instrument Calibration
8f86756a-1b68-5daa-947d-31bc3f297073 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-122 Instrument Calibration | Required Data
e0a822f7-dda0-5901-9a63-ca38e4799e78 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
c403bbf2-3c25-5655-b228-5786b0761361 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
9fa32e21-0500-4466-a79c-734851f2968c |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-123 Instrument Pre-Commissioning
3ccab48f-8825-5d4d-bf78-eca9ec819381 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
59b31de9-f36c-5427-b7c3-900b477e68a5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
9f4617d4-f84a-5b8c-8e1f-9b40f8a08e0d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
5985d36c-3a88-5378-8b51-fcf926a5f63d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
4c7acef6-911a-5d78-8cf3-743eb6029f1d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
0a5b88c5-7912-5372-a280-98924a523949 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
60698136-2def-5538-a12c-6d0f33c5f04e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
83e62313-6d95-50ab-88d0-21cac501b893 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
a7257b5f-ef33-5c95-a01f-140a5ec9ee38 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
a71d2f84-7a1e-5d10-8da3-6885fd45eac3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
fe597b0e-c71b-5942-bc20-ca61a71debec |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
bccd2ecd-f98c-5301-a3f7-a35b73bf6e1c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
6da3a81e-6bed-5ce1-9a2c-fe1cbf27a444 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
bcb51d5f-7758-5ce4-b8e9-3555d0519b7d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
ce8134b8-f61b-5bca-8ac4-9199bd66ff86 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
c64bd31b-3b60-560e-9621-00dc6424af28 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
7fcad09d-61de-560d-943c-45e6a1ba2b29 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
e270805b-e8b0-5da0-858c-60c214118295 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
2338434e-ff23-55b2-a9ac-924525fd91f8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
fae65f68-7da5-53d1-8b24-33e4d1f6c583 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
00fdad7e-1bcc-5c06-94d0-a5a11d02252c |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
87996b87-c5c6-4561-b185-9a59e6099a1c |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-124 Commissioning Instruments
eda4d00e-7695-5976-8fe2-91d54896f325 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-124 Commissioning Instruments | Required Data
55f75adc-863f-56d0-8cf8-d380bdb55e05 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
849e1591-6bed-5738-94d4-46816dd15c61 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
a9019b64-e2ee-541d-8d84-4dee0f5a60e6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
0149f575-4847-5edf-927d-011b6da2886c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
c909c90c-02e7-5b31-a8a8-125b064b6a21 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
e6f1712f-e340-5e6c-bb5d-20c2bf8395d3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-124 Commissioning Instruments | Set Point 1
49558ace-ecdd-5ea1-b2e5-36ede7395f02 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-124 Commissioning Instruments | Set Point 2
f019c050-7917-5030-8be3-bedf423b9bfc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-124 Commissioning Instruments | Set Point 3
dd3d430d-913e-5094-a28e-58a98b703eeb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-124 Commissioning Instruments | Set Point 4
0da7203b-57fc-526a-9c00-de72a6980fef |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-124 Commissioning Instruments | Calibration settings
b76c25e8-6110-5a18-beff-9cbff8c17f42 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP010 - U3 ORC SGW Supply Strainer, Differential Pressure | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
fa2cc5ea-2ace-4cf3-866b-36ffcd516f30 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT
57cd77dd-e6f5-408a-bc94-c428a24db735 |  | checklist-flat | not-started | ITR-CL-1-121 Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-121 - Instrument Installation
78aa35f0-fa1a-540a-9bbf-d11ca65f3f88 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-121 - Instrument Installation | Instrument Installation (Mandatory Photo)
909da801-3a74-5c13-bbb1-f42794e9e05d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-121 - Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
3ffc5c14-4906-47e2-962a-e0ea8dfe29eb |  | checklist-flat | not-started | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation)
d3a51bd1-0c0f-573c-a106-455865ea7bb2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Equipment
5badb37b-dce8-55e7-b41f-6b846a3103d9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Valve
173f8e9a-97b1-55fb-8f32-784a8ac50ea8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Actuator
e7f369e1-d4ed-5702-af4b-a4d97cb0f633 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Positioner
1dbec1d7-027d-5f79-a9c9-a6216fddedc1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | I/P Converter
40156809-3d86-5754-b6fe-720903ba108b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Filter/Regulator/On-Off Valve
71a4e50d-349b-581b-a2fd-4360495745a6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Fail Action
c752e145-e191-5053-81ad-3d928b953574 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Valve Field Calibration and Hysteresis Check
87ff22d7-0502-5646-9955-012ceed11242 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Proximity Detectors
6fd560e7-ac06-5f53-84ce-2b562d7629c5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Solenoid Valve
b38674c8-79f3-52d1-8d5c-9f089cbaabae |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Pilot Valve
1e5e21b8-7710-5f76-bf57-d5bcd35f26ad |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Hydraulic Actuator
85be6120-d6d1-5e75-9a66-73841b93bddf |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Accumulator
e7537d0d-6190-59b5-8635-c3f9fc08815a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Electric Actuator
32e464f2-62e5-52fd-be03-cddae61b712a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Miscellaneous Equipment
6289f64e-3fe5-5f71-98c8-3c53c1f55903 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | All relevant signatures (Installed by, Approved by, Client Representative)
5dc2f629-32d3-491b-a394-b70fa3586358 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-122 Instrument Calibration
88cf11e3-9ca5-56e9-87b7-cffe35b3ec33 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-122 Instrument Calibration | Required Data
d6b72f3a-fba0-564f-ad3c-fc47b218c15a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
73a344a6-9935-590c-aa58-c46e84689fbd |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
b26e3186-647c-4d1f-b197-55916139c1c9 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-123 Instrument Pre-Commissioning
7a1558c7-a8fa-5d07-9e48-3719cfb53f5f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
9ec64f7b-f984-5247-9627-b4c14e2eec9e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
612c90d6-4e7f-56a4-87be-c967117c9f5f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
ed23fa94-dd31-5b83-8fbe-52108d1c6874 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
fde91cca-c913-55ef-bbb1-bc2c06f88099 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
1ad76b90-2b0c-50f9-90dd-6af3755f6c9c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
44331e25-71bf-5272-bdbc-a72112c50323 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
72c5f73d-6295-56af-9338-1baa251f1a46 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
a7b29a2e-1b6c-510a-a50c-e3eafc5f6463 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
cd3d4ac7-4a89-5e5c-9cbd-ca421ad573c6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
d271cb2c-1ccd-54a0-9846-cf66509bdd70 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
54faa220-ba1e-5965-8cc9-d76edd93846b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
cf9b795c-48f1-5350-9e5c-23f716d8ee9c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
c82d2e7b-6424-5d84-80f4-54dc3672f9e5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
cd13f13f-09fe-576d-b7be-1e6aeb783453 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
84fc1f1d-d61e-5f25-8d9d-02483a8ab2c3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
295f1e50-d6d3-5cb6-aff3-474c2c2931d1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
b8e763ff-7bdf-5bc8-b0bf-d67706635ec9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
39bf1ff0-233f-5371-869e-4cddb6861704 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
3807ed74-8d36-5d0c-a38b-8ecac85d1ff5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
bb4c4e62-bd65-54a4-8e74-75e278d1f0ea |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
967f820d-ca6e-466c-9e0b-18379ddf5960 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-124 Commissioning Instruments
cb4ed9a4-3885-5681-a311-2645d310b4a8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-124 Commissioning Instruments | Required Data
90158148-0a35-5a85-bbbd-509e79634419 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
98e7463b-cc14-5f2d-90ff-e21e1bfd9cdd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
99c72918-39d2-513b-b631-ad8ad66d9cb2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
32336f2d-b1ab-5287-a9ca-47c1f2c0d88b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
c831f401-6fee-5a06-8163-b7aecc96b208 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
21ccecb1-1482-5e39-bc60-0226b163ae44 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-124 Commissioning Instruments | Set Point 1
8be33ec1-efb9-5ffa-9fdb-621d70e2f003 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-124 Commissioning Instruments | Set Point 2
4e8cf60d-690b-5b15-8639-d905f7f66f2f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-124 Commissioning Instruments | Set Point 3
a610e372-fca3-555a-953c-de6c7ab4fc28 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-124 Commissioning Instruments | Set Point 4
8c8c4aa9-ebd4-5fab-a37a-7b026130a97f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-124 Commissioning Instruments | Calibration settings
6ea32fe2-8f9b-5a21-91da-49117e7784cc |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)-SET POINT | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
e5b40218-e1a1-4fd7-a5fe-9c48a265269f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint
01494040-5a8c-460e-886b-c70d5426830a |  | checklist-flat | not-started | ITR-CL-1-121 Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-121 - Instrument Installation
630be1a8-3ece-5df7-a8bd-1307c31d3b9c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-121 - Instrument Installation | Instrument Installation (Mandatory Photo)
b36c48e3-5272-5dfa-a965-2d2a5d42f742 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-121 - Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
a2a54a04-8057-4aa7-9153-7beff0342146 |  | checklist-flat | not-started | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation)
6fe3dce4-d3cb-5d71-81ff-e06f6f3fefa2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Equipment
cccd215e-1d4e-57e7-9921-1f243ebdb90f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Valve
f38f38a7-c8a9-5b12-9683-a0004945f5c8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Actuator
34d21dfa-462c-5f30-ba57-8dc2be64ba5d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Positioner
e35460d3-ac12-5455-a2d0-e1f55dcfb65f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | I/P Converter
17c544d1-1500-52ca-b730-0c4066f46741 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Filter/Regulator
2665f159-62c6-5188-9136-25f0ad7a546d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Fail Action
24020508-640f-5a7b-a23f-28df07e77b05 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Proximity Detectors
e639eea9-05ab-5f77-b510-32fd1a56951f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Solenoid Valve
9567967e-48d7-5ddb-b893-6e2a4f974c0d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Pilot Valve
d5e741d7-5b35-5b12-bdc4-9771523262b1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Hydraulic Actuator
77220a7b-e4e7-5a8f-9529-f580a4eee226 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Accumulator
68120d43-7f21-597d-8b8f-e0d007a8fb93 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Electric Actuator
c9e6b8fe-255f-5408-8480-b0fc826077d2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Miscellaneous Equipment
8ee8d541-6c26-5fd0-b984-0c51c96785ff |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | All relevant signatures (Installed by, Approved by, Client Representative)
ef46c46d-1b5e-4b23-ab10-21656cfa4e34 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-122 Instrument Calibration
478fb31f-06d2-5ce1-8ca3-dc88ac920beb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-122 Instrument Calibration | Required Data
4c000590-685d-5212-a6db-a26a9a55f381 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
7cd39699-2b33-512d-8101-1694ad8da441 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
80006121-b17e-47af-93ac-40460216161b |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning
b2b12bd9-d0bb-5965-990d-ef0a64993b2e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
1e3ca097-7bee-5bae-99f5-b8191d5c3f4e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
d9aa7cfb-1524-582b-8cb0-31c44089126d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
8e900125-879b-5589-bc22-795e3d09af1c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
8b7ba9c9-ffe4-593e-9be9-ce33e5779f2d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
e1ec3119-fa1b-5f15-9360-e963a6635bf7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
4baa9563-b940-55ea-9625-181c131e931e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
d3195933-9531-58e0-ae4f-f4919e726aa1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
199f9cf1-0038-5525-925a-408081a39d80 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
a2f79792-327b-5077-b423-8f2b6cd6168e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
cc29b108-7214-5c59-9787-e6ff6f3c091b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
80fc280a-b1ff-5c97-a924-cc9c39793ecf |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
47853b48-8e79-503e-b01b-5d64fc5d6f91 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
e0fdc194-9b0b-5033-8c36-84dd9253174a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
6e4bd7ca-88c3-5e89-9da9-23c903ac1afd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
6199980d-16b8-5ca2-a555-976a3309e6e9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
86a4c3fd-5a17-56c4-856b-933469caa588 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
f4d2028e-4f6e-5a21-9a4d-bf13efbc5f82 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
5b4f8671-941d-50b5-8954-dd4ba6dd6753 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
465b35b1-9bad-53a5-b526-4ed987a0b65f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
9923799c-94e9-5d60-b4cb-42d5268e103d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
45c6aada-b43e-4632-9b85-48f4da53f4a2 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments
d0804945-2a3d-55f6-82b6-bc09799c0756 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Required Data
508a4176-d847-5975-a2e7-1bc2fc313bcb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
7e13f551-5399-5983-bc26-a55e5023521e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
ccfef811-142b-5c2e-b920-8e7ea2815204 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
df8c7d48-f9fd-57b2-b4f6-5da15b37281d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
b238706f-8bac-550f-9167-66b4f55dfaed |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
bade88f8-dc87-534f-be29-33e15aae531c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Set Point 1
80dfe6b0-0c7a-523c-afc1-16cbde6e2c8a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Set Point 2
063bf259-8d38-51be-acd8-c5b38fc92394 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Set Point 3
7eb006d1-e214-5ab4-b065-3a52330ebb27 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Set Point 4
1e9e7ca4-98ca-585d-857a-e61eb9f01868 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Calibration settings
13627387-ad2c-5eb9-bacf-facdd2bce45d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)- Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
6f28ce56-1f5e-41d7-aca3-8a187bafb4a6 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint
416e9d98-ecd6-41c2-abea-25d6533fe817 |  | checklist-flat | not-started | ITR-CL-1-121 Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-121 - Instrument Installation
5a9a3d69-70f2-5003-821e-2cab135de268 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-121 - Instrument Installation | Instrument Installation (Mandatory Photo)
2e159c7c-648c-5d64-9787-812e7de27216 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-121 - Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
285a7ad2-d05c-4179-bcde-1f77523710a2 |  | checklist-flat | not-started | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation)
891d2be4-d9bc-5f9f-9e82-325299201105 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Equipment
302e07fb-da1b-5599-b95f-176f832a8249 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Valve
1e140bd9-e188-5702-a458-613baba1aba0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Actuator
ebfe1e83-68ee-58b5-8275-0cbf762b8226 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Positioner
6f7984a3-fc6a-5736-b8ed-d4532b1b4f7a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | I/P Converter
9556ad7f-8989-5fe3-ae0e-19e41eb2c9e3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Filter/Regulator
d6d6ac89-442c-5c29-ba46-76753c08b6a4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Fail Action
92dc015e-fc7e-55e2-bdab-d4cbed0168e3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Proximity Detectors
9c931814-afdc-5700-866e-e2f77abcb40d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Solenoid Valve
b5dc6625-d4e0-53d9-ac9b-d4d97e5a46de |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Pilot Valve
a56a5447-5537-57d5-9e78-a7895be61917 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Hydraulic Actuator
7d0ccea8-38db-508f-a9e0-1a6d866dd1b7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Accumulator
9cbdb2f1-704b-537e-80ee-3fdefd0994fe |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Electric Actuator
828e581e-27bc-5e33-a7be-c1bcc95ed9f1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | Miscellaneous Equipment
b0504704-cd59-5b8e-b0e1-9c8540448eba |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-120 Analogue Valve & Ancillaries (Pre-Installation) | All relevant signatures (Installed by, Approved by, Client Representative)
acc01008-6f83-4719-8f5f-1640cd86682a |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-122 Instrument Calibration
cc0350c6-8aa2-5d9a-a0fe-4b136375f53a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-122 Instrument Calibration | Required Data
4bdf7448-08ba-55f9-a265-592d086c3a69 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
19bf48c0-4771-5c3f-ae86-2a26aca6881b |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
f9ea3e14-8d49-4424-9a08-3d7c37242db9 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning
25eae0dc-fea8-5ec9-bffd-09864b000991 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
9edb45ea-5073-5723-86c6-b8e56bf348a7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
0f5cba3b-e65a-5ed8-824b-3ad3ac037ede |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
38707926-5815-5909-879b-850a3c7c886b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
aae40c86-7963-5a28-beab-bb896cab6ef8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
1d35a221-3390-53ff-8150-d496a59ed076 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
26abb51c-c422-5cc5-b980-032dda71f725 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
ce47a5ec-cc45-5929-baad-b0c96d6fd531 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
dfc1634b-b82c-5946-bd9a-f5b5618f835c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
e0c1b112-9ded-5f8b-b8d9-5be74cef621d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
80229ed0-388a-51ff-bb20-e75b92433956 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
2befcac6-8742-5960-b85f-c4ec3cd9214d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
624a2aa0-3599-5477-81b5-d7b245c68a58 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
8692a209-8e44-50f6-a93e-94711624d4c7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
d84c5d90-36e0-5077-a7eb-4c30852f6e55 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
852b2347-9c3d-59ce-a7b3-c45162a404dd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
a79c4f73-8905-5c91-a7cd-dc4bfdab2899 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
a8eec3d5-2f2f-5456-895a-f350ea10ef40 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
410b2639-c2e7-5346-becb-35b08b91731e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
7c770f1e-ba99-5792-b6d9-05b4071becd5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
cb808916-1b70-578c-8f89-3d39bd9d867d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
a83cfa50-1bea-4903-a666-befdd9b92792 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments
f63fc115-bfe4-51fc-8126-70b043d4270b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Required Data
813a452f-aedd-5140-8a9e-df279aa35cbe |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
199558fb-3258-5e8e-8489-a9a99155c2a6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
96219229-1a2a-5470-a027-9df75acf1f79 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
64e8dc37-f7f6-545e-bc3e-c45bee39bb59 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
e2c16873-d359-5d20-8228-ea27b6ea153a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
e6daf19e-0152-5bec-abf3-dac9844a221b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Set Point 1
dc3f0310-64ec-58af-9ee7-78a864b09016 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Set Point 2
9ab4a36f-225f-59f0-a6b8-833fcb0a9e89 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Set Point 3
58c08ef0-88b5-55bd-b6b6-3de6a293786a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Set Point 4
a97a53d7-2071-52b2-a66b-00c3b906fcc0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | Calibration settings
89d513e2-b905-58cf-906c-314d335eee94 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)-Valve Position Analogue Feedback AND Valve Position Setpoint | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
073b030d-d750-43eb-9245-538dd950a862 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve
2edc2854-a6d6-4b15-b059-f00866b487a0 |  | checklist-flat | not-started | ITR-CL-1-121 Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-121 - Instrument Installation
d0c7ad5c-439e-575f-99fe-6eb4795d7c00 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-121 - Instrument Installation | Instrument Installation (Mandatory Photo)
e9f0f391-af5c-5ee6-8ba1-c7022b4eb672 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-121 - Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
9a0e1393-9c26-40bf-aaa5-e57c37eabdaa |  | checklist-flat | not-started | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation)
cdd8ec62-fa4c-537a-ac23-776f7c1e3e8b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Equipment
666d2e98-29c1-587d-9ace-1be7a2eb32a6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Valve
a9301d06-8193-5715-8539-adb02f428114 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Actuator
b8ad3f22-0c1e-5bc0-b515-77f83c200c11 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Positioner
d54a2d50-5e6d-52e7-b2f1-dccac20015ce |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | I/P Converter
e6191968-b66a-5298-94a4-dd006ab17644 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Filter/Regulator/On-Off Valve
15d26832-c353-5ecc-9db1-f4e86602a046 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Fail Action
6b4be7fc-d10f-59d9-b2ab-178a63631d37 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Valve Field Calibration and Hysteresis Check
8f69d5b5-cf01-531c-a8c6-3aedb3872d06 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Proximity Detectors
0d4a0f43-0326-5946-b254-d280948944f2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Solenoid Valve
28793500-dd6d-5c47-afb2-bdec22e5565b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Pilot Valve
8530f9a6-4d24-546e-bfc7-93a0bf045d66 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Hydraulic Actuator
e119ab79-93fa-5497-8a4d-2411bf0f348c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Accumulator
1f3de658-15da-53d0-9150-c24fe7754897 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Electric Actuator
ad803dab-c56c-5025-bb7d-d8bdaee0e394 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Miscellaneous Equipment
34adc425-9218-5c3f-a3e8-9ba403212dfd |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | All relevant signatures (Installed by, Approved by, Client Representative)
d333405e-7e8e-4e2a-83a5-064f0e2278b5 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-122 Instrument Calibration
0a89ddef-b341-5643-9ddf-ead622d01440 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-122 Instrument Calibration | Required Data
c8bd083f-d41f-5a66-a022-924ce4a2465c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
5ae71feb-4ef9-597f-b5ac-50263687991d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
0da6838a-dac5-4f79-a42b-4dbbe491a7ff |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning
58aa9a22-56bb-5fce-93a1-1dfc5f7a8b67 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
06194163-b1aa-51d6-bb72-6e48c95d75a1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
ab9deb43-f465-5b84-8118-5afba08efe0b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
3bd436a9-bcd2-5085-a375-87c1bcef7153 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
deb3f3d4-4e19-5ba6-b0c2-3bcd3c28470f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
99ac600d-fcd0-579a-b5f7-3849a6b0cd6f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
df6b2d68-98b9-5a79-8280-59f6c201e113 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
45fe2034-7d06-5189-8346-39682edb7005 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
2ce16b00-7239-5f1b-b197-6d640b0c916e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
f570ac0d-ce52-51cf-959c-4506944b64e9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
0872de36-a7c6-53b6-8df3-21c39f0883c1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
a51996eb-2d17-5a4a-9799-e4dfb7e7c7f1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
607d64f9-7927-5999-ba61-1bfb5ceed843 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
33363b44-b74a-52e6-92b9-3abf5a4eedd2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
48f2aeb6-201e-561a-a4ee-150ed7469b49 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
afafaf76-b759-574c-b5e4-ea8d0894f6a6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
e18e4602-3833-5e6e-a927-b1b88bf3d1f8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
4962a7ab-9016-50b9-a8dd-f3effbf401cd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
c0767bf0-b7ed-56d5-9b21-0206cbabbf86 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
666b36f3-3d36-57b4-8b6c-e37a5515f17f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
c3896fd0-6af8-5d01-a784-3c71de5a3ce3 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
fbbf004c-9637-493c-9dd3-7bec70e69f99 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-124 Commissioning Instruments
a01f2485-e870-5e1b-bf9f-efe0d87808b0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-124 Commissioning Instruments | Required Data
16d85aa0-43b4-5438-a05d-77e73a8fed36 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
dd8c8de8-df1a-5ea8-bb04-0407e84745b5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
2c196d27-ede6-5665-b95a-d73a42f500d0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
79366c8c-bfb0-531d-8b0c-77cafa400e63 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
c5a28e1d-70e7-5851-a12c-6ad9afc46bbe |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
6519987b-af11-53b6-8f1f-90fcab263cd8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-124 Commissioning Instruments | Set Point 1
ed7682ae-c711-5740-90a9-683c5217b973 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-124 Commissioning Instruments | Set Point 2
0004a6f1-2b31-5627-8b0c-d06fdf620e41 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-124 Commissioning Instruments | Set Point 3
7a6f8d56-c963-56d5-868e-9efb34f30951 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-124 Commissioning Instruments | Set Point 4
7097b8a4-966d-55f8-a8e7-db7942b920da |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-124 Commissioning Instruments | Calibration settings
4b86038d-ba5c-5299-b519-5229ab8a22fd |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA110 - Rock Muffler 1 Control Valve | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
8675cceb-9639-4f37-b797-f1fb643a2aba |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve
6acfd815-bd56-4139-9f94-110997f09603 |  | checklist-flat | not-started | ITR-CL-1-121 Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-121 - Instrument Installation
6ea0087f-9120-5b7f-ac9a-fdf064edd976 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-121 - Instrument Installation | Instrument Installation (Mandatory Photo)
258409f5-88f3-5340-a43b-557f839c70ba |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-121 - Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
2e3f5bd6-9ef4-4922-bbf4-2a5772fd9b02 |  | checklist-flat | not-started | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation)
00eb5bfd-0930-52d8-8f19-b232f0b11517 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Equipment
725ac352-f9ee-5963-8608-556cfe5eebb3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Valve
98353be7-b480-59c3-9404-79b115c50687 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Actuator
5b14c554-c39c-5859-b30c-a3d20683c2db |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Positioner
82af1b5c-b685-5297-8505-617055e819de |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | I/P Converter
1302100e-711f-5f81-93e5-be58c85dcdd7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Filter/Regulator/On-Off Valve
60cb5d03-32cc-5e75-8083-d5aad5392e45 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Fail Action
9154eee8-d2a8-5238-afd3-0c7a42596de7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Valve Field Calibration and Hysteresis Check
da95854a-4a6a-558c-b504-267a618e1861 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Proximity Detectors
435bd9e8-6574-57da-8121-48023d06f49a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Solenoid Valve
fb09fea0-9910-5631-b163-d25c67d5385b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Pilot Valve
cd04e841-103e-5961-beee-935261a959e1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Hydraulic Actuator
b0c0a885-944b-5d15-9ee6-e77f764f87da |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Accumulator
55b2ed58-3057-5b46-8e19-235de0cd0843 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Electric Actuator
2f9e9ea3-a29c-564f-84e7-f9afad444bef |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Miscellaneous Equipment
42061da2-d207-5609-a699-bf90d1289eaa |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | All relevant signatures (Installed by, Approved by, Client Representative)
8548e041-be9d-4285-9242-596ffdd38f8d |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-122 Instrument Calibration
dce1500c-067e-5fcd-9cea-91d0dafcd02e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-122 Instrument Calibration | Required Data
504d3570-dd6a-5dfd-bd96-ad3dab685a6d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
78eb8f59-1d54-5fac-8a97-4aa2ad021f27 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
c2034bfc-721a-44e5-b3f2-fb2b10e4852a |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning
6eb31b10-c397-55f9-9a9c-47e7b3bd5e5a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
cf670790-2ec9-5782-9354-bb142e38737a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
cfabfea9-e612-5b2e-b39b-6c6b74199675 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
767bd02f-ca26-5c71-86d0-a3d994eff187 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
16173482-faad-5574-821e-4a1d5f87f638 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
84abf601-1f81-5db2-bf69-a37b1ec48980 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
cb0a4aed-648d-54ec-9653-467c77d10aa5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
d44b10d0-3e27-5f33-beff-474bbf02ff4a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
3c17c756-e218-5b05-a20c-56cd404e0f08 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
cbdf98c6-efc0-5d37-9971-319e3c6d3c93 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
044f9ee3-637a-5c53-9535-b5e460aa2ebd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
7adbb79c-4fc2-5b3c-9a71-e8e72832b654 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
3fb805da-90e4-547b-bdba-d63acae552fb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
d342235d-4444-55bd-9999-04292e85cad8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
612f1811-707d-5680-9f77-4932f6b4ae90 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
be95cbef-ec61-59e9-8a74-47e784ecba8e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
8e90ccd3-12c3-57a8-96c2-297a7035e1ba |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
5b197ecc-e1e0-5179-b9a6-df5a9a6735db |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
24d074a3-4d72-59b8-99ba-255c2e43e502 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
04da0e12-7166-58fd-9ca0-6e9f0c17db02 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
a0dc8277-34da-5181-8c56-88e2e5db3eb8 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
8abe5e97-4f9a-49cc-8096-d061cfdc13f9 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-124 Commissioning Instruments
e4297951-ac4f-5501-ac77-3adfd0da50c6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-124 Commissioning Instruments | Required Data
05ad503e-425a-551b-9485-aaed1f010613 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
b46e0f01-5934-5d27-b3c0-b92db873f197 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
dc19ea23-664a-558e-83db-4bf2707be44e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
e6ee6348-5f1e-540c-93b7-7b5210ead437 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
e4efd5d2-7442-59b9-8a1f-f4a0e06d9651 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
1fbb4922-0e13-5842-97dc-71b380efd48d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-124 Commissioning Instruments | Set Point 1
5c7056b3-eb04-5b70-9843-26a44454def0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-124 Commissioning Instruments | Set Point 2
b962f335-79c7-5d9c-89e3-a68a3402056e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-124 Commissioning Instruments | Set Point 3
a8ab299d-dde6-546e-ab9c-16713744700c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-124 Commissioning Instruments | Set Point 4
961b4a8d-653b-54ce-9832-bcb3eb857ded |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-124 Commissioning Instruments | Calibration settings
a6ac4b17-1f74-5d96-8422-eded62c7e5b7 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00V030NAA10AA120 - Rock Muffler 2 Control Valve | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
b1dd182e-3cfa-4938-963e-3ba4c99a8f33 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV)
aad0704a-9a67-4915-93c4-f7abfd509f83 |  | checklist-flat | not-started | ITR-CL-1-121 Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-121 - Instrument Installation
3f05c63b-d91c-5eaf-944c-a3a8e34ddf54 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-121 - Instrument Installation | Instrument Installation (Mandatory Photo)
7655c74a-a090-5f82-b4b0-aedebc43ccb8 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-121 - Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
bfceec02-3ffc-459a-98af-7edcccf575ba |  | checklist-flat | not-started | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation)
4986be3d-6873-5fbc-9b2f-345c6e4e0112 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Equipment
b8af78b5-242d-5f15-ab4d-76950880734c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Valve
68d911db-3f90-57d2-a687-4d6889f3defd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Actuator
7108eeaf-0553-5027-b531-30d06525adda |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Positioner
2b56afe9-2283-5679-8ebf-28ab74b77a23 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | I/P Converter
de9ce5d1-40b8-5f81-9ac2-6665fd4b2cbf |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Filter/Regulator/On-Off Valve
dca5ba1c-9ab4-51d1-b750-6e8c4dabffb5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Fail Action
cc77bc4f-c0c3-5444-9f4d-893eace9b96b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Valve Field Calibration and Hysteresis Check
ab4e33a6-2868-5d8c-8afc-704e935aec09 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Proximity Detectors
8c769012-ccb1-570d-907b-2470113e2d85 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Solenoid Valve
73108237-3c99-51dd-9830-eb545e7a4e08 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Pilot Valve
2fdb6d36-f0e4-50b9-aa18-be72c0079300 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Hydraulic Actuator
0fa26816-b4d9-5680-aca8-cbc9d1094a7a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Accumulator
be05e520-114a-519e-840f-34428fbfb4e1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Electric Actuator
d711f25b-d269-5264-a0c8-ce9855062415 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Miscellaneous Equipment
edd65844-4f5f-596b-baf3-8d98570e9d86 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | All relevant signatures (Installed by, Approved by, Client Representative)
90dc3c94-d7f3-4ac0-87b1-04b393996148 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-122 Instrument Calibration
3f77a67e-5082-50eb-90db-845536a21bd5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-122 Instrument Calibration | Required Data
4b51ffe5-715b-5723-ade8-8fa97b03dafe |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
cd3ead0d-cdef-5752-abd5-f00bc3b43319 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
3e149886-c156-4287-9043-c18b3b273a1e |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-123 Instrument Pre-Commissioning
ac59eb71-1932-56e5-b010-94e17cbd4775 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
0c909fd0-8c4e-5a41-8fea-c827e3824657 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
0ea70d1e-fd47-5efa-9ec4-9eab9cad7ea5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
b7b899cd-4dc0-5ca3-b842-a970b5a58bfb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
d172243d-40de-5db5-b400-63b679b2ba02 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
02b2b90b-a4ea-539a-b97a-56d6ec182784 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
06578151-ec93-58f9-a6a3-0066b61f5c3c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
ca3b36c6-4e24-5b1b-9f3b-b88b1e18c83b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
404801d2-b1b0-547d-b763-783e77acfb70 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
d2373eb1-6d00-5ce6-a2d1-7b625ab91ed2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
e9a58032-c16a-5b1e-82f8-22d403a3afb6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
cf882093-ba1e-508c-81e3-475b49bef290 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
43e1547a-3a52-574a-9eaa-6c57996e6f4f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
74bba904-9dbd-5c4d-94c1-cb42f8ad3712 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
cd9f45e2-0d8b-5a07-ab8f-acd0d1e315ab |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
3e604865-b9d6-539f-9479-e8322f04455b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
e288715f-aa3a-5544-ac7a-9250ef1934bd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
83dcb3da-1861-5ea6-af24-c691bd965f97 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
4dae16df-0461-5cb3-9fd4-8bb977e017b1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
47323c88-9b1e-5af9-8df6-d87b3c8f8f7c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
dcc4b7d9-6887-5435-8414-d74da0bffb05 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
8587051b-b536-42b1-bad7-272953305db6 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-124 Commissioning Instruments
8ef135e9-0cd4-56e7-9f6d-2d6ddf52cf92 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-124 Commissioning Instruments | Required Data
cf7b4f17-f247-57bf-9566-77f836ad2dc5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
9483efa0-2601-5f68-bda3-442dfa4e1267 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
1ece7483-9a26-558b-9761-5aefb48ce7a8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
9188aa6b-465d-54c9-b259-96239486b12f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
771e8cb4-228a-518b-9d0b-a062ef201a37 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
46ca0a09-eef3-5368-9058-42d58be8ad30 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-124 Commissioning Instruments | Set Point 1
92e1d65e-ff50-5ab4-a063-a5f88f96c0d5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-124 Commissioning Instruments | Set Point 2
8ff09fd9-dbd8-5914-b21f-9fbaa57b3e27 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-124 Commissioning Instruments | Set Point 3
a28f1ef6-f39d-54fc-8902-226afbced16d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-124 Commissioning Instruments | Set Point 4
52250bc1-24dd-50f5-a31f-92f5650dd432 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-124 Commissioning Instruments | Calibration settings
eb084aff-fe70-595d-9e6d-9d81780d2b2a |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA110 - SGW Vent Valve (MDV) | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
9fff323f-c0ee-4517-97e3-64e3e239738b |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1)
b4a32831-4d39-4640-a039-4dee739d0f5d |  | checklist-flat | not-started | ITR-CL-1-121 Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-121 - Instrument Installation
73791eac-e1e6-5e99-86c9-75507b0c2f21 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-121 - Instrument Installation | Instrument Installation (Mandatory Photo)
cd001f3c-7e37-5b3e-83e7-58af845c7c3c |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-121 - Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
ef44c247-57ac-45d2-b861-480f5ed6dc20 |  | checklist-flat | not-started | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation)
5841bc5f-c96c-5219-b82a-7ca45199bdb2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Equipment
21fe7417-f18d-5a1f-8348-f2f9131b4b56 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Valve
c8cbaa17-a9c7-5394-9df8-75f2f85e4843 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Actuator
db05c6d0-fbcd-5424-ad7a-b3d5b4780c30 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Positioner
fea92714-6577-5d9f-9330-69a30dcce244 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | I/P Converter
19242c73-2069-53c9-97fd-08bf82ee3902 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Filter/Regulator/On-Off Valve
c20c7535-21bb-55c9-82f9-4af29d798475 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Fail Action
d421b3d0-6164-55ed-af93-13c5947db324 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Valve Field Calibration and Hysteresis Check
504fbd5b-c8b2-5728-8c41-3af3e606c579 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Proximity Detectors
cf7a45ff-2322-5398-a0ef-2f53b5042a9a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Solenoid Valve
442e022b-eef1-5b3c-a0b3-cdb638f0a5b4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Pilot Valve
cfe19c66-2b45-5989-9a4c-f76f0df1d6ac |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Hydraulic Actuator
e70909d3-28ab-5313-8e47-3ba3cf69733c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Accumulator
4ec6ca13-87b7-5251-a88e-ae26959f9d03 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Electric Actuator
ec0c96f1-853b-5304-b903-a6fc6cda7c35 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Miscellaneous Equipment
8da3a5d4-c3f3-571b-8430-4efc3149d4ae |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | All relevant signatures (Installed by, Approved by, Client Representative)
d0ca4928-eb8d-4d83-a233-3e1c79e4211a |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-122 Instrument Calibration
dbc18d07-8afc-5cd1-a7bd-0bc360bf511e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-122 Instrument Calibration | Required Data
e4b4705e-b282-5687-b218-ce8681a58c00 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
3c0ec637-7e46-5362-840d-e90ccbc52865 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
9f23e982-aac4-4866-bd08-a642c000f117 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-123 Instrument Pre-Commissioning
e6f93dcb-fc72-5fcb-a1dd-2bb81359ebc6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
b0d21294-83da-526b-9b90-12f482b17121 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
10a4980f-97a1-59ad-9875-ea0c256d371d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
58f2d09b-e7f1-5f71-acb0-944b81ae5acf |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
36147ea4-63c9-5dab-a1ea-56a57475829c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
04b54924-8638-5613-a787-9f4ebda02b6c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
a4265b3e-5da7-5380-b289-533f97d4e8de |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
ca3bb6b9-034b-5cfb-a62c-d5cdc8734e1a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
0c7376e8-ce68-5cca-87c8-bb3df16d49d3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
a4be5131-7e37-56d3-9d89-a11e622d37eb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
21eb5f5c-cb6d-5104-8870-fdfa9d6a620c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
5f0420cd-be0e-5685-9113-d0a571fe819b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
eaac57af-cb58-54b8-aa94-cf68597f1835 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
ad90d9f8-3c19-5ffe-a1d2-f1fc80e60759 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
7e09b184-3573-5be0-b5ed-ff2f55fd15c1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
42af878f-29b1-5913-bab6-3757d097b828 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
ef2ea72a-2293-572a-8a9b-92da6a95c280 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
5c11cf45-7edb-5bdb-94cf-6af8012d943e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
0f3a1165-65a7-51c5-9183-c2a3f94dc80c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
a5778685-2ebe-5c43-9dff-58908054e0df |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
8c66bfa5-e7fe-5c68-9ff7-bf0b5962d101 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
93942e06-fa3b-4cfd-bec9-8b6c0e808759 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-124 Commissioning Instruments
c4e6ca4f-f50d-5a5a-be12-b91e188f5ee4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-124 Commissioning Instruments | Required Data
514cd27d-6c4e-5c55-ac60-78f81530135a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
c499aea3-9e3d-54e6-8318-6f72fe3cdaf6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
eae0cf77-d4b7-5ffd-b3c4-f3a022b3c633 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
4cb9d574-292d-5f45-87dd-a56eca5deb99 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
3cb247ef-71bd-538a-9ea7-91a0264f3307 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
4daa6c03-6f89-52d1-9877-593deddf5114 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-124 Commissioning Instruments | Set Point 1
105fe06c-95a4-53e9-86af-f91f74f21855 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-124 Commissioning Instruments | Set Point 2
5106e184-cc28-5413-aa3c-a8d02d437a27 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-124 Commissioning Instruments | Set Point 3
ba621473-73d0-5171-80aa-67bcdead3bbc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-124 Commissioning Instruments | Set Point 4
43f8f7ea-29f9-500b-9ac7-e5a86e460a6c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-124 Commissioning Instruments | Calibration settings
caa58966-b96e-5845-9ec4-87aa035396d0 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA120 - SGW Vent Valve (EDV 1) | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
0d835645-0bb5-4a54-a29d-976b957de589 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2)
13e8b5ac-e35a-48fa-9f6e-3010e75b3ef6 |  | checklist-flat | not-started | ITR-CL-1-121 Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-121 - Instrument Installation
c7d584c7-2798-57f7-8f7f-3c4c8184e973 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-121 - Instrument Installation | Instrument Installation (Mandatory Photo)
af8cf422-8d0e-53cb-9043-fe2bcb270a1c |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-121 - Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
b7ac91f3-6f53-4acc-9ba1-929dcd1811ce |  | checklist-flat | not-started | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation)
39f6d529-802a-556c-a050-4c38f379e54a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Equipment
3b03ab5b-c81a-5c1a-a6b5-4a3051445740 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Valve
8a82a984-703c-599f-829c-61e5b92dcaf9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Actuator
182da2cf-998f-525f-a981-4b57e45b719d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Positioner
79ad56b6-cabc-50f6-8f15-b3a49edb4e88 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | I/P Converter
07d4a911-f794-589d-a8b7-ecb17aaa8f75 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Filter/Regulator/On-Off Valve
9c714624-d7c9-58da-bc85-bd1d4bdc458a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Fail Action
b4aa660b-cf7b-584b-8989-563ecf035eba |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Valve Field Calibration and Hysteresis Check
bb95a672-0265-5692-a13f-f5788f7bec37 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Proximity Detectors
99afc34d-3045-5677-8737-af6f8003a500 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Solenoid Valve
9485d660-6d4c-5a67-8a6e-4d584cbf1f37 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Pilot Valve
497e0a63-2950-5324-9da2-fddd12cfcbe8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Hydraulic Actuator
0e9b4f35-64d1-5a50-82fc-f15214197947 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Accumulator
91608f09-3333-525d-92e7-0ab0bcbe0496 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Electric Actuator
d66f9863-98ac-5839-a368-9f89a5bdac0c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Miscellaneous Equipment
2b1d38d3-a90b-5e6b-a399-e8d8ae11adf4 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | All relevant signatures (Installed by, Approved by, Client Representative)
19892b57-258e-45f3-afd8-3f41d0f8360c |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-122 Instrument Calibration
a77ba1d7-417a-55f7-a7b2-b0ac2b27534e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-122 Instrument Calibration | Required Data
59c2ad3f-52f5-5ce9-abec-1909f46dab2c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
806b7273-41d9-5487-99d5-12c86fc2be01 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
b607ee3a-d39b-445d-852d-5fba8bbd9aa3 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-123 Instrument Pre-Commissioning
38af08c3-da95-5364-9a33-e9df9d30c8bc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
288d72a6-6c1c-558c-b50a-895e2b2dc070 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
996ffc57-c14c-5729-af8f-7f23315065e8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
e1861838-293e-57a0-ab15-18db0a8d35b4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
4ee6d0a7-efbe-5274-9ce9-b40127535a35 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
c81185b0-88c3-58e4-b517-646c4bf19002 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
13c44a64-8000-5f55-af62-b9e82425943c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
78077894-9ad8-50e0-86db-0a76e44b6b29 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
0aca7a67-3c50-5876-8434-a5ae0589b623 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
9e9346c1-67ff-51f0-8cc1-73ff56851b90 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
5e07bd1b-cddf-5a02-8ff6-8df16cf782b8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
fa5f738e-52b6-5d5c-8f9e-a4af06a30be7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
08fa6965-715d-56f7-b8f9-7ddf2b8ac143 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
ab1396e0-f8a0-5c85-9191-ad538efaf113 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
1b9e5337-5c57-59e4-800e-879bed8a9bdb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
e063189e-1200-5f90-bb61-57bc629a5bcc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
1a558cbc-b12d-5819-b0b7-16c8913829b3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
30fac7e5-86ea-5d4f-b209-7affbeecafa0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
f078b3dd-7178-5fdc-89fb-519e6eab548c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
76b3adda-2914-5ce2-98fd-98f960e7d977 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
b7db19ca-54e3-5349-8ada-b4ecf97cf079 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
4c15f67e-bb3f-4725-9322-38f108dd826a |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-124 Commissioning Instruments
ae33fd2c-376a-55ce-9eb0-e018d4c2fe6c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-124 Commissioning Instruments | Required Data
8ba901c4-1076-505a-b279-2ec05119212a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
b8c6e383-9c15-5c1a-947d-049199df67a3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
e1a00a99-ab57-5a5f-a3d8-0853d8ee8d6c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
4b41f3cc-db42-5a66-8ae3-6902d79c7dac |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
83f7f7a3-47b2-5848-84f8-adcc0bf173d8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
90ac29f7-7bd3-583b-9c9a-03d299948f12 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-124 Commissioning Instruments | Set Point 1
28d60660-def4-50b0-92b5-b3c5f5bf9b0e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-124 Commissioning Instruments | Set Point 2
7bff38cf-167b-5185-89f5-791f23521409 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-124 Commissioning Instruments | Set Point 3
38634b84-248c-59d9-83e3-c802dcba9033 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-124 Commissioning Instruments | Set Point 4
bb0d7b35-9ab8-54f6-bd95-4d59e0c415fa |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-124 Commissioning Instruments | Calibration settings
a6ceba07-4c43-535e-baea-c5e1672c4702 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20AA130 - SGW Vent Valve (EDV 2) | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
b8d78913-36f1-40a8-a0a1-72ec21922d33 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE
b025cffa-326b-40a4-ac38-0ff42ae40d70 |  | checklist-flat | not-started | ITR-CL-1-121 Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-121 - Instrument Installation
bbad1129-c68e-5fc6-9677-b180fde7ef21 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-121 - Instrument Installation | Instrument Installation (Mandatory Photo)
7fa9eaed-0918-5ce2-a456-15c36c4ed136 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-121 - Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
308f5e46-d82e-4997-945f-7c1e89c05997 |  | checklist-flat | not-started | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation)
08ce5862-dab8-52a6-9286-825444c98099 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Equipment
e16cbaaf-12a6-5884-95f6-4c0e9cde14a8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Valve
11dcf0cd-4630-556e-98aa-3f07f7f46dd5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Actuator
f4c39575-1266-58ec-b9c8-58960c197b11 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Positioner
60c98900-febe-50da-9377-d1feb2e4b58f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | I/P Converter
ffd030ea-fb59-57db-9aad-910f795155fe |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Filter/Regulator/On-Off Valve
9b306259-2a12-57b5-87b9-a1badc9b7882 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Fail Action
d2a09c0f-fa33-5b53-9590-7ee818d43af1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Valve Field Calibration and Hysteresis Check
bb095f68-7f3a-54c0-9b82-1d0bbd42202d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Proximity Detectors
e58bc236-a709-523f-a3ce-fa394cff2911 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Solenoid Valve
1c63afaf-1158-506f-8806-375fc8e887e1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Pilot Valve
36ee44a2-fcb6-5038-93be-1a46e41b0273 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Hydraulic Actuator
e9092115-682f-5fe9-ad55-03f3ca7e2f5d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Accumulator
e506b1df-3d46-57d5-bf89-94f7777b31c5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Electric Actuator
004f8526-10df-5996-bee1-3d95a1d28e2e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Miscellaneous Equipment
426e4219-f263-588e-a89f-8cfddcc8fbf6 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | All relevant signatures (Installed by, Approved by, Client Representative)
35475fbe-19f3-433c-ac0a-792a6777430e |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-122 Instrument Calibration
16b6d985-d31c-5ad6-a608-73e56b44ad41 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-122 Instrument Calibration | Required Data
f68e3b8c-a594-5e1b-8fd3-6d3c4d28d7c6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
ab4d2022-76c1-56af-b533-d52d98b2c2ff |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
5ea1a9df-5054-4f8a-aac3-11a0729566d7 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-123 Instrument Pre-Commissioning
fdda8e40-87b7-570a-a8dc-9ae33d6a08a3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
86c462d3-754e-577d-880f-88801f4d2da5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
2c61a9e2-9aad-5825-9bbd-5027eed02b6d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
9044f61d-9916-5552-9db3-9aeeac80c93c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
44711361-4d92-50ef-9663-80323b898b38 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
a7e676cd-6f68-501f-8595-0047ccec912f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
dc9ffb66-34ad-57a6-8333-cb9ab965a058 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
c1985d3f-fc71-55d3-a018-019442632cbe |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
e0090a95-bcfa-5283-952c-b4dd1f305c05 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
f577c31e-ea5f-5577-842e-76845e215327 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
0864fd9c-ae8e-5f74-ab72-ec01ab2ffe00 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
4ff5ae49-7a5f-5656-b07b-249cbff86677 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
272483b1-374f-5f8a-b840-ace44cbd4098 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
8fcd3b5f-fc10-559d-a1f5-01285d8fdb31 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
5dab07aa-cef6-5b47-a8fa-2b106256019e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
ddc41e4c-b446-59c4-ade7-27dd8c6ddac5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
ea539bf8-5d80-5330-b9fb-8725e3496bf3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
01e555b9-0c30-5047-bd1c-9e40866583db |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
e6467199-eb14-5416-a533-0c7e3864a683 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
0f303340-f9f8-5053-b06a-c972628e55bd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
1f0bb2f1-a4bc-5c0f-a3a3-8c1ed6d53d08 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
f8bd3677-f51d-4b16-9cf8-7a590fc92ddd |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-124 Commissioning Instruments
cc7794c4-17aa-5704-8f2c-f604343bd9b8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-124 Commissioning Instruments | Required Data
e48bac41-04bd-5d1a-a46f-58ec684ab809 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
64a8dae7-a5f7-578f-b73e-a0c650b27faa |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
df4fb099-46ff-5566-90f1-dfdbcaa04383 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
25658c6b-e654-54be-a7be-592a177660c9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
164208b0-a050-570a-a70f-0ab530b1dfbf |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
77aacad3-52aa-50f1-b880-cf07d834506c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-124 Commissioning Instruments | Set Point 1
2e34b232-f320-5f19-a315-9a480f006c7a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-124 Commissioning Instruments | Set Point 2
1b858613-9069-56c4-abf4-41adf70163c9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-124 Commissioning Instruments | Set Point 3
7610ef74-43f0-5065-a804-0a95d8fe2ed6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-124 Commissioning Instruments | Set Point 4
a73c0e35-bf05-573b-89f9-d58d0478a8e2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-124 Commissioning Instruments | Calibration settings
c7b92026-cdf2-569e-b0a7-dc3a3cfca2c0 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030LFC10AA420 - SGW DRUM SOLIDS TRAP PURGE VALVE | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
d2c720ff-b047-4b4a-b9aa-f90bb39669b0 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1
986ca650-f435-49bd-ba85-5d9c24a76c03 |  | checklist-flat | not-started | ITR-CL-1-129 Flow Meter Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-129 Flow Meter Installation
9c66be2f-384d-563d-836d-9d0c1bf7ea96 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-129 Flow Meter Installation | Flow Meter Installation
b4e8f55d-37e4-5ebf-af03-9d4d5303d7f1 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-129 Flow Meter Installation | All relevant signatures (Installed by, Approved by, Client Representative)
75f13524-6d4c-4938-a02d-5cb523d61cb2 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-122 Instrument Calibration
41d3d6f0-e747-50d1-b822-93d254b0976e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-122 Instrument Calibration | Required Data
462fa14a-2c39-5f01-9283-2ce3dd475f19 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
c7b08031-3732-51a7-8047-824f62d0a433 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
6868a991-12ca-4410-ac80-2a506ba5b1cb |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning
1d5f839c-ec6b-53d6-b1e1-1e177707aa1a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
70f06688-134d-5df5-8e1e-78fd9852b1b8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
0f7108dc-8aae-5597-a8af-e1365d0124c9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
91484d56-826a-5f23-8a43-1e93a8540acc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
129f23a5-33bf-5ec9-ba9e-df535c6207c7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
64e173e7-482e-5712-8954-206eebe2da07 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
b6af7d73-953e-5e7c-96ae-a7176cb3f621 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
9cc56069-a08d-53e7-a443-c1f1a2b738c9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
f39da02c-7158-5557-b310-3fec6f664c89 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
0d555d12-ae11-5f03-8c68-2b9346821bd5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
2e7cd60b-0bfa-5396-b360-f22de67a5c20 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
856e63cf-7b6d-5a72-a3dc-974896b61e00 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
967def95-f850-57d6-a1fd-efe0259f2354 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
34ff2811-578c-5d97-949c-b8a41eace48b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
2f4078a8-eaea-56a5-9bed-a46051866f64 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
45280809-2064-5a72-be30-c2f328f3dcc8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
7adb617c-a1e4-52da-9242-67599c853081 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
714ee57e-b972-54b1-9673-70ee2277c7fd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
24ee857d-a223-5b73-9571-725dffbd5377 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
e4d33383-73a5-52c3-968c-b508facc75a0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
fc07d135-db37-5831-b987-e79dc732d4f8 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
0730c0c8-2573-4fc3-9d6a-0f008068014d |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-124 Commissioning Instruments
7a7f705d-9899-5d61-b82f-93682632fbbd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Required Data
d4762b45-9ebf-54fa-b3f9-4d326383fdac |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
6c2af58b-dada-50ef-bbc6-c75441374f75 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
b964715c-73a3-58e9-a19f-422a35e7b8dc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
c96a5236-6080-55fe-9466-a1e38bf44be8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
7e1cd695-ae97-5d8c-b1f8-83a7c288b77d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
877fda5b-b617-53cc-a1a7-d79d7efdb820 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
9e91ae2e-23d0-597b-bf56-0b2e9f03c3c8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
567e2ac2-d629-5b33-ae19-45f031d9e8dd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
3386376d-05cf-57b2-b885-147be8d41c65 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
5598b4a1-ac4c-565c-8ca0-59d3ca15fd9c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
092d71f1-40df-5fd6-973a-8ab4077436d3 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF020 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
c768c1c3-3179-475e-a70e-33c2de45aa91 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2
f2812c2b-a9d9-4602-90ae-5ed137636c39 |  | checklist-flat | not-started | ITR-CL-1-129 Flow Meter Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-129 Flow Meter Installation
106564c7-6267-5376-8887-743783c8c7f2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-129 Flow Meter Installation | Flow Meter Installation
cf3547d4-3315-568a-8e9e-92bf0cc3c6f8 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-129 Flow Meter Installation | All relevant signatures (Installed by, Approved by, Client Representative)
3db18b29-67e0-44ad-b74e-219d204046ca |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-122 Instrument Calibration
e6190eb7-445f-5287-9db6-52f73d923a76 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-122 Instrument Calibration | Required Data
952e7dbf-cb8a-581f-bbe7-e99921f716af |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
e17215a6-ef3d-54ac-bdf2-bdfb50c2aa79 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
a110a47b-4300-4606-9687-f702553c5c40 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning
16fe88c9-40af-51f7-b01f-1fd8c4c80b8d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
55dad0e5-20eb-55d3-b18d-afe0092e1019 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
6ee1ace9-0b50-5a06-b17d-6d5531f73595 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
c1d23dd3-ce22-5d4a-8646-dd569969bba4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
b7253327-ef3b-5e1d-a002-0d98f3494f15 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
6db4b6fd-223f-5506-9f69-22ec336bb701 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
2431bf6c-ee69-5724-9521-58e112fa84b7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
150ff0ad-8c4a-51e8-92cf-23bea5bb8d07 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
6812283e-401e-56b2-b03a-6d1f856207d9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
1308d9f1-dea8-5d3b-ba6a-fece0702fb5f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
5a9e58f3-b1ae-5e3b-b3a7-a3443b8cbe37 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
190a58d7-fc31-5e36-8dc2-7ac6926576eb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
ed88a94e-92f8-5b09-9d25-110531614850 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
5b1d6380-827a-5afe-a917-3fffe0ceb9cc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
ab54c86b-8bba-56cf-9ac1-bd47fd90582b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
ed63a358-4e5a-5168-bf49-cc8de7f912dd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
27b4732b-63ec-588b-8ba7-a0ba767faf87 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
3a38fe5e-def4-5564-b622-47cf954d2ff1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
fd7ee15e-9ebe-5d24-b61f-56902ac4b6a7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
aaf51de4-1623-51c8-a155-23527d557dc6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
c0b3bf6d-fde0-5912-8d56-3699615a959e |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
fd10d446-f895-4191-b029-0b9bbc18b073 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-124 Commissioning Instruments
e8b37322-9875-5206-bec9-2c4067602428 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Required Data
c2e9d467-58f6-5249-aaaf-dba3c927de70 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
984e58c2-ea97-5c5d-ad25-4c7f00c34de7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
d2bc55ba-511c-5f73-87d1-ba0127292208 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
b41be589-1ffb-547e-b5a7-29e9420de0bc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
e04636d1-bd58-5304-a83e-c427bc3010a3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
f3083b45-1321-504d-bc5e-2662ba326fa8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
ad1ebeb5-7365-579f-8c51-45c989f0f21c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
79cfc9e3-3d72-52d7-a659-db8853c4870a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
5b8b64ef-14c4-59a8-a6bb-bb602a9375af |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
0b49f7e8-411b-5e6b-8bf2-39d90d752b65 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
93d3eaad-f3c0-58c0-a3b6-58314175d416 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CF030 - U3 ORC Steam Supply Performance Monitoring, Flow Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
8c87ee99-0823-4036-a66d-4da36e1e25f0 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1
c1572087-4752-4577-ad8e-3cb64b191590 |  | checklist-flat | not-started | ITR-CL-1-129 Flow Meter Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-129 Flow Meter Installation
784fd944-e62f-54d8-b92a-13a52b3a3e3c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-129 Flow Meter Installation | Flow Meter Installation
6f6c2781-9afe-52c4-a2aa-461be2939452 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-129 Flow Meter Installation | All relevant signatures (Installed by, Approved by, Client Representative)
0dfae940-47f5-417a-9ea6-8ead799d0a06 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-122 Instrument Calibration
70d4cdd5-c6a3-5d43-aa1f-4dae5d41c7ba |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-122 Instrument Calibration | Required Data
731b0c20-ed6f-592e-b8bb-fd543244d3c1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
79fb7c0e-9552-5cf1-8222-9069dabc6197 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
85b68adb-fd85-454c-a60d-2fd1b85564d3 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-123 Instrument Pre-Commissioning
53e63768-0229-514c-a896-e0212838203e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
0b1d454f-2e65-5141-b7e3-2c085334f9f4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
7e326989-0cbe-545c-89bc-405dd189e649 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
d3d22bb2-8018-54f2-a0c6-aa01f570b128 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
2717aac5-2409-570a-be0e-d29870aca2c0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
578d8b12-e9d2-5c26-b881-399d263d006c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
b4fc87c7-302b-5bea-ae15-9bbff2047e74 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
e6e66766-24bd-5d3d-924c-19bad354c5a2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
e33029fd-3ce7-5b7a-bb0b-1ba65980e169 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
f6fe7a09-d033-527f-91d1-5a89113bb6f6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
d18a2848-3ce8-5cb7-b6e3-5c02dc67828c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
58e71cdb-b90f-55fd-84b3-eee71281412b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
843970b6-bbab-5e81-9e54-919688c84817 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
0bc25b9b-f184-506d-94fe-4bd1ec1661b9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
062ef870-2db2-5585-93c3-6b3cded3c856 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
2f1c82af-1c86-5e91-b80a-904e057b313a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
4e709355-fb74-504c-aacd-4f6a241ee909 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
17c10584-df45-5fe3-a1bb-bec48bc72f74 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
c1009d66-9f74-5cf1-8c8b-943b9deddb82 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
a610c6f4-1c33-5571-9b9d-0a5d2f01d40f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
c1e04510-a0aa-5c9e-b5b3-f21ea212a7ca |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
2bbac1f0-3e43-4478-817a-058aecd0e11c |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-124 Commissioning Instruments
12fc03e8-6a67-525b-bc48-90ad286c0124 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-124 Commissioning Instruments | Required Data
3110b50e-0b6e-583f-b36f-3598706d79ea |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
87b608b8-08b5-5e23-a6c6-11eb2b050da0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
27510fea-38bb-54cb-8045-21525742b64a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
a279c4ba-b4cf-5acf-9b97-34868a0d1a71 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
92a18dba-737a-55a6-8e4b-9ba40e33900d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
8f07ec56-37c5-5a73-ba0c-6c2bfa1dc8ee |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
38b99711-ae1f-57fb-9ed3-4d62b79bbf9c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
d6a27a79-9697-53e4-a4cc-243052663d15 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
26af9bbc-fe2f-5687-8adf-df866a6a278a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
3338d0f1-6504-5430-b953-2c19b32fdfb7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
5a3084f7-4f9f-5a4d-bd87-90331b387f81 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF020 - FLOW TRANSMITTER, VENTURI, SGW PERFORMANCE TESTING 1 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
1409fd37-8e97-4d2b-9d79-ecb0ab07d896 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP)
c9ac83bb-d7d5-4de2-a095-17986d4708db |  | checklist-flat | not-started | ITR-CL-1-129 Flow Meter Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-129 Flow Meter Installation
12216d00-c4d0-5f2d-b2eb-fa66bb8da607 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-129 Flow Meter Installation | Flow Meter Installation
f4b9e03e-1dda-5cfc-99b3-6ae94fe6c52f |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-129 Flow Meter Installation | All relevant signatures (Installed by, Approved by, Client Representative)
37faa2dc-c795-407d-ba47-b727020c75b9 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-122 Instrument Calibration
7821d5a6-380d-539f-bec8-7f0c6c67d317 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-122 Instrument Calibration | Required Data
d09c86eb-7e2f-5387-9714-d6f7ba275d39 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
0f2492fb-02ef-5cb3-8e4e-a86e2bb72a59 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
ecdb14ea-9d6d-434d-a7a3-5c22ef59b470 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning
6f23c11e-015e-5de0-8452-eaa23e1ef4e3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
877fe080-4518-5586-96ef-04362f613a82 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
d2b98cc5-070a-5d44-b357-0dc5d0d421c0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
d4744177-fd98-5900-b7d2-67b138af875e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
fcaae395-480b-5753-8ce9-ba5e5e57ceeb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
adbfc3e1-cd68-589b-a29e-1b07f2973aec |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
15929874-7e39-5863-b54d-ec8948f253f7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
12c6da8f-5455-569d-a7de-521f2ed0c252 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
5174f4fa-4b33-5e22-9826-396c00ad9522 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
780546ac-4a54-5302-9e57-44f6e0b64399 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
7ac445ef-1343-5131-8d1c-227e0661e4a9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
abe9586e-8204-59f2-a19e-8424c032b298 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
722c9b1e-b11f-54f9-97a6-167e63211cb2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
615f2f33-d6a8-55d0-9586-9f79ecea4577 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
e4b8d0da-2c1c-577c-a1c7-4bba01b5eb61 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
7924508d-586a-51a0-ac95-1480e701c520 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
a4be8064-6b63-5731-a8c2-ed36002f723b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
88f657d2-5bf0-507f-b210-7f0341429eec |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
fc5ad1d5-a1f9-57d6-9517-fca1b2291397 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
5fa29728-b105-526e-87d5-ccde401f1dd1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
cc70b359-e948-5a23-ba34-a1cd228cd032 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
4236a39c-67c5-4005-a2a6-c36428a3b6ef |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-124 Commissioning Instruments
c59f2c79-f5b1-5d03-8df5-6f5663e8b9d2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-124 Commissioning Instruments | Required Data
42901e82-798d-5b3d-a3fe-523aeef9ca70 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
879fe990-ab9e-50aa-a52d-141e4fb22f90 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
98948f26-26f3-5c59-b30d-72d02e5e2c0f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
46631575-3ee4-5fcc-8a2e-75c309eca73f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
cbb9ee37-f1ba-58ed-99ba-b06f33766291 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
fd472ac2-c77c-5a0a-84d8-3956e3725322 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-124 Commissioning Instruments | Set Point 1
a75315e3-0e6e-535c-9c9b-243452d1ad6e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-124 Commissioning Instruments | Set Point 2
5dbcfaff-d7b0-53a0-8651-5888c02cdec4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-124 Commissioning Instruments | Set Point 3
779dcbd6-0e40-5997-927d-a93ea9259261 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-124 Commissioning Instruments | Set Point 4
fa416b3f-0e65-5d42-babc-6b1a17919027 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-124 Commissioning Instruments | Calibration settings
f90d48b3-27c7-5fbf-83ac-a229f8b82757 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF030 - U3 ORC SGW Supply Performance Monitoring 1, Flow Transmitter(Venturi DP) | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
a39af2ee-b42b-43db-b903-0d3db1324e17 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP)
55bb86fa-f38b-4264-a09b-3198a91f1778 |  | checklist-flat | not-started | ITR-CL-1-129 Flow Meter Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-129 Flow Meter Installation
f86819d1-4e1a-5eb5-9e7d-112fc9a2c70e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-129 Flow Meter Installation | Flow Meter Installation
78fc7fa4-fddc-53b5-8a4e-51408d3d1ebd |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-129 Flow Meter Installation | All relevant signatures (Installed by, Approved by, Client Representative)
06d7604f-bd8b-4d63-9ded-d14fe27a4b83 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-122 Instrument Calibration
4d32c5d7-764f-541c-b854-0707613b75e2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-122 Instrument Calibration | Required Data
57cb1484-fecc-5779-a25a-d23b51953e8d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
a09ec4d0-ccda-5083-8a67-de1b476a890f |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
a6a4362f-40df-4140-8441-a9efe977c404 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning
fcd96645-b170-540c-a87e-67df92507ed8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
5e9a1808-baf4-5eab-8157-e623a03c2e38 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
ed8ba120-2020-5db0-b6b5-1cba9abf7a8a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
9b966409-9f19-57b0-a052-2687cc06062a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
bfd9cad9-c01d-51ce-8434-0d75d280c0c9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
c440739a-7536-546d-afc2-e8e85de3051d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
019e4458-046c-5a41-a6aa-c3f791a64417 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
c7020aea-ca38-5585-8714-fd7ee7e7f263 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
90f955d7-86a8-5afc-90e8-12938a13cec5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
d57de0ef-fe83-5663-9d9a-43a42fdc1bbe |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
c7c87af5-232a-5e1a-875f-fb69ce767869 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
eb15ef90-efe4-56fe-a3fa-dbf6e4873365 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
1ba745ad-d812-5dea-ab95-d4b87ede2620 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
93d6ba7c-d905-5885-9773-bfde095796b3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
f3a89ec2-722f-5303-9afd-b4d61e60cc78 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
6dfc99be-db2a-5555-ba1d-5c70b8fa5065 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
efbb2f3b-0f77-5efe-a1d5-061a51d20ade |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
fb6f20e0-463e-5b76-afee-17d387e7a7fd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
a4be2ccf-a7fd-51c4-9b28-d564f0b2418e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
8bedf3e8-a2fa-5649-a56c-a5446369b7cb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
7c96a0d5-f613-5c64-ba35-c9be6ad5ec76 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
73599be9-d23e-4d86-ad33-8503d8ed2f98 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-124 Commissioning Instruments
71c6fa22-2c49-55e6-b41d-3ebfe39ca750 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-124 Commissioning Instruments | Required Data
5faa3924-2a7a-5176-b0d2-5d37fd122a4c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
c8520282-ef49-51f2-868b-de75e00ca8a6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
8f98bf44-2372-5364-a22f-faa00d8f44b1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
71b97a41-5dbd-57e8-9fb0-fbd138a13f92 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
d4a1d913-5dd7-5b25-991e-ac70692ff8ea |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
96eb221d-2bda-5fab-b958-14131a31fc8b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-124 Commissioning Instruments | Set Point 1
8ad0a3fc-40bd-5d06-81a5-3bd2cea7b708 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-124 Commissioning Instruments | Set Point 2
4f27fb86-94ac-5e7f-b163-8ac89d4aef82 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-124 Commissioning Instruments | Set Point 3
d0601fed-6f90-55b9-a5c8-1c5991d56d56 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-124 Commissioning Instruments | Set Point 4
417486eb-1c88-501e-91ee-31493d2591fe |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-124 Commissioning Instruments | Calibration settings
a7573c9e-b663-542e-973b-0dcbee064afe |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CF040 - U3 ORC SGW Supply Performance Monitoring 2, Flow Transmitter (Venturi DP) | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
b1508c92-0529-4bf9-b7ef-37d6c5424da4 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter
e8b081d7-482c-4222-bdca-d61a2db8fcb1 |  | checklist-flat | not-started | ITR-CL-1-130 Pressure Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-130 Pressure Instrument Installation
4cacf055-adc8-5594-ab3b-457c2bc5f496 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-130 Pressure Instrument Installation | Pressure Instrument Installation
51972894-0a47-5f9d-8719-bc944d3b9c82 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-130 Pressure Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
c7be5658-2813-434d-980d-116702e9e0de |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-122 Instrument Calibration
7a5e4dd7-8ad7-50ee-91a9-31bd62ab3d1f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-122 Instrument Calibration | Required Data
b6c4fa71-df82-51cd-9de1-eaae7dbfbe5d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
7312737e-4f85-5e51-a8e5-ebf7d9a6d539 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
07a06cad-93bf-4157-8c68-c851e2fd63a6 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning
b8b42f40-80cd-59ef-ae07-c1efe449588f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
b74f44f2-a709-5df4-a4f4-75abdf2218ac |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
5ebdf3b3-cdd7-5b15-84f3-a4d613f6efbc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
03bc0749-b1a6-5606-b5bc-2c105e7c1610 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
1bdadaae-640e-5398-a056-8bb8db60a0e0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
3f55482e-1f50-52a1-a092-aaa8497a71b0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
aaeab5e7-d280-527c-99f3-65220fe4f050 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
cd11c9d4-9670-51e3-987b-d5e2332b731e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
2131be42-0c52-550b-86fe-9c1e2a0b00ec |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
c546e6d0-1b60-525d-84a8-ecfbb9c26f4d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
fd4a2cad-64a6-5be4-9682-e0d9e8c66b28 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
d6723e77-2ce0-5af2-a85e-397a14006e18 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
d2d132b7-12f7-5421-b3e5-69a9223aa829 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
e7d2c3ac-186e-5abd-aa59-ec6fd18ae872 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
1e8697fb-4a8f-5cc9-96b2-8fba106997f3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
4ed5173f-3c76-560e-bfe3-bf964c00f43a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
06d5b2d1-32cb-5549-94d3-e82cd74323fe |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
4025605f-43fa-533d-a926-962af93deb48 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
1697f7e2-89f2-52bf-8551-00b977777614 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
f4a2aefb-7cac-5454-a3cb-aab158157c18 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
63add84c-2306-56ce-ada5-dc15bd960047 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
db2f3fd7-65ba-4567-a694-d9da604d7109 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments
15c479c1-5374-545a-99e9-ebed7bdfdbee |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Required Data
0cedb7e2-48bc-544c-8bdd-c2e633c6279b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
570877f7-5a6b-5f86-85fe-856f9028fb51 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
3b4ea413-8877-57d5-9845-0c6dc9d76da8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
70aebeee-12d7-5715-9080-bb215f31494e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
6a74636c-206d-5ae1-9c32-5883699abd59 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
0375ea78-5990-50eb-b46b-eaefbb893410 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 1
872db65c-98ce-561e-ae7f-4060fc4bfb82 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 2
6516c48a-7453-5222-9d6a-3f6632867339 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 3
ddee1a12-a1b6-5cf5-8485-771d81c1f937 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 4
9379d85b-2b6a-58d7-abdf-d96dfa62b637 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Calibration settings
43813f1d-988a-5079-a39c-4be07389e5c3 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CP020 - U3 ORC SGW Supply Performance Monitoring , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
14e09f0e-b0d0-48f2-9fd0-2475bae9e57c |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter
088858a3-a72d-45d5-a451-f4c18c3e4929 |  | checklist-flat | not-started | ITR-CL-1-128 Temperature Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-128 Temperature Instrument Installation
c4d8e120-ae68-51f5-9988-aa9095cd5508 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-128 Temperature Instrument Installation | Temperature Instrument Installation
4a9e6aad-7ba9-549b-9fc2-1dcc4c9fba6d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-128 Temperature Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
f5991996-a002-410f-a72f-32f280462028 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-122 Instrument Calibration
cda7e439-71a2-540a-af20-642d6d5138eb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-122 Instrument Calibration | Required Data
2b6b3599-7dfd-5f24-a5e8-a1014a66cc01 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
36429803-26db-54a6-896d-8933e4aef7e7 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
ec17de8c-8248-4ede-81df-9c49fb131afd |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning
962c3de9-951c-5f23-b40b-459ffccf83fd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
5d9b050d-575a-562d-a1c5-d562d66d1f13 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
ba50c190-6272-5f06-9015-f8b7a832a666 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
3e13d8f4-c37a-527a-b095-2c7338fc4307 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
706d2928-9d90-5d14-9188-a76c6cd89f28 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
b3ab3ea4-a809-5bbd-9e5e-26c7a8dc1e92 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
82d0808f-8912-5eba-9be5-77e27c5976a6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
2bed0f34-d93d-5242-9924-f2361167d811 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
a02a8d3c-d8ec-55f9-bf48-8e963743d4a7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
d1c46469-4892-5c98-acc8-d87f86069eb5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
5b5395a7-6eac-51d0-91ba-8d7be187aa3b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
3cd5f0e6-f182-585b-ac20-133eea51adf6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
e341ae76-1753-501f-a82a-5a35c695c70c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
49fa1bd4-0c22-5bda-a428-1e0057b90553 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
ce2f4938-1d29-5a80-b221-12606c6a13bd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
39aca28f-0875-539a-b546-ce4aefb459df |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
df69c3c4-7be5-55ec-9b1c-0735184e8f60 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
4219ad2f-8be0-5bb8-8064-b631ae64479b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
7c49cc3e-e67a-53b1-9836-220d650abd6e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
13dd790f-b8d4-5423-82aa-67b0e070ab8c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
13ca997d-a0c2-5e1c-b236-af9ba985862b |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
9f2cf00a-6433-4c54-8cfb-faacb49390ef |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments
c60e7d2a-841e-52eb-b119-94982344e486 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Required Data
f2565b9e-ee57-586d-a133-5287a18b9dd3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
02410edb-a157-558a-bfdc-12f66f12e0c9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
3169d97e-e06d-599e-96d2-a6d09a304800 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
87ca6c2b-de04-5cdf-9c98-4398a117a8e5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
a6a1946c-2529-5c2d-9738-d7be6f783dba |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
ac282740-9e35-59b4-a8db-e14e914a9ded |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 1
2bcbfb67-0d2f-5990-a182-b8fc44a59546 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 2
e032bbc8-473e-5f10-a069-57c98742b7f7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 3
1ace77fb-1f0b-5a6d-8cce-d69dadd1b14c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 4
bc65e23c-8e49-5858-81b9-b469560c5bdb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Calibration settings
f33875c5-9ce3-531d-9d3b-3a2f4d35de7f |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NDA20CT010 - U3 ORC SGW Supply Performance Monitoring , Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
ab93a58b-b813-48b6-8ade-f135ca976511 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1
03c922dc-57fb-4520-b596-44b12f08eb94 |  | checklist-flat | not-started | ITR-CL-1-128 Temperature Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-128 Temperature Instrument Installation
29860b61-6ee2-5aa7-90e8-fdd633ca3df5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-128 Temperature Instrument Installation | Temperature Instrument Installation
b185bd82-cad1-5071-ba70-042c1cb24560 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-128 Temperature Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
37d7532e-3991-4dea-ab9c-8dbcb33f14f6 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-122 Instrument Calibration
a65f468f-43d2-5a66-9803-10dffa5d3665 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-122 Instrument Calibration | Required Data
0e9a718e-5f34-5234-ba80-348e2761695f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
9ca67d1c-3ec2-5fe8-9216-23661135a94c |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
973510b8-4676-45d2-8944-620819c8c54c |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning
ae5cbaca-1d1c-5ced-ad4c-0aa56ae066dd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
3981363c-7541-5b69-9cec-f9a2cf459317 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
d1e7d4a1-072b-59f3-b3f4-ce8181756f43 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
32e5bce9-3112-5521-ae94-e22baf2d9e8b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
a638e47a-34bf-550b-97b4-3560d4896fb7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
1918b3e5-79e3-585b-b4fa-e5d6962f1248 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
16801b76-a802-5aa0-92ad-40ad8d74e552 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
d2b3b7e5-ee1a-538e-a551-46e77950b77b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
c7974bf4-0e0a-5f80-ae08-53d96815d42c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
b094df4f-e36a-5fa0-a0d5-cb39d54b4ba8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
1cfd6691-4069-5188-86e7-17c067a8dd3d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
ae956db6-0359-5562-b0a2-341e9ca292fe |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
6975d40b-4b1b-58d0-a9c5-c897c647426a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
d5a4f7ca-37af-546b-914a-43e50901d985 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
c62f3ed1-d2f4-5d2f-97b7-18f5950c0efd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
91baccac-d27a-532f-ad09-5bce00316f0c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
2281ae71-87be-5fca-8a17-a4a4745d72db |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
6cf08039-7ada-5aec-92a1-37b84c61fa62 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
8296b85c-9725-5b6d-8bc1-4f9afe4db2a7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
05909b15-4a19-5496-89e7-4b0ebd4c7b3d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
4992d965-7e0f-5397-bd39-4b8cc0a6bbf3 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
d8f04d7e-c9ea-491d-8a97-7894e60f5663 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments
2c7d3da0-25b8-5393-8da3-f3b63bb99aa9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Required Data
76375398-e0e9-5541-8f6a-e009b3b052d0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
b285ef76-8693-5d96-bd28-204670d1c1c2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
b972839e-09cd-5e8c-a5d4-319643893566 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
c18e6224-6eaf-523a-8979-6a5cde4631ef |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
4ecd5cc9-eba3-5685-8beb-fadf626e05b5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
734acf4d-309a-57cc-af3c-80eead7959b9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
55f1c07d-92ae-52ef-b8e6-0c425464ecab |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
1b076024-71ec-513c-a0b9-5eca9fdbfe60 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
4ac05bad-262b-5bdd-b073-0877f9d93d54 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
0b1f710b-9cfe-5ac2-aa5c-b13f68e107b8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
3f581311-f8b4-5dbb-b140-7c2e969d6d31 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT020 - U3 Steam Supply Performance monitoring, Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
d366b0da-00a2-4245-b4b0-08f057449ffb |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2
1de9b0c5-28a8-4f2f-9190-b6fba754c0f8 |  | checklist-flat | not-started | ITR-CL-1-128 Temperature Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-128 Temperature Instrument Installation
629e906a-8afb-5b62-8ac2-71175431227d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-128 Temperature Instrument Installation | Temperature Instrument Installation
ad3cc8b2-da90-528f-abc2-bdb2d7dfed71 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-128 Temperature Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
9ac39e83-bd9c-4ed1-b49c-8613d9d0c233 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-122 Instrument Calibration
73f0984b-c08a-5360-bee7-9c41d9a59083 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-122 Instrument Calibration | Required Data
8f00f3e9-64ab-59fe-9e17-fc7eade26aeb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
30576a35-723f-5432-aab8-d21f6c53f27a |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
f85a85d4-f1b4-4df5-b8aa-9bc13f5ff44c |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning
7f8cb656-b7fe-5184-b03a-0fc3d6ebe23f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
bc6e4689-a828-5e2d-8f1b-7355117872a8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
a7174ada-2cd9-5fee-98c9-ff59bca5a76c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
8faab895-dae0-5dba-bcf6-e43920af168b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
26fd8a04-a61b-590d-a841-94c02af1e393 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
64cc358b-f6bc-5795-bf8e-76cac5419455 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
a8e43a8e-a4fe-51cd-8ed6-f26514b4dd50 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
5e6f2aad-7419-529b-9318-ca8132746eb4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
5b4c57b6-bd25-554b-9c2c-72419c899483 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
cd973cb3-63b7-52e9-a544-003db79bed46 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
c7b9cb33-1411-59ce-baa9-a9fe1d1378b3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
914694b1-fede-54c4-a21a-efe0542323cb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
9ef45605-1d20-5bae-bb08-dcd286095911 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
a76ff19b-ea6c-5dc4-88dc-d182ab9d29bf |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
ea5226a0-91db-54dd-bb30-de6c28ea6a18 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
02a05386-39fd-5909-9a9e-fc838c107f80 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
f9ce4538-a65c-5749-8b07-c419913def24 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
3a3df42f-524e-5dfe-b19d-fee12bef8d26 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
39e346f3-8384-5ef2-a721-64834bcb1409 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
ad360234-26ad-5659-91c6-55e8117df29c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
2ce7d638-c634-503e-9e8d-418f870ca4a5 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
dc45cd13-35a2-4b71-a65d-e874772fcf76 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments
cbe6698c-9f81-5b54-a28b-34992bbe76ac |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Required Data
c23a5d01-e170-59f9-a477-8188e85fca76 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
c3406574-0c25-5507-bde7-74d3ca4b6919 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
a8619551-6faa-5916-ab93-7f85641b2beb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
b8322d77-3482-5ffd-8816-65e573c9d342 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
0db48a5e-b6b6-5cc2-8a44-66130bb0d205 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
88a9fffc-0c69-5fba-afcc-cc49efa21733 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
1c1f4174-3157-5a12-ad80-18d2ed65ace8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
6604c794-1b2e-5015-9cb9-b7af89b8f1dc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
9b46caa3-cd75-598e-826f-16503e7c093f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
3b9c92ba-38d9-59b4-a0cd-bba290fb56ee |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
1a04b607-e5de-58dc-8aa9-983ad5c89395 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CT030 - U3 Steam Supply Performance monitoring, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
c11ec479-bd9f-4a79-8a51-a0a43d8836e1 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter
9a9e8ff0-de62-4a67-ab2e-539da847322c |  | checklist-flat | not-started | ITR-CL-1-130 Pressure Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-130 Pressure Instrument Installation
12a2c3f0-589f-51b3-8309-fdb7d52d4f9a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-130 Pressure Instrument Installation | Pressure Instrument Installation
79084736-30d5-5eb0-9506-4e000ba263e7 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-130 Pressure Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
838115c1-0ecf-478d-956f-cbb0f21299d6 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-122 Instrument Calibration
a5bec897-d939-5d58-97a8-554c3e9d9008 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-122 Instrument Calibration | Required Data
31327b12-f17e-5734-86fd-d696e50437ba |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
e2d0b937-0001-5541-8d07-d6f87fe5246e |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
6b615a66-bfb4-4015-8a9d-50e464382a3a |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning
0454f282-da32-558a-932d-7d32c9811d76 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
48f298aa-9711-549b-8849-ccc0a4cbe31a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
f3e080d8-249e-5ee8-8beb-c651bf2660cc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
3f16f92e-4be0-5731-a8e6-09fbf82f6cff |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
e83f8894-3f6e-5765-975d-6d69a386a798 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
dd708de9-da2a-564e-b815-1da88f6712cd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
8e39a832-ce91-5276-8f19-9b3085ed52ba |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
963e7f3b-ad3d-5dfb-99ae-d745f0ec20b8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
f1a0a637-be02-5949-80f0-0167c5b9cdcd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
7db80cdf-371a-53c8-a1b2-9b87c3a0785e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
35e3916d-dcae-52c2-8b5e-dbfab71f34ff |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
2bdc3bc4-3555-5d01-b7fd-176171016684 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
5dd99acd-030b-5f61-9905-ba562eac75c1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
5f054bf4-afcd-5705-9381-e509c3ff3cd4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
377a128f-25a3-5dfb-8c49-89fe523659ca |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
28ca74f9-715a-5e9e-bfdb-8f3f43f9ee7d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
54257507-7c5f-515a-b2a4-3aec15a7bad0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
84366f91-6e5a-5f05-ad93-76ef78985acd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
27cca1cf-13e3-5428-8ba6-be53e54fcae8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
f3a51b40-afcd-52d0-8863-59e59fc7b900 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
f89e9ee4-2f5a-5727-8549-a2008d2c3dfe |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
c06af090-9dbc-4542-bb2f-ba4b28aa9dda |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments
3cd82472-1671-5974-9dc9-93f0b3aabaa8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Required Data
d2566aea-09bd-50a2-9f37-3268bb850f1c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
b45a6480-e47e-5e63-8ee8-71491f741b76 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
2daec199-38b7-5e90-b1a8-fe126ee70960 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
410fa29a-2672-5540-afae-2f838f7eb8ff |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
cff2767f-db07-5ae1-a6d9-476a6be54bc3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
7c57cda9-19a9-560d-9a56-e48d825e4466 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 1
0c7d59b1-fcae-5411-96e4-0f02cdc28bf3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 2
f8e82847-cb57-595c-8f20-7ffe8b390924 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 3
d10498fa-732f-54a4-82ba-a83340427c7f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 4
e00a6eaf-fc44-5f97-a67f-3e4a9b87fe2b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Calibration settings
b8fac37c-c7ff-5494-a4ee-39a0cb2bc08b |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CP010 - U3 ORC Steam Supply Performance Monitoring, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
5f4922ba-3153-4c3e-8f72-9f96ed3cdea8 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter
44157ced-6396-4d34-94e1-a786dbb9660a |  | checklist-flat | not-started | ITR-CL-1-131 Level Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-131 Level Instrument Installation
61232a06-2f40-530e-a743-75a297ca8994 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-131 Level Instrument Installation | Level Instrument Installation
870f965f-7d4c-553d-afd8-c87d2cbf085c |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-131 Level Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
850790f2-63ee-4384-baa2-7bdfcbc02305 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-122 Instrument Calibration
a0fe16fa-3553-5f06-bd0e-012a763929bb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-122 Instrument Calibration | Required Data
1ea7ff35-1608-5914-a112-c32c7cb8c6e6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
861389a6-5d07-549a-9bd3-bba140a889b8 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
4da89128-bea2-481f-9da2-0dc816587bc3 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning
eddffe3c-4aab-523d-8265-89d96e1492ee |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
5956077a-32f9-59f9-a531-a68cb6566cf3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
78254134-f108-5b07-82f5-f1cd92281302 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
3143384f-4da3-56ee-a83e-10d7b576343d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
95d481e6-870f-5a7a-96f2-6d69d75aa990 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
76c9a015-ea6e-5389-8a1f-912cdc5972b5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
7a46ddde-36d7-540f-92e3-e892af3577f5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
2f4cbd65-6ccf-54f1-9a14-8ba1a5136d71 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
ce54f473-2e43-5afe-81dd-97b7758773df |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
152e3586-cc9f-5f34-b38a-78e56d48c74e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
aba41a34-edb8-5156-8b9b-498221527a56 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
1eb7f7d9-d9c8-55e4-a51e-f5b1536b5cc4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
d4bd7f38-efcd-5d4a-b8a8-b12ac1ceab6a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
3c3a0b46-dbe1-56d5-b588-44c6199a7107 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
d787af45-3227-53bb-810d-15d0ba1fa88c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
b42b6314-9a61-56af-b4f7-0021d43181d2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
3f9ba220-3b32-5bc6-b780-448d8382efc5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
994b7458-413c-504c-bd27-01083c8524ce |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
725d4ce8-9fff-5f42-af0e-3f343648e5d3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
bf5e2830-cb03-50e1-98df-8f48de32e99d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
9542bbe4-10ac-5034-b044-e4f6eaa80377 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
4f9d9caf-f568-42fc-acb7-106f046bc38b |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-124 Commissioning Instruments
5e5c13fd-e045-5242-9cba-599be676550f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Required Data
0320f17b-d733-59a1-94db-df4d88776f67 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
fd35c756-64a5-58a6-b3a6-20e3a511046a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
a39bb5f7-1992-50c0-b915-434f0a27441f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
52e6dcda-a402-592a-b309-d7d6efbccc9f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
b3c28109-4250-53a7-9fc8-fa114392689d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
7b8b300a-5a4c-52e0-9c84-7a9ec7f7c025 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 1
96c730b4-9044-5708-af2f-36e927bbeba7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 2
2eb25cee-ff0b-5c1d-af13-5ec5da37ed0d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 3
4d1d5361-6c89-5314-8772-929d617fddb8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 4
62e20440-8154-56b9-9793-b0558f89665a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Calibration settings
12165e02-3dbf-50ae-8ec1-e22f1b1b8144 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00S030NAA10CL010 - U3 Steam Supply CDP3, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
8558aeb9-2634-4c9d-acbf-b5aac9e4fea2 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter
06bf0d29-383e-40e1-84d0-26ec56722a39 |  | checklist-flat | not-started | ITR-CL-1-129 Flow Meter Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-129 Flow Meter Installation
7d136e39-9866-5970-a219-470d65042d4f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-129 Flow Meter Installation | Flow Meter Installation
9b0b620b-6fdb-553f-9aae-98884594018c |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-129 Flow Meter Installation | All relevant signatures (Installed by, Approved by, Client Representative)
adb395ae-bac0-4d31-9561-932704fe8079 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-122 Instrument Calibration
2bc3d77c-caf1-5112-8db8-3083d4317399 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-122 Instrument Calibration | Required Data
50edf295-f6f8-57d0-9d3d-b3f1b06be9da |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
4dbb1adf-9490-5902-85a8-27eed1f4493c |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
ed11985d-3c3d-4cc6-b911-6f0451db3cc1 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning
189c8260-0045-5692-84fe-160eebd7663d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
1c559489-9fdc-5d32-ae8b-683beb4efc60 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
33b2bb5e-916f-5772-8c1f-dc620420b28d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
aa27d104-3d58-530d-8d4b-b7002c3507af |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
816bfd3b-df88-528d-b59f-8331249e4fd4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
507484ec-65c5-50d6-af01-bb8d2abec0ae |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
27a02571-9e72-5f49-83c7-29f1414fe18b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
9a2e986a-d82a-59d5-a119-fd6960eacd58 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
c6a02849-8349-5ef7-8c77-73c30f8cf7eb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
c3c15c77-6389-5e9c-8414-dddc13afd5a7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
17a33f2e-4fa3-5c3b-ba75-9226da88ecd0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
0c31e7a2-1649-522d-80bd-e1e09f5702f0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
2bf653d3-1062-5b6e-8c75-e4d74ca5a6ed |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
f989e130-e18f-52d9-86c9-af1dbbf6e20d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
2957788a-f522-5c6b-a2c7-c73c49292578 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
c336d3dd-6d16-5a82-9941-ecd0b8170b20 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
c153b83f-2fcb-5b8c-9e72-0ffad841d297 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
5fd56d64-0dd9-585e-a2f3-cef5d563602e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
35a7a8f2-51f5-5f77-ad79-ec6f4eddd9c3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
9ca91312-a0b3-57fa-8551-bee5f9f58739 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
608e5765-121a-536a-829e-3358e29b5080 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
b18037a3-7ec8-42f4-872a-0cbb6ffae559 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-124 Commissioning Instruments
3c7b187e-3935-52de-8a17-03b4b67ed980 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Required Data
83c42c99-9c82-5429-a068-5751df4d1df9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
80f0ccd7-6107-5205-8a68-460426aca096 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
abd0fd38-1343-59e0-b1e2-7e2872cd983d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
d93052c7-185f-5a04-9d26-79010230b4af |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
3b5379af-3e10-5f22-8179-bc2f74dd11d6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
a4af6914-a13e-5610-9ec7-9ad02151c144 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 1
be965ce0-e62e-5b25-8e1b-a97de4e1615c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 2
6478d140-e12c-508f-bf01-5bffbbac0241 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 3
fa4f523f-6846-5fb7-ba61-284aac025591 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 4
092cf237-6b31-5d4e-889d-82db3ffb5418 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Calibration settings
d1f4affb-44d5-5916-8916-3e55d6c37799 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CF010 - U3 ORC SGW Return , Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
3da14fc2-0146-4091-884a-adee15d63e01 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter
89eff451-cd9c-4173-b710-5ac7eedd8560 |  | checklist-flat | not-started | ITR-CL-1-130 Pressure Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-130 Pressure Instrument Installation
ecc207ce-c424-51e8-ba45-284a7d190d4d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-130 Pressure Instrument Installation | Pressure Instrument Installation
6a089913-08aa-52c2-aacd-2b18f08bc13a |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-130 Pressure Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
a2a828a6-c9a3-40bd-a6a8-8096e929db5f |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-122 Instrument Calibration
acb29932-abb0-5fcb-a8d7-65be8eecb117 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-122 Instrument Calibration | Required Data
d6d0771a-45cc-57f9-b0bb-5cb819308c14 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
6d19bbdd-36d2-5cef-b9e7-4716c9465c2e |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
e8b15876-4977-48d9-80c6-4b5d31951f9e |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning
7c23b750-c7d0-52c0-8a35-f523b2a25595 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
ef250cb6-7414-52b5-a6b5-0858fc1440bc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
ad515fe7-faf7-5e8d-9b31-2e74acd9fa45 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
03e89adf-1fd2-5a9b-a810-3488635d4482 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
6ff64399-a041-59bc-97a3-c2937caa2a6b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
3dcc3737-6af2-5306-8bb1-ff027c3d6c14 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
464dbc10-2bba-56f8-b768-6b998680831b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
f768403e-893f-535f-9d1e-fc4cae994191 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
f72ee8a4-6df7-577b-88dc-e338ea46b6e5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
5943c502-73c7-568d-9719-78d86673bda2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
128a15d3-3a32-5855-a9fd-e6055aa15cc9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
bd6acd0d-304b-55f3-8e7d-99ba6a1322f5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
b98f062e-fcd5-5c3d-bcf5-48b5329bf9b7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
7b2f08b7-feb6-57fe-9e7e-ee4d0990e6b6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
65f61e96-a4eb-542a-828f-d7db940e5386 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
674bc91b-bd1b-5d12-8430-eb1179852ecb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
e5cdb38e-5dda-50aa-88d2-7b2ff649ca98 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
5370f392-a3d5-5fc0-8087-980f4ec1da63 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
c8e930ad-2542-5bb7-a96a-38e3962fd0a1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
810c16d3-aee7-538f-ad24-2a45e9841eaa |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
ba1b6454-f475-5118-a16c-dd4c9cd94b67 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
3a00c2bb-30c9-4166-9b62-cd355eae5efb |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments
cf3b7362-70c8-58eb-9bfe-2b6a5fd52fa3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Required Data
6b932572-3bc0-5d11-93cf-7bc6ee33c8f4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
af1ee67b-9def-5712-96b8-c41f8d8e8966 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
bc9dca0d-4b0d-5267-8273-8c6c73c80b8a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
f94f567c-67fb-5aea-8814-789da5ff0e9f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
1f30f1fe-1811-5432-90d4-b5b89ac52795 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
07ffbb19-2752-5e84-9466-4c763fdde74b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 1
a744de12-b6fe-5661-b607-566df3e8d2b0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 2
e3bece4c-6525-51a3-a6b9-7a063cd10d96 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 3
7ee3664f-39a8-597c-b052-6c5408225c73 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 4
e2346847-b8e7-5b2d-89be-c8813c6b9c9c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Calibration settings
18b17bc3-d613-5ca7-afc0-9c147c55d0c3 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CP010 - U3 ORC SGW Return , Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
8fe00952-7761-47a3-8491-55452bd47e26 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1
ca230147-5ee0-4c5f-bf72-3d93c65f8f87 |  | checklist-flat | not-started | ITR-CL-1-128 Temperature Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-128 Temperature Instrument Installation
d2ebdb6e-97a3-56ae-b71e-f86dffcb65a7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-128 Temperature Instrument Installation | Temperature Instrument Installation
310de228-758e-5295-9357-89c09d4d4b2e |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-128 Temperature Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
3ec1631a-b9b1-4b23-8d37-0b824b50a774 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-122 Instrument Calibration
0065beaa-8483-52f7-8ae8-f482b323e6e9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-122 Instrument Calibration | Required Data
8c0f692e-b533-563b-8e0c-647e4d1ad188 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
9ae348d4-f616-55ec-9105-99218f1c9a6b |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
74c9fd19-b805-4dde-aca3-d42fb77d3729 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning
9c00412b-6421-5520-b300-6d32f5188203 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
72faeb5b-4a25-519a-a953-08ce99c52db6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
0741b849-ab10-55ac-878c-4632a189def7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
daba819f-82d9-5125-9dd1-61051fc55e46 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
339a4795-5036-5973-9771-4aab657ec3de |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
a6ac9696-ee93-50e7-9353-e58c6c4caa68 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
7899b25f-c92d-5031-bab1-6be80ce79f56 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
d8ddee3e-27fa-53c6-b75d-5b127148a7f3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
2175a882-3ae5-5dd9-82ef-a960ea30b0f2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
6281e15e-94f3-5d1c-ba66-8915c7fb977b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
68a1a3e3-1875-5c54-bc94-36e46e56d00c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
5f35153f-be09-5685-929f-2db0f4d0885c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
92b79ab5-72f2-5be3-924d-f5f9541bd8ee |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
b84bd2f5-aff8-57e5-abfe-808cef37fdc0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
834d1aa3-8b27-551c-8d53-584e3818e44c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
cdb29641-b016-54e6-bd19-aaa6d0c6b5f0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
e86645de-a60a-5773-af7b-423da06dd267 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
48115529-9942-5dfb-ae06-506daf3486fa |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
c2d48a36-882c-5d34-86e8-c078076525f1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
f0ab0875-c250-5a4a-931c-b0f9560a7682 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
243794a2-da0a-56ae-848b-81350141c444 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
9469a95d-3a8a-4f49-b179-c17628efcfd6 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments
fa94a563-4505-5374-81a9-acaf367d80e6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Required Data
b3797374-7dd7-5daf-834a-f74708f6bb48 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
90476c67-aff4-5c59-a5d6-37a711e03210 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
ee94a7fc-1f3a-5775-a649-23b148960c86 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
cf916185-1542-5073-881a-6fc6d925ec51 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
76e75f9e-8f5a-5eea-8efd-616e760bc571 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
98fb6f7b-9925-5591-b2be-40e539ed0c49 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
a5c9d2bb-eefd-5e35-b391-feadb84f55d9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
2d17bb49-1f6e-52ee-bbd2-45ef62d4a6d8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
e8a31998-c489-588f-bba2-1211b698a6e0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
09a92730-0ec2-54f8-86e7-4238a156f417 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
b5427deb-fcc1-52af-b1a0-a4acc043192a |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT010 - U3 ORC SGW Return , Temperature Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
af047718-7575-42fd-87c4-116dca6d5511 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2
4faa3e59-79c6-4536-a400-fcded834ba6f |  | checklist-flat | not-started | ITR-CL-1-128 Temperature Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-128 Temperature Instrument Installation
8579af8c-ec8f-5ab4-9acd-5725aa8eca1f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-128 Temperature Instrument Installation | Temperature Instrument Installation
92a308bf-90f8-5854-9e36-53363b62c972 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-128 Temperature Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
5d16331f-e4b9-41cd-a9ac-acbc51e17aff |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-122 Instrument Calibration
5773a6ae-7c9e-556f-8aa7-b2933514ba6b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-122 Instrument Calibration | Required Data
b1634e29-462b-58f7-8a67-4b153fc43a56 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
38afa761-8e5b-5921-8ee5-6e04a5ef6c59 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
2c1fe494-2a12-4021-9b12-22490996216a |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning
ec3fb0a5-a762-5705-8f95-866e0533b146 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
e032bdf3-11b3-58eb-a860-2f315b3a28c4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
bc51aeb7-1893-5968-837b-5a83a6e05a03 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
930d94a4-58d0-52ac-8122-a493bbeb9c1b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
237a96d7-9f78-5203-8522-6aeb02b7f794 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
aa5e34ae-ecd4-5ded-bad9-a6eda00e0e61 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
af173e85-6f9c-58f6-878c-d6471ce06598 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
db3011e7-52f8-5840-b7fb-9da6aff0ee6d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
31473b22-3ead-5199-99a0-e61a9bef2f69 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
72628748-b25a-59e0-98ce-905ce35d8cad |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
97bfd2d9-75e8-51ae-b2de-53c21bf46e42 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
8f657213-9b0b-5d2f-bcf2-28581380f4d0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
d07ce816-b306-5414-ba69-a5fd25962f33 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
22481c06-ebba-5a02-b0ac-28b0219dab6e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
28031d65-86cf-59a0-a647-977f36bcbd45 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
2867ed6d-b9b4-5b11-b3a2-48d4631b0261 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
59f45a78-b933-589b-a22b-3e1e2fda9c79 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
5cd1325e-fc46-5ef1-b89c-2292f6833f70 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
e94f973e-b8e2-578e-bbd8-c5f1b614d0fd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
6f5c086f-58d1-5155-9212-2e0fa84440e2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
c21938cb-cb86-506b-8df9-b7d375388b1a |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
5c8fe8b0-423a-44e6-8b97-334053a9dc8b |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments
92941c60-8d9e-5b3f-a033-98502f5858ca |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Required Data
21b56d62-b61a-59c0-8506-eff5eea3a552 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
03a6ce20-bdab-5d09-a5a1-826c4e8cb3ed |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
14b56528-2a4a-5a40-a223-8fcd719224d7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
3df11d92-b441-55d7-8963-7d479bef67bc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
f41eda6c-144a-5152-88c8-1531aaab77ca |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
098a8bcd-549a-5a9f-91d2-fb70d7f7f955 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
c390f7f1-27a5-5759-8b36-4a42cbaf18de |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
8fc6616f-abf9-5f91-bc22-e8dfbaf39322 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
2e0b719a-8ddf-50a4-9597-767f655c8448 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
ff021d43-9815-5114-adba-0b5db30c0ef0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
c476814e-953d-5dbd-8854-2e38fbab48e4 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Instrument | TH00L260NDB10CT020 - Reinjection Line D/S EDP return, Temperature Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
9005843e-6981-4101-bf3c-b1ea0886a57f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables
a75ab5e0-4e55-487f-aa13-2f9dc16f23d1 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030LFC20CL040-A01
3a6e7aa3-6559-4ed8-a102-55fd9032fec3 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030LFC20CL040-A01 | 1.5mm2 1Pr CuSn CS
c3098d59-f8ad-5605-81ba-03f1572c7aad |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030LFC20CL040-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
eac8babb-72d0-5e4c-a57f-4c1883251710 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030LFC20CL040-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
045e087a-f2bf-41e0-bfcd-8f229b24b7d8 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | Junction Box 01
9c5454db-1a4b-465d-91f8-b877a50f624d |  | checklist-flat | not-started | ITR-CL-1-106 - Junction Box | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | Junction Box 01 | Junction Box 01
d0af2458-7a96-5f24-b714-dc94777ad839 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | Junction Box 01 | Junction Box 01 | Junction Box
d30fd337-a828-421b-b73d-86ef46273542 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030BHX10GY101-A01
13672b01-077a-42b2-b48c-5dad53208430 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030BHX10GY101-A01 | 1.5mm2 12Pr CuSn ESCS
8b29de54-fd34-5191-8ca2-3b6001dcbb67 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030BHX10GY101-A01 | 1.5mm2 12Pr CuSn ESCS | Instrument Cable
69762f5a-b265-5c62-a252-7fb9ff856237 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030BHX10GY101-A01 | 1.5mm2 12Pr CuSn ESCS | Electrical Checks
fad0b52f-643d-48cc-b39a-1979e9666369 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT051-A01
6c3026ae-d8b6-48b8-bd02-c5addc616afb |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT051-A01 | 1.5mm2 1Pr CuSn CS
63a1bd6d-1622-531b-ab21-4edc4be99fe2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT051-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
8abf4019-01dd-5fed-a7cb-f2e3f890e198 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT051-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
a6700bd3-029f-4673-9f7b-9d8a885382d5 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT052-A01
fa45c4ac-8ecd-4db5-aac9-9ce854fbb700 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT052-A01 | 1.5mm2 1Pr CuSn CS
80726285-bda3-5cdb-8ea9-e46910b75330 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT052-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
eec4866f-ec12-52e3-b1fd-6ae4b323393f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT052-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
5d450e09-5c95-454e-9d15-8466bcff4bdb |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT053-A01
a10ac3c7-19fc-466b-9ddb-1a8e180c3a36 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT053-A01 | 1.5mm2 1Pr CuSn CS
7ad76aa6-680b-53fe-a916-a3176447060f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT053-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
e985fa37-c8c0-5b86-b472-a424c3216341 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT053-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
b956b9f2-66e2-4e00-be82-1773793544d9 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT054-A01
543dc6be-1d1d-4661-a6a9-b4b84de65a28 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT054-A01 | 1.5mm2 1Pr CuSn CS
3c9a7030-ba68-5958-b47d-ab6858205d67 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT054-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
3ace9039-a955-5593-b88e-fa6b34c5b135 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT054-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
33720965-ce7b-44ac-9d41-bdc4096638ba |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT055-A01
a9d48bca-ca74-4d4d-a234-444c5e69e313 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT055-A01 | 1.5mm2 1Pr CuSn CS
bc42a0b4-e0fc-58a3-85fd-7b7dad2abb46 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT055-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
c541f91d-e48d-5c83-b248-217e3622a805 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT055-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
4edcb81d-346c-4c50-9e8b-b70af9ad4df4 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT056-A01
d17969ce-1bba-4f7a-be65-171de7c5a492 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT056-A01 | 1.5mm2 1Pr CuSn CS
e63d9c30-a24e-546a-8071-e715ce68ed20 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT056-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
48254c99-b709-5eed-8f7b-56070bd195b7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT056-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
e9a3087a-5b0f-4616-b70d-3da31ac6cc6d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030BHx10GY101-A02
7b24f8a6-3fa2-4565-a9d0-95a7d55e54ac |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030BHx10GY101-A02 | 1.5mm2 12Pr CuSn ESCS
d68a33fb-5a74-5580-9058-26d8573fbdb5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030BHx10GY101-A02 | 1.5mm2 12Pr CuSn ESCS | Instrument Cable
2a196f1e-77cf-599b-8463-fdc70fc1ffd3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030BHx10GY101-A02 | 1.5mm2 12Pr CuSn ESCS | Electrical Checks
ddb93459-82fc-412f-a57c-510965a8101e |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00V030NAA10AA110-A01
3eacb607-5a43-4219-8419-85ddf875b36b |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00V030NAA10AA110-A01 | 1.5mm2 2Pr CuSn ESCS
75ee96bc-b5a9-5203-be4b-593dd2ce3489 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00V030NAA10AA110-A01 | 1.5mm2 2Pr CuSn ESCS | Instrument Cable
4f9efd89-e710-5423-b305-292ea27984ec |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00V030NAA10AA110-A01 | 1.5mm2 2Pr CuSn ESCS | Electrical Checks
fc79524f-1ab3-410e-91d0-292f7faa57b4 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00V030NAA10AA120-A01
e072245d-e048-4b4c-8519-f5fdc3345079 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00V030NAA10AA120-A01 | 1.5mm2 2Pr CuSn ESCS
e7f8df2e-3998-5977-a49e-4de19b5817a2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00V030NAA10AA120-A01 | 1.5mm2 2Pr CuSn ESCS | Instrument Cable
b409f0a2-88de-5c15-b5d4-742f4287c029 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00V030NAA10AA120-A01 | 1.5mm2 2Pr CuSn ESCS | Electrical Checks
3aa12805-f4fc-4e67-8af6-1dd891571aa4 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CF010-A01
4856c745-c352-4369-971c-06fce836c461 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CF010-A01 | 1.5mm2 1Pr CuSn CS
d6dac60f-8d2f-53ec-b7b4-ec36bd609408 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CF010-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
9addd21d-7b58-5ab8-88bc-f666826e8f85 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CF010-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
cc0baed4-b111-464a-80cb-37c3429782e2 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CP010-A01
5832bdfe-98ab-442d-a935-974d7b1790a4 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CP010-A01 | 1.5mm2 1Pr CuSn CS
84152913-ac2b-5225-aedb-d175b79f6f06 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CP010-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
43b4499e-bed0-507c-a749-43c9a0bf668c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CP010-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
b9331f62-4cb5-4037-b30f-d614c6025f11 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA110-A01
b5d84bb0-088f-4b67-ba73-5b21055ad36b |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA110-A01 | 1.5mm2 1Pr CuSn CS
7931fd22-6911-56cb-a43d-bce6d8be9e0f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA110-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
6d91ba92-6bb8-55fa-a1ff-988a20f5acf0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA110-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
5820cc56-c076-486a-855b-b22ae8771457 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA120-A02
35dc4526-602a-46a1-a454-cb33a12dbbe4 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA120-A02 | 1.5mm2 2Pr CuSn ESCS
217a55c6-d05a-58b9-92b3-d3f43d93ca09 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA120-A02 | 1.5mm2 2Pr CuSn ESCS | Instrument Cable
3e1a538b-a6e5-58e8-996c-891aa4db1dec |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA120-A02 | 1.5mm2 2Pr CuSn ESCS | Electrical Checks
f5955572-f8ff-4b86-baca-6fca2011de25 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA130-A02
8198d92a-08b8-4610-b8a4-a19b13f7a0d7 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA130-A02 | 1.5mm2 2Pr CuSn ESCS
be3899d3-7d0d-57bb-a528-1ef57d442ee0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA130-A02 | 1.5mm2 2Pr CuSn ESCS | Instrument Cable
be06d9ac-05a3-5920-aec6-a34828c12005 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA130-A02 | 1.5mm2 2Pr CuSn ESCS | Electrical Checks
ee17e915-bf75-42a1-9ddd-3dce5f0579f2 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030BHx10GY101-C01
aca7ef58-4bba-4ac7-b249-f0ab9da17ebd |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030BHx10GY101-C01 | 1.5mm2 27C CuSn PVC/PVC
4c9c8206-4de6-53ea-a498-7fb95ee57e83 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030BHx10GY101-C01 | 1.5mm2 27C CuSn PVC/PVC | Instrument Cable
3a2b64cd-7029-5eec-8361-e09d1e2244a0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030BHx10GY101-C01 | 1.5mm2 27C CuSn PVC/PVC | Electrical Checks
0b2ad06a-b62f-4597-b430-22bee4f34bb0 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00V030NAA10AA110-C01
a783771e-7ec3-4304-aa6a-463215842bb0 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00V030NAA10AA110-C01 | 1.5mm2 4C CuSn PVC/PVC
91f8b8cc-3f52-5277-85ca-82fb454c3b0d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00V030NAA10AA110-C01 | 1.5mm2 4C CuSn PVC/PVC | Instrument Cable
7425da84-3e63-5243-b2b7-c37bca5084ba |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00V030NAA10AA110-C01 | 1.5mm2 4C CuSn PVC/PVC | Electrical Checks
92c62472-440e-4b9e-8c14-7e27d5a002d1 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00V030NAA10AA120-C01
5ea7369f-09c9-4d2a-9300-d5cdb9fad34b |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00V030NAA10AA120-C01 | 1.5mm2 4C CuSn PVC/PVC
d81df519-7539-58bc-8ea9-26c72d97722c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00V030NAA10AA120-C01 | 1.5mm2 4C CuSn PVC/PVC | Instrument Cable
4d3f7c8a-c2a2-59fe-812f-f11c99c748f6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00V030NAA10AA120-C01 | 1.5mm2 4C CuSn PVC/PVC | Electrical Checks
ee6091e0-b745-4da3-8c7b-b73c00782542 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA110-C01
ca96421a-f92f-40b4-8031-bc707cec557f |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA110-C01 | 1.5mm2 4C CuSn PVC/PVC
1f34b455-8a27-5422-a742-4b973357e8ed |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA110-C01 | 1.5mm2 4C CuSn PVC/PVC | Instrument Cable
39390238-e989-5bda-836b-278b5b89bd14 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA110-C01 | 1.5mm2 4C CuSn PVC/PVC | Electrical Checks
15e36b20-b6ee-47cb-b289-c84358f22f26 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA120-C02
50e3c30c-dfab-4988-90d7-987aaf661f5a |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA120-C02 | 1.5mm2 4C CuSn PVC/PVC
03513d2b-f008-50b1-86ed-bc3091be1bab |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA120-C02 | 1.5mm2 4C CuSn PVC/PVC | Instrument Cable
8e43efc2-35bb-5465-850b-df62ca232b0f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA120-C02 | 1.5mm2 4C CuSn PVC/PVC | Electrical Checks
6dad0e32-8983-4b4d-9903-38923b475db5 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA130-C02
bfa49c44-3b6f-45e9-879b-bc7b28a1f09b |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA130-C02 | 1.5mm2 4C CuSn PVC/PVC
fb68e9e7-471d-5882-bb0a-e092dbb217cc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA130-C02 | 1.5mm2 4C CuSn PVC/PVC | Instrument Cable
b7374fef-388f-5b28-bfba-d3c7d54339f8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA130-C02 | 1.5mm2 4C CuSn PVC/PVC | Electrical Checks
47cdc0be-e90e-436f-8295-80ce4288199d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030LFC10AA420-C01
e68d4004-b70f-4de3-8358-1d150ff97b7f |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030LFC10AA420-C01 | 1.5mm2 4C CuSn PVC/PVC
8cef16d2-0e75-50ab-a4fb-239edc2de7da |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030LFC10AA420-C01 | 1.5mm2 4C CuSn PVC/PVC | Instrument Cable
e98d8671-1bea-593c-b288-b677808fa52c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030LFC10AA420-C01 | 1.5mm2 4C CuSn PVC/PVC | Electrical Checks
f253ed2a-4d94-4973-afaa-6069aeb30f24 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | Junction Box 04
8a570e36-f2e7-4713-ad46-ab04df297da4 |  | checklist-flat | not-started | ITR-CL-1-106 - Junction Box | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | Junction Box 04 | Junction Box 04
2e36b18d-0e85-5905-a8df-f085c4b5225e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | Junction Box 04 | Junction Box 04 | Junction Box
29e7d274-144d-42d5-86aa-ca1144826286 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030BHx10GY104-A01
2849a31f-49bd-4f5d-9c3e-edf45e8036ad |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030BHx10GY104-A01 | 1.5mm2 12Pr CuSn ESCS
a3e0f0a6-c61e-5c6a-a104-e6e0489c23f6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030BHx10GY104-A01 | 1.5mm2 12Pr CuSn ESCS | Instrument Cable
1397fb42-d6c1-5998-8acb-d1e2b4288b27 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030BHx10GY104-A01 | 1.5mm2 12Pr CuSn ESCS | Electrical Checks
1cb8d7a6-d031-4bc5-9391-86f416c575c8 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030BHx10GY104-A02
7b71e1ba-337d-43f9-add9-31893fe9982a |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030BHx10GY104-A02 | 1.5mm2 12Pr CuSn ESCS
078d3013-bfc8-59ef-aca0-90ed42d88537 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030BHx10GY104-A02 | 1.5mm2 12Pr CuSn ESCS | Instrument Cable
4a23feba-bc4b-5e0b-9416-95b79078cd22 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030BHx10GY104-A02 | 1.5mm2 12Pr CuSn ESCS | Electrical Checks
ca29b5c0-ca3e-46c4-8060-bfaa096a40bf |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CF020-A01
cb1b2aa1-3ad1-43d5-92ae-a7532d3c109c |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CF020-A01 | 1.5mm2 1Pr CuSn CS
21386600-2a4f-5525-97a4-c6aaa71482d1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CF020-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
c3c79917-1cbb-57a3-b2a7-7fd9db202a56 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CF020-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
1a107654-9e88-46f8-a399-31f25bf50f54 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CF030-A01
be625a0f-ca32-4173-bd68-8897d27d74fd |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CF030-A01 | 1.5mm2 1Pr CuSn CS
ca1849a5-7eb6-579c-98ed-994a7b88ecb4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CF030-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
b8a6c4f1-60a3-561a-b1bd-16695f01b4e3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CF030-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
08ca7e86-e443-446d-82af-56bac7be70dd |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CF020-A01
7e9b0409-83b7-4688-92b6-0275d6af8361 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CF020-A01 | 1.5mm2 1Pr CuSn CS
52a268f8-968e-584a-bb85-7494740d1d90 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CF020-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
4ac808fb-6c8f-5b70-bd6e-c3170f06d252 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CF020-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
5be76f72-8312-415d-9045-b7b05042eee9 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CF030-A01
30cacdc0-17c3-44f2-a655-6c60ea769d50 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CF030-A01 | 1.5mm2 1Pr CuSn CS
1f91295e-29d2-5f26-ad77-fa34b6bcae52 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CF030-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
0504c2a0-bb6d-5c69-aff9-b4954983f114 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CF030-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
85755732-4a8d-4ff4-8fdd-88d0c02f364a |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CF040-A01
45a102d0-4c62-4267-a64c-c5c2c556da56 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CF040-A01 | 1.5mm2 1Pr CuSn CS
379f9013-3165-52a4-bdf0-68c977148b21 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CF040-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
80288baf-613d-5d07-83fb-e7ef377d0f3a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CF040-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
0c0778c8-772f-45bb-a374-2cf4cb8e050e |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CP020-A01
3c77fed2-b7c2-41c2-88d9-dba757933b72 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CP020-A01 | 1.5mm2 1Pr CuSn CS
ce0a8914-f42c-5a89-ab28-0110287c2a46 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CP020-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
07c22585-ff62-5594-81dc-4db0d538ef75 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CP020-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
e9fde0df-35b4-4e13-90d0-b3528f65a7b5 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CT010-A01
f424c4c9-1482-4f22-a883-68298a7acd73 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CT010-A01 | 1.5mm2 1Pr CuSn CS
2d6cdc5f-fa74-5421-9e66-4255048dc3fb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CT010-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
8f46b8c5-c863-5ba5-bf2d-e5fe596e19b8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20CT010-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
9149668b-20de-424f-babf-a98a95406e07 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT020-A01
8d0b79ba-3306-402c-9041-7829cb533c5c |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT020-A01 | 1.5mm2 1Pr CuSn CS
e864e844-3430-5da5-a483-4e8f576daa95 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT020-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
9f8d3b6a-97bf-5c16-ab5b-81c820275a54 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT020-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
8110734a-df50-451d-9d3a-79bd27997fef |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT030-A01
8f9d26c0-eeab-4031-8c3a-ab8613c08981 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT030-A01 | 1.5mm2 1Pr CuSn CS
f89dfada-5e99-5119-b588-4d73c2c69530 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT030-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
9df01d37-2b08-58eb-952e-9e06055e5b17 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CT030-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
1a99a452-feae-48d5-a8cc-436357d3b1eb |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CP010-A01
8f2a5a07-6997-4fc3-b71b-28da7d2ed54c |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CP010-A01 | 1.5mm2 1Pr CuSn CS
810fd323-97ca-50a1-99cb-1f82a68b74af |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CP010-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
5a713d3d-5b7c-567d-9d4a-0f590a1fa8f5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CP010-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
d6fe9e53-9424-4381-86cd-ada863a13b6e |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CL010-A01
dc88fe56-52b8-45fe-921c-32cf65270e67 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CL010-A01 | 1.5mm2 1Pr CuSn CS
0587e96a-a1d3-5570-91e0-00f399338333 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CL010-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
4d88e132-0eb2-5779-8002-ec7376c534d0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NAA10CL010-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
6ba2487d-cce4-4cd6-afc0-87dba7a4c900 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00L260NDB10CF010-A01
e14b3b35-1346-4e67-aa46-7bfa08bcfef7 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00L260NDB10CF010-A01 | 1.5mm2 1Pr CuSn CS
e612c04e-bf1b-5f1d-b146-0deec5526a01 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00L260NDB10CF010-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
de4c8534-4092-50ea-a9e1-e78212afdf71 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00L260NDB10CF010-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
654831a1-933f-4d71-840d-c34908922a7c |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00L260NDB10CP010-A01
5dfdc73d-1a9f-4af1-8aa1-f91112307249 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00L260NDB10CP010-A01 | 1.5mm2 1Pr CuSn CS
ff7f7d96-e2d6-5d4e-8461-18020c916392 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00L260NDB10CP010-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
ea66b5ce-5f5a-56f1-afa8-2d4ac5125205 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00L260NDB10CP010-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
dfa9c57e-4a37-4db5-ac8b-a1a1ff9f5e59 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00L260NDB10CT010-A01
0387be75-6abb-4892-a5b5-c362ac6fbc42 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00L260NDB10CT010-A01 | 1.5mm2 1Pr CuSn CS
cbacfc19-1295-5af5-8ba2-febd0e47748c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00L260NDB10CT010-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
c4fce459-c0e9-5bae-a4c2-cbc2fc41b578 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00L260NDB10CT010-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
e249de06-70cd-4e49-9fe1-ab6ef965de81 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00L260NDB10CT020-A01
2dd54593-3936-4cf7-a98b-b1128a928856 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00L260NDB10CT020-A01 | 1.5mm2 1Pr CuSn CS
3e9d96b8-ebee-571c-bd54-48fee96a69d7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00L260NDB10CT020-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
72f3d899-0fa4-5756-9807-76977cf2670a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00L260NDB10CT020-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
945f7cca-c77a-4da2-9c5e-766e415d416c |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA120-C01
b0fc1982-d83f-402e-825d-3f2af5dbba43 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA120-C01 | 1.5mm2 2C CuSn PVC/PVC
623199f9-3e08-579f-8719-a281789dfc90 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA120-C01 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
b3bfa1ed-2e38-5a62-b6fd-4e6d53906576 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA120-C01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
822ee323-42e3-4787-a7a5-78b12cf49977 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA130-C01
9d334465-80bb-4da7-ba93-684a47c0af6b |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA130-C01 | 1.5mm2 2C CuSn PVC/PVC
eb1adbbd-47a9-5a46-9e1e-61f446e5099b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA130-C01 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
4cddc5d5-0179-501b-8031-be91a6216ba0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Cables | TH00S030NDA20AA130-C01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
671a9be3-31a8-42fb-8134-491277f2742b |  | checklist-flat | not-started | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP-SEP-E-005 SEP Vent Station | Certificate of compliance (COC)
85b18f1e-2fd5-524d-a7f9-a8f74818b3cf |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-005 SEP Vent Station | Certificate of compliance (COC) | Please upload Certificate of Compliance here when complete (COC)
988e00bf-0210-4f6f-a768-a851716b38ac |  | folder-normal | pass |  | step | TRUE | FALSE | TOP-SEP-E-002 SEP UPS A System
c5d3e186-91e5-4bcb-b35e-9c6724366bc6 |  | folder-normal | pass |  | step | TRUE | FALSE | TOP-SEP-E-002 SEP UPS A System | Electrical Installations
401153d1-525e-4ade-9904-dcf214251b8b |  | checklist-flat | pass | Cable Pre-installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-002 SEP UPS A System | Electrical Installations | Cable Pre-installation
ed71e10f-9cbd-5061-86a8-882c2e244f75 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-SEP-E-002 SEP UPS A System | Electrical Installations | Cable Pre-installation | Cable Pre-Installation
cf9180c2-f069-487d-ac8b-083959131f23 |  | checklist-flat | pass | ITR-CL-1-114 UPS Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-002 SEP UPS A System | Electrical Installations | TH00S030BRA10 - 110VDC UPS A
91a12285-609e-554e-aa06-398e92c953f0 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-SEP-E-002 SEP UPS A System | Electrical Installations | TH00S030BRA10 - 110VDC UPS A | UPS Installation (Mandatory Photo)
f8812fb6-a95d-575f-ad77-e7df106a5241 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-SEP-E-002 SEP UPS A System | Electrical Installations | TH00S030BRA10 - 110VDC UPS A | Test results
31c960f1-870c-4905-83d5-42f7199d343b |  | folder-normal | pass |  | step | TRUE | FALSE | TOP-SEP-E-002 SEP UPS A System | Cables
7b2be45b-0513-46ca-af08-8e60baf65b47 |  | folder-normal | pass |  | step | TRUE | FALSE | TOP-SEP-E-002 SEP UPS A System | Cables | S030BRU10GH010-P01
30e1e0a4-3208-4c22-b3de-df4edafeb9f1 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-002 SEP UPS A System | Cables | S030BRU10GH010-P01 | 4mm2 4C+E CuSn PVC/PVC
e9a8840a-4bea-509a-8e99-49819d3a48b0 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-SEP-E-002 SEP UPS A System | Cables | S030BRU10GH010-P01 | 4mm2 4C+E CuSn PVC/PVC | Low Voltage Cable
280ff0bc-00b2-506e-8a8d-e635d859648c |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-SEP-E-002 SEP UPS A System | Cables | S030BRU10GH010-P01 | 4mm2 4C+E CuSn PVC/PVC | Electrical Checks
64355a96-61ff-5ad9-885e-79e0b8fbbb1a |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-SEP-E-002 SEP UPS A System | Cables | S030BRU10GH010-P01 | 4mm2 4C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
37849b61-b03f-478e-b0ed-1cede11d09ed |  | folder-normal | pass |  | step | TRUE | FALSE | TOP-SEP-E-002 SEP UPS A System | Bonding
1d69e957-357b-40a3-b95a-15450abb4c48 |  | checklist-flat | pass | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-SEP-E-002 SEP UPS A System | Bonding | S030BAW10-E16
19d67f26-a951-5fcf-b9ce-c886be5a8711 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-SEP-E-002 SEP UPS A System | Bonding | S030BAW10-E16 | Electrical earthing system installation
0da75970-9b17-5aa6-a92d-ec65a8fe47e7 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-SEP-E-002 SEP UPS A System | Bonding | S030BAW10-E16 | Test Results
139bdc7a-1250-4ed3-b54a-b39d468cda70 |  | checklist-flat | pass | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP-SEP-E-002 SEP UPS A System | Certificate of compliance (COC)
4d2be892-da4d-5565-a1a3-18da7b813e5a |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-SEP-E-002 SEP UPS A System | Certificate of compliance (COC) | Please upload Certificate of Compliance here when complete (COC)
95b4fed1-db31-45f9-9b6d-8ec408ac28a0 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field
6c9d4086-c432-4d06-8041-7f44e5eb9b0d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Electrical Installations
990fa6c6-e93d-42d8-96e3-d0b1bfb7863e |  | checklist-flat | not-started | Cable Pre-installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Electrical Installations | Cable Pre-installation
bed37460-371e-5390-a275-8d650436dec1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Electrical Installations | Cable Pre-installation | Cable Pre-Installation
ddf06001-f9e2-401e-b15b-d680f109bb2b |  | checklist-flat | not-started | ITR-CL-1-101B Cable Supports Above Ground | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Electrical Installations | ITR-CL-1-101B Cable Supports Above Ground
6b6d892c-07f0-5920-80d7-47b23bfa1784 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Electrical Installations | ITR-CL-1-101B Cable Supports Above Ground | Cable Supports Above Ground
95658f97-4b13-4da4-ac78-4f6d0a077697 |  | checklist-flat | not-started | ITR-CL-1-101A Conduit/Ducting Below Ground | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Electrical Installations | ITR-CL-1-101A Conduit/Ducting Below Ground
da68d34a-8eb2-59de-865e-4b9070cf6d62 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Electrical Installations | ITR-CL-1-101A Conduit/Ducting Below Ground | Conduit/Ducting Installation Below Ground
526bbd34-5e71-4e6c-9f84-6fc4d3265fdf |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Electrical Installations | ITR-CL-1-111 Electrical earthing
47f8a97a-ebb8-5a4d-9e94-f95232a581b8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Electrical Installations | ITR-CL-1-111 Electrical earthing | Electrical earthing system installation
cef731af-a818-58ae-92f1-c5321b824c7d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Electrical Installations | ITR-CL-1-111 Electrical earthing | Test Results
0f99425e-5dd4-4f47-84c4-4bdacbec724d |  | checklist-flat | not-started | ITR-CL-1-106 - Junction Box | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Electrical Installations | ITR-CL-1-106 - Junction Box
8c8719e5-3eaf-5af3-94da-6e70fb7b82d7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Electrical Installations | ITR-CL-1-106 - Junction Box | Junction Box
2642e69a-b3a8-4249-bcbc-7af756c0e850 |  | checklist-flat | not-started | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Electrical Installations | Certificate of Compliance
642b8a49-8c80-54a2-b493-7f91767e614e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Electrical Installations | Certificate of Compliance | Please upload Certificate of Compliance here when complete (COC)
bd260b17-ea88-4fc2-b095-b517e7e48f97 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument
ea31ebf0-62c9-4cb8-8e65-4fb80a2a6f85 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER
60621dcc-3360-409b-b5df-567ff45bbb63 |  | checklist-flat | not-started | ITR-CL-1-130 Pressure Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-130 Pressure Instrument Installation
a4f80397-ac56-5134-9d63-e5a33bd8076e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-130 Pressure Instrument Installation | Pressure Instrument Installation
26564a17-82e6-5113-9314-f6dfe63d7d7f |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-130 Pressure Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
8fd9ecd9-3b72-4614-8362-796229220236 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-122 Instrument Calibration
ee5c8f72-767d-5667-9696-362b8d5aa69e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-122 Instrument Calibration | Required Data
16ef5c46-f12e-5bb4-9cdf-5b1fe0753530 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
02b22de2-2a18-57d9-b346-c89d6be0b03a |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
d0811961-a24b-4dc0-9436-eeb315c140fd |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning
a2931892-16e8-5846-b915-db168afecb81 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
fb12e1a3-e021-591c-93bc-07770aab89bc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
f7945624-0f5f-5380-82c5-82bb2fb46be7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
e12dec6a-0012-546c-a397-1b80dff66c3e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
81e8e075-4e42-5ecd-a298-33ceca9a84ae |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
b0fa688c-3879-53d5-bd7f-9fc4feff6496 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
e2868b1d-2a29-5e89-8386-71e9ec358d94 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
7c4c2e9e-51fd-5d86-bb5f-ea2606576676 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
c4a86833-9819-5e6d-8cfc-c6e499a50b13 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
2e2a5a07-daff-5547-9c38-150baada8c1f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
86ebe01d-488d-569a-bdf1-64cd7c1f8855 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
e747ab49-3e6e-5ea6-a237-3e4460d235b9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
77901b76-0f89-5648-a09c-37cb54cf1edd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
02540db2-63eb-578e-b08b-8cd049ba0fb1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
0d4a7378-23d9-5df8-822b-bb94d3abdd41 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
3e022763-f9a5-5b67-8039-f242b7d9658f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
95b64d54-58bf-59cd-8484-e1c2fdd00b58 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
372ff821-b224-51b7-b48c-d8644cb97e38 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
0a8b84a7-3a19-5095-a87f-73325b676540 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
d0e07791-fe3c-5fd2-af17-a1cd4cbf877a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
6c495ae5-0087-5735-b24e-7b82668d6255 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
c9b9b3f1-5b6c-4450-a1ee-c8cfb4a90882 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments
300c9000-91d1-52e6-a1fe-81d40110fbac |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments | Required Data
44e2595e-ddce-5df8-9a6a-2314cfaa542b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
9830b309-f482-5f5c-be31-99b60e00ac83 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
5bbf0670-500e-56af-9be1-ca757a8fbc13 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
3bb866c7-38fc-512e-a2ff-e5a84c164ca6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
4b4f65bc-1810-5dde-86b6-1b5fa45ae1b6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
431330c2-1ee8-5d2c-a3bd-0a7e8b546c4b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments | Set Point 1
89e3be37-e0cf-5c9b-a008-8751af21de5d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments | Set Point 2
0d367c44-06e8-519f-9dde-300eb9fd5bbe |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments | Set Point 3
44ae862c-1497-56fb-9fdd-1d11e749ef1e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments | Set Point 4
07ea21d5-e542-5efa-92a6-be686d8774a5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments | Calibration settings
282b3e8d-2d08-54da-b499-56e8a27c9711 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030QFB10CP020 - INSTRUMENT AIR PRESSURE TRANSMITTER | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
a6dd8909-10c0-4812-b61d-044ef71c659c |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1
008a6516-ae10-4571-a825-17b30de862af |  | checklist-flat | not-started | ITR-CL-1-130 Pressure Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-130 Pressure Instrument Installation
67e01858-6d9b-5e8e-8000-5d5c3bea5c16 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-130 Pressure Instrument Installation | Pressure Instrument Installation
b76410a3-74d2-5262-a9b4-1e5246868246 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-130 Pressure Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
6cfdb89a-b3da-4c6d-80d4-5ca29c7a1fbb |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-122 Instrument Calibration
1aa8dab8-1047-543d-a2de-4354fdc94be2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-122 Instrument Calibration | Required Data
4382e0ff-98cf-51d3-8635-58d2b51503c5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
61252997-6097-566d-809f-7c0ae697361d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
f746bfd0-1cd7-4508-bd02-c0c6f365590a |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning
fe62c80a-c157-5b89-9221-487d25eb4593 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
6fb51ff8-3afe-5909-a419-3afa850fabed |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
ac8f2413-426c-53c2-9336-e41c4229d75f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
911cfd48-2ea4-5ccc-b113-f38339f7478e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
506a625b-125f-5391-a536-5804d0a18fae |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
2c662c6f-e8fc-5851-aca6-18ac5c9d63ab |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
161b61ae-0ff0-5fcb-b90e-15629baa60e6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
0a9eb12a-0add-5be7-b835-94bf6d3c3746 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
149919c3-8bce-507e-b3ab-1f1e5f8e5aac |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
b693d35b-4bce-53fd-87a3-c0bb39291f18 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
1d914ea6-3b5b-5e9d-a2ee-09bb9578522b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
51f22f82-8dd2-5a34-ad73-d80fabfcd209 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
6bb81c7f-9e96-58c1-8f58-faedc6d72caf |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
caf062ea-ed9d-575b-a6bd-0cd8aef4cbd3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
ffd59319-cd00-5551-81c3-18b17c6afeb5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
7dd077f9-644f-519d-8ca3-7cc2fa6ef44a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
c878bc94-1956-5dfe-8b45-7f7463ec48b2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
ddd58d25-0c29-528d-a59b-ef767a775c16 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
a623ea43-90f9-5d95-9252-3ebcc2cf66f3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
524e0c69-5bb3-5bb2-a061-dc1cadde88d8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
01092351-7b94-521f-a698-5c993f9b9c5d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
16703ba1-8cd2-4355-85a8-fbc7546937ee |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-124 Commissioning Instruments
2991d003-6f89-5629-ac47-021c2da02637 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Required Data
d701de38-669d-5e92-8ab6-41c68013d1d8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
127f9f4d-cbf0-52ee-abba-271368e0fc5a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
f7f41fbe-45a1-5ab8-89d5-278c816bffdb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
441fd619-5223-5d32-a4a9-5417053924bd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
49666a9c-e0f8-561d-affd-741d2c5d8c47 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
aecc0881-9091-5635-ba36-eeae4c5be625 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
435c56de-d100-50f7-a034-24ffe90ff3ba |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
2942ab4a-d395-5fa1-9357-8cea1fd2b684 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
edbb6342-7a8d-54b4-a312-0670b65399d4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
06f78df7-1fa0-5dce-b22c-1d29d4b71134 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
0fd39cbf-78c9-56a0-bf39-62f48795124e |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP021 - Separator Discharge Steam, Pressure Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
389b1539-1a02-42c7-9f81-e1c0181595ed |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2
e06ba065-ba05-403f-be5e-b937f60af30d |  | checklist-flat | not-started | ITR-CL-1-130 Pressure Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-130 Pressure Instrument Installation
fb44c32b-9abb-590d-9b11-17280b8d793f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-130 Pressure Instrument Installation | Pressure Instrument Installation
255f56cb-8676-506b-bf64-d4af9c170fac |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-130 Pressure Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
8917bf42-8796-42eb-93f7-12649731b75c |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-122 Instrument Calibration
db091513-c16c-5c65-8bdb-f79b4e7d132a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-122 Instrument Calibration | Required Data
8ccc13e2-7f91-56fe-b4a2-fb4b3e92c2c1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
4ef4511c-6a13-547a-b381-fc7813f37826 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
9dce56bc-c6a8-4240-8152-b4e675333da6 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning
7ce5b30b-5e5c-50c7-b7dd-8ec7b7a371cf |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
dc8d8606-d13d-50ce-ba42-9614ab985a01 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
5fe96c94-1dc0-5fc0-a1aa-f66d84d36936 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
638c9fe2-504b-5b47-b1a0-661eba8dfba4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
4c2bb12b-046c-5341-b03d-f0107e1949db |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
e81cb730-15ec-51ff-9528-1738e1c84d75 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
5797c0f0-8230-5efd-954a-a1d02c45f5b4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
27fbe55f-e53f-58d2-9831-9bd4baa78535 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
d41e1d02-e39e-5fcf-9ff8-fa1dd329f69e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
53c58d89-5c5e-5e2e-93f8-22bbdb6f436a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
328de36f-0d0c-5a79-a93b-28c962c8e3a5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
a987a35e-649e-5d82-9b1d-e0e9201202f7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
524c25c8-860f-5cdf-9a99-955abdf33f0e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
673bb0a7-b407-5f1e-8b02-36c3ace61014 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
68b8edd3-277d-583c-b786-e2ad55f15034 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
93c8185e-b936-5c8f-8147-5df49462b160 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
5d271d4b-4f76-52b0-ad97-19a2e1e81a3d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
349687b5-49eb-508a-ba20-acdf1ccd77f5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
33f0496e-f13f-5c8a-a1f8-06248725d7dd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
38a90636-f5b8-5751-904b-f367595d2e18 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
0d6390ad-0c62-5ef1-98e2-8e8d55deb11b |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
22a5cd7a-fd56-4175-b1f7-79f66348f6c6 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-124 Commissioning Instruments
c0617133-e568-512d-92bc-b3323e4f05e0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Required Data
1cfb3352-2a54-5289-b583-39572fd1a25e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
4aabf0a8-a07d-53da-a36c-405622ddd356 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
2cc1c6cd-500f-5dc0-b700-6ba1d9eec6d0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
299d5313-eb27-540f-8176-2ef761c5cc44 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
04f5bb99-923f-5448-8d02-47ca6d75b028 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
51e12f93-05fd-5f9a-b1cb-9c32ef848615 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
72f12d12-92e6-5f0a-9a28-df29a349625f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
94a26017-126b-5f34-b108-ef390cafe9b4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
63b222f5-1b4d-5fe2-a57a-cd5568738d3b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
514126e5-58a3-5a58-8045-e0f939f55312 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
49952d90-a30b-55c4-b225-a6fe3f61c8a9 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP022 - Separator Discharge Steam, Pressure Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
0b871013-c484-4307-8ad5-71ebd8e952fa |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3
64b579a4-8bda-4f29-be8e-0569ad7ec90d |  | checklist-flat | not-started | ITR-CL-1-130 Pressure Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-130 Pressure Instrument Installation
54c807bf-0ebd-5055-a713-19cd23f3251c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-130 Pressure Instrument Installation | Pressure Instrument Installation
5ce3f416-ec58-5bd3-9b33-75ef9d2945dd |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-130 Pressure Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
02a8f66f-30a1-4f93-ba9a-9b29b967978e |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-122 Instrument Calibration
7eba8bc0-3af0-5be1-8bbd-29232902769c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-122 Instrument Calibration | Required Data
77b9899c-6d8a-53bb-bd1b-36f3f7805526 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
1595d608-da7b-52c0-b404-b1db6f80ef0b |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
8b078dd5-5c3b-4b6b-bc7d-d6335a8a17ba |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning
df093f6b-0697-59ce-9b89-bfc051ad8e98 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
f6b2a52e-a0b5-5f03-9c99-00132cf2a669 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
c20b22ce-cf08-5125-bf37-29fc873283bc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
5b86b71c-7778-50dd-a2da-944c2410f763 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
8abc8e2c-3ad4-5d14-ba91-277e03b30684 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
47512272-9f85-5692-9960-ffab75ca6ab9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
6a3c09e4-92fd-5f6a-831b-68cad3111b13 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
0393bbfe-1395-5737-b73a-8f360eda0fc5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
2f2bb7d4-ff28-5df3-bbea-d740d14ffa2e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
34a08b87-e20c-5d53-85b4-ea3f3295f4bf |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
8600fd34-c0c4-5ebb-a048-86b58e84c054 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
0206389b-a3f5-5359-a78b-2d374eb7a156 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
15c86c7c-f9b6-59fb-a444-b5a51ee37694 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
a995b3c6-ae17-570e-84c5-6b1650512933 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
6233daf2-de63-5625-88e7-4b9d9335b1f3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
d04b4425-6d57-5314-9d16-667f0399b4d7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
b3c92a01-4714-597c-bf00-9703a002a2f5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
d329c904-18e1-59a2-9843-ffb638f5dc3e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
73771d65-2cdd-5cec-9be4-2e667e05e2fa |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
321d430d-3aba-5d0f-9bad-435e27f961a4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
889f78be-4196-50a7-942a-4d600badac09 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
1ae99e60-882f-4374-9d55-0a6182c0be6e |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-124 Commissioning Instruments
5526c832-9fbb-5c41-88be-f364d1083be7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-124 Commissioning Instruments | Required Data
375fe12d-befb-52cf-8ebc-70caa6f466d0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
2a17aee5-f8ec-52a5-9f8b-f801265a56d7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
36883b4e-2398-511d-9703-08e22d4c3bb3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
f9f4c78f-a47c-5471-bf73-e9cb5aa740b3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
9f04f2e6-07c2-5f13-a24d-25926322aac7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
3fd324b6-3fc0-59bb-a598-99ded5137ba2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
f894877e-1b0a-5d59-a3c7-4dffed72bd31 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
886ab875-bee6-52fa-ba3b-52ca02aaa136 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
54c5b016-c880-5669-992b-18d9a5d0c548 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
75c1d050-6353-52bf-84c6-cd2f9a81985d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
4626ba0c-082d-5ca4-8ff2-434d0b0741e6 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CP023 - Separator Steam Discharge, Pressure Transmitter 3 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
87d43554-99e2-448a-a122-1c68a9ada360 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter
e4706b01-b3ea-4fed-b237-ed032f768569 |  | checklist-flat | not-started | ITR-CL-1-129 Flow Meter Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-129 Flow Meter Installation
3a7e3d2b-3c27-53ca-ba12-5933d90ebba7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-129 Flow Meter Installation | Flow Meter Installation
a0ab5f83-17ae-5ecf-888c-eda37078f09b |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-129 Flow Meter Installation | All relevant signatures (Installed by, Approved by, Client Representative)
e8bea658-0c40-487e-af69-b531ed853ae2 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-122 Instrument Calibration
df73700e-6cf9-58f6-a7c7-6420809390be |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-122 Instrument Calibration | Required Data
5953ba07-1770-514c-8ef7-8c9ebe73ac97 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
b8b7788c-5c3d-50c4-be3e-7663afd9262a |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
4140681d-be1f-4bd7-9c2d-661610b4de75 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning
3f862f5a-03d0-5d8b-a377-e5a26e9f8fa5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
239c3d77-a124-5de2-bf3a-27a9abb9cd9e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
087d5e8a-086f-5018-afa4-11770af0f5bb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
cef65772-d00a-5256-bbad-572efde4ab02 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
b0de6ab0-92aa-5629-87a1-98311b8df354 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
21db1be5-7749-531c-ad62-976bdd74d93c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
1250f5e8-e981-58ae-9c79-1fd69a839402 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
1aae52a4-1fae-557a-9d81-cb9c69f5b608 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
f8683322-a848-54c1-97eb-c7a2d6c5e8ba |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
9255ff8f-0f09-53b7-afeb-ab133974090c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
4633489e-6f60-55d3-840b-c3d90c0a7848 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
9f521821-e4bf-5b8b-b492-096c261681bc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
6342cd83-2380-5e80-8156-fa00b9e99e6d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
9d35bc97-c767-5844-8c21-cb8bbc18e2a4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
cf4c1181-86bb-5c28-ad5f-84ab2885bbe7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
dfc736e2-8272-5d2d-a0e4-bf82b5f20262 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
45142042-ff21-576e-b9c4-e6731e494d83 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
547c8826-396e-5298-8ca5-30ff3dcc7e08 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
fdd56fe3-6d5c-59c8-b317-8a99c5de848c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
207e0425-c89d-5e53-acb7-dfe4b11f5d38 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
3099952c-33e3-51c0-835f-b6f780fbec80 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
652abff6-6c60-40ed-a43b-9978981af577 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-124 Commissioning Instruments
05fdd0b2-0c61-5e50-b272-8ba13e0535c1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Required Data
701f78cf-56d2-59ab-a1a4-836bc0deb3ab |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
ea883ff9-cd0a-5c37-9d02-995827d6621c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
ac86fba9-847c-586f-a075-354506f46ece |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
5d7a3cd4-88ab-5b64-8365-cd53e2b361fd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
27e4caf6-cb6a-53a3-bb1b-0434f1d44172 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
0d77f1d7-9592-5251-890f-8648ea23da73 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 1
7053d303-c73c-5e88-a6c1-84a537be8dfa |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 2
9dd199b6-4ca7-58e4-80f4-754f475d89fb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 3
1d2d6bd5-1a51-5aac-b01f-053123345fd2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 4
e9be4232-b479-5c65-a823-78b747ca7e24 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | Calibration settings
229ec4e0-4449-5361-8fac-96657a805b14 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CF010 - U3 Separator Steam Line, Flow Transmitter | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
278f7ac3-ae73-4322-b6a0-cd284df26465 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter
9609a6c6-94ea-4ad8-b2bd-23789f993af7 |  | checklist-flat | not-started | ITR-CL-1-128 Temperature Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-128 Temperature Instrument Installation
5ebb665a-1ccd-5b69-902f-5e0b028b0a66 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-128 Temperature Instrument Installation | Temperature Instrument Installation
7e46b89d-c094-596a-88b4-5723cba114dc |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-128 Temperature Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
698a04f9-e13e-45d4-b7b6-0604ad2e6e54 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-122 Instrument Calibration
8c7d48da-961b-52a0-a91a-fa65befab3ec |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-122 Instrument Calibration | Required Data
ded54487-d740-5d3e-93de-8b050629b736 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
46c0fb2e-d96c-5030-9568-7dc878c8672f |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
dabbb5c7-ba6a-439d-9290-c35f4678f070 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning
3fd70aa2-61dc-5168-bf95-1762fb6e7015 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
98de2da8-e1c9-5142-a411-ae0a94549150 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
76c21b95-b24b-56d7-8e76-6f166a29e243 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
ada69bdd-3094-5f19-b827-3d9d5dd02a56 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
26d5673d-5f93-5511-9b67-65a1a2bf4f1c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
d20e369b-0eec-5981-a325-3f73b944b734 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
8ba538e5-d5a9-574f-9d02-145531c8eebb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
2b9a12b6-07fc-55a1-bae4-508b0a453b97 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
e6af860d-57cd-5e40-9d51-6335f02c9f12 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
440e3526-3213-58b7-b20c-0ba38e90ddec |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
256a8b02-dff2-5a6f-b8d4-32d335abbe3a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
897daeda-426f-561d-97a9-550b6a408c01 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
4cc2376f-6b7e-5652-8352-e185b9cead49 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
65093f49-d7a7-5662-b103-8b06170d914c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
66e7f919-d8db-527c-9742-cd85862b14dc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
3274d8ed-8ac8-5a20-86e3-6b2da3194121 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
28b5f79f-423d-5d5c-9764-6a7dea5b7074 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
2622b823-5fbd-5791-ae41-3bb40169a176 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
4e6eb032-331d-5660-9d0e-bbfeba53b1d1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
356df42b-007c-5ce2-a8a8-aa15085b531a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
7de6b573-0a0d-52b3-af5f-c118b02daacd |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
c7d030c2-71dc-4efe-9d12-1ddc7477be0a |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments
020e4ef4-d6a3-5bbd-abf1-0a5e8eadec3d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Required Data
f9787149-dfca-5083-9de3-0b83a152543a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
fd12311d-be49-5a9f-adf8-207d7931a702 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
e29d744e-8c8e-5c76-8aa6-51d0598507d4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
28538aa9-c180-539b-a145-39092874149b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
ca5bafd9-c93b-5d95-9374-aef69fbe2074 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
430a0dd2-0453-5814-95c1-c2067eff1b6d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 1
a3f0c1f1-f69b-5f1a-98ef-3f04d314adb3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 2
48c70353-e13c-55c0-94c5-6d222d2c5a44 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 3
e84af7e5-3b25-50d3-b7ce-a9c9e32d32b9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 4
c045a727-1368-5255-86bf-c3558fdee581 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Calibration settings
4aa53589-884f-5665-8494-c3b113e3f7eb |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NAA10CT010 - Separator Steam Discharge, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
f67192bb-8a2a-4706-a33c-504fdfacd329 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1
e075bc69-100c-4803-bb8a-d2eb6643bf49 |  | checklist-flat | not-started | ITR-CL-1-130 Pressure Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-130 Pressure Instrument Installation
79bbdc76-906d-5e1b-ad5f-39be33218b77 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-130 Pressure Instrument Installation | Pressure Instrument Installation
a5f876b2-5b03-5452-aee2-89d49274ab9a |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-130 Pressure Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
230004a8-304a-4df3-aa95-3ea4b789962e |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-122 Instrument Calibration
d1c06616-72d5-5884-a82f-c06b644e28db |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-122 Instrument Calibration | Required Data
22d63c54-c703-5c21-b555-8a480953b525 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
a86df37e-c51c-5bec-b2bc-6cd48060e0f4 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
6024158a-7fbc-46f1-958b-3a911aa5f90f |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-123 Instrument Pre-Commissioning
3be45866-927c-54c3-ae4f-b9ea966558e0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
ece4f4b9-4464-513d-9697-cf4e95fe62c5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
f4c08877-cef5-5798-9b17-96557f7744b6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
95928c63-050a-569e-a061-6f39af63e413 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
c91b6363-edf3-587d-ba7f-bab56135ee2e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
e92f4b10-29e7-5d04-87b8-df66a60b2e93 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
ba342f87-a574-5eb5-9c3f-edcb314b4dcd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
cc8b5ede-5572-54a4-912c-9c818fb301b6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
3cba620d-109a-561f-89e0-becd245e7444 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
73c4b3ef-25e3-51bf-b67c-9b541390af9d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
d9e78990-af9d-5d8c-bb62-91fd428b5831 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
8af52daf-f207-527e-91a9-c7bfa8ee0a65 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
385f5f47-05fb-52ec-af18-d29326cdd10f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
00336835-cf0c-548a-baf5-ea164441719c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
93166bcf-82d3-5b4a-bf1a-014e03fc5448 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
8017079c-f8db-5f52-952c-56e303216268 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
4572a71b-c6c2-5693-9b94-e636f2da85f2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
53ae927a-2857-5737-9e9b-870ca5104549 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
1f00ce16-3a91-54da-a951-0e1fad70b8b1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
d5d43e8b-da18-578f-937e-978c528093ac |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
a840e117-589f-5638-8c60-d8988df88a05 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
371e7a7b-63d3-4fb5-bee0-cb8137c7c540 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-124 Commissioning Instruments
a79ab330-94d5-5591-a764-1c54e5d65454 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-124 Commissioning Instruments | Required Data
edd8e0ae-f44e-539e-ae9e-420dc44cbaba |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
4186bb62-c436-58c2-97ea-c30d98edf2a3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
eae688e8-c1ff-54bf-bd29-cff278cf6d36 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
97a11734-f601-54f5-9dc6-d29bee85f6a1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
730be346-b14b-57da-8d3a-28a0557c8b43 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
b57d8496-cc02-5557-868d-e4a30beddc0c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
c1d7a74f-dd1e-5b42-9fbf-b232f793c447 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
540e0181-dd74-5cbd-9b77-d12fde01c7c5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
519bcb1b-c0f0-533a-b6aa-e02597c95dd0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
f6236bc9-0241-58af-b4da-dab00ca44f14 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
74708996-4064-5654-ad1a-a22cbc9d8523 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL021 - SGW Drum, Level Transmitter, Differential Pressure 1 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
9cc03d2f-aa32-48e1-996a-37a77bbbeef1 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2
9ff53093-0c80-41dc-b20d-f6f85752e97d |  | checklist-flat | not-started | ITR-CL-1-130 Pressure Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-130 Pressure Instrument Installation
433e9f95-cf94-57c9-a38a-7957c83ca51c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-130 Pressure Instrument Installation | Pressure Instrument Installation
2ba50608-721c-5814-8472-530b05d82ad4 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-130 Pressure Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
9eed98e4-1c34-40c3-bc61-fafab2a0adf3 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-122 Instrument Calibration
2febc2f7-c7cb-5e81-ba62-ec10471a388f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-122 Instrument Calibration | Required Data
dfd4c3cd-6e52-583d-b19f-e02015f2cd20 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
3fe4506e-f39e-59f1-aa53-27f9895c5596 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
93584fb3-4da3-4a7e-be7b-37add543954a |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-123 Instrument Pre-Commissioning
be1d5858-0943-50bf-adac-677f78427f8a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
1c8973a2-9220-5fb1-8055-edb3f2935392 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
aba704c2-be08-5aa7-b9d8-de9994c7fdf0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
99db5ac2-6340-5fb3-a4cb-ba9c38f8e990 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
0b48fa22-2026-5e2c-bc73-d659f12af833 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
156c3e1e-1d5a-5027-ac07-53a7889251c2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
9d9c9b7f-ad83-56ea-ba90-200b8cd54946 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
d2db25c3-6ef9-5a04-b4b3-26b30e46fc61 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
69e73246-a8d2-5087-b4dd-e0c5adc4786c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
9fcb076e-6b5d-56a3-9e0f-9f5248c8e723 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
3e7e2dde-4786-59bc-bc68-e52f0a98cc12 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
67f940ea-c94e-54f9-9951-2665b048cd2e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
366849ab-d1a4-56a3-b59a-8642a2d30554 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
f33da0f3-09c0-5975-8efb-b56658e402a6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
595c16db-6f16-5f7b-9637-506cdb96f44b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
a7468f19-0f98-5992-8e39-0bbaf072e3b6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
499eeae0-13be-59ba-b189-cb35b2f60515 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
11336df8-e0d6-5886-8231-27635070dfdb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
623a38cd-2523-5415-bfed-3ae68d2203ee |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
74548003-d0f2-5649-a5b7-f29efcb58e11 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
d90b751d-8632-5730-9d92-a6004fbc5d5e |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
ed6ad5e1-7057-4ff8-82e4-49f48bf97337 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-124 Commissioning Instruments
5679dbb9-5ec8-524a-b5ef-91b54830c951 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-124 Commissioning Instruments | Required Data
f84728d5-ec26-5b2d-87f8-0a67c7d4d851 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
bfd82137-2979-5078-bac2-94ee519db261 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
7697c9b1-96a6-505e-a5b7-4cbd0c3d01b6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
fac5af96-d95a-504c-912e-226e2cdc6ed9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
9c9f1c25-b2ec-59bc-abbd-e9eec8eaec5b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
86164640-bea1-57a0-9586-6b602bc59afc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
49202b8a-f9ff-56dd-9352-6cc5886fb6a6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
86d67825-9bd9-5b9e-815b-ad576910c8c9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
19faa67e-2114-5cd7-918f-77e1e3111760 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
7aff6abd-15d9-5449-9151-2b99306f378f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
e35be91e-1d99-570c-a58e-cb7cb0187453 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL022 - SGW Drum, Level Transmitter, Differential Pressure 2 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
e057a48b-0c65-4fc0-ac1f-9eb6a9cf284f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3
5e2e3f97-7a2f-42af-aeb6-608c176bca85 |  | checklist-flat | not-started | ITR-CL-1-130 Pressure Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-130 Pressure Instrument Installation
2d7d5810-53cb-5567-a7ba-77621065a876 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-130 Pressure Instrument Installation | Pressure Instrument Installation
cebbbd3e-7938-53d4-9e09-211c7dfbabea |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-130 Pressure Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
309f0978-70c5-4d69-a101-c09929ace5d1 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-122 Instrument Calibration
f9e4130f-bed5-5291-9773-bb2b54981882 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-122 Instrument Calibration | Required Data
f3e83ec4-3a43-5ebc-a2c4-250de97dbd1b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
2899f560-266e-5810-b19e-6780401eaa44 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
b5962fd8-2228-49ed-a5f0-ceff68f3a77c |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-123 Instrument Pre-Commissioning
bb7156d5-1336-5d45-b0d4-142e5f3ac244 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
c93584eb-2279-5d6d-ab30-299334d75235 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
99de73e3-cfcb-5313-b802-f60df568045e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
3d3720bb-c9fb-5b51-bd7f-0842aa903991 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
feb1a2a1-b680-5219-a8c1-17f74b93edaa |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
8cbfbf73-d11f-5073-a1fe-e95e45b81824 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
0f16c0a5-ee00-5b24-87ad-f4f84ca4bca3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
f240feba-0942-56d2-b03b-567e27ac22e4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
733d5b90-f30c-5238-b4e7-af05e7f84ea2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
6c4138d9-d27b-57e5-aca0-f5f1ceff3f56 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
bfe1c337-9a7e-52b5-b008-d853b919004a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
bc1e7400-65d5-55d0-b9a7-aab322dec7ea |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
e080d3f2-3743-5799-9970-2bc6b8bc8b1c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
234a8b9d-f8e5-5e4a-9e99-c7c0763f458f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
c5f45d03-2b15-5580-b834-66becece5afe |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
ad982c3e-81d3-5e52-8c89-89a57b770087 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
458d906e-3edc-5067-95af-4a98dcf84e70 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
38cbc1b1-37be-5a60-b0b7-48287104e71e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
d8096932-0e8c-5c73-b4cd-ce2ecc9665b2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
c37636fb-2606-5237-8c09-c186faae76ea |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
4ed7893c-fa56-5ec1-8903-5a4266d595c9 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
89b1c4bb-27fd-4d79-862b-bbc9f318a35f |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-124 Commissioning Instruments
b4d76351-2707-5ee1-a598-d163e99ea681 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-124 Commissioning Instruments | Required Data
f36253ab-1b75-53a5-af03-47269d8edc42 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
2751fd32-d115-5d11-9473-c8c4827efe41 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
0dd7fb6c-6f00-52d1-b0bf-15256a9db246 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
e48f9ab9-fed4-56bd-9a6d-52c1607ab1f6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
3d442de6-80dd-590b-8221-1ee13fff7759 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
6ef7e548-1060-55dd-8379-49da19412863 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
0f723cd1-6e8d-5325-be40-c54060ed5db0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
9959634c-a094-5464-a5ca-e2756051041e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
79f3d0d7-48f2-5a16-b53b-f9b10a551872 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
55bb80bd-0140-55f2-a3b9-4fe53d9b9d5a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
9d4cfbf7-02af-58f7-95d5-1efb06b33337 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL023 - LEVEL TRANSMITTER SGW DRUM DIFFERENTIAL PRESSURE 3 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
0383c903-73ed-460f-8539-35bcce1132c3 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter
6efe3549-8c28-41a6-8674-0bf2f0af8a48 |  | checklist-flat | not-started | ITR-CL-1-131 Level Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-131 Level Instrument Installation
d70adc19-89c9-579b-b87f-e302dae63f49 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-131 Level Instrument Installation | Level Instrument Installation
c23951e4-67cd-51ce-91b0-88272ee1f2bf |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-131 Level Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
9460acf9-5157-4857-9499-7198b45bad11 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-122 Instrument Calibration
d5afe5d0-3305-589b-bf58-b36c729e52d2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-122 Instrument Calibration | Required Data
d164bef2-db54-5966-bfa7-23be4751b4c8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
c5b49dbe-a172-5aff-8859-2ba934e5fcb0 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
9a8647d2-919b-4f14-998a-074596fdacb7 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning
5a9939c9-e71d-5668-858d-1433f4fbcf83 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
021591b1-636e-5f3a-8972-0f1aa8ec95f1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
382c51b1-a977-5a43-856c-7edcfcce102f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
d9597a0c-af90-5c10-a3bd-36e809ebe11d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
085f4f27-89f9-5f5a-b6ef-da44e8ab925a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
e1579f26-e2b0-533c-97b9-a84a9967c052 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
4583f543-aae0-5b4d-a971-798f75422add |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
1b67b015-d8b7-5281-a36e-82739e1e4a2c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
a1eda3eb-9ce5-5cf5-9427-40ac8263e26a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
facdeae3-e996-5edb-a748-5cc2711de52b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
00f5e669-2256-5341-ae3b-6b130490732a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
31b4a3d4-2d7b-500b-b805-039fe1fa5ca0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
c7df9e23-974b-5067-ba0b-e08fb2510c39 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
b7da89b0-257a-555e-8b9a-017784f4b79e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
a12032dd-038f-5f9a-ac11-49016807756f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
4edb8c1c-0dd7-589b-a5fd-1bdfd396c868 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
8b73dc2d-640a-51ed-ba9d-9b74ffd76f51 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
cb93b93e-edac-58c2-86f4-3539474d775e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
2ef3587f-8391-5a16-a116-e07b198a1177 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
c3d50f8e-5b72-54f9-800b-30e7f80a5ff8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
f18d0919-c4a5-5876-8ee3-6d2ee79d447d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
431f0859-7b63-45be-a11d-8f941fe5f091 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-124 Commissioning Instruments
14a4e90f-a14b-520e-aa72-41eca42af989 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Required Data
86d3c02b-e67b-5936-accf-8ae96fa944d2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
cd883079-807b-554d-afb4-6e7da4ed44dd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
44683ea0-d4ed-5456-95f1-b5a3c81ab224 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
a16d7760-c684-5816-8201-c3cffd17043b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
882d2d40-8d9c-5b83-b72f-edb885131faf |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
4d9c6032-d516-5e87-bdb1-fd978cfc8076 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 1
05377fac-b61a-50fd-930f-cba5a8cae430 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 2
3d19c588-d821-5b4b-94f4-ac1c3ffd2df0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 3
4f1fc781-3628-56f4-b51e-88cbf2578d9e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 4
9d2bb8fe-35b4-51fc-8046-e818e733dc58 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | Calibration settings
ddd9ad55-62ba-57c6-b5f8-a3bc6312a4b4 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL024 - SGW Loop Seal, Level Transmitter | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
97351eb3-12da-46b2-ab5f-292633e0cc2d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1
c8837eca-6370-4d3c-a817-b0c2b01440ff |  | checklist-flat | not-started | ITR-CL-1-131 Level Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-131 Level Instrument Installation
1e6bddcd-ef00-503f-ad85-f0b094771507 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-131 Level Instrument Installation | Level Instrument Installation
465c27f3-3df2-521d-bddc-ac95d47fa177 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-131 Level Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
69e1eed1-8bf6-45cf-b3bd-53743d322b2e |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-122 Instrument Calibration
73e8e214-f4a5-5dc3-8f41-35fc3cc33d18 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-122 Instrument Calibration | Required Data
0cf13373-be99-5cd8-8f2b-da52ae2de3f4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
f938589c-5e2a-577c-bfa4-a331114b76ee |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
384d3e1c-9184-448b-9df4-b7190a3cb1c7 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-123 Instrument Pre-Commissioning
967e52dd-f93b-5b70-89c9-7fe94f747ce5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
e9e1be8d-79c8-57f4-8c2c-2490efcb5cba |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
edd906d3-4f86-5304-8965-87c8c42e9eee |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
65cd6537-69c2-54a0-a0f6-d48456471884 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
86dba45e-697f-5b40-8663-9f5af46a13a1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
86b84077-bf21-5bd1-9250-44479c80c44b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
6c5f02bb-037a-58fb-b1c2-1a8882f6613d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
f297dc45-bed8-5a4a-aaf5-b664b24ce008 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
e9ca856c-c208-5349-9005-c82b11680ad2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
c6c3c4b7-776b-536c-8e49-7996aae02fb9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
f4931d0f-7daf-5668-bf3a-ed7297431a2e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
2f10a7cb-5038-54cf-8854-cc8c19537a28 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
58f90d28-7871-5ac8-9bbd-2067b88c6346 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
0840803a-d0af-5784-95ab-8e7686d32939 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
4be469b7-323c-5720-9656-6f529a4e1899 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
4aac95ec-f4e1-5d41-8286-762661fe57fc |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
20719a27-636a-549e-81a7-41719a490d12 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
4d58d4b9-2984-590d-adeb-147bb06f2325 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
757b11fb-fa33-5520-92d7-0387560fb5b8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
a9e0be92-cf44-50cc-a069-6b38c6d68b31 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
9bd76e69-eea2-52ea-be74-78d0f229f961 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
7a3096ee-6826-49cc-a215-d2f0d2d6909b |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-124 Commissioning Instruments
ba979a65-6f4a-50b1-97e4-3fa045628071 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-124 Commissioning Instruments | Required Data
bf1845ed-eef0-5870-82b2-2eb84b9d49b0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
29792a4b-98bf-56be-b5c6-d02d0b0b6039 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
fb8ccd97-8c7b-58e6-abbc-5e894946a69a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
39a8d1c1-17c3-507c-b089-77145b6feb55 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
0adbe70f-0ddf-561f-bb52-52db56065030 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
353097d1-4871-5673-9b36-80d1440153a5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
7ca53b6c-3f07-5c13-9050-0d1b1e4c87f6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
09608f9b-130c-5d12-8042-49b11f59b2df |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
9b848e7a-4fc8-5fbb-ac70-21aed2e41df4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
9dff8246-ff57-5ebd-9f58-3502efd679fe |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
5529bcaf-cb38-5164-af2d-e800f30da4cc |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL011 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 1 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
06123c09-1582-40b3-b844-5557a76aa335 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2
f6e46e34-55b6-42ff-a0ba-8eccabc43dfa |  | checklist-flat | not-started | ITR-CL-1-131 Level Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-131 Level Instrument Installation
531edd9f-b895-5abf-a8c8-005f1d579dbb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-131 Level Instrument Installation | Level Instrument Installation
0959309e-9145-5c49-b7e8-5b2c5d8444f5 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-131 Level Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
abec3402-ec5c-4754-837f-65eb64de519d |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-122 Instrument Calibration
249dbb2f-2144-5ffc-8479-4813265f6992 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-122 Instrument Calibration | Required Data
e14d4c99-105a-5493-bdb0-4af2a59aa249 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
762b5eb7-6363-5186-a463-6450bc3af580 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
4ad54c83-aa46-4d9d-87be-4aaf758da316 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-123 Instrument Pre-Commissioning
0b47fe55-b160-551d-8e97-1d817697273e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
a662a23c-a6b6-53ad-86bc-16deed066582 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
7c9bd883-6c81-5876-95d1-1e6b9a241d69 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
48b1474e-a6a5-59a3-b9b0-79d2b5c0dc6a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
22269761-38ff-5b34-bd78-7916eae031d1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
3f43cde9-a5b6-531f-bf6f-9b8bbe22df3b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
ad079f3b-144b-5c1f-8c77-862da53e57b2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
d4a05d74-3d51-59d2-95f6-4222113ddf49 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
6569cae0-20c5-54ab-941e-7ab83fb02d2c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
c26ec864-7a0b-5246-966c-391a9f8ce3fe |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
11dc36f1-5850-5e42-af38-0ccb2709f743 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
1ca5f0a0-4413-5991-94bb-35a0629e79c4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
86c9a368-8019-5270-90be-a249b1a41aef |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
1ba72f4c-1d39-5242-b2dc-60f4d57b709a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
439c4f1f-4b26-586f-9eef-25d96d7d75b4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
6db9568a-01f8-53bb-a941-e73770c2354d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
2c70906e-c736-5379-9feb-ca934b999eae |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
d07311d2-23b2-5d99-9402-1669bda6df1a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
c771b50c-d1df-5014-8452-53ee8f52349b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
b6605fbb-2acb-56dd-879b-bba581aeee5d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
3a63e97f-d5e5-52ca-8bb9-0e4031349a1d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
71b6ad6e-f883-47e9-8099-96fbad051ba5 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-124 Commissioning Instruments
55b7e6bf-22e2-58d7-b9f5-d1ce2c0910c5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-124 Commissioning Instruments | Required Data
94d5c26b-e31c-54c1-8857-8500b312a01a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
e5ee5838-c3e3-5785-9a32-0593e8c0cf9f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
c60a498d-9af8-57ac-930b-27556f03b11f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
22279476-a85e-555a-9f69-f518b17c5b3b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
86a28758-d207-52af-bc00-db8c84188d13 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
74175b34-8c12-5d4b-8707-72eaa7e82f0a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
faa0a6d8-633b-5257-89dd-6877ce3d3f70 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
8828c8e0-890c-5ad5-b6f5-cd39503a7e77 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
d4c2bf9d-8972-5aae-a653-7bfa846a48f4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
79246b32-dbf3-505b-90a0-1ff7a0647ce0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
8d5e511e-59d8-59f3-8444-8e419dd6ef55 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL012 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 2 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
709db61f-6d79-4ca7-8669-99d89028d714 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3
53d3be29-5339-4062-aeaa-fd9ad2baf8ff |  | checklist-flat | not-started | ITR-CL-1-131 Level Instrument Installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-131 Level Instrument Installation
6b14932a-a814-56a9-9e36-113d334ee1ef |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-131 Level Instrument Installation | Level Instrument Installation
0b457d67-6cb1-58f0-8099-6f2a688787f9 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-131 Level Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
7e2c9791-fd6c-4d4e-acb5-32e41a52753e |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-122 Instrument Calibration
3cf4765b-9c92-5ead-9f72-3c5f1201d54a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-122 Instrument Calibration | Required Data
53a17713-a1fe-5430-8e1b-2c4cf8cf5d03 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
644a39e5-afdb-5a07-9679-e5fd21c76aaa |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
848370ce-e61d-417e-8662-3ba06741e69b |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-123 Instrument Pre-Commissioning
87a30998-4b14-5433-9e65-324db380e93b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
6a9f87fa-4f2c-50d7-a0c2-acc477655b73 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
cc9082ff-d03d-5735-bbb5-c453466eb5b1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
0eef66f3-5240-53ec-a872-0fa3c6feb22d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
e8e7f258-8811-5336-a372-6615580f4274 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
79e33d7f-a57f-567f-ac6b-50108584c973 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
2162e225-41bc-5f58-bb1e-3a462b11da17 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
f98d4552-26f2-5c33-99e6-738582ce7115 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
de24d1f1-04d8-537e-99aa-147da9c7b3f0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
7a5529c8-015c-591a-8675-f83d944ff2d2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
400c8fca-65b6-569f-840c-9a1dc8f11c6d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
3fda390f-5303-5503-b96c-aee6e921fb63 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
e0bc6b24-4711-569a-bcf1-513efbebec05 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
dcdc0825-5893-5348-99d7-783a1c49ccfd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
414ddd88-e42a-5a49-adec-ad91e7ed8891 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
7b8a4224-0c1f-5344-a2f1-7f20bc1a96f4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
7676b5ab-ffc7-51bd-9713-8d6b4ed21e17 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
5c5ae7b7-475f-5302-940c-eca43668aad6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
1fd120d8-a045-5fbe-9f01-f80a2f8f2d36 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
bd537b1d-9937-559a-ae71-f77daf120441 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
b2238d61-d34f-5c98-a3e7-c6f199f4c363 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
74729a62-35e7-4d9e-92c4-a5b62bb415fb |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-124 Commissioning Instruments
fec294da-7b11-5d5b-b46e-a7d49b528d17 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-124 Commissioning Instruments | Required Data
404b1533-e9fb-528b-acf4-8451fc464887 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
349e7346-26e2-5837-9cff-6cab5839984d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
7c9354f6-838c-552e-a08b-8dcfd334cdee |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
4d3f42d8-09f0-5ec1-ae1e-b06cc894b369 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
2753b711-b3b1-516d-89fc-1b4e5e72ea96 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
7bc1de91-b38f-547b-a6b7-fa95cf37cae3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
f08be3ec-ddb4-5841-8460-f49bd79a0671 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
e5b0244b-4ad5-5ade-8e69-1173d6f9c645 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
ed56cd42-26d0-590b-a045-c7a3ee551b2b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
8f09c14d-f18f-5faa-a8ad-b0219fa3724c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
e484dce3-586e-573e-97cf-5e46de7cfbf9 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Instrument | TH00S030NDA10CL013 - SIS LEVEL TRANSMITTER SGW DRUM RADAR 3 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
73c4502a-481e-4c55-987d-3e64a151e551 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables
e4f2fea5-4e69-4501-b7c8-6418db73f283 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030QFB10CP020-A01
cd76b172-39cd-446e-af05-b051724f0ff6 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030QFB10CP020-A01 | 1.5mm2 1Pr CuSn CS
d14e5e91-0df8-5701-8da2-9fb30e00dfd5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030QFB10CP020-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
2535d5cd-ff39-5bf9-878e-3f0f0d1c18df |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030QFB10CP020-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
9344249d-06a4-436d-8ee0-6952c4b5ccae |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | Junction Box 02
f54a8725-ec9d-4203-82fa-914693682546 |  | checklist-flat | not-started | ITR-CL-1-106 - Junction Box | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | Junction Box 02 | Junction Box 02
e3b40f2e-99b7-5154-9133-06aa11613052 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | Junction Box 02 | Junction Box 02 | Junction Box
1156a77f-68f8-4153-98ca-112a35419bc5 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030BHX10GY102-A01
6b0e241c-9f00-4a90-a203-4c78d3b74cea |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030BHX10GY102-A01 | 1.5mm2 12Pr CuSn ESCS
11cd6ed3-2944-5a47-a3da-7a5da31ce724 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030BHX10GY102-A01 | 1.5mm2 12Pr CuSn ESCS | Instrument Cable
5d62d52b-fba4-55bf-89b0-35e2b8b240d9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030BHX10GY102-A01 | 1.5mm2 12Pr CuSn ESCS | Electrical Checks
79caf54b-3241-4e3f-96ff-44af92efb1b2 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NAA10CP021-A01
6f2fa370-610d-493c-bedd-bcdb34bb730e |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NAA10CP021-A01 | 1.5mm2 1Pr CuSn CS
a6740bd7-1595-50be-a342-0926e500db54 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NAA10CP021-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
57a225b6-026a-5386-a8c8-ffd8aa9b440b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NAA10CP021-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
25f24a3c-8f69-499a-9741-1624e6bba49e |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NAA10CP022-A01
8d1dc6e0-c3e5-49cf-a3a9-c408cf1f41d3 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NAA10CP022-A01 | 1.5mm2 1Pr CuSn CS
b68a89aa-34db-585f-bb1d-d4e706e6a1f6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NAA10CP022-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
0fe2fcf4-0957-5e0e-bae3-17b7b1693235 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NAA10CP022-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
016ad1c9-3f31-4167-aa0d-f5a301aa6c00 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NAA10CP023-A01
5e33fe06-db00-4f13-837a-ee19255f97fc |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NAA10CP023-A01 | 1.5mm2 1Pr CuSn CS
a5f09139-5e60-5fdc-80e4-3f95e5de2937 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NAA10CP023-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
2b6e2ffd-dfa2-5874-8b23-ef5295216d84 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NAA10CP023-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
0489b6f8-b4ea-4a2d-a058-2f3258bdd03d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NAA10CF010-A01
cc5c82e9-ca21-4ecd-8419-cca714633d04 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NAA10CF010-A01 | 1.5mm2 1Pr CuSn CS
1eedd229-7e01-5e66-9c69-fc954b80c8f7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NAA10CF010-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
6f43086c-7e7f-5e8d-9332-2ada88df3a26 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NAA10CF010-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
91bdcd12-dbb5-4366-9d35-b1636f108450 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NAA10CT010-A01
ea1e71c7-db6c-4f16-8ad6-4a08b24b1228 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NAA10CT010-A01 | 1.5mm2 1Pr CuSn CS
2d6fd3b9-9b9b-5e60-abc1-e5101e10a1e7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NAA10CT010-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
0d6613ad-4e51-5ec5-9c5a-11ba43ad48ad |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NAA10CT010-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
5b19fd0e-87f5-4bc6-95dc-ac9d599a827e |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL021-A01
1b982bdf-503d-4c3f-b362-527b9f053632 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL021-A01 | 1.5mm2 1Pr CuSn CS
a6578c2c-9d11-552a-aa9d-8dabcd574652 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL021-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
d4ff3a86-597a-5fc4-9c4b-bd7089a2e022 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL021-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
1975a226-73f8-465e-88c2-6c90e2ee8ff9 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL022-A01
d2b92ffe-18ba-422a-9f49-3a05498dea5d |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL022-A01 | 1.5mm2 1Pr CuSn CS
169f43b6-2be1-5268-9fcb-401a718b9513 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL022-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
22c01786-b826-5ee2-8301-64471546ed52 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL022-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
0c7fab9f-982a-4888-8555-e3f3013a14ad |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL023-A01
99f2875b-7956-42d6-80b2-47c908c4d36c |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL023-A01 | 1.5mm2 1Pr CuSn CS
ec490ad6-1f2a-55a1-9b09-1f2d3bfc667e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL023-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
b2d7a1f3-514f-5fe7-a4f3-8f3335654387 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL023-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
9254360b-36ce-4643-bcae-cbe59694e76d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL024-A01
4b96cab4-db99-4808-a9c9-4cf76a172da6 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL024-A01 | 1.5mm2 1Pr CuSn CS
68981b47-27d2-5384-b88f-729f9489ce90 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL024-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
b2235361-3cb8-5181-9a4e-13d0adc3ee72 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL024-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
5b762b12-8913-445c-8436-6ef610b9e619 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00L040NDA10AA010-P01
f35573a7-84b5-45aa-8a3a-a8e46317983a |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00L040NDA10AA010-P01 | 35mm2 3C+E CuSn XLPE/PVC
d02251b1-26f1-5b05-add8-4efba0cefc68 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00L040NDA10AA010-P01 | 35mm2 3C+E CuSn XLPE/PVC | Low Voltage Cable
fcc682b0-6bea-51b9-a2db-4be14ea47a58 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00L040NDA10AA010-P01 | 35mm2 3C+E CuSn XLPE/PVC | Electrical Checks
f878a1bc-220f-5b42-8462-278200eeb74e |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00L040NDA10AA010-P01 | 35mm2 3C+E CuSn XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
b7347d23-77df-4163-90cc-f788d87a2bfa |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00L040NDA10AA040-P01
4f341263-e38e-441a-b484-0389e7248b5d |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00L040NDA10AA040-P01 | 16mm2 3C+E CuSn XLPE/PVC
5f592d3d-e9e7-5873-92ec-19e408097075 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00L040NDA10AA040-P01 | 16mm2 3C+E CuSn XLPE/PVC | Low Voltage Cable
11ba4cc0-dbdb-5d24-bc0f-d728e1c6aa2e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00L040NDA10AA040-P01 | 16mm2 3C+E CuSn XLPE/PVC | Electrical Checks
b445db1a-d603-5747-9f86-1cc299d970b9 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00L040NDA10AA040-P01 | 16mm2 3C+E CuSn XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
55c5aedf-2fc2-4406-9b33-f181834f320d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10AA420-P01
75adb1a4-c6ab-47bf-9ae7-3ff7277a6362 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10AA420-P01 | 16mm2 3C+E CuSn XLPE/PVC
6705925d-a612-5b15-9ec9-59cce06fb6d0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10AA420-P01 | 16mm2 3C+E CuSn XLPE/PVC | Low Voltage Cable
fee6c417-8b55-58a9-848f-ee9e15806b93 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10AA420-P01 | 16mm2 3C+E CuSn XLPE/PVC | Electrical Checks
24d60366-721f-59af-b4fd-74b99931a2b7 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10AA420-P01 | 16mm2 3C+E CuSn XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
c9ebde8e-01bb-48d9-8b90-11bbc5a9e960 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030LFC10AA010-P01
b0129b64-cbb3-4883-9464-7d3121373982 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030LFC10AA010-P01 | 16mm2 3C+E CuSn XLPE/PVC
16114150-4dc7-5200-970a-a4b3064b6e5c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030LFC10AA010-P01 | 16mm2 3C+E CuSn XLPE/PVC | Low Voltage Cable
b36264d9-7e8c-59da-9247-c8eca4e06311 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030LFC10AA010-P01 | 16mm2 3C+E CuSn XLPE/PVC | Electrical Checks
5ed9bde7-12c1-51a0-99b0-c963bea59272 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030LFC10AA010-P01 | 16mm2 3C+E CuSn XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
c4d44144-6ad9-4db6-b793-3531f8c3389a |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA20AA002-P01
7d5ff68c-5d08-4ef3-b12e-643b04646285 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA20AA002-P01 | 16mm2 3C+E CuSn XLPE/PVC
0edf5cad-9354-54c4-8164-9536bf49eff0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA20AA002-P01 | 16mm2 3C+E CuSn XLPE/PVC | Low Voltage Cable
5469abaf-8e11-58db-9a6a-6b723ed333ea |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA20AA002-P01 | 16mm2 3C+E CuSn XLPE/PVC | Electrical Checks
118566de-8508-585a-8924-b7d400246230 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA20AA002-P01 | 16mm2 3C+E CuSn XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
e9498c5e-838d-4827-8821-84a6a0c64ad9 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00L040NDA10AA010-S01
b3f21c9f-5687-4840-af1f-a81d6a1759f9 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00L040NDA10AA010-S01 | Profibus DP - Grey Sheath
cd8449dc-f43c-56ef-aea8-3c388f89a443 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00L040NDA10AA010-S01 | Profibus DP - Grey Sheath | Instrument Cable
c4558731-ff29-5f88-8e76-67df952e0db1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00L040NDA10AA010-S01 | Profibus DP - Grey Sheath | Electrical Checks
50893097-3fb0-4f8c-93d4-6a4d5ce0c21b |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00L040NDA10AA040-S01
3a57744f-337b-4412-92af-d73aec8965b6 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00L040NDA10AA040-S01 | Profibus DP - Grey Sheath
af8b70e0-a978-5899-96fb-d6d1dc7383be |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00L040NDA10AA040-S01 | Profibus DP - Grey Sheath | Instrument Cable
8ed0c367-89c4-548c-9135-09c50f107ca7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00L040NDA10AA040-S01 | Profibus DP - Grey Sheath | Electrical Checks
506fffa6-799a-4f35-b3cf-a561e579b106 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA01AA420-S01
977b9cbf-93c1-422f-ab4f-494d4b53ff19 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA01AA420-S01 | Profibus DP - Grey Sheath
7fb6f0d9-50dd-52e0-91f3-5c260b0dba9a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA01AA420-S01 | Profibus DP - Grey Sheath | Instrument Cable
e1e715b8-af39-57ae-ab93-45b4aff53c78 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA01AA420-S01 | Profibus DP - Grey Sheath | Electrical Checks
9fb223cd-8edb-4224-b5b9-117cbd20a155 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030LFC10AA010-S01
22f7e996-6e39-4ee6-a4ee-ce5b9e1786c5 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030LFC10AA010-S01 | Profibus DP - Grey Sheath
48652c7b-4660-5cde-b99b-eed6e08d9642 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030LFC10AA010-S01 | Profibus DP - Grey Sheath | Instrument Cable
b6cfc839-4288-5b2e-9969-ea4c3cde33f2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030LFC10AA010-S01 | Profibus DP - Grey Sheath | Electrical Checks
ee0cae06-b0c9-423f-aea5-37c185021521 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA20AA002-S01
c237cbaf-7517-453d-b5c4-93d426105610 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA20AA002-S01 | Profibus DP - Grey Sheath
fce0317a-3298-5f70-9dc4-a929292464c4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA20AA002-S01 | Profibus DP - Grey Sheath | Instrument Cable
0d65919e-3b9d-5203-a072-773dcd9c26fe |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA20AA002-S01 | Profibus DP - Grey Sheath | Electrical Checks
562ad1a6-eaa6-4157-8f53-6940ea60ed34 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL011-A01
f3b69d9d-a387-40f1-9353-7c59250f5436 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL011-A01 | 1.5mm2 1Pr CuSn CS
07d7b349-e640-5d8d-907a-bcdb2e196f72 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL011-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
369932a4-f2c8-51e4-b6c1-f4db4f4537a1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL011-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
c1824f7d-e072-40d5-8a18-69dc9e21c92a |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL012-A01
81aff855-d968-401e-a61d-fa37fdf2614b |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL012-A01 | 1.5mm2 1Pr CuSn CS
e4316fc7-f582-52a4-b44a-1979fe54f93b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL012-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
ad54b277-8293-5539-8122-b81d9dcc7510 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL012-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
ce85883d-b672-44e0-891c-a4ec8379e420 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL013-A01
9a914f55-2f7c-4629-ad30-62d7211a3196 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL013-A01 | 1.5mm2 1Pr CuSn CS
432eca9d-7bc2-57a1-a5b1-d0255243f0bd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL013-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
ed789a78-5fe7-52e4-a423-ac3bd113a1b3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Cables | TH00S030NDA10CL013-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
ff473192-9c0a-4c5f-a55e-5879c95b41c9 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Earthing
0daa811a-3dca-4159-b4d5-2bebc344d71d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Earthing | TH00S030BHX10GY102-E01
76bea8bc-17c8-440a-96e2-7b656e1e02a1 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Earthing | TH00S030BHX10GY102-E01 | 120mm2 1C Cu PVC/PVC GE/YE
87ee2546-33d2-5b23-bbf1-a70447b72895 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Earthing | TH00S030BHX10GY102-E01 | 120mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
4a328cf4-5efa-5be8-af80-f9fa1c50bd65 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Earthing | TH00S030BHX10GY102-E01 | 120mm2 1C Cu PVC/PVC GE/YE | Test Results
11c0c469-3c68-4e3a-bad6-a116d213f047 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Earthing | TH00S030BHX10GY103-E01
88ae7aea-b94f-4a95-bc51-7035782ef2b2 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Earthing | TH00S030BHX10GY103-E01 | 120mm2 1C Cu PVC/PVC GE/YE
6b6557fe-80f9-5b91-8fe1-c7c93de5273b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Earthing | TH00S030BHX10GY103-E01 | 120mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
0d0d4a55-572a-5f09-88c2-7db5e8cd2f5f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Earthing | TH00S030BHX10GY103-E01 | 120mm2 1C Cu PVC/PVC GE/YE | Test Results
d1f120fe-dd17-4d0b-b2ad-85a6261241b8 |  | checklist-flat | not-started | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP-SEP-E-004 SEP Seperation Field | Certificate of compliance (COC)
3a11d38d-d86e-56a8-9789-d2f37f86703d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-004 SEP Seperation Field | Certificate of compliance (COC) | Please upload Certificate of Compliance here when complete (COC)
f240a705-3340-4cb3-8abf-ec4b9a9cc0d4 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms
f26d82b8-ec6e-4bf7-a273-fbb0efaa1f0b |  | folder-normal | pass |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Electrical Installations
7bea1cb7-6af0-47cf-ab38-6a29db8defaf |  | checklist-flat | pass | Cable Pre-installation | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Electrical Installations | Cable Pre-installation
08629e79-9c85-5af3-8611-49ae20e5cb6c |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Electrical Installations | Cable Pre-installation | Cable Pre-Installation
d5d169e6-a331-4a06-8e75-d8d4b313eb2d |  | checklist-flat | pass | ITR-CL-1-109 Electrical Equipment Package | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Electrical Installations | ITR-CL-1-109 Electrical Equipment Package
8e1de9e9-0448-5ad9-a8c1-2037ed09ae6e |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Electrical Installations | ITR-CL-1-109 Electrical Equipment Package | Electrical Equipment Package
a882ce35-1742-4848-86bd-692be8e6bdaa |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables
44a6a3b4-db1c-4fa9-b4d6-ec7399fa3dc1 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH000000BJB10GS010_-F01-C01
24d37b03-d2ac-4e32-a43c-831d856338dc |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH000000BJB10GS010_-F01-C01 | 1.5mm2 12C CuSn PVC/PVC
3f2e7e92-5086-52dc-aac4-2feb4d90cbce |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH000000BJB10GS010_-F01-C01 | 1.5mm2 12C CuSn PVC/PVC | Instrument Cable
9d3e0d44-c05c-552c-95fd-c987712deb82 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH000000BJB10GS010_-F01-C01 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
fcedae50-55df-489a-a79a-768a3cd5b7da |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH000000BJB10GS010_-F05-C01
09e798f3-a62c-4bec-8528-89ca2ed173aa |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH000000BJB10GS010_-F05-C01 | 1.5mm2 12C CuSn PVC/PVC
a2f9a1fc-42bb-57af-b364-6b6359f39be8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH000000BJB10GS010_-F05-C01 | 1.5mm2 12C CuSn PVC/PVC | Instrument Cable
dbd2907e-35ff-5437-92a6-299e523486f9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH000000BJB10GS010_-F05-C01 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
cccd268e-91ae-4b74-991e-56042880da96 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB10GS010_-F01-C01
610277fe-5298-45ae-a3ed-238e5439931c |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB10GS010_-F01-C01 | 1.5mm2 12C CuSn PVC/PVC
49176f5f-0ddf-53ef-a782-e1dadb225dfb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB10GS010_-F01-C01 | 1.5mm2 12C CuSn PVC/PVC | Instrument Cable
d38d55e5-9ed1-599a-a38d-dd534a1e7878 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB10GS010_-F01-C01 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
82fe6e09-a30b-49e2-87cc-a202386b62a9 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB10GS010_-F05-C01
a753d047-a1fc-4aeb-842e-b41ecb4ba7bf |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB10GS010_-F05-C01 | 1.5mm2 12C CuSn PVC/PVC
1f095e0e-da91-52d5-87e4-c567e90bc8b1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB10GS010_-F05-C01 | 1.5mm2 12C CuSn PVC/PVC | Instrument Cable
c6f92728-4b90-5844-b807-3442e588d252 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB10GS010_-F05-C01 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
9050752a-e538-4d8f-8f2f-a879031aec03 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB10GS010_-F01-P01
06f9fc68-518c-4c11-8517-807365f62a3e |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB10GS010_-F01-P01 | 1.5mm2 2C CuSn PVC/PVC
9d569293-f4e0-51e3-852e-74b0ca45bc6e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB10GS010_-F01-P01 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
98980ce9-ed4d-5016-ab80-a09d235cf6e1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB10GS010_-F01-P01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
c3b7b55c-ba1e-4443-afe5-2e5a2a6393c9 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB10GS010_-F05-P01
aa3bcd95-ee45-4f9b-be79-f8d916e15b60 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB10GS010_-F05-P01 | 1.5mm2 2C CuSn PVC/PVC
d66c39ef-31ac-5855-9376-78088b3546c6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB10GS010_-F05-P01 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
30425cc2-1491-5cbb-8bd3-0b913f1a2774 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB10GS010_-F05-P01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
2db74652-723c-4742-893c-86bb0746e73f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB10GS010-C01
8f562ede-fac1-43f5-9c65-279fa1eea5aa |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB10GS010-C01 | 1.5mm2 2C CuSn PVC/PVC
4023335e-7732-5e21-88dd-8c7b3eeaad4d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB10GS010-C01 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
4fba3485-0a55-5fba-a279-bf7da394674f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB10GS010-C01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
f1c5123a-13b3-40a6-8773-616d79bc0fec |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB10GS010-C02
10525415-d582-4e70-b75c-6dd116929f6a |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB10GS010-C02 | 1.5mm2 2C CuSn PVC/PVC
1a78439c-df07-54aa-86fc-3807d0014b94 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB10GS010-C02 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
320a4cf0-eefd-5452-8faf-46a7cd2f7677 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB10GS010-C02 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
0b1e3077-a818-4731-b718-f66de36e25a7 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CFX10CT010-C01
fd13a521-45b0-4e0b-bb33-155ecd598c32 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CFX10CT010-C01 | 1.5mm2 1Pr CuSn CS
3d33dd65-e221-52e1-88b0-3df9f58fb454 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CFX10CT010-C01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
5d7762ec-97f9-56a2-ab4b-1ca24d3e3e34 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CFX10CT010-C01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
ee02ccde-1b6f-492e-bbc9-7b9457ac0145 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030SGY10EH010-C01
7fd746c4-596b-445d-98f7-9393f45839e9 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030SGY10EH010-C01 | 1.5mm2 2C CuSn PVC/PVC
4c030191-0bf1-5054-a6db-abd4c8beecdf |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030SGY10EH010-C01 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
042cfc31-135b-5896-958c-5f5d3c982bad |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030SGY10EH010-C01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
22d58976-da07-47b0-889f-dad90262199a |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB30GS010_-F06-C01
525b6e2a-970f-4fc5-a324-0256eb7fcade |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB30GS010_-F06-C01 | 1.5mm2 12C CuSn PVC/PVC
009eb949-7e07-5248-a864-5e7917903eec |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB30GS010_-F06-C01 | 1.5mm2 12C CuSn PVC/PVC | Instrument Cable
bd3563b9-a3c9-507b-99f8-b4b61d27fd2f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB30GS010_-F06-C01 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
4e6c4e5b-e734-4c6c-b8ac-c21ba8ff78be |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CYP10EM010_QH01
76b5b4fd-e939-425a-9c21-9fda386d6d5a |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CYP10EM010_QH01 | 1.5mm2 4C CuSn PVC/PVC
c93e3594-112a-5a85-97f6-664f1c41a26b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CYP10EM010_QH01 | 1.5mm2 4C CuSn PVC/PVC | Instrument Cable
40ef3585-374b-5e70-b0ff-6fb6089c79c5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CYP10EM010_QH01 | 1.5mm2 4C CuSn PVC/PVC | Electrical Checks
ced9b2b5-3400-495b-aae0-4c8f9c3e9d8c |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10EU101-A01
5aae6d83-1cea-4ee7-9215-450217c1d91e |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10EU101-A01 | 1.5mm2 1Pr CuSn CS
72f9ce8d-74fc-5d88-bfe5-5b6d335a3102 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10EU101-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
26cc0017-810a-5dbd-a2d6-2a501535fdec |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10EU101-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
d4b90187-6b10-47b2-a034-d11bd5081b7f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10GW011-P01
3fc03ee0-d3d8-48b4-bd6d-5f8dd6a356af |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10GW011-P01 | 4mm2 2C+E CuSn PVC/PVC
61d8e591-ca88-55ef-a882-0ae8f120ebff |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10GW011-P01 | 4mm2 2C+E CuSn PVC/PVC | Low Voltage Cable
d25d3176-c1b6-5a60-9ed4-2bb6634c4d6f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10GW011-P01 | 4mm2 2C+E CuSn PVC/PVC | Electrical Checks
bc5467ac-7b00-51b2-a91c-536b2ff0ffc0 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10GW011-P01 | 4mm2 2C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
393d2354-b950-4561-8952-6e4251bd5ed3 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10GW011-C01
c8204a3e-0253-4bc6-a421-bd202a721b93 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10GW011-C01 | 1.5mm2 2C CuSn PVC/PVC
7d51e192-1b2e-5e4e-be6f-ceaa26cee1ae |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10GW011-C01 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
e230a64a-cb6e-568a-9343-1ba8191cdb94 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10GW011-C01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
d312451b-358a-4ecb-8f8a-7685c62fe15e |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10GW021-P01
369ea3f7-5911-463e-ab57-0e0137990345 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10GW021-P01 | 4mm2 2C+E CuSn PVC/PVC
0512deab-f6e3-5964-b062-9a5864ed6d06 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10GW021-P01 | 4mm2 2C+E CuSn PVC/PVC | Low Voltage Cable
dd2765a6-3feb-5b0f-835a-6a385951729b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10GW021-P01 | 4mm2 2C+E CuSn PVC/PVC | Electrical Checks
5a0b2e98-2bc0-565b-873a-189d0ea838bb |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10GW021-P01 | 4mm2 2C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
5101fcaf-242c-41a9-9e91-c7cc74953b04 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | S030BAW10-E06
cfb72645-0aa1-4f7c-be9f-14d436b0df6f |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | S030BAW10-E06 | 70mm2 1C Cu PVC/PVC GE/YE
0762e4c8-1a95-5d31-a082-e6ada6d2fe66 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | S030BAW10-E06 | 70mm2 1C Cu PVC/PVC GE/YE | Fibre Optic Cable
92090cb7-740a-4ddf-9e48-87edc5fffedd |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10GW021-C01
3f056f3e-afd7-453e-818f-d94fc28e49f4 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10GW021-C01 | 1.5mm2 2C CuSn PVC/PVC
2d5c650f-9b06-51f2-bdc1-27aee6143c45 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10GW021-C01 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
f07471a1-473f-5c9f-a4e8-2e0806cdd1a2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10GW021-C01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
35a62be3-0f62-4b86-97ab-4b9d37a2552c |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | S030BAW10-E07
636007ca-da16-4ec0-b18f-014e5e98bc39 |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | S030BAW10-E07 | 70mm2 1C Cu PVC/PVC GE/YE
b80d2a94-40ff-5027-9154-864147418084 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | S030BAW10-E07 | 70mm2 1C Cu PVC/PVC GE/YE | Fibre Optic Cable
069179ea-ad90-4588-a5bb-fc4adfc95e0d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10CL011-A01
43e51b39-85f1-45e3-8ca7-23b99dc58eb9 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10CL011-A01 | 1.5mm2 1Pr CuSn CS
4d22897d-ac18-5137-a5c3-ca19e1d878be |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10CL011-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
fdd1b8c5-33bb-5758-9844-35a20d5b30fc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10CL011-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
625c2cbe-26f3-47b0-b0ef-3624f43fd92b |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | S030BAW10-E011
1e08e0ba-a928-475a-af40-7e508cb5ffa3 |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | S030BAW10-E011 | 70mm2 1C Cu PVC/PVC GE/YE
17281dbf-dfe1-51e3-861b-b3bfbb2244da |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | S030BAW10-E011 | 70mm2 1C Cu PVC/PVC GE/YE | Fibre Optic Cable
426cc6c7-6831-4629-9c94-9aea1a126e68 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10CL011-C01
b5cfb479-b0fc-4ece-9397-bf9ca74057b9 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10CL011-C01 | 1.5mm2 12C CuSn PVC/PVC
ba3da424-3e20-5342-a6d5-447f59c9241d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10CL011-C01 | 1.5mm2 12C CuSn PVC/PVC | Instrument Cable
002e98f4-25a8-5a10-922c-ad5c9c8d8b74 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10CL011-C01 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
3c43ce92-fd14-45ed-92f2-64bbf34552ac |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | S030BAW10-E14
3ff1a405-a701-42ed-8a72-af7077f797c3 |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | S030BAW10-E14 | 70mm2 1C Cu PVC/PVC GE/YE
20ff5a55-4167-518f-8e19-0595f12bf425 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | S030BAW10-E14 | 70mm2 1C Cu PVC/PVC GE/YE | Fibre Optic Cable
ea3cc211-a6d1-4b25-9016-ee1c41e50ce5 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10CL012-A01
da2b82a7-fd53-44d6-8642-5c410a60c415 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10CL012-A01 | 1.5mm2 1Pr CuSn CS
f3908620-6f30-55bc-89e8-18e3128d1b94 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10CL012-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
1bb5e645-77e8-5ad6-b08b-40c3b23bc234 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10CL012-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
21a6dc2d-6100-4c2f-bbba-e0a73571edee |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10CL012-C01
e88d1090-5cea-43e1-bf32-78c262f15618 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10CL012-C01 | 1.5mm2 12C CuSn PVC/PVC
d39609ad-f88a-557e-9165-34ead37f2d0c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10CL012-C01 | 1.5mm2 12C CuSn PVC/PVC | Instrument Cable
e92f3066-c344-5197-a7cd-c1fbd68b5ed9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10CL012-C01 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
de9f49d2-20a3-47f9-b955-70a7f25fdede |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10CL013-A01
4772ca30-d349-44a1-a4ef-bcc7433214c5 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10CL013-A01 | 1.5mm2 1Pr CuSn CS
d28d90e5-6142-51e4-ad49-b100a312f4ac |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10CL013-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
f312ed09-13b1-5546-b5e2-dc7b843cd44f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10CL013-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
22a534b9-e117-4311-8bf0-d1a4628eac78 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10CL013-C01
2c9328b2-bdd4-4bf1-bf34-213e1c5c06dc |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10CL013-C01 | 1.5mm2 12C CuSn PVC/PVC
07fdaa38-7ab9-5cc4-baa7-5337c0973c65 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10CL013-C01 | 1.5mm2 12C CuSn PVC/PVC | Instrument Cable
88872a15-08d3-516f-9763-e8458a2452af |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030CRJ10CL013-C01 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
c155b6fa-f1ac-4371-bd19-fa64c1c6aeb3 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB20GS010-P01
7e9bd735-9fa9-4558-a9cf-6a95f886ece1 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB20GS010-P01 | 2.5mm2 2C+E CuSn PVC/PVC
297bf19e-1d6f-51f2-9c5c-10b06d65a092 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB20GS010-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Low Voltage Cable
691d960b-fb20-5382-adb4-6b9c178df57c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB20GS010-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Electrical Checks
dddace4a-8144-5eab-a754-7605d9977407 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Cables | TH00S030BJB20GS010-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
cebdda04-d96d-42d2-a9fd-ae1420f8b007 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Fibre & Comms
0a656351-928b-4b83-a7f0-910ca4a0596b |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Fibre & Comms | TH00S030CRA10GH010-F01
3edcf3b6-3d93-4ff3-9f89-b16c6ebc4432 |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Fibre & Comms | TH00S030CRA10GH010-F01 | 24C OS2 + 24C OM3 INSTALLED IN Emtelle 7 Tube Duct
0b12116c-0bdf-5d53-8b03-2ed7d9c9a82d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Fibre & Comms | TH00S030CRA10GH010-F01 | 24C OS2 + 24C OM3 INSTALLED IN Emtelle 7 Tube Duct | Fibre Optic Cable
ad56a7a8-ce7d-4319-b2a3-ab8cf29f5eba |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Fibre & Comms | TH00S030CRA10GH010-F02
d9dc8a96-7ae5-419a-ac94-2322958afcd8 |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Fibre & Comms | TH00S030CRA10GH010-F02 | 24C OS2 + 24C OM3 INSTALLED IN Emtelle 7 Tube Duct
13772351-8a9a-5537-b1ed-e6c9817d2060 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Fibre & Comms | TH00S030CRA10GH010-F02 | 24C OS2 + 24C OM3 INSTALLED IN Emtelle 7 Tube Duct | Fibre Optic Cable
381fb337-d77c-41ec-b99a-9f9f27d3a643 |  | checklist-flat | not-started | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP-SEP-E-003 SEP DCS & Comms | Certificate of compliance (COC)
6cf6dc5c-b9fb-5030-8544-8472dd75f183 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-SEP-E-003 SEP DCS & Comms | Certificate of compliance (COC) | Please upload Certificate of Compliance here when complete (COC)
3bea5652-e541-4982-bcae-57d1d1126aab |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms
31d1b356-225e-4b60-81c1-833a3c7c79ba |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Earthing
13eb4af4-f448-428a-9254-46d814dd0ab0 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Earthing | JUNCTION BOX-08-E01
d69106c9-b708-4ffe-a0b4-856dd5c2075a |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Earthing | JUNCTION BOX-08-E01 | 120mm2 1C Cu PVC/PVC GE/YE
bb8bd5d6-b6de-5ab5-b88b-acd8c5f37e54 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Earthing | JUNCTION BOX-08-E01 | 120mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
c2acea30-314f-510d-9b8f-3c4650101727 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Earthing | JUNCTION BOX-08-E01 | 120mm2 1C Cu PVC/PVC GE/YE | Test Results
6d725986-25ac-43ce-9ea3-f21452f1447a |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Electrical Installations
25da47dd-4ba4-46e6-8822-8f546f504847 |  | checklist-flat | not-started | Cable Pre-installation | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Electrical Installations | Cable Pre-installation
296d3943-0f27-57ba-8a66-f8573a3bcc73 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Electrical Installations | Cable Pre-installation | Cable Pre-Installation
58b49340-6bf8-4db1-95e8-6af9712f469d |  | checklist-flat | not-started | ITR-CL-1-101B Cable Supports Above Ground | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Electrical Installations | ITR-CL-1-101B Cable Supports Above Ground
06a523a8-9003-5ded-8f75-114e38cb8e73 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Electrical Installations | ITR-CL-1-101B Cable Supports Above Ground | Cable Supports Above Ground
ca7be36f-b259-419b-8d3b-8d82706a7214 |  | checklist-flat | not-started | ITR-CL-1-102 Entec - Distribution Board Installation | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Electrical Installations | ITR-CL-1-102 - Distribution Board Installation
f3b8ca74-6977-5d69-9aa4-4bc9ef162eca |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Electrical Installations | ITR-CL-1-102 - Distribution Board Installation | Distribution Board Installation (Mandatory Photo)
83607830-a948-5a01-b60b-26a66bc5af0c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Electrical Installations | ITR-CL-1-102 - Distribution Board Installation | Test Results
58e64d0b-68fe-5a3e-a05d-16137d03ad69 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Electrical Installations | ITR-CL-1-102 - Distribution Board Installation | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
9b0acb1b-e4c5-4375-9072-ec211664e320 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables
d7e676f0-1801-41ab-a5a3-bb6a251af57a |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | Junction Box 08
f1769e9c-93a8-44a4-a4be-3c5fda89b0be |  | checklist-flat | not-started | ITR-CL-1-106 - Junction Box | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | Junction Box 08 | Junction Box 08
61308fbd-78c8-55a7-8d58-0c069edba095 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | Junction Box 08 | Junction Box 08 | Junction Box
d26f0864-c8a4-401f-98be-5cf2d5b9147a |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | JUNCTION BOX-08-C01
3076f109-c953-4bb2-9cf7-c168a7e01a0c |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | JUNCTION BOX-08-C01 | 1.5mm2 27C CuSn PVC/PVC
a41f408f-00d7-5465-9f3d-b12a269338b1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | JUNCTION BOX-08-C01 | 1.5mm2 27C CuSn PVC/PVC | Instrument Cable
b6ce64c9-0ad9-5980-a8b1-3053333c2a60 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | JUNCTION BOX-08-C01 | 1.5mm2 27C CuSn PVC/PVC | Electrical Checks
78af8541-8dc5-4edd-9d9a-39cb25bc4270 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | JUNCTION BOX-08-C02
6a8b140a-d414-42ca-b201-e1743a22f7ba |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | JUNCTION BOX-08-C02 | 1.5mm2 27C CuSn PVC/PVC
78c58420-fb39-5386-9352-6a1816a5d77e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | JUNCTION BOX-08-C02 | 1.5mm2 27C CuSn PVC/PVC | Instrument Cable
3d3a9061-23b6-5bd1-9231-1fdb87b41e00 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | JUNCTION BOX-08-C02 | 1.5mm2 27C CuSn PVC/PVC | Electrical Checks
5b453752-b574-4f17-96e6-37d19764db00 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | JUNCTION BOX-08-C03
42ce2e7b-b2fd-449c-9b76-e5cd9bdfa6d0 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | JUNCTION BOX-08-C03 | 1.5mm2 27C CuSn PVC/PVC
1946999c-7840-527d-b162-75e4ba8b84fc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | JUNCTION BOX-08-C03 | 1.5mm2 27C CuSn PVC/PVC | Instrument Cable
13c5ef50-63dc-51cb-ad8f-1c720c2dd5af |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | JUNCTION BOX-08-C03 | 1.5mm2 27C CuSn PVC/PVC | Electrical Checks
baac5c46-74ea-43f8-9880-c73829e43231 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | JUNCTION BOX-08-C04
4496e4b6-421f-4456-9f1d-d2b2bb78a335 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | JUNCTION BOX-08-C04 | 1.5mm2 27C CuSn PVC/PVC
10071b5c-9837-577f-bf77-0dcad62001cc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | JUNCTION BOX-08-C04 | 1.5mm2 27C CuSn PVC/PVC | Instrument Cable
4e336036-fe1e-5229-9a7f-efe543868620 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | JUNCTION BOX-08-C04 | 1.5mm2 27C CuSn PVC/PVC | Electrical Checks
5a81d928-c439-4d9a-b7a2-9b036c5cfec0 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | JUNCTION BOX-08-A01
eea6ffad-23f3-475f-95c7-2200e2223226 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | JUNCTION BOX-08-A01 | 1.5mm2 12Pr CuSn PVC/PVC
276116d2-f5e4-55e9-b536-5b2fa0a72369 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | JUNCTION BOX-08-A01 | 1.5mm2 12Pr CuSn PVC/PVC | Instrument Cable
8d0e662b-549a-5ac8-88b1-9950e94c7e01 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | JUNCTION BOX-08-A01 | 1.5mm2 12Pr CuSn PVC/PVC | Electrical Checks
2ea580ab-761a-4c27-90ad-8f4786b9b344 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F01-C01
63637f59-51fd-459a-ace2-92f421b4f79d |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F01-C01 | 1.5mm2 12C CuSn PVC/PVC
af7bfdfe-a600-5ed8-9510-669c6965cff9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F01-C01 | 1.5mm2 12C CuSn PVC/PVC | Instrument Cable
00b7e1e6-8583-5c59-9e0d-9dd71bfe553a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F01-C01 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
f32469ec-5d12-4700-b172-1b65f7e39e1b |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F01-C02
e9f46779-2e54-41eb-bec7-ac3f2ca160e8 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F01-C02 | 1.5mm2 4C CuSn PVC/PVC
0c723ebd-c65d-572e-af48-d5b03f8ff6e5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F01-C02 | 1.5mm2 4C CuSn PVC/PVC | Instrument Cable
2517a509-efee-5b11-95b7-c55b7d55c565 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F01-C02 | 1.5mm2 4C CuSn PVC/PVC | Electrical Checks
f8d427ff-c0f0-4e6f-84e8-59661441af03 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F05-C01
4a4d0793-3526-497d-86d7-5fe25751be32 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F05-C01 | 1.5mm2 12C CuSn PVC/PVC
386f6e3a-c1fc-579d-8c24-7afc33111c63 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F05-C01 | 1.5mm2 12C CuSn PVC/PVC | Instrument Cable
7ffc508f-5691-5f28-a023-de2350137662 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F05-C01 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
1a2a9c94-3b82-4f0a-aa9f-092a912858ce |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F05-C02
8644f2cc-9a5b-4bfb-b50f-0b37ba713d1c |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F05-C02 | 1.5mm2 4C CuSn PVC/PVC
70414042-f3f2-51dd-aa09-c118a8963b37 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F05-C02 | 1.5mm2 4C CuSn PVC/PVC | Instrument Cable
65818785-658f-567e-9d0d-2125bdec0242 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F05-C02 | 1.5mm2 4C CuSn PVC/PVC | Electrical Checks
3557cc6c-0514-47f3-b840-8e8c251e4c73 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F09-C01
e8d6c01e-d6e8-4bb4-ae61-e604da30cf02 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F09-C01 | 1.5mm2 12C CuSn PVC/PVC
2dd78412-6640-560a-8e00-1d180ec5c265 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F09-C01 | 1.5mm2 12C CuSn PVC/PVC | Instrument Cable
a665d0a1-5158-5101-9e6b-2e85b8397813 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F09-C01 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
698320e0-44ca-414f-96b2-2484df8a3919 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F01-P01
1a26a013-2bdb-4bf2-89e7-45c49232aa3a |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F01-P01 | 1.5mm2 2C CuSn PVC/PVC
10142792-5081-5df9-b390-1dc7e042e71f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F01-P01 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
de01a454-1f34-520b-9cd2-abd9da222d2f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F01-P01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
a1fc9ab0-c100-4654-a443-cad29a4f4dbb |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F05-P01
1ce15883-e88c-467c-b5d7-c3015119de58 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F05-P01 | 1.5mm2 2C CuSn PVC/PVC
dba32805-3d54-5cf0-935e-5c9fe7bd2f40 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F05-P01 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
b5320966-5b0f-5f00-9212-04c8677fa950 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F05-P01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
0af66226-4f83-4219-93c0-7ca93bb7064e |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F09-P01
d7b18264-fbc4-450f-96c1-864e43ce3ae8 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F09-P01 | 1.5mm2 2C CuSn PVC/PVC
3835d004-bfa6-55e2-bed9-d19424b8d89e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F09-P01 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
8b122054-918d-5ab0-a137-f6ea39180b10 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F09-P01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
36b7e958-220a-415e-ac74-6819da78df20 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFT20-C02
ead2a28f-97ff-4254-9d43-341be100343d |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFT20-C02 | 1.5mm2 2C CuSn PVC/PVC
69c11e65-8e15-5155-a773-04ff3bc45725 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFT20-C02 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
c6a4b074-f9b3-5d28-9ff3-c777925efe0e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFT20-C02 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
522a3b6d-2838-4cb4-bd57-9912d43b9657 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFT20-C03
0006304d-9d0c-4185-8ac0-91a488cfa059 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFT20-C03 | 1.5mm2 2C CuSn PVC/PVC
89b93c53-07ae-5bf3-a20c-a1bd448265d1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFT20-C03 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
7b2d73d4-a8f9-52fd-8087-3979e243c4f5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFT20-C03 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
ca1c2a56-1cde-4178-9453-8db5b59f50ca |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010-C01
787728d9-f418-4689-b864-0b8775d74456 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010-C01 | 1.5mm2 2C CuSn PVC/PVC
7fc1b402-b123-503a-ae30-351279e4d8c1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010-C01 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
9e8ba3aa-c0e0-5f45-badb-05d6ce52fd5b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010-C01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
0a5e0009-372a-4e92-96c7-3a3bbe50d0d6 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010-C02
5e09e8ac-8ecf-4607-b7f7-5c6969cfe2af |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010-C02 | 1.5mm2 2C CuSn PVC/PVC
7849c33f-578e-504e-8aad-688753a2b13f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010-C02 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
c22306f1-dcf1-5607-ab29-c6fcc9a26892 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010-C02 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
87dd6bfc-f1e3-414a-9b33-0d515152b86d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F37-C01
7fbd48ce-2920-4e78-97ac-f398568c3355 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F37-C01 | 1.5mm2 12C CuSn PVC/PVC
e1888549-4432-5216-b2f0-22cb381a2e0f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F37-C01 | 1.5mm2 12C CuSn PVC/PVC | Instrument Cable
540af467-1fa0-58d9-bbdd-3cb6bf7edd85 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F37-C01 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
1b9a0b72-f2bd-43fb-aed9-2d0f90165f20 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F40-C01
cf87c4f9-ce9e-4d82-b688-77348ad6301a |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F40-C01 | 1.5mm2 12C CuSn PVC/PVC
f52288bf-ad7a-55f0-b64c-b479bdce814e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F40-C01 | 1.5mm2 12C CuSn PVC/PVC | Instrument Cable
539a8b7b-b25c-5dbc-a5bb-d209ac89d3c0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F40-C01 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
ad817d0c-c849-4f29-b1c0-cebf730f6495 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F43-C01
7fa97ba7-4b49-4860-a443-f5a600a5e038 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F43-C01 | 1.5mm2 12C CuSn PVC/PVC
7987fcc5-95c9-53ed-9eb3-2bc4fa37b2e5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F43-C01 | 1.5mm2 12C CuSn PVC/PVC | Instrument Cable
b8dffa88-87b5-5d46-af29-6dd93d5cc42f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F43-C01 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
0d543a7f-1cd9-41a7-aabe-5e8899249c1c |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F46-C01
cbb21688-3486-42e4-a671-0422f8153b15 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F46-C01 | 1.5mm2 12C CuSn PVC/PVC
23b76e13-b4bb-505c-85c4-e1095bbf04db |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F46-C01 | 1.5mm2 12C CuSn PVC/PVC | Instrument Cable
8ada0e06-553f-5ab0-a125-d5174e646eb3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F46-C01 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
8f8f19bb-df49-4291-bc3e-39c4eb7b587f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F49-C01
361170fa-57c7-4b24-8d3d-cd0403388d55 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F49-C01 | 1.5mm2 12C CuSn PVC/PVC
8f3936f4-dbb3-51ba-b154-5fd69b846aae |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F49-C01 | 1.5mm2 12C CuSn PVC/PVC | Instrument Cable
f4fbe5c4-4b54-5173-a820-531c45f042a8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F49-C01 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
db2e3cb7-e8a2-4ab5-8ab5-f08b4000d063 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F52-C01
6be405d5-f92b-48fc-a3d4-53956e6f7f22 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F52-C01 | 1.5mm2 12C CuSn PVC/PVC
dd708410-8b69-5f50-b57e-a4a8fac51e34 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F52-C01 | 1.5mm2 12C CuSn PVC/PVC | Instrument Cable
8d29de1c-65ca-5256-bfb0-28e8c661a611 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BFA40GS010_-F52-C01 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
069bb631-59b6-4051-a434-996248456d6f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BRA20-A01
b62f18fd-7f4b-4750-a43b-b42fdbd6e992 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BRA20-A01 | 1.5mm2 2Pr CuSn PVC/PVC
ed0a7bb2-f372-5fee-83b1-bf4fc2994618 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BRA20-A01 | 1.5mm2 2Pr CuSn PVC/PVC | Instrument Cable
8404f60f-0768-5b0b-9260-0e1ec0375fc3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BRA20-A01 | 1.5mm2 2Pr CuSn PVC/PVC | Electrical Checks
26d3fa7d-09f2-49e0-8c5e-16a74b0c09ec |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BRA20-C01
8a3fb913-fed7-40d9-9d11-c9daa4e222d7 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BRA20-C01 | 1.5mm2 4C CuSn PVC/PVC
31c6f5a1-3fec-5250-ad1a-f5bc4f2212e4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BRA20-C01 | 1.5mm2 4C CuSn PVC/PVC | Instrument Cable
0dbae9bb-f371-5e1d-98da-d04da768343c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BRA20-C01 | 1.5mm2 4C CuSn PVC/PVC | Electrical Checks
520d8c62-195b-4512-b02b-ca75109d4174 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BUC20GU101-C01
d402f596-5db1-49a4-b07b-5a92b8515a5b |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BUC20GU101-C01 | 1.5mm2 2C CuSn PVC/PVC
5592d408-05b9-532c-bb30-3bbe925ecf7d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BUC20GU101-C01 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
bcad7fc3-1f2e-530a-82d3-dcf52182b3c1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000BUC20GU101-C01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
8216a483-6bc4-4102-a2e8-c3eb5d022a13 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000MAJ20-C01
f00c6a21-ae18-4d93-9f19-81ee9b8fdb52 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000MAJ20-C01 | 1.5mm2 12C CuSn PVC/PVC
12519893-5116-5f5b-9dcb-3d1e255426d2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000MAJ20-C01 | 1.5mm2 12C CuSn PVC/PVC | Instrument Cable
b8cd3872-bcb0-581c-aa8a-0d57b1fad83f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000MAJ20-C01 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
1ab8bd8f-92c5-426d-8639-0c79d74ec7cf |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000SGY10EH010-C01
23d8e2e8-8817-4f1d-8813-4237ae98cdc1 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000SGY10EH010-C01 | 1.5mm2 2C CuSn PVC/PVC
0ea84261-ba5c-51b3-be44-39172e6225f4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000SGY10EH010-C01 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
9dfe18e4-198a-5feb-a039-af86b1607dcc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000SGY10EH010-C01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
6ca63ac3-c2c1-439c-9bc1-8a1ebdd25d92 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000CFX10CT010-C01
6c24f8d6-36b7-455c-8cc7-93d8c2018439 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000CFX10CT010-C01 | 1.5mm2 1Pr CuSn CS
80181a40-f8b6-5296-9c1b-e56397181ad6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000CFX10CT010-C01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
c0c6159f-c433-548d-b01b-5b92b8c5f894 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Cables | TH000000CFX10CT010-C01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
80f4ed4b-c7c9-4ca6-badf-bb27eecbde82 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Fibre & Comms
8f31b3e8-88af-43f7-89d6-30d54dc63e0a |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Fibre & Comms | TH000000BFA40GS010-F01
c5d02ad9-0538-4ff8-a228-d4245a0e4cc2 |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Fibre & Comms | TH000000BFA40GS010-F01 | 8C OS2 + 8C OM3 INSTALLED IN Emtelle 7 Tube Duct
4ea09bfc-b8d9-56f3-98c8-7b57ac0cfdbc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Fibre & Comms | TH000000BFA40GS010-F01 | 8C OS2 + 8C OM3 INSTALLED IN Emtelle 7 Tube Duct | Fibre Optic Cable
de758186-6bf7-4598-aafd-7071778823dc |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Fibre & Comms | TH00S030CRS10GN009-S01
efae3cd1-3cba-442d-bbd1-170ea239d690 |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Fibre & Comms | TH00S030CRS10GN009-S01 | OM3 Fibre Patch Lead
749d50c2-31cc-5f67-92ec-91da93815410 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Fibre & Comms | TH00S030CRS10GN009-S01 | OM3 Fibre Patch Lead | Fibre Optic Cable
fdd209b8-5804-4fe9-8487-bdae7d065c6e |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Fibre & Comms | TH00S030CRS10GN009-S02
7f47eeb0-9c62-4dcf-b29a-516949c5aa47 |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Fibre & Comms | TH00S030CRS10GN009-S02 | OM3 Fibre Patch Lead
8a02633c-db08-5d8f-9234-3bfde3b1f4f0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Fibre & Comms | TH00S030CRS10GN009-S02 | OM3 Fibre Patch Lead | Fibre Optic Cable
c1966ee7-c234-49c1-8854-5046f7237766 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Fibre & Comms | TH00S030CRS10GN009-S03
cdac0e65-4300-4cec-ac7c-4de666cc405d |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Fibre & Comms | TH00S030CRS10GN009-S03 | CAT 5E
cfd7fa66-476f-5ee4-b5f0-24aefd787fd7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Fibre & Comms | TH00S030CRS10GN009-S03 | CAT 5E | Instrument Cable
90768a40-2aa0-52a2-a031-ee241768dc88 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Fibre & Comms | TH00S030CRS10GN009-S03 | CAT 5E | Electrical Checks
adab010c-e8b4-4259-afc4-088e601af875 |  | checklist-flat | not-started | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP-ASB-E-003 ASB DCS & Comms | Certificate of compliance (COC)
66a80ad9-6ddf-52db-8dd0-c85bbc3bd64c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-003 ASB DCS & Comms | Certificate of compliance (COC) | Please upload Certificate of Compliance here when complete (COC)
716fbcac-da59-4e6a-b611-180fed981c4e |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms
58ef0581-2732-493e-ac38-7b0c2895ad84 |  | folder-normal | pass |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Electrical Installations
5f29a362-a7ef-48a9-9136-1d0b0e6f873b |  | checklist-flat | pass | Cable Pre-installation | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Electrical Installations | Cable Pre-installation
b1185ec0-f988-53bf-87f3-2e82d6ec420d |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Electrical Installations | Cable Pre-installation | Cable Pre-Installation
2527c1da-0ea9-4b5c-b84f-a5a491d3ca45 |  | checklist-flat | pass | ITR-CL-1-109 Electrical Equipment Package | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Electrical Installations | ITR-CL-1-109 Electrical Equipment Package
a75a5519-cfdc-56d0-9fd2-fc1c76c5e115 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Electrical Installations | ITR-CL-1-109 Electrical Equipment Package | Electrical Equipment Package
a4503958-a7cf-4e99-9030-ebe5733f23cb |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables
bc8ce7c8-dd48-4c60-889c-16bb74762333 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GH010-C01
95da5e1b-dd98-4420-b587-2894edc694ce |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GH010-C01 | 1.5mm2 12C CuSn PVC/PVC
6c8be9e3-5e7a-5129-bbee-2d742a1ca9ab |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GH010-C01 | 1.5mm2 12C CuSn PVC/PVC | Low Voltage Cable
f9215ff3-4642-5732-b001-544724aa9a05 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GH010-C01 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
f9f48c4d-399f-5444-b613-6cec8f073ec6 |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GH010-C01 | 1.5mm2 12C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
b30d12dd-d4b9-491a-af14-56e525584cd2 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GH010-C02
75ae2bc2-4375-4d27-a85f-ca4c12f8026e |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GH010-C02 | 1.5mm2 12C CuSn PVC/PVC
07181309-867c-594d-a185-1c79d9226b84 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GH010-C02 | 1.5mm2 12C CuSn PVC/PVC | Low Voltage Cable
a3cc95e8-efa9-5408-8b56-996712baa239 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GH010-C02 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
8c2ab0aa-6f31-58e2-aec2-0814f2e0cf46 |  | holdpoint | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GH010-C02 | 1.5mm2 12C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
47434ede-34f8-423e-a1a3-3253d700b6e5 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GH010-C03
6128357a-23d2-4640-b69e-e583bbf720a8 |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GH010-C03 | 1.5mm2 2C CuSn PVC/PVC
0efb68fb-ace9-539a-b33e-7954c4576ff5 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GH010-C03 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
2ddc179f-ed9c-5294-ac5e-b4369119f456 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GH010-C03 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
e90e0c55-395c-5f2a-92c3-b3a8f0635dfc |  | holdpoint | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GH010-C03 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
60bb147e-fbdd-452c-a078-3c7685f7a62e |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GH010-C04
4eef1dad-5c7d-4cd0-a878-ba13081fc6b2 |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GH010-C04 | 1.5mm2 2C CuSn PVC/PVC
453fd290-3adf-5847-a3a3-88faa4e7c3aa |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GH010-C04 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
3f675642-2237-53f9-9a04-40cad78b5883 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GH010-C04 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
9e2ab453-288f-5d17-aeca-1372c67c6cf7 |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GH010-C04 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
a2d99473-419e-4fe4-81fd-1d4e9e26e992 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GW010-C01
27f4a315-abe4-4b1b-a9c9-226b64de7394 |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GW010-C01 | 1.5mm2 2C CuSn PVC/PVC
f66a5e92-1bf3-539c-ae6b-6d35d50dcf01 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GW010-C01 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
8eddb87a-7ddd-52ad-9430-c93ab195c59f |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GW010-C01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
f7adb2e1-5f31-59d4-9679-086fe6d03b42 |  | holdpoint | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GW010-C01 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
cb20b4e2-b60c-4fa7-9085-33dfecafd7c9 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GW011-C01
716fe6c7-0724-4ddc-9955-c1d498c274f4 |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GW011-C01 | 1.5mm2 2C CuSn PVC/PVC
ada1a3cf-cfb2-5292-95e5-38adcd6702db |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GW011-C01 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
d023de14-8ab9-592c-9db0-ccde2661612a |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GW011-C01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
847a993f-dd76-53ea-ad09-12cd34349dd9 |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GW011-C01 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
b5a67fa9-f566-4bac-8328-571fa0a90591 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10CE002-C01
53eb7f30-a8a1-43fa-bb12-c2f165339aaf |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10CE002-C01 | 1.5mm2 1Pr CuSn CS
28f2ab29-5ee1-5e4b-8371-f00153d149c9 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10CE002-C01 | 1.5mm2 1Pr CuSn CS | Low Voltage Cable
3cd4dad2-eb57-5b9b-bc24-74f40ca0f29c |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10CE002-C01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
0f3d7c77-7d9c-5158-bf62-e216a172560a |  | holdpoint | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10CE002-C01 | 1.5mm2 1Pr CuSn CS | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
a525554e-49dd-4c50-a12c-7be950d1b0f1 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GW020-C01
b1d4f12c-0f29-4411-88a2-6d6d081fea0a |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GW020-C01 | 1.5mm2 2C CuSn PVC/PVC
6255ba7d-5366-5d1c-8b82-31e1d135db8a |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GW020-C01 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
184907c5-21ea-5d86-89c8-518fba77b144 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GW020-C01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
6d012f81-7208-5775-9d14-0d86b14282fb |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GW020-C01 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
7b704a1f-5737-4493-9f42-6ff523c1aa2f |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GW021-C01
343a819d-fe3a-43a6-a3b8-21df3b386b9f |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GW021-C01 | 1.5mm2 2C CuSn PVC/PVC
b4493c15-9f07-5cc1-9c2e-13b4026994f2 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GW021-C01 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
de750573-8c2b-52c3-b349-314a5ce7f976 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GW021-C01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
06d4aa68-32fc-50cc-aed0-ce5c01923e6e |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GW021-C01 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
095f0620-942d-4d8a-9f32-f556d0dc1ed8 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10CE002-C01
f23a47ec-cede-4f08-a30e-09cddfecd810 |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10CE002-C01 | 1.5mm2 1Pr CuSn CS
ae7cc72a-4600-52a5-8569-ca6167e3b112 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10CE002-C01 | 1.5mm2 1Pr CuSn CS | Low Voltage Cable
f881d35b-8111-5b90-bbbc-ef8f724ad8c4 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10CE002-C01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
54396cb3-cf6c-50a8-9160-0d977c78e46c |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10CE002-C01 | 1.5mm2 1Pr CuSn CS | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
93c2f9ff-8be9-42f7-b8ee-dfc021c0c025 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GH002-C01
a6167944-2c40-498b-8d77-18e10b4ad907 |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GH002-C01 | 1.5mm2 2C CuSn PVC/PVC
3f1a9799-5dc7-5c2b-b6d3-8a855a4eb7f8 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GH002-C01 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
ac33f275-c8a0-515a-8dc1-503e8423e038 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GH002-C01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
9d20efc5-2c42-5dd7-a4b7-3c9a3f8797df |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GH002-C01 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
c51d857e-647b-4675-bcef-ac57f0bb9479 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GN007-C01
63d59696-2067-465c-a134-8870a9f06305 |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GN007-C01 | 1.5mm2 2C CuSn PVC/PVC
80b24e02-a632-5a84-ada0-ebe4d35f4e68 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GN007-C01 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
dc30de6b-088d-5bed-9703-8611743df6d4 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GN007-C01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
7f9297b4-2a2e-537e-99fb-91dd83f86939 |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000BJB10GN007-C01 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
b50e9298-7582-4c00-92c1-41555c35df95 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GU003-C02
663093ea-0e8c-4539-9e1a-19cc8d020af5 |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GU003-C02 | 1.5mm2 2C CuSn PVC/PVC
f692abcb-b57c-5ee5-b902-1bae0292717c |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GU003-C02 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
0552c0be-a1eb-5745-b568-62761457722d |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GU003-C02 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
fc344562-cb0c-525d-b79f-45ce5cd02607 |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GU003-C02 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
0a3f32cf-c106-4c16-9aa4-5d66b39d6594 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GH002-C02
03eddd75-5f59-4393-9e75-a511d4c41865 |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GH002-C02 | 1.5mm2 2C CuSn PVC/PVC
e06c3851-fc3a-5e45-9535-457ddea03bea |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GH002-C02 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
1e744631-cd58-5baf-9eaa-f8fc1d6b45ad |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GH002-C02 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
4dae7627-753e-5edc-8a85-fd979c275bd9 |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GH002-C02 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
a9b20f4e-a920-4064-9b06-56d74d047d0b |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYP20EM010-C01
6e798002-3982-4fef-a9fa-43e8344b4354 |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYP20EM010-C01 | 1.5mm2 2C CuSn PVC/PVC
97a62ac7-86ec-5bb8-95b9-e77d4b4f3924 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYP20EM010-C01 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
d324ef73-85cc-5a7a-a502-1286af36d6f3 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYP20EM010-C01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
5135c61f-7e75-58eb-a9ef-4e746cdcee92 |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYP20EM010-C01 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
63b468e9-34e0-4e63-aec3-51556a79dc91 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GH002-C03
27ae9e01-87b0-4128-b919-0643f5351cd1 |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GH002-C03 | 1.5mm2 2C CuSn PVC/PVC
a9db96d3-ee03-570b-9dcf-91edb6e20d74 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GH002-C03 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
f9e633eb-292c-59e7-b3ad-f8e282ebb0be |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GH002-C03 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
0a1e67ed-c384-5eea-abb2-8a963fd4b409 |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GH002-C03 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
098d73c9-f615-404d-aa7b-5a9b460c4959 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYP20EM010-C02
41a3c1ef-0bfa-41c9-8d37-b3842ae5eb53 |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYP20EM010-C02 | 1.5mm2 2C CuSn PVC/PVC
f8d3f562-3879-592d-8b55-415232a6a235 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYP20EM010-C02 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
e4a1e0f7-d0e5-530e-bec2-c29470479505 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYP20EM010-C02 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
24bf9b0d-e87c-571b-90fd-422e862e2e83 |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYP20EM010-C02 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
74fd3bdd-8b4a-46ea-94fc-2fdde973e671 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | TH000000SRxCF010_-S01-C01
5dcc1669-3dc2-422a-9de0-95eb27caaedb |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | TH000000SRxCF010_-S01-C01 | 1.5mm2 2C CuSn PVC/PVC
638f476f-bb2b-5e26-890e-70ee68c7e709 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | TH000000SRxCF010_-S01-C01 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
9016a2bd-042f-5826-916e-a93edbf0874c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | TH000000SRxCF010_-S01-C01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
f77af731-b9b8-4df7-ad16-63702b992ede |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | TH000000CFX20CT010-C01
aff5a34d-1b1e-4505-b453-15f35c775971 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | TH000000CFX20CT010-C01 | 1.5mm2 1Pr CuSn CS
cd14f273-2d0f-54bc-91ce-d7189764b6a0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | TH000000CFX20CT010-C01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
813f1beb-4279-5ba8-82d1-ae90af958e5d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | TH000000CFX20CT010-C01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
d6f4df9c-a7d4-4162-a749-418c832d49a2 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | TH000000MAJ10-C01
e396ebae-b5a8-46b5-b3e0-7355dadbeb69 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | TH000000MAJ10-C01 | 1.5mm2 12C CuSn PVC/PVC
73953bad-f36a-54f6-a194-74a05645a8bc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | TH000000MAJ10-C01 | 1.5mm2 12C CuSn PVC/PVC | Instrument Cable
ff033f42-7ede-55db-a764-9b859f9ec3a3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | TH000000MAJ10-C01 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
ea4634ec-2f6c-4fdf-8348-58207b4fe1d8 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | TH000000SGY20EH010-C01
33326213-ba5c-4ff3-aa7d-36fd9f3a3731 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | TH000000SGY20EH010-C01 | 1.5mm2 2C CuSn PVC/PVC
0b6c515a-3fea-5e66-ac53-f1e8c001d46f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | TH000000SGY20EH010-C01 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
83ee04ec-fcd0-5ae5-b0f4-77289d8e9a53 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | TH000000SGY20EH010-C01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
c2121c01-2eee-43a8-9248-e03edeb3f6c0 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GH00-C02
cbc93126-35ce-4067-8f6e-52c149b28c8e |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GH00-C02 | 1.5mm2 12C CuSn PVC/PVC
a7f0c2f9-f737-53e8-8730-15011014c16b |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GH00-C02 | 1.5mm2 12C CuSn PVC/PVC | Low Voltage Cable
92be9623-5300-502f-80e5-ea7a61b0f3a4 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GH00-C02 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
cd89dd6e-7062-516b-94b7-a6983861da5b |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CYW10GH00-C02 | 1.5mm2 12C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
fea762f1-d3b7-4d9a-9db9-2f13dc0fbbe2 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | EDP3BPA10GH010-A01
481392f9-1408-4dd4-ac76-bd37e0c202b1 |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | EDP3BPA10GH010-A01 | 1.5mm2 4pr CuSn ESCS
f8d96ff9-86d6-57a9-9189-0e13ca56d997 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | EDP3BPA10GH010-A01 | 1.5mm2 4pr CuSn ESCS | Low Voltage Cable
515f9a60-ebed-5a6c-aff1-6713f8827e68 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | EDP3BPA10GH010-A01 | 1.5mm2 4pr CuSn ESCS | Electrical Checks
e6e4ec48-c8af-50cb-a31a-17d312228a22 |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | EDP3BPA10GH010-A01 | 1.5mm2 4pr CuSn ESCS | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
e9ffe9e2-7bd3-423c-aa6e-d9ec841f0706 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | EDP3BPA10GH010-C01
47103c61-490f-4a87-8a2f-a96591175156 |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | EDP3BPA10GH010-C01 | 1.5mm2 12C PVC/PVC
51f7b781-fa71-556f-a10c-ff1724aad552 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | EDP3BPA10GH010-C01 | 1.5mm2 12C PVC/PVC | Low Voltage Cable
3367628e-4bfb-56c0-a6ee-067c211e6bb0 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | EDP3BPA10GH010-C01 | 1.5mm2 12C PVC/PVC | Electrical Checks
13e61ad2-bb23-5287-9d44-d44c7075becd |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | EDP3BPA10GH010-C01 | 1.5mm2 12C PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
434a6a96-76c9-4226-b03d-7178d021d64c |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CVA10GH010-A01
25157c9e-b3a9-4865-b2b0-9be31437761a |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CVA10GH010-A01 | 1.5mm2 12tri CuSn ESCS
2ac5f1eb-4307-5cda-a44c-fc79d8f844ce |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CVA10GH010-A01 | 1.5mm2 12tri CuSn ESCS | Low Voltage Cable
9ea8b298-89ac-5f60-8df8-92bc6f2b07d2 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CVA10GH010-A01 | 1.5mm2 12tri CuSn ESCS | Electrical Checks
cb61b1f8-0462-503b-a587-349fb2a40971 |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Cables | 0000CVA10GH010-A01 | 1.5mm2 12tri CuSn ESCS | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
30cd40cb-8900-4f89-a830-301e07a4089b |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms
79a064a3-2cf3-4d20-9b0b-4c35e971685c |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CYW10GH002-F01
652cbebf-ded1-4a88-aa60-28ed1b11767d |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CYW10GH002-F01 | 24C OS2 + 24C OM3 INSTALLED IN Emtelle 7 Tube Duct
1c0c6850-e23b-5328-87b0-e5780ac91542 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CYW10GH002-F01 | 24C OS2 + 24C OM3 INSTALLED IN Emtelle 7 Tube Duct | Fibre Optic Cable
1efbfeed-c71b-44bf-bb71-5ab1fc5746e5 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CYW10GH002-F02
eb930695-c2af-48b0-b5ff-0c266767b676 |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CYW10GH002-F02 | 24C OS2 + 24C OM3 INSTALLED IN Emtelle 7 Tube Duct
a440272f-5f21-5afe-a669-1174bd1fcc8b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CYW10GH002-F02 | 24C OS2 + 24C OM3 INSTALLED IN Emtelle 7 Tube Duct | Fibre Optic Cable
a41dea6d-1d17-4467-99ee-f60b87d8577f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRR10GU101-S01
3f332d22-d393-45ef-afe4-69a2e3eb9bfb |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRR10GU101-S01 | OM3 Fibre Cable
c27f82d9-a377-5df6-886a-679ad7d7c26e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRR10GU101-S01 | OM3 Fibre Cable | Fibre Optic Cable
8f7eb34c-15c0-4c76-b0eb-e6c26189c793 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRR10GU102-S01
66a30707-cdae-493a-beef-a2832761b490 |  | checklist-flat | not-started | ITR-I-44A Fibre Optic Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRR10GU102-S01 | OM3 Fibre Cable
94e03958-8073-5b58-9e15-74c8a6efc0a0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRR10GU102-S01 | OM3 Fibre Cable | Fibre Optic Cable
3bd38288-5680-496d-9838-26edf4988aca |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRA10GU003-S02
70de31d8-999f-4bf2-9110-15328e90f187 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRA10GU003-S02 | Profibus DP - Grey Sheath
fd00dc00-8dbd-57ce-bcc2-06684fa9d71b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRA10GU003-S02 | Profibus DP - Grey Sheath | Instrument Cable
8b543ffa-7eec-57ac-a928-164ae4cd503c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRA10GU003-S02 | Profibus DP - Grey Sheath | Electrical Checks
3078eb45-fd78-445b-8db0-e8d49daaa270 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRA10GU002-S02
c528df54-75d1-42d0-8d2f-c3dda75f79a4 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRA10GU002-S02 | Profibus DP - Grey Sheath
230f5e9f-b98c-545d-a033-0aed29a14781 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRA10GU002-S02 | Profibus DP - Grey Sheath | Instrument Cable
a38cb87d-93c2-5acf-aa3b-ad627f9d6538 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRA10GU002-S02 | Profibus DP - Grey Sheath | Electrical Checks
288714ca-2230-4808-a8ea-7e486574d1e9 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRA10GU009-S02
22a5a490-79fe-4d9c-b37b-4c198207e806 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRA10GU009-S02 | Profibus DP - Grey Sheath
c5e914a6-1954-5d16-8afd-df8b27e829d3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRA10GU009-S02 | Profibus DP - Grey Sheath | Instrument Cable
78572f64-445b-5106-af81-a9c3a5cf25aa |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRA10GU009-S02 | Profibus DP - Grey Sheath | Electrical Checks
18c06be4-d755-4baf-96b2-8654a4ff93a3 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRA10GU011-S02
db8d3876-7160-4bdb-91ac-8f06bc027d56 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRA10GU011-S02 | Profibus DP - Grey Sheath
f8fc9db7-681f-5f89-8ad6-9c86238a6fbc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRA10GU011-S02 | Profibus DP - Grey Sheath | Instrument Cable
455691e2-19ae-59c1-a8cc-e904c5e459cc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRA10GU011-S02 | Profibus DP - Grey Sheath | Electrical Checks
0a2a4e29-bc11-4f63-beb4-afe83f61faa3 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRA10GU010-S02
eaf5ff45-4d5a-4dc2-a79d-06677e15e2e0 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRA10GU010-S02 | Profibus DP - Grey Sheath
7706123e-7aa4-5302-84d7-287270a91188 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRA10GU010-S02 | Profibus DP - Grey Sheath | Instrument Cable
4cb0f052-006d-52c3-b116-dca43574e076 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRA10GU010-S02 | Profibus DP - Grey Sheath | Electrical Checks
659cfffb-48f5-40d3-aaf7-706798348c22 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRA10GU012-S02
033c5394-62d4-4845-b706-289388ff7c4d |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRA10GU012-S02 | Profibus DP - Grey Sheath
e87f11ee-6224-54da-84ae-8b168ac86220 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRA10GU012-S02 | Profibus DP - Grey Sheath | Instrument Cable
6bbc03b6-034c-5fa0-8321-fe23e34334a4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH000000CRA10GU012-S02 | Profibus DP - Grey Sheath | Electrical Checks
cdcb0b84-6e39-45f4-af9c-6957879b437c |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH00EDP0BPA10AP010-S01
036faa19-0133-4519-ad7b-84e0fc660d95 |  | checklist-flat | not-started | Cable Test Record | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH00EDP0BPA10AP010-S01 | Profibus DP Grey Sheath
b3564644-2aa5-5244-b4cd-eb1070c1d4b1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Fibre & Comms | TH00EDP0BPA10AP010-S01 | Profibus DP Grey Sheath | Upload completed ITR scans
dde15c67-f172-4032-be07-c55c7b74a4e6 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Earthing
8b7dfa20-68b3-440f-9b61-22fdb006c4ff |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Earthing | TH000000BJB10GS010_BOND05
f37d2816-c1e8-4eec-acce-1dad262288e6 |  | checklist-flat | work-in-progress | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Earthing | TH000000BJB10GS010_BOND05 | 70mm2 1C Cu PVC/PVC GE/YE
b4e9aead-7a3f-5199-a211-6ec2a898f197 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Earthing | TH000000BJB10GS010_BOND05 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
7f2db3d3-9c6d-5a16-885f-b87f0d73c702 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Earthing | TH000000BJB10GS010_BOND05 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
74cb6876-297e-4f61-b9a0-b512a40bea66 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Earthing | TH000000BJB10GS010_BOND06
beb1abf4-1141-4265-acf8-d56e483b2412 |  | checklist-flat | work-in-progress | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Earthing | TH000000BJB10GS010_BOND06 | 70mm2 1C Cu PVC/PVC GE/YE
b2fab8c2-f587-5a8f-8c7b-b7e2ded4fbd8 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Earthing | TH000000BJB10GS010_BOND06 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
19a1b57e-3537-5cb1-aa99-7704ac62b6e2 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Earthing | TH000000BJB10GS010_BOND06 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
2b25b27b-5844-4b0b-a2c5-8b91da4bc276 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Earthing | TH000000BJB10GS010_BOND07
83362358-6a0a-432f-942b-02bfdea05934 |  | checklist-flat | work-in-progress | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Earthing | TH000000BJB10GS010_BOND07 | 70mm2 1C Cu PVC/PVC GE/YE
8e6d48b4-eb97-5bb7-88f6-3a851362d0ba |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Earthing | TH000000BJB10GS010_BOND07 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
18a2033c-21ea-56c1-883a-889a7f6ca061 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Earthing | TH000000BJB10GS010_BOND07 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
b8824cc5-e642-45e6-a335-1bc12c6a3235 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Earthing | TH000000BJB10GS010_BOND08
222c39f9-a2c7-474b-8149-59a1a5cbb3ec |  | checklist-flat | work-in-progress | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Earthing | TH000000BJB10GS010_BOND08 | 70mm2 1C Cu PVC/PVC GE/YE
3255af79-38f9-5d84-9b32-45c103226db8 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Earthing | TH000000BJB10GS010_BOND08 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
ba47f385-6238-517b-b95a-39b6a529b7fb |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Earthing | TH000000BJB10GS010_BOND08 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
dd66d053-e7ae-4071-a1a1-21a0693392df |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Earthing | TH000000BJB10GS010_BOND14
c3d7596a-eb06-41d2-a459-a2284c529fb3 |  | checklist-flat | work-in-progress | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Earthing | TH000000BJB10GS010_BOND14 | 70mm2 1C Cu PVC/PVC GE/YE
4f90673c-82ef-53f4-8874-1ede4d47874d |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Earthing | TH000000BJB10GS010_BOND14 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
0f85c184-541f-5273-862f-379fcfaee536 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Earthing | TH000000BJB10GS010_BOND14 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
3eb83a1e-68a4-4e28-8956-d4f13805a93d |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Earthing | 0000CVA10GH010-E01
126847e9-a4f9-47d9-9e0c-34a72541f92f |  | checklist-flat | work-in-progress | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Earthing | 0000CVA10GH010-E01 | 120mm2 1C Cu PVC/PVC GE/YE
e3545a6f-e8e0-514a-a4c4-7f9b7a9a2223 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Earthing | 0000CVA10GH010-E01 | 120mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
7e8b3428-ddfe-59fc-9f6f-624e4684a97c |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Earthing | 0000CVA10GH010-E01 | 120mm2 1C Cu PVC/PVC GE/YE | Test Results
819758a6-3cad-4ea1-b7b0-107ca5857f4e |  | checklist-flat | not-started | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP-CSB-E-003 CSB DCS & Comms | Certificate of compliance (COC)
a4002e3d-4f75-586d-b5bd-fc954bf16647 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-003 CSB DCS & Comms | Certificate of compliance (COC) | Please upload Certificate of Compliance here when complete (COC)
e0366928-b2c8-4a3d-b9a3-d4dda49b4abe |  | folder-normal | pass |  | step | TRUE | FALSE | TOP- ASB-E-002 ASB UPS B System
af3cd4e9-0042-424c-b414-466bcdd8e073 |  | folder-normal | pass |  | step | TRUE | FALSE | TOP- ASB-E-002 ASB UPS B System | Electrical Installations
eae56641-13c8-4043-86ca-c70b00255ade |  | checklist-flat | pass | Cable Pre-installation | checklist-flat | FALSE | FALSE | TOP- ASB-E-002 ASB UPS B System | Electrical Installations | Cable Pre-installation
ea3e5ee7-6877-5a96-bc83-43bb62cf7ac6 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP- ASB-E-002 ASB UPS B System | Electrical Installations | Cable Pre-installation | Cable Pre-Installation
3a561226-7ead-4b88-9c15-0c1e99a8d939 |  | checklist-flat | pass | ITR-CL-1-114 UPS Installation | checklist-flat | FALSE | FALSE | TOP- ASB-E-002 ASB UPS B System | Electrical Installations | TH000000BRA20 - 110VDC B
aa0a022e-f572-5bf1-bb6d-3a074d65fb37 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP- ASB-E-002 ASB UPS B System | Electrical Installations | TH000000BRA20 - 110VDC B | UPS Installation (Mandatory Photo)
067a8f5e-61e9-5ae5-9727-1ea1055ffa49 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP- ASB-E-002 ASB UPS B System | Electrical Installations | TH000000BRA20 - 110VDC B | Test results
9e07bbd2-9fc7-42a1-98e2-9f792a617abf |  | checklist-flat | pass | ITR-CL-1-101B Cable Supports Above Ground | checklist-flat | FALSE | FALSE | TOP- ASB-E-002 ASB UPS B System | Electrical Installations | ITR-CL-1-101B Cable Supports Above Ground
e78e6601-16f2-5ea6-b812-c1384c0131f3 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP- ASB-E-002 ASB UPS B System | Electrical Installations | ITR-CL-1-101B Cable Supports Above Ground | Cable Supports Above Ground
f2e202bb-5ca3-4295-9897-decae599efd5 |  | folder-normal | pass |  | step | TRUE | FALSE | TOP- ASB-E-002 ASB UPS B System | Cables
98e81570-f9bf-4dec-b920-1223e3429ee7 |  | folder-normal | pass |  | step | TRUE | FALSE | TOP- ASB-E-002 ASB UPS B System | Cables | 0000BRU30GH010-P01
30fe5b6e-b785-470e-88eb-40269aba47f4 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP- ASB-E-002 ASB UPS B System | Cables | 0000BRU30GH010-P01 | 4mm2 4C+E CuSn PVC/PVC
4ffd33e1-6633-51c6-8e03-bd4ccc54f583 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP- ASB-E-002 ASB UPS B System | Cables | 0000BRU30GH010-P01 | 4mm2 4C+E CuSn PVC/PVC | Low Voltage Cable
927227da-cc33-5928-a507-eeca4b9c4dd3 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP- ASB-E-002 ASB UPS B System | Cables | 0000BRU30GH010-P01 | 4mm2 4C+E CuSn PVC/PVC | Electrical Checks
22e7cb8f-e313-5a0f-aa4d-fb224581944f |  | holdpoint | pass |  |  | TRUE | TRUE | TOP- ASB-E-002 ASB UPS B System | Cables | 0000BRU30GH010-P01 | 4mm2 4C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
4dd97fec-b73a-41ca-a092-d938982b5a90 |  | folder-normal | pass |  | step | TRUE | FALSE | TOP- ASB-E-002 ASB UPS B System | Bonding
3d81132e-421d-4e47-a453-85af93294614 |  | checklist-flat | pass | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP- ASB-E-002 ASB UPS B System | Bonding | 0000BAW30-E08
ed51e2f0-c6bf-593e-987c-cd6ca445eecb |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP- ASB-E-002 ASB UPS B System | Bonding | 0000BAW30-E08 | Electrical earthing system installation
4a6dc65c-b06f-543a-beba-59b5c1e0fb02 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP- ASB-E-002 ASB UPS B System | Bonding | 0000BAW30-E08 | Test Results
e03b17df-ac64-408c-97a3-22e27e5e9f4e |  | checklist-flat | pass | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP- ASB-E-002 ASB UPS B System | Certificate of compliance (COC)
34d978cb-a455-5946-bffa-bf7be4febba3 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP- ASB-E-002 ASB UPS B System | Certificate of compliance (COC) | Please upload Certificate of Compliance here when complete (COC)
10aaa371-8c3f-480a-9132-06ed90f1065c |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power
6b6ce78b-36e5-40af-96f3-07729dff8852 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Electrical Installations
2cee4f9a-feb5-43c5-af8b-2aec58ac0c0f |  | checklist-flat | not-started | Cable Pre-installation | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | Cable Pre-installation
aa7cad67-61c9-5f1d-8ba4-bacd41a4b844 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | Cable Pre-installation | Cable Pre-Installation
dc6d54c7-429b-474f-ad13-43635dfdff17 |  | checklist-flat | not-started | ITR-CL-1-114 UPS Installation | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-114 Entec - UPS Installation
0544e939-ea59-5861-9e0b-c6dc923a0a23 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-114 Entec - UPS Installation | UPS Installation (Mandatory Photo)
49123a6a-c009-5ae5-b8a1-2dce70027597 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-114 Entec - UPS Installation | Test results
24cfa9e7-3e43-4893-aaf9-9283c2ec2ed6 |  | checklist-flat | not-started | ITR-CL-1-101B Cable Supports Above Ground | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-101B Cable Supports Above Ground
6db6460b-542a-58d7-8a16-2a55a13d2232 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-101B Cable Supports Above Ground | Cable Supports Above Ground
c7b27aba-5bfc-4815-bd73-9a1fc77d6f18 |  | checklist-flat | not-started | ITR-CL-1-101A Conduit/Ducting Below Ground | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-101A Conduit/Ducting Below Ground
9616413d-1192-5ba9-b666-fe4781db3885 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-101A Conduit/Ducting Below Ground | Conduit/Ducting Installation Below Ground
dec8c3ae-dc18-4983-99ff-58a7318405fb |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-111 Electrical earthing
ce2b4cc9-7fcd-505b-acf5-2376bcc947fa |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-111 Electrical earthing | Electrical earthing system installation
8ae4e794-f847-5c1f-ae65-725bec155089 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-111 Electrical earthing | Test Results
7454f03e-0a0c-4b5a-82a6-dd9f3e537005 |  | checklist-flat | not-started | ITR-CL-1-108 Electrical Switch Rooms | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-108 - Electrical Switch Room
58cac6b8-fe14-573a-964d-2d17076921d1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-108 - Electrical Switch Room | Electrical Switchroom (Mandatory Photo)
bdeed7be-edb6-45b1-849d-3845b0248a86 |  | checklist-flat | not-started | ITR-CL-1-102 Entec - Distribution Board Installation | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-102 - Distribution Board Installation
c10be505-87c2-5772-9537-a30b99ce7193 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-102 - Distribution Board Installation | Distribution Board Installation (Mandatory Photo)
07ac3b95-a5c4-59b1-bb63-8c21cf1ecc3a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-102 - Distribution Board Installation | Test Results
cb9c9bcd-b384-5f8f-a44a-39ab3e9e9eb0 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-102 - Distribution Board Installation | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
3c877307-fd19-4c01-8a98-a27153dc19fd |  | checklist-flat | not-started | Cable Test Record | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-103 - Schedule of Test Results DB
c25946eb-115c-5d0a-8fc5-31dd2a7ac1e8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-103 - Schedule of Test Results DB | Upload completed ITR scans
56c2bd1c-a5af-4916-8ad0-942a72d596a3 |  | checklist-flat | not-started | ITR-CL-1-109 Electrical Equipment Package | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-109 Electrical Equipment Package
2b73d989-5537-5e08-8b94-8604461b6806 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-109 Electrical Equipment Package | Electrical Equipment Package
94b63c25-a903-4691-9bb1-b7f0c70c9aaf |  | checklist-flat | not-started | ITR-CL-1-100 General Electrical Equipment | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-100 General Electrical Equipment Install
a7d3fa68-cae0-5c4c-b32d-c48fe7e820f9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-100 General Electrical Equipment Install | General Electrical Equipment
b7d685e1-0a19-5f3a-ab1d-b37fc2442a03 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-100 General Electrical Equipment Install | Electrical Checks
f4fe331c-65c5-5533-bac6-f7ffa28a05eb |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-100 General Electrical Equipment Install | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
1e1f0e97-d162-49df-9dbc-32e9879ce2a8 |  | checklist-flat | not-started | ITR-CL-1-106 - Junction Box | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-106 - Junction Box
02bb0364-94b1-5998-972b-f663266d84e7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-106 - Junction Box | Junction Box
6b7e634b-0aed-4a32-ad48-a37735977f35 |  | checklist-flat | not-started | ITR-CL-1-105 Control Panel | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-105 Control Panel
9da1039e-408f-5c4e-9d8c-0668ac16e7ad |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-105 Control Panel | Control Panel
be00eeb6-bd09-54e4-818d-f15f1209df4b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-105 Control Panel | Electrical Checks
050874ee-eb85-5511-9177-f5bf117949a7 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-105 Control Panel | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
5b489a33-8192-4f96-bcdb-c8b58d97a7a7 |  | checklist-flat | not-started | ITR-CL-1-110 Generator Package (LV) | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-110 Generator Package (LV)
ecee169b-4a4b-5636-869e-0717cda1cb4b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-110 Generator Package (LV) | Generator Package (LV)
c99f1f5a-1cdf-58f0-b2a7-e32e48925cea |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-110 Generator Package (LV) | Electrical Checks
12399e34-8cc6-5ed8-aa17-08db423fbfc9 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | ITR-CL-1-110 Generator Package (LV) | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
a9040861-35e3-4577-92fb-6039eac1417c |  | checklist-flat | not-started | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | Certificate of Compliance
cc6b6555-21f6-5aad-b791-290953272a50 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Electrical Installations | Certificate of Compliance | Please upload Certificate of Compliance here when complete (COC)
1395d6bf-5fa5-4b1b-8a04-27771fc669c6 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables
847071fa-9d9b-4386-80c4-41e1054f954d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - R01
b5f31292-4d2a-4aa2-a219-c53c4e95e956 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - R01 | 630mm2 1C AL XLPE/PVC
341e10f7-32ad-53e7-a27d-f96e46d98d5c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - R01 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
d9de6b6e-2c1b-5a87-b4f4-aafbc4cdbe38 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - R01 | 630mm2 1C AL XLPE/PVC | Electrical Checks
bc896995-6b75-5556-8a25-8a96c157fba0 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - R01 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
40978dc8-8127-44ae-a039-2187ac1c31d0 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - R01
b52f67e1-baed-4560-a43f-0f0374ca3c99 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - R01 | 70mm2 1C Cu XLPE/PVC
559733a9-8cf5-5de4-8148-79bdb61bd920 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - R01 | 70mm2 1C Cu XLPE/PVC | Low Voltage Cable
3a6497c4-0fe1-5473-b943-0ee4bce1c47b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - R01 | 70mm2 1C Cu XLPE/PVC | Electrical Checks
d9db9d32-ce7a-51f7-a8c6-07986c835453 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - R01 | 70mm2 1C Cu XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
81b39281-cf6e-4fa0-b8cd-32fd98ffdd07 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - W01
31f2b16f-1965-4512-a8ca-3446aae03d3e |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - W01 | 630mm2 1C AL XLPE/PVC
67084724-74da-5d5f-b0e4-b1bff179404e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - W01 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
9444b1b5-1b27-5747-871b-44deef7d3e09 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - W01 | 630mm2 1C AL XLPE/PVC | Electrical Checks
085f670a-f81d-53f4-a267-b265f3adaebd |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - W01 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
d60bafff-e9a4-4ab5-9981-b9cd670cc286 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - W01
f7a8d6e5-369a-4e76-a8e2-a2771d94c68d |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - W01 | 70mm2 1C Cu XLPE/PVC
ba067885-1e95-56da-83c1-d25853e5721e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - W01 | 70mm2 1C Cu XLPE/PVC | Low Voltage Cable
bc9aa1a6-72d7-590d-b985-c28738e2e414 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - W01 | 70mm2 1C Cu XLPE/PVC | Electrical Checks
e0cbe1a3-802b-54cd-8d1d-35c48f38baf8 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - W01 | 70mm2 1C Cu XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
01515969-851d-4a85-8410-55992c249f4e |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - B01
3f73325e-9cb5-4314-aad2-4747d229c51b |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - B01 | 630mm2 1C AL XLPE/PVC
1df100d4-9344-524a-b00a-660964f33c01 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - B01 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
65783391-0e53-580a-a822-57635d2e620b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - B01 | 630mm2 1C AL XLPE/PVC | Electrical Checks
451476f3-ea57-56dc-bae3-ca927430fa6e |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - B01 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
e733218b-6f93-4dab-a786-d3a0046890e7 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - B01
e4b40d04-441e-4654-acfd-ec41e3967196 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - B01 | 70mm2 1C Cu XLPE/PVC
04affa4e-d97f-58e4-8842-4e44c5579179 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - B01 | 70mm2 1C Cu XLPE/PVC | Low Voltage Cable
4f46fb88-3124-58cb-999c-5865e37a63e6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - B01 | 70mm2 1C Cu XLPE/PVC | Electrical Checks
5b71271c-ff7c-5ecc-bfeb-fa1d27d5bca0 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - B01 | 70mm2 1C Cu XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
78c996eb-2a1f-4c51-82e6-5de98bdc6b47 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - R02
65966153-60b8-429f-b9d8-c6652d7f397f |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - R02 | 630mm2 1C AL XLPE/PVC
016ec70d-d0bb-502d-9f95-c0adac9580e1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - R02 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
3e47eb44-76ee-58f4-abf0-8a0d5b9f60ff |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - R02 | 630mm2 1C AL XLPE/PVC | Electrical Checks
c0b7305c-387f-5b26-9418-74ed5629ebd6 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - R02 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
b4b10c1e-2d01-441f-87dd-609f44340f24 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - N01
4975d6f5-9c18-453c-bb67-568904aa5c8a |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - N01 | 70mm2 1C Cu XLPE/PVC
cd95e17a-815e-50ff-b42b-64b2bdbbc7a6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - N01 | 70mm2 1C Cu XLPE/PVC | Low Voltage Cable
7f1ac175-4ef4-5e92-b31d-fbbf496a9ba1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - N01 | 70mm2 1C Cu XLPE/PVC | Electrical Checks
79bad90b-f200-5255-9e22-77afc1a3362d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - N01 | 70mm2 1C Cu XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
1b808edb-a266-4bc5-812f-e6a612593a10 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - W02
25ac9f98-ae70-40f7-a026-e98442ebfa60 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - W02 | 630mm2 1C AL XLPE/PVC
f2e51188-5680-500d-9131-bc44c65bb7a5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - W02 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
e414de26-8391-597b-8af3-a9372b1cde23 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - W02 | 630mm2 1C AL XLPE/PVC | Electrical Checks
1a005da2-6b0b-59d1-8f89-e85eff439a4e |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - W02 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
39d9f7b9-add1-43f1-af2b-d2618bad3306 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - E01
9083c912-ed84-4b22-869c-2c7ec51835a6 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - E01 | 70mm2 1C Cu XLPE/PVC
b6b5124f-536f-504b-aaf9-74541eb2287a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - E01 | 70mm2 1C Cu XLPE/PVC | Low Voltage Cable
bdc12f37-d6f5-5d5a-8428-509ffbc11123 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - E01 | 70mm2 1C Cu XLPE/PVC | Electrical Checks
ebad3661-2c29-5598-9c17-a95d6e1b7b21 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F34 - E01 | 70mm2 1C Cu XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
4d01096d-4170-48ef-b963-9d97372703d1 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - B02
5dc59ef1-b3c1-4bba-a020-a1cae79b2178 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - B02 | 630mm2 1C AL XLPE/PVC
448ba78a-16aa-5c8d-a5ae-a74e70c8c480 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - B02 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
f1bebce4-418c-5d15-8485-10647d4dce4c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - B02 | 630mm2 1C AL XLPE/PVC | Electrical Checks
3abb1056-dc56-5c38-be1b-0d2412555d84 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - B02 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
cc8a4d78-8b6a-49a5-a392-67075627cbd8 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - R03
3eb24632-f784-4a5d-991a-4a581152c60e |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - R03 | 630mm2 1C AL XLPE/PVC
2a5c26f8-5552-5134-809d-f606f2dfac19 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - R03 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
89a79aab-62d1-5497-be99-e52a85af0ffa |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - R03 | 630mm2 1C AL XLPE/PVC | Electrical Checks
87f00207-0a43-5f1f-8ae1-51781ad63435 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - R03 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
dbaf9516-a964-408d-85a2-801f3094f7c9 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - W03
32003f84-70b4-4c6d-8909-0a2b75fd4160 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - W03 | 630mm2 1C AL XLPE/PVC
590e23cc-8347-51e3-ad3f-c98196dd22dd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - W03 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
306f1477-769a-5548-ae3c-f61cee3ecf13 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - W03 | 630mm2 1C AL XLPE/PVC | Electrical Checks
604ba99f-b7f7-5203-af14-a0d41fef5ee1 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - W03 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
7524243e-8e8f-42e1-9f86-28d0d5ca042f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - B03
92ef2fb8-337e-4555-a268-e7464b7995af |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - B03 | 630mm2 1C AL XLPE/PVC
52c5c4fc-d13e-536e-a19c-d2e6b6dd602e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - B03 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
b6f92ebc-b17d-55a9-9b1b-c2ad511844b0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - B03 | 630mm2 1C AL XLPE/PVC | Electrical Checks
7ec8b9da-cfd3-53c7-b0e8-eae37b036034 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - B03 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
76ed81c4-0bb4-4a08-bc41-20b43d14ab92 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - N01
56147b2c-4aab-491c-8ec4-96d52f849426 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - N01 | 630mm2 1C AL XLPE/PVC
a5d9ae89-d57c-5c5d-be80-8834983977a8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - N01 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
e931f711-31c2-52a4-950f-b402ea615a61 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - N01 | 630mm2 1C AL XLPE/PVC | Electrical Checks
d5a599e4-ed5b-58e7-896d-da768a913e59 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - N01 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
e9bcccc7-568d-46c4-ad70-716ec7951f47 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - N02
79dc6f87-62ac-48a9-a82d-7452b6a68869 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - N02 | 630mm2 1C AL XLPE/PVC
65995b30-6e40-537d-9375-841b9132e648 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - N02 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
ffd629bb-6eee-55d2-afa4-a83ec690bb33 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - N02 | 630mm2 1C AL XLPE/PVC | Electrical Checks
2b10642c-2f78-5a54-aee3-bca97559dcf1 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F01 - N02 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
bbd61141-58a4-4544-985a-461cf05f647d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_F01 - N03
880eaa4f-2bdc-4a7e-a049-1aed5c74431a |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_F01 - N03 | 630mm2 1C AL XLPE/PVC
a487397f-5c49-5bc1-969a-cd26e36e5ec0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_F01 - N03 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
d7aad6f7-a2ad-5067-8bae-32d9231c8e23 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_F01 - N03 | 630mm2 1C AL XLPE/PVC | Electrical Checks
f8924997-fb69-501b-b70c-2db9be44d67b |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_F01 - N03 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
a4dc71d5-55ba-466e-a2f1-83d5a113b2c6 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - R01
a1d98776-1721-46be-abf1-8dd59d5cfa5b |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - R01 | 630mm2 1C AL XLPE/PVC
ae4c89f0-4457-59b8-8304-1897ebf33f13 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - R01 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
4ce4d202-140f-5e9c-a1e5-d12ee4608c7d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - R01 | 630mm2 1C AL XLPE/PVC | Electrical Checks
c3aab0d4-dd2a-52b1-9c3f-35ad5ff31853 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - R01 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
14fc2428-8424-4113-82cb-e335c7c25638 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - W01
c21c5140-6a5c-43c7-9e3a-36e0d8d3af92 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - W01 | 630mm2 1C AL XLPE/PVC
9e07c3e5-ba5e-5429-81dc-2c32f72de25c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - W01 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
3fdad768-b4db-51a1-8d18-fda700871c22 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - W01 | 630mm2 1C AL XLPE/PVC | Electrical Checks
4bd9ace0-8fcb-513b-bd21-35ec105043c1 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - W01 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
d0237bee-3ddc-4095-a933-6dd702481b29 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - B01
9c3b09db-613f-4bb7-9855-9fba5a0a4b37 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - B01 | 630mm2 1C AL XLPE/PVC
796110af-e1bf-5342-8784-5396b1308209 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - B01 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
0bfa0595-d590-59f6-8291-1dccba55807e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - B01 | 630mm2 1C AL XLPE/PVC | Electrical Checks
97687196-d82a-59ff-b44a-30c0b2d5b362 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - B01 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
c83ea12d-2aa3-4996-b4e7-fe9ba4708241 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - R02
fefee16e-c2ef-45fb-b652-8081e33622e0 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - R02 | 630mm2 1C AL XLPE/PVC
b5e1bf4f-2944-5872-9c6a-8654fcad3396 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - R02 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
0028d011-94c7-58f4-9865-c0b6610aca70 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - R02 | 630mm2 1C AL XLPE/PVC | Electrical Checks
2dba1193-7d14-594d-a16f-f5537d000b16 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - R02 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
fdc2f7ea-766b-4b53-a40b-6d21ec0002b1 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - W02
d2f1a0ab-a383-418b-a959-0f670a8d912f |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - W02 | 630mm2 1C AL XLPE/PVC
b2707e60-cea4-551d-be1d-15a15c02ef98 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - W02 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
5d015640-5608-59c5-9ea3-516f776d2070 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - W02 | 630mm2 1C AL XLPE/PVC | Electrical Checks
4f26703d-522a-5758-8d0e-37086d2917cf |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - W02 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
314d4f8b-f843-484a-840c-4508f89b6177 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - B02
7c8278c5-2de2-43b3-9e66-c462b04ef26b |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - B02 | 630mm2 1C AL XLPE/PVC
261b4479-28ef-5ac6-9690-63635247e085 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - B02 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
acdd2bb4-069d-5ef6-bb41-b707bffd2f23 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - B02 | 630mm2 1C AL XLPE/PVC | Electrical Checks
29220473-214c-558d-9426-b1eec61ea845 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - B02 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
288ae242-9961-4e01-ad94-b0c0a57ea0c2 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - N02
d4dd9cf2-ac6a-4b13-b262-92ea93781664 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - N02 | 630mm2 1C AL XLPE/PVC
6223fae1-54e6-52cb-9ed2-9050b37225eb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - N02 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
d069ebf1-fc2a-5bef-b678-7da8cd727b23 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - N02 | 630mm2 1C AL XLPE/PVC | Electrical Checks
d361a744-1492-59df-b63b-b3c2fd695424 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - N02 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
46974061-205c-41f2-bcd9-90bee9aa0615 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - N03
ed7495be-347a-42dc-9662-f6696296932c |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - N03 | 630mm2 1C AL XLPE/PVC
4fa10521-0931-5f5c-ad21-f096517af1f2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - N03 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
1f2b107e-72a1-5119-9c96-e376c4ef37e3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - N03 | 630mm2 1C AL XLPE/PVC | Electrical Checks
f2bb8fda-42a7-5d49-ac48-59a9e130e974 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F05 - N03 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
566f9920-f85e-47ad-b3fa-60470e33ab8e |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F40 - R01
00d866c1-bab9-4f26-93a9-9782754c4e05 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F40 - R01 | 240mm2 1C Cu XLPE/PVC
9147d24a-2fee-54e8-b97e-bb1d553844df |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F40 - R01 | 240mm2 1C Cu XLPE/PVC | Low Voltage Cable
2d42ddf9-a068-5549-8567-9cbc1400d871 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F40 - R01 | 240mm2 1C Cu XLPE/PVC | Electrical Checks
8085f5c8-8b6a-5a03-9fe4-409b8bf9d38a |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F40 - R01 | 240mm2 1C Cu XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
047b2185-43df-4f75-8a94-4f1c4afb76a0 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F40 - W01
4897a1d2-d405-4354-ab8a-f7fefc0006e7 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F40 - W01 | 240mm2 1C Cu XLPE/PVC
31fc5b94-53f4-5395-bda8-7e5527a1387b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F40 - W01 | 240mm2 1C Cu XLPE/PVC | Low Voltage Cable
08a10130-8132-501e-b878-81b2fb700b31 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F40 - W01 | 240mm2 1C Cu XLPE/PVC | Electrical Checks
d058fabe-52a6-5d51-b333-21e788650506 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F40 - W01 | 240mm2 1C Cu XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
d3e3a149-424a-4722-9324-1e904ea94d2b |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F40 - B01
7ee3fd8e-3dac-4a09-ba86-82347e6891c2 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F40 - B01 | 240mm2 1C Cu XLPE/PVC
80f5b4ba-df77-5ca0-be11-0852012293b8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F40 - B01 | 240mm2 1C Cu XLPE/PVC | Low Voltage Cable
5a9d344e-850d-5167-8f7b-996d05b1c54b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F40 - B01 | 240mm2 1C Cu XLPE/PVC | Electrical Checks
8334b860-bfa2-5d50-8104-cd75015e679a |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F40 - B01 | 240mm2 1C Cu XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
f7a0bf17-5856-43e0-bde8-369684d8b299 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F40 - N01
a9e2f030-0a94-465c-8296-28818e20ddf2 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F40 - N01 | 240mm2 1C Cu XLPE/PVC
e8eb2962-d349-501a-8e7a-d8fad7485126 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F40 - N01 | 240mm2 1C Cu XLPE/PVC | Low Voltage Cable
4d2d0379-89e0-5884-91fa-e6c47a524c90 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F40 - N01 | 240mm2 1C Cu XLPE/PVC | Electrical Checks
531e5a2d-8ab6-555c-a7cb-bcb78a293174 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB10GS010_-F40 - N01 | 240mm2 1C Cu XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
a725019b-6713-4e7b-ab16-e9c66d049a6d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB20GS010_-F05-P01
3e6cf5f7-0bbc-4688-9daa-40380418bbd5 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB20GS010_-F05-P01 | 2.5mm2 2C+E CuSn PVC/PVC
45b3fc8b-e047-5b30-968c-cee45f9f4c90 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB20GS010_-F05-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Low Voltage Cable
e904c7d0-a0e2-5163-98a5-5dcf2c62464f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB20GS010_-F05-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Electrical Checks
80276ff3-4911-58e7-a2cd-1c0c2ae5c185 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Cables | TH000000BJB20GS010_-F05-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
fb1a0963-ea02-4c04-bf53-38854ce09a81 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Earthing
79d38683-103b-4360-8b8e-35b1026c2da8 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_F01 _E01
fa344981-7ba9-4072-b67e-2cb91b095d32 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_F01 _E01 | 120mm2 1C Cu PVC/PVC GE/YE
55b05abf-e05d-599c-8ad1-8fe5186265a3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_F01 _E01 | 120mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
61f44f47-d36f-5c3b-94e3-84d722ed12b0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_F01 _E01 | 120mm2 1C Cu PVC/PVC GE/YE | Test Results
6febf8ea-f84e-4a35-ac04-e7ec043cb976 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_-F05 - E01
170a6de9-2747-455d-96d0-aad142192ca1 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_-F05 - E01 | 120mm2 1C Cu PVC/PVC GE/YE
3b3fca3b-76d3-5ff8-b01d-08fdd658dabc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_-F05 - E01 | 120mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
72571303-e188-5fa4-8301-db9742ae2f9d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_-F05 - E01 | 120mm2 1C Cu PVC/PVC GE/YE | Test Results
075b1beb-6bd8-4355-a6de-1c94c15512d0 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_-F40 - E01
d31f9840-eb9f-4ba8-a1cf-bdda94c176d3 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_-F40 - E01 | 95mm2 1C Cu PVC/PVC GE/YE
7375aa28-bae4-5f3f-a937-ffa19dfadd99 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_-F40 - E01 | 95mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
c429edfb-5f8b-5800-b70f-41c7eff6042b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_-F40 - E01 | 95mm2 1C Cu PVC/PVC GE/YE | Test Results
9daa8929-f8c8-4148-8165-b5009dfcd44b |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND01
8ce90b9b-39f2-4d31-b3bd-cf3519cd1863 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND01 | 240mm2 1C Cu PVC/PVC GE/YE
083962b1-b175-53b2-89c9-dcbc4928600f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND01 | 240mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
65d0a533-1866-591c-9c92-4fd25d5f6c48 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND01 | 240mm2 1C Cu PVC/PVC GE/YE | Test Results
e96255fa-3c48-4313-942b-f208503a3566 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND02
662d2035-65da-4b65-8d9e-eb647cdd1247 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND02 | 240mm2 1C Cu PVC/PVC GE/YE
9d24f6ab-ea4b-5a8a-87ef-2d7fb3a05c07 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND02 | 240mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
b500b5f6-c7e5-5ae7-9526-ec21c39b2390 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND02 | 240mm2 1C Cu PVC/PVC GE/YE | Test Results
e14c4685-128a-48f9-8cae-b4711d51113e |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND03
94afee65-094b-4d81-b8ac-422e6c237541 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND03 | 70mm2 1C Cu PVC/PVC GE/YE
1af0cfad-8b91-5e10-91c2-36ed53feb44b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND03 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
60a9f0f3-a27f-588e-a8a1-9debe5500a1b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND03 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
dc358e5e-7b62-47bd-8093-ad85df204830 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND04
85a25344-3514-4ed3-a0d3-4bc9e2d6793e |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND04 | 70mm2 1C Cu PVC/PVC GE/YE
53c4e6d2-808d-50b1-a3b9-bc80aa306a0f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND04 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
07a3357f-bb51-50ab-80d7-672c2f984c6b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND04 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
f915c7c9-9fb7-4754-b72a-ddd1a5bcb654 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND17-1
41169b7d-ddef-4fac-b7e7-8b64a7e0d298 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND17-1 | 240mm2 1C Cu PVC/PVC GE/YE
beaaf38a-781e-57d9-a80a-bed3009f8ec0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND17-1 | 240mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
73f2be59-f6f7-5bad-abeb-57357d39027c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND17-1 | 240mm2 1C Cu PVC/PVC GE/YE | Test Results
361eeeb4-5165-49f5-ae79-8b3c91db82d4 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND17-2
c905f017-77a9-46b0-9682-8eb9aca8ba21 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND17-2 | 240mm2 1C Cu PVC/PVC GE/YE
82027b83-cd42-5623-9296-808281fee910 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND17-2 | 240mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
9f04e7a1-ad57-549b-9421-c317e4e2aed6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND17-2 | 240mm2 1C Cu PVC/PVC GE/YE | Test Results
9adbacd9-7939-472f-b001-93af2f88fd56 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND18
2c422196-6461-455c-9a36-d80a5d8cc4bb |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND18 | 70mm2 1C Cu PVC/PVC GE/YE
af9bd7e2-17b9-55bf-ac28-b3bd047dccaf |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND18 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
6e7f551a-bf3e-5cd7-975c-d7fe52464412 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Earthing | TH000000BJB10GS010_BOND18 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
3ab645a2-4c70-4236-8b79-d59c7cbb3608 |  | checklist-flat | not-started | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP-CSB-E-001 CSB LV Power | Certificate of compliance (COC)
8b5e5a35-3a75-5f2d-925d-8f697da5dcfe |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-001 CSB LV Power | Certificate of compliance (COC) | Please upload Certificate of Compliance here when complete (COC)
e37ece37-14e5-4092-bf69-6079b1bc1df2 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-007 CSB UPS A&B
dd0fc34a-17be-4b09-a32b-4633e4e1c2bb |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Electrical Installations
59595db2-e8ca-45d2-8566-01db27a66f84 |  | checklist-flat | pass | Cable Pre-installation | checklist-flat | FALSE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Electrical Installations | Cable Pre-installation
8d8ded59-d0e3-522d-8a02-08243fa23f98 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Electrical Installations | Cable Pre-installation | Cable Pre-Installation
340580a0-c116-4cc5-b0c0-bf0832ba802b |  | checklist-flat | pass | ITR-CL-1-101B Cable Supports Above Ground | checklist-flat | FALSE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Electrical Installations | ITR-CL-1-101B Cable Supports Above Ground
b2aad99a-f608-5a19-aba3-15b38ded14fe |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Electrical Installations | ITR-CL-1-101B Cable Supports Above Ground | Cable Supports Above Ground
08e48460-7584-468c-bc74-08639dbfdd02 |  | checklist-flat | pass | ITR-CL-1-114 UPS Installation | checklist-flat | FALSE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Electrical Installations | TH000000BRA10 - 110VDC/230VAC UPS
6c503f00-da2e-54cb-8960-f05b0a43447a |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Electrical Installations | TH000000BRA10 - 110VDC/230VAC UPS | UPS Installation (Mandatory Photo)
d015a752-c437-525a-a39a-d9af139f5d61 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Electrical Installations | TH000000BRA10 - 110VDC/230VAC UPS | Test results
1983086c-bc6e-413e-8cc3-4ddf0da399c3 |  | checklist-flat | work-in-progress | ITR-CL-1-100 General Electrical Equipment | checklist-flat | FALSE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Electrical Installations | TH000000BTA10 - Battery A Fuse Box
d482a573-74ca-5960-a29b-8670e7de8960 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Electrical Installations | TH000000BTA10 - Battery A Fuse Box | General Electrical Equipment
76e3b9fa-6b4d-5e2b-84a9-73f628e55b1c |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Electrical Installations | TH000000BTA10 - Battery A Fuse Box | Electrical Checks
ced23424-b3ab-55c2-be78-82b11fc20e14 |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Electrical Installations | TH000000BTA10 - Battery A Fuse Box | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
e7335a71-ee50-4f24-ba40-2b95c3eca212 |  | checklist-flat | pass | ITR-CL-1-114 UPS Installation | checklist-flat | FALSE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Electrical Installations | TH000000BRB10 - 110VDC/230VAC UPS
555f2833-9204-5dff-b91d-f00aa1f6f48e |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Electrical Installations | TH000000BRB10 - 110VDC/230VAC UPS | UPS Installation (Mandatory Photo)
f2c226e4-3762-58fa-825c-9ffe148defae |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Electrical Installations | TH000000BRB10 - 110VDC/230VAC UPS | Test results
a03dc611-ef39-4822-b052-57726896291b |  | checklist-flat | work-in-progress | ITR-CL-1-100 General Electrical Equipment | checklist-flat | FALSE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Electrical Installations | TH000000BTB10 - Battery B Fuse Box
6112632a-7c17-5bbb-af66-ce3440329b7e |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Electrical Installations | TH000000BTB10 - Battery B Fuse Box | General Electrical Equipment
c2fd72ce-71f8-592c-83b9-6e85906bf7ba |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Electrical Installations | TH000000BTB10 - Battery B Fuse Box | Electrical Checks
6146b7fb-4a55-5ea0-b1ea-fbd5b7f2ecd7 |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Electrical Installations | TH000000BTB10 - Battery B Fuse Box | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
65985e64-f794-42bd-b65b-4579e836ff5d |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Cables
81c45121-6023-41bf-87f4-f85798278f1d |  | folder-normal | pass |  | step | TRUE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GR010-P01
6733ffa8-3770-4de5-a617-ae3e954d3be4 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GR010-P01 | 150mm2 1C Cu XLPE/PVC
edbba171-29c7-5381-ad58-021f69851e1f |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GR010-P01 | 150mm2 1C Cu XLPE/PVC | Low Voltage Cable
87a65c91-f1b1-5849-a753-a28654f3bba5 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GR010-P01 | 150mm2 1C Cu XLPE/PVC | Electrical Checks
445ec77a-47df-59e8-a6a4-aa2f90434028 |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GR010-P01 | 150mm2 1C Cu XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
3810c585-f488-4837-a1c7-2970af21d261 |  | folder-normal | pass |  | step | TRUE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GR010-P02
d7103916-64c6-44d7-bf8c-b9c65327b532 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GR010-P02 | 150mm2 1C Cu XLPE/PVC
db5602a1-a808-5f78-8917-967fefa75b8b |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GR010-P02 | 150mm2 1C Cu XLPE/PVC | Low Voltage Cable
9cb37458-faa1-5dbc-91e2-55b983b1b2ed |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GR010-P02 | 150mm2 1C Cu XLPE/PVC | Electrical Checks
01f1246d-51be-5a70-af4e-c7c30d4cc215 |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GR010-P02 | 150mm2 1C Cu XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
2e86b7b9-da52-4c23-9477-7962cfb14c28 |  | folder-normal | pass |  | step | TRUE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GR010-P01
c5b13452-da9d-4acd-a2d1-16965b14048e |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GR010-P01 | 150mm2 1C Cu XLPE/PVC
97a3c30c-d627-50a2-9f42-f0be1f056d2b |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GR010-P01 | 150mm2 1C Cu XLPE/PVC | Low Voltage Cable
046a55a7-4b85-534f-b3ed-660bfd5efc0c |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GR010-P01 | 150mm2 1C Cu XLPE/PVC | Electrical Checks
d19cc4f5-8a4b-5c68-821f-d054a77e484e |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GR010-P01 | 150mm2 1C Cu XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
5055ae00-2978-4c1e-bb0c-c4772d6bb081 |  | folder-normal | pass |  | step | TRUE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GR010-P02
37f156c0-ff1b-4fae-ba8a-30ce93c17800 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GR010-P02 | 150mm2 1C Cu XLPE/PVC
42944a51-74f2-56ae-a245-fa9209a574c3 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GR010-P02 | 150mm2 1C Cu XLPE/PVC | Low Voltage Cable
cdf3bf54-8198-52b4-a120-49a68a1a6f3e |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GR010-P02 | 150mm2 1C Cu XLPE/PVC | Electrical Checks
169c8f12-7722-5485-abc1-f16559433889 |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GR010-P02 | 150mm2 1C Cu XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
fddbca7c-142c-4dbc-bb8b-e4fe561f3366 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GH010-P01
b9ff4f36-a08a-4bdb-b6eb-af76115c451b |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GH010-P01 | 16mm2 4C+E CuSn PVC/PVC
249ccead-2cf6-5f03-957a-f587c6d9ef93 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GH010-P01 | 16mm2 4C+E CuSn PVC/PVC | Low Voltage Cable
ddc04576-bb9c-567b-a117-cb2f152b4694 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GH010-P01 | 16mm2 4C+E CuSn PVC/PVC | Electrical Checks
4543e537-25f2-5577-b623-37431d7c448b |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GH010-P01 | 16mm2 4C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
3e14b675-70f5-4944-a64e-9d9ce2aacfb4 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GH010-P01
6c01a9d0-be33-459e-9973-039ff0a68681 |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GH010-P01 | 16mm2 4C+E CuSn PVC/PVC
37b76a6a-7169-59de-b0a2-103425d050a5 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GH010-P01 | 16mm2 4C+E CuSn PVC/PVC | Low Voltage Cable
a34563f6-60ab-52c6-8e38-c70b8cd6a681 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GH010-P01 | 16mm2 4C+E CuSn PVC/PVC | Electrical Checks
bb1360b4-771a-5880-9611-2b39f0a7834d |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GH010-P01 | 16mm2 4C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
fa7d6c54-ec4c-490b-9bb6-8836a0dd0f33 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GH020-P01
8ab11070-c06a-4e04-8dac-e01d9e8d0434 |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GH020-P01 | 16mm2 4C+E CuSn PVC/PVC
9eaf7862-6869-59f8-b5e6-0e8a2c64c943 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GH020-P01 | 16mm2 4C+E CuSn PVC/PVC | Low Voltage Cable
ded012a7-d209-501b-8de8-f35e59866393 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GH020-P01 | 16mm2 4C+E CuSn PVC/PVC | Electrical Checks
43bdc1b1-66ba-58b1-b25e-5df2cde2c339 |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GH020-P01 | 16mm2 4C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
b595e256-4357-4875-b001-c17d0e7ad698 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GH020-P01
6aef33d1-a6b7-4a9c-aaf8-f2e5276775ad |  | checklist-flat | work-in-progress | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GH020-P01 | 16mm2 4C+E CuSn PVC/PVC
987ca1da-60cf-5e32-825e-b85937372fd9 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GH020-P01 | 16mm2 4C+E CuSn PVC/PVC | Low Voltage Cable
dae4d47a-3bbe-5924-b620-a6cfcbf8f28f |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GH020-P01 | 16mm2 4C+E CuSn PVC/PVC | Electrical Checks
e22507b4-e919-5bd7-bcf4-cab2ea931afb |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GH020-P01 | 16mm2 4C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
5939f7b0-098b-4e16-a35b-7e3878f49847 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GR010-N01
34e5bf25-dd7f-4b03-8686-6488d2c06c7e |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GR010-N01 | CAT 5E
ef8e8014-4fa3-563e-b8ce-c7edf5857381 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GR010-N01 | CAT 5E | Low Voltage Cable
6f81e61c-5463-523a-9fab-14cdbfddb254 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GR010-N01 | CAT 5E | Electrical Checks
2b5341f4-9f0f-54fc-84bf-cb39122f1dd8 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU20GR010-N01 | CAT 5E | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
7d7f933d-cf1d-4bae-bf55-4016ab245ac0 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GR010-N01
5961261a-b4c9-4023-8ee9-b0fe6be5ad00 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GR010-N01 | CAT 5E
ea597130-8d93-5f15-8756-a18dd7d99e9c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GR010-N01 | CAT 5E | Low Voltage Cable
7327f119-ce66-5f22-953a-9b3609d9f20f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GR010-N01 | CAT 5E | Electrical Checks
2a9dfd0e-9279-5c32-8da8-4a6dc78d4893 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Cables | 0000BRU10GR010-N01 | CAT 5E | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
9e6954d6-5492-4d4b-9a82-173d046dd919 |  | folder-normal | pass |  | step | TRUE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Earthing
3ff504ad-8d8f-43c7-bedc-b8c28488c476 |  | folder-normal | pass |  | step | TRUE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E01
fdc1cd8f-a571-4222-bfd9-78684636efa2 |  | checklist-flat | pass | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E01 | 70mm2 1C Cu PVC/PVC GE/YE
701882d2-8a34-5923-95af-223e6fbe4971 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E01 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
b063d84f-3e1b-5f4d-9b4b-caa72776bb84 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E01 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
2f7fc24a-9604-48cc-ab9d-406defdd4bd9 |  | folder-normal | pass |  | step | TRUE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E02
6e167463-5ef8-4763-8231-18a2e6ddc904 |  | checklist-flat | pass | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E02 | 70mm2 1C Cu PVC/PVC GE/YE
fd80abd5-f423-511c-a079-273cbea1ffa0 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E02 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
188f649a-1e21-5ac8-82e0-2062218018d9 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E02 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
ea5615c4-6d7d-4990-980b-1e13dd392ac0 |  | folder-normal | pass |  | step | TRUE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E03
94b2c419-46a7-431c-bcf4-a98c564f99cf |  | checklist-flat | pass | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E03 | 70mm2 1C Cu PVC/PVC GE/YE
3ad6bde9-b3b0-5655-819c-ffa9e06bb7ff |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E03 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
733901c8-35d8-5d54-b5ce-b783ade53d8b |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E03 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
cf8911be-540d-46fd-a884-64af2f92823f |  | folder-normal | pass |  | step | TRUE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E04
6fb6cd31-f656-4883-b7ce-455af5936373 |  | checklist-flat | pass | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E04 | 70mm2 1C Cu PVC/PVC GE/YE
b8319de8-d5d8-5e62-9a50-43910b3cafe4 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E04 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
25482eba-1d5d-5f3b-88e1-cc74f3099bed |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E04 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
0aa49df2-49d3-4dd9-a05a-dd36ed663f15 |  | folder-normal | pass |  | step | TRUE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E10
dcb57c96-3dea-4bfd-b291-f04fffd2ae7f |  | checklist-flat | pass | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E10 | 70mm2 1C Cu PVC/PVC GE/YE
ff85d56a-5f7e-5375-b4b7-7b8c3af60129 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E10 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
bba96c7c-1150-5803-aa73-e913bf57d243 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E10 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
98a50e6c-c619-4cdb-a4b1-90c7f9eb89c2 |  | folder-normal | pass |  | step | TRUE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E11
c3025809-9b2e-46ec-8fd8-96d79a275c5b |  | checklist-flat | pass | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E11 | 70mm2 1C Cu PVC/PVC GE/YE
4cef58ec-6a10-5948-aaf1-f36cd2641b96 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E11 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
fcdf23d1-673f-5a1e-bfa9-e504b6956481 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E11 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
c4b48001-be78-44b6-86f1-c6e0e667ca7f |  | folder-normal | pass |  | step | TRUE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E12
89849eff-a516-4a4f-9c0f-b0377931f3ed |  | checklist-flat | pass | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E12 | 70mm2 1C Cu PVC/PVC GE/YE
f2c75f1b-627a-5221-8fa8-2df21ec71f4e |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E12 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
f1a6c268-2679-5bcf-9bf9-5353a59eb3ca |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Earthing | 0000BAW40-E12 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
f59ed0fd-58b7-4f20-94f1-b3560b4d5fe6 |  | checklist-flat | pass | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP-CSB-E-007 CSB UPS A&B | Certificate of compliance (COC)
38a6cc44-c4c6-5313-b234-dfbc35c0443a |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-CSB-E-007 CSB UPS A&B | Certificate of compliance (COC) | Please upload Certificate of Compliance here when complete (COC)
a40dfc17-c1f6-4a1f-bc0a-18bc2a45bfa7 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power
85503270-88fe-4f17-bf11-c8b490be64b0 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Electrical Installations
6f431c63-a07d-44b0-96c8-670150bcccef |  | checklist-flat | not-started | Cable Pre-installation | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Electrical Installations | Cable Pre-installation
ff487b99-4981-5625-ac60-408de02217b7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Electrical Installations | Cable Pre-installation | Cable Pre-Installation
39fd4894-f2a1-497c-b48a-2663f0c6c103 |  | checklist-flat | not-started | ITR-CL-1-101B Cable Supports Above Ground | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Electrical Installations | ITR-CL-1-101B Cable Supports Above Ground
572807b1-fb7f-528d-b0ae-e494f93b4acf |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Electrical Installations | ITR-CL-1-101B Cable Supports Above Ground | Cable Supports Above Ground
ae379d5f-6d2b-4eb4-94f8-b10f7d61ffd0 |  | checklist-flat | not-started | ITR-CL-1-101A Conduit/Ducting Below Ground | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Electrical Installations | ITR-CL-1-101A Conduit/Ducting Below Ground
ca3efdec-039c-5a07-a40f-14576c5abae1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Electrical Installations | ITR-CL-1-101A Conduit/Ducting Below Ground | Conduit/Ducting Installation Below Ground
a15eeafe-a28d-4d12-936f-fae0cc25e40d |  | checklist-flat | not-started | ITR-CL-1-108 Electrical Switch Rooms | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Electrical Installations | ITR-CL-1-108 - Electrical Switch Room
877107d3-1787-518a-abff-3f1296c11827 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Electrical Installations | ITR-CL-1-108 - Electrical Switch Room | Electrical Switchroom (Mandatory Photo)
b58be67e-c20f-4b9c-92a5-13a2331798f4 |  | checklist-flat | not-started | ITR-CL-1-102 Entec - Distribution Board Installation | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Electrical Installations | ITR-CL-1-102 - Distribution Board Installation
906819d9-3075-51eb-b249-00f5c3d68ced |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Electrical Installations | ITR-CL-1-102 - Distribution Board Installation | Distribution Board Installation (Mandatory Photo)
b8b472c1-aa0f-5238-8c8c-45b281604299 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Electrical Installations | ITR-CL-1-102 - Distribution Board Installation | Test Results
c2a0ab29-3fed-5024-bfe2-eb562781a3c2 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Electrical Installations | ITR-CL-1-102 - Distribution Board Installation | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
4cb254e4-739d-4b77-92fa-52b21c3ac7c4 |  | checklist-flat | not-started | Cable Test Record | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Electrical Installations | ITR-CL-1-103 - Schedule of Test Results DB
ec648bac-a8d3-5c25-8266-67f83e4fd9a6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Electrical Installations | ITR-CL-1-103 - Schedule of Test Results DB | Upload completed ITR scans
4bd42f96-46cc-4556-84eb-8a72de60540a |  | checklist-flat | not-started | ITR-CL-1-109 Electrical Equipment Package | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Electrical Installations | ITR-CL-1-109 Electrical Equipment Package
6f71dcba-3aa8-5bc2-ad7c-d00566689622 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Electrical Installations | ITR-CL-1-109 Electrical Equipment Package | Electrical Equipment Package
05e1e6f4-3469-4444-b4ad-b30d2da2f106 |  | checklist-flat | not-started | ITR-CL-1-100 General Electrical Equipment | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Electrical Installations | ITR-CL-1-100 General Electrical Equipment Install
143c2820-d663-53ba-b4fd-55fa8db96272 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Electrical Installations | ITR-CL-1-100 General Electrical Equipment Install | General Electrical Equipment
25887943-3661-58bd-94ca-716bbdb6201b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Electrical Installations | ITR-CL-1-100 General Electrical Equipment Install | Electrical Checks
184efb28-df49-5b9f-8567-783059b201e8 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Electrical Installations | ITR-CL-1-100 General Electrical Equipment Install | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
19ae5832-919e-4378-b56b-ee87702b553d |  | checklist-flat | not-started | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Electrical Installations | Certificate of Compliance
6896f42c-0f3f-5277-9049-eb3bd6ff1ba0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Electrical Installations | Certificate of Compliance | Please upload Certificate of Compliance here when complete (COC)
4d091191-fdbc-4f45-957b-b8cbf8e152cc |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables
144e3355-f143-405f-bfcb-ce3bff68b331 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-R01
6386cbe7-3829-46ae-ac49-884c4402b19c |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-R01 | 630mm2 1C Al XLPE/PVC
9904d6c3-54dd-522b-9254-d56cf79e1083 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-R01 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
06ae866e-a7ed-5e31-beaf-3f0b2f9860fa |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-R01 | 630mm2 1C Al XLPE/PVC | Electrical Checks
739fe562-0e3a-59b2-9592-027d749f487d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-R01 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
f9262fa0-fb5a-435b-983f-b12cfe285227 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-W01
e86bf769-1162-4d10-81db-45408f05057b |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-W01 | 630mm2 1C Al XLPE/PVC
9da27378-527d-575d-bcc9-738911507dcb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-W01 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
5c681eb5-9618-56a2-a8f4-3cbff5f118ce |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-W01 | 630mm2 1C Al XLPE/PVC | Electrical Checks
c94f74c2-017e-5baf-8707-c802070af7b9 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-W01 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
01e41d2e-b795-4f5f-b584-1ca74d9cab8f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-B01
28270615-c60c-4119-8903-4a770f9ee823 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-B01 | 630mm2 1C Al XLPE/PVC
8bf30181-305e-50a6-a223-9f0026197f6b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-B01 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
29c5c820-448a-5100-98c5-185677fb34f2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-B01 | 630mm2 1C Al XLPE/PVC | Electrical Checks
7299b3fe-fc9e-5b65-8a6d-ce610118242f |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-B01 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
005fd428-de48-4877-aaf4-9915bda5cf1d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-R02
49f8b730-af1a-4e14-a4aa-6dcc9db8003f |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-R02 | 630mm2 1C Al XLPE/PVC
2d81c16c-3234-51a8-b50e-688159ac3cb3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-R02 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
d70181ee-7dd6-577e-ba17-ebd38973d78f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-R02 | 630mm2 1C Al XLPE/PVC | Electrical Checks
0e051241-4106-5421-9810-78ed96924990 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-R02 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
e6196c30-d90f-4763-b612-aad0357391f0 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-W02
daa64407-6855-44d8-9a5c-a4ea633056a4 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-W02 | 630mm2 1C Al XLPE/PVC
18d2aef2-b972-5d2e-82dd-21f3020df196 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-W02 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
d4ac4fdc-3a94-5d80-a343-fa56709ac21c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-W02 | 630mm2 1C Al XLPE/PVC | Electrical Checks
28dc015e-d5fd-565c-88bd-e6e20381959d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-W02 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
4e5c7637-a367-47d6-9dc3-3e82d4f8662d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-B02
147e617c-471e-47cd-9c8d-9b947c3b6a8e |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-B02 | 630mm2 1C Al XLPE/PVC
955c988d-799a-5f1f-8d30-1b753c24bb20 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-B02 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
d2e625b2-29db-57d4-9b4d-c9fa0dc1c6a1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-B02 | 630mm2 1C Al XLPE/PVC | Electrical Checks
d021f7b8-5bb9-58e2-ba2c-d70f162c2a11 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-B02 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
07e17bbd-2c82-4adf-9df0-b925a2a8ea8f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-R03
b344a839-41e6-4d75-9f3c-d50d538cb9ea |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-R03 | 630mm2 1C Al XLPE/PVC
0480367c-8145-5ba3-90e9-3060da646db3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-R03 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
654cd4d2-dcbe-5a98-a810-13619473d80c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-R03 | 630mm2 1C Al XLPE/PVC | Electrical Checks
a95680e2-c6e0-5ee5-98e5-beb13804e35a |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-R03 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
059c66c8-b921-4de1-961b-b7e1e83e5379 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-W03
ce2301da-bfa7-4b87-818d-cd55402aba9d |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-W03 | 630mm2 1C Al XLPE/PVC
e9aaebf1-e47c-58a9-8221-11b940bd75bf |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-W03 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
9d55dbf0-608d-5a22-bec6-2d19372de0e2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-W03 | 630mm2 1C Al XLPE/PVC | Electrical Checks
0c1fa865-f6ef-5c0f-bb02-681374a5e322 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-W03 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
6be6e356-4c5f-4be0-a317-7c99ee9e0331 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-B03
c675af76-d347-4d8f-b18e-e57c4db3002c |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-B03 | 630mm2 1C Al XLPE/PVC
fece5597-b93e-59a0-852a-e3d8bc24c3d7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-B03 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
10b05f3e-d568-5d92-ab8e-5a9620debabb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-B03 | 630mm2 1C Al XLPE/PVC | Electrical Checks
13b4fcb1-fbc7-5971-9dbb-69d7bf791248 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-B03 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
4c629d00-c74e-4168-9d24-3600de256882 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-N01
2ea9ecf2-7f36-4d09-85bc-6cfea58ce90c |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-N01 | 630mm2 1C Al XLPE/PVC
7a61d176-d42c-558e-93be-5a3d4c8838f6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-N01 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
47abe3d3-4754-5a43-a57b-94bce6d0d780 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-N01 | 630mm2 1C Al XLPE/PVC | Electrical Checks
99c801e8-3d40-56e4-9ed2-7c78c88bebb1 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-N01 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
7d6f93a6-98bd-43b1-96b1-6bf7fdee31e2 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-N02
9a2fa4be-ef56-46c5-9f06-a65bdd48d583 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-N02 | 630mm2 1C Al XLPE/PVC
708c5355-a975-5db1-9dba-1bf271163b1f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-N02 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
bec42e4a-d815-585f-bb66-8977e5180088 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-N02 | 630mm2 1C Al XLPE/PVC | Electrical Checks
e36e17b9-66b1-5387-822f-2726e7f666a1 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-N02 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
66189f94-2f9a-4dba-86ef-cadc7f63b7e6 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-N03
76366532-e3dd-49c0-86e6-fffdad9e4e26 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-N03 | 630mm2 1C Al XLPE/PVC
32938639-b70d-5592-9fb4-e9b516f20259 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-N03 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
b0c46683-04fe-5bc8-8ff6-d9e927b51020 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-N03 | 630mm2 1C Al XLPE/PVC | Electrical Checks
8aa41f99-4079-5ecd-9e90-a25e06a7a499 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F05-N03 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
0f95c862-441f-48f8-be89-7114a3c24078 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-R01
28e61981-423e-4ee9-bb4b-5aa7c2a2204d |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-R01 | 630mm2 1C AL XLPE/PVC
bffbe2ec-f5ad-5800-a763-ae12da2e1867 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-R01 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
a44db2f1-8aa7-5f97-928c-a6bdf8180bf1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-R01 | 630mm2 1C AL XLPE/PVC | Electrical Checks
f302ae03-552b-5233-9417-f818d5c09451 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-R01 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
cb0badef-201a-4d4f-b93a-5c24f383d0ad |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-W01
c432301e-c2c8-4a62-bb69-f13c68a4d12f |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-W01 | 630mm2 1C AL XLPE/PVC
408c0c0b-1ada-5660-88c3-6b998b780998 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-W01 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
e90811a7-4bfe-55a7-9d91-1ade4eedeee4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-W01 | 630mm2 1C AL XLPE/PVC | Electrical Checks
5f0f4a1f-8515-5e45-80dc-fe6455205cc9 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-W01 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
85892720-b08f-420b-9eba-74a79e0d8ca4 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-B01
14080be9-d340-4713-8cc8-b10100a3e2cb |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-B01 | 630mm2 1C AL XLPE/PVC
47467b45-8341-55df-bb2d-6f85ac4d5a72 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-B01 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
09ba1c60-b048-56fb-b527-5fcb26611129 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-B01 | 630mm2 1C AL XLPE/PVC | Electrical Checks
4870130c-7a94-5df0-87bf-b11c6dc52540 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-B01 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
7e573264-3cb1-4121-b6ca-823bc5310098 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-R02
d4513741-dd05-4311-b1b3-7e45b4fde36c |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-R02 | 630mm2 1C AL XLPE/PVC
06d04283-a302-51c7-b9fa-c6f0f31fab22 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-R02 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
c04eec94-9721-548b-a627-c51a13f25b0a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-R02 | 630mm2 1C AL XLPE/PVC | Electrical Checks
6d7125a8-a0ea-5b80-b587-8a0b7cf199a3 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-R02 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
58fa4ed1-55d0-4d05-acd3-d8fadd5b9dec |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-W02
326d9e1d-619e-49f7-9713-baeb3ea00386 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-W02 | 630mm2 1C AL XLPE/PVC
271b17d1-db83-5cc8-96c8-70c7dac32c3e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-W02 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
bce5b1e0-4134-57ce-9940-669116417353 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-W02 | 630mm2 1C AL XLPE/PVC | Electrical Checks
ade26577-fb85-5c50-970a-df2faa171c09 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-W02 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
65cc93e1-5b1e-4607-a6e4-25562fc570de |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-B02
507c6026-51da-47bc-a5e5-7c59501eb3d4 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-B02 | 630mm2 1C AL XLPE/PVC
fde04c0a-7634-5cac-b8de-dbd00d5a9a90 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-B02 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
b5ca4118-5133-588b-b161-2adf55f87162 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-B02 | 630mm2 1C AL XLPE/PVC | Electrical Checks
acaa7c3a-7777-5bf4-97e8-0c1b6675282b |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-B02 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
37c180fb-1317-45ed-b590-a83f08a835bc |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-N02
8dd486f0-3dfd-40bd-9056-5879094c4974 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-N02 | 630mm2 1C AL XLPE/PVC
6049b5a4-3f93-5023-8932-c73ecc453fdf |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-N02 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
5234c550-9ca9-5fdf-bcff-8765b96b5915 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-N02 | 630mm2 1C AL XLPE/PVC | Electrical Checks
65ad6cdb-abf7-52c6-921c-8fdb7254d916 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-N02 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
8b92eaa7-02e2-409b-85a0-4711f5334e1c |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-N03
ff1a614a-8e32-4a3b-b964-4e6238ebbdfb |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-N03 | 630mm2 1C AL XLPE/PVC
bb4bff46-af4e-5ffc-a404-a7906949eeee |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-N03 | 630mm2 1C AL XLPE/PVC | Low Voltage Cable
ea02bfec-7519-5b58-a5d2-28bd60a590e8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-N03 | 630mm2 1C AL XLPE/PVC | Electrical Checks
4f119930-5826-516e-a6cf-2e49025954f4 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Cables | TH000000BFA40GS010_-F09-N03 | 630mm2 1C AL XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
4c8a46b9-42ec-47c7-88e7-d895ac1d7a5d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Earthing
09d2fa8e-71aa-4b95-852b-470ccdd57d85 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Earthing | TH000000BFA40GS010_-F05-E01
ab149788-21ca-4014-a842-d5e00052d2a3 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Earthing | TH000000BFA40GS010_-F05-E01 | 240mm2 1C Cu PVC/PVC GE/YE
b1540a38-75f0-57e3-bb92-83253c20b727 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Earthing | TH000000BFA40GS010_-F05-E01 | 240mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
9e7269f0-20ce-5543-9fca-c52b206da26e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Earthing | TH000000BFA40GS010_-F05-E01 | 240mm2 1C Cu PVC/PVC GE/YE | Test Results
ee0c01f5-e2d7-4fca-9657-c2ea82e405d8 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Earthing | TH000000BFA40GS010_BOND02
f1028527-efe4-4188-87f2-b144e26cf14f |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Earthing | TH000000BFA40GS010_BOND02 | 120mm2 1C Cu PVC/PVC GE/YE
0e46693c-4550-54c9-90ae-6521cf708d8a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Earthing | TH000000BFA40GS010_BOND02 | 120mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
2371e7aa-69e2-5609-a714-10a376c23339 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Earthing | TH000000BFA40GS010_BOND02 | 120mm2 1C Cu PVC/PVC GE/YE | Test Results
5570d96d-5b88-4674-9739-4ca53c00da3c |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Earthing | TH000000BFA40GS010_BOND03
ece4c176-2ba1-4bf9-bced-ed254707d59c |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Earthing | TH000000BFA40GS010_BOND03 | 120mm2 1C Cu PVC/PVC GE/YE
ae46483f-ba7b-57c6-830f-c588f36662e5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Earthing | TH000000BFA40GS010_BOND03 | 120mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
27b89571-f0de-5c60-a4ec-75459b0eec7e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Earthing | TH000000BFA40GS010_BOND03 | 120mm2 1C Cu PVC/PVC GE/YE | Test Results
e91fc2c0-d087-4f4c-bd8d-6a3b3fed952d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Earthing | TH000000BFA40GS010_BOND04
9fcfb569-2dbd-4d37-b70c-6a7e59f1a5f1 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Earthing | TH000000BFA40GS010_BOND04 | 120mm2 1C Cu PVC/PVC GE/YE
92be925c-e666-508b-8801-8e84c6c81c0d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Earthing | TH000000BFA40GS010_BOND04 | 120mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
c8a9c494-4f52-545c-8963-4a264d120c23 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Earthing | TH000000BFA40GS010_BOND04 | 120mm2 1C Cu PVC/PVC GE/YE | Test Results
a31da313-c5a4-4b1e-88f8-f970ea57c41a |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Earthing | TH000000BFA40GS010_BOND05
ddada020-c185-41a5-90bf-b8294430d7cf |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Earthing | TH000000BFA40GS010_BOND05 | 120mm2 1C Cu PVC/PVC GE/YE
c29b490a-ad76-5d38-a93c-0a540ce46c22 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Earthing | TH000000BFA40GS010_BOND05 | 120mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
74f61302-1a12-5bbc-b35d-31cf9ce5b5f0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Earthing | TH000000BFA40GS010_BOND05 | 120mm2 1C Cu PVC/PVC GE/YE | Test Results
e0380fbf-a711-45c5-accd-b95f5bd4fc5f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Earthing | TH000000BFA40GS010_BOND06
19981010-6c4d-4d99-8bf0-e2e2fc8068e0 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Earthing | TH000000BFA40GS010_BOND06 | 120mm2 1C Cu PVC/PVC GE/YE
7f03b4fe-8feb-52a2-982c-1471c6806be2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Earthing | TH000000BFA40GS010_BOND06 | 120mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
4460ae07-31d0-505a-9345-7f2dc4eedba9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Earthing | TH000000BFA40GS010_BOND06 | 120mm2 1C Cu PVC/PVC GE/YE | Test Results
512f4093-f4e8-48d9-8713-a32605d7643f |  | checklist-flat | not-started | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP- ASB-E-001 ASB HV & LV Power | Certificate of compliance (COC)
74d4f9d0-6408-531e-8615-4d6f87a3df6d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP- ASB-E-001 ASB HV & LV Power | Certificate of compliance (COC) | Please upload Certificate of Compliance here when complete (COC)
e5718006-3256-470b-b7ab-c50713acd957 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump
3cd65e4d-208a-4e7e-95ff-ed063df85e28 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument
b563c66f-00ce-49ea-8c38-3061e078db0a |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1
6a06d0d8-68b0-4fb8-8399-27622f431f19 |  | checklist-flat | not-started | ITR-CL-1-131 Level Instrument Installation | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-131 Level Instrument Installation
82e2f3ea-a92b-5814-9d35-fb9c6512e2b7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-131 Level Instrument Installation | Level Instrument Installation
fdcc0bf7-9e05-566c-b8b9-71a9919ac468 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-131 Level Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
791ea6bc-6664-4b05-a08d-23a3228c1614 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-122 Instrument Calibration
ee6798b4-93cd-52d5-b55a-43f7128f5563 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-122 Instrument Calibration | Required Data
a3f00432-38c8-5420-98ec-624068fe1c22 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
24f3665f-9a00-502e-8e4d-3d659eb30f35 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
7eb678b0-6501-4a25-a6aa-ac21faf0a47d |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning
20288ede-9e4f-5ede-8d2e-78d116be2a47 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
a1c2b4bd-ff5d-560c-9bf8-6d68247ce140 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
39be1701-2ad0-5b24-9f7c-a9a09d4130d7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
7823a2ac-a7cb-5986-8a49-cd1132e32771 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
117628c7-d2e4-5522-9660-7adc6409d2ee |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
01a79e0c-b317-5c09-886c-37e7db160dcd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
935e8008-5ff1-5d00-917f-f595c286be75 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
2128450f-bef6-54e4-98b8-6e6a3424ed85 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
7d840d02-b1c2-52bd-a3aa-b304a7cacc41 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
1ab8055c-11cc-5b2d-b56c-cc847652c463 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
0b267975-286b-5de0-a38b-1e1f1d39c1bd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
ad5a0085-4b11-50f9-a7b6-3b32bee18842 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
b7122df9-6bea-5856-8233-f770ecf66d37 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
15e0a075-1571-5bea-be0f-8810ab8ef993 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
e7a3d99f-4efd-5b03-82e1-56a23588884f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
142b4719-245e-537e-ab84-3ba23191fbc6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
5416a116-d727-50ee-84f0-891c5bf960a5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
59547ddb-43fd-552e-a01d-32cf1784fd73 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
97ac83d8-8daf-5ad1-94a4-a2ed5842476f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
287e743d-f9c0-5feb-a3d2-059dc7a365ad |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
c6619633-e68c-57d4-9208-7cdc7c44223a |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
4635dc60-dcd7-4c26-9cd6-2d6c028671f7 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-124 Commissioning Instruments
0fa61220-5f45-5698-9f22-7ac6274eb26b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Required Data
45519977-3ab6-5033-8941-de9c22bec4b2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
302cf308-1019-5319-a8dd-24855f2b17e6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
520675ca-2683-5ec4-8b96-a7f234fa4aa4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
21570950-e960-5de4-88ef-dafa48e6cbe8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
43b45e7a-7e1e-5226-9a2a-411ea58c1bc8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
f7519844-7a9f-5b29-83ec-f55cece7b0a7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
8cce6bde-957b-5067-9826-ba3522369a0d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
9aaa5110-4074-5dc4-b91e-bfc3beffbb61 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
cbdc42a0-d9d4-50df-8d08-52287c3820e8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
f16abfdd-0a5a-5dd4-8b10-92d0b5ec4165 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
084ea773-1bab-538a-862e-23266c43c4c2 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL010 - Emergency Dump Pond, Level Transmitter 1 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
4148d5bf-04ce-4249-8016-8efa63d0af81 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2
e1e6a76b-f2f6-4cfe-89eb-6eea53bd1b17 |  | checklist-flat | not-started | ITR-CL-1-131 Level Instrument Installation | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-131 Level Instrument Installation
8aeb8688-c440-5833-8243-a1c500171de6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-131 Level Instrument Installation | Level Instrument Installation
81b2d13a-c01b-5900-963c-78d6cf0c0305 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-131 Level Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
5bd907b6-f2b4-4d33-83be-99a0166b90b3 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-122 Instrument Calibration
10a3abf5-6424-5bec-bb18-22f4e10e7c19 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-122 Instrument Calibration | Required Data
b5d8069b-62b8-5ea1-aa58-aa553f4a3fbd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
5a60792d-4dde-5f1b-b5c5-50688870b380 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
83421e1f-734d-4dee-bf37-1fd9bf166047 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning
7d6f85ba-2296-59d8-b5c9-f9dbfab6fbfd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
80bff2ed-a25b-5242-83f0-666a5227b88e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
ac21d2de-5b87-5252-ad36-5749269374fa |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
89a0d288-075b-5cf9-a258-9618eccc2a36 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
f0472380-9701-57d3-9617-470aee7d210a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
aec7a90d-89c6-5363-8cc6-9906c18f080e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
2f464639-e5cd-5893-9c20-537d002fd0ee |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
dd990488-9a24-52a3-b7a0-342ff3a40036 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
5fe625c0-edb9-59ed-ad2c-263e41f74e97 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
c4125104-acf9-517b-95af-fd3c7d12308f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
c2b730a8-caae-5a8a-a9cf-0f3a7e653007 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
d48b7edd-30cd-5854-afca-1a75155bb632 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
e651ffb4-3ec6-56af-a03b-6ab731c3dee6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
6cfb7edb-0417-5ec1-acda-b3c7bbbf13f5 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
7a3e5f7e-d6c4-5541-b723-3df9daa1d0d1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
c573db9d-1ea3-561d-b348-0e9413cacbff |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
472fb693-01db-54f7-bf6d-fcab6c8ae172 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
fc133df3-2fe3-5f26-9283-859faa3c845e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
bc5d30eb-fb76-5012-9f62-8a9020ccce5a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
64f61e94-695e-5186-ac2f-a1cc35df05a8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
1d21762e-719f-5c13-87b8-6d787437b710 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
b877454c-befe-43bc-aadd-e47672020ba2 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-124 Commissioning Instruments
786bcfde-ceda-50dd-9db8-686650761018 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Required Data
7ac0b21e-0813-5661-9f06-b75ca0cc629b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
a1ae7941-db4b-5ced-9a19-6489d6612f7d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
7e978f2d-2501-5dc6-a878-48bdd7b83073 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
099dd64b-0f9a-58d7-9102-e9d37fee9c93 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
c148fa58-e6b2-5ee5-a3e7-b34b5605effd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
cbb7d0d5-dbbe-5a3b-9685-21fa64dfa99b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
050462ac-fe0c-5014-88d9-bedf6f90c2d0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
9645cbfe-fc8a-5ca5-acd7-75fc452c70e9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
b07ca78d-4b95-5ab9-ab81-6d074580416a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
87ac217d-d0b8-5969-b82a-e0b96e41c6a7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
64da7135-acca-5ad7-9c2e-619e70e62f8a |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL011 - Emergency Dump Pond, Level Transmitter 2 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
ebf94afc-8911-4a20-bc32-7ad2f680247e |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3
681ee844-215c-4c77-988b-3ac7a2a9dd97 |  | checklist-flat | not-started | ITR-CL-1-131 Level Instrument Installation | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-131 Level Instrument Installation
8220cc76-458a-5636-af57-1da482148e82 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-131 Level Instrument Installation | Level Instrument Installation
40419b5a-9eb2-5a04-91ff-133467e78f44 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-131 Level Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
3d21e93b-0d95-4531-8c61-5d4357d46540 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-122 Instrument Calibration
4dddaf58-1685-5ddc-8823-bfd30c63cf3e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-122 Instrument Calibration | Required Data
581e8054-c23b-5d60-a362-f78b8eac6d63 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
f6641247-ef56-5f81-b9ad-e4b6864da76b |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
bd9fce3b-f9b5-4735-bdfc-354ee01fd4df |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning
8f26b007-62cb-5621-be90-963ecadfe349 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
6f684220-603d-59fc-bce9-650cf70399a6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
a9a272b4-1c4e-5fb0-a07a-810388dcf58e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
7d3c93bc-d982-50fd-916f-d2e3059c2990 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
2ef0dce3-a5cf-575d-aa6c-07a18848ace0 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
1f119f29-b18d-53d9-ba07-b8496932bb74 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
47d282e0-0855-5d7c-a04c-3bfc233354af |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
606d63e0-e46d-5438-840f-e40dce5c6146 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
5b804ec9-2d28-59c4-b13e-61d1e186e378 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
3d1145e2-b073-54fc-aa5a-59a6a97cd650 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
09e03e0d-0382-5a36-8654-53d33664b817 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
ecab6a08-3954-550b-9a3a-3ed3958f8ffe |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
d40c8250-950a-5419-bccb-b0e8382efc9f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
f1d07711-149b-562f-a633-d2c3dbebb803 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
5574faca-eb43-5a1d-8524-de5e9731b4ed |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
86bd772a-9e66-5385-b36d-4f193d87224e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
fdc69faa-7669-5012-aa8c-e1d7a0305a07 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
82e44ab0-3a1c-5724-bc7e-c4ea3b6d8c78 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
b16fac9f-bfd1-53b1-b74f-3fbd61893fc2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
ec2abc7e-ef91-5e12-9b97-c78761a1030e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
89cdd2e8-c9a9-5bec-b3db-ed731974b519 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
e01c6331-c66f-42f5-93f8-66b4cb6f5cca |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-124 Commissioning Instruments
77f8326e-2e4f-59a9-8152-66f3c6f4d564 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-124 Commissioning Instruments | Required Data
9b56946a-d6b0-50af-86ea-de636488ad05 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
0e432184-0158-5f9f-b711-15a9608d71cb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
6a7c26fd-36b7-56dd-8519-ea990a385228 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
a0895ba7-1f40-582b-999a-85dcea129f23 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
a4dca879-a48d-5cf7-a661-701f91ba3784 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
04650a68-948d-5f11-b9ed-cd150fedec1e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-124 Commissioning Instruments | Set Point 1
607d89d3-cd2c-5134-b04c-f129bcdc2617 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-124 Commissioning Instruments | Set Point 2
b4084d5c-782b-5ac4-a2e2-b070122d4bb7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-124 Commissioning Instruments | Set Point 3
f8bf3f39-5659-52c5-87eb-012226aa3311 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-124 Commissioning Instruments | Set Point 4
99e433c6-a1e3-5cb8-8459-c5b4faceb587 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-124 Commissioning Instruments | Calibration settings
495ffea9-8b8a-533c-9c09-7e96b2cb39ec |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CL012 - Emergency Dump Pond, Level Transmitter 3 | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
8df5e1a8-1962-4d11-bc2d-20f2b1888442 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter
12ea76fd-8d9b-4a8b-b85e-fcf980583065 |  | checklist-flat | not-started | ITR-CL-1-130 Pressure Instrument Installation | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-130 Pressure Instrument Installation
8251091d-2650-55ed-a743-6d165e4f071f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-130 Pressure Instrument Installation | Pressure Instrument Installation
e145d978-b96e-54ec-9ede-ef74713fd3a7 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-130 Pressure Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
f6524155-50c1-4b7e-9b23-07f5ddc67d33 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-122 Instrument Calibration
30f948f1-331d-57a1-b1f7-6f4e075f7f78 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-122 Instrument Calibration | Required Data
4200f7ac-15ed-5546-ae24-86b38c67c2a4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
20c8934c-4954-5bd6-9369-5926a78bebb0 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
e0fd14ea-9583-49c4-8918-9a4244073de3 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning
88b1ee8e-4fa3-5752-b1bf-bbddd22979fa |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
9fe77eb8-05bc-535e-8e91-2f29f98e4cfc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
956c265f-42c9-57f0-ba9c-c9d19ed3dc81 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
46ccdb0a-002c-5b10-9a5c-3fa526b7a712 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
ce172e72-37b8-5b60-91aa-971f9c2aac6a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
f55ff3be-682c-556f-86d9-23c66eadc70a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
0e4e73d4-4d59-5aaa-b73b-26dd1d38d128 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
c8709e35-94df-5b9b-8759-56b368f8745e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
96be3da3-328f-5bcf-9a49-468c3a23c1d4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
e5dabd49-dc96-51bd-8bd2-c4ad6b56caaf |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
9f31a4ca-1682-5215-b7f1-b9a4f33584dd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
5e5bd720-47c5-5eef-a3eb-3a2e499c3f2d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
58af5426-bf5e-5bd4-93cd-4a199ec3c2d1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
5d1a6b83-7ec1-58f9-ae89-f463d9aa0253 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
8d4b1d90-4efa-512a-8208-94c629a4669f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
6d052083-0932-5f93-826d-552a1a7d80af |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
1e5d3042-ea59-5112-91ec-b164831dc54a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
a390d40c-b6ee-51ab-977f-d5b9a7f6050f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
7fd6a44b-3f2e-5810-9283-d177f4ae2c6e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
2b798c79-5977-5b8f-aa81-a259acb91302 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
a776dd3d-ab93-5cc7-a51f-9190a1b631a0 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
d13a226a-6182-474a-aa5a-11322f9ee129 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments
5e6e3127-b4be-506a-8fb7-8c0b988f0758 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Required Data
aa081534-e61c-5a89-9264-918228ec624b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
ace463f3-160e-58e8-9410-68b7744c0028 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
b4b2dafd-bbb4-5de2-b919-fae54129d287 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
4159265c-57c1-54d1-9a4a-9d79170795e7 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
92e07978-4692-5882-b997-18b43d6b6ec9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
a0fe9fa4-8b9e-5105-9038-b006b025ea8f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 1
e5d67ace-3ad7-5865-bd2b-b1b5ec5f579b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 2
e061aaba-6591-5466-bde9-9e3c1f0387c4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 3
0c694966-adca-5ed6-a97b-0c37fc80b1c1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 4
c0dab14d-df86-5f92-8388-3c8de4480aef |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | Calibration settings
3f4ba6e4-4772-5b46-b827-8956fee26c0b |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CP010 - EDP Pump Discharge, Pressure Transmitter | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
e592a2e2-4349-45fd-b61c-8cfa4e485cd0 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP)
f1d7c65a-c42a-4a02-8135-613b0c5a6403 |  | checklist-flat | not-started | ITR-CL-1-129 Flow Meter Installation | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-129 Flow Meter Installation
f6593267-864f-5402-bbf9-18b012eadd36 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-129 Flow Meter Installation | Flow Meter Installation
50958641-76a8-5553-9a83-ca0debd82187 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-129 Flow Meter Installation | All relevant signatures (Installed by, Approved by, Client Representative)
30cb8dbf-0109-4a79-821a-4df6d6f4d0f0 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-122 Instrument Calibration
e9eac1ef-c73a-5ae3-b631-97c355925f08 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-122 Instrument Calibration | Required Data
59239bb0-f9b6-590d-9ef3-ecb66bc78480 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
7b029605-5f9e-5191-898d-b35bfc2dd6f1 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
8b92e095-c419-4fc2-a9be-a9bc24d97469 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning
4be6796a-62cf-5414-8f10-8e98124fbf5c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
ef04830a-ddd1-5c12-8ecf-f0e0071fb70e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
b9e2f3f2-1d52-5231-abe7-486c6279e9d4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
79782839-d74a-5942-a570-6a5b8f98c7c6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
a80c8830-3bd2-5d43-a162-a57bca6b245b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
a68f7ce4-e6d3-5c0a-8d7c-96c244a9d816 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
3a780c0c-5035-5cfb-86bd-6e842c413974 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
30646312-6ba2-59f9-93e5-ba1e7c18835b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
e1919f1f-fdee-52a8-9017-22b5c6919b0b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
2758ae6f-62cf-5077-a105-e4777003b047 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
d015b938-5706-5b71-ad1f-c2c8a8e3aab4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
c36b1d3e-442d-5f15-9184-0b67b8ac19b3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
6ec23119-5341-5b0e-9b37-c6480da9e5e6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
c44248cc-ac1c-5f4b-9b1f-3dccaac23057 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
09e8de8d-69e2-5164-aa64-750ad789d0ab |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
5e25c533-7d98-50e9-b680-4cd6d8c2c88b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
65a92d4e-4164-5d83-8aa2-b647d2afcdac |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
b4e1e292-1616-5e17-98d1-acd6bbf512eb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
75b26ef7-ebe6-51e6-b538-da0ce6646f1b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
92b2db0e-70ab-56f8-98aa-31fc2b80523e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
d04bee53-b73a-50a6-aa99-d83b9c12aa3e |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
91542f75-7ba3-45aa-8a5d-150778979ed5 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments
34a0c110-032d-5876-ab22-cd90c9409bd1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments | Required Data
b95b3c90-2c6d-52ea-b307-cf6ac7856ba3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
30b1cbb7-7416-57e9-b4ef-bdc961e91a03 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
c1a66734-5a4a-562a-9f45-332c1edacc24 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
d870edb4-3528-5e7f-b81a-924557f15dd8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
7055cddf-aa08-5487-8277-f24a4da86c48 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
47c54d3d-7973-5bcb-bf11-5b59e198eac6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments | Set Point 1
302ac729-fcc7-5916-942e-9b211b15df4c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments | Set Point 2
c5c6a12a-a55e-593f-b350-dfa1c7e8355a |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments | Set Point 3
cfd8e66f-442d-58ab-a477-45849fe6060e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments | Set Point 4
e9a30315-679e-5293-99b2-08a32bf710d1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments | Calibration settings
131dcbee-43d3-580c-bba1-ccd8a155258a |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CF010 - EDP Pump Discharge, Flow Transmitter(Orifice DP) | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
cecc60c5-2507-461f-b30a-8037d963bf2f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE
59eaf72e-f7d0-4ed6-be07-2b84ef360e94 |  | checklist-flat | not-started | ITR-CL-1-128 Temperature Instrument Installation | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-128 Temperature Instrument Installation
ba66fe88-c362-5bea-81b3-fd7144e24970 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-128 Temperature Instrument Installation | Temperature Instrument Installation
8e9effab-a90b-5b20-9094-62b58fc6b043 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-128 Temperature Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
e08f2426-2aad-4eb8-bac7-ce35da3d9adc |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-122 Instrument Calibration
4b0ca21c-87e9-58a9-a35b-f8eab7486be9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-122 Instrument Calibration | Required Data
22285436-b217-5f6f-9646-edee629dfe29 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
442e0487-8689-56a6-95da-e9df420fa1f5 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
12612718-856b-45a2-9efc-7ac1d775a09b |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-123 Instrument Pre-Commissioning
b9941879-6626-504f-bd5f-8150b9e1ec15 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
40c8446b-5d30-5b03-ac74-27a88ac3ca8e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
357aba62-c623-5b72-b3af-ef3221b5b0e9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
00ca4e61-d69b-5c35-b2f3-80c5713342e9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
eee8682d-aea3-5faf-9d3f-b87ce029d362 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
fca187ad-d374-56d8-997c-dcb935988137 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
b7348bbc-039f-5e70-9ed5-75146a92dc9e |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
807fbee7-ae1e-5cd7-aa09-fddceaec302d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
305ae74e-24b9-51f9-9e10-adea1ecf73df |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
dc114772-30eb-548c-beb8-bb470ee2e9fb |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
412d91c5-3f6c-5d6d-8df0-aaf27c4679b2 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
11e76c8c-b73a-5f33-84b0-52c2b2cd3d04 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
ea6ad801-0eb6-5418-b2ee-a6934714a4f8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
7f19c64f-ea44-573d-bc54-a4059ff83e49 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
86d686f1-d32a-5610-8624-8b77f0cb3e27 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
d4a05c02-b37b-58af-9ea1-df7675cf0860 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
c31077db-1897-5a4c-8370-97cfcfa73990 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
0ce0a121-9dfd-5aa3-b9ec-fadcc990c28b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
d26ed76f-8717-50ad-bc3e-6dcc9eb4666d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
a5ada609-9b19-528c-9fa4-32ea34134290 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
023b9417-8f92-5b11-8470-24e2c0f11f16 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
2dc6479f-5b09-442a-82d2-2b6d0c0862fc |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-124 Commissioning Instruments
4f9bc422-26ba-5570-b6dd-304328adc7d1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-124 Commissioning Instruments | Required Data
db74decf-6c27-5551-8d53-0739a2de40f6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
7b7927ec-fd55-5a6d-82d8-58ddfbd3af6f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
2f3bb0f6-c847-5cbe-8eba-5d8a552355da |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
d1b8b80c-35bf-5e05-8af3-2ac496551e25 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
b0343f70-f9d6-5807-8344-4b8eaaf8cfee |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
93371b9d-9bd7-5e45-a9ec-681ae5c511f3 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-124 Commissioning Instruments | Set Point 1
44916c11-b389-5896-a8da-52f648b165a8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-124 Commissioning Instruments | Set Point 2
bd7343af-5d3c-5700-ae2c-bbe95f651784 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-124 Commissioning Instruments | Set Point 3
5867deb2-b19e-5b1e-b94f-8d7a05e19523 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-124 Commissioning Instruments | Set Point 4
6737a9a0-a88e-54c6-9968-59394e9704b3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-124 Commissioning Instruments | Calibration settings
d7975cfd-525d-5e13-bdce-5e055b558f0d |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GNK10CT010 - EDP PUMP DISCHARGE TEMPERATURE | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
be91ce9f-af2c-42b0-b8af-68c57b944306 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter
77b0a595-4fe1-4c08-96dc-9a15aeadff44 |  | checklist-flat | not-started | ITR-CL-1-128 Temperature Instrument Installation | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-128 Temperature Instrument Installation
e09be0cb-f5f6-50e4-a2f8-f09782f2de04 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-128 Temperature Instrument Installation | Temperature Instrument Installation
839a6c73-f226-5c6d-aa66-10b9b5c25810 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-128 Temperature Instrument Installation | All relevant signatures (Installed by, Approved by, Client Representative)
e20d10a5-0e76-48f8-b23a-da87cb245b40 |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-122 Instrument Calibration
0f9d4c89-f80e-552d-89e0-321f42f50b83 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-122 Instrument Calibration | Required Data
a3cc84d1-40d4-522e-9a20-83dfc1caf682 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
4c3b23b8-df42-5077-b366-db2d15c9a905 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
61a3aaed-eff1-40f8-888d-b340577116a1 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning
f69cf8f2-7e38-513b-9f07-ef4df18eb7b5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
1ca6202f-2a0d-58db-98c2-80382b9f374d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
df82d253-32e9-5ca7-a544-650cd3a0b73c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
ea427c49-2221-5abe-8ce0-0d4e37fe487c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
2bd0ca3d-fa9f-5c33-88dd-5eda837ddf2f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
3d936faa-2e76-5461-9978-787fc1c82297 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
5a4fc7db-2e77-55f9-9262-dd7f5424dbfa |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
3648a8cc-5294-559c-a3c8-167508c3978c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
cdecc248-8216-5c6f-bcf5-0648721e5daa |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
d59f6a0e-9469-5c7a-8ed0-bfcfe5575a92 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
26e9488e-e9f5-5e5b-a657-307ac23dd92b |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
0a5b0737-8cb8-5cad-bb76-92f3787f6cc8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
4d22e1d5-8849-5c7c-a7b0-a3488274a3b6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
2949091f-c35c-5ccf-9941-ed944b3d3cb8 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
d2f0c5eb-647a-522f-9b98-ab1aa01988e1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
954e423d-fc23-599a-87b4-34a9cc233aae |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
a7292058-0d8b-5cce-8c58-7fa3b882d217 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
962b36e1-f238-529d-b173-90b5e8fdb4de |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
06e7390b-0733-537f-8e01-70ca7cdde920 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
1c5fc5e3-5242-5858-91ad-95f789cd9dc2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
51968c1b-777d-54b6-862d-4a1d43703c34 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
02eb7feb-e0b0-4d45-840c-884abf5101e2 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments
d60a5b1f-01ef-5a37-a929-fdcee4590d76 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Required Data
567bed60-d667-5335-9e90-9494db757dd1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
a1b8204d-08ec-5b47-81a6-49156a108554 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
999077fc-f444-5f32-b758-552ebe09268d |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
1ab72734-caa0-5e26-912c-92be3ccd4919 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
43d942a9-d178-54aa-a3d7-8679d4621666 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
c1b5b5fd-fa54-58f1-b650-f186dbe59baa |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 1
2869b7fb-6c14-5e9e-b058-3a85ed5542a9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 2
98fdda4b-7033-5063-bf93-eb552a403bf4 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 3
3328b270-e39e-5378-84d8-ff0f16d40b08 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Set Point 4
28a285ca-1dcb-5fa6-a71c-f6d127c106c7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | Calibration settings
716c920d-6307-5e92-a3b5-b13856df6c91 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00EDP3GMA10CT010 - Emergency Dump Pond, Temperature Transmitter | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
f8ef983d-ed3f-4953-ab35-80629f7ef6ea |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve
331b0a73-1941-4e0c-87f5-f35ed5d5a6b4 |  | checklist-flat | not-started | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation)
719c537f-dfbe-5bec-8718-b4a01deaa957 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Equipment
3fa5a66c-c95f-540e-9354-5b1357c52cb5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Valve
c5ac27b6-58cd-5da6-a45f-1876a1c7696e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Actuator
09a7ad56-360d-5ce2-b51c-0ef49ae6b1af |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Positioner
cb63eb51-478c-51c2-bd2d-c88e523ef158 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | I/P Converter
252034ea-10bf-5ed0-aeed-f6e2a92245f9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Filter/Regulator/On-Off Valve
1926a919-587f-51ec-9d62-4d8108b05eed |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Fail Action
ec1f79db-9e0a-58f7-b55a-0a06c62d3ac3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Valve Field Calibration and Hysteresis Check
d91b8e74-2846-5a43-862a-8f5b0a9110eb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Proximity Detectors
b2062fa3-90e7-5fc1-9a1e-8b34b7aae35b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Solenoid Valve
102e402b-3a56-5bbf-ab18-bd25a9ccb803 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Pilot Valve
475f3c52-4b03-50dd-8686-a2ef879ad804 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Hydraulic Actuator
f8e6a3a9-38e7-5ff3-8182-885b6ba07578 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Accumulator
1562afdd-cc64-54ea-8b1c-442bdf25baf0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Electric Actuator
cd7224ba-796d-5eaf-9c26-c5fbf2a4d87c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | Miscellaneous Equipment
4a380059-21bd-5594-a646-ddbd6fde4da6 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-119 Valve & Ancillaries (Pre-Installation) | All relevant signatures (Installed by, Approved by, Client Representative)
1b2503e0-667e-432c-808a-dadf5ae1038f |  | checklist-flat | not-started | ITR-CL-1-122 Instrument Calibration | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-122 Instrument Calibration
9cf61bcb-e9f6-503f-9e4f-266c03bd1fdd |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-122 Instrument Calibration | Required Data
9ccabec6-80fb-5658-bfb4-0253cc8779c8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-122 Instrument Calibration | Instrument Power Supply
0ea2aa0b-69fb-5d12-97be-8dee706ddd5a |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-122 Instrument Calibration | All relevant signatures (Installed by, Approved by, Client Representative)
70dbc18b-0bb0-413c-834f-d678dc6100a0 |  | checklist-flat | not-started | ITR-CL-1-123 Instrument Pre-Commissioning | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-123 Instrument Pre-Commissioning
0b63be16-2735-5aa2-949b-e46d8853275e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Checklist items
cf2c3ec6-f759-55fe-85ab-0e7afd7e4b8d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
5e8286f5-83ae-5b65-a82c-9f18012366da |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Analogue Input:
041f0068-670e-54b6-830f-47720341f059 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Rising
b762372e-5d0c-55b7-8167-3c5178255d54 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Rising
0b8b8285-c4ae-55e8-9876-cee6d28432da |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Rising
a2a6ceb4-05a3-59c5-9b95-86123a013511 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Rising
1dddb8c4-8fa5-537c-9f33-9dfd9f91d745 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 100% Peak
4e2efa1e-42c8-5f3a-965c-22bddd2e725c |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 75% Falling
9fc3c2e4-12c0-5e2c-81b7-0998c4f85958 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 50% Falling
0acd0756-2d10-54a3-afa0-084b9a19ed06 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 25% Falling
a701e9a6-1138-5986-9607-c155b07f860f |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-123 Instrument Pre-Commissioning | 0% Falling
7504c834-edf6-5a2b-9a52-12050edca3ef |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Digital Input/Analogue Alarm Trip Points
a1fc9463-533c-5a76-a16d-328aed3e9035 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo:
11cb63f2-4ba7-50b7-9415-07e1e70c74d9 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Lo-Lo:
c7e6d98f-a2f8-59fe-96d1-07ffb0c2ca24 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi:
249eda87-2c06-5c4c-ac42-63ab30258bba |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Alarm Hi-Hi:
1a5779fc-d12f-5587-8e1b-7ba0767e32e1 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Control loop set points correct:
58e82ff9-8c6b-5db2-a33b-51190f334bd9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Startup, Shutdown and Override functions
3ad4e41d-951f-5da9-938c-fe45e0883058 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-123 Instrument Pre-Commissioning | Additional checks
241cd31e-547c-5df3-a9dc-a51ea1e5e8ec |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-123 Instrument Pre-Commissioning | All relevant signatures (Installed by, Approved by, Client Representative)
4f98996b-4763-43c7-b75f-6f4b1157f496 |  | checklist-flat | not-started | ITR-CL-1-124 Commissioning Instruments | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-124 Commissioning Instruments
dcd9e6ee-952c-593d-8c7b-49ba414506fa |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-124 Commissioning Instruments | Required Data
0a96b009-3070-5367-8705-7d42b9adca61 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-124 Commissioning Instruments | Alarms & Set points
9e315177-6314-5f75-a398-fad10733e627 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-124 Commissioning Instruments | Alarm Lo
8ef8f058-7444-538d-a47a-79cc812ea989 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-124 Commissioning Instruments | Alarm Lo-Lo
dc95dc9b-c67e-5ea3-b006-43c95b9bcfec |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-124 Commissioning Instruments | Alarm Hi
2b43e1ba-7a93-51a7-b90a-60cf4a3728e6 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-124 Commissioning Instruments | Alarm Hi-Hi
4649054e-d37b-5a09-8dac-c180ac23fc64 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-124 Commissioning Instruments | Set Point 1
cd9f1ba9-7272-555c-81d9-a29528071d23 |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-124 Commissioning Instruments | Set Point 2
9e3a37a5-0167-5b60-b07e-c3c52f2963da |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-124 Commissioning Instruments | Set Point 3
881a5ee6-49bf-5f66-817c-0020be1bacff |  | checkpoint-no-status | no-status-not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-124 Commissioning Instruments | Set Point 4
64b73440-17da-5835-bb07-48a6fa28ee47 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-124 Commissioning Instruments | Calibration settings
d3f8ed3a-a368-5081-91c9-5f7940193c8b |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Instrument | TH00L040NDA10AA410 - TH32 Low Point Silencer Dump Valve | ITR-CL-1-124 Commissioning Instruments | All relevant signatures (Installed by, Approved by, Client Representative)
610d823d-e27c-4223-a316-ad9b5d4dff68 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Cables
ec8de19c-5caf-4eea-9587-28c803820c8f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | Junction Box 05
795c81ee-e814-40a2-aeab-8d698e422b73 |  | checklist-flat | not-started | ITR-CL-1-106 - Junction Box | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | Junction Box 05 | Junction Box 05
b36e40f0-3543-50c1-90b8-9a3102997b9b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | Junction Box 05 | Junction Box 05 | Junction Box
8ce775d2-de65-463a-b6fe-4bf4ec85ca87 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP0BPA10AP010-P01
79ce462d-c761-4493-a0d9-89f36395ae40 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP0BPA10AP010-P01 | 185mm2 +25mm2 3C+3E Varolex VSD CuSn XLPE/PVC
973e04ac-b2a2-5a80-838c-187e9db63c1b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP0BPA10AP010-P01 | 185mm2 +25mm2 3C+3E Varolex VSD CuSn XLPE/PVC | Low Voltage Cable
66422f93-8db0-5faf-b1df-507b2b159378 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP0BPA10AP010-P01 | 185mm2 +25mm2 3C+3E Varolex VSD CuSn XLPE/PVC | Electrical Checks
92a69762-627b-56c3-9f49-d1466b58ab4a |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP0BPA10AP010-P01 | 185mm2 +25mm2 3C+3E Varolex VSD CuSn XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
ec439696-6921-4d27-8edc-0fe05742ac6a |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP0BPA10AP010-A01
423e4181-1562-4462-adf1-77b35321da38 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP0BPA10AP010-A01 | 1.5mm2 4Pr CuSn ESCS
24c6e357-6dff-5271-9fb6-e731c1201fc4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP0BPA10AP010-A01 | 1.5mm2 4Pr CuSn ESCS | Instrument Cable
9122fdfc-9f9e-5631-b8b2-eb05101d0fbe |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP0BPA10AP010-A01 | 1.5mm2 4Pr CuSn ESCS | Electrical Checks
7e4328a7-7b48-4f2b-aac4-f86490406148 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP0BPA10AP010-C01
42eac410-13f2-4e36-91d2-c7fa3247d34e |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP0BPA10AP010-C01 | 1.5mm2 12C CuSn PVC/PVC
87c33a3a-57cf-5acb-8d86-53f60d14fa0d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP0BPA10AP010-C01 | 1.5mm2 12C CuSn PVC/PVC | Instrument Cable
ad61055f-1ac6-56a4-9f0f-dcd95d06cb79 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP0BPA10AP010-C01 | 1.5mm2 12C CuSn PVC/PVC | Electrical Checks
0bbe2aae-4e68-4d58-abca-70ca206aa742 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10AP010_-M01-P01
a01a452f-8aea-4401-8d85-e84adc1875a2 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10AP010_-M01-P01 | 185mm2 +25mm2 3C+3E Varolex VSD CuSn XLPE/PVC
13e4a8d1-f680-5d2d-b173-04d6375d8740 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10AP010_-M01-P01 | 185mm2 +25mm2 3C+3E Varolex VSD CuSn XLPE/PVC | Low Voltage Cable
ca59fdae-d677-5f76-bcd5-c26b0d53dcb9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10AP010_-M01-P01 | 185mm2 +25mm2 3C+3E Varolex VSD CuSn XLPE/PVC | Electrical Checks
ecda202b-b0de-5d28-bafa-05a4861dd145 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10AP010_-M01-P01 | 185mm2 +25mm2 3C+3E Varolex VSD CuSn XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
507f0773-f22f-4749-9aeb-741aa977b9e9 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10AP010_-M01-C01
6003b274-71be-4454-9b9e-baac2f4117b6 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10AP010_-M01-C01 | 1.5mm2 2C CuSn PVC/PVC
e3204a26-0168-55fd-a34c-ad15cedf74e0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10AP010_-M01-C01 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
36d1ce96-9107-5974-88e2-dfc658fa57c4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10AP010_-M01-C01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
7f27cffb-8caa-48e3-897f-3fb0130ce8fb |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP0BPA10AP010CP-P01
643b9f35-e420-4387-8746-8787910bf367 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP0BPA10AP010CP-P01 | 1.5mm2 2C CuSn PVC/PVC
1f5cb3cc-dbfc-531e-ab10-d07d7792a507 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP0BPA10AP010CP-P01 | 1.5mm2 2C CuSn PVC/PVC | Instrument Cable
67c5251e-2323-5b53-a6c8-cb9feb4b915c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP0BPA10AP010CP-P01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
ddceda13-b7cb-4011-9a0e-8ac292e548df |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH000000BHx10GY101-A01
8a9ca9fe-114c-406a-b915-e1038b59e488 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH000000BHx10GY101-A01 | 1.5mm2 12Pr CuSn ESCS
052c6b1d-d733-5504-a875-0b6b270e112b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH000000BHx10GY101-A01 | 1.5mm2 12Pr CuSn ESCS | Instrument Cable
b5f06694-98ea-525f-a5eb-07100ade8446 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH000000BHx10GY101-A01 | 1.5mm2 12Pr CuSn ESCS | Electrical Checks
7119bab8-5585-4fc7-853c-8aedfb5c38f4 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10CL010-A01
ee98e122-8144-44f5-a384-0f20913ccd4e |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10CL010-A01 | 1.5mm2 1Pr CuSn CS
2ef7a5dc-31ea-51ac-9e18-b6509ce6a449 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10CL010-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
0dc19bb2-dc19-5d58-9fbd-5b9e7c7a9b58 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10CL010-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
640700e1-0ca5-4cd0-b3a4-448800272757 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10CL011-A01
8812693e-a105-4e92-b217-ea6326397112 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10CL011-A01 | 1.5mm2 1Pr CuSn CS
56259917-d9dc-5ef3-8145-fd4a5ec5d81a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10CL011-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
7235e523-2118-5a56-bd88-7fc49175655a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10CL011-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
b1ee26aa-e336-4164-8af4-45303b435f94 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10CL012-A01
ecd9b174-8e88-4c82-b21c-f2464b7c2c67 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10CL012-A01 | 1.5mm2 1Pr CuSn CS
65073530-26a0-50ab-935a-6a005411128a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10CL012-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
2b755773-fe9c-50d5-a574-8deb60be6305 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10CL012-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
74f295a5-fb76-4093-a325-b55a4f0615e2 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GNK10CP010-A01
5e575692-c359-4f89-ae10-1125465ce3bd |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GNK10CP010-A01 | 1.5mm2 1Pr CuSn CS
7699c692-3356-57f2-8e37-7030b2b7c6ff |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GNK10CP010-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
03a7d7d9-1368-5db6-a855-82e081092b46 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GNK10CP010-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
8ccdb605-7122-4d1c-9090-506ce0701162 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GNK10CF010-A01
df1f8d5f-f39e-4faf-a50b-706fcedc1334 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GNK10CF010-A01 | 1.5mm2 1Pr CuSn CS
27840c11-b604-578f-a6c8-90a835fc1c40 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GNK10CF010-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
93480a78-6bd2-5fca-a215-15449021e7d2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GNK10CF010-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
17afa9d1-a9dc-45d4-9606-559ae0cd751d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GNK10CT010-A01
e9d17a7f-1fd8-4435-955c-20f8775fdfc3 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GNK10CT010-A01 | 1.5mm2 1Pr CuSn CS
9ddc5846-2e9e-50cf-b675-46d85ccdbc56 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GNK10CT010-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
7f6d6d2f-7a1c-53c9-951d-d12036cebb85 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GNK10CT010-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
1f43464b-0a6a-4220-8ea5-bd1e3a678279 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10CT010-A01
35040cd8-570b-48aa-a110-ef327f72ce5b |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10CT010-A01 | 1.5mm2 1Pr CuSn CS
ceb7058d-36e0-5db8-9c3b-40f581c0b7bc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10CT010-A01 | 1.5mm2 1Pr CuSn CS | Instrument Cable
3a835905-2034-564c-ae05-91c27af0e215 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP3GMA10CT010-A01 | 1.5mm2 1Pr CuSn CS | Electrical Checks
2b8a9460-33e8-453f-a4d6-36715bce792a |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00L040NDA10AA410-P01
b3cc3285-974c-4e03-a52e-91b290912ad8 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00L040NDA10AA410-P01 | 70mm2 4C+E Cu XLPE/PVC
dbee2fd7-ac49-536a-9835-a37dee255f6e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00L040NDA10AA410-P01 | 70mm2 4C+E Cu XLPE/PVC | Low Voltage Cable
1139dc7c-8986-59eb-a435-4499b30daa3c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00L040NDA10AA410-P01 | 70mm2 4C+E Cu XLPE/PVC | Electrical Checks
fbc9fd72-2ac1-5d5e-8862-b84f11266aa3 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00L040NDA10AA410-P01 | 70mm2 4C+E Cu XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
60d1ecd0-b738-43b3-9977-2a7d1c66c88d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00L040NDA10AA410-S01
ae50301f-4943-4e99-a229-f671bb9fd640 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00L040NDA10AA410-S01 | Profibus DP - Grey Sheath
5fa48a98-db33-51e1-a171-257f9cc3f2e1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00L040NDA10AA410-S01 | Profibus DP - Grey Sheath | Instrument Cable
299e5381-7e5b-5656-91be-df84e5650364 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00L040NDA10AA410-S01 | Profibus DP - Grey Sheath | Electrical Checks
fc0ca589-3406-4f90-9cb5-b8603e7f4c6c |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP0BPA10AP010-S01
d088c323-e0d2-4063-b7bb-398c25a689ac |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP0BPA10AP010-S01 | Profibus DP - Grey Sheath
b6dbea19-23e9-5c83-8261-8c7b5443985b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP0BPA10AP010-S01 | Profibus DP - Grey Sheath | Instrument Cable
7ac5f98b-3c57-5520-8de9-bc0812d47cc2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Cables | TH00EDP0BPA10AP010-S01 | Profibus DP - Grey Sheath | Electrical Checks
6b9a2097-79ce-4838-8dcd-9d2c84f50f5f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Earthing
a77586fd-b854-41c0-a909-a8dff78f3661 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Earthing | TH000000BJB10GS010_BOND09
fbf06f40-2f78-4740-9653-c522bdd48c35 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Earthing | TH000000BJB10GS010_BOND09 | 70mm2 1C Cu PVC/PVC GE/YE
330742f2-6d83-5809-ad4a-9daecac837d9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Earthing | TH000000BJB10GS010_BOND09 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
712e4f82-f69c-5b58-a59e-34d1e84670cc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Earthing | TH000000BJB10GS010_BOND09 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
39037171-4103-4c57-8891-d17d3a302c59 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Earthing | TH000000BJB10GS010_BOND19
603a0106-b82d-4bcc-b93e-551934bb49c5 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Earthing | TH000000BJB10GS010_BOND19 | 70mm2 1C Cu PVC/PVC GE/YE
f51957c1-50df-561d-876b-15400666b581 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Earthing | TH000000BJB10GS010_BOND19 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
d2229923-0a1b-5e57-b51e-721af42330f1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Earthing | TH000000BJB10GS010_BOND19 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
278f2e11-bfc6-4c1d-9f80-11d67f6f5f87 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Earthing | TH000000BJB10GS010_BOND20
483c80e7-f973-4efc-a17b-ab02bb3b998f |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Earthing | TH000000BJB10GS010_BOND20 | 120mm2 1C Cu PVC/PVC GE/YE
5cc465c3-61c0-5ef3-8827-a4e9b2fdb02f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Earthing | TH000000BJB10GS010_BOND20 | 120mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
4e57d96e-6aaa-5665-8424-a08fe9e79934 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Earthing | TH000000BJB10GS010_BOND20 | 120mm2 1C Cu PVC/PVC GE/YE | Test Results
20b90421-de39-4bf7-b75d-92135a99b0c9 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Earthing | TH000000BJB10GS010_BOND21
4ea55f8f-3a6b-4dde-a1fb-73860ba8ae23 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Earthing | TH000000BJB10GS010_BOND21 | 70mm2 1C Cu PVC/PVC GE/YE
02451e93-d427-5392-80c3-acfa0b3edfdf |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Earthing | TH000000BJB10GS010_BOND21 | 70mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
b35162f3-c5ea-5eca-8e9d-8c3eea976232 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Earthing | TH000000BJB10GS010_BOND21 | 70mm2 1C Cu PVC/PVC GE/YE | Test Results
33779ba6-95c6-4605-94cd-ae3f614c3f5c |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-CSB-E-004 EDP Pump | Earthing | TH000000BHx10GY101-E01
19582d6b-4de6-4cd4-bc74-e25a41e63860 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Earthing | TH000000BHx10GY101-E01 | 120mm2 1C Cu PVC/PVC GE/YE
01982765-64e3-543e-ade8-fec355a17f2a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Earthing | TH000000BHx10GY101-E01 | 120mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
4f9a473a-1b83-59d1-bf17-328523da9992 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Earthing | TH000000BHx10GY101-E01 | 120mm2 1C Cu PVC/PVC GE/YE | Test Results
b4763a70-3926-44be-b582-e5c0b9a1221b |  | checklist-flat | not-started | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP-CSB-E-004 EDP Pump | Certificate of compliance (COC)
be3ae4eb-26b5-5217-adbb-7cecc9772969 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-CSB-E-004 EDP Pump | Certificate of compliance (COC) | Please upload Certificate of Compliance here when complete (COC)
f137f461-a154-4b3f-bd36-19270ab64f91 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-001 Ormat U3E Supply
43b3389e-b602-4ce1-b7ef-5851f3528230 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Electrical Installations
7aa4ca0f-a608-441a-8d10-2faaf192ab2f |  | checklist-flat | not-started | Cable Pre-installation | checklist-flat | FALSE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Electrical Installations | Cable Pre-installation
601c71e4-0605-566f-930a-2e57c5cb503b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Electrical Installations | Cable Pre-installation | Cable Pre-Installation
33d7fb65-7081-4ff5-866b-f8eb5295b21a |  | checklist-flat | not-started | ITR-CL-1-101B Cable Supports Above Ground | checklist-flat | FALSE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Electrical Installations | ITR-CL-1-101B Cable Supports Above Ground
04bc85d6-8034-5efc-a797-b2b0891b04e3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Electrical Installations | ITR-CL-1-101B Cable Supports Above Ground | Cable Supports Above Ground
6fa46bbb-b05f-45e3-ba28-26ac9525d7f9 |  | checklist-flat | not-started | ITR-CL-1-101A Conduit/Ducting Below Ground | checklist-flat | FALSE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Electrical Installations | ITR-CL-1-101A Conduit/Ducting Below Ground
8531c66a-1c28-5964-b43e-b5e26635de14 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Electrical Installations | ITR-CL-1-101A Conduit/Ducting Below Ground | Conduit/Ducting Installation Below Ground
aca18f6e-27ec-466c-82ec-76027608cfb3 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Electrical Installations | ITR-CL-1-111 Electrical earthing
f0eefadf-4d1b-5981-8faf-76f3d7174296 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Electrical Installations | ITR-CL-1-111 Electrical earthing | Electrical earthing system installation
3a61da24-70d9-5d2d-9590-db02098b1103 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Electrical Installations | ITR-CL-1-111 Electrical earthing | Test Results
5a1b11d1-87fa-4cbc-886d-2cadf7b270d0 |  | checklist-flat | not-started | ITR-CL-1-108 Electrical Switch Rooms | checklist-flat | FALSE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Electrical Installations | ITR-CL-1-108 - Electrical Switch Room
1c058f19-2e9e-56fb-86c3-f880cf4fea94 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Electrical Installations | ITR-CL-1-108 - Electrical Switch Room | Electrical Switchroom (Mandatory Photo)
a4a81d44-e808-4e1f-a167-f71dbb054c91 |  | checklist-flat | not-started | Cable Test Record | checklist-flat | FALSE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Electrical Installations | ITR-CL-1-103 - Schedule of Test Results DB
a7ac7e33-7091-52ac-8731-243254cdc04a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Electrical Installations | ITR-CL-1-103 - Schedule of Test Results DB | Upload completed ITR scans
aeeb3b23-e2e9-4b93-9d88-a119f2f5367f |  | checklist-flat | not-started | ITR-CL-1-109 Electrical Equipment Package | checklist-flat | FALSE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Electrical Installations | ITR-CL-1-109 Electrical Equipment Package
2898d3fb-de77-5155-8064-05a276a15b7c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Electrical Installations | ITR-CL-1-109 Electrical Equipment Package | Electrical Equipment Package
7d8d6873-dfcc-452e-8ad7-d4b471de4835 |  | checklist-flat | not-started | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Electrical Installations | Certificate of Compliance
14eb75a3-5200-511c-ab1f-8aa29009bbdb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Electrical Installations | Certificate of Compliance | Please upload Certificate of Compliance here when complete (COC)
9f322dac-3b72-42cf-b56e-a0dac8efca71 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Cables
02b153e5-634b-43af-80b8-fd009095c591 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-R01
a7f40bd5-c5c5-47f9-ac26-ceba40df77dc |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-R01 | 630mm2 1C Al XLPE/PVC
49a29afd-6582-5ae6-b77c-73eaa9e66c40 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-R01 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
7abac373-66a1-51c4-886c-b826e1a48d51 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-R01 | 630mm2 1C Al XLPE/PVC | Electrical Checks
0ccc6b24-5062-58d1-adc5-88cd6423a64f |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-R01 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
6559cb5f-3f42-4bf6-bc50-078bddbc8847 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-W01
cc24ff85-75a1-4c1c-af88-820fdf600634 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-W01 | 630mm2 1C Al XLPE/PVC
78064394-0198-5b20-8631-cd844cf8049e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-W01 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
25505356-62b7-51a1-8fef-0345ae496f21 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-W01 | 630mm2 1C Al XLPE/PVC | Electrical Checks
acc0bef3-36e6-5e76-894f-a28261e16bc5 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-W01 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
6b877fa5-40bf-49b2-ad29-addc31aeb68f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-B01
145695bd-27b5-4b5a-b7dc-dee55c7f2134 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-B01 | 630mm2 1C Al XLPE/PVC
80df844a-ce97-5963-bc1f-7f7182c57bed |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-B01 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
29878da4-11c5-578d-9bb6-7e393c75ab01 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-B01 | 630mm2 1C Al XLPE/PVC | Electrical Checks
4a22f365-071c-5017-adbb-877120b891ff |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-B01 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
63048893-67b6-4edd-a379-8f932db06bf9 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-R02
3eecfddd-0e99-48d8-bd5a-b6872791500c |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-R02 | 630mm2 1C Al XLPE/PVC
6f6c37ee-60d8-5753-824e-fa3ae22434ce |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-R02 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
3e5fb01d-2b55-55a6-b646-8e0c62d07fb2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-R02 | 630mm2 1C Al XLPE/PVC | Electrical Checks
382e7d62-6c14-5586-b6a6-a546ec5a0cc7 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-R02 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
6036045b-47ad-4114-9784-86ebebd3045b |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-W02
a124d78d-02c5-48e2-b1d7-e231af7b2ae4 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-W02 | 630mm2 1C Al XLPE/PVC
0281497f-f8ce-512b-ba29-a8f131096014 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-W02 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
190fddfd-7d7a-5c3f-9ec5-cb5651616021 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-W02 | 630mm2 1C Al XLPE/PVC | Electrical Checks
b13b233a-1e59-5252-ba9c-0c621352839c |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-W02 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
ded7c0f3-cce5-4fa0-b330-2fc29f87b8ac |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-B02
5e9d71ba-afcc-45db-8069-432a5754dc64 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-B02 | 630mm2 1C Al XLPE/PVC
22fe4a88-85f4-5caf-8b98-51e7b6856223 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-B02 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
5ded4b5c-0037-582f-90d9-4365f44c20f1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-B02 | 630mm2 1C Al XLPE/PVC | Electrical Checks
947c8b4e-0221-5d28-a187-b18d9aaa295e |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-B02 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
e980c4c7-34cb-4365-9555-f917edca452b |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-N01
cd1cedba-eec7-4546-9a69-579e79a00c3a |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-N01 | 630mm2 1C Al XLPE/PVC
7c9cd98d-f8d0-55ca-b7e3-f60345b7e51e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-N01 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
8d8a9189-e298-5f14-8102-aa3ca66650f9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-N01 | 630mm2 1C Al XLPE/PVC | Electrical Checks
e3d1f54a-ad18-585a-8af3-09f9b8cac5d4 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-N01 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
6961a701-41de-4c64-bba9-5c9d104d20bd |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-N02
80e72fc9-f26a-4940-afd8-5eeab6dd8603 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-N02 | 630mm2 1C Al XLPE/PVC
a928c750-b489-5ced-a499-540e8b985790 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-N02 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
47736e33-1310-5ba3-a6c9-80fa199af3fb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-N02 | 630mm2 1C Al XLPE/PVC | Electrical Checks
e7f296bd-6789-5002-a9f6-4f46ed8e8d53 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Cables | TH000000BFA40GS010_-F43-N02 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
d5a8ddda-3aae-4cfc-9e13-3fafb5235f2a |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Earthing
b5dfcf4c-4a74-4083-bc0c-080c6f38b8f0 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Earthing | TH000000BFA40GS010_-F43-E01
b9223163-6a0e-4958-853c-3ccbd707986d |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Earthing | TH000000BFA40GS010_-F43-E01 | 240mm2 1C Cu PVC/PVC GE/YE
961e1f4b-a1a3-5f54-8466-9b7f9a3a939a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Earthing | TH000000BFA40GS010_-F43-E01 | 240mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
75fadfcf-dc63-5d4d-9acd-cc1ae7089e29 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Earthing | TH000000BFA40GS010_-F43-E01 | 240mm2 1C Cu PVC/PVC GE/YE | Test Results
4b6b5231-58a1-456b-8169-5c6a82d06a8e |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Earthing | TH000000BFA40GS010_-F43-E02
67cf6d01-7483-42c4-9b65-d1e361110d55 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-ORM-E-001 Ormat U3E Supply | Earthing | TH000000BFA40GS010_-F43-E02 | 240mm2 1C Cu PVC/PVC GE/YE
302a85f8-7152-5b53-a3ab-1fe24242deb3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Earthing | TH000000BFA40GS010_-F43-E02 | 240mm2 1C Cu PVC/PVC GE/YE | Electrical earthing system installation
5d556483-4a20-5e0a-b8d8-d219c94c9de2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-001 Ormat U3E Supply | Earthing | TH000000BFA40GS010_-F43-E02 | 240mm2 1C Cu PVC/PVC GE/YE | Test Results
26a746f5-d907-4498-acc2-689bea125586 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-002 Ormat U3C Supply
54191e80-36fd-4084-b91c-6957c91ed76e |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables
ff836a0e-08bc-4c43-b8d0-0cbd20a049e4 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-R01
040e2077-4af5-4aec-a3e4-9c0e2dad7f2d |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-R01 | 630mm2 1C Al XLPE/PVC
9dd9a7fe-2ccc-5282-9910-91765fbf5a60 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-R01 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
20e6909f-96dc-5dc9-8802-97c38c1a1be7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-R01 | 630mm2 1C Al XLPE/PVC | Electrical Checks
610c908d-dff1-51df-8f6e-c33e58615551 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-R01 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
2c628427-0e65-4717-82fc-8d5dcae1f71c |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-W01
acbd9403-34a0-4831-b57b-f2ad43cfbd51 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-W01 | 630mm2 1C Al XLPE/PVC
1e0df3c4-befe-5c17-8d8a-8750f926577d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-W01 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
9432cb92-2fa5-53aa-ae82-c17d8a007e9d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-W01 | 630mm2 1C Al XLPE/PVC | Electrical Checks
4377971c-96c7-5039-8cb5-bd866b5ddaf2 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-W01 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
300342fa-68e4-4f23-9acc-f685c68e27c0 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-B01
98c00fd2-4984-4885-94dd-df2bf57926be |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-B01 | 630mm2 1C Al XLPE/PVC
706087d9-15ea-56fa-bcc7-8b0b985cf2f9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-B01 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
66becc65-6dd9-520d-9f92-3dd4669dbc9f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-B01 | 630mm2 1C Al XLPE/PVC | Electrical Checks
3e40778b-223a-58b0-9237-ac82c97408f2 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-B01 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
75b2023c-5c28-47c3-8c3b-6101fbacf472 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-R02
22c66fb9-bf5a-4d1b-983c-1b362f1958f7 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-R02 | 630mm2 1C Al XLPE/PVC
2b35ab30-3e5a-56ec-aff6-bf846dcd91cf |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-R02 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
cca7e916-6e09-5db2-b1b5-2f017dbeaee3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-R02 | 630mm2 1C Al XLPE/PVC | Electrical Checks
c94a03d3-88cb-5322-b40a-029cb960fd91 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-R02 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
2d9b4bca-69d5-4bec-a8fa-f3a4ffb966d4 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-W02
3f641487-aa6c-4326-97a6-15f94d8dd61a |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-W02 | 630mm2 1C Al XLPE/PVC
3cbb9c25-612c-581a-85f8-3944a84b9af1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-W02 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
690d1aa8-e032-5e14-a11b-c5bad517d6a4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-W02 | 630mm2 1C Al XLPE/PVC | Electrical Checks
86bc1a53-f45e-537b-9a94-cbe9ad7271a2 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-W02 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
bb39966c-81e3-45f4-b42d-285e1afc3c20 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-B02
ebe4bbe0-7fd1-4256-91df-dd812d8e735f |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-B02 | 630mm2 1C Al XLPE/PVC
0afc079d-7ed5-56d5-836c-2cf814d2a4fa |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-B02 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
5da5d741-916c-5532-a773-6c23650b9a57 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-B02 | 630mm2 1C Al XLPE/PVC | Electrical Checks
444da683-955e-5e03-813c-7a58dbb3ae2b |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-B02 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
ad106ed0-2b84-432e-9556-95a4986fc840 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-R03
fb5db3a9-f82a-4a2b-9d41-242bad08f917 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-R03 | 630mm2 1C Al XLPE/PVC
09d8c63c-1adc-5cb2-ba06-b6f1c5b11452 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-R03 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
4ace400b-b35e-5eac-acf0-f742777e8c92 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-R03 | 630mm2 1C Al XLPE/PVC | Electrical Checks
e141c622-08e8-50e2-98db-5338c6935cbf |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-R03 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
f46c90d8-4a9f-4451-a455-75b4f43dd50a |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-W03
9bedc548-4d0e-4e23-8f92-4140fe59524c |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-W03 | 630mm2 1C Al XLPE/PVC
6a95e40f-b17c-54a8-b14d-c1ca755a7205 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-W03 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
6eef89fe-e5d5-56da-ba19-a4c8ac2d455c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-W03 | 630mm2 1C Al XLPE/PVC | Electrical Checks
ef30f16f-aa1d-5d7b-a145-64f33e8084d6 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-W03 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
b8f724f0-72c5-48da-816d-20a0adaeb9c4 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-B03
8a3c552f-c39b-4631-906f-f1b19220da80 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-B03 | 630mm2 1C Al XLPE/PVC
3f5a60fc-a6dc-5069-bbcb-354c6d3922ff |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-B03 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
bba1067c-840f-56f8-bc04-abb5c510abcf |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-B03 | 630mm2 1C Al XLPE/PVC | Electrical Checks
ee9afc91-74aa-5b1a-86d9-6729c722a0d4 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-B03 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
c8f3f87d-ef3c-496b-b06b-45a0340f113c |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-N01
ec2a3e29-6af4-4bf9-9fe1-27bd25aa3638 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-N01 | 630mm2 1C Al XLPE/PVC
ac421ace-30cb-5f29-87d9-bf32f1a4fc36 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-N01 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
34f8ff3f-1055-583f-8ac5-912f12a1dffb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-N01 | 630mm2 1C Al XLPE/PVC | Electrical Checks
60fb3506-4817-5d6b-8564-3641d42d2009 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-N01 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
ad61349c-cfdd-4c2f-98c7-817a013ed01d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-N02
19fd5fb4-e12a-4c3b-92ea-13259ba501ec |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-N02 | 630mm2 1C Al XLPE/PVC
cfd73393-c7fa-5f64-93ab-9eff542e5860 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-N02 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
b0ec5a1f-75e3-5dab-8cbf-83dfdc7bf8c8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-N02 | 630mm2 1C Al XLPE/PVC | Electrical Checks
69e102ef-2706-53de-8b93-1974467f620a |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-N02 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
b6647cf2-b908-4bcc-83af-266c0d67a405 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-N03
0f0c5998-5a48-4652-aecf-c3f9ce248c22 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-N03 | 630mm2 1C Al XLPE/PVC
b7d9ee44-0312-556d-b4d0-1878f17d1cc2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-N03 | 630mm2 1C Al XLPE/PVC | Low Voltage Cable
d9e6292f-d2c5-5daa-a1e2-ff6a2f1830ab |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-N03 | 630mm2 1C Al XLPE/PVC | Electrical Checks
3ec438ba-764d-59dc-94a2-2f957c5b100e |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Cables | TH000000BFA40GS010_-F01-N03 | 630mm2 1C Al XLPE/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
b4cef470-021a-4116-856c-d99a062777e2 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Earthing
e29cdf51-dcdc-4f1d-83ba-f66abbbccb08 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Earthing | TH000000BFA40GS010_BOND01
ab19d7cf-aac7-4475-bd8c-2b30bb85a096 |  | checklist-flat | not-started | ITR-CL-1-111 Electrical earthing | checklist-flat | FALSE | FALSE | TOP-ORM-E-002 Ormat U3C Supply | Earthing | TH000000BFA40GS010_BOND01 | 1.5mm2 2Pr CuSn ESCS
d6ae17a7-3164-5902-9dfd-1cbf270d3586 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Earthing | TH000000BFA40GS010_BOND01 | 1.5mm2 2Pr CuSn ESCS | Electrical earthing system installation
116cd7cc-ac9c-5399-897a-1633ba2b6b70 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-002 Ormat U3C Supply | Earthing | TH000000BFA40GS010_BOND01 | 1.5mm2 2Pr CuSn ESCS | Test Results
48fb204d-9990-4cf0-b054-44d182de036f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-003 Ormat SIS Interface
76b2bb85-ddf8-4d2a-81c9-db4d35741d9d |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-003 Ormat SIS Interface | Cables
973358df-b074-458a-9830-480f82a88913 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-003 Ormat SIS Interface | Cables | ORMAT-A01
61d9e19f-d90e-44cf-a171-00037dda198c |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ORM-E-003 Ormat SIS Interface | Cables | ORMAT-A01 | 1.5mm2 12Pr CuSn ESCS
e25fb5c4-a7f7-543c-8cac-3f659909b8ff |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-003 Ormat SIS Interface | Cables | ORMAT-A01 | 1.5mm2 12Pr CuSn ESCS | Instrument Cable
5ba19cd5-9d68-5d64-9ba5-310d58f9f9f5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-003 Ormat SIS Interface | Cables | ORMAT-A01 | 1.5mm2 12Pr CuSn ESCS | Electrical Checks
0b1c51de-28e4-4438-bf11-8b29669b46bc |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-003 Ormat SIS Interface | Cables | ORMAT-A02
915e5899-8334-4e90-a027-f045d33a62af |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ORM-E-003 Ormat SIS Interface | Cables | ORMAT-A02 | 1.5mm2 12Pr CuSn CS
d184aa32-fb6f-5935-8f3b-c1d4620e3f9f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-003 Ormat SIS Interface | Cables | ORMAT-A02 | 1.5mm2 12Pr CuSn CS | Instrument Cable
ad5fa750-1dd8-5004-8f30-7451a9b1895f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-003 Ormat SIS Interface | Cables | ORMAT-A02 | 1.5mm2 12Pr CuSn CS | Electrical Checks
31e47f44-d532-4dd3-b491-0cbc356578c1 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-003 Ormat SIS Interface | Cables | ORMAT-C01
8eb1ed39-bb3a-4a69-a833-29516af25b53 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ORM-E-003 Ormat SIS Interface | Cables | ORMAT-C01 | 2.5mm2 12C CuSn PVC/PVC
f0d90966-85dd-5a55-ab85-5b1e97426903 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-003 Ormat SIS Interface | Cables | ORMAT-C01 | 2.5mm2 12C CuSn PVC/PVC | Instrument Cable
75b8e0a4-8a06-58c5-9631-1d24eb151d49 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-003 Ormat SIS Interface | Cables | ORMAT-C01 | 2.5mm2 12C CuSn PVC/PVC | Electrical Checks
41f2a6d2-1bd6-4a40-9327-af96ad3ad710 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ORM-E-003 Ormat SIS Interface | Cables | ORMAT-C02
54367435-7845-49c4-b588-6f7375d71f64 |  | checklist-flat | not-started | ITR-CL-1-132 - Instrument/Control Cables | checklist-flat | FALSE | FALSE | TOP-ORM-E-003 Ormat SIS Interface | Cables | ORMAT-C02 | 2.5mm2 12C CuSn PVC/PVC
f1006927-d43a-5e23-a4e3-49da74a7fd55 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-003 Ormat SIS Interface | Cables | ORMAT-C02 | 2.5mm2 12C CuSn PVC/PVC | Instrument Cable
3261c8ab-2462-5903-8370-8b8813d21d99 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ORM-E-003 Ormat SIS Interface | Cables | ORMAT-C02 | 2.5mm2 12C CuSn PVC/PVC | Electrical Checks
b05eb0c1-52ab-4e3b-b77e-9eb44a2cd641 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-004 Building Light and Power
a3f9ca51-13dd-403a-a853-81d7500daa69 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-004 Building Light and Power | Electrical Installations
0e61aeaa-f405-4a3d-9aba-6ab311356c1c |  | checklist-flat | not-started | Cable Pre-installation | checklist-flat | FALSE | FALSE | TOP-ASB-E-004 Building Light and Power | Electrical Installations | Cable Pre-installation
09bb1981-5827-5613-ad9f-0766f89e4922 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Electrical Installations | Cable Pre-installation | Cable Pre-Installation
10893ed9-2547-4c1c-8d02-34c049833eb3 |  | checklist-flat | not-started | ITR-CL-1-101B Cable Supports Above Ground | checklist-flat | FALSE | FALSE | TOP-ASB-E-004 Building Light and Power | Electrical Installations | ITR-CL-1-101B Cable Supports Above Ground
51f6b21d-6f34-53fd-b054-bce6457517d4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Electrical Installations | ITR-CL-1-101B Cable Supports Above Ground | Cable Supports Above Ground
81d0e87c-516b-40df-bc29-a1356b8beb6e |  | checklist-flat | not-started | ITR-CL-1-101A Conduit/Ducting Below Ground | checklist-flat | FALSE | FALSE | TOP-ASB-E-004 Building Light and Power | Electrical Installations | ITR-CL-1-101A Conduit/Ducting Below Ground
b06ea0a2-b0f1-579b-b73a-6575f6f4dae0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Electrical Installations | ITR-CL-1-101A Conduit/Ducting Below Ground | Conduit/Ducting Installation Below Ground
c97b49e6-2156-4156-b4fb-018437861dd5 |  | checklist-flat | not-started | ITR-CL-1-102 Entec - Distribution Board Installation | checklist-flat | FALSE | FALSE | TOP-ASB-E-004 Building Light and Power | Electrical Installations | ITR-CL-1-102 - Distribution Board Installation
8988fc73-df5e-5f42-91ab-433ad87aab94 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Electrical Installations | ITR-CL-1-102 - Distribution Board Installation | Distribution Board Installation (Mandatory Photo)
d122b5b0-306f-53db-87ad-d982a4de080e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Electrical Installations | ITR-CL-1-102 - Distribution Board Installation | Test Results
a8aaf23c-aa27-5324-8e6b-650ee4733268 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Electrical Installations | ITR-CL-1-102 - Distribution Board Installation | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
8972dc93-29a0-46db-bea9-131260078230 |  | checklist-flat | not-started | Cable Test Record | checklist-flat | FALSE | FALSE | TOP-ASB-E-004 Building Light and Power | Electrical Installations | ITR-CL-1-103 - Schedule of Test Results DB
7cf7b1c5-61ad-5179-9f54-9a51f8f8349a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Electrical Installations | ITR-CL-1-103 - Schedule of Test Results DB | Upload completed ITR scans
10e8eb73-28f1-4c94-aa8f-bdc846e79f14 |  | checklist-flat | not-started | ITR-CL-1-100 General Electrical Equipment | checklist-flat | FALSE | FALSE | TOP-ASB-E-004 Building Light and Power | Electrical Installations | ITR-CL-1-100 General Electrical Equipment Install
0dcfcaa2-2748-5558-947f-5f44ea64a549 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Electrical Installations | ITR-CL-1-100 General Electrical Equipment Install | General Electrical Equipment
3e03517f-1522-5870-98ed-f6c0d20f73c8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Electrical Installations | ITR-CL-1-100 General Electrical Equipment Install | Electrical Checks
abfaea62-740a-5425-8628-795e472fae8c |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Electrical Installations | ITR-CL-1-100 General Electrical Equipment Install | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
1f01c524-e272-41af-aa3a-82eb58fb0149 |  | checklist-flat | not-started | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP-ASB-E-004 Building Light and Power | Electrical Installations | Certificate of Compliance
bf59f15e-bb26-53b3-bc76-34e5231dbcd2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Electrical Installations | Certificate of Compliance | Please upload Certificate of Compliance here when complete (COC)
2b3a1693-cbc6-4a55-8ca0-fbc5946e8e92 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-004 Building Light and Power | Cables
b84401ac-2d3f-47f3-975f-d1e669029d20 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F01-P01
1e0cf795-d488-4ab7-a286-07e31555be71 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F01-P01 | 2.5mm2 2C+E CuSn PVC/PVC
da4ceb8f-53a6-5436-81bf-d55ac9e44217 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F01-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Low Voltage Cable
5ebd8315-995e-5414-88e6-72c4e9ba1824 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F01-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Electrical Checks
a549cb12-9ddf-5c97-93b0-0d89aef286d3 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F01-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
cc7868b2-51b2-4290-8b8e-bfa9d95daf4f |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F03-P01
27161449-20ff-48b2-a710-67054f144bb0 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F03-P01 | 2.5mm2 2C+E CuSn PVC/PVC
0458f699-c9e4-5124-b2f8-94141d664174 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F03-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Low Voltage Cable
cba22e20-89ab-5c8e-8743-d9fda1ecdf93 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F03-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Electrical Checks
fbd1fda1-00b7-5935-b02b-07fe61024057 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F03-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
ef1cc7d1-b5b9-4c2c-927e-d5b06da22bfa |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F04-P01
4f096d00-e541-433e-af04-887a5c12afe4 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F04-P01 | 2.5mm2 2C+E CuSn PVC/PVC
6c6893e7-21d0-56e3-922b-b58ab021583d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F04-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Low Voltage Cable
fb1ea86a-99b1-5bce-ad7a-0d4ed4786125 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F04-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Electrical Checks
53355abb-07dc-5e70-915d-61409724e455 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F04-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
c8fc0bec-97f3-4334-aaf9-e38ab66966a5 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F05-P01
69480dde-5e38-4268-959c-bbf7454b4cdd |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F05-P01 | 2.5mm2 2C+E CuSn PVC/PVC
ace17420-b9e4-55c5-a879-9ec84f0c83bb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F05-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Low Voltage Cable
2bad783e-d51a-539c-bff6-2000e1f57ce3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F05-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Electrical Checks
c917ae36-8121-5720-8dd4-3da2e3964997 |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F05-P01 | 2.5mm2 2C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
9d852198-bc1f-499d-a499-b444a6c1e851 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F06-P01
84515265-c722-4e50-9ec3-f60f750c3e72 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F06-P01 | 4mm2 4C+E CuSn PVC/PVC
57b3aa44-c792-5b8e-8125-d008ed4e6982 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F06-P01 | 4mm2 4C+E CuSn PVC/PVC | Low Voltage Cable
e861800c-c66c-52ca-a1ce-cb07b8eedca8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F06-P01 | 4mm2 4C+E CuSn PVC/PVC | Electrical Checks
bdf657b0-7518-5dd2-95cd-e0b77b92452a |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F06-P01 | 4mm2 4C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
092ed425-389f-4424-bfc4-ed587771b2a4 |  | folder-normal | not-started |  | step | TRUE | FALSE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F09-P01
7f03e132-6053-4aa7-9c40-e2b4dce76e50 |  | checklist-flat | not-started | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F09-P01 | 6mm2 4C+E CuSn PVC/PVC
69bc9fcd-981a-5ba1-8aa2-6762a571fb5a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F09-P01 | 6mm2 4C+E CuSn PVC/PVC | Low Voltage Cable
27300f61-f259-5bf2-b98c-3e23c7ecc545 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F09-P01 | 6mm2 4C+E CuSn PVC/PVC | Electrical Checks
33071cef-69f3-511d-8902-fcf5d067dafc |  | holdpoint | not-started |  |  | TRUE | TRUE | TOP-ASB-E-004 Building Light and Power | Cables | TH000000BKB10GS010-F09-P01 | 6mm2 4C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
87d2247c-eaac-4ee1-95ac-d0b7e02ca491 |  | folder-normal | pass |  | step | TRUE | FALSE | TOP-ASB-E-007 Temporary Construction Supply to ASB & SEP
6144d89d-8638-450c-9159-de1dace2b8d9 |  | folder-normal | pass |  | step | TRUE | FALSE | TOP-ASB-E-007 Temporary Construction Supply to ASB & SEP | Cables
13d27eb3-8a2a-407b-a1c5-c6df68f5bd14 |  | folder-normal | pass |  | step | TRUE | FALSE | TOP-ASB-E-007 Temporary Construction Supply to ASB & SEP | Cables | TEMP SUPPLY/1
25cfaffd-eb0b-4ee8-9138-9b14c637a408 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ASB-E-007 Temporary Construction Supply to ASB & SEP | Cables | TEMP SUPPLY/1 | 25mm 4C+6mmE PVC/PVC Flex
8450a824-032e-5013-be79-5ae6d4f16b04 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-ASB-E-007 Temporary Construction Supply to ASB & SEP | Cables | TEMP SUPPLY/1 | 25mm 4C+6mmE PVC/PVC Flex | Low Voltage Cable
d7212ed7-69e4-5edc-9324-7b76272b21b1 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-ASB-E-007 Temporary Construction Supply to ASB & SEP | Cables | TEMP SUPPLY/1 | 25mm 4C+6mmE PVC/PVC Flex | Electrical Checks
2b558dca-f6fb-5543-a5d1-bee3ed86180e |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-ASB-E-007 Temporary Construction Supply to ASB & SEP | Cables | TEMP SUPPLY/1 | 25mm 4C+6mmE PVC/PVC Flex | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
6189c877-6b6d-4a52-9a08-cea870f846bd |  | folder-normal | pass |  | step | TRUE | FALSE | TOP-ASB-E-007 Temporary Construction Supply to ASB & SEP | Cables | TEMP SUPPLY/2
6c146f95-6613-4105-af40-bd954b15ff1c |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | TOP-ASB-E-007 Temporary Construction Supply to ASB & SEP | Cables | TEMP SUPPLY/2 | 25mm 4C+6mmE PVC/PVC Flex
37eb4bfc-35c5-529c-897f-1c3d6d0ec590 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-ASB-E-007 Temporary Construction Supply to ASB & SEP | Cables | TEMP SUPPLY/2 | 25mm 4C+6mmE PVC/PVC Flex | Low Voltage Cable
c522f7c6-3447-56fe-aea0-ba8d842283bf |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-ASB-E-007 Temporary Construction Supply to ASB & SEP | Cables | TEMP SUPPLY/2 | 25mm 4C+6mmE PVC/PVC Flex | Electrical Checks
befa4c19-b528-5565-a88c-672b4a99e5ab |  | holdpoint | pass |  |  | TRUE | TRUE | TOP-ASB-E-007 Temporary Construction Supply to ASB & SEP | Cables | TEMP SUPPLY/2 | 25mm 4C+6mmE PVC/PVC Flex | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
39717749-61db-4aed-a57f-9663e4ef130e |  | checklist-flat | pass | Certificate of compliance (COC) | checklist-flat | FALSE | FALSE | TOP-ASB-E-007 Temporary Construction Supply to ASB & SEP | Certificate of compliance (COC)
4f77f15d-ab8b-52df-9021-8534bb1b3bd0 |  | checkpoint-status | pass |  |  | TRUE | TRUE | TOP-ASB-E-007 Temporary Construction Supply to ASB & SEP | Certificate of compliance (COC) | Please upload Certificate of Compliance here when complete (COC)
23b55c31-c7e1-4723-9fcb-c7417fb23988 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Inground Earthing
cce7ba0c-0b5b-4a85-a52c-2b967aaefd0c |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Inground Earthing | Cadwelds
0abaf9b2-02f1-44ff-aa9d-fb01c2e2ed33 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Inground Earthing | Cadwelds | TH32 Wellpad
c3266496-7a1f-4b1b-b098-9eb8d1b48df5 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #1
c59f650b-90cb-5f00-b4cf-7815e5e7dc8b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #1 | Mold type, # and cable size identified
f7205518-40e6-5f25-9430-8dd3d7b48433 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #1 | Cadweld Visual test
d564c7da-01ee-5b11-94df-482fba1f2b55 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #1 | Cadweld Ductor test
7df09eb3-8db9-5550-b04d-4ace410541c6 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #1 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
eb23b98d-f31c-5289-851d-42ba5b6558f4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #1 | GPS coordinates taken
5faddcb1-2237-4e19-b876-b5fab93c8384 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #2
0765c0c8-ab31-5fb5-a806-f27a597d3511 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #2 | Mold type, # and cable size identified
c77a4e19-e52e-57b8-8bc0-33e4b872fc11 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #2 | Cadweld Visual test
5ddab91a-d076-5309-bcfd-73d645df49de |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #2 | Cadweld Ductor test
b5630408-76fd-5b3d-ae7f-308131b2ff3d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #2 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
92016a67-6573-5449-b841-583329eb6c6a |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #2 | GPS coordinates taken
055c20dc-f0f2-453e-afa2-89c65b6079a6 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #3
8697ff41-0163-5bfd-b585-92c39af8a452 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #3 | Mold type, # and cable size identified
d03b6cb1-77a8-56e0-b159-66be15578581 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #3 | Cadweld Visual test
64371f92-3e89-5e24-9b1c-7e4db59886f7 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #3 | Cadweld Ductor test
869261ad-7607-5bb1-88a6-b0435a32035f |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #3 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
6953eb93-8e72-5077-b18d-e48445ea87cb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #3 | GPS coordinates taken
d2dc91c6-b4fb-4e8b-b203-b2aecdb5a31e |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #4
3d26b9ed-2e1b-5604-b51b-858ce25c54e9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #4 | Mold type, # and cable size identified
dff838fe-e79a-564f-af8e-196088618d3b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #4 | Cadweld Visual test
b47e7135-1e13-586e-b91c-053d28c64d52 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #4 | Cadweld Ductor test
5a82956b-90ae-5659-9cd3-1d9359878fd1 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #4 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
6db9ea9d-5c3a-5f5f-a8fa-0f0938fc107e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #4 | GPS coordinates taken
fc6adfbf-8027-4a37-9650-436aee18457d |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #5
9c8f151f-f975-545f-8af7-37bd69562b89 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #5 | Mold type, # and cable size identified
72212d80-7f14-5b04-ae11-37c639a4f406 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #5 | Cadweld Visual test
508079ea-ae29-5125-86d3-f178ff1cf1bc |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #5 | Cadweld Ductor test
0199bc28-72cc-56d2-a53d-9c964f5187e2 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #5 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
ee1a216a-42a0-56e5-a24e-47b5acd36056 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #5 | GPS coordinates taken
5813ab49-cd8f-476e-8669-46a22edb3016 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #6
a4f20e67-bdd6-5b11-b814-75156f046553 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #6 | Mold type, # and cable size identified
a18f1976-4cb5-594a-9645-ae2a960fabe8 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #6 | Cadweld Visual test
e3ca235d-8aa4-599c-ad5d-41826a95c05a |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #6 | Cadweld Ductor test
9bd731cb-11f6-591d-8d37-bfaf3d40691f |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #6 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
b610b36f-8bd2-5424-bd15-8602fccd12d7 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #6 | GPS coordinates taken
d1b2ba27-83e8-4c0b-9212-2cb6f8c87d43 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #7
550fdc37-e32b-59d1-bd3c-7e374fa5a80b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #7 | Mold type, # and cable size identified
dbb7f334-f5da-5b19-8dda-56417dd0b189 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #7 | Cadweld Visual test
a32f469b-1a4e-5355-b7b6-d862af6ab1b5 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #7 | Cadweld Ductor test
5d4b2ff2-8940-5037-b31c-95bc5e4fb572 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #7 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
949298a9-66ac-580b-9803-4b0b449561e0 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #7 | GPS coordinates taken
699cb2e1-6289-4703-8fc6-34357e401f52 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #8
ea4207a5-82fb-55ab-9a52-758e0ed49b81 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #8 | Mold type, # and cable size identified
0e4eea4e-bd0e-51bb-83ab-20bada6f0fdb |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #8 | Cadweld Visual test
ee3768fd-431a-51b2-9c6f-b5b08a14d372 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #8 | Cadweld Ductor test
2ada41ad-6e12-5357-8a43-e1349d2aa74d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #8 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
5674b1e3-9ffb-5e60-a487-f2182192e0ee |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #8 | GPS coordinates taken
341bef82-9aa0-4f0f-a974-d02705dc863a |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #9
df202ca2-7b58-5a31-a26c-2497bce99e1c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #9 | Mold type, # and cable size identified
f91a2a34-8a0a-5dc0-8808-3b0119bc638d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #9 | Cadweld Visual test
33d751c9-79ce-515c-b4cf-b9c461cb8f3c |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #9 | Cadweld Ductor test
6fbd3dba-57bc-592c-ba7a-8745b1a62a75 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #9 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
6551a439-751b-5755-a579-1d0b8246ed8d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #9 | GPS coordinates taken
959ccae0-b647-4a03-80e9-5753827751ca |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #10
08b9691c-6a38-5406-9842-7649372a416b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #10 | Mold type, # and cable size identified
097d720b-62f2-562c-9e23-36b0d05a86d3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #10 | Cadweld Visual test
33bcc4d5-55d5-501e-bc5d-bb2dff8e3b15 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #10 | Cadweld Ductor test
cab6f8eb-34af-5cdb-929f-1dd6efc73387 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #10 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
9766e30b-1d91-5c2a-9068-b24264be436c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #10 | GPS coordinates taken
a4c9239d-8f42-425f-8399-07cc4bb3bdc0 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #11
e02b8b30-2988-5a25-a51f-52214ece75a7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #11 | Mold type, # and cable size identified
e8aa8e0c-0c66-58ee-8e88-db3c46db6abf |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #11 | Cadweld Visual test
16b72b29-3990-518f-b598-d662f0d5ad9e |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #11 | Cadweld Ductor test
d586894a-e45d-52fc-80c4-01620ec190cc |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #11 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
0faabb93-2fe2-5af7-aeff-81df113f8acb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #11 | GPS coordinates taken
2e42ca76-1516-4db4-b178-bba69e51c8c7 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #12
ec26561c-98ab-5c01-8f01-72988a9a4430 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #12 | Mold type, # and cable size identified
50839cd1-fe4a-5345-a737-6c29e30a5a32 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #12 | Cadweld Visual test
902878ab-5483-586b-bc73-d5df6b6cd223 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #12 | Cadweld Ductor test
874badb5-0a6e-59a6-ae34-0cea45cd6c5b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #12 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
ae65742c-92de-5a7c-8e97-ddab47d1fa53 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #12 | GPS coordinates taken
cf849e44-102b-49db-8843-9c64865c6e59 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #13
338b5192-935e-5756-866e-49e9640cb3ce |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #13 | Mold type, # and cable size identified
fda8a622-4263-5fca-a118-b3a62bbd7128 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #13 | Cadweld Visual test
b5975f86-b800-5c23-891e-d5a9424d39c8 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #13 | Cadweld Ductor test
80a0731d-1b65-53a6-b97c-50fc4eac578d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #13 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
0f8de45b-d00a-5c20-a30b-1b53d1183e83 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #13 | GPS coordinates taken
258bdb38-2a33-44a5-a691-ea6090846a62 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #14
c4abb651-58ed-584b-b6c9-c569d77d55e8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #14 | Mold type, # and cable size identified
7bd78fbf-4705-5a03-b294-2abb121ac93b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #14 | Cadweld Visual test
290a9d2c-8b09-5ec8-8e36-8fae79f32044 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #14 | Cadweld Ductor test
002689b2-ec11-5cfc-ba61-31bc3d151a38 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #14 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
cd569f60-bb01-51be-8187-e9aba16b7b70 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #14 | GPS coordinates taken
537521e1-f971-4ff2-9808-afe2e2cc388a |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #15
e125773f-c758-5c6e-9cdb-d3fec9329ef9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #15 | Mold type, # and cable size identified
084df771-bf2f-5ec2-b0b6-b9a90d6af33a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #15 | Cadweld Visual test
85fcf073-c4d5-51df-afdc-36441ca7e600 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #15 | Cadweld Ductor test
64198ae9-b5c0-5784-b44e-943df4b11ada |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #15 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
b3d640a2-98ff-5d5a-b6bc-2f000037d95e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellpad | Cadweld #15 | GPS coordinates taken
d508eb31-2aeb-49f5-ae01-48f5ea72130c |  | folder-normal | not-started |  | step | TRUE | FALSE | Inground Earthing | Cadwelds | TH14 Wellpad
c3d13de0-594b-4a15-8a96-5b3b0c640572 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #1
63ecfb8a-2cca-5f2a-9c14-3e37e708edb0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #1 | Mold type, # and cable size identified
cc242ec4-4287-5dfe-8e30-644973f5f532 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #1 | Cadweld Visual test
815b06b6-ffb6-5e56-a688-7160b29d163e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #1 | Cadweld Ductor test
173c81b7-ec87-59f2-b775-2c597d0eed1c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #1 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
44b89ec5-d307-5f32-a3aa-7ff777f9ab31 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #1 | GPS coordinates taken
c6aeef2f-bf59-48ab-b512-134d790bee65 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #2
a9a7ca72-989a-57f1-9340-b94386caad97 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #2 | Mold type, # and cable size identified
c90068f7-8a9b-5ffd-af59-fd3d6079eea9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #2 | Cadweld Visual test
2500512f-b49d-5ad4-8a62-4d92319b0c27 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #2 | Cadweld Ductor test
1179639f-6e08-58f4-a9df-95df8b7b87d3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #2 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
e196328e-3a52-5c23-af56-66fb7de50a4b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #2 | GPS coordinates taken
fc6f3c98-34c6-4de9-a04a-20ba16355910 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #3
b4c1cc4c-ba31-5d72-822d-1cb9fc1aa9ec |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #3 | Mold type, # and cable size identified
b613ea38-54be-5a08-b2ee-89362b21c7c6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #3 | Cadweld Visual test
85f6a453-9fac-5c0f-8128-93aa6ead8da9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #3 | Cadweld Ductor test
a0825bb9-c00e-5ed0-8826-f7b5b8e720c6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #3 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
4f4b9cf7-9664-5aa9-b33a-45e759d3392b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #3 | GPS coordinates taken
97a999ef-93be-4238-979a-7c0afabdf8c6 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #4
08e77bb3-e72d-564d-8ee1-0ffcabb7f707 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #4 | Mold type, # and cable size identified
3837da52-68e7-5b7a-bc02-844ff86656ed |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #4 | Cadweld Visual test
beb907e9-9444-5e73-a066-01b50cd060d6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #4 | Cadweld Ductor test
f45a986d-edaa-5483-bb2a-05d0aadcfdd1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #4 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
216d4020-8012-5029-91d8-d7b2d54da52b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #4 | GPS coordinates taken
259e8896-61ba-41a5-9f3f-fa2d31bb13fc |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #5
aca438f9-9f7d-52e6-b7dc-1c94f8750c28 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #5 | Mold type, # and cable size identified
95c171de-0e63-558d-ba62-c2cdd2f4116b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #5 | Cadweld Visual test
7e701d67-3e15-5a85-855b-08be83aeb68a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #5 | Cadweld Ductor test
3da88b38-f210-516e-8376-e3cc8ec61502 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #5 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
c965b629-21d1-5f3b-a4f7-06732d33b542 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #5 | GPS coordinates taken
e3e83557-e1ad-4bad-af88-54a7dbd334b0 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #6
ada972b6-8335-59b8-9bbc-529f964dee88 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #6 | Mold type, # and cable size identified
45466e22-9e43-50db-a871-fd1faf37b2b9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #6 | Cadweld Visual test
cbcaf700-bf86-5f73-a7a9-0e2fc61515ae |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #6 | Cadweld Ductor test
d502fe44-b854-5be0-8f43-439e279c9549 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #6 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
3251ec81-d7ce-5a4f-9cdd-dc4b0b0b6de9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH14 Wellpad | Cadweld #6 | GPS coordinates taken
415ada8c-79d3-479f-af82-0e0dc2199463 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Inground Earthing | Cadwelds | Separator
f85c64fc-6107-4c31-a0ea-9bedd0dc6e06 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #1
29152d3c-f7b7-5d2b-85a3-669dbeb7b3b2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #1 | Mold type, # and cable size identified
90cf7370-0df4-560f-a24c-f28f9aea36b6 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #1 | Cadweld Visual test
20ca1a46-5727-5dd4-9085-a536187e907d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #1 | Cadweld Ductor test
2012de03-57c9-5c8f-bdf1-4e11ac68fc90 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #1 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
867f8278-3b0c-517d-8c16-1b03fad151cb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #1 | GPS coordinates taken
6fbdec56-b44a-40a0-b31e-57d6a44e29c6 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #2
0f0f3c7d-efaa-5a97-93d2-2f6f33c202bc |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #2 | Mold type, # and cable size identified
ad81f23c-087f-5033-abac-0d067b90f0f6 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #2 | Cadweld Visual test
37d1c7a6-02a2-5a34-9eb5-29bae676f9e8 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #2 | Cadweld Ductor test
588e4ca8-adc5-5a80-840b-cc35478e949c |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #2 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
2debe0f2-13e1-5eb0-97b1-ec55bf2561c9 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #2 | GPS coordinates taken
16cfb67e-2090-486e-8e47-06fd85595c58 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #3
595bf4d8-b65f-56b0-b7d4-d3937b57b25b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #3 | Mold type, # and cable size identified
ee4f4a89-e8b4-5ba4-bb94-1dddf5c37334 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #3 | Cadweld Visual test
eb421f63-b995-5a2b-8d36-592f30e45862 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #3 | Cadweld Ductor test
ed3d1c31-a407-5585-a821-844c8563d4c8 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #3 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
f34647dd-56fb-54de-85f2-046b023ac6dc |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #3 | GPS coordinates taken
c51bdf55-0440-494a-ac3d-2adf222730a7 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #4
ceb02a89-0271-50c3-a952-402a2f24eec0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #4 | Mold type, # and cable size identified
99b53a3b-e9a0-5ee6-8190-a2b5dff67fc1 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #4 | Cadweld Visual test
d7586b90-3f89-5f5c-bd58-bb3e7575040a |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #4 | Cadweld Ductor test
bd172bd0-a017-5f94-a8a4-3874006d6383 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #4 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
3042417a-51ef-5eb8-a0d1-d1421e1cacc6 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #4 | GPS coordinates taken
8f33b608-e991-48b8-ba7e-76fd63f621b5 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #5
78f48a17-44b3-564c-ad55-cba24b55ad9b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #5 | Mold type, # and cable size identified
3fbeb821-01cd-56be-b3a2-8a1e0c64c09e |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #5 | Cadweld Visual test
6aa44e82-89c1-5f0c-a0fe-7e0ffffc0012 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #5 | Cadweld Ductor test
b3adf995-c5e2-5009-b228-3d04bc0cdad1 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #5 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
0130b337-e13e-5151-9bc5-626cc7a0fce9 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #5 | GPS coordinates taken
0b27f578-6cea-43b9-a01d-6b5323dd4f5a |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #6
080623a1-847d-539a-ab00-a05da21a0487 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #6 | Mold type, # and cable size identified
fa1efeac-ffa2-551f-950a-00f11f39c416 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #6 | Cadweld Visual test
992db9d6-82b6-5b4e-859d-e580e726f654 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #6 | Cadweld Ductor test
71be3017-5e8b-59a2-9584-eaa23f312760 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #6 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
3cee414a-8a7f-54a0-91bc-13bd10bad287 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #6 | GPS coordinates taken
dd9b92e9-c201-4182-a2b7-28383b56d2a0 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #7
77b0b7c7-7496-525f-8250-9e450c23adec |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #7 | Mold type, # and cable size identified
bdc8e9d3-447d-5af7-80f3-c89cbd38a803 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #7 | Cadweld Visual test
63ae7093-412c-5fcc-909f-30a4ce77a72b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #7 | Cadweld Ductor test
5ca5f522-3b03-5443-add1-055d4c135f65 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #7 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
54b2ac23-b583-5243-b179-82fd4de72041 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #7 | GPS coordinates taken
bc92fede-8d69-486d-a6e8-fc147fd3f42b |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #8
7936af5d-48e4-5ec2-8099-6c19b8c85892 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #8 | Mold type, # and cable size identified
87e5bc37-f5a1-5a9c-bdb0-3692310ce217 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #8 | Cadweld Visual test
fcbcfe33-5973-54de-8832-c661a785d9dd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #8 | Cadweld Ductor test
566b4ff2-a3a1-56d8-98a0-78fa2023c728 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #8 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
b08eca09-0c11-57a9-90f1-af58c0fc034a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #8 | GPS coordinates taken
ecdf40d6-27d5-4167-aa76-4ae96b401f8f |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #9
70044665-8e6b-5797-942c-28aec4305a8a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #9 | Mold type, # and cable size identified
df7ed1d6-bf70-515c-ad21-d2f24f26d928 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #9 | Cadweld Visual test
b51e59ad-be5e-540f-871a-f8a566dc91e2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #9 | Cadweld Ductor test
f9b3ce13-bd87-5764-ab62-af278886536f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #9 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
42fe5cc9-3b09-5876-9c53-36a783216d2a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #9 | GPS coordinates taken
e51140d0-88a9-40e8-a149-a8a757599abf |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #10
c47ed039-b762-5846-a6fe-279905982a27 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #10 | Mold type, # and cable size identified
62286699-a65a-5f97-b966-965f1885b52a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #10 | Cadweld Visual test
14d40b5d-d253-524e-a73c-c35339f7883d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #10 | Cadweld Ductor test
f7d4413e-2325-50f2-93b5-e1a824cec67f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #10 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
8f644a8a-b570-51c2-b37c-fded3fba334b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #10 | GPS coordinates taken
3253abdf-4721-4731-b5c9-606fd1486422 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #11
f849ad4d-9eaa-5937-8e7a-ac86332926a2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #11 | Mold type, # and cable size identified
9939862e-b3ac-5968-be68-21eeefd79ffa |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #11 | Cadweld Visual test
6ed00cda-527a-5950-901d-a43c7b4ed236 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #11 | Cadweld Ductor test
538ea3e6-04de-521b-a34a-f7ca1226da64 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #11 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
0018a259-ee4f-559a-99f3-2cd664669e5e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #11 | GPS coordinates taken
15aa5517-92cd-4a08-add7-a8b1cee84aec |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #12
59b88e0b-dcb2-564e-9c19-d8f17d51947b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #12 | Mold type, # and cable size identified
6a90c9f8-43a5-5f86-90b0-1adf4502759b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #12 | Cadweld Visual test
0004bd5b-0223-5ab2-be78-55770fbceebd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #12 | Cadweld Ductor test
eaf2c1cb-ec5e-5946-85b3-28f9acdc0e2e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #12 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
54ee383a-e902-58bc-a00c-ab45bed02cd4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #12 | GPS coordinates taken
2536ee98-3bc3-4283-940a-340794329ae3 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #13
130f0cb3-98d8-5752-84b2-0cb03c624dcb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #13 | Mold type, # and cable size identified
9b1ea7e4-ecbd-5d40-a668-cc27bfcbaa6c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #13 | Cadweld Visual test
78eab1e5-c104-57c2-9d64-5fe6731b0178 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #13 | Cadweld Ductor test
56f9049b-c09c-5908-ac0d-39512e350b7c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #13 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
b1265ed4-63ac-5234-ad8e-86926b14b661 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #13 | GPS coordinates taken
b3cb00e4-1c4b-4be6-98f8-c49d435bc941 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #14
d5ad64a2-a980-50a4-abfe-a525abe32dd5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #14 | Mold type, # and cable size identified
27d4581f-4435-5602-82b9-a1d415e99a4e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #14 | Cadweld Visual test
f56e8d36-0854-515d-87d9-015f207b158d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #14 | Cadweld Ductor test
ded09529-159d-56c0-b117-20819333372d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #14 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
123703fc-38dd-569d-b558-6d33010eea79 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #14 | GPS coordinates taken
45f9da7f-7d60-4cbc-8c6d-43ab814d9af0 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #15
04a0300a-9eae-50cd-ae3f-02cf21dd929e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #15 | Mold type, # and cable size identified
981a7fda-fe33-5343-8019-aea06c02ff69 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #15 | Cadweld Visual test
7ed698b8-f7a5-5785-be97-35e611b239e0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #15 | Cadweld Ductor test
d36859c9-aa87-5b0d-ad52-37764fa3b93a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #15 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
4ec3c3d3-1352-5644-af65-7d1f0f572993 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #15 | GPS coordinates taken
c83fdf68-d73b-47f9-b440-94c17dee0cec |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #16
0904e30b-a1d8-56c4-8d1b-cac0e14cb341 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #16 | Mold type, # and cable size identified
0f41c7d3-716e-5358-b2ad-ae6a4d192e1a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #16 | Cadweld Visual test
3d36c844-fb22-5ade-8a7d-e0767a87900c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #16 | Cadweld Ductor test
0078d527-9ba8-5e77-81b8-1b91146932f1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #16 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
36a08f4b-dd06-547d-a1b7-f0f3c77c7d30 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #16 | GPS coordinates taken
495d33b5-9493-48a3-87eb-c41823ee96db |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #17
b6825ba6-d29b-51a4-8c07-b2c954df391d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #17 | Mold type, # and cable size identified
eaef9e1b-fa72-56fd-a05b-141e3458bed1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #17 | Cadweld Visual test
a214d6dd-61ac-5053-8bf4-abd456f53322 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #17 | Cadweld Ductor test
3e527d81-926e-5ca0-be77-50860c438283 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #17 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
c28c44e1-3739-5130-9d80-e04aa51ef3d0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #17 | GPS coordinates taken
686d619f-8e45-4d49-9dcf-b2ea1739374d |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #18
006fc95b-b9cd-5852-b1b8-8fe9bcb5b15a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #18 | Mold type, # and cable size identified
1ee369d0-10df-5637-adde-55bffa4b76da |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #18 | Cadweld Visual test
10dd4666-8875-5fa2-b901-702d1aa0cf28 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #18 | Cadweld Ductor test
1f3c9615-8433-5e69-9a10-c04940617d6f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #18 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
7e94872e-d189-5f85-906e-7f1ffc2a68fb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #18 | GPS coordinates taken
7e494718-5f7c-45b3-933e-09191518b761 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #19
034dd355-73c0-5494-9d58-d5ec6febb93d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #19 | Mold type, # and cable size identified
8a7b759a-2656-55cc-8b84-da4ac63298dc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #19 | Cadweld Visual test
39c2a722-68ea-5127-890f-a0c429b824ea |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #19 | Cadweld Ductor test
616ba4b8-a92c-55b6-83cd-cfc295a2733b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #19 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
282eb774-c8eb-585d-a372-68f5e9a81dea |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #19 | GPS coordinates taken
515880dc-0048-444f-a500-2ff546b0fc5f |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #20
6cf3fe24-d528-56d5-8b4c-37a269572df4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #20 | Mold type, # and cable size identified
ff40dabe-94cb-5ea6-8981-03e1277d340a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #20 | Cadweld Visual test
1fb833d8-b17c-5657-9600-ac3648dc4a51 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #20 | Cadweld Ductor test
52007d49-d949-5b67-b893-26df9d5d27aa |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #20 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
470e2f9e-dc8e-5f60-9f26-a85c4d975297 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #20 | GPS coordinates taken
bb913f43-f2df-4179-be63-0571c017dea9 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #21
3b94583a-fa97-57ff-be83-fcab6d5578fc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #21 | Mold type, # and cable size identified
250eed27-dec7-563d-a28d-c705cad28ac7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #21 | Cadweld Visual test
1c30eb96-8cc4-5247-a3bf-c353ec5ba49e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #21 | Cadweld Ductor test
156f6fdd-eadf-5e0f-8a56-e275bfe7ac8c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #21 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
e0a54bb6-d36d-5cd1-b30e-31d892ee34d4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #21 | GPS coordinates taken
0ee1568c-5a0e-4721-8a45-a51111374585 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #22
f49fe749-1ec8-5d60-99ba-5b34144c507f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #22 | Mold type, # and cable size identified
bb8cbc8c-62e5-582b-90a1-5d837fdf535b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #22 | Cadweld Visual test
05450721-032f-5c6e-8077-c724d2a7f6fa |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #22 | Cadweld Ductor test
4de32804-3a28-5ff2-a270-1fdcab94605c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #22 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
189c28c2-48a0-50c0-a3fb-8b1fc74cc19f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #22 | GPS coordinates taken
1407aa06-5948-4491-a32f-cd59b34a3372 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #23
895b3000-3b89-5954-b3b1-9fd0cbcb5dae |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #23 | Mold type, # and cable size identified
e27d9235-2c19-5109-b62b-9940f10786dc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #23 | Cadweld Visual test
1b638148-b55c-53bc-ba25-58857b4e8f03 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #23 | Cadweld Ductor test
35b7df32-4792-5111-ab52-313192721ee9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #23 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
fc466e16-c361-5f8f-a40a-581d663cf63e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #23 | GPS coordinates taken
3fc69506-a05f-44b5-8f71-1bc28c2c64b2 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #24
0f1efb0f-2e70-597b-923c-c928c2b9e0f1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #24 | Mold type, # and cable size identified
0af61118-6333-5fd1-8c67-c9ee92baf708 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #24 | Cadweld Visual test
a96e55de-704c-5432-ace7-ee6929a96963 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #24 | Cadweld Ductor test
eff72c11-f764-58d7-bc72-9722b94fe1b5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #24 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
6e53ee4e-07a1-56d8-9439-fa6bdc35546b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #24 | GPS coordinates taken
a29569d6-0275-43c1-ad57-fd3017a5afc6 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator | Cadweld #25
df8c8ba9-0c08-5c0b-ba34-4d6eafa68ff5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #25 | Mold type, # and cable size identified
581bddd3-fb85-5b3f-abbe-cc2b3ae270d4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #25 | Cadweld Visual test
b577f846-637b-5ba7-846c-2deded31e60d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #25 | Cadweld Ductor test
f8f844dd-090b-5268-848e-88b95a0fed26 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #25 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
2de7b537-cdd9-5d63-8d45-0c7597adcb2c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator | Cadweld #25 | GPS coordinates taken
63c68b8c-e624-4987-8fd6-0613dbb0c862 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Inground Earthing | Cadwelds | Vent Station
d2ba2048-c911-4fb9-83b6-f8130a22be8b |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #1
3fd69464-277f-5ca4-bbea-dbf9bf4aefd2 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #1 | Mold type, # and cable size identified
15b0275e-6e91-5466-b177-f142d6e519e8 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #1 | Cadweld Visual test
eb370467-e0d9-5b0b-b717-1a553288d942 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #1 | Cadweld Ductor test
f8238b8d-f539-55b1-877e-74ff3c8d0fd8 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #1 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
c2d6fb3c-b076-5a16-95be-6d209b9c2c4f |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #1 | GPS coordinates taken
431119a1-9860-4ed8-8aa2-d5df1d486132 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #2
1e18a18e-e59a-5910-a184-6d9a9af44f41 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #2 | Mold type, # and cable size identified
159be1d7-b326-51bf-ba3e-580c1e3af41c |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #2 | Cadweld Visual test
26dff038-d092-5136-b612-44c0b701944d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #2 | Cadweld Ductor test
39e855d2-7069-52cd-aad0-52aaf90d0ca9 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #2 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
541312e7-e71e-557f-9f76-0febb9fe1255 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #2 | GPS coordinates taken
2535776d-2fb9-46fe-ac46-4d4d2378ac3a |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #3
307a66d8-3bc9-52c3-8e5e-2b70538ac445 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #3 | Mold type, # and cable size identified
07b41932-a7f5-5af2-9266-2f91ff47fc7b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #3 | Cadweld Visual test
2912d8b5-c0a0-550d-9d7c-ad6337b5f0ea |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #3 | Cadweld Ductor test
f828400e-4843-526c-ab14-a3da4cd2fc70 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #3 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
21dda572-0711-5c5a-97e9-5aa406f3c99a |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #3 | GPS coordinates taken
bcf16632-e1f5-4f37-9217-2cd020deb6eb |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #4
f20b8360-03f4-51fb-9ed5-8b0862d08231 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #4 | Mold type, # and cable size identified
ce0ebad6-113f-5cdc-b3a5-24c0d8608949 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #4 | Cadweld Visual test
15a75a5a-0927-5df7-b618-43777b8064ae |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #4 | Cadweld Ductor test
95f03edb-269d-53c8-a1c3-a4e81f58f6ce |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #4 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
983ba119-b5bf-54fe-b477-93269f9ca179 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #4 | GPS coordinates taken
8954c515-a40d-48f6-a7e9-87db05fca8af |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #5
7fdf4a8c-b79c-5aa3-8a7f-4f30cbe52d37 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #5 | Mold type, # and cable size identified
c76e6049-5e98-57a5-b634-ff1b97c59041 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #5 | Cadweld Visual test
75df5bb7-00db-5ebe-a922-84adf14e970c |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #5 | Cadweld Ductor test
0e4f23bb-b9bd-5eb1-b223-198e8ca570c6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #5 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
fac4e4b1-198b-5b6d-b3af-924db507493a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #5 | GPS coordinates taken
8355536d-09ad-476d-944d-8a0a9dc458b0 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #6
60a9d61a-02bb-52e2-8471-71814c906804 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #6 | Mold type, # and cable size identified
ba59227b-7af1-5965-96c0-ce66533c56fd |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #6 | Cadweld Visual test
e50c82ec-80c6-58c5-b3f4-694f9828d78c |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #6 | Cadweld Ductor test
f875d10f-71f2-5db4-a8c7-15931485907c |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #6 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
87ac5ef1-dd94-50a2-96d0-1ab5b3497036 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #6 | GPS coordinates taken
da067674-2e55-471c-9a0c-35a4587bbb53 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #7
1185077d-8e0c-5bc4-8b15-49cd88abf16e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #7 | Mold type, # and cable size identified
777ecfcd-e894-5a01-ace1-3edb3d84c124 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #7 | Cadweld Visual test
45be885c-2b02-5197-87fa-44c5e29b3e43 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #7 | Cadweld Ductor test
8625c123-e41e-5e4c-a76f-577b4ca26134 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #7 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
a484b372-c3fa-561d-a13c-4193f89884f1 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #7 | GPS coordinates taken
9558a3f6-3a89-48c2-9344-b43c5180e966 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #8
dcdd5ea4-340c-570a-9c18-8a898421232d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #8 | Mold type, # and cable size identified
51d13d0d-0a21-5fe1-88c4-cb887a7ab295 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #8 | Cadweld Visual test
bb078668-396c-5f8c-a639-77d5c9f5cd68 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #8 | Cadweld Ductor test
7d6e54a4-a874-5ce0-ab6b-528879d41874 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #8 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
49161dec-b738-50ca-b1d0-281ef777995b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #8 | GPS coordinates taken
40936dfe-bf0a-4604-a720-bbae0bf4b87d |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #9
c41d2a42-a8a6-5307-a8c2-e4f20ff72d44 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #9 | Mold type, # and cable size identified
1ac6f039-5dec-58ad-9409-529c90b7ecc5 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #9 | Cadweld Visual test
f0e116a8-031a-55ae-844a-d1072a707f97 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #9 | Cadweld Ductor test
dd33a921-047c-5311-a536-7989f29b29a3 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #9 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
77a29cd5-77c8-599e-8619-ebaee4e71a40 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #9 | GPS coordinates taken
ecf679a7-a380-4582-a6dc-c1611f6b5046 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #10
47f42736-7059-5497-ae72-2e0f914fe1e3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #10 | Mold type, # and cable size identified
53cd84f9-b098-5780-adc0-349c022f7ce2 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #10 | Cadweld Visual test
b803a0f2-db72-54a9-a0f1-5ddf5c92b03f |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #10 | Cadweld Ductor test
a292586e-d312-5bd6-aee3-17c318d64522 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #10 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
65fbac5b-990d-5f7e-9b87-5accd97045e9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #10 | GPS coordinates taken
7afe19c6-b294-442f-aece-a6234a763a59 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #11
f3f00b16-7b1f-5fc8-ae6f-daedb7206911 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #11 | Mold type, # and cable size identified
3588f62c-cc81-560c-b216-a99e3fd9575f |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #11 | Cadweld Visual test
7484f2f3-7b01-5247-8e5c-430f9ba6816f |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #11 | Cadweld Ductor test
558e55f7-b1af-5614-9944-ece702747eaa |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #11 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
3d1cb94e-907a-5e4a-b3cf-d9427a1bbfa7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #11 | GPS coordinates taken
8cb6bbbc-be60-4801-812c-7685698f2f73 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #12
176bf92e-bfe8-5101-9530-8eb453518357 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #12 | Mold type, # and cable size identified
a014efcd-855d-5aba-a5ff-90b5559facf3 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #12 | Cadweld Visual test
f7109332-ed61-5052-8111-63d4106ab743 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #12 | Cadweld Ductor test
1045b824-f1ed-5ffa-a923-01f325dddaf5 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #12 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
47d71e45-7042-5dca-9158-1ced08492a9d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #12 | GPS coordinates taken
31fac2d1-282a-48ab-bde0-29d0a26b3940 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #13
d34e3e18-6c32-5569-8ab4-f73138751401 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #13 | Mold type, # and cable size identified
875c35de-0fff-5271-8957-94ea689d1e7d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #13 | Cadweld Visual test
6edca4eb-7820-5347-9827-2fab26279433 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #13 | Cadweld Ductor test
4c9a5822-d449-565b-a397-33199e8c0cac |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #13 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
7588debc-988b-513e-93fd-f0025b665ad2 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #13 | GPS coordinates taken
272f8520-4b01-4dae-bb73-07c65f02c560 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #14
d1a9db63-9fee-5338-ab1e-b25bed16e693 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #14 | Mold type, # and cable size identified
d9e7f09b-a3c6-5ca9-ad1a-8b0cdc098ce8 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #14 | Cadweld Visual test
84c09d82-c38f-5f0c-a2b1-da0b0b3b5e5e |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #14 | Cadweld Ductor test
d1e694da-1df9-553f-9d57-e5ee349ce04b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #14 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
ff94f639-df0c-5736-ab60-789a6d0d9f5b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #14 | GPS coordinates taken
8fea3d2a-1da8-4a8a-84f6-0469636a1c62 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #15
3bebdcdc-c643-5f0a-b27b-dd64a4fcec6a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #15 | Mold type, # and cable size identified
94f1a007-d152-5a72-873e-08e5e8c1dab2 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #15 | Cadweld Visual test
f05a9d1f-0eef-55df-98b4-f6449d04cb5d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #15 | Cadweld Ductor test
addc40c7-712f-55b6-adcc-56dadfa08f51 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #15 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
aa4d4534-7513-5850-968c-87b16d27cdbc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #15 | GPS coordinates taken
adbc0089-3c81-4bdc-bb6e-93cd40768d93 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #16
aaca6d8d-a0a7-5554-8f53-808afa24ebc1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #16 | Mold type, # and cable size identified
424f3c64-254e-521a-b544-b2e9919d076f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #16 | Cadweld Visual test
acf0a584-699b-52e6-a0ad-2bd10b843846 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #16 | Cadweld Ductor test
aad183e5-fcc6-531e-aaba-587087676b8b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #16 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
4f594f5e-ed98-5578-b289-f7fc700eaae0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #16 | GPS coordinates taken
8259c6ae-f21d-4ad2-b038-ab5853aa1b3e |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #17
a9448386-48d1-5b15-81bc-fb22ae5c8842 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #17 | Mold type, # and cable size identified
d660d21b-3bb6-59d8-8b96-44f71cfed4ff |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #17 | Cadweld Visual test
f72d43e4-5a9e-5a80-9349-0e0a9cacf236 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #17 | Cadweld Ductor test
1a266c69-e08e-5008-afde-5a3475f51ec0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #17 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
6c25f84b-2cc1-59dc-b315-909d6b15a317 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #17 | GPS coordinates taken
c2404ead-7c34-44f2-bc2f-c877e779b668 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #18
2b1cac4e-16f9-53a8-abef-2def16916932 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #18 | Mold type, # and cable size identified
692232fa-70c0-5ed5-9199-9209e9befe6e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #18 | Cadweld Visual test
c9cebcdd-3980-5712-b5be-b1ccec427d13 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #18 | Cadweld Ductor test
f8538d02-1ee4-5eff-a176-1ba5e0a65d01 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #18 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
f3b1f27b-bb93-5b8d-9e5a-f0d4ccd8110b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #18 | GPS coordinates taken
42414e81-42f9-4449-9306-44b2068a9ff6 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #19
ebb3d9ab-c611-5420-b5f2-9ec76eac6742 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #19 | Mold type, # and cable size identified
a986613e-ec37-5b42-af72-aa8ca2d68e20 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #19 | Cadweld Visual test
b0a07601-3bd1-54c9-a535-31e2e1a21ac2 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #19 | Cadweld Ductor test
1bfb99e3-463d-5efc-8679-f7fcc7892c81 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #19 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
5438c7e5-ed2f-5451-b892-683ecfe19a1d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #19 | GPS coordinates taken
3379c3fe-17d2-47c6-afed-9f375040fd57 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #20
a55dbea4-b34f-53c9-87da-50108e065d96 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #20 | Mold type, # and cable size identified
fe4bd21a-dcbb-5f42-a362-e56595b58e73 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #20 | Cadweld Visual test
fae5b9a1-6dd1-508a-af7b-487bd50eded7 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #20 | Cadweld Ductor test
e6d50651-5b55-5bb5-b0cd-cbccb06727a8 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #20 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
57e2cfff-38b5-523a-affc-728329883e0e |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #20 | GPS coordinates taken
76c6bf83-b735-46f3-a0ca-9bb59d6709f0 |  | checklist-flat | work-in-progress | Cadwelds | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld # 21
12a25ad7-d129-578f-bef3-e46f256c738f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld # 21 | Mold type, #, and cable size identified
d40fc3f9-4b57-50f6-8a49-2811ca80e829 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld # 21 | Cadweld Visual test
34d93b4c-3a4e-507a-a598-5f0dde6c8347 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld # 21 | Cadweld Ductor test
5a71a0d3-1dd3-5bc4-bfb6-890cf6bde27a |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld # 21 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
383a00ff-d190-57da-813c-5b16d3065c05 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld # 21 | GPS coordinates taken
61edebc3-62be-4e3b-bf42-7551d77a7266 |  | checklist-flat | work-in-progress | Cadwelds | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #22
06b8beec-c8ad-5733-b716-97c10e78ba3b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #22 | Mold type, #, and cable size identified
e0ffc641-34c9-592d-a510-7b2b40b76265 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #22 | Cadweld Visual test
f5a90c91-039b-5c93-b1d7-f13e69a3bc12 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #22 | Cadweld Ductor test
acc2631b-1739-5b4d-a76b-7868418ffa41 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #22 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
0f0ba8a1-51eb-5211-8112-6bdabc59262b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #22 | GPS coordinates taken
1af24030-1446-46f8-8b16-3452f7ea051d |  | checklist-flat | work-in-progress | Cadwelds | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #23
20f28c06-1df6-5787-ba06-2a52c38db2c5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #23 | Mold type, #, and cable size identified
6eb20e00-5ef9-5b94-a6ee-35761bcdb1cd |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #23 | Cadweld Visual test
7496b390-7809-56a7-9256-4cdd09e5d4d4 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #23 | Cadweld Ductor test
5f54b7e2-d0e9-512e-98fb-bca8caea9cce |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #23 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
b50fffb0-140c-5477-a5a5-575a66ec43cf |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #23 | GPS coordinates taken
db450044-317a-4957-bafc-853c5bfbc802 |  | checklist-flat | work-in-progress | Cadwelds | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadwelds #24
8f06fa41-df84-586a-b1b8-d28bf291a198 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadwelds #24 | Mold type, #, and cable size identified
7fd098ea-559a-51fe-8b8c-b7e4663203cc |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadwelds #24 | Cadweld Visual test
601ca93e-3690-59c4-8644-860cb9ddb421 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadwelds #24 | Cadweld Ductor test
212f7d97-987f-53d0-9580-11fc75a6222a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadwelds #24 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
94cbb2cf-07dc-5567-b318-b73ed55172f2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadwelds #24 | GPS coordinates taken
624708f0-ee11-4e82-abf2-634bd36dbbe3 |  | checklist-flat | work-in-progress | Cadwelds | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #25
026acc5d-17bd-537a-a7b0-b50ff69bce96 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #25 | Mold type, #, and cable size identified
1d956952-75d8-5de1-ac23-8a6fb84cb7c9 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #25 | Cadweld Visual test
5a356776-ca89-5712-b1fb-4ad64114911d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #25 | Cadweld Ductor test
3ddf0237-0ce3-59d8-9311-c852b20287be |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #25 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
2565edb2-377f-579d-b756-98791724b1c8 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #25 | GPS coordinates taken
2666e6ae-9dd3-48d7-8f50-81b709cc2bc8 |  | checklist-flat | pass | Cadwelds | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #26
c3a7118b-ce2c-5885-bb78-94ca3ba788c3 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #26 | Mold type, #, and cable size identified
eddbd1f5-3968-5839-a634-6566e1ad7bd8 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #26 | Cadweld Visual test
3b242384-358f-5434-9bc1-bbfaa7ba4d0d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #26 | Cadweld Ductor test
a44efe64-3928-59d4-9ddf-a33ea443f08d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #26 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
ad6b859f-2e59-5579-b439-8b0535843126 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #26 | GPS coordinates taken
525d2fd7-9666-4f35-a685-64954757991b |  | checklist-flat | work-in-progress | Cadwelds | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Vent Station | Cadweld #27
aefb7a2f-d519-57a6-88c4-749ded395865 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #27 | Mold type, #, and cable size identified
b99304f6-087e-5a73-b052-d4aa817da56f |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #27 | Cadweld Visual test
e8e92fb0-fab6-525c-833b-815b5c9859f0 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #27 | Cadweld Ductor test
93c5c132-0e34-5393-890a-2e2df2b9c6db |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #27 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
31631178-a825-5a90-9851-e1cb825f97d7 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Vent Station | Cadweld #27 | GPS coordinates taken
a947fcee-c1c5-408e-972b-e29aefe60a47 |  | folder-normal | not-started |  | step | TRUE | FALSE | Inground Earthing | Cadwelds | Unit 3 Interface
9152253b-60c8-4edd-864d-9e7a0b85c12e |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #1
ebee36b5-a863-59be-8281-8ee570d577a1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #1 | Mold type, # and cable size identified
955b823b-9daa-50a2-ac3e-87b4a28342f5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #1 | Cadweld Visual test
92d89c84-d36e-5bb8-9610-5db409a12d0d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #1 | Cadweld Ductor test
1b1250d8-b444-5263-8b66-395c5e0e199f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #1 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
25a38ab5-7091-5833-9fea-38387aa527ad |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #1 | GPS coordinates taken
bbfbc41a-795a-4236-9dd9-746a779f296a |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #2
104f2407-6721-5ee3-b8a5-38c8da274cdc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #2 | Mold type, # and cable size identified
7b4aa7d0-71d4-5eb1-92fb-db52d4a9d48f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #2 | Cadweld Visual test
022e7d09-870d-5470-b69f-a6d01ff472e4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #2 | Cadweld Ductor test
6512691d-e4f0-5c96-82d5-1e711f9e0833 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #2 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
d357d331-b043-5680-9572-36ac214438d8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #2 | GPS coordinates taken
10fa4bc4-7a3d-47ee-b500-695bfdc7e59d |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #3
fa3678d7-a32d-5748-a52b-c672f9e1aa9c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #3 | Mold type, # and cable size identified
df83130a-87b8-5db6-b41d-0ea07666a98e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #3 | Cadweld Visual test
a1a936ec-2409-5a70-bfd1-fe8bf0bb5885 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #3 | Cadweld Ductor test
44119d96-af18-5033-8efb-ae7259c3bb29 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #3 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
c07cbc0d-b5db-54b6-9106-2b6c65011f56 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #3 | GPS coordinates taken
93d4ed3b-e91a-480d-9c7a-bc0ef50271ba |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #4
72e00508-881c-5d7c-b634-ba37155fb6db |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #4 | Mold type, # and cable size identified
b0b9af2d-788a-5e38-9084-370f228022af |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #4 | Cadweld Visual test
cdf6459c-7397-50aa-b339-744dbd9b3614 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #4 | Cadweld Ductor test
d487526d-9952-5a49-a1db-7c86f11b9297 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #4 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
b92761c2-5f50-545c-afef-395344e92baa |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #4 | GPS coordinates taken
da19cd84-57d8-4923-af62-16a8c971cfed |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #5
a41150df-b921-5ec3-9b78-848af12acc37 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #5 | Mold type, # and cable size identified
af12fa62-9ad9-583d-ad59-1d91d79ac768 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #5 | Cadweld Visual test
56ebd463-b755-5d95-a4b3-c15bdd367481 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #5 | Cadweld Ductor test
9ac2189d-787d-53a8-bcb1-2e93eb4c8c28 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #5 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
9ba45963-cdba-525f-b8aa-45f002985932 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #5 | GPS coordinates taken
b428fd62-1884-4d34-8375-d7074d4616d7 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #6
d37adbc0-f98b-5b7d-8566-69e2cdeac8f5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #6 | Mold type, # and cable size identified
a276fac5-4a33-5983-8d0e-d5c24ed2bb8a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #6 | Cadweld Visual test
26d33ada-e882-5ed0-abb4-e4d4d309152e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #6 | Cadweld Ductor test
2132d2f8-3bac-52db-8f69-0cf38b1ffe10 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #6 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
f0ece337-6153-5b51-8b74-88eb42cd7f20 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #6 | GPS coordinates taken
3e163c8c-69b8-4719-a1cb-4f1ac9bfc361 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #7
dcb00228-aacd-5a75-b8e1-f0636d82f786 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #7 | Mold type, # and cable size identified
d63c1fd2-f5af-5529-84be-3e17317d006e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #7 | Cadweld Visual test
7ef80cff-61e3-52c4-b116-e0b6d78b890e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #7 | Cadweld Ductor test
32a977f3-025e-5d95-8700-fcb15fc78473 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #7 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
d4445be7-a99a-506c-86a0-d9f5c4f39c9a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #7 | GPS coordinates taken
55d725c9-bda6-4af7-82e8-6f60d81a0e13 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #8
49ad3e4a-ce81-5379-ac32-ce0f4b3a3157 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #8 | Mold type, # and cable size identified
b5fb541c-0a83-5028-8f57-3209cde537c2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #8 | Cadweld Visual test
6cb51871-f344-5b88-b803-3da4d7cd2a92 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #8 | Cadweld Ductor test
efc1623e-b16f-5337-9497-b7afbf584851 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #8 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
82a8230b-7c05-588c-a247-e03333d4e365 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #8 | GPS coordinates taken
e72e1456-4104-4d4e-b968-aa6ba47fc62d |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #9
9eea2a8e-4e00-5049-aff4-b031262299df |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #9 | Mold type, # and cable size identified
f8825a42-594c-5372-86bb-2d429e7bae50 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #9 | Cadweld Visual test
094232af-5319-587d-843a-51c65d1c8194 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #9 | Cadweld Ductor test
bf266c32-c13c-57c7-b164-ec1ff870a3fd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #9 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
00446e68-6724-5fff-a2ba-c6a4bac2f473 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #9 | GPS coordinates taken
581aacbf-20c2-44cf-9e49-3832639907ae |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #10
82c6f28d-6afa-590d-b9b6-7249372f25da |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #10 | Mold type, # and cable size identified
3650b68c-20d8-5d05-9ae6-5fa7f8c3a89d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #10 | Cadweld Visual test
37e1520a-77b9-5bc0-86d2-0d7f47ff7510 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #10 | Cadweld Ductor test
c9fb7081-9503-5866-8774-eb92b7342a34 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #10 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
5272cf4d-a221-567f-994a-ffae01c8624e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Unit 3 Interface | Cadweld #10 | GPS coordinates taken
d68fd907-cdda-4486-8a31-74116b64b4ca |  | folder-normal | not-started |  | step | TRUE | FALSE | Inground Earthing | Cadwelds | TH39 Wellpad
fed74f1a-79f0-4d3d-b212-d3c13dd6cee3 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH39 Wellpad | Cadweld #1
0e23f0c1-49e0-5ba6-9d3e-ba4cfe73bfee |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellpad | Cadweld #1 | Mold type, # and cable size identified
94f97e84-4016-5c81-a292-650872038722 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellpad | Cadweld #1 | Cadweld Visual test
08d4d5b6-96e1-5f8e-b0d6-9611f7bf49b5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellpad | Cadweld #1 | Cadweld Ductor test
1a671092-494c-5cc3-9a9f-fae5a7343c15 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellpad | Cadweld #1 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
5dc8e18f-fbd3-598a-9c84-8d8c3f13550d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellpad | Cadweld #1 | GPS coordinates taken
d4386935-6893-4eaa-b8a1-c3097fe06339 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH39 Wellpad | Cadweld #2
e693fb94-aade-5c4a-b0ac-1049d4b84104 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellpad | Cadweld #2 | Mold type, # and cable size identified
21fb8d97-b008-5e5c-8005-2eb4112f523b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellpad | Cadweld #2 | Cadweld Visual test
163a93df-d7f5-593c-ac3a-c0e7efeb89e5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellpad | Cadweld #2 | Cadweld Ductor test
bf499870-33d1-511f-accf-d334b22011cf |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellpad | Cadweld #2 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
2f01aea3-1bb8-5474-8968-51162762d085 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellpad | Cadweld #2 | GPS coordinates taken
cf8b46c7-ca4c-4b1a-8fdd-896fd437939a |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH39 Wellpad | Cadweld #3
6754fda8-c992-58fe-988b-fd6aedd27277 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellpad | Cadweld #3 | Mold type, # and cable size identified
36c7fcca-a526-58e3-ae32-bf276f204cc0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellpad | Cadweld #3 | Cadweld Visual test
6dc5a8a9-42de-57a0-b474-30a4560d25fe |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellpad | Cadweld #3 | Cadweld Ductor test
f9f34965-5662-5ab1-a9a2-2e6eb5931e63 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellpad | Cadweld #3 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
681e8948-06f5-5079-952d-1ae0909b90b7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellpad | Cadweld #3 | GPS coordinates taken
b8303aef-c051-4300-a7ce-71f835336b44 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH39 Wellpad | Cadweld #4
5e283274-0d28-5620-b485-fc666fc7e724 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellpad | Cadweld #4 | Mold type, # and cable size identified
4a0d5336-862d-5f79-b580-476a35ddd6eb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellpad | Cadweld #4 | Cadweld Visual test
807647a5-6068-568b-bd08-9fcbde1d9488 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellpad | Cadweld #4 | Cadweld Ductor test
dd632a7a-c2e6-592a-af44-38365a337c70 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellpad | Cadweld #4 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
78e869ad-33bd-5974-9dbd-00cda6601cac |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellpad | Cadweld #4 | GPS coordinates taken
72401c39-ca9a-4576-9cf2-b0ec666d9e59 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Inground Earthing | Cadwelds | ASB Building
ac4be795-f51f-42a6-88a0-146d9e179832 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | ASB Building | Cadweld #1
9e5741fd-0582-53b4-acc8-d3f6f29ca43a |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #1 | Mold type, # and cable size identified
580bd1a3-6611-5158-a2db-70700bbe18b0 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #1 | Cadweld Visual test
df8ca2e8-ce71-52ce-8a29-5fb9b3133f05 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #1 | Cadweld Ductor test
822272ea-a5d9-5c53-90a8-cb5b0da3d257 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #1 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
5d059ead-140b-567c-a559-b4d8ac471d1f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #1 | GPS coordinates taken
6d7fca0e-ef60-4a32-958f-344247473df2 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | ASB Building | Cadweld #2
1ba209b1-67b1-5fa9-86cc-7a3bcc8d3a90 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #2 | Mold type, # and cable size identified
b6d988a9-d333-568f-aa76-dba00b5ab53e |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #2 | Cadweld Visual test
e7c1244e-3c21-5b23-9e50-22d711902728 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #2 | Cadweld Ductor test
b43964a5-0033-5b8a-bee7-5fdd774a580a |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #2 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
6f37c79b-e106-5439-8793-dfef6b7d6b1a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #2 | GPS coordinates taken
c7120c67-cc9c-42e9-bf36-cf0f089f8c78 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | ASB Building | Cadweld #3
5bcc2217-de88-59dd-bcc9-cb226d2b0557 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #3 | Mold type, # and cable size identified
08128518-3978-527b-a840-294c51a77c3d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #3 | Cadweld Visual test
ddbf15bd-751c-58f9-987c-19b365b4e780 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #3 | Cadweld Ductor test
3cc0e081-36d2-5059-9c0b-4087308e1294 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #3 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
12d18c1a-f9d5-5755-bd75-2fe2f4cdf792 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #3 | GPS coordinates taken
18ec17a1-28a5-4231-9ad0-8b1c2fcb98ee |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | ASB Building | Cadweld #4
fc90c019-a017-503b-a574-26ecf0c7ad61 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #4 | Mold type, # and cable size identified
8dd5ddfc-6295-5002-943f-6b5ace2678f2 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #4 | Cadweld Visual test
b89c00df-801b-5be2-9400-74ab2893c5a2 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #4 | Cadweld Ductor test
112cee2d-ae3f-5435-ab36-5f9e0ce41dcb |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #4 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
5fd46c00-b44b-54cc-aa27-78e2abf5104c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #4 | GPS coordinates taken
418a92ea-bb5a-42c3-a839-b4f126ecc71f |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | ASB Building | Cadweld #5
b71564f6-eb38-5707-ba19-0fbf590b6b78 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #5 | Mold type, # and cable size identified
541c11b7-1b51-5cea-b3aa-43ec24ee5dbc |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #5 | Cadweld Visual test
6ece8c53-24a3-5f52-b036-18c140ffc9f0 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #5 | Cadweld Ductor test
0c31989a-3093-5ef9-be2f-d19b195f8528 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #5 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
aa51f985-a334-53bb-b7df-c7520a81a2f5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #5 | GPS coordinates taken
38eb2e1f-286b-4750-88a3-b06dcd62b629 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | ASB Building | Cadweld #6
85fe0914-40ff-52b3-accb-c8792295d44c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #6 | Mold type, # and cable size identified
e667ddea-9d26-5fe1-919a-25b1e940098f |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #6 | Cadweld Visual test
8137e303-3490-5f3e-ad05-7f32050d6bb9 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #6 | Cadweld Ductor test
77464abe-b6c6-5a98-b765-e089e68f330e |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #6 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
c01edd00-43ff-5f85-bd7b-90bfbf745e78 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #6 | GPS coordinates taken
5b49af19-6a22-49e9-99c1-8647062d69ca |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | ASB Building | Cadweld #7
407ce401-04db-52fe-baa8-e397d61c8799 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #7 | Mold type, # and cable size identified
948367e0-b172-5c65-9216-73dcb0cc60bb |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #7 | Cadweld Visual test
c7389635-209a-5128-a0cf-413462018aeb |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #7 | Cadweld Ductor test
f84fb0cb-7154-5bf9-9c26-f802cc2ac5d9 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #7 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
e5844680-2e68-5e8e-a8e1-358ce6adcedc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #7 | GPS coordinates taken
1f1a33af-bbbe-476f-9310-8be5989dd465 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | ASB Building | Cadweld #8
dcd203d1-7e24-54d9-a948-c8bbe05b9bc8 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #8 | Mold type, # and cable size identified
1628d2c9-85ed-5b22-827c-154b5b4cfb38 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #8 | Cadweld Visual test
68561fd0-a703-5cdc-9bcf-20b219566cd1 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #8 | Cadweld Ductor test
dd15ccdb-2e76-5d11-a2f3-8dcf6721db7e |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #8 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
53f48fb4-7b35-57d7-b849-837a2d96e757 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #8 | GPS coordinates taken
27269a20-b93c-4471-92d5-f4b08279bc0d |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | ASB Building | Cadweld #9
74d1ae07-fcce-565d-8b84-52aad8d2a9c7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #9 | Mold type, # and cable size identified
a0d7a23d-5b91-5c44-baf0-0767583e83de |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #9 | Cadweld Visual test
790ac16c-db65-53fc-b2cd-5da1b3bc2bcc |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #9 | Cadweld Ductor test
5cb41f68-5868-569d-b29d-b4179abef34d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #9 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
207edff1-de4a-5e7a-a023-6c79956268af |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #9 | GPS coordinates taken
74d862c3-0d3b-4ef2-9590-9b2d5b321275 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | ASB Building | Cadweld #10
2c85ef0d-94d2-51b2-9a19-59a4f0455b6f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #10 | Mold type, # and cable size identified
916df40f-d888-5576-885d-7ab57fdf3c18 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #10 | Cadweld Visual test
c0cc7211-e1bc-5571-987a-854871d9c50f |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #10 | Cadweld Ductor test
465cbbbf-1939-5d63-8b6d-6292ffe85136 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #10 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
51c904f4-1cb4-59d7-b517-4627a10b470f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #10 | GPS coordinates taken
5700f795-3c27-44c5-905f-85700aa553a8 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | ASB Building | Cadweld #11
54214ec1-4f47-5c87-882a-7c5aa20286a8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #11 | Mold type, # and cable size identified
da42bd71-8088-5005-824a-2838e6f91d12 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #11 | Cadweld Visual test
9328954c-08df-568e-9dc6-8615c432f023 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #11 | Cadweld Ductor test
570f4b99-7c7d-510d-8df7-77310da47128 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #11 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
d3f53119-297f-594a-bc03-3643653f6ba4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #11 | GPS coordinates taken
c5692d53-2f40-47aa-8fbe-f436c76a1e51 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | ASB Building | Cadweld #12
75ebf60d-ba06-5290-ab46-ee3eed8a59fb |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #12 | Mold type, # and cable size identified
bfdd4530-45b3-5faa-955d-dbf9f935cc0a |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #12 | Cadweld Visual test
37c76822-d516-5254-b69c-517a7005862a |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #12 | Cadweld Ductor test
030175e4-c9eb-51a4-8bbf-ee604f9f6047 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #12 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
4b7b7bfd-c575-5f97-9eb3-7f41b462d66f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #12 | GPS coordinates taken
9f5dcb2d-6a91-4197-ba9d-24f43551fe95 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | ASB Building | Cadweld #13
d5ac4012-109c-5c76-b8ab-455fa7fa815a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #13 | Mold type, # and cable size identified
7d758be0-02bf-50cb-b3f1-53bcfd564cb0 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #13 | Cadweld Visual test
2c01fb03-c85d-5362-8ff2-c29efe4c08b6 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #13 | Cadweld Ductor test
4a7e38c5-5c93-5e11-898d-5ff29e691a55 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #13 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
3e7688ac-c362-575a-aa3b-9ecd8d1c4215 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #13 | GPS coordinates taken
123df65e-a17c-4727-aebd-d52d39a82862 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | ASB Building | Cadweld #14
5422214f-cdef-57e3-affe-cd4487695cfb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #14 | Mold type, # and cable size identified
5f4480f7-113b-5316-9436-8f16dca7bb0d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #14 | Cadweld Visual test
d374ba3d-ded5-5409-bd28-d15e5714ebde |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #14 | Cadweld Ductor test
bf373282-190c-58b3-ab7d-1f59610cdc16 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #14 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
49f017ed-409f-5c00-a493-6d15e159846d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #14 | GPS coordinates taken
b9862bc2-d1ac-45e3-b6f0-8f7b37f08bee |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | ASB Building | Cadweld #15
7d2dedd3-aef2-5d58-b80e-c6155f15ada1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #15 | Mold type, # and cable size identified
c6daf85a-6836-5d5c-8f66-ba5c017916da |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #15 | Cadweld Visual test
5d58e7e1-3b0e-5f50-b97f-9a4de652940b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #15 | Cadweld Ductor test
0dab7a77-ef32-53e3-8542-569511e00fa0 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #15 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
f335d867-18e7-5f8c-b1f1-e9667cc43a2c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #15 | GPS coordinates taken
055c6ea9-a0f4-45c1-8d5c-9265df664386 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | ASB Building | Cadweld #16
7b045451-e138-566a-9923-166034b62348 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #16 | Mold type, # and cable size identified
636a016a-98e9-572a-b746-39f9076f97ae |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #16 | Cadweld Visual test
fedda106-01d1-538c-8e20-aa73888811fe |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #16 | Cadweld Ductor test
f9ea826f-75ea-5616-80da-e878e63eaa65 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #16 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
86ca4d37-0b43-5a04-9b83-13f1f813ca61 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #16 | GPS coordinates taken
6ea361ae-1dd7-4452-8d40-11b39c6c9e97 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | ASB Building | Cadweld #17
47456c63-0073-58b2-8873-eefc55a1c3c5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #17 | Mold type, # and cable size identified
1d8c5668-c90d-5797-949e-48d190268bc4 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #17 | Cadweld Visual test
a6239afd-f137-5c82-8119-56bd8f153f66 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #17 | Cadweld Ductor test
0c27ae92-40f2-55ee-b47d-25078e454f7f |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #17 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
c5f4ac7c-73d4-546d-ab22-62862b84e923 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #17 | GPS coordinates taken
34d69753-781b-47e7-a3db-d4636a848d21 |  | checklist-flat | work-in-progress | Cadwelds | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | ASB Building | Cadweld #18
52c4173f-3883-5c2a-bc90-db507a61c17f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #18 | Mold type, #, and cable size identified
4ebb681a-8849-5a4b-9a4c-230b62aff3b7 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #18 | Cadweld Visual test
5607967f-997b-5401-96eb-57cd85b1f932 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #18 | Cadweld Ductor test
9793e1d7-e780-5354-8abd-0fce0448b204 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #18 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
094546a7-2a17-5215-afe3-4c0944627dd2 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #18 | GPS coordinates taken
d3015db8-fced-4670-a2cb-fb4bda00d624 |  | checklist-flat | work-in-progress | Cadwelds | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | ASB Building | Cadweld #19
0567b4b4-ae60-5faf-a8be-a51c23c2bc06 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #19 | Mold type, #, and cable size identified
a82deb9a-090c-597c-a608-bf80eb98ed34 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #19 | Cadweld Visual test
7f9ecbe3-8ba8-5b45-b8ce-d8c17e19f449 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #19 | Cadweld Ductor test
f5e85d2f-9e75-5d52-9ca9-d2e76c9af5f8 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #19 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
594a2a52-04c0-5fba-85a6-6d6617e81914 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | ASB Building | Cadweld #19 | GPS coordinates taken
00b0df59-9ee4-44d2-bd40-26b8622cc7fb |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Inground Earthing | Cadwelds | Separator Station
8d147a92-7ca7-4f39-9c2c-fffeffc10d5e |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator Station | Cadweld #1
373548b0-e2d7-5759-95e4-8df501dae6e2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #1 | Mold type, # and cable size identified
371d47e1-23ac-57ea-af8f-9753c83c470d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #1 | Cadweld Visual test
eaecfdbc-82c2-5d40-aef7-219cc1acd3e9 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #1 | Cadweld Ductor test
b84c1677-7ed1-5447-8ac5-4d373a982805 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #1 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
aae29b28-2f7d-5f55-ac1d-858efa6d48a6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #1 | GPS coordinates taken
008ccc2c-288b-4733-91e9-df4710a6f11b |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator Station | Cadweld #2
d1f7705b-6559-5dbc-b70d-deadd830d1ea |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #2 | Mold type, # and cable size identified
56566891-51a9-55c4-a49a-d920e592fbb2 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #2 | Cadweld Visual test
3a9e0d4a-4299-5b03-9091-ae63e354edf8 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #2 | Cadweld Ductor test
10e44f45-35a2-5169-b1c8-a44fa5776888 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #2 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
136715e9-a605-53a5-a983-55ee0fcff13f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #2 | GPS coordinates taken
04500b18-2b1f-4791-8fd2-7399a53d42ff |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator Station | Cadweld #3
a4f64520-75fc-5c79-82a1-38e91fa955c9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #3 | Mold type, # and cable size identified
92cec9f8-7864-5085-9a0b-8307cb3035fa |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #3 | Cadweld Visual test
e83ede2c-6a29-5a22-bed1-dc0aaf8c707e |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #3 | Cadweld Ductor test
00a48938-cd60-5326-bb0b-a7708f5978bf |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #3 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
98a1eeed-a3a4-529b-a438-e6f5a9fa0329 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #3 | GPS coordinates taken
d7c71e7e-9cb0-4db6-83ef-96566c7790e9 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator Station | Cadweld #4
71144f12-2f67-578b-8756-1e712fb3d6e7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #4 | Mold type, # and cable size identified
305127b9-b877-57f9-be30-df06c83fc489 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #4 | Cadweld Visual test
4118240b-a99a-52e3-9316-4f557f686d35 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #4 | Cadweld Ductor test
1af7161b-f3f2-5311-b30f-bc943f5621a8 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #4 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
a3610b16-3009-508f-abed-71ffc222dcd1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #4 | GPS coordinates taken
2c17e354-7c1d-4c1a-a259-8f78e7656494 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator Station | Cadweld #5
e4f1c24e-b6e6-5dac-b2b2-c773cf6b4dd3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #5 | Mold type, # and cable size identified
220cc26e-1ef6-58df-beb9-e8a122065492 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #5 | Cadweld Visual test
9b4f5684-cf8f-5a6d-8cd7-f94e80c061e3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #5 | Cadweld Ductor test
b03de66f-e3a5-5a13-8771-130c08c0c036 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #5 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
d9969e73-5bc8-5fba-9e3b-cd8e9be8e0ef |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #5 | GPS coordinates taken
563cc205-20f1-4377-b1cd-b029868abc98 |  | checklist-flat | not-started | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | Separator Station | Cadweld #6
ebf2d328-b232-5f8c-90f9-537c5290b167 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #6 | Mold type, # and cable size identified
19cbb6b0-7eef-57d5-b6ea-8bb30b27b41e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #6 | Cadweld Visual test
27695e63-89c7-5df1-a983-bfcdaf88c10e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #6 | Cadweld Ductor test
840cdff2-c852-55ab-b072-37ab0042e9a0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #6 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
c1b7b349-4255-5e6d-89d2-c3b45167c393 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | Separator Station | Cadweld #6 | GPS coordinates taken
a3c8b31a-aee6-494e-ae39-903b23da9380 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Inground Earthing | Cadwelds | TH32 Wellhut
856e42fc-0cf1-4b51-b1da-00f2c5989f06 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #1
9c83e90f-b0ec-5c5b-a396-c661f3905061 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #1 | Mold type, # and cable size identified
80f7bc34-8444-5185-921d-e2ade75580d9 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #1 | Cadweld Visual test
ac891025-52fe-54a8-bdd5-22841a29d10e |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #1 | Cadweld Ductor test
eb8eec93-4401-52bb-91ec-4fcb35926a97 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #1 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
da2cbc5d-d91d-5b7d-ae2b-84552e115afa |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #1 | GPS coordinates taken
29fe7b41-ebe4-4401-a27e-0d1e877c44d1 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #2
6adf89cf-81bb-5678-8356-c158919f0429 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #2 | Mold type, # and cable size identified
53ef6af4-17b8-592d-a487-6285e3ad0c60 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #2 | Cadweld Visual test
448e3a46-9c22-5c21-b78e-8691172c1409 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #2 | Cadweld Ductor test
65929d89-5d44-56bf-bc63-762d7fd830b9 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #2 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
ef5e4e40-9450-59f1-9836-da211a52f827 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #2 | GPS coordinates taken
bb7e40d0-f248-4e71-a591-5b307bbc9017 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #3
eca22ad2-36a3-5729-ba4f-98e1075ae3f2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #3 | Mold type, # and cable size identified
3d0fb87f-7a54-58d0-8640-a53767507042 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #3 | Cadweld Visual test
8befa3cd-8c4f-5d8d-94ec-758126be0a43 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #3 | Cadweld Ductor test
fb5d89a5-926e-51cd-bf0b-c019498a1de9 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #3 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
7dc40a79-5cb9-5904-93f5-c00e91fdcebe |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #3 | GPS coordinates taken
d18d995d-dbe9-44ba-adde-d6b0d7e8aaed |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #4
0c02edb4-c38b-5a7c-87c7-02a1b3ceca80 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #4 | Mold type, # and cable size identified
c22aa38d-764c-5aa2-a5b4-430a259d0811 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #4 | Cadweld Visual test
c499c39b-e612-51c6-ba9a-21c545730cac |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #4 | Cadweld Ductor test
c1d93b50-8939-5b0a-8b31-987656433d36 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #4 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
bcdf2646-d70a-59e5-b984-2010cd35b1b6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #4 | GPS coordinates taken
5fa6fbb4-391e-4fd0-b1c0-77406425f113 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #5
2830c4fa-5560-5fda-bd94-476d6c98d8a4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #5 | Mold type, # and cable size identified
228bcb1a-503e-53a0-a87f-8ab53a83eea4 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #5 | Cadweld Visual test
a0f9f783-dea1-5208-bc63-77add44bac7d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #5 | Cadweld Ductor test
55833310-03b6-532a-9f93-3ed75bdff229 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #5 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
27f9c999-5f84-5675-8899-5239188c65ac |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #5 | GPS coordinates taken
032d1e68-fa75-4516-967d-69a07c188c81 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #6
1916d8e6-465a-5766-bf1d-0b78daecdaab |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #6 | Mold type, # and cable size identified
317b4954-2ab3-532a-b1ed-847737782a4b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #6 | Cadweld Visual test
8d594054-8a0d-58db-ba6e-c43eb51e414b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #6 | Cadweld Ductor test
7dab3feb-2d27-53c1-95be-69633edac038 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #6 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
b973a3e1-111b-59d2-835f-1e57fd445fce |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH32 Wellhut | Cadweld #6 | GPS coordinates taken
3eb9ca3d-d2fb-4036-b8f3-456117545068 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Inground Earthing | Cadwelds | TH39 Wellhut
0ccc87f1-8216-453c-abcd-0a80fa2d69a1 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #1
4eece2ea-384d-5f60-bf17-f0d7f7b6b6c6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #1 | Mold type, # and cable size identified
e98f1d8d-b31d-5def-bebc-e4911013e71d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #1 | Cadweld Visual test
30c0458b-ae3f-5dea-9a4a-e4e92ddc32e2 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #1 | Cadweld Ductor test
b72c4d3b-ea96-5da6-a7ef-ccdd359fb19d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #1 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
dc7703c4-79f6-54ab-9265-1a3f777e6e50 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #1 | GPS coordinates taken
77fa18f9-05d1-4557-81f1-908d541da491 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #2
fb3ae7cc-7400-5460-8f2e-e71f5d66a700 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #2 | Mold type, # and cable size identified
11b3b5d4-19e9-57c2-80c2-ae6942f70c43 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #2 | Cadweld Visual test
c24cf9c3-79a1-5060-b486-5696e4b4bb9c |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #2 | Cadweld Ductor test
368a76c6-e071-53d7-8f3f-045504e304da |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #2 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
0eef3507-641c-5047-aea5-6e4a6683ae42 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #2 | GPS coordinates taken
9e4ae6e7-8c87-40a8-8bd6-ecac32367535 |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #3
f0d4ef08-3d43-526b-908d-9cf95d737bff |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #3 | Mold type, # and cable size identified
fea83205-5da0-5a58-bd52-03873e67bb8f |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #3 | Cadweld Visual test
450d3ae4-66ad-552c-ac7b-e25e3b5781ec |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #3 | Cadweld Ductor test
b6320491-48b3-5235-b757-6d83735860bc |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #3 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
2991f257-e111-53bc-94f4-2410208874c2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #3 | GPS coordinates taken
38a3c41e-6e52-4887-b98d-72b06227a04c |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #4
62ac36ba-f844-51d3-ba6c-81911acd68e3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #4 | Mold type, # and cable size identified
5da984a3-39c8-5f27-97a4-d2cd9f17f8ea |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #4 | Cadweld Visual test
e58276ea-94f5-5843-a15a-9d44dad036ab |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #4 | Cadweld Ductor test
c696dbdd-643e-5b68-b9cf-1b00121a99aa |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #4 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
e3219489-c502-5968-8d2d-d7af5935f9ae |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #4 | GPS coordinates taken
47ef47e6-58f6-4c15-acbf-d2c21b20391e |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #5
27efb5a2-c19c-586f-bc5f-a37755a50b1e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #5 | Mold type, # and cable size identified
bbbd5cef-bd76-5025-a8b7-d0d770090986 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #5 | Cadweld Visual test
20934ce3-8ad7-51e3-9236-da7f126fcaf8 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #5 | Cadweld Ductor test
f70c6722-ca9d-5f68-9374-57a5325f9db2 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #5 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
7661c92a-e066-5402-a720-5a33d5ec0780 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #5 | GPS coordinates taken
a31d82e0-7e51-4af6-9636-8dd3cbcc77bc |  | checklist-flat | work-in-progress | 69dd6d208ef151c3f4efe96ab17db40f4e3a6a7f352430f34c6f3d4ffd8276bf | checklist-flat | FALSE | FALSE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #6
41aff4df-d7a5-53cb-bfd1-67404cd7603d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #6 | Mold type, # and cable size identified
1cd69a57-c29a-58a5-8a7a-84561209de53 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #6 | Cadweld Visual test
d5681480-4f0f-5b5e-9383-adee18938cee |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #6 | Cadweld Ductor test
61c94826-6ca4-5f25-aa8d-daf97e620833 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #6 | Cadweld wrapped in 3M SCOTCH 23 RUBBER, 3M TEMFLEX 1500 GREEN TAPE
cb50ab06-2e1b-5db7-9b27-9b6dcda98e12 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Inground Earthing | Cadwelds | TH39 Wellhut | Cadweld #6 | GPS coordinates taken
b9dce75c-0d69-4f0f-80df-63b90390cfa8 |  | folder-normal | pass |  | step | TRUE | FALSE | CSB - UPS Cables
e2a530c2-79b1-4c0b-97af-e8f02e58fde0 |  | folder-normal | pass |  | step | TRUE | FALSE | CSB - UPS Cables | 0000BRU10GH010-A01
055fa6ec-9718-4152-abff-e3cd5bb91ce6 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | CSB - UPS Cables | 0000BRU10GH010-A01 | 1.5mm2 2Pr CuSn PVC/PVC
b087827c-a9b8-5e9f-9352-f8035055a44d |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BRU10GH010-A01 | 1.5mm2 2Pr CuSn PVC/PVC | Low Voltage Cable
3fbb56f2-67e4-5799-b197-0892bc1989c4 |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BRU10GH010-A01 | 1.5mm2 2Pr CuSn PVC/PVC | Electrical Checks
8a3868bb-4e54-598c-a2dc-61fbc47fac77 |  | holdpoint | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BRU10GH010-A01 | 1.5mm2 2Pr CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
389d6353-2348-4f58-812c-11ae56959368 |  | folder-normal | pass |  | step | TRUE | FALSE | CSB - UPS Cables | 0000BRU20GH010-A01
4c161b5b-3a00-4e5f-ade1-8418ae0833a7 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | CSB - UPS Cables | 0000BRU20GH010-A01 | 1.5mm2 2Pr CuSn PVC/PVC
b353f5bb-fbe9-5b88-805d-cb009a1a63ad |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BRU20GH010-A01 | 1.5mm2 2Pr CuSn PVC/PVC | Low Voltage Cable
63433860-4581-5962-9b9c-b996c22ddd11 |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BRU20GH010-A01 | 1.5mm2 2Pr CuSn PVC/PVC | Electrical Checks
714c0a99-94bd-5913-9a10-37d951313404 |  | holdpoint | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BRU20GH010-A01 | 1.5mm2 2Pr CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
980b23b0-77f0-4517-9728-74248c0297ca |  | folder-normal | pass |  | step | TRUE | FALSE | CSB - UPS Cables | 0000BRU10GH010-C01
2ede5913-40b3-44de-9b9e-1db332b2656d |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | CSB - UPS Cables | 0000BRU10GH010-C01 | 1.5mm2 4C CuSn PVC/PVC
221f7c0d-37ef-512e-be1e-6b009351f552 |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BRU10GH010-C01 | 1.5mm2 4C CuSn PVC/PVC | Low Voltage Cable
b0abe0bc-c1b2-53e0-a21c-d6f9604b41d5 |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BRU10GH010-C01 | 1.5mm2 4C CuSn PVC/PVC | Electrical Checks
9a20fcaf-927d-5286-b030-700bd91f9cb1 |  | holdpoint | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BRU10GH010-C01 | 1.5mm2 4C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
26718257-d911-446b-82fb-aed68f75ace0 |  | folder-normal | pass |  | step | TRUE | FALSE | CSB - UPS Cables | 0000BRU20GH010-C01
c49614c8-4423-4521-b270-876ccd1d623f |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | CSB - UPS Cables | 0000BRU20GH010-C01 | 1.5mm2 4C CuSn PVC/PVC
023a9eba-ed78-592b-824b-9891349c5475 |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BRU20GH010-C01 | 1.5mm2 4C CuSn PVC/PVC | Low Voltage Cable
f283694f-4209-574d-b290-51f8f70c5328 |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BRU20GH010-C01 | 1.5mm2 4C CuSn PVC/PVC | Electrical Checks
d829f7a5-f829-5b7e-9489-401902c0416d |  | holdpoint | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BRU20GH010-C01 | 1.5mm2 4C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
1c8710dc-6a26-41cb-b495-1c4412470302 |  | folder-normal | pass |  | step | TRUE | FALSE | CSB - UPS Cables | 0000BRU10GH020-A01
661be0a8-7de7-49b6-be29-7d090b5ee52b |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | CSB - UPS Cables | 0000BRU10GH020-A01 | 1.5mm2 2Pr CuSn PVC/PVC
b376e0ad-62e4-5a4c-b731-1078d04d069c |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BRU10GH020-A01 | 1.5mm2 2Pr CuSn PVC/PVC | Low Voltage Cable
a327ed5d-d857-5b03-bc9d-b125ca33df56 |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BRU10GH020-A01 | 1.5mm2 2Pr CuSn PVC/PVC | Electrical Checks
15d1f798-a9d8-5a1f-a636-791df6523481 |  | holdpoint | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BRU10GH020-A01 | 1.5mm2 2Pr CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
9244dcb2-5cdc-4ba2-a39d-a7231df41621 |  | folder-normal | pass |  | step | TRUE | FALSE | CSB - UPS Cables | 0000BRU20GH020-A01
62a6a43b-1ecc-4fc5-91d4-a122f9cd1db9 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | CSB - UPS Cables | 0000BRU20GH020-A01 | 1.5mm2 2Pr CuSn PVC/PVC
487544ad-37d2-5a9d-a79b-fb38a6c044d1 |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BRU20GH020-A01 | 1.5mm2 2Pr CuSn PVC/PVC | Low Voltage Cable
51da87ea-9f23-5b81-970d-319eae5c1419 |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BRU20GH020-A01 | 1.5mm2 2Pr CuSn PVC/PVC | Electrical Checks
ba9156c1-98e1-5727-b834-85ce0af34025 |  | holdpoint | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BRU20GH020-A01 | 1.5mm2 2Pr CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
106a0506-14d6-42cd-b39c-b5103a81c31b |  | folder-normal | pass |  | step | TRUE | FALSE | CSB - UPS Cables | 0000BRU10GH020-C01
fe2c6f92-fe5b-408f-a555-7eb22f02ce2a |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | CSB - UPS Cables | 0000BRU10GH020-C01 | 1.5mm2 2C CuSn PVC/PVC
c47a1b89-7813-56ae-904e-7138b5ed6326 |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BRU10GH020-C01 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
f197ca2d-c3d9-5f86-bb5e-91b11871acfa |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BRU10GH020-C01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
6a7aa807-bdd0-597d-b73e-d93c5560fa03 |  | holdpoint | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BRU10GH020-C01 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
7a8e50b9-fc70-41b5-acf0-8002d06adada |  | folder-normal | pass |  | step | TRUE | FALSE | CSB - UPS Cables | 0000BRU20GH020-C01
94ce92ea-0bae-49b2-80f3-b1d292d4857b |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | CSB - UPS Cables | 0000BRU20GH020-C01 | 1.5mm2 2C CuSn PVC/PVC
d5e6d21e-a71a-5ab8-a36b-a7207c28f77d |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BRU20GH020-C01 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
ad6ec377-1fd3-58ac-9d81-6781d037978e |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BRU20GH020-C01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
bfbca494-35d2-5830-bbbc-7d23208c8fe7 |  | holdpoint | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BRU20GH020-C01 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
1d6f6acb-aa0c-47e2-ad92-b8fa3d4aaa1a |  | folder-normal | pass |  | step | TRUE | FALSE | CSB - UPS Cables | 0000CYW10GW010-P01
a42ead00-18f7-4f03-9793-09c13e98b388 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | CSB - UPS Cables | 0000CYW10GW010-P01 | 1.5mm2 2C CuSn PVC/PVC
6c12e437-c146-5106-819b-2d910b9f60f9 |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000CYW10GW010-P01 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
eeadc6c9-cfaa-5e3b-a33b-08b935e9be76 |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000CYW10GW010-P01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
d74c309f-b391-5f51-816d-c7dbef698f18 |  | holdpoint | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000CYW10GW010-P01 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
ada3fb8a-5cff-4a31-a735-773e981032e6 |  | folder-normal | pass |  | step | TRUE | FALSE | CSB - UPS Cables | 0000CYW10GW011-P01
43dc2b7c-bee4-4c6d-b27b-6927f96e877a |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | CSB - UPS Cables | 0000CYW10GW011-P01 | 1.5mm2 2C CuSn PVC/PVC
5b00f204-8363-5afa-9a5c-8143cccc5fac |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000CYW10GW011-P01 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
500b9901-14b2-577d-9703-85b78c23fbe0 |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000CYW10GW011-P01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
196e1746-5b33-5e74-bfc5-d014495d316f |  | holdpoint | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000CYW10GW011-P01 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
41368a91-18e1-4b88-9072-3b9a22f69206 |  | folder-normal | pass |  | step | TRUE | FALSE | CSB - UPS Cables | 0000CYW10GW020-P01
f76f0696-511b-48e4-b8d4-dbb263a9f4a9 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | CSB - UPS Cables | 0000CYW10GW020-P01 | 1.5mm2 2C CuSn PVC/PVC
167de724-9b51-5601-9344-5e8b3c221109 |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000CYW10GW020-P01 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
ea477c58-54a3-5e18-b1e1-38a9f694d3cd |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000CYW10GW020-P01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
a3116774-5f2e-54a1-ac82-8b1e9b78f00f |  | holdpoint | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000CYW10GW020-P01 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
b707a8c6-af8f-446c-ba1b-e849445ff6e0 |  | folder-normal | pass |  | step | TRUE | FALSE | CSB - UPS Cables | 0000CYW10GW021-P01
170b8986-94ad-46b7-a30e-5434fa0f8101 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | CSB - UPS Cables | 0000CYW10GW021-P01 | 1.5mm2 2C CuSn PVC/PVC
a2604bce-426d-576b-889b-43a0ea267865 |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000CYW10GW021-P01 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
0e3c5fd6-bd87-563d-ac96-7be225d0c72e |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000CYW10GW021-P01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
7baf756c-0a2b-5c75-bd8e-ca92229692b5 |  | holdpoint | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000CYW10GW021-P01 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
513008bb-93ce-4958-8066-87a49c76e434 |  | folder-normal | pass |  | step | TRUE | FALSE | CSB - UPS Cables | 0000CRA20GW010-P01
62bc3d54-8fb9-4737-8711-b8014362f435 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | CSB - UPS Cables | 0000CRA20GW010-P01 | 1.5mm2 2C CuSn PVC/PVC
0edff960-b0ea-5395-9f66-dbe713f0ad92 |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000CRA20GW010-P01 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
17320fbf-ec3d-5281-bc71-895690391343 |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000CRA20GW010-P01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
197e5ed2-1aeb-5cd9-a305-9278278c085c |  | holdpoint | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000CRA20GW010-P01 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
e37645ff-bcbd-4d76-a910-defcedb0373c |  | folder-normal | pass |  | step | TRUE | FALSE | CSB - UPS Cables | 0000CRA20GW011-P01
a5212121-fa98-4573-9b38-776b834cb3e5 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | CSB - UPS Cables | 0000CRA20GW011-P01 | 1.5mm2 2C CuSn PVC/PVC
b7be431a-9022-5a4a-be1d-6d6051ae069d |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000CRA20GW011-P01 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
0ae33abd-2027-5f11-b3ac-971cce0798a1 |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000CRA20GW011-P01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
b4d3a970-ea69-5711-ab4a-94d1a34127fa |  | holdpoint | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000CRA20GW011-P01 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
c8784dab-5236-4729-8215-1a300db7e3a9 |  | folder-normal | pass |  | step | TRUE | FALSE | CSB - UPS Cables | 0000CRA20GW020-P01
482ee1dc-77bf-4c15-ab71-e4d2976fa0d4 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | CSB - UPS Cables | 0000CRA20GW020-P01 | 1.5mm2 2C CuSn PVC/PVC
93e39d72-9f2d-5c3f-8257-2176c7ef0705 |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000CRA20GW020-P01 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
8ab30d1e-45a7-56de-a972-a0a1f2bae201 |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000CRA20GW020-P01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
040751d5-83a8-5861-922a-f23a1ab1626d |  | holdpoint | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000CRA20GW020-P01 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
90fcd846-733b-46ea-9506-3e4a54c594fb |  | folder-normal | pass |  | step | TRUE | FALSE | CSB - UPS Cables | 0000CRA20GW021-P01
ad8bec90-bf88-41b4-84e3-d8be525e58df |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | CSB - UPS Cables | 0000CRA20GW021-P01 | 1.5mm2 2C CuSn PVC/PVC
3254bd12-80c4-5b91-a638-e9a6e05b2a2c |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000CRA20GW021-P01 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
be5ed881-e215-5f64-b6ee-8a741b5df466 |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000CRA20GW021-P01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
c9efd2f2-1e0d-5a55-99e7-5da1f477bd84 |  | holdpoint | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000CRA20GW021-P01 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
9e70544d-9d03-4fcc-88bb-71033da57ca2 |  | folder-normal | pass |  | step | TRUE | FALSE | CSB - UPS Cables | 0000BJB10GH010-P02
2d74dd8e-fb97-4acd-a464-dfa18255b526 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | CSB - UPS Cables | 0000BJB10GH010-P02 | 1.5mm 2C Cu/Sn PVC/PVC
f71b3c30-0248-593d-9df5-6a6d02cb7f2f |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BJB10GH010-P02 | 1.5mm 2C Cu/Sn PVC/PVC | Low Voltage Cable
4006d343-72ed-54c6-a311-31eb6a5357fa |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BJB10GH010-P02 | 1.5mm 2C Cu/Sn PVC/PVC | Electrical Checks
c9f51e3e-4060-5885-9e62-c2a8ec312493 |  | holdpoint | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BJB10GH010-P02 | 1.5mm 2C Cu/Sn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
87de1616-20ce-4a2e-af22-3cc058e0142b |  | folder-normal | pass |  | step | TRUE | FALSE | CSB - UPS Cables | 0000BJB10GH010-P01
c133803f-002a-4a2e-bf54-dd03d44098a5 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | CSB - UPS Cables | 0000BJB10GH010-P01 | 1.5mm 2C Cu/Sn PVC/PVC
05ec712b-2807-5ee9-a3a0-0b23ff8e01d3 |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BJB10GH010-P01 | 1.5mm 2C Cu/Sn PVC/PVC | Low Voltage Cable
ccfac3a2-1af5-5303-9e19-8be2fc5c73c0 |  | checkpoint-status | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BJB10GH010-P01 | 1.5mm 2C Cu/Sn PVC/PVC | Electrical Checks
de21e426-bd3b-553c-922c-b6c045b8472b |  | holdpoint | pass |  |  | TRUE | TRUE | CSB - UPS Cables | 0000BJB10GH010-P01 | 1.5mm 2C Cu/Sn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
aac305ef-a3cb-4de4-b0a9-8dfbddc6ad3b |  | folder-normal | pass |  | step | TRUE | FALSE | ASB - UPS Cables
06eda962-ab79-4856-b396-792ac4b2fa1d |  | folder-normal | pass |  | step | TRUE | FALSE | ASB - UPS Cables | S030CRA10GW011-P01
7ce341c3-4724-4860-aff7-8c23a70f8592 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | ASB - UPS Cables | S030CRA10GW011-P01 | 4mm2 2C+E CuSn PVC/PVC
edd1430a-587a-5de3-9376-1b8964d20c0c |  | checkpoint-status | pass |  |  | TRUE | TRUE | ASB - UPS Cables | S030CRA10GW011-P01 | 4mm2 2C+E CuSn PVC/PVC | Low Voltage Cable
5ec039db-392d-5bcb-b5be-1122c8cc3c26 |  | checkpoint-status | pass |  |  | TRUE | TRUE | ASB - UPS Cables | S030CRA10GW011-P01 | 4mm2 2C+E CuSn PVC/PVC | Electrical Checks
8ee9c0cb-073d-535e-8b7c-702f5eed6628 |  | holdpoint | pass |  |  | TRUE | TRUE | ASB - UPS Cables | S030CRA10GW011-P01 | 4mm2 2C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
21d156d5-8df2-4f62-8c8b-a061b9c1a8f6 |  | folder-normal | pass |  | step | TRUE | FALSE | ASB - UPS Cables | S030CRA10GW021-P01
8645d698-d546-4a98-805f-4799094953cc |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | ASB - UPS Cables | S030CRA10GW021-P01 | 4mm2 2C+E CuSn PVC/PVC
3d7b9df3-6e47-5f84-a82f-f1762ccf10b6 |  | checkpoint-status | pass |  |  | TRUE | TRUE | ASB - UPS Cables | S030CRA10GW021-P01 | 4mm2 2C+E CuSn PVC/PVC | Low Voltage Cable
5dcd4f36-ea6e-5f16-a298-5609a15b535e |  | checkpoint-status | pass |  |  | TRUE | TRUE | ASB - UPS Cables | S030CRA10GW021-P01 | 4mm2 2C+E CuSn PVC/PVC | Electrical Checks
9879397c-19d5-5347-a89c-5976ac6e5f2e |  | holdpoint | pass |  |  | TRUE | TRUE | ASB - UPS Cables | S030CRA10GW021-P01 | 4mm2 2C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
fa49f767-03c3-4758-85d3-a4901cb1cf4f |  | folder-normal | pass |  | step | TRUE | FALSE | ASB - UPS Cables | S030CRA10GW031-P01
f8dad177-d9f8-45bf-891b-2429a1d187cc |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | ASB - UPS Cables | S030CRA10GW031-P01 | 4mm2 2C+E CuSn PVC/PVC
bae97fb2-af77-544c-af5b-ef2f9e0806b4 |  | checkpoint-status | pass |  |  | TRUE | TRUE | ASB - UPS Cables | S030CRA10GW031-P01 | 4mm2 2C+E CuSn PVC/PVC | Low Voltage Cable
2b8ef969-91a1-554e-bbf1-3036a09e8c10 |  | checkpoint-status | pass |  |  | TRUE | TRUE | ASB - UPS Cables | S030CRA10GW031-P01 | 4mm2 2C+E CuSn PVC/PVC | Electrical Checks
374d56eb-7124-5a78-957f-ec6c84611049 |  | holdpoint | pass |  |  | TRUE | TRUE | ASB - UPS Cables | S030CRA10GW031-P01 | 4mm2 2C+E CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
04a2634a-72f1-408a-8bff-9c9b26923d7e |  | folder-normal | pass |  | step | TRUE | FALSE | ASB - UPS Cables | 0000BRU30GH010-C01
e4c358d9-f730-4897-8542-72e280a95cb6 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | ASB - UPS Cables | 0000BRU30GH010-C01 | 1.5mm2 4C CuSn PVC/PVC
60394c26-0368-54a6-bb64-4c951584850d |  | checkpoint-status | pass |  |  | TRUE | TRUE | ASB - UPS Cables | 0000BRU30GH010-C01 | 1.5mm2 4C CuSn PVC/PVC | Low Voltage Cable
32e961e3-b1e2-58a1-abd6-9a3daca16e03 |  | checkpoint-status | pass |  |  | TRUE | TRUE | ASB - UPS Cables | 0000BRU30GH010-C01 | 1.5mm2 4C CuSn PVC/PVC | Electrical Checks
7b80bb72-6ebc-508d-8136-0258fdceb501 |  | holdpoint | pass |  |  | TRUE | TRUE | ASB - UPS Cables | 0000BRU30GH010-C01 | 1.5mm2 4C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
cb69d60b-ef46-4569-a6a3-990ddaf15c1e |  | folder-normal | pass |  | step | TRUE | FALSE | ASB - UPS Cables | 0000BFA40GH010-P02
2576fced-7272-4bb2-91dc-1f20c3802319 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | ASB - UPS Cables | 0000BFA40GH010-P02 | 1.5mm2 2C CuSn PVC/PVC
9b6bda9f-62f9-5926-b513-7a4c8f75f25f |  | checkpoint-status | pass |  |  | TRUE | TRUE | ASB - UPS Cables | 0000BFA40GH010-P02 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
631dab56-b7f7-55a5-8679-18ad6b494590 |  | checkpoint-status | pass |  |  | TRUE | TRUE | ASB - UPS Cables | 0000BFA40GH010-P02 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
f91f3bc4-8b57-5a49-8a17-43f4c3b85db1 |  | holdpoint | pass |  |  | TRUE | TRUE | ASB - UPS Cables | 0000BFA40GH010-P02 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
5a4b97a3-4e50-4039-86f0-8d6a99ecc753 |  | folder-normal | pass |  | step | TRUE | FALSE | ASB - UPS Cables | 0000BFA40GH010-P03
6e46956b-2998-43f4-ae37-5f5762e65958 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | ASB - UPS Cables | 0000BFA40GH010-P03 | 1.5mm2 2C PVC/PVC
e44c5bf6-b2f3-5762-bc62-cbb735cc2ed3 |  | checkpoint-status | pass |  |  | TRUE | TRUE | ASB - UPS Cables | 0000BFA40GH010-P03 | 1.5mm2 2C PVC/PVC | Low Voltage Cable
d6c6ca65-14fe-5094-84eb-e33f6fc77410 |  | checkpoint-status | pass |  |  | TRUE | TRUE | ASB - UPS Cables | 0000BFA40GH010-P03 | 1.5mm2 2C PVC/PVC | Electrical Checks
a070d2d0-7326-50da-a03b-18b97fd3a074 |  | holdpoint | pass |  |  | TRUE | TRUE | ASB - UPS Cables | 0000BFA40GH010-P03 | 1.5mm2 2C PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
a8ffca8a-3987-463c-a13b-ce0f0b9d809a |  | folder-normal | pass |  | step | TRUE | FALSE | ASB - UPS Cables | 0000BRU30GH010-A01
df6d4d76-29d8-4a81-96ca-d701a3981d1d |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | ASB - UPS Cables | 0000BRU30GH010-A01 | 1.5mm2 2pr CuSn PVC/PVC
be65ad5c-679d-5bed-86c2-c2076324fe50 |  | checkpoint-status | pass |  |  | TRUE | TRUE | ASB - UPS Cables | 0000BRU30GH010-A01 | 1.5mm2 2pr CuSn PVC/PVC | Low Voltage Cable
4877e3ae-1357-58c3-be1c-ac49498c0dcb |  | checkpoint-status | pass |  |  | TRUE | TRUE | ASB - UPS Cables | 0000BRU30GH010-A01 | 1.5mm2 2pr CuSn PVC/PVC | Electrical Checks
64afb56c-f5aa-54c4-b29f-2cf105590a97 |  | holdpoint | pass |  |  | TRUE | TRUE | ASB - UPS Cables | 0000BRU30GH010-A01 | 1.5mm2 2pr CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
5c1c5c41-a878-4e25-9ef1-835565fe38ac |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | ASB - UPS Cables | Bonding
d11e0acb-a20c-453e-954d-7c44b79623b9 |  | folder-normal | pass |  | step | TRUE | FALSE | SEP - UPS Cables
8392bded-4604-4e32-86f0-f02a92c84eb2 |  | folder-normal | pass |  | step | TRUE | FALSE | SEP - UPS Cables | S030BJB10GH010-P01
85411f78-a9f3-4e79-bd69-586b34933534 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | SEP - UPS Cables | S030BJB10GH010-P01 | 1.5mm2 2C CuSn PVC/PVC
07207099-f4d6-5497-933a-9529a2992eb2 |  | checkpoint-status | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030BJB10GH010-P01 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
ab046969-7d1e-53e3-b570-01277b06c2d6 |  | checkpoint-status | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030BJB10GH010-P01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
00485692-d6fa-518e-ad0e-f8967e66a845 |  | holdpoint | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030BJB10GH010-P01 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
c7f5c220-1a26-4ac1-b20d-851ab9153668 |  | folder-normal | pass |  | step | TRUE | FALSE | SEP - UPS Cables | S030BRU10GH010-A01
faa44aa9-1f14-4bd4-b624-0817863ed9f0 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | SEP - UPS Cables | S030BRU10GH010-A01 | 1.5mm2 2pr CuSn PVC/PVC
ac0206c4-86d1-5dbc-a66e-71f808975309 |  | checkpoint-status | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030BRU10GH010-A01 | 1.5mm2 2pr CuSn PVC/PVC | Low Voltage Cable
ea0de91f-c99e-5e8f-80dd-5ae7b6bdd75a |  | checkpoint-status | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030BRU10GH010-A01 | 1.5mm2 2pr CuSn PVC/PVC | Electrical Checks
69f01c7d-be5c-5ffe-b420-2e339337fca2 |  | holdpoint | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030BRU10GH010-A01 | 1.5mm2 2pr CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
77f0016a-f192-4944-9b11-5b24b9eb1721 |  | folder-normal | pass |  | step | TRUE | FALSE | SEP - UPS Cables | S030BRU10GH010-C01
ae5056e8-38ec-4d7d-8ea5-43c03def1802 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | SEP - UPS Cables | S030BRU10GH010-C01 | 1.5mm2 4C CuSn PVC/PVC
6f1880b0-3904-500f-bfef-e3ca1b5b5457 |  | checkpoint-status | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030BRU10GH010-C01 | 1.5mm2 4C CuSn PVC/PVC | Low Voltage Cable
fa3e00db-9f19-57bb-b3d9-a54edee06286 |  | checkpoint-status | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030BRU10GH010-C01 | 1.5mm2 4C CuSn PVC/PVC | Electrical Checks
e6846e68-b0cf-5b47-8585-cc51c29d46c1 |  | holdpoint | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030BRU10GH010-C01 | 1.5mm2 4C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
4c17e85a-3667-4951-ac01-99cc9dec3e59 |  | folder-normal | pass |  | step | TRUE | FALSE | SEP - UPS Cables | S030CRA10GW010-P01
230c22ad-8ab0-4cb4-8a6a-04088e93d535 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | SEP - UPS Cables | S030CRA10GW010-P01 | 1.5mm2 2C CuSn PVC/PVC
85acdd7e-3f8a-55aa-a9b7-9d365a42162e |  | checkpoint-status | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030CRA10GW010-P01 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
d567bdc0-9ca5-5b56-8a4a-3f99b4ba7da1 |  | checkpoint-status | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030CRA10GW010-P01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
6880386c-08c4-5b94-ab43-ffa2485080e5 |  | holdpoint | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030CRA10GW010-P01 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
d9bf86bd-7313-46f4-9edf-e3256aa0d026 |  | folder-normal | pass |  | step | TRUE | FALSE | SEP - UPS Cables | S030CRA10GW020-P01
ac476db8-3dfb-4d54-bf1c-cbe6d7f6f9d3 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | SEP - UPS Cables | S030CRA10GW020-P01 | 1.5mm2 2C CuSn PVC/PVC
9f57f526-81a5-53ac-b0fd-f60212b44973 |  | checkpoint-status | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030CRA10GW020-P01 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
a7389695-d28f-55e1-b35f-3642e9b42b05 |  | checkpoint-status | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030CRA10GW020-P01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
7723a7bf-f6fe-5232-9a47-9f384b5f4a4e |  | holdpoint | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030CRA10GW020-P01 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
84010880-ceea-474b-97a1-e5b1fbafdaba |  | folder-normal | pass |  | step | TRUE | FALSE | SEP - UPS Cables | S030CRA10GW030-P01
eacbacda-631d-42c0-aa2f-3444f2009c07 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | SEP - UPS Cables | S030CRA10GW030-P01 | 1.5mm2 2C CuSn PVC/PVC
a1f529a4-091d-5df7-930f-fb4c394ac44a |  | checkpoint-status | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030CRA10GW030-P01 | 1.5mm2 2C CuSn PVC/PVC | Low Voltage Cable
b784bc4d-cd96-5bcb-80cb-c54472d551b0 |  | checkpoint-status | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030CRA10GW030-P01 | 1.5mm2 2C CuSn PVC/PVC | Electrical Checks
a4273809-fb93-588a-8e65-261b8d3aebb9 |  | holdpoint | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030CRA10GW030-P01 | 1.5mm2 2C CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
520ed639-bc87-4733-b2da-5d3f61730edf |  | folder-normal | pass |  | step | TRUE | FALSE | SEP - UPS Cables | S030CRJ10GW011-P01
f0e2fce5-0e73-42a6-8092-8fafc5d81cc9 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | SEP - UPS Cables | S030CRJ10GW011-P01 | 4mm 2C+E PVC/PVC
bfd232df-82c7-580b-a921-f984e889169d |  | checkpoint-status | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030CRJ10GW011-P01 | 4mm 2C+E PVC/PVC | Low Voltage Cable
be1770dd-f643-54b0-a870-79254eb64a61 |  | checkpoint-status | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030CRJ10GW011-P01 | 4mm 2C+E PVC/PVC | Electrical Checks
1abb62b9-cdb5-5d5d-a7af-a9860b111ede |  | holdpoint | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030CRJ10GW011-P01 | 4mm 2C+E PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
b7c21689-8843-4f47-ad85-476ba25fff74 |  | folder-normal | pass |  | step | TRUE | FALSE | SEP - UPS Cables | S030BJB10GH010-P02
1ead9864-e813-4841-9e91-02ed3029e0d0 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | SEP - UPS Cables | S030BJB10GH010-P02 | 1.5mm2 2C PVC/PVC
3e0c2126-2e7a-5bb9-a31c-cc9b6cadb049 |  | checkpoint-status | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030BJB10GH010-P02 | 1.5mm2 2C PVC/PVC | Low Voltage Cable
306f28bf-f3e4-5635-a403-0c3122abe573 |  | checkpoint-status | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030BJB10GH010-P02 | 1.5mm2 2C PVC/PVC | Electrical Checks
85fbeef1-0fa6-5a9c-b34c-50fc1065cada |  | holdpoint | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030BJB10GH010-P02 | 1.5mm2 2C PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
4ee21d46-1187-4a82-b896-1613434a4452 |  | folder-normal | pass |  | step | TRUE | FALSE | SEP - UPS Cables | S030BRU10GH010-A01
1384b6c2-1c5a-4643-ae2c-90bc046ccbf3 |  | checklist-flat | pass | ITR-CL-1-104 - Low Voltage Cable | checklist-flat | FALSE | FALSE | SEP - UPS Cables | S030BRU10GH010-A01 | 1.5mm2 2pr CuSn PVC/PVC
f1e7bde4-92aa-5cdf-a02d-4a85a8121b16 |  | checkpoint-status | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030BRU10GH010-A01 | 1.5mm2 2pr CuSn PVC/PVC | Low Voltage Cable
dea4e021-3b4f-5bec-9fe9-158e5d9c1b13 |  | checkpoint-status | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030BRU10GH010-A01 | 1.5mm2 2pr CuSn PVC/PVC | Electrical Checks
b2d743d9-3891-514f-855b-0ba92bde57d0 |  | holdpoint | pass |  |  | TRUE | TRUE | SEP - UPS Cables | S030BRU10GH010-A01 | 1.5mm2 2pr CuSn PVC/PVC | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
68887403-8f4c-40c9-b50c-763250a94d93 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | SEP - UPS Cables | Bonding