## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-151-STR-Shotcrete-SSB
ITP Description: |  | Shotcrete-SSB
Discipline (e.g. CIV/STR/RAIL: |  | 151-STR
Revision Number: |  | 0
Revision Date: |  | 2024-04-19
ITP created by: |  | Mike Freeman
ITP approved for use by: |  | Mike Freeman
Special Notes to ConQA Team : |  | ITP to be visible for Station Street
Inspection & Test Plan - Shotcreting
|  |  | Document No.: | [5 empty] | Revision: | 0
[9 empty] | Date: | 2024-04-19
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 610 June 2019 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.2 | Non Dependent | VicRoads Section 611 November 2018 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.3 | Non Dependent | VicRoads Section 684 April 2019 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.4 | Non Dependent | AS3810.1 2018 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | Preliminaries - Materials
2.1 | Concrete Mix | 684.04 (a) 684.04 (d) (i & ii) 684.05 (a) (i & ii) Table 684.051 684.05 (b) Table 684.052 610.07 Table 610.071 | Concrete Mix is Registered with VicRoads. Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings. Maximum drying shrinkage shall meet the values shown on table 684.052. Where applicable, steel fibres shall: i. be deformed ii. have a minimum tensile strength of 800MPa iii. have an aspect ratio between 40 and 70 iv. have a minimum dosage rate as per table 684.051 Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each mix design, 4 weeks prior to placement of concrete | HP | Nominated Authority | ConQA Hold Point Release
2.2 | ACRS Certification (for Reinforcement) | 684.04 (c) 611.05 (a) | Current ACRS certification for materials and for bar processing. Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery) Enter: Teambinder Material Approval number [free text box] | Document Review | Once for each supplier, 14 days of award of contract | WP | Nominated Authority | This ITP
2 | Preliminaries - Materials (Continued)
2.3 | Galvanising (for Reinforcement) | 684.04 (c) | All reinforcement and tie wire used in the Works shall be hot-dipped galvanised in accordance with AS4680. Attach: Galvaniser's Certificate of Compliance | Document Review | For each reinforcement delivery from each galvaniser | WP | Nominated Authority | This ITP
2.4 | Bar Chairs/Aspros Certification | 610.26 (a) | Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads. Concrete aspros require annual compressive strength and soluble salt testing is required. Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box] | Document Review | Once for each supplier, 14 days prior to placement of reinforcement | WP | Nominated Authority | This ITP
2.5 | Evaporative Retardant | 684.10 (b) 684.11 610.17 (f) | Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product, 4 weeks prior to placement of concrete | WP | Nominated Authority | This ITP
3 | Preliminaries - Procedures & Documentation
2.6 | Curing Compound | 684.12 610.23 (d) | Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product, 4 weeks prior to placement of concrete | WP | Nominated Authority | This ITP
3.1 | Shotcrete Work Method Statement | 684.07 (a) 684.07 (d) (i) 684.07 (d) | Shotcrete WMS, detailing the proposed equipment and preparation works, to be submitted for review to the Nominated Authority. Any changes to the approved WMS shall be deemed a new Hold Point. Enter: Teambinder Approval number [free text box] | Document Review | Once, 4 weeks prior to placement of concrete | HP | Nominated Authority | ConQA Hold Point Release
3.2 | Contractor Competency | 684.06 684.07 (a) 684.07 (d) | Personnel undertaking the shotcrete works, including the nozzle operator, supervisor and finisher, shall have a minimum of 5 years experience in shotcrete application. Any changes to personnel shall be deemed a new Hold Point. Enter: Teambinder Approval number [free text box] | Document Review | Once, 4 weeks prior to commencement of works and for any personnel changes | HP | Nominated Authority | ConQA Hold Point Release
3 | Preliminaries - Procedures & Documentation (Continued)
3.3 | Test Panels | 684.07 (b - d) 684.07 (d) (i) 684.10 (a) | For each combination of nozzle operator, concrete mix and spraying equipment, 2 no. test panels (750mm x 750mm x the maximum design thickness or 150mm min.), shall be cast. The panels shall be cast using the same reinforcement design and in the same orientation as the Works - panels shall not be cast horizontally on the ground. For each test panel, 8 no. core samples shall be taken, perpendicular to the surface, no closer than 125mm from the edge and after 48 hours minimum. Core samples shall be tested for: 1 no. 3 day compressive strength 1 no. 7 day compressive strength 2 no. 28 day compressive strength 2 no. VPV tests 2 no. visual inspection showing reinforcement encasement in concrete Any changes to approved test panel combinations is deemed a new Hold Point. Where existing test results for the same combinations exist, this is considered to be a pre-qualification and new test panels are not required. Enter: Teambinder Approval Number [free text box] | Document Review | Once, 4 weeks prior to placement of concrete, for each combination of personnel, concrete mix and equipment | HP | Nominated Authority | ConQA Hold Point Release
3.4 | Concrete Sampling and Testing Procedure | 684.08 (a) 610.18 (a) (v) | Concrete sampling and testing procedure to be submitted for review to the Nominated Authority. Enter: Teambinder Approval number [free text box] | Document Review | Once, 4 weeks prior to placement of concrete | HP | Nominated Authority | ConQA Hold Point Release
3.5 | Shotcrete Prequalification Toolbox Meeting | 684.07 (d) (ii) | Shotcrete prequalification toolbox meeting held to discuss the quality requirements. Minutes of this meeting to be submitted to the Nominated Authority. Enter: Teambinder Approval number [free text box] | Document Review | Once, prior to placement of concrete | HP | Nominated Authority | ConQA Hold Point Release
3 | Preliminaries - Procedures & Documentation (Continued)
3.6 | Hot and/or Cold Weather Concreting Procedure | 684.10 (b) 610.17 (a) | Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority. Enter: Teambinder Approval number [free text box] | Document Review | Once, 2 weeks prior to placement of concrete | WP | Nominated Authority | This ITP
3.7 | Curing Methodology (for Concrete and Grout) | 684.12 610.23 (a) | Curing methodology/procedure to be submitted for review to the Nominated Authority. Enter: Teambinder Approval number [free text box] | Document Review | Once, 4 weeks prior to placement of concrete | HP | Nominated Authority | ConQA Hold Point Release
4 | Pre-construction Activities
4.1 | IFC Drawings | MRPA Quality Management Plan | Check the revision of the IFC drawings are current as per the drawing register (on Teambinder) | Document Review | Prior to starting Works and at regular intervals | HP* | All | This ITP
4.2 | Substrate Preparation | IFC Drawings Shotcrete WMS 684.09 (a - c) | Substrate shall be formed to the correct line and grade to provide adequate thickness for the works and shaped (or repaired - for concrete) to prevent any abrupt changes in thickness of the shotcrete. Any loose materials, oils, grease and coatings of any description shall be removed. Smooth concrete substrates shall be roughened to create a construction joint. | Measure Visual | Each lot | IP | Foreman SE/PE/SPE | This ITP
4.3 | Subsurface Drainage | IFC Drawings 684.09 (a) 702.03 702.06 702.07 702.09 (f) | Subsurface drains shall be the type nominated on the IFC drawings - any changes must be approved by the designers if no equivalent exists. The drainage shall be wrapped in geotextile, full height of the structure and located as shown on the IFC drawings against the substrate to prevent encasement in concrete. Joints in the drainage shall be over-lapped 450mm min. by the geotextile. | Measure Visual | Where applicable, each lot | IP | Foreman SE/PE/SPE | This ITP
4.4 | Waterstop Seals, Compressible Seals & Isolation Joints | IFC Drawings Product TDS | Waterstop seals, compressible seals and isolation joints shall be the system(s) nominated on the IFC drawings - any changes must be approved by the designers if no approved equivalent exists. Seals and isolation joints must be full height of the structural element(s) and located as per the IFC drawings. | Measure Visual | Where applicable, at each existing structural element | IP | Foreman SE/PE/SPE | This ITP
5 | Construction Activities
5.1 | Reinforcement Placement | IFC Drawings 684.04 (c) 684.09 (c) 611.06 611.09 611.10 611.11 611.12 | The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings. Tie wire is to match the reinforcement it is securing, with contact between dissimilar metals isolated with zinc-rich spray paint, electrical tape or have a minimum gap of 10mm. Layers are spaced apart using bent reinforcement, not bar chairs. Projecting reinforcement is the correct length and location. Splice lengths achieve the minimum length and are in contact for this length. The reinforcement surface condition is free from dirt, debris and damage. The resulting cage securely held with sufficient ties to limit displacement or deformation during the shotcrete application. Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations). | Measure Visual | Each lot | IP | Foreman SE/PE/SPE | This ITP
5.2 | Cast-in Items | IFC Drawings 610.47 (a) Table 610.472 AS3810.1 Table 3.3.6.2 | All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement. Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress. Tack welding of any cast-in items shall be performed by someone pre-qualified to do so. Grout tubes shall be fastened at regular intervals to prevent kinking. Placement tolerances to comply with the IFC drawings, if not specified, use the following: i. Bolts, ferrules, projecting bars & couplers = ±3mm ii. Running dimensions of a group of the above = ±6mm iii. Ducts and conduit location = ±12mm iv. Diameter of ducts and conduits = ±3mm | Measure Visual | Where applicable, each element | IP | Foreman SE/PE/SPE | This ITP
5 | Construction Activities (Continued)
5.3 | Pre-pour Inspection | IFC Drawings Bonded Anchors ITP 684.10 (b) | All preparation works on the substrate have been completed and the surface moistened without free-standing water to prevent premature drying of the shotcrete. Evidence that the reinforcement and embedments are conforming to the requirements of the specifications and the IFC drawings. | Measure Visual | Each lot | HP | Nominated Authority | ConQA Hold Point Release
5.4 | Weather Conditions & Evaporation Limits | Hot and/or Cold Weather Concreting Procedure 684.10 (b) 610.17 610.17 (a) & (e) Table 610.171 | All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented. The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete. When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS. Record: Required information on the Concrete Pour Record. | Measure Visual | Each lot | IP | Foreman SE/PE/SPE | This ITP
5.5 | Concrete Testing - Sampling Frequency | Site Sampling & Testing Procedure 684.08 (a) RC 377.01 610.16 (b) | Concrete cast in one continuous operation to be tested at a frequency as shown below: 0m³ to 10m³ = 1 sample 10m³ to 25m³ = 2 samples 25m³ to 50m³ = 3 samples 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders. For each additional 50m³ and additional sample shall be taken. Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum. Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength. Where applicable, fibre dosage rates are to be tested at a frequency of 1 in every 5 truck loads. Record: Required information on the Concrete Pour Record. | Test | Each lot | IP | Concrete Tester Foreman SE/PE/SPE | This ITP
5 | Construction Activities (Continued)
5.6 | Concrete Testing - Slump | 684.08 (a) 610.16 (c) | Slump testing tolerances = <60mm = ±10mm ≥60mm to ≤80mm = ±15mm >80mm to ≤110mm = ±20mm >110mm to ≤150mm = ±30mm >150mm = ±40mm Record: Required information on the Concrete Pour Record. | Test | Each sample of Standard or Superplasticised Concrete | IP | Concrete Tester | This ITP
5.7 | Concrete Testing - Compressive Strength Cylinders | Site Sampling & Testing Procedure | Correct quantity of cylinders manufactured per sample. Record: Required information on the Concrete Pour Record. | Test | Each sample | IP | Concrete Tester | This ITP
5.8 | Supply & Discharge Rates | 684.05 (c) 610.13 (a) & (f) | Concrete is supplied at an adequate rate to ensure no cold joints are formed. No water is to be added once discharge commences. Maximum time between batching trucks is 25 minutes. Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants. Concrete that stiffens or is showing signs of stiffening shall not be used. Record: Required information on the Concrete Pour Record. | Measure Visual | Each load | IP | Foreman SE/PE/SPE | This ITP
5 | Construction Activities (Continued)
5.9 | Application Process | Shotcrete Work Method Statement 684.10 (b) 684.13 610.18 (a) & (b) | All concrete batches are traceable. Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged. Probes or non-corrosive thickness indicators shall be used during the application to determine the actual application thickness. The spray nozzle shall be held to ensure placement of concrete behind and around all steel reinforcement. For vertical surfaces, application shall commence at the bottom and overhead surfaces shall be applied from the shoulder to the crown. Each layer of the sprayed concrete shall be built up by making several passes over the working area with a maximum layer thickness of 150mm. Concrete shall not be sprayed through more than one layer of reinforcement in one application. Where a layer of sprayed concrete is to be covered by succeeding layers, it shall be allowed to set prior to application of the succeeding layer without the need for curing compounds. The surface shall be checked for soundness, segregated, loose or otherwise uncompacted sprayed concrete removed, repaired as specified, cleaned, and wetted using a blast of air and water, leaving a dense, homogenous monolithic layer. Record: Required information on the Concrete Pour Record. Attach: Concrete Pour Record Attach: Concrete Dockets | Visual | Each load | SP | Foreman SE/PE/SPE
5 | Construction Activities (Continued)
5.10 | Surface Finishes | IFC Drawings 684.11 684.14 610.31 610.20 | Surface finish as per IFC drawings. Where surface finish is not detailed, structural concrete retaining walls, soil nail walls, tunnel linings, CP Overlay and other structural components forming part of permanent Works shall have a class 2 finish to reduce the chance of cracking. Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority. | Visual | Each element | IP | Foreman SE/PE/SPE | This ITP
5.11 | Curing | Curing Methodology 684.10 (b) 610.23 Table 610.231 | Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231. Curing methodology to be in accordance with the approved procedure and manufacturer's TDS. | Visual | Each lot | SP | Foreman SE/PE/SPE | This ITP
6 | Post-construction Activities
6.1 | Concrete Testing - Core Sample Frequency | Site Sampling & Testing Procedure 684.04 (d) Table 684.041 610.16 (b) | 75mmØ core samples shall be taken after avoiding reinforcement, from each day's production for each lot at a frequency as shown below: 0m³ to 25m³ = 1 sample 25m³ to 50m³ = 2 samples For each additional 50m³ an additional sample shall be taken. Each sample shall consist of 5 no. core samples, taken perpendicular to the surface, no closer than 200mm from the edge and after 48 hours minimum. Core samples shall be tested for: 1 no. 7 day compressive strength 2 no. 28 day compressive strength 2 no. VPV tests Note: MRPA has D.o.T acceptance to remove the 3 day core and take core samples on test panels in lieu of completed Works See: MRP-MRPA-GNC-XCN-0096 E-mail from D.o.T 7.06.2021 | Test | Each lot | IP | Foreman SE/PE/SPE | This ITP
6 | Post-construction Activities (Continued)
6.2 | Compressive Strength & VPV Test Results | IFC Drawings 684.08 (e) (i - iii) Table 610.051 Table 610.061 610.16 (g) | 3 & 7 day compressive strengths (cylinders and core samples) to comply with table 610.051 for early indication that the strength is tracking correctly. 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength and VPV results comply with table 610.061. Visual inspection of all cores confirm that the minimum thickness of no less than 85% x thickness, and there are no signs of defects. Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength. Note: The average of the 2 no. 28 day cores per sample may be as low as 85% of the required strength, as long as the difference between each core, does not exceed 20%. Attach: Compressive Strength Test Results Attach: Core Sample Compressive Strength Test Results | Document Review | Each cylinder and core sample | IP | SE/PE/SPE | This ITP
6.3 | Surface Inspection | IFC Drawings 684.08 (b) 684.15 684.16 610.31 (a) - (n) 610.32 610.24 | Surface to be as per the required class of finish with no visible lack of compaction, dry patches, voids or sand pockets. Soundness inspection shall be conducted with a small hammer to locate ‘drummy’ or ‘hollow’ response areas which indicate a possible lack of bond, delamination or other defect. For core sample penetrations and if any visual defects are observed, follow Structural Concrete Cementitious Patch Repair ITP for investigation and repair. No cracks greater than 0.2mm (exposure classification B1) If cracking is observed, complete the Structural Concrete Crack Repair ITP for investigation and repair. | Visual Measure | Each element | IP | SE/PE/SPE | This ITP and/or Structural Concrete Crack Repair ITP
6 | Post-construction Activities (Continued)
6.4 | Fibre Wash-out Test Results | 684.08 (c) | Fibre wash-out test results shall be within 1% of the concrete mix design fibre dosage rate. Attach: Fibre Wash-out Test Results | Document Review | Where applicable, each test | IP | SE/PE/SPE | This ITP
6.5 | As-built Survey | IFC Drawings 684.13 610.47 Table 610.472 | Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element. Where a shape is required, ±25mm with no depressions greater than 15mm. Attach: Survey As-builts / Survey Report | Document Review | Each element | IP | Surveyor SE/PE/SPE | This ITP
6.6 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /