## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | FC - S - External Envelope |  |  |  |  | Yes | FC - S - External Envelope | 88eda53c-370d-42d9-87fa-2f02b4420f94
checkpoint-status |  |  | checkpoint | Eco ply taped nailing checked
label | 98ac687d-181e-5db5-9660-1abc095fad3e |  | note | Supplied & installed by others
checkpoint-status |  |  | checkpoint | RAB board Fixing and spacings checked in accordance with manufacturers specs (Photos attached)
checkpoint-status |  |  | checkpoint | Fire strip installed (Photos attached)
checkpoint-status |  |  | checkpoint | Soffit checked and accurate (Photos attached)
checkpoint-status |  |  | checkpoint | Garage reveals checked and accurate (Photos attached)
checkpoint-status |  |  | checkpoint | DPC installed checked and accurate (Photos attached)
holdpoint |  |  | signoff | Request sign off
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | FC - S - Exterior Timber Framing |  |  |  |  | Yes | FC - S - Exterior Timber Framing | a12e5349-1ac9-4cf1-b851-1c86a5e2c5cd
checkpoint-status |  |  | checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint-status |  |  | checkpoint | Framing Dimensions / locations checked & accurate
checkpoint-status |  |  | checkpoint | All frames have been installed square, straight and plumb
checkpoint-status |  |  | checkpoint | DPC installed (if required) correctly
checkpoint-status |  |  | checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint-status |  |  | checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (ensure acoustic & fire rating requirements)
checkpoint-status |  |  | checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | FC - S - Windows, Sliders and Sealants |  |  |  |  | Yes | FC - S - Windows, Sliders and Sealants | ab347309-0214-42b0-b4cf-1105a6a4124d
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Fixings and clearance around opening min 6mm & max 18mm and PEF rod/air seal are within acceptable tolerance level
checkpoint-status |  |  | checkpoint | Check taping around, before installing the windows and sliders
checkpoint-status |  |  | checkpoint | Packers to be correctly used and set back to allow continuous air seal
checkpoint-status |  |  | checkpoint | Jambs level and straight for finishing lines on the side
checkpoint-status |  |  | checkpoint | Door and window jambs flush to GIB Board
checkpoint-status |  |  | checkpoint | Check air seal is provided at the rear of the window reveal
checkpoint-status |  |  | checkpoint | All joints detailed as per attached Detail Document
checkpoint-status |  |  | checkpoint | All framing completed correctly within tolerance in respective area
checkpoint-status |  |  | checkpoint | Sill support fixing bars installed for all joinery within acceptable tolerance level
checkpoint-status |  |  | checkpoint | All windows, sliders and sealant installation completed to specification & within tolerance in respective area(s)
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS