## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | SNOC ITP Beatrice St To Fox St West - 670582 ITP v1.1 | itp |  |  |  | Yes | SNOC ITP Beatrice St To Fox St West - 670582 ITP v1.1 | 0ae1763f-4f63-4259-9b13-04c64b1f82d7
checkpoint-group |  |  | section | Preliminary and General
checkpoint-status |  |  | checkpoint | 1.1 - Construction Programme Completion
label | b34a5d77-8c3c-5d18-a2c4-441d9b757080 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 1e1df8ef-70bc-5158-a2c7-97bdde40a7f3 |  | note | METHODS OR REFERENCE - Best Practice Contract Specific MMP
label | 7c777f8d-6386-5f25-a1b7-3eac242764b2 |  | note | FREQ. - Before work commences
label | fb7c2051-c381-5ca6-b257-58bbb9ef59de |  | note | ACCEPTANCE CRITERIA - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date.
label | 35ab8e4a-fc84-5ed2-b833-14663a5d04f2 |  | note | INSPECTORATE W/H: Type - W
label | 38247ab1-5161-5910-8af5-e7cd02c64714 |  | note | RESPONSIBLE PERSON - Renewals Manager
checkpoint-status |  |  | checkpoint | 1.2 - Approved RQP
label | bbbf2772-7c9a-57be-8801-a2e2952b2450 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 25fa7f95-b93e-524b-af59-60b39b9a576c |  | note | METHODS OR REFERENCE - Contract Specification
label | 65b84833-fcf1-516e-a4ce-83c2c79460c6 |  | note | FREQ. - Before work commences
label | 8a172c85-5c35-5bed-9317-32fec0fdb9a3 |  | note | ACCEPTANCE CRITERIA - Principal Acceptance according to guidelines in appendix 6.3
label | e452676e-8019-5c92-a815-64b8b6660f09 |  | note | INSPECTORATE W/H: Type - H
label | 80ca15a2-3f68-5414-806c-9edd848e89ad |  | note | INSPECTORATE W/H: Description - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. NZTA to approve
label | 810c1736-634c-5343-b26b-212f0dbbe589 |  | note | RESPONSIBLE PERSON - Renewals Manager
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3 - Traffic Management - TMP
label | 2fd4f17a-d506-5685-a035-1e5a4f8b7a44 |  | note | VERIFICATION ACTIVITY - Visual check
label | 41caa907-0088-50c9-958b-dd092a6b7564 |  | note | METHODS OR REFERENCE - CoPTTM
label | 8a41575a-73fa-5fe8-8990-d456bed05c6c |  | note | FREQ. - Before traffic management set up
label | 1f1f01c2-cee5-5c01-8205-1ee77fc79d11 |  | note | ACCEPTANCE CRITERIA - TMP checked and approved Plans approved, Current EED (if applicable)
label | f872213a-23a7-59f9-98b1-2885672eb693 |  | note | INSPECTORATE W/H: Type - H
label | 9dd57f3f-6d57-56c4-9f24-5a450271e7e7 |  | note | INSPECTORATE W/H: Description - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | 64d938b1-b24f-5e89-93d2-d95d7a101298 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.4 - Mix Design Verification for all mixes Check Laydown Trials are complete and compliant
label | db501463-188e-5706-8066-4627aa7d7429 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 343db0a3-7556-5480-a23a-82226056fe14 |  | note | METHODS OR REFERENCE - NZTA M/10, P/11, P23
label | df9da1b8-9d88-58a7-bb93-c3699845587e |  | note | FREQ. - Before planning commences
label | 387b209c-7501-57dc-bcba-9ac2ae28fd45 |  | note | ACCEPTANCE CRITERIA - Mix Design compliant, current and relevant. Batching plant production capability is confirmed
label | 8a7b92aa-aa4e-5638-afac-f9ff5b98b555 |  | note | INSPECTORATE W/H: Type - H
label | bc4a0d2e-fe9d-5d9f-9758-9e89f6132be4 |  | note | INSPECTORATE W/H: Description - Hold point - No planning of on-site works shall commenced until the mix design is verified.
label | 3102f812-eb97-5328-a8cc-ad5c53501b68 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.5 - Notification of intention to start work
label | 3bec74df-4adc-5323-8a8d-e27ad91d1a39 |  | note | VERIFICATION ACTIVITY - Notification
label | 8b2e642c-215a-55a6-a51c-dd24028405bc |  | note | FREQ. - Before work commences
label | 8f831e35-ecc7-5fe4-ac54-91dd936b1942 |  | note | ACCEPTANCE CRITERIA - Letter drop to local residents. Greater consultation where required
label | b7b5e76c-5000-5dc5-aa8a-84055ba34db6 |  | note | INSPECTORATE W/H: Type - H
label | 5586f246-b8d6-56ba-9858-62f2de4170f5 |  | note | INSPECTORATE W/H: Description - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | 0f2910f4-2b60-5190-aa0c-e84e220ec65e |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.6 - Works Extents
label | dd56d52e-2faa-561b-9fc0-ee87d438b761 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 20c5bef6-067d-524c-8ed5-5f5424df517c |  | note | METHODS OR REFERENCE - Site Visit
label | e9ed9236-1dc7-518a-834f-de2af0426140 |  | note | FREQ. - Before work commences
label | 9235abea-4984-567c-9d68-702c3bed9774 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and/or Client to agree extents of project
label | eecc37e4-33b1-53f1-8652-ca9317d631fe |  | note | INSPECTORATE W/H: Type - H
label | 80e610fa-db3b-5b41-8524-d7cc062ec139 |  | note | INSPECTORATE W/H: Description - Hold point - Walk over site with Renewals Engineer and/or Renewals Manager and/or NZTA
label | a6acc3b1-f14d-5579-92e5-65e84de33918 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.7 - Pavement Marking Records
label | d86bcb18-cf8d-52b4-b908-a01acad43f41 |  | note | VERIFICATION ACTIVITY - Measurment Data
label | 5223db5f-b964-5517-b4a7-198823b70e0d |  | note | METHODS OR REFERENCE - Site Measure or Video Viewer
label | 5723c033-7c79-5332-9f1d-e5619cb6b4c8 |  | note | FREQ. - Before work commences
label | 362fac42-8a09-527b-81d0-5d77234636cd |  | note | ACCEPTANCE CRITERIA - Measure existing markings to aid reinstatement
label | dfd0c7a1-eb0f-59b8-a837-58154d6f9a33 |  | note | INSPECTORATE W/H: Type - H
label | 0cad1cc2-70a8-5b5b-8b86-cb8099ff1c3d |  | note | INSPECTORATE W/H: Description - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | 6cea7b29-4fde-5d93-9c55-7783ec3830a7 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Milling and Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | d5c51c23-cfd9-5919-92bb-26eca807a10f |  | note | VERIFICATION ACTIVITY - Visual plan, BeforeUDig Cable locate (electronic or pothole for line & depth)
label | 815a04f6-b706-54ad-86db-b947eb458b30 |  | note | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | 32f32edd-a456-5b9a-8a20-a73cb1467fe4 |  | note | FREQ. - Before work commences
label | 98a98273-62c2-557a-9580-3711b964488c |  | note | ACCEPTANCE CRITERIA - Zero service strikes
label | 61ba68c3-4cdc-5eaf-9b2a-eac2a3f48c5d |  | note | INSPECTORATE W/H: Type - H
label | 79819669-9b86-562f-bb2a-030b5f8165be |  | note | INSPECTORATE W/H: Description - Hold point - No excavation/milling is to be commenced until services are located and accounted for
label | 18aa349a-b949-5336-8ae8-373885ded679 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.2 - Stormwater Management
label | 38287e11-5c71-5cbd-9e2b-617b48dadfff |  | note | VERIFICATION ACTIVITY - Visual check
label | bfc91b45-b7a1-53c1-9980-09066c362b0f |  | note | METHODS OR REFERENCE - On Site
label | b3f452dd-0bf3-53fd-94d8-bb5f73fb8a07 |  | note | FREQ. - Before work commences
label | 3dab06f9-f922-5810-bb73-1a66a80503ad |  | note | ACCEPTANCE CRITERIA - Mudtanks bunded or filtered to prevent mix from dropping in or runoff entering
label | 287328de-c183-521d-a926-ba1e215d7017 |  | note | INSPECTORATE W/H: Type - H
label | 84fbd7c4-94e8-55c8-9b9c-cb22e4f1206f |  | note | INSPECTORATE W/H: Description - Hold point - No work to be commenced until protections in place
label | c72bbde3-49b8-5dcc-ac1a-4f7c92f98354 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.3 - Traffic Management - Setup
label | 21475685-6bdc-5cbd-a0d2-964b927ec55f |  | note | VERIFICATION ACTIVITY - Visual check
label | f8743050-d270-54ca-8a26-e867b2d08361 |  | note | METHODS OR REFERENCE - Traffic Management Plan
label | 3ec89b4e-34db-5b61-b3a7-e33aeb339cad |  | note | FREQ. - Before work commences each day
label | 0e072c5c-bad0-52e2-b6a7-e59f755d0adb |  | note | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | cd52c0b7-c9d6-51e9-bc5d-8f3ab8482cfd |  | note | INSPECTORATE W/H: Type - H
label | f761c87c-03e3-5265-82a2-a0069f46af35 |  | note | INSPECTORATE W/H: Description - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | 664b80d6-9bc3-528b-b36f-00ccb3384f8d |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.4 - Milling Depths
label | b0361a68-49e6-5890-9779-06a71d729119 |  | note | VERIFICATION ACTIVITY - Measurement
label | 9aa0b9ba-8f61-5819-b582-b7599324b6e1 |  | note | METHODS OR REFERENCE - On Site
label | f04ba1af-3e86-5c82-9dc9-79e999ac8d4b |  | note | FREQ. - Measure each side of milling machine cut
label | 41aa7264-1ea6-548d-81d4-5355492fe7ef |  | note | ACCEPTANCE CRITERIA - Every 10m. Depth matches target
label | d8bda20e-fa9e-5d76-b594-5a4fd389f532 |  | note | INSPECTORATE W/H: Type - H
label | cf69db14-49a7-5262-b822-a244b5e8d9a9 |  | note | INSPECTORATE W/H: Description - Milling String Sheets or photos of depths taken and uploaded to CONQA
label | 46006d54-328e-53c0-aa82-7d7c8f02b157 |  | note | RESPONSIBLE PERSON - Site Foreperson / QA
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.5 - Service Covers Preparation
label | a999d51f-c0b7-515b-9336-268437af76d0 |  | note | VERIFICATION ACTIVITY - Visual
label | b37c9690-03a3-5922-a7f8-c20c553c9974 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 2f9e2ad8-cd3d-5482-b53d-b3431d84fa36 |  | note | FREQ. - All Covers
label | 0f237edc-eba4-5766-adeb-601859af9910 |  | note | ACCEPTANCE CRITERIA - Hand excavation around ironwork and adjustment to desired level (if required)
label | b3aaab05-7f31-5569-bc95-0d0cd8c2876c |  | note | INSPECTORATE W/H: Type - H
label | 30770e62-9bed-5be6-9bf9-528a9a1cce50 |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.6 - Additional Surfacing Preparation
label | d2f43623-e525-5042-ba3d-56b2f27ae846 |  | note | – Side Roads
label | 2a93cb85-7203-52a3-b474-21af15a5912f |  | note | – Accesses
label | 1271c9af-b3bf-5518-a040-986332704a59 |  | note | – Driveways
label | 53b6c98c-8fbb-59a7-8a5d-957b1f9875f4 |  | note | – Dish Channels
label | f3fedb6f-15b1-570b-ada0-7e197c23d067 |  | note | – High Shoulders
label | da468f70-efbe-529b-8860-cb98cc588b1a |  | note | VERIFICATION ACTIVITY - Visual Check
label | 118fe2b0-bca7-5a3e-bb0c-faf7d467b1ab |  | note | METHODS OR REFERENCE - Per Design
label | 9378cc4e-4439-50f1-9092-9417c2c53f63 |  | note | FREQ. - Before Membraning and Paving
label | 6c01a5a0-4f4a-52ef-aa91-cd5f202652ba |  | note | ACCEPTANCE CRITERIA - Have all areas of additional surfacing on the design been prepared, membraned and marked for paving?
label | 4d7c36bc-13d9-5527-8ff9-c592a8bc9b15 |  | note | INSPECTORATE W/H: Type - H
label | 529efbb2-6df8-513a-a4fd-d2e5cc1da823 |  | note | INSPECTORATE W/H: Description - Hold Point – All areas planned for AC are prepared ready for surfacing layer
label | 297514cc-6589-5316-98b6-e6e52adb70c5 |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.7 - Milling Surface inspection / walkover
label | 6376f81c-10f6-524c-ae81-1b5adac7ad4f |  | note | VERIFICATION ACTIVITY - Visual Check, proof roll with loaded truck to check deflections
label | 663dd6b9-81bf-5aeb-b537-a13adf41f15d |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 079893b5-e54d-5881-8611-291b16d3103f |  | note | FREQ. - Prior to surfacing
label | 2a34a4d1-bc8b-5b5a-bba3-d37cd5357d94 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree if any additional overmilling is required
label | 6d36d953-9852-5a28-9dab-5e80910c0f60 |  | note | INSPECTORATE W/H: Type - H
label | 1b2c5f52-3840-5c9b-8d2e-ad747397a3ef |  | note | INSPECTORATE W/H: Description - Hold point - Inspection and agreement by NZTA
label | eb62ad86-6d61-5063-91c3-d809ff209874 |  | note | RESPONSIBLE PERSON - Paving Supervisor / Paving Manager
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.8 - Over-Milling
label | adaef8db-13dc-5ec9-8e06-8ac7da2432a1 |  | note | VERIFICATION ACTIVITY - Measurement
label | 2109edb5-bcfd-50be-8ed9-efdd25fd517d |  | note | METHODS OR REFERENCE - On site measurements & photos
label | c288f2c5-19b0-5c28-89d4-9076f4ce9997 |  | note | FREQ. - Prior to pre-level
label | 0b1d8716-99ae-5ade-99be-211ecf29e2d5 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree need and extent of over-milling and infill.
label | f4061172-9d48-520f-9f03-dc66c95c89b5 |  | note | INSPECTORATE W/H: Type - H
label | 0293af5e-0fd2-56b0-9ef4-888b60374aba |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.9 - Pre-Level
label | 6d54a9f4-2c7f-554a-8568-95206718aedd |  | note | VERIFICATION ACTIVITY - Measurement
label | 17046adb-722e-5ce5-b60d-56acaad4cfb0 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 65ec33b6-20eb-5ed8-bfca-54976de7928a |  | note | FREQ. - Prior to surfacing
label | 8d4c665f-6491-556d-a9a6-d5384db41ab3 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree pre-level extents
label | f50e0b84-12d1-5036-a561-083fdadbdd12 |  | note | INSPECTORATE W/H: Type - H
label | a31bf24b-9d30-5259-a279-30ecf2bec567 |  | note | INSPECTORATE W/H: Description - Hold point - Inspection and agreement by NZTA
label | 768bbdda-b807-5754-b78f-d9b18229a3cd |  | note | RESPONSIBLE PERSON - Paving Supervisor / Paving Manager
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Paving Structural
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | 69f4bc6f-def2-5209-b2c1-3af0d82df93a |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | 0747837b-2f7d-570e-aef8-71f6e4b8d689 |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | f99a8515-f558-5a42-b1d4-3372b274d658 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | f1b74c6d-7a6a-5ca1-9ea9-e98481aee229 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 0e0acf18-e8cc-5ff3-b362-a52605e442b4 |  | note | INSPECTORATE W/H: Type - W
label | 67e394aa-abb5-5a7d-b03a-40bd669acc17 |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | d626eb19-2600-56d2-b30b-b5844b84659a |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | 19a0e553-bd66-52bb-8425-9d8e2b21317d |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | 7c50f37b-99e3-5dff-846d-2299578bf03d |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | 016c0680-ecf1-5202-a921-7f03b99d536d |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | d3f4f693-8bbc-5810-be30-d6dc31f5caaa |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 2dde50e7-9967-5ff0-a17c-3c12ff4f0914 |  | note | INSPECTORATE W/H: Type - W
label | 2ba8962e-dd12-5e77-801c-5f053e10222d |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | aa95514d-3f15-5e9b-ba6d-b28cb094ce9c |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | 22581381-e828-5c88-bda9-e475ecbf8783 |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | be27bea3-6b62-5bfd-b5fb-a80d834287ba |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | c967dfa0-0b0a-5f6d-bb82-053bcd549255 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | fa98eb15-dd86-556d-93c4-22225d290df2 |  | note | ACCEPTANCE CRITERIA - Per Mix design
label | 387a8190-f8cd-5c5a-84f3-efc9e82b31ce |  | note | INSPECTORATE W/H: Type - W
label | ab1bfb29-f94a-5c7d-9b75-f1ebd63fda3a |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | e991ba6a-c659-5e3e-9122-91f73f872592 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | 7ea56853-d2c1-5599-9972-dea3ab226106 |  | note | VERIFICATION ACTIVITY - Visual
label | 81729875-d2eb-5585-aad1-6cbdbac55626 |  | note | METHODS OR REFERENCE - NZTA M/10
label | ead4d9d7-454c-5865-a26f-37b35a9c382b |  | note | FREQ. - Prior to Shift
label | 1f8a10d5-7f4f-52fc-8a55-bc488970f939 |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | 6a781e7b-6a4e-5bdd-860e-c4d1b51c49f3 |  | note | INSPECTORATE W/H: Type - W
label | f00fb747-4f29-5bde-bd44-5b9af39b997f |  | note | INSPECTORATE W/H: Description - Paving Plan and Crew Briefing Plan completed prior
label | 532ca5fb-7f1f-50f1-80eb-726528e9f1f0 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | 4f95029d-4dfc-5735-892a-00983503d487 |  | note | VERIFICATION ACTIVITY - Visual
label | 0c544136-7934-557e-985b-d245fd0000a8 |  | note | METHODS OR REFERENCE - NZTA M/10
label | d72f632d-f07d-52ed-a606-edde7c54f302 |  | note | FREQ. - Prior to Shift
label | f58fe63d-9b4c-5236-94e4-ee9322dd5780 |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | 00395cdc-4876-5671-93d1-bb415bfe0c6e |  | note | INSPECTORATE W/H: Type - W
label | 9f157440-5fb8-592f-9a2c-268a2769f60b |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.4 - Mix Inconsistency and Deficiency
label | 0ed5591f-aa20-58a0-b56c-03e3e9b4dc1c |  | note | VERIFICATION ACTIVITY - Visual
label | 6bc413b5-9586-5ee7-bf8a-5e4b6ef413fe |  | note | METHODS OR REFERENCE - NZTA M/10
label | c9b660c9-f71c-563f-a01d-52d3e755922e |  | note | FREQ. - Continuous
label | 85bb2cdf-92c7-503f-8be9-d9fd141b7c29 |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | ca2ba431-fccf-5651-9dcb-d129efd74dfb |  | note | INSPECTORATE W/H: Type - H
label | db3385f8-ae02-5474-aff8-3a0a04182d28 |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3.5 - Load Locate
label | b8544120-b4a4-5542-9a35-8123ee8e165b |  | note | VERIFICATION ACTIVITY - Measurement
label | 40fb6522-58a4-508e-8f74-e4fb7b5774b4 |  | note | FREQ. - Every Load
label | 191355a4-bc1a-5d9b-ba02-3b55325bc595 |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes:
label | 35673af4-eeaf-5e37-a2c3-3f196c5ba00c |  | note | – Truck ID/Rego/Driver
label | 24b796b4-7429-5193-a8cb-6e845dac24f8 |  | note | – Depart Plant Time
label | 08de50ce-123d-5274-a92c-5da91daea844 |  | note | – Arrive Site Time
label | fbdb220a-4197-5b0d-bc84-3e46d2b77882 |  | note | – AC Temp on Arrival
label | 7f048e4b-7953-5d2b-866d-a494e16a1008 |  | note | – Ground Temp on Arrival
label | 02e903d4-558d-59d2-a88c-31ed45d81b75 |  | note | – Tonnage
label | 662fcd0e-4a72-5a36-a4c1-0a3e59018732 |  | note | – Run Width
label | 0f2d5514-0419-5ab2-b50a-064632541baf |  | note | – Estimated Run Length
label | facc5c7c-8870-5adf-b085-2eb0807b44dd |  | note | – Calculated Area
label | 67dc34c5-75e5-566d-890f-bfe9015ecc30 |  | note | – Calculated Average Depth
label | 133dcae5-34d4-5a8d-b00c-57afc3bdd828 |  | note | INSPECTORATE W/H: Type - W
label | c58ebab1-ba04-5fd1-bdf5-8d21dac6585b |  | note | INSPECTORATE W/H: Description - Per standard practice
label | 6153eae8-a945-5126-9305-f2049fdc0880 |  | note | RESPONSIBLE PERSON - Quality Assurance Engineer
checkpoint-status |  |  | checkpoint | 3.6 - Laying Temperature
label | e500a87c-4ff5-58e9-85f5-26b799222752 |  | note | VERIFICATION ACTIVITY - Confirmation
label | c0b2bbba-d28a-5d02-9f24-89e9e3d06b73 |  | note | METHODS OR REFERENCE - NZTA M/10
label | d29da16e-0324-5d6b-9984-68e1e09522b0 |  | note | FREQ. - Every Load
label | 1c01c23b-bf88-532a-94be-103095440da0 |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | 298d986d-5287-5735-86ac-e0228cd04d7d |  | note | INSPECTORATE W/H: Type - H
label | bbea2cc6-76b2-52a3-8626-ec79e559b41c |  | note | INSPECTORATE W/H: Description - Hold point - Reject mix for non- compliant temperatures.
label | 54f856f5-fc09-5281-89b8-2b47d7a79c67 |  | note | RESPONSIBLE PERSON - Quality Assurance Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3.7 - Compaction
label | 50aaee2f-35ba-5a9d-95f2-ed1e9519bd37 |  | note | VERIFICATION ACTIVITY - NDM Testing
label | 07e216bc-61cb-5ba2-b8ce-59f912c68dc4 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 76ee459c-412a-53f0-8db8-162d88eb2a11 |  | note | FREQ. - Minimum:
label | c371b213-30d3-5f4f-93bd-618bcc8baff0 |  | note | ○ 1 Test per 300m² within Mat.
label | c8a7866c-a20e-592d-b5a6-03adefe83d73 |  | note | ○ 1 Test per 100m of joint.
label | 2356d8c6-b3c8-5f8c-a1bf-e63752128ad2 |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | 2edea9a2-e0c3-57ba-8ac6-4a44b69ea24b |  | note | INSPECTORATE W/H: Type - H
label | 4965438f-84ab-587e-824e-325209c670da |  | note | INSPECTORATE W/H: Description - Hold Point - No Wearing course paved until any non-compliance is sorted. PQI / Core recorded with RP, lane, offset, date, air voids. Core results received within 2 weeks.
label | 98900161-1c19-5a56-aaf7-08078f0123c3 |  | note | RESPONSIBLE PERSON - Quality Assurance Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Paving Wearing Course
checkpoint-status |  |  | checkpoint | 4.1 - Production Properties - PSD (Particle Size Distribution)
label | 0a0db51c-8fff-5461-903d-4882a668d17c |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | 8ddef4dc-59c7-5ff1-8d75-eedfa50582a4 |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | 285ac6a7-1df1-54ee-abd5-d9b7ff224b87 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | ac0d6138-736d-534f-99ef-125e0040ba08 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 0c4cb756-2d41-5507-b25b-e25de9b65259 |  | note | INSPECTORATE W/H: Type - W
label | 9efe6e47-e59b-598c-bd8d-decc19fae7f8 |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | ac49716f-78c5-5a58-950a-4098fbdda801 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.1 - Production Properties - Binder Content
label | 8c137a7c-92b6-54f9-8f45-ebf4991105cf |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | 1971895b-dfe9-58f9-894d-eeb901027a55 |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | d906da4f-29fd-5dd6-b98b-f54c8b3b6f70 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 7f2e5180-3993-54ff-96c6-ac26865b3f1a |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 739d749f-33b1-5a64-b761-d74c8976e795 |  | note | INSPECTORATE W/H: Type - W
label | 9c12b9d9-6c09-5f8b-98c3-08c9fcb51e3d |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | 172064bb-6b03-5a82-a27b-2481b077ac2e |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.1 - Production Properties - Maximum Specific Gravity
label | e49ef7a1-d63f-5dad-b360-77890a51d937 |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | 3549853a-094e-5be1-af51-414ac3c24306 |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | a8aaacce-f077-59f9-8380-5e1db7ca6bac |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | ea86c47b-515f-572b-a886-ab9f3a2633e9 |  | note | ACCEPTANCE CRITERIA - Per Mix design
label | 42806d4d-c54c-5076-a2c0-b9ebef3de941 |  | note | INSPECTORATE W/H: Type - W
label | 9cf0b3b6-9b0c-5e95-bb2c-a0461279dd61 |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | df1674dc-ccaf-5254-8efa-9c409dd1b0e2 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.2 - Preparation
label | 2e0260b3-0b04-586c-b7d1-606f38d4c0c5 |  | note | VERIFICATION ACTIVITY - Visual
label | 30abf6e6-b3d9-5a27-9bae-4048555efdc4 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 95d77c1a-a4aa-55b0-9dc9-137193918f31 |  | note | FREQ. - Prior to Shift
label | 45b15a9b-c6aa-5322-bb1b-a17ee6b77cea |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | 3b962539-e39a-56a5-8118-2e58f748cd68 |  | note | INSPECTORATE W/H: Type - W
label | d99d875b-6acd-529a-b00e-ca1ae878b763 |  | note | INSPECTORATE W/H: Description - Paving Plan and Crew Briefing Plan completed prior
label | d43984ac-246d-531a-83a7-9c13e27762c1 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.3 - Joins
label | 0a6bbced-3c1b-53e4-96af-6fa4377cb8a1 |  | note | VERIFICATION ACTIVITY - Visual
label | 8390819e-8cd6-5b84-bef3-2a3963dc0cce |  | note | METHODS OR REFERENCE - NZTA M/10
label | ae7da918-e0fc-52fe-bf9a-670caa43d554 |  | note | FREQ. - Prior to Shift
label | 8b02d216-834b-5429-a9e5-0c72e21cbab7 |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | 34fbd0d7-544b-57c8-b88a-860847d366f3 |  | note | INSPECTORATE W/H: Type - W
label | 2d2d7810-e98e-5c1a-8054-8067f824eb65 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.4 - Membrane Sealing
label | 063df287-0c81-5ee9-9095-06fa2e7dcc64 |  | note | VERIFICATION ACTIVITY - Visual
label | cbb357fe-c286-550c-bc88-8f58c34fd845 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 5658e232-3e0e-5f8a-815b-92c637ca008e |  | note | FREQ. - Prior to Paving
label | 1f5aeb48-95e7-500e-953e-7c60b5ea32ea |  | note | ACCEPTANCE CRITERIA - Membrane seal meets design and extent. Sealing Docket record kept
label | ba63771a-3a31-560f-bee3-1d9cf0e91491 |  | note | INSPECTORATE W/H: Type - H
label | 3157a62d-a90e-5264-a913-a288595e6739 |  | note | INSPECTORATE W/H: Description - Hold Point - No paving until Membrane Done. Ensure correct application of chip & emulsion
label | 2e5b252e-376e-5473-844b-f68f223a13d5 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.5 - Mix Inconsistency and Deficiency
label | 386a88c8-5c09-5efc-9499-ebbe7b341376 |  | note | VERIFICATION ACTIVITY - Visual
label | 8466c8e3-de09-5e5c-95fe-2aa9e380d47d |  | note | METHODS OR REFERENCE - NZTA M/10
label | 48f3ae39-d905-500e-8829-f568fc27ff47 |  | note | FREQ. - Continuous
label | 591f32f0-ed5f-5ccd-8683-a1925aacfb44 |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | 0714c9a7-9c14-53de-b63a-8d202857312a |  | note | INSPECTORATE W/H: Type - H
label | 814bd1a2-0265-5e2c-abd6-4828db39bcf3 |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.6 - Load Locate
label | 66253566-a54a-59ba-965a-08ba21c45064 |  | note | VERIFICATION ACTIVITY - Measurement
label | 78466778-2e55-5182-849f-eec238104b3d |  | note | FREQ. - Every Load
label | 3d9f8c2f-ba33-533f-a08e-3fac5d37d5ba |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes:
label | d846866c-f657-5960-8675-7f174b5c098b |  | note | – Truck ID/Rego/Driver
label | 43eb61ad-c0f4-5a8f-b9be-ae5c5fec9489 |  | note | – Depart Plant Time
label | 1549ddeb-6520-597b-80c0-edad1fc495ea |  | note | – Arrive Site Time
label | 90d53889-cfa2-5411-a2b1-00f44019a284 |  | note | – AC Temp on Arrival
label | e9d6d0d8-93ca-50a0-b834-b9484675e275 |  | note | – Ground Temp on Arrival
label | b68a3bd7-6467-51f4-a78c-bed51b546bab |  | note | – Tonnage
label | 09e26c04-ff2a-5a6e-9a23-b0a612fc03ef |  | note | – Run Width
label | 0caf0ff2-0d92-5eec-8f93-9aa8eb83b829 |  | note | – Estimated Run Length
label | 1cfdd326-d1f2-5727-9c78-fbf659c2253d |  | note | – Calculated Area
label | b0ad0780-ea9f-54bb-b5d1-ab26a64b9543 |  | note | – Calculated Average Depth
label | 0b226841-60f4-5c3e-b08a-d08beac28da5 |  | note | INSPECTORATE W/H: Type - W
label | d23c0a96-0cbd-5e2d-9d81-1d47d5819d08 |  | note | INSPECTORATE W/H: Description - Per standard practice
label | 31585b75-c1f8-52b5-b7b0-241c4c491b4b |  | note | RESPONSIBLE PERSON - Quality Assurance Technician.
checkpoint-status |  |  | checkpoint | 4.7 - Laying Temperature
label | 8d5801b3-140e-50a0-9cbc-687579889866 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 960612a4-9dac-5de7-b22f-f90f81a5b22b |  | note | METHODS OR REFERENCE - NZTA M/10
label | fd2d956e-b01d-5147-8fb2-7caf4d3b9984 |  | note | FREQ. - Every Load
label | 6306a510-94f8-5c1a-acb5-cff5dfa98e6e |  | note | ACCEPTANCE CRITERIA - Based on Mix design
label | 841e7b64-c5a5-50a0-a147-75409c1f92ca |  | note | INSPECTORATE W/H: Type - H
label | 65dbe647-2215-558d-99ce-a9a1a2caf76a |  | note | INSPECTORATE W/H: Description - Hold point - Reject mix for non- compliant temperatures.
label | 59c2607c-fb21-5a3a-9b3d-7e4cfa4f3598 |  | note | RESPONSIBLE PERSON - Quality Assurance Technician
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.8 - Compaction
label | ff0e2bdb-52b0-5b31-a60a-fa207c6c234d |  | note | VERIFICATION ACTIVITY - PQI Non-Nuclear Gauge/Cores. Or Non Distrctive Method Testing.
label | bfba5abc-fe37-5782-99de-ce547dbe953b |  | note | METHODS OR REFERENCE - NZTA M/10
label | 08f97b90-9448-5c29-b1d7-def6feb436b3 |  | note | FREQ. - As per Agreed on Contract.
label | 74061c59-c1be-54e6-a60a-1ddc80b3d6d2 |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | b4e9cadc-9788-5d4e-9aec-0359c219a4d4 |  | note | INSPECTORATE W/H: Type - W
label | 101aee00-811f-5368-88aa-cbf76e3f8cd6 |  | note | INSPECTORATE W/H: Description - PQI / Core recorded with RP, lane, offset, date, air voids. Core results received within 2 weeks.
label | 17b20e66-d959-5645-92f7-62cd4be43749 |  | note | RESPONSIBLE PERSON - Quality Assurance Technician / Paving Manager
checkpoint-status |  |  | checkpoint | 4.9 - Roughness
label | 486c1498-b341-5155-b210-2e04e320c9d9 |  | note | VERIFICATION ACTIVITY - Visual
label | daf235ea-e8f8-5df6-9b32-e9eabc438f4b |  | note | METHODS OR REFERENCE - On Site
label | 46a52542-3adc-5665-b228-9a4a637029b9 |  | note | FREQ. - Post Construction
label | bd0b0d94-d490-5741-9661-8e23b0595a15 |  | note | ACCEPTANCE CRITERIA - Agreement with WK as per M10
label | 89de00bc-7296-52e2-9f7a-88ff16d1d5b5 |  | note | INSPECTORATE W/H: Type - H
label | 9529af52-ced1-5927-b0a1-35b487c61174 |  | note | INSPECTORATE W/H: Description - Site walkover with client to determine ability to comply with straight edge measurement outlined in M10
label | e1889ec8-9dce-5070-a146-550843f33257 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Site Reinstatement / Clearance
checkpoint-status |  |  | checkpoint | 5.1 - Post-seal Area Check
label | 5147246d-0620-5740-9fbe-83ab80105558 |  | note | VERIFICATION ACTIVITY - Measurement
label | 2b63297d-7eed-5258-a4a9-27d4323acc58 |  | note | METHODS OR REFERENCE - On Site tape- measure
label | d3ada050-00e4-5b68-8467-47627ae529bc |  | note | FREQ. - After Surfacing
label | 7aed677a-167f-525b-b3fb-d6cf49f31710 |  | note | ACCEPTANCE CRITERIA - Check sealed area meets design
label | d216bd08-e36c-5712-ba0f-3e3b97052eae |  | note | INSPECTORATE W/H: Type - W
label | 2e129182-d022-52c9-a7e5-20db66a9bdad |  | note | INSPECTORATE W/H: Description - Notify Renewals Engineer or Renewals Manager
label | 14bdc04e-44b1-5c93-be90-df355aa35e3c |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.2 - Service Covers
label | 8ed84b82-3770-51c3-b4cf-ab4b4ada9673 |  | note | VERIFICATION ACTIVITY - Measurement/Visual
label | 15f55554-ddd2-58cb-829c-90588cdd66dd |  | note | METHODS OR REFERENCE - On Site
label | 6415564d-b731-5e9b-8218-ab31478df685 |  | note | FREQ. - After Surfacing
label | 825d8f48-c613-5153-a831-1722f62e2aed |  | note | ACCEPTANCE CRITERIA - All service covers are checked and adjusted (if necessary) to finished level (+10mm, -0mm)
label | 7bb20c51-a8a2-5804-8fc5-b98ca69f085c |  | note | INSPECTORATE W/H: Type - W
label | f7781555-db59-5f63-b1d8-1a4f301b3135 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.3 - Joint Sealing
label | cb25d1a4-590d-5cd5-b9db-d402e300963d |  | note | VERIFICATION ACTIVITY - Joint Sealing
label | a9f3e732-cb2a-5ee1-b0a3-8682309f8781 |  | note | METHODS OR REFERENCE - On Site
label | 8e24221f-57d5-533d-86a2-dcc3f7ef09c2 |  | note | FREQ. - After Surfacing
label | bf8b2874-b12b-5cb7-b76b-952741216475 |  | note | ACCEPTANCE CRITERIA - Check cold joints are bandage sealed
label | 4e3bb8e3-63a1-5c66-99c6-0fff2e868b24 |  | note | INSPECTORATE W/H: Type - W
label | 883bf626-3749-5645-ad0d-c4bb5bb444d4 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.4 - Road Marking
label | d283ca07-d879-5e9a-a3b2-d563af7483d7 |  | note | VERIFICATION ACTIVITY - MOTSAM
label | b0325928-9c21-5d75-a31a-5439d342d7b9 |  | note | METHODS OR REFERENCE - Visual inspection
label | bc28d0d6-9ef5-5f03-b075-62b6df748ebe |  | note | FREQ. - All markings
label | e11e21a8-322a-53c8-ad77-c9708b4c75a7 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, or per design
label | f131ee34-27c2-500c-a1cf-c641e0c9b791 |  | note | INSPECTORATE W/H: Type - H
label | 6c9ecd49-7eec-5757-8af1-515d828cd4ff |  | note | INSPECTORATE W/H: Description - Hold point – Site TTM cannot be removed until markings reinstated
label | 2b886f89-8d6f-563f-b9d1-88f078b36cbb |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.5 - Other Traffic Services - Marker pegs/ Signs/Markings/RRP Ms Replaced
label | 82180400-828c-5a0b-9d28-8f6ec314389a |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | b43eee77-a4cd-507a-b5b6-ea68d6a33cd8 |  | note | METHODS OR REFERENCE - Visual inspection
label | 758d1afe-1495-5a1a-baf3-d35ecc3f7c22 |  | note | FREQ. - All signs/markers
label | 9c3aac94-ce9b-5784-a499-9e618ed3c48f |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | eec78353-dfb1-5b35-9d45-00056fc895f5 |  | note | INSPECTORATE W/H: Type - H
label | fc70484c-0ad3-5255-a7c8-ca223fe965ea |  | note | INSPECTORATE W/H: Description - Hold point – Site TTM cannot be removed until marker pegs, signs, markings and RRPMs reinstated
label | b3d227a6-2e1a-536a-bc03-810bf22a31ef |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.6 - Stormwater Management Controls removed
label | 8239ffb8-15d6-5266-80e4-5bfb626b28a8 |  | note | VERIFICATION ACTIVITY - Visual check
label | ed29ade8-6c92-5677-a48e-cd9488d4ed5f |  | note | FREQ. - All installed measures
label | bd3719dc-d473-5500-aab6-0820b060836b |  | note | ACCEPTANCE CRITERIA - Installed controls are removed
label | 51b05401-9ca5-5b7a-8599-f015e3c68e06 |  | note | INSPECTORATE W/H: Type - H
label | ee235a1b-a4d7-5541-9cdb-8c5204c28420 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.7 - Traffic Management Removed
label | fba25754-3395-5db0-9c0c-3449bb757c88 |  | note | VERIFICATION ACTIVITY - Visual check
label | d5c5c114-6c1c-5181-aa8c-77637448b94a |  | note | FREQ. - When safe, after all physical works completed
label | a9ce1cc3-81c4-5016-835e-7fd8d8ed2cc3 |  | note | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | e77d1e0a-4f40-5720-831c-e0eb75fae4fd |  | note | INSPECTORATE W/H: Type - W
label | f32ccb81-c149-5d49-a5fe-f487c7069528 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.8 - Site left clean & tidy
label | dd7d7dc8-b789-5870-a2b9-e17e2943fdf0 |  | note | VERIFICATION ACTIVITY - Visual check
label | dfbfceec-5dbf-5689-b3f1-f9c690be1dbe |  | note | FREQ. - After vacating site
label | 6f8b471b-37eb-55f3-b2e0-fbd18d1be9bb |  | note | ACCEPTANCE CRITERIA - Stockpiles removed, Plant removed, Litter cleared from site
label | 5739db1a-348d-54ba-88f6-3b86800be2bf |  | note | INSPECTORATE W/H: Type - W
label | f9d68f52-22bf-5ca8-8e45-504c78ebd0f5 |  | note | INSPECTORATE W/H: Description - Invite NZTA to carry out joint site inspection to inspect site.
label | 3c7a3c3a-95a9-5e2c-9cec-56fb9af6b5b9 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-group |  |  | section | As Built Records
checkpoint-status |  |  | checkpoint | 6.1 - Collect asset data
label | 87086c87-b05f-56e0-9ed4-cf6794dbc991 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | a7a0ad11-3671-539f-83c5-d987568187c6 |  | note | FREQ. - During construction
label | 5862379b-d8fa-5927-b90c-03f6ba4acb84 |  | note | ACCEPTANCE CRITERIA - All relevant as built information collected.
label | feacea24-7b23-574a-8f45-543eb62ed852 |  | note | INSPECTORATE W/H: Type - W
label | 06fbf655-85d2-5f1a-81b8-43e6bcde499c |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 6.2 - Enter asset data into RAMM and/or register(s)
label | d58d5624-43ca-503e-9421-f580b70bdec2 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | 7ec70eff-6507-5314-bdca-1d48cc9a00bf |  | note | METHODS OR REFERENCE - RAMM
label | d9d62ca4-a082-58d2-8659-7e1a4a91969f |  | note | FREQ. - At completion of work.
label | bf44efa0-749a-5ce2-8f5c-0d48f571f4dd |  | note | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.
label | d8a22ede-2bc3-5527-bb61-473a33f9b037 |  | note | INSPECTORATE W/H: Type - W
label | 98e41734-75b2-51ad-a73d-64040deba9d3 |  | note | INSPECTORATE W/H: Description - Data entered by 20th of follow month after month of completion
label | f3ec9012-c2b9-5f24-be6d-2d23b5c70106 |  | note | RESPONSIBLE PERSON - Asset Information Manager
checkpoint-status |  |  | checkpoint | 6.3 - Construction Completion Report
label | 24841594-0f1a-5db6-92a1-779d70323c1a |  | note | VERIFICATION ACTIVITY - Confirmation
label | a2afa2b3-416f-56c0-add5-03ffc8f7eda0 |  | note | METHODS OR REFERENCE - Contract Specification
label | 07d6fdc2-bd0a-5ae6-ad86-b224ad9c5cc5 |  | note | FREQ. - At completion of work.
label | 578f72a4-3e85-515a-988d-debe046f7eaa |  | note | ACCEPTANCE CRITERIA - Checked and approved
label | 0b5dca03-e912-54e0-ae52-8a953293ec8b |  | note | INSPECTORATE W/H: Type - W
label | 843c0d9b-e950-5a1f-a4fc-db8e5577088b |  | note | INSPECTORATE W/H: Description - Completed within two months after Paving Wearing Course
label | 088b336d-b253-549d-bb4b-460d4c919c1c |  | note | RESPONSIBLE PERSON - Renewals Engineer/ Renewals Manager
checkpoint-status |  |  | checkpoint | Quality Assurance Close Out by:
text | 5c0ea1e1-3405-5621-bfd5-adc2e5af391c |  | textbox | (name):
date | 524655cb-0111-577e-b880-51846a673468 |  | date | Date:
label | 71cbe8f1-03cb-51eb-804b-01d20c9054ae |  | note | This record to contract file.
holdpoint |  |  | signoff | (signature)
checklist-sectioned |  |  | checklist | SNOC ITP Thornbury Intersection - 670586 ITP v1.1 | itp |  |  |  | Yes | SNOC ITP Thornbury Intersection - 670586 ITP v1.1 | 33b15793-587b-4d25-a6e7-59764fda61ee
checkpoint-group |  |  | section | Preliminary and General
checkpoint-status |  |  | checkpoint | 1.1 - Construction Programme Completion
label | f435f99b-a5a0-5c65-83c5-55c8285757f7 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 4156e29a-e520-5693-981e-46a307a8c861 |  | note | METHODS OR REFERENCE - Best Practice Contract Specific MMP
label | 70bf68d4-8357-5dc9-85a2-32f9f3ff6768 |  | note | FREQ. - Before work commences
label | 3d6e48b4-cab8-58aa-a6c6-6e9b77dd2f5b |  | note | ACCEPTANCE CRITERIA - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date.
label | 5acc8165-8137-55ab-894a-3e7c6615f309 |  | note | INSPECTORATE W/H: Type - W
label | 276e1a32-0a7c-525a-9418-ce590855da06 |  | note | RESPONSIBLE PERSON - Renewals Manager
checkpoint-status |  |  | checkpoint | 1.2 - Approved RQP
label | ea7f7823-5a5f-5c21-96a3-7b909ec20f48 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 8a197931-7b27-51a6-9a67-1d7266c9e9aa |  | note | METHODS OR REFERENCE - Contract Specification
label | 97da19af-063b-552b-94d4-b6e7a675baa9 |  | note | FREQ. - Before work commences
label | 0340ea05-ffe7-5d61-b865-7e3eb1ad0533 |  | note | ACCEPTANCE CRITERIA - Principal Acceptance according to guidelines in appendix 6.3
label | cf5f9579-9e3a-5d03-84aa-c9611e632dc0 |  | note | INSPECTORATE W/H: Type - H
label | d984220a-dcd8-5e33-adbd-064a74aaf07c |  | note | INSPECTORATE W/H: Description - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. NZTA to approve
label | 1e5a1b2b-1f1c-5de3-9631-06ed704b0c30 |  | note | RESPONSIBLE PERSON - Renewals Manager
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3 - Traffic Management - TMP
label | 831967b7-1e2e-5dac-a463-e1bf553d8a97 |  | note | VERIFICATION ACTIVITY - Visual check
label | 544cdbf9-e442-5e33-bc26-6aba5edba857 |  | note | METHODS OR REFERENCE - CoPTTM
label | ae00baa3-b381-5a4d-af3b-f038d54b7b3f |  | note | FREQ. - Before traffic management set up
label | 40b5de9c-0ba6-5edd-b77e-3cf46760dcaf |  | note | ACCEPTANCE CRITERIA - TMP checked and approved Plans approved, Current EED (if applicable)
label | 8e866e13-14d5-57da-8bee-9c76826b86c1 |  | note | INSPECTORATE W/H: Type - H
label | ce4e2383-4e74-59a8-847c-f7f7fcaf25d6 |  | note | INSPECTORATE W/H: Description - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | e846a03f-2702-501f-af68-a2ef1a40b826 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.4 - Mix Design Verification for all mixes Check Laydown Trials are complete and compliant
label | 108702f2-39ee-5d2c-9a5b-0d383e1cb2c4 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 32a0d2ca-7283-5118-8971-c26b35d655d9 |  | note | METHODS OR REFERENCE - NZTA M/10, P/11, P23
label | 73ee78ed-1164-5ec5-99b5-851c483e459c |  | note | FREQ. - Before planning commences
label | ad571699-dfe5-5d6a-9cd6-207335212b49 |  | note | ACCEPTANCE CRITERIA - Mix Design compliant, current and relevant. Batching plant production capability is confirmed
label | d0bdb6b0-22e5-5dd4-aee2-c29b7b589426 |  | note | INSPECTORATE W/H: Type - H
label | 8382b03b-67cd-53ff-89d5-46c40ae296df |  | note | INSPECTORATE W/H: Description - Hold point - No planning of on-site works shall commenced until the mix design is verified.
label | d5533614-4957-51d9-9269-e17265e1a719 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.5 - Notification of intention to start work
label | bb48b40d-84cc-5d9a-8a9e-bf8e4164c050 |  | note | VERIFICATION ACTIVITY - Notification
label | 99001bbd-d20b-5211-ae2b-f12896f51811 |  | note | FREQ. - Before work commences
label | 95e57ea6-756d-5c9f-aef3-28dc9cf12946 |  | note | ACCEPTANCE CRITERIA - Letter drop to local residents. Greater consultation where required
label | 2286f745-6086-54f0-8187-124bb1bda8bd |  | note | INSPECTORATE W/H: Type - H
label | 12b469bd-ff7c-5fab-bd5a-98d0e9744836 |  | note | INSPECTORATE W/H: Description - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | f3204e3c-ca63-5b03-8a23-67ea91c27cb4 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.6 - Works Extents
label | 11d258ea-dd4b-57db-a4e1-a9d21182c07c |  | note | VERIFICATION ACTIVITY - Confirmation
label | cefa0720-4986-57b6-9105-b9fa6e02210b |  | note | METHODS OR REFERENCE - Site Visit
label | 45d5f69a-e35f-5e20-99a3-4924e76ff9e0 |  | note | FREQ. - Before work commences
label | 0b284c3e-5b22-5769-8a88-b14584ddaf50 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and/or Client to agree extents of project
label | 8bb6d985-57ef-5a54-b62e-3c0ea8fd4ab1 |  | note | INSPECTORATE W/H: Type - H
label | 27470930-ba00-59f9-8973-833becaacb52 |  | note | INSPECTORATE W/H: Description - Hold point - Walk over site with Renewals Engineer and/or Renewals Manager and/or NZTA
label | b39f4581-23d7-52a7-aceb-047589a9c71d |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.7 - Pavement Marking Records
label | b868c0da-61e6-53ff-858b-c17f8a550e12 |  | note | VERIFICATION ACTIVITY - Measurement Data
label | a6931a1b-fd38-5aa6-b108-1e547955a409 |  | note | METHODS OR REFERENCE - Site Measure or Video Viewer
label | 824c5942-9fd4-50f6-a454-bb8e90c7ed28 |  | note | FREQ. - Before work commences
label | 76376983-cfe1-5bb5-9354-e9c960abc01f |  | note | ACCEPTANCE CRITERIA - Measure existing markings to aid reinstatement
label | feea0311-c59d-5aa6-9400-e423bb403672 |  | note | INSPECTORATE W/H: Type - H
label | 4623666e-3b96-5955-aa50-78947e2578b0 |  | note | INSPECTORATE W/H: Description - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | f461bcbd-bf4d-507d-bf72-c58b5219373d |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Milling and Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | 97def897-59c4-5510-808a-d0406d8bd7e8 |  | note | VERIFICATION ACTIVITY - Visual plan, BeforeUDig Cable locate (electronic or pothole for line & depth)
label | 42291649-9c89-5d05-8031-669235b7332f |  | note | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | 0f212265-6d4c-588c-a25a-c9ab629419f5 |  | note | FREQ. - Before work commences
label | 893a65ef-be51-5ee8-aadf-d527c4fa0864 |  | note | ACCEPTANCE CRITERIA - Zero service strikes
label | c8b63af0-dcef-56ff-b986-903e6029e36d |  | note | INSPECTORATE W/H: Type - H
label | 392e1ed4-bd0a-540b-a30a-e27ca471249a |  | note | INSPECTORATE W/H: Description - Hold point - No excavation/milling is to be commenced until services are located and accounted for
label | d2419388-43b8-5844-9a89-b9891be3a954 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.2 - Stormwater Management
label | 5993ee1c-ae82-55d4-a616-6da82927800a |  | note | VERIFICATION ACTIVITY - Visual check
label | a36d5231-0f6a-542d-a5b2-ef6b00ae37d3 |  | note | METHODS OR REFERENCE - On Site
label | fc65a841-a3ee-5acc-b72f-0a9681163265 |  | note | FREQ. - Before work commences
label | 09dcaae4-99b0-5e3d-a36b-95d0ff579394 |  | note | ACCEPTANCE CRITERIA - Mudtanks bunded or filtered to prevent mix from dropping in or runoff entering
label | 2e9912c1-31bc-5282-af1f-9dc0abaacd0d |  | note | INSPECTORATE W/H: Type - H
label | 0845a0ed-0d29-5406-b450-9ed4c56874e1 |  | note | INSPECTORATE W/H: Description - Hold point - No work to be commenced until protections in place
label | 3a240d8a-ecbe-528c-a76a-b051e432689d |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.3 - Traffic Management - Setup
label | 185ba055-1666-5526-a090-162621b9e56a |  | note | VERIFICATION ACTIVITY - Visual check
label | 032d6c1f-5f72-5f4c-85c3-24c714d4e28e |  | note | METHODS OR REFERENCE - Traffic Management Plan
label | 48c13439-228d-5c8e-bf06-960aa3da63ae |  | note | FREQ. - Before work commences each day
label | db38981f-1b23-57bd-a2c7-852933a8271b |  | note | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | 84635a39-66f2-50ed-b58e-cddf73ef0bce |  | note | INSPECTORATE W/H: Type - H
label | dcf3707d-dca8-5021-a367-a79f1786f39c |  | note | INSPECTORATE W/H: Description - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | cfaa70d7-79a0-5fa5-9cba-9a950b8952a2 |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.4 - Milling Depths
label | 5d43e8c4-fe42-5108-a517-a0f99ca67796 |  | note | VERIFICATION ACTIVITY - Measurement
label | 44ed6840-e0d2-51cd-9690-ae12d429f8a0 |  | note | METHODS OR REFERENCE - On Site
label | 1cfb5f58-f883-5256-b2ed-21385d6d79f9 |  | note | FREQ. - Measure each side of milling machine cut
label | 8e839029-2ada-58ec-bfb3-49130a3e0d2f |  | note | ACCEPTANCE CRITERIA - Every 10m. Depth matches target
label | 1d145420-8b20-536c-9469-386f31f75d2e |  | note | INSPECTORATE W/H: Type - H
label | 6ee00829-a609-5030-ab51-6dc152dab9b8 |  | note | INSPECTORATE W/H: Description - Milling String Sheets or photos of depths taken and uploaded to CONQA
label | 44dee61e-0413-5c9a-a386-dd3451161f8a |  | note | RESPONSIBLE PERSON - Site Foreperson / QA
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.5 - Service Covers Preparation
label | 5a956a65-775c-5f8f-9186-7176596317cc |  | note | VERIFICATION ACTIVITY - Visual
label | d8e45bd9-c7d0-545f-9a2f-6ce1b8697b30 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | dcc5417d-1666-5742-8923-1c2dad57b5c0 |  | note | FREQ. - All Covers
label | e3034998-5944-5c3f-9220-54701b45cf89 |  | note | ACCEPTANCE CRITERIA - Hand excavation around ironwork and adjustment to desired level (if required)
label | 95f8f755-8629-5b55-b861-ec74a3e08c76 |  | note | INSPECTORATE W/H: Type - H
label | 45a4c86a-39eb-592e-a4e7-ce034e24d087 |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.6 - Additional Surfacing Preparation
label | 843131b9-cd39-5415-a778-09666ce54fd6 |  | note | – Side Roads
label | 921c2174-e852-5136-b017-fa17e275c50f |  | note | – Accesses
label | 88c0d717-9966-54ea-8b3e-589378d2947a |  | note | – Driveways
label | 1e75745a-7e2f-5635-ba98-eb10721bb64f |  | note | – Dish Channels
label | 0491d1f9-6dcf-55a1-a1fa-8360d21674f5 |  | note | – High Shoulders
label | 8484f729-2070-5b0c-9fb9-bdb630922ac3 |  | note | VERIFICATION ACTIVITY - Visual Check
label | da252925-6adc-588a-90a5-5688a3ebf215 |  | note | METHODS OR REFERENCE - Per Design
label | e6d20cc3-3058-504f-917c-170d1b336074 |  | note | FREQ. - Before Membraning and Paving
label | 1a55523b-32fa-524d-bd52-7871296769da |  | note | ACCEPTANCE CRITERIA - Have all areas of additional surfacing on the design been prepared, membraned and marked for paving?
label | c4a3b719-008b-5b50-8e92-99b737fdecd3 |  | note | INSPECTORATE W/H: Type - H
label | 14105d1e-b2f9-5b4d-871d-18ea06d47fb9 |  | note | INSPECTORATE W/H: Description - Hold Point – All areas planned for AC are prepared ready for surfacing layer
label | 0571fd64-3e89-5cf4-b25a-727953e6bd7d |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.7 - Milling Surface inspection / walkover
label | dbf6961c-f4e3-5398-984a-94703f552603 |  | note | VERIFICATION ACTIVITY - Visual Check, proof roll with loaded truck to check deflections
label | 2b4ff827-039a-5008-8b83-f2ac495aac59 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 27358c31-5864-5fb3-b466-6b811cf0648f |  | note | FREQ. - Prior to surfacing
label | b2beaeca-a176-54ee-aeb2-5185ecfc6797 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree if any additional overmilling is required
label | b7abed6d-cc77-544f-81a8-e59fafcf6f12 |  | note | INSPECTORATE W/H: Type - H
label | 406b2bec-b7e1-5be2-9115-82914e92fab5 |  | note | INSPECTORATE W/H: Description - Hold point - Inspection and agreement by NZTA
label | 856dde0a-9cfa-5022-b24d-c08aa640c630 |  | note | RESPONSIBLE PERSON - Paving Supervisor / Paving Manager
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.8 - Over-Milling
label | 7ec00392-9474-5f71-af53-bac12e9d2911 |  | note | VERIFICATION ACTIVITY - Measurement
label | 80f6da8c-fec9-5253-8b55-100800c71de5 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 71276323-f1fe-57cf-99e9-aa61231cfa62 |  | note | FREQ. - Prior to pre-level
label | 7cf442fa-a4d4-5f3d-b7da-2e1725bf6c1a |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree need and extent of over-milling and infill.
label | afbb4bd6-853a-5285-8b5f-b286faf9a426 |  | note | INSPECTORATE W/H: Type - H
label | 933d51b5-a1d8-59c2-8cba-bb006798bf6c |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.9 - Pre-Level
label | b9e22a88-f7d9-59a4-a9b6-e75dc05e435c |  | note | VERIFICATION ACTIVITY - Measurement
label | e7b2e23d-0c7c-53ef-827a-17a78774b1a9 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 7b9655e8-3b61-5467-b544-611600f20686 |  | note | FREQ. - Prior to surfacing
label | 807c0901-8de5-5bb9-aece-82c3888bc604 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree pre-level extents
label | 8fe3effe-8b73-5537-ae76-972beb7439d6 |  | note | INSPECTORATE W/H: Type - H
label | dbd4d57c-aaa5-590a-a3d4-a3c8b5d0119c |  | note | INSPECTORATE W/H: Description - Hold point - Inspection and agreement by NZTA
label | 3ac3cbed-20d0-5f02-9450-51c8387f7ac6 |  | note | RESPONSIBLE PERSON - Paving Supervisor / Paving Manager
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Paving Wearing Course
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | 130cdb43-f5ac-5dca-864c-1f59085cff66 |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | 3eac02fa-d990-5baf-985f-ee0b080331d2 |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | b0c33ff7-d8f5-5ecc-a006-b33bb9072b2a |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 907a7c41-311d-59a6-9677-a2daa8722597 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 13fb524c-3128-5e8e-a2b8-ad1a3238fe43 |  | note | INSPECTORATE W/H: Type - W
label | 4f80bf8b-9375-53b9-80bd-f12762b54a52 |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | 0b995df2-1500-50cf-9106-9c0b703e1e65 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | 16309d34-00be-5961-9088-b73bd76d5535 |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | dc717c1a-b1f3-5cbc-b9f5-8a48ec6d9ec2 |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | 2cf7f2bd-209d-5b2f-84b9-88f9564f012a |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 3dd0d1e5-71f5-5f15-b285-ce516a084ecc |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 2d7bae9a-37d6-5b21-8b09-fbb7449af12d |  | note | INSPECTORATE W/H: Type - W
label | e4790777-f55f-5072-b08d-498ab73a1a5a |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | 0e527a34-b1f6-5725-9d1b-42ac158287df |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | 54b1936f-143d-52ad-b527-f8d9cfc40385 |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | b6869944-e5ac-5e68-ae34-961203b1fa91 |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | 1157c45e-a3e1-505a-ad49-594ada9dcd19 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 96ad378e-890d-59f9-8be7-d65f5c677b0e |  | note | ACCEPTANCE CRITERIA - Per Mix design
label | 8da361e8-4380-5b2c-aaae-71e0c057eb5a |  | note | INSPECTORATE W/H: Type - W
label | e52effea-19c4-5533-8a97-5d9928e10172 |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | c4831d28-aaf4-508d-8358-3f09e5dfdeb9 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | ab08df42-ebc6-5d8a-b6e3-7ab17962922b |  | note | VERIFICATION ACTIVITY - Visual
label | 79251966-1dc6-5a8f-bd2a-8f59e6799fb1 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 089a817f-67e1-5ab0-8439-c0edebd40357 |  | note | FREQ. - Prior to Shift
label | 389d3eac-ec46-5ebd-8384-a243b4f7b0fa |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | 610831c7-9235-5225-a82d-5fa4ad1caa88 |  | note | INSPECTORATE W/H: Type - W
label | 6fafccd2-181b-514f-812c-832537b44c26 |  | note | INSPECTORATE W/H: Description - Paving Plan and Crew Briefing Plan completed prior
label | 1fb1dab4-cb45-59ec-b714-c4b1ea4fe9ba |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | 1ed48cf0-b395-5caa-b192-33da75770eb6 |  | note | VERIFICATION ACTIVITY - Visual
label | fa92faa1-a9e0-5a4a-8f79-02e7c03716a9 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 770aad69-2e70-502c-85c1-bec308723669 |  | note | FREQ. - Prior to Shift
label | be273974-3dc8-5527-b566-63b67b4d2328 |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | b9a75c29-6e74-5a13-9c27-ed2998876318 |  | note | INSPECTORATE W/H: Type - W
label | 5683f43d-bcf3-5631-ae43-a578cfdc0e2a |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.4 - Membrane Sealing
label | 7d49fe61-7c1d-532c-a0b7-51765ada49f8 |  | note | VERIFICATION ACTIVITY - Visual
label | a738fb0a-3c72-53d6-91ad-9ac02610f432 |  | note | METHODS OR REFERENCE - NZTA M/10
label | c20e6683-dc4d-527e-bffb-6860e5c6e92d |  | note | FREQ. - Prior to Paving
label | 1f304b19-72d4-585a-a8e9-d390aec022a1 |  | note | ACCEPTANCE CRITERIA - Membrane seal meets design and extent. Sealing Docket record kept
label | 3c88f2ec-3e50-5bcb-a396-75987f0da7a7 |  | note | INSPECTORATE W/H: Type - H
label | a7cb969e-dffc-5139-88fa-c85560df5e0b |  | note | INSPECTORATE W/H: Description - Hold Point - No paving until Membrane Done. Ensure correct application of chip & emulsion
label | c37dc09a-7fdd-545e-a469-cd170e8afdd4 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3.5 - Mix Inconsistency and Deficiency
label | 1971a3e1-2b88-52ca-9873-18705e447db6 |  | note | VERIFICATION ACTIVITY - Visual
label | 35d46002-ecd7-5844-bb93-06679c2993ad |  | note | METHODS OR REFERENCE - NZTA M/10
label | 4054577f-c490-5e73-9e5b-d1ba1ecef70b |  | note | FREQ. - Continuous
label | 7cdeb3ef-2b48-5dbf-a1b0-358053f834d9 |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | 90f40394-70dd-5614-9661-01ca473c1c43 |  | note | INSPECTORATE W/H: Type - H
label | 4d81dfa4-51c2-5afd-9eb9-90cdd6ba4e54 |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3.6 - Load Locate
label | 1cbe3e5e-b641-515e-8460-3e80aadce626 |  | note | VERIFICATION ACTIVITY - Measurement
label | 9805232f-8b27-595e-badf-1927de1c3cbc |  | note | FREQ. - Every Load
label | b8128ed0-2ebd-5b07-8289-05f2b2a8cd64 |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes:
label | 5d89b042-5bc2-5ecc-9d82-8f2ee45fbf27 |  | note | – Truck ID/Rego/Driver
label | 9bc6cd18-bcba-5536-9a71-3e94382dd9ca |  | note | – Depart Plant Time
label | fa369b3d-8377-5bc3-a707-d549d675371a |  | note | – Arrive Site Time
label | 712f059c-03e6-5a7b-92ed-59a0b1296aee |  | note | – AC Temp on Arrival
label | 6b9bef06-9b9f-5a77-a36c-16312cf2ef0d |  | note | – Ground Temp on Arrival
label | 8065cc1d-8d0a-599e-8963-298144f08cb7 |  | note | – Tonnage
label | 6d438cf2-6076-5d52-885d-a81b40995a29 |  | note | – Run Width
label | c15c1be1-dbd4-5bad-ae18-9e60a56fefd4 |  | note | – Estimated Run Length
label | d757b0a0-3789-57ee-b13f-0ae42f7cdf26 |  | note | – Calculated Area
label | 3db094af-f1ec-5a65-8841-ef2b39d489b1 |  | note | – Calculated Average Depth
label | b8672d6c-0be2-5ff8-b8f8-9ab690b72645 |  | note | INSPECTORATE W/H: Type - W
label | d2867004-0d47-5c69-806c-05ef7bd46d72 |  | note | INSPECTORATE W/H: Description - Per standard practice
label | 741133b4-da1e-58af-9a9e-718f7ef2ab2d |  | note | RESPONSIBLE PERSON - Quality Assurance Technician.
checkpoint-status |  |  | checkpoint | 3.7 - Laying Temperature
label | a35af98d-2ce6-52a5-9801-13ce8c0cf606 |  | note | VERIFICATION ACTIVITY - Confirmation
label | e24fd6c7-29ce-5a90-b9dd-e4f12f32ce41 |  | note | METHODS OR REFERENCE - NZTA M/10
label | e068bad6-0e81-5db0-b85a-95f18b94dc8c |  | note | FREQ. - Every Load
label | bffff155-7bb6-5af6-a195-bdb243d44bfe |  | note | ACCEPTANCE CRITERIA - Based on Mix design
label | 68b7aefc-54af-5026-ae32-52396abaf5d4 |  | note | INSPECTORATE W/H: Type - H
label | 50c2770d-b67b-5de4-95af-eb47b58cbdf8 |  | note | INSPECTORATE W/H: Description - Hold point - Reject mix for non- compliant temperatures.
label | af4b2b85-3ea1-55ed-8e6a-4d6bb3f96f6a |  | note | RESPONSIBLE PERSON - Quality Assurance Technician
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3.8 - Compaction
label | 7039d29a-bc52-54a0-b702-0d7815d080bf |  | note | VERIFICATION ACTIVITY - PQI Non-Nuclear Gauge/Cores. Or Non Distrctive Method Testing.
label | 07c6384e-8998-5009-a50b-e19fe06eaa8d |  | note | METHODS OR REFERENCE - NZTA M/10
label | 3848597a-850a-5d58-b6ca-15079d4377e4 |  | note | FREQ. - As per Agreed on Contract.
label | 2f7dff44-259a-50b2-931f-8ff993fdd8d6 |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | d44b70f7-9222-5de9-bb66-05baa55d30b0 |  | note | INSPECTORATE W/H: Type - W
label | fa68519d-0d60-552f-8c7b-45867355a374 |  | note | INSPECTORATE W/H: Description - PQI / Core recorded with RP, lane, offset, date, air voids. Core results received within 2 weeks.
label | 8e944bae-d8d6-5045-a321-f3f0ba07a441 |  | note | RESPONSIBLE PERSON - Quality Assurance Technician / Paving Manager
checkpoint-status |  |  | checkpoint | 3.9 - Roughness
label | db5f093e-8f3b-5c3d-9d35-b713dd89f2ca |  | note | VERIFICATION ACTIVITY - Visual
label | 3abfcb7a-bcd9-5208-8936-42b5a1b0308c |  | note | METHODS OR REFERENCE - On Site
label | 7fb0b8c3-ea27-5723-88b6-a6107f35494e |  | note | FREQ. - Post Construction
label | 0114fe14-1f4d-5ff9-a283-72e4ea83bf64 |  | note | ACCEPTANCE CRITERIA - Agreement with WK as per M10
label | 42534f85-e6cf-52b2-aad2-1f9daaa1a0e3 |  | note | INSPECTORATE W/H: Type - H
label | 64b8dcef-a57e-50f9-a7ea-21b4c459554a |  | note | INSPECTORATE W/H: Description - Site walkover with client to determine ability to comply with straight edge measurement outlined in M10
label | 4cc394f2-8851-5f19-82d4-a94f2d731487 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Site Reinstatement / Clearance
checkpoint-status |  |  | checkpoint | 4.1 - Shoulder Reinstatement (where no K&C)
label | c36ebea1-bff5-5858-8b46-545eb7df2161 |  | note | VERIFICATION ACTIVITY - Measurement/Visua l
label | 6cc4e529-149d-5bcf-b055-dfdeef07796a |  | note | METHODS OR REFERENCE - On Site
label | e2ed4ce3-4ef9-52f9-b3ff-4807b4888e26 |  | note | FREQ. - All low shoulder created by paving edge
label | 4a530b9f-627c-5ed3-b35a-bd783a34a753 |  | note | ACCEPTANCE CRITERIA - Shoulders reinstated to between 1:4 and 1:6
label | d544c845-e486-58f1-afad-7a20fe6c2602 |  | note | INSPECTORATE W/H: Type - H
label | 6dcd1c5e-05c7-51b4-9a8e-f1275012789b |  | note | INSPECTORATE W/H: Description - Low shoulder created by rural paving is corrected using AP20/40 or DG Mix. Not relevant in kerb and channel scenario.
label | 37d16ec7-948d-5319-9c19-9ba2c5e480ee |  | note | ○ Hold Point - Site TTM/TSL should not be removed until these hazards possible are attended to.
label | 648880c0-a84e-5df9-8134-76626c74386f |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.2 - Post-seal Area Check
label | 7c4d5e4e-762b-5a07-bd71-0127ae6cdc9d |  | note | VERIFICATION ACTIVITY - Measurement
label | faf4eaac-356e-53b8-ad0b-70d15956e44a |  | note | METHODS OR REFERENCE - On Site tape- measure
label | 2e553b1c-d54f-50ae-b6cf-8a05ee954307 |  | note | FREQ. - After Surfacing
label | f070549a-b2d9-5c32-8fe2-6a69cc1ba419 |  | note | ACCEPTANCE CRITERIA - Check sealed area meets design
label | d2a52525-841f-5ae0-b332-c328a0ac2a5a |  | note | INSPECTORATE W/H: Type - W
label | 7b45d325-eaeb-5671-897c-53ea3e5db687 |  | note | INSPECTORATE W/H: Description - Notify Renewals Engineer or Renewals Manager
label | 8a1db471-6dbe-5b05-94da-7277e2d9f577 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.3 - Service Covers
label | e978f4a7-9988-508d-b900-24d4ccec1c3e |  | note | VERIFICATION ACTIVITY - Measurement/Visua l
label | f8be0d17-0ce1-5269-b44a-30f47d361d51 |  | note | METHODS OR REFERENCE - On Site
label | b16a9f54-9f0a-5b4d-a852-6fcc9ca052b3 |  | note | FREQ. - After Surfacing
label | 29b4d609-9eb9-5d23-b0e9-5624ff5c3429 |  | note | ACCEPTANCE CRITERIA - All service covers are checked and adjusted (if necessary) to finished level (+10mm, -0mm)
label | af876cd9-183f-568d-adc3-f513701b4dbe |  | note | INSPECTORATE W/H: Type - W
label | 5d76a246-5395-5223-8a91-6505d462bb38 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.4 - Joint Sealing
label | ad2762d5-3b31-531b-89cd-142285bdbed0 |  | note | VERIFICATION ACTIVITY - Visual
label | 19f52601-b272-5952-8676-717d3632e2cc |  | note | METHODS OR REFERENCE - On Site
label | 9016626c-e9fa-5fd2-b589-ad26b383c3f1 |  | note | FREQ. - After Surfacing
label | 7bbf9985-ed8a-582d-b4fd-69364060ae7f |  | note | ACCEPTANCE CRITERIA - Check cold joints are bandage sealed
label | a21c55a2-d383-54c1-b971-139c3bc35bd7 |  | note | INSPECTORATE W/H: Type - W
label | 826c5c39-e250-589c-99c0-2bffddade5b8 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.5 - Road Marking
label | dd1c54b5-8b70-53c8-ac44-424262635921 |  | note | VERIFICATION ACTIVITY - MOTSAM
label | 7e015459-a2d8-5bd5-bd62-4f61f35cb9fd |  | note | METHODS OR REFERENCE - Visual inspection
label | cdd12416-c2fd-550a-a064-17cad34b1759 |  | note | FREQ. - All markings
label | 5bf26ea0-443e-51bb-9465-cf2c4dccdd75 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, or per design
label | f429c49c-59c5-5623-b83b-dfe66fc6e9cb |  | note | INSPECTORATE W/H: Type - H
label | 274b4c56-5caa-5de9-8412-238b86a78a1f |  | note | INSPECTORATE W/H: Description - Hold point – Site TTM cannot be removed until markings reinstated
label | c7619d60-f996-5645-b67d-17b51f73ee8e |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.6 - Other Traffic Services - Marker pegs/ Signs/Markings/RRP Ms Replaced
label | d90f29bc-b901-5667-8b9e-46776402ed6e |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | 65dce093-7408-56f5-9548-1516197849a8 |  | note | METHODS OR REFERENCE - Visual inspection
label | 3c336930-9f07-5351-8a10-6c6385ca493b |  | note | FREQ. - All signs/markers
label | af324b24-e686-528b-b7cd-405f0c08e0ed |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | d4125441-c5e9-51ea-8b17-92a02de7af74 |  | note | INSPECTORATE W/H: Type - H
label | 4c2bb1e0-0c35-5e49-8d15-e319732ed1cd |  | note | INSPECTORATE W/H: Description - Hold point – Site TTM cannot be removed until marker pegs, signs, markings and RRPMs reinstated
label | e18efb81-d598-54dc-94f3-407e818efa59 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.7 - Stormwater Management Controls removed
label | b2612730-55a2-5e0f-940f-3b7fdf429f00 |  | note | VERIFICATION ACTIVITY - Visual check
label | 6ff3aaf3-4bd4-5d33-a3cc-e4c46ea23897 |  | note | FREQ. - All installed measures
label | 03baf2b6-41a2-5635-9d83-cb4da898f83f |  | note | ACCEPTANCE CRITERIA - Installed controls are removed
label | 62ae1aea-018b-5233-8d9a-fbaf77414574 |  | note | INSPECTORATE W/H: Type - H
label | 8f6bb530-053c-5bb7-8a8c-b3fabab1f171 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.8 - Traffic Management Removed
label | c9d6bf41-6bd7-51c7-8ed5-de395080ff5b |  | note | VERIFICATION ACTIVITY - Visual check
label | 2c53b481-c81c-57fd-b521-4e60d10ed58f |  | note | FREQ. - When safe, after all physical works completed
label | 471d271d-d284-5a93-b993-59b8fa718ca8 |  | note | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | c37daa5b-c53f-5b2a-a96a-70d2942ee555 |  | note | INSPECTORATE W/H: Type - W
label | 314715ec-2af2-5d2c-8f8e-45a9e4e82b90 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.9 - Site left clean & tidy
label | 40e4fb67-5f21-5147-aa1f-9e1a30afd360 |  | note | VERIFICATION ACTIVITY - Visual check
label | acc509fa-4888-5f8e-a4fa-b61bd0b507ac |  | note | FREQ. - After vacating site
label | 2ff6a824-894f-5584-9f49-6ee449f59049 |  | note | ACCEPTANCE CRITERIA - Stockpiles removed, Plant removed, Litter cleared from site
label | 102b246c-2703-5cca-9a87-abd3ae5be9e2 |  | note | INSPECTORATE W/H: Type - W
label | f80db808-3ac0-5989-953a-74829b0efdbc |  | note | INSPECTORATE W/H: Description - Invite NZTA to carry out joint site inspection to inspect site.
label | 44fe5362-34d9-5e89-8347-a643dcd2b9f7 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-group |  |  | section | As Built Records
checkpoint-status |  |  | checkpoint | 5.1 - Collect asset data
label | 41bd6d63-025b-5118-b49d-977df7b55e0d |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | e9396dcb-e598-5012-8cd6-3b3adf3f548a |  | note | FREQ. - During construction
label | 83c58c88-3d6a-5411-a0a7-bf4b351d2960 |  | note | ACCEPTANCE CRITERIA - All relevant as built information collected.
label | 34906e6f-dc29-519a-af94-66470ef45fd9 |  | note | INSPECTORATE W/H: Type - W
label | 2ffdcf43-2033-50a8-a62e-847bcc5dad53 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.2 - Enter asset data into RAMM and/or register(s)
label | fb11e044-3e00-5400-80f4-75748f70455a |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | 093b80d1-2d62-545f-9439-4685af1b9032 |  | note | METHODS OR REFERENCE - RAMM
label | 023be411-113d-522a-b8c9-7de57a39bb9f |  | note | FREQ. - At completion of work.
label | 495c08f1-58fa-5740-86cb-70e73cc651c2 |  | note | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.
label | f5563487-565f-519c-b124-0ac3fff8d564 |  | note | INSPECTORATE W/H: Type - W
label | f366c789-f2ba-5476-9302-e15ea54840c3 |  | note | INSPECTORATE W/H: Description - Data entered by 20th of follow month after month of completion
label | 43f15cf8-81d1-52f1-b105-54d0fa7ffc10 |  | note | RESPONSIBLE PERSON - Asset Information Manager
checkpoint-status |  |  | checkpoint | 5.3 - Construction Completion Report
label | 80d850e8-9dcb-5e2c-bc23-fdc9a513c722 |  | note | VERIFICATION ACTIVITY - Confirmation
label | cac8389c-7518-570c-b50d-58523e4d699d |  | note | METHODS OR REFERENCE - Contract Specification
label | aed4a2fe-08db-5eab-b3c8-e6941bba62be |  | note | FREQ. - At completion of work.
label | 3d7067c1-a1f8-55f8-8f61-af252b6fa06e |  | note | ACCEPTANCE CRITERIA - Checked and approved
label | 4d50b9c8-7a98-59fe-bce0-d4c27939e36b |  | note | INSPECTORATE W/H: Type - W
label | fcd72f41-a840-5ed9-b8a1-e8f6d916743b |  | note | INSPECTORATE W/H: Description - Completed within two months after Paving Wearing Course
label | 83255f62-353c-5012-a1ce-dd53d36f4380 |  | note | RESPONSIBLE PERSON - Renewals Engineer/ Renewals Manager
checkpoint-status |  |  | checkpoint | Quality Assurance Close Out by:
text | 3ce190fc-143d-5293-a65e-c9e75d1898ee |  | textbox | (name):
date | 9805de49-dc21-597c-8409-447052f648f8 |  | date | Date:
label | e33d1417-1bfd-557f-9efd-28931dd08b01 |  | note | This record to contract file.
holdpoint |  |  | signoff | (signature)
checklist-sectioned |  |  | checklist | SNOC ITP Argyle Corner 1 - 670585 ITP v1.1 | itp |  |  |  | Yes | SNOC ITP Argyle Corner 1 - 670585 ITP v1.1 | 73aa984e-6480-4472-85cb-71eac92c3cc3
checkpoint-group |  |  | section | Preliminary and General
checkpoint-status |  |  | checkpoint | 1.1 - Construction Programme Completion
label | dd3a0594-87ce-5619-b26c-8aca98e2b474 |  | note | VERIFICATION ACTIVITY - Confirmation
label | b5147959-bd0b-53dd-8e42-dc21ca158e06 |  | note | METHODS OR REFERENCE - Best Practice Contract Specific MMP
label | bdbea156-d03d-5ae3-82d3-4147612d1511 |  | note | FREQ. - Before work commences
label | 9db0c731-5f9e-52c1-839f-2a5f7fbb72f8 |  | note | ACCEPTANCE CRITERIA - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date.
label | 46e84f14-eb0b-5337-9634-66d3a03d216f |  | note | INSPECTORATE W/H: Type - W
label | cdc88be9-6b95-5234-858c-62b07cfbe4bf |  | note | RESPONSIBLE PERSON - Renewals Manager
checkpoint-status |  |  | checkpoint | 1.2 - Approved RQP
label | cd677377-3a62-56e9-b299-dfa531947fcf |  | note | VERIFICATION ACTIVITY - Confirmation
label | 330d243a-1e65-593d-b88f-33b716a151dc |  | note | METHODS OR REFERENCE - Contract Specification
label | 8bc1368c-5080-5a6d-9a6b-54c7b579ca9d |  | note | FREQ. - Before work commences
label | a79494df-641a-535d-8c58-0fda531aa54b |  | note | ACCEPTANCE CRITERIA - Principal Acceptance according to guidelines in appendix 6.3
label | 9dd72dd9-fc6e-5227-a8a7-e1d6f37bfdc5 |  | note | INSPECTORATE W/H: Type - H
label | 74d46637-2dc5-52bb-bfba-a65342b6ddcc |  | note | INSPECTORATE W/H: Description - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. NZTA to approve
label | ca21b272-cf19-5535-bb89-c3a353eea745 |  | note | RESPONSIBLE PERSON - Renewals Manager
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3 - Traffic Management / TMP
label | f50b30bb-4d67-5e9e-8680-6cfe3dcdcd11 |  | note | VERIFICATION ACTIVITY - Visual check
label | 8f1ac2cc-260c-54ae-8122-9b129fe1cca7 |  | note | METHODS OR REFERENCE - CoPTTM
label | 65a7e7dc-7720-5732-bb36-02886c170314 |  | note | FREQ. - Before traffic management set up
label | 04a7cc62-21c6-54ec-86a9-21c9f91fd40f |  | note | ACCEPTANCE CRITERIA - TMP checked and approved Plans approved, Current EED (if applicable)
label | 30f0231d-8cb1-5c64-9dbd-01069609cb75 |  | note | INSPECTORATE W/H: Type - H
label | 26d2dd06-484f-58ca-9d1b-c1b2f3825775 |  | note | INSPECTORATE W/H: Description - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | 67600297-160f-5137-9787-2f060441bcf4 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.4 - Mix Design Verification for all mixes Check Laydown Trials are complete and compliant
label | a02d559f-2e3d-56c4-bce9-d9e86ffc81bb |  | note | VERIFICATION ACTIVITY - Confirmation
label | ab2f9e2d-0794-54f8-a6d1-c0d89c642e4f |  | note | METHODS OR REFERENCE - NZTA M/10, P/11, P23
label | fead91f5-2047-5419-a1a4-f4d2b2d0e14e |  | note | FREQ. - Before planning commences
label | 0b861491-27f5-5432-9468-cde82aa30345 |  | note | ACCEPTANCE CRITERIA - Mix Design compliant, current and relevant. Batching plant production capability is confirmed
label | f84153c4-d329-5ac3-9991-e57582eccc8e |  | note | INSPECTORATE W/H: Type - H
label | 235ba9ed-11c4-532d-ba17-0e20dbcf43a7 |  | note | INSPECTORATE W/H: Description - Hold point - No planning of on-site works shall commenced until the mix design is verified.
label | 046be585-f309-5416-92fa-0f061a62abf3 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.5 - Notification of intention to start work
label | fecbaca0-09a3-509d-a917-3af0c03468e3 |  | note | VERIFICATION ACTIVITY - Notification
label | 5f7f9fc6-c1bc-5d93-8954-01a177dc6fc8 |  | note | FREQ. - Before work commences
label | 35df38fb-8da5-5766-a73a-54fbecf737c5 |  | note | ACCEPTANCE CRITERIA - Letter drop to local residents. Greater consultation where required
label | b6c0dc03-4026-581f-9010-41b9b4913b2a |  | note | INSPECTORATE W/H: Type - H
label | 54b41235-563a-5d43-8707-fdfb681ccd0d |  | note | INSPECTORATE W/H: Description - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | fc3a4699-cb46-5eea-872b-3527a5a6f6fb |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.6 - Works Extents
label | 55873146-3b54-53e8-be9c-18d9b32daac8 |  | note | VERIFICATION ACTIVITY - Confirmation
label | f0b8ded9-488c-52ab-9c72-5de76050bc6d |  | note | METHODS OR REFERENCE - Site Visit
label | 7ae53a93-ec90-52dc-904e-bffab63f6a79 |  | note | FREQ. - Before work commences
label | ba669d29-f661-546d-a450-0f8a3864913d |  | note | ACCEPTANCE CRITERIA - Renewals Manager and/or Client to agree extents of project
label | 7b88e6c3-9448-5b65-9fe9-19b7c569d1f3 |  | note | INSPECTORATE W/H: Type - H
label | 2fa76501-22ca-544e-adb6-2ae5f26aa915 |  | note | INSPECTORATE W/H: Description - Hold point - Walk over site with Renewals Engineer and/or Renewals Manager and/or NZTA
label | 7ee003e2-abc0-57bd-90ac-61722b409b43 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.7 - Pavement Marking Records
label | c2afb5db-6b2d-592f-9705-19a3f42552fb |  | note | VERIFICATION ACTIVITY - Measurment Data
label | 7b50c1b6-47a8-5e9a-aef7-f8eb1487f87f |  | note | METHODS OR REFERENCE - Site Measure or Video Viewer
label | 6b388838-e09e-5e3e-873c-e815cbfa8419 |  | note | FREQ. - Before work commences
label | 74a871cb-299b-556d-9915-2b4f5e30c320 |  | note | ACCEPTANCE CRITERIA - Measure existing markings to aid reinstatement
label | 3665672b-1d08-55c0-abc0-9e83dd7b7f3d |  | note | INSPECTORATE W/H: Type - H
label | 241a2d72-be39-5659-acee-2efe3abddca6 |  | note | INSPECTORATE W/H: Description - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | 148b8c69-23c0-517e-8fc4-4278aef0cd3c |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Milling and Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | d82f22f8-b510-5b7f-a43a-5d8c75de7960 |  | note | VERIFICATION ACTIVITY - Visual plan, BeforeUDig Cable locate (electronic or pothole for line & depth)
label | 68c944ab-6569-5e56-badb-156004847a3d |  | note | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | f3e48865-fc9e-5d12-b55e-d4fcb89f7186 |  | note | FREQ. - Before work commences
label | 0e88bb93-dcc4-53c6-8841-f91e56f8a191 |  | note | ACCEPTANCE CRITERIA - Zero service strikes
label | 7fd3fda6-838e-56b0-b739-4cf2b81fce40 |  | note | INSPECTORATE W/H: Type - H
label | 41c7c96d-2dee-5c8b-9284-a3cb364eae22 |  | note | INSPECTORATE W/H: Description - Hold point - No excavation/milling is to be commenced until services are located and accounted for
label | a9b51dae-4076-537e-aa0e-dfc0eadfb0fa |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.2 - Stormwater Management
label | d0606d47-23c6-538b-8a1d-c2a05c9a3bea |  | note | VERIFICATION ACTIVITY - Visual check
label | 187df5a2-d311-58b0-a345-1e8a4035821b |  | note | METHODS OR REFERENCE - On Site
label | 360e0bdc-5ba3-586f-8e23-d2c23cae2bd7 |  | note | FREQ. - Before work commences
label | 49a9d0a8-25bb-5f1d-9b63-3590fe1ede61 |  | note | ACCEPTANCE CRITERIA - Mudtanks bunded or filtered to prevent mix from dropping in or runoff entering
label | b14dfb15-8797-579d-a0b5-b9c5c298afe7 |  | note | INSPECTORATE W/H: Type - H
label | d8e348fd-8e95-520e-b97f-13eb2d9a94d3 |  | note | INSPECTORATE W/H: Description - Hold point - No work to be commenced until protections in place
label | 1207975e-7b90-501c-b58c-990452eaf6ad |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.3 - Traffic Management - Setup
label | 1d723b49-f888-5ea0-84db-581051ab3255 |  | note | VERIFICATION ACTIVITY - Visual check
label | 343ab310-28b9-51f8-b258-8be3fc756881 |  | note | METHODS OR REFERENCE - Traffic Management Plan
label | 48b8b60c-bff1-5ef6-9dfc-26f17880e9eb |  | note | FREQ. - Before work commences each day
label | 9222b1af-7716-5e01-95f1-67584495d993 |  | note | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | 73c6c33e-7c42-5038-9ab4-9b1c475fbdcd |  | note | INSPECTORATE W/H: Type - H
label | 8e0aab72-dd20-56b5-b3eb-a61d58de3dc8 |  | note | INSPECTORATE W/H: Description - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | 0ccd00c9-73ef-5801-9472-f4b1c71b5122 |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.4 - Milling Depths
label | 3c81478b-40eb-577c-ba1f-6e8d222ff25d |  | note | VERIFICATION ACTIVITY - Measurement
label | 75868caa-cf52-584d-aa5a-7b16123a9532 |  | note | METHODS OR REFERENCE - On Site
label | 4f42081b-e3c0-5bdd-a1ee-253f693dd45c |  | note | FREQ. - Measure each side of milling machine cut
label | 71ff14b5-2cba-5826-8472-386612789312 |  | note | ACCEPTANCE CRITERIA - Every 10m. Depth matches target
label | 3b417562-9779-5b45-b40c-a1f43448509a |  | note | INSPECTORATE W/H: Type - H
label | 84ccd0f9-0c8b-5e94-b610-a3035bf795e5 |  | note | INSPECTORATE W/H: Description - Milling String Sheets or photos of depths taken and uploaded to CONQA
label | 3953f3bc-426d-5f01-b19d-1494f3bb2914 |  | note | RESPONSIBLE PERSON - Site Foreperson / QA
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.5 - Service Covers Preparation
label | 29b25845-dae9-5df5-8dfd-4dc9c8434de7 |  | note | VERIFICATION ACTIVITY - Visual
label | f1fb4d94-7dbc-5877-8c13-f0ef05c9b2f8 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | b2091aca-49c1-52a6-b446-c530579314a7 |  | note | FREQ. - All Covers
label | c1964f1d-83ca-50f7-a1ca-b38ce761fe56 |  | note | ACCEPTANCE CRITERIA - Hand excavation around ironwork and adjustment to desired level (if required)
label | b5f06ff3-8bb8-56a2-ad82-a2a2b79eba06 |  | note | INSPECTORATE W/H: Type - H
label | 317812f8-bce6-58a9-98ac-459f9894a1bb |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.6 - Additional Surfacing Preparation
label | fb232b70-14c6-573e-8c12-660fde1cf08e |  | note | – Side Roads
label | fadf6e18-5291-5d81-9fb7-163c83497f07 |  | note | – Accesses
label | e542ca3f-acc4-5f36-97b4-3c12288e9386 |  | note | – Driveways
label | 12dd312b-d594-50ff-ae6c-89373bb9ab2f |  | note | – Dish Channels
label | 95210ca7-717a-5ab3-a48d-89622c79a907 |  | note | – High Shoulders
label | ee74bc25-ba5a-53ce-b29a-86f680649472 |  | note | VERIFICATION ACTIVITY - Visual Check
label | f4618149-1c71-5c0f-b90e-e10121714d16 |  | note | METHODS OR REFERENCE - Per Design
label | 7d9cdd5c-07d9-52e6-a994-e5f53ece2fa3 |  | note | FREQ. - Before Membraning and Paving
label | b3953287-3762-53ee-8eec-670e6a06da5d |  | note | ACCEPTANCE CRITERIA - Have all areas of additional surfacing on the design been prepared, membraned and marked for paving?
label | 39c51819-c666-5d0d-89bb-51ad494177bb |  | note | INSPECTORATE W/H: Type - H
label | 9e9560be-a398-50af-9624-e154d22d8470 |  | note | INSPECTORATE W/H: Description - Hold Point – All areas planned for AC are prepared ready for surfacing layer
label | 6f415d92-703e-5ec2-9e6f-5b88bc6cfd70 |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.7 - Milling Surface inspection / walkover
label | dfb5c833-5b32-5dcd-90fb-e951fa3fe1dc |  | note | VERIFICATION ACTIVITY - Visual Check, proof roll with loaded truck to check deflections
label | c3000206-259e-58da-95b5-7d03f05f9e43 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 1f7322ae-7a98-5f9f-bf38-ff88ce7569ab |  | note | FREQ. - Prior to surfacing
label | 09ae545a-bf0a-5c30-bc0b-0fda4e25da46 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree if any additional overmilling is required
label | ff505d58-e264-551f-bd82-524298cdce99 |  | note | INSPECTORATE W/H: Type - H
label | a2628973-c0ea-520f-a1a7-1a0ba0c30ff4 |  | note | INSPECTORATE W/H: Description - Hold point - Inspection and agreement by NZTA
label | b1efbaa1-79a9-5946-bfa0-1618a219a468 |  | note | RESPONSIBLE PERSON - Paving Supervisor / Paving Manager
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.8 - Over-Milling
label | 78e80741-b2c3-5602-b0a4-9909da416216 |  | note | VERIFICATION ACTIVITY - Measurement
label | ba080a1b-67a1-5197-b17f-4d1b1ae735d6 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 19ded790-278a-5e70-8fc4-2989dd2715a7 |  | note | FREQ. - Prior to pre-level
label | 4d304c82-759d-5b97-a9c3-0fc5fa5ce5e7 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree need and extent of over-milling and infill.
label | 1ebab0db-4373-55f5-a94d-ba9b27e4ca29 |  | note | INSPECTORATE W/H: Type - H
label | ab36a608-b98a-54db-badc-870c75896ab2 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.9 - Pre-Level
label | 869054db-ebb1-50db-9e0c-e999a743a31d |  | note | VERIFICATION ACTIVITY - Measurement
label | 349b3fa0-2080-5db6-8eba-6913cb2cec56 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 8862eeb3-7333-5661-bc9e-12280f9fb936 |  | note | FREQ. - Prior to surfacing
label | 3b1aad9e-78f0-588e-aef1-f8aaf9a352ee |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree pre-level extents
label | 5f307240-d90f-5849-b2e3-a9d88337a502 |  | note | INSPECTORATE W/H: Type - H
label | 59faeffa-23e9-5bf1-b2d1-9956eae10d32 |  | note | INSPECTORATE W/H: Description - Hold point - Inspection and agreement by NZTA
label | 31dba64f-b0f5-56f4-b5d8-6e9ff35c85a4 |  | note | RESPONSIBLE PERSON - Paving Supervisor / Paving Manager
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Paving Structural
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | 6e30a218-a5e9-53fe-a57a-8d7d05e6e072 |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | e463b821-0390-589f-a857-5f42b21c816b |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | 6eea7f78-7853-5b59-b37f-7e0339ed507e |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 8fdd9382-067f-5136-b7a4-1f2324b3a819 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | d8b782ba-c8ac-5a40-8b8d-0806e1428e58 |  | note | INSPECTORATE W/H: Type - W
label | 5524d1ae-6662-5d08-8268-eb7c2f90a82c |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | 46f221f4-d30f-5317-a789-d1d70b43e431 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | 205ca5e6-0be6-59f9-9d37-caad13f58720 |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | f481ee8f-e00a-5a48-9f22-9118875a6254 |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | 0f681732-523c-5a01-8258-ba6dd8fb83cb |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 737f5b5a-a3a2-59dc-a506-40a62e5c2dc9 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | be929589-b2a5-5fae-af07-b2e2906f3d8a |  | note | INSPECTORATE W/H: Type - W
label | eba4f275-e0e2-5b06-aef2-42d3aeed78d4 |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | 78d5e8bd-4c39-5e3a-ad13-c1791086ae18 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | 3f82ef3c-a738-58e7-8774-a6864b8e97d7 |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | e9c1de92-a0b3-5546-a22e-4f03701db812 |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | f58d7991-abcd-584a-85bc-b5f76845d057 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 138e95c1-7b34-5a8b-a19c-7aa845fe6718 |  | note | ACCEPTANCE CRITERIA - Per Mix design
label | e3ded1db-4139-54ba-a763-69b0bf878bd6 |  | note | INSPECTORATE W/H: Type - W
label | 647c6f62-dd04-58f6-9cbe-fede540210a1 |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | c2d4077b-37ab-510f-b851-9e8fd2d7e95f |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | f4a5a28e-c612-5907-9f25-d7584035779b |  | note | VERIFICATION ACTIVITY - Visual
label | da3e64a7-c322-5336-b975-afde803b4943 |  | note | METHODS OR REFERENCE - NZTA M/10
label | b578d693-325d-56d8-8c3e-ae5761c507b0 |  | note | FREQ. - Prior to Shift
label | 5d19dded-ce25-5170-b136-3429b0a4211f |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | 8c9a099e-00e6-5c7c-ad84-3f6f624aad94 |  | note | INSPECTORATE W/H: Type - W
label | 33a211bd-a186-5afe-af41-7c05e6b837a6 |  | note | INSPECTORATE W/H: Description - Paving Plan and Crew Briefing Plan completed prior
label | a55cd75b-29ab-5fa1-9de7-6386a98d08a2 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | 7bcb4357-e584-5b78-a2f3-05a482d2eeaf |  | note | VERIFICATION ACTIVITY - Visual
label | 6532341d-d20b-5600-a3c0-998f1125d999 |  | note | METHODS OR REFERENCE - NZTA M/10
label | e7f0f409-d3b7-55b0-adcc-b521ec34a593 |  | note | FREQ. - Prior to Shift
label | 7d740790-a464-58d2-921d-643ca1e1d045 |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | 3a48249f-7391-51d3-bfe2-99c7ed851ca2 |  | note | INSPECTORATE W/H: Type - W
label | 25dde696-033d-50b6-9655-ecffe3ba92d3 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.4 - Mix Inconsistency and Deficiency
label | 18d29f7c-9484-5940-be65-d6245726b06f |  | note | VERIFICATION ACTIVITY - Visual
label | 010ce1d9-5470-5581-8836-750c09b939c6 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 745f3e7f-4956-5495-99ce-aa8caf57116d |  | note | FREQ. - Continuous
label | 6e87553b-8e9c-5c7a-bad2-8d4a700b4a6b |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | 707d3450-0a56-54a2-a2b2-1af00fe824c5 |  | note | INSPECTORATE W/H: Type - H
label | 90d92219-264c-5ccd-9ce7-fb79ac2649ab |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3.5 - Load Locate
label | 41797201-8b15-5f00-952d-0be5096f9b47 |  | note | VERIFICATION ACTIVITY - Measurement
label | b7e3c975-b056-55de-bd28-bc689ac6510e |  | note | FREQ. - Every Load
label | 97ed7242-b187-591d-8d9e-56f3735c98f7 |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes:
label | c63bee9e-05ef-5b5a-8949-3a3ea7f987a0 |  | note | – Truck ID/Rego/Driver
label | 651a7341-35e6-56ab-ad5a-3b464bd50f90 |  | note | – Depart Plant Time
label | b0b2fbb4-0003-5cab-a24e-8708923993f5 |  | note | – Arrive Site Time
label | 66de64bf-3245-5a14-abc2-e04e635a4c49 |  | note | – AC Temp on Arrival
label | fec8ff46-c25b-5c3b-bd8c-86b58cec0187 |  | note | – Ground Temp on Arrival
label | 12497468-f6d2-55ee-8697-898b1158ff1e |  | note | – Tonnage
label | dadbbd8c-f4bd-5c82-a46f-0623d3e6590c |  | note | – Run Width
label | 7bbefc1e-b967-572b-9982-d2f3e4158486 |  | note | – Estimated Run Length
label | 649d979b-06f1-59c5-aa0b-3c2f7e2009c7 |  | note | – Calculated Area
label | 65750e30-88c2-5071-b857-4c9d8f72ed40 |  | note | – Calculated Average Depth
label | 991b3476-05d4-57be-a971-a86b223afdab |  | note | INSPECTORATE W/H: Type - W
label | bd7de85a-ef08-5d83-ad33-d3297245ac00 |  | note | INSPECTORATE W/H: Description - Per standard practice
label | 9436fa4c-be9c-5721-9060-a58d1f910975 |  | note | RESPONSIBLE PERSON - Quality Assurance Engineer
checkpoint-status |  |  | checkpoint | 3.6 - Laying Temperature
label | 6ddb0f47-238a-5dee-a731-0fdfbede5a1b |  | note | VERIFICATION ACTIVITY - Confirmation
label | 61f97514-0852-5bdb-8789-e271dadaa109 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 49ece17f-6320-50cb-b097-42d2c0b8e7f5 |  | note | FREQ. - Every Load
label | 60b9d459-2a1b-5f0b-a9e8-8c8bdb4bfa2c |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | a8f3f0fb-7fc5-5600-8964-44c8e683e431 |  | note | INSPECTORATE W/H: Type - H
label | 4b563ae2-30bd-5093-8777-df157ffbc568 |  | note | INSPECTORATE W/H: Description - Hold point - Reject mix for non-compliant temperatures.
label | 841698a3-a709-57d8-b02b-8c770e1b0140 |  | note | RESPONSIBLE PERSON - Quality Assurance Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3.7 - Compaction
label | cea24dd1-4913-5566-99d7-7b524e517ab5 |  | note | VERIFICATION ACTIVITY - NDM Testing
label | 2b044829-4432-5734-bb21-7c1d67502ceb |  | note | METHODS OR REFERENCE - NZTA M/10
label | 73bbc2cc-7948-5cfc-a5eb-06d5427b6530 |  | note | FREQ. - Minimum:
label | ab0fa97c-b50c-5d15-981b-aa963a52b179 |  | note | ○ 1 Test per 300m² within Mat.
label | 5f7d1127-794a-5fb7-bbe8-7e978444d0eb |  | note | ○ 1 Test per 100m of joint.
label | c7fcb66e-9467-5854-8dc5-8ef4728c6944 |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | fc3d669d-8d66-5287-8253-b4660c627b81 |  | note | INSPECTORATE W/H: Type - H
label | a5ccf9c2-06b7-50fe-a936-fc3fc583383d |  | note | INSPECTORATE W/H: Description - Hold Point - No Wearing course paved until any non-compliance is sorted. PQI / Core recorded with RP, lane, offset, date, air voids. Core results received within 2 weeks.
label | e3fc5a05-b79d-5cc7-96ea-789316bd15c2 |  | note | RESPONSIBLE PERSON - Quality Assurance Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Paving Structural
checkpoint-status |  |  | checkpoint | 4.1 - Production Properties - PSD (Particle Size Distribution)
label | 4fcccd2c-a816-5382-9d5d-b532e0475b14 |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | e4b2d9a4-f981-52da-9bae-9eecd7c5ea5e |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | e2c4c683-42cc-569e-be2e-4c793ecb00eb |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 777fad3d-faec-5e73-9a93-52eae70356f6 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | bc426fb8-fe8b-552f-ba7e-008deb5c7ede |  | note | INSPECTORATE W/H: Type - W
label | 4fff984b-69ae-5470-97aa-8be4880c4de3 |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | 89172b5f-48c0-5fb9-b1d3-d03a4801e6f3 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.1 - Production Properties - Binder Content
label | 96e725f2-e595-5c2d-93e4-4b78fb8cde2c |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | 68a2a043-17bd-510d-a257-fc8ddf14f09b |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | 6a89afc1-9b74-5130-8508-f6fca52cb633 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 47931b8e-aeb1-52dd-8164-4ddadfa1c634 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 6d6d525a-c38b-5521-b5fb-808eeffc3193 |  | note | INSPECTORATE W/H: Type - W
label | 951c07e5-a076-5fe9-8803-af778bd20a88 |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | 98509879-3997-5d97-8f05-9b8e677fb3de |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.1 - Production Properties - Maximum Specific Gravity
label | 64d15dd5-0121-562e-96ec-7806a28a82d7 |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | d6368eb3-b4e3-59c3-b0b9-f50333941029 |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | 794e5e3a-3f8a-51f2-963c-d452060c8a1f |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 0e0ef9a4-a276-50f9-8ffb-8f703e22cdc7 |  | note | ACCEPTANCE CRITERIA - Per Mix design
label | b07de6d0-4f3b-5246-991b-53cbe9a87479 |  | note | INSPECTORATE W/H: Type - W
label | 40d4d900-cdc2-59f7-b4d7-a27e621378d5 |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | ce2de9a7-e815-5fde-9125-7c2ddb1227bb |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.2 - Preparation
label | c9b66e80-fbb9-5b94-ac9a-24eb684ed883 |  | note | VERIFICATION ACTIVITY - Visual
label | 0d9fd4f0-5e6c-5fe1-9974-bad3b13dbf92 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 49cdc4d0-5bac-5373-ab04-3b9b2cc4d946 |  | note | FREQ. - Prior to Shift
label | 4cbfda99-5c2e-5aa1-8469-a67985bc84b1 |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | f42e95d9-e3ce-5cbc-ad2c-2779cb329a77 |  | note | INSPECTORATE W/H: Type - W
label | b9393294-2ec3-50a9-b002-04a839477fd3 |  | note | INSPECTORATE W/H: Description - Paving Plan and Crew Briefing Plan completed prior
label | 3b13df13-edc0-5bc6-aeb9-ce3c7c17c0aa |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.3 - Joins
label | 28d97fc1-b82f-5214-9696-4d6fe61f853a |  | note | VERIFICATION ACTIVITY - Visual
label | f3084f85-bec5-5d5d-8111-fe23fa5d4c77 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 5f43dc4b-faa7-53b4-9558-c01fc40f57f5 |  | note | FREQ. - Prior to Shift
label | f88d71cc-7318-5cae-90f6-5922b0c7a9f5 |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | 0944fdac-699e-54b0-bc1a-eaa80de3c782 |  | note | INSPECTORATE W/H: Type - W
label | c5e97401-7ad4-5495-8ec0-1555f6d9ab65 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.4 - Membrane Sealing
label | 7faf72e2-5c81-564f-ac91-466f59efc8d4 |  | note | VERIFICATION ACTIVITY - Visual
label | be68cb08-fd93-5199-b3b3-b7fe6edb64f2 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 671a1075-e937-5d6d-a21c-51eb0cbd82c1 |  | note | FREQ. - Prior to Paving
label | 410a22b2-3028-5144-91f4-8cbac912f84d |  | note | ACCEPTANCE CRITERIA - Membrane seal meets design and extent. Sealing Docket record kept
label | 1041a611-8fbf-5204-999f-a410871896ab |  | note | INSPECTORATE W/H: Type - H
label | e836fd5d-ff43-5e2a-94dc-3eae2867782f |  | note | INSPECTORATE W/H: Description - Hold Point - No paving until Membrane Done. Ensure correct application of chip & emulsion
label | 0b5e17ea-1951-5977-8419-19ec46384281 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.5 - Mix Inconsistency and Deficiency
label | 8120aa98-cdcb-5e56-94b8-a15f4cd4564c |  | note | VERIFICATION ACTIVITY - Visual
label | 74d646d5-d69b-5a01-9d66-2d99887595e5 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 469d21fe-5fc4-5ec8-bea6-5be4750d17b2 |  | note | FREQ. - Continuous
label | a8d523b5-d5d2-546c-8eef-f9896c397e39 |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | 1add6aef-0120-5c6f-87a3-7223bb709ba1 |  | note | INSPECTORATE W/H: Type - H
label | e96812ef-bdee-5206-8c7c-5b461d285d96 |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.6 - Load Locate
label | 36cb1029-e78b-5031-838b-601ebce29803 |  | note | VERIFICATION ACTIVITY - Measurement
label | 1edee410-9a10-5693-9445-1cba984a8e4b |  | note | FREQ. - Every Load
label | 66b4cd1d-843d-5e7e-95d8-f5bf95d5fe4e |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes:
label | 4b8ed62d-7155-5b61-8935-01f970a38c2e |  | note | – Truck ID/Rego/Driver
label | 52fe1b2a-d1a4-5632-94c1-5de025fbee4d |  | note | – Depart Plant Time
label | 05b52fd7-74d5-5d33-b61f-34626eba59e6 |  | note | – Arrive Site Time
label | 1bd28e8f-872f-5c70-ab4b-f9f6c6215526 |  | note | – AC Temp on Arrival
label | 89a77ec8-bc1e-507a-af9a-b53cf3e02c8c |  | note | – Ground Temp on Arrival
label | c7c67319-8560-54c1-b844-2dadb26942d5 |  | note | – Tonnage
label | 8c22556c-8a5a-5874-b782-d3d34bcfca10 |  | note | – Run Width
label | a43b40e4-cbff-5b2b-9b8e-8e6f0ac28d84 |  | note | – Estimated Run Length
label | c6ddc735-37ab-564f-a91b-a25102552a6d |  | note | – Calculated Area
label | 9ab6abf5-1860-5674-bf2a-21ccdecdb9f2 |  | note | – Calculated Average Depth
label | 840329db-f3e7-5c65-9b64-b9e0d2dbab1d |  | note | INSPECTORATE W/H: Type - W
label | 4b84a7c9-154e-5abc-926c-3c83d3b47fcd |  | note | INSPECTORATE W/H: Description - Per standard practice
label | 71d68230-b247-5a78-ad2a-5208912396e5 |  | note | RESPONSIBLE PERSON - Quality Assurance Technician.
checkpoint-status |  |  | checkpoint | 4.7 - Laying Temperature
label | b9a16d58-3606-5eaa-80ab-03ce0a25e534 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 5c4523a2-61b3-50dd-b69d-8fdf3dd96fcf |  | note | METHODS OR REFERENCE - NZTA M/10
label | 59240978-7466-58b1-884e-bfb0557ef92e |  | note | FREQ. - Every Load
label | b2ea8449-e6f9-5f72-918e-784ceab3ebce |  | note | ACCEPTANCE CRITERIA - Based on Mix design
label | e173d980-37da-58a5-839d-fcd51aa3486d |  | note | INSPECTORATE W/H: Type - H
label | 66d23073-9e4d-51b0-b70a-6d84e94e042d |  | note | INSPECTORATE W/H: Description - Hold point - Reject mix for non- compliant temperatures.
label | 182c3d28-493e-5681-8c35-064b43a90b36 |  | note | RESPONSIBLE PERSON - Quality Assurance Technician
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.8 - Compaction
label | 756475d9-7be4-5ad6-92cd-47acde7045da |  | note | VERIFICATION ACTIVITY - PQI Non-Nuclear Gauge/Cores. Or Non Distrctive Method Testing.
label | 8c063077-8789-5cce-8f34-7fb329f96edb |  | note | METHODS OR REFERENCE - NZTA M/10
label | 1e3ff88b-94ad-5698-940f-672e0c0a4aa0 |  | note | FREQ. - As per Agreed on Contract.
label | 0beaa655-4335-5655-aedd-fe2f08cb1620 |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | 94eba5e6-25f1-5a4a-a3fe-c245e1032fc6 |  | note | INSPECTORATE W/H: Type - W
label | 01c39f32-5eab-568b-b9d6-27e096a03849 |  | note | INSPECTORATE W/H: Description - PQI / Core recorded with RP, lane, offset, date, air voids. Core results received within 2 weeks.
label | d75884cb-baf8-5e2a-ac32-c4351f5ce07a |  | note | RESPONSIBLE PERSON - Quality Assurance Technician / Paving Manager
checkpoint-status |  |  | checkpoint | 4.9 - Roughness
label | 3aa8dda9-4c0b-5340-91e0-98260acc3647 |  | note | VERIFICATION ACTIVITY - Visual
label | 9108e4bb-2559-5adc-b3d2-4d7c5c675280 |  | note | METHODS OR REFERENCE - On Site
label | 32482deb-1bf3-5230-9356-ee653887dfd1 |  | note | FREQ. - Post Construction
label | 0027f70b-0be3-5d14-852a-7785d2a9ff08 |  | note | ACCEPTANCE CRITERIA - Agreement with WK as per M10
label | 7fa28dff-d24b-50fa-a8fa-d8e83f09e40a |  | note | INSPECTORATE W/H: Type - H
label | 0f068e15-1c5e-5ddb-aa51-bfbbf6b8a8b4 |  | note | INSPECTORATE W/H: Description - Site walkover with client to determine ability to comply with straight edge measurement outlined in M10
label | f7a369a3-4fda-5d03-ab3a-93bc4ae4a5d2 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Site Reinstatement / Clearance
checkpoint-status |  |  | checkpoint | 5.1 - Shoulder Reinstatement (where no K&C)
label | f5038da8-9f14-51d8-9981-4af9bd0607e0 |  | note | VERIFICATION ACTIVITY - Measurement/Visual
label | 84dcbb42-f65d-5c60-b035-fdd5dd04465c |  | note | METHODS OR REFERENCE - On Site
label | fe9f8151-d175-537d-9c51-439a621bfdd3 |  | note | FREQ. - All low shoulder created by paving edge
label | e452c930-eec6-55da-9fa9-155c0252e8a2 |  | note | ACCEPTANCE CRITERIA - Shoulders reinstated to between 1:4 and 1:6
label | 8723881b-ad6b-594c-9dbd-4d92f0e0191e |  | note | INSPECTORATE W/H: Type - H
label | e28be69f-ec7a-5067-a393-c482a76cb860 |  | note | INSPECTORATE W/H: Description - Low shoulder created by rural paving is corrected using AP20/40 or DG Mix. Not relevant in kerb and channel scenario.
label | e47ff1f7-8305-5f8a-9b12-58c0dacc2d83 |  | note | ○ Hold Point - Site TTM/TSL should not be removed until these hazards possible are attended to.
label | e2823d33-e40b-596d-b441-554b407afedd |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.2 - Post-seal Area Check
label | ba3f8321-889c-578a-aff1-cf288f77aa9e |  | note | VERIFICATION ACTIVITY - Measurement
label | 72627dfb-2351-5f1f-96cb-051123e71715 |  | note | METHODS OR REFERENCE - On Site tape- measure
label | 97f99570-2500-5db7-a1ee-85a33c145579 |  | note | FREQ. - After Surfacing
label | c842f027-207d-5311-8983-5ae23f81c1a9 |  | note | ACCEPTANCE CRITERIA - Check sealed area meets design
label | 4878848b-669c-5c38-be5e-5dd9d31ddf7d |  | note | INSPECTORATE W/H: Type - W
label | f5483771-f029-5ec4-a318-a5902bab19d8 |  | note | INSPECTORATE W/H: Description - Notify Renewals Engineer or Renewals Manager
label | 250b26b2-b96e-5cd8-8578-fbe28f5ce1d7 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.3 - Service Covers
label | a84073e5-b076-574f-b3df-f2735221c4af |  | note | VERIFICATION ACTIVITY - Measurement/Visua l
label | 8be6b6f2-d9c3-565e-8d4b-b69917c6d2b8 |  | note | METHODS OR REFERENCE - On Site
label | a7359ef7-48c2-5762-915a-259351e21c8a |  | note | FREQ. - After Surfacing
label | 68bc7a78-457f-5716-baca-763fcfdb52b0 |  | note | ACCEPTANCE CRITERIA - All service covers are checked and adjusted (if necessary) to finished level (+10mm, -0mm)
label | 2e3410db-931b-500a-b48b-99e1fceed5a4 |  | note | INSPECTORATE W/H: Type - W
label | f9a58f7f-a8d5-5142-9008-9ae16a30d5ee |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.4 - Joint Sealing
label | 9af23b6d-0f61-58b5-b558-8f993d800448 |  | note | VERIFICATION ACTIVITY - Visual
label | 63f1ffac-f6be-5cfd-a7c9-fb09ae1322a8 |  | note | METHODS OR REFERENCE - On Site
label | ac2fda4f-5cda-5443-a732-ebba04f6f5c6 |  | note | FREQ. - After Surfacing
label | 96a2b529-38a7-5aba-bd02-dfacc52e4d60 |  | note | ACCEPTANCE CRITERIA - Check cold joints are bandage sealed
label | 84887e08-92de-548f-b78a-a57b1da0cf1a |  | note | INSPECTORATE W/H: Type - W
label | 5b274e99-4fb7-59a1-b781-a166a413e97b |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.5 - Road Marking
label | 5dc4491e-e945-545e-ad89-2607098a406b |  | note | VERIFICATION ACTIVITY - MOTSAM
label | c6b9e3e5-b5e2-55c3-8bf0-637af94bf3f5 |  | note | METHODS OR REFERENCE - Visual inspection
label | f8d4ea20-9ee8-5695-833c-4343d3b2c07c |  | note | FREQ. - All markings
label | d1368ea6-28af-5766-bc81-291f2cbb4b23 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, or per design
label | 3242372a-da9b-58d3-b5e8-228517bc9308 |  | note | INSPECTORATE W/H: Type - H
label | 93390076-d608-5b29-a929-2d3b84b9925e |  | note | INSPECTORATE W/H: Description - Hold point – Site TTM cannot be removed until markings reinstated
label | 4a6ff51b-56e1-52ff-aa28-148912e091fb |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.6 - Other Traffic Services - Marker pegs/ Signs/Markings/RRP Ms Replaced
label | c36ebae6-d764-5aa8-94fd-ba3e381fcd52 |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | b235b74b-95e9-58f2-937b-c9d6ba85d7c6 |  | note | METHODS OR REFERENCE - Visual inspection
label | 0ccec963-a0fa-57e6-befc-8ac5b1eba70e |  | note | FREQ. - All signs/markers
label | a2770995-183c-54d3-bbd8-435257afeef8 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | ad6e01b1-6fe6-5d3a-865b-f260024324a2 |  | note | INSPECTORATE W/H: Type - H
label | 66f9a443-e431-575f-85e6-999bdf2999f9 |  | note | INSPECTORATE W/H: Description - Hold point – Site TTM cannot be removed until marker pegs, signs, markings and RRPMs reinstated
label | 9a4bd27a-a0a8-5dc4-8661-eeb7904c0d39 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.7 - Stormwater Management Controls removed
label | aa4250e4-c907-59de-88c2-39ebab639a9b |  | note | VERIFICATION ACTIVITY - Visual check
label | 68262446-0ddf-5df3-8c05-0fc38083a0d1 |  | note | FREQ. - All installed measures
label | 375f161f-56df-5e6f-98b7-1c8d15ee805a |  | note | ACCEPTANCE CRITERIA - Installed controls are removed
label | 378cbc38-3622-5950-8d17-e0071da84143 |  | note | INSPECTORATE W/H: Type - H
label | 52b33f3d-676f-5f4a-a706-5360e5315ee8 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.8 - Traffic Management Removed
label | bb66f08d-adeb-5bb9-9fa9-8195833bd7ee |  | note | VERIFICATION ACTIVITY - Visual check
label | 1c8a0270-48cb-5331-b851-41d16dfb8545 |  | note | FREQ. - When safe, after all physical works completed
label | fbe2008f-9150-5ee0-8a6c-425eac9443be |  | note | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | 45b5ef9e-eb97-57c9-9f3b-2a9ca8860085 |  | note | INSPECTORATE W/H: Type - W
label | 516eed3f-539a-5d1e-bd3f-f74f705bef9d |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.9 - Site left clean & tidy
label | 130f854d-22bb-5930-b75c-e1970e57a956 |  | note | VERIFICATION ACTIVITY - Visual check
label | 2e45917f-0903-58ef-b97e-e3815c731c78 |  | note | FREQ. - After vacating site
label | 4d602cb4-d557-5268-a458-9a3e24e694a5 |  | note | ACCEPTANCE CRITERIA - Stockpiles removed, Plant removed, Litter cleared from site
label | 2bcfd1d7-5a5b-515f-aa35-c6102b9fcb8d |  | note | INSPECTORATE W/H: Type - W
label | 4b790c4e-eadf-5406-9a49-9d7e0e894737 |  | note | INSPECTORATE W/H: Description - Invite NZTA to carry out joint site inspection to inspect site.
label | 553caaf9-007e-57c8-a516-a061d959e808 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-group |  |  | section | As Built Records
checkpoint-status |  |  | checkpoint | 6.1 - Collect asset data
label | cd6c27f1-5340-53d3-bf97-5f7595fe77e9 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | ab96afcc-c0ec-542d-825f-e5b7b2175a22 |  | note | FREQ. - During construction
label | 91f49f82-6e40-5e1e-9c5b-970778a2f486 |  | note | ACCEPTANCE CRITERIA - All relevant as built information collected.
label | de7b3463-2cad-503e-9525-f4e6fd88a0bb |  | note | INSPECTORATE W/H: Type - W
label | 266e16de-3dd7-51e4-b457-4975d28e751c |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 6.2 - Enter asset data into RAMM and/or register(s)
label | e0ef4bec-8446-517f-b95b-eeacfde91acc |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | ed64a118-84c0-58d7-bf86-10e25a204832 |  | note | METHODS OR REFERENCE - RAMM
label | 2a10fbb8-d639-5604-a92e-b52c6734d790 |  | note | FREQ. - At completion of work.
label | de4fe8f4-4c79-57b4-9c37-8ca28916dd95 |  | note | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.
label | 916cb438-a67b-51fb-aa1e-a73516c3c303 |  | note | INSPECTORATE W/H: Type - W
label | ff99510c-3d23-50b8-9fdc-fceb7a1edfd1 |  | note | INSPECTORATE W/H: Description - Data entered by 20th of follow month after month of completion
label | 18becc52-83d6-5c35-a699-06ef469de0b8 |  | note | RESPONSIBLE PERSON - Asset Information Manager
checkpoint-status |  |  | checkpoint | 6.3 - Construction Completion Report
label | 0625d888-4f17-554a-b537-4931ac92adc4 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 58a0ac3f-68f2-5863-ad55-92a88bae0023 |  | note | METHODS OR REFERENCE - Contract Specification
label | af020d0d-edf3-56b9-b088-07ae8904afcb |  | note | FREQ. - At completion of work.
label | 5ba74620-3812-59c5-96a8-145757beb3f3 |  | note | ACCEPTANCE CRITERIA - Checked and approved
label | 2fe6844c-1487-5aac-96fa-f2c86bc1a9dc |  | note | INSPECTORATE W/H: Type - W
label | 88689e6c-efd9-5ffa-95a0-e3c89ebcd10e |  | note | INSPECTORATE W/H: Description - Completed within two months after Paving Wearing Course
label | ed279aec-0a38-5239-9dc8-93ac3c93eb85 |  | note | RESPONSIBLE PERSON - Renewals Engineer/ Renewals Manager
checkpoint-status |  |  | checkpoint | Quality Assurance Close Out by:
text | d2c99d3f-3db3-57b9-b6c6-ea71b86f412e |  | textbox | (name):
date | 93e7e082-c6e3-57ab-8089-2c1a439f17c8 |  | date | Date:
label | 7b60a378-97dd-537c-bc8b-faca56e2d383 |  | note | This record to contract file.
holdpoint |  |  | signoff | (signature)
checklist-sectioned |  |  | checklist | SNOC ITP Intersection SH1 &96 South Mataura - 670583 ITP v1.1 | itp |  |  |  | Yes | SNOC ITP Intersection SH1 &96 South Mataura - 670583 ITP v1.1 | 7a9700ec-0a75-42ad-b5d4-05df893db350
checkpoint-group |  |  | section | Preliminary and General
checkpoint-status |  |  | checkpoint | 1.1 - Construction Programme Completion
label | 5c2929c6-ac5a-537a-81bd-06dd1b484dd6 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 23f9459c-eff7-54d5-a372-d19fd9bdc545 |  | note | METHODS OR REFERENCE - Best Practice Contract Specific MMP
label | 106e8d62-b7ed-5b2f-899e-24ff70c0343a |  | note | FREQ. - Before work commences
label | b983c545-6190-525a-8447-f284b3bf24f0 |  | note | ACCEPTANCE CRITERIA - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date.
label | 81d3b9dd-0473-5fdc-a857-41c030417901 |  | note | INSPECTORATE W/H: Type - W
label | 9016e45e-2557-5b94-a6a1-2fe30087432b |  | note | RESPONSIBLE PERSON - Renewals Manager
checkpoint-status |  |  | checkpoint | 1.2 - Approved RQP
label | 673f5441-7e25-5202-bb5f-f1e9b8b8ff2f |  | note | VERIFICATION ACTIVITY - Confirmation
label | 5bb196b5-aedf-57ff-9697-698769ad58e0 |  | note | METHODS OR REFERENCE - Contract Specification
label | ae33b58e-8178-5c84-9f69-7f6e4f1bd452 |  | note | FREQ. - Before work commences
label | b1ade37d-c096-5b64-a071-ca6aa552f277 |  | note | ACCEPTANCE CRITERIA - Principal Acceptance according to guidelines in appendix 6.3
label | e338dcc9-d5b8-53c8-9e74-2d80f3e9ac08 |  | note | INSPECTORATE W/H: Type - H
label | f79d3e4e-5622-5414-8861-76c50ca55f98 |  | note | INSPECTORATE W/H: Description - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. NZTA to approve
label | de2ca1f5-32d0-5452-8ad5-0db69c07d7ae |  | note | RESPONSIBLE PERSON - Renewals Manager
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3 - Traffic Management - TMP
label | 45f306ee-db8f-5e40-9c0f-c450b01c389d |  | note | VERIFICATION ACTIVITY - Visual check
label | 07c0c163-2ca1-56f3-879b-2bc562d36814 |  | note | METHODS OR REFERENCE - CoPTTM
label | 0ef66edd-74c0-538e-bb63-0e880e2b7753 |  | note | FREQ. - Before traffic management set up
label | 2921f560-f0cc-5d8e-8b17-17a62a87c6fd |  | note | ACCEPTANCE CRITERIA - TMP checked and approved Plans approved, Current EED (if applicable)
label | 54e55fb7-b26a-559f-964b-ef9fdd9f914b |  | note | INSPECTORATE W/H: Type - H
label | 8057e43f-01fb-5ddd-99aa-e9411d2d4017 |  | note | INSPECTORATE W/H: Description - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | 8f142915-64c0-500c-b8c5-0f854d7b18f1 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.4 - Mix Design Verification for all mixes Check Laydown Trials are complete and compliant
label | 4b85f70e-d508-555e-8990-093e488f11c9 |  | note | VERIFICATION ACTIVITY - Confirmation
label | dacaaeb0-c59d-5a4e-95a5-663bf02d9e84 |  | note | METHODS OR REFERENCE - NZTA M/10, P/11, P23
label | a6300dd9-e16c-55f5-b819-e1ae20a5a2c4 |  | note | FREQ. - Before planning commences
label | 76c6c97e-eef4-5115-97ed-ceec15904841 |  | note | ACCEPTANCE CRITERIA - Mix Design compliant, current and relevant. Batching plant production capability is confirmed
label | 1e9e2839-d685-5ae0-a114-d8567e3ec456 |  | note | INSPECTORATE W/H: Type - H
label | aaaa90eb-34b2-5c35-8d01-a8cd94476cf2 |  | note | INSPECTORATE W/H: Description - Hold point - No planning of on-site works shall commenced until the mix design is verified.
label | 6f9e1a84-8fbe-5697-b9af-506b24adb58d |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.5 - Notification of intention to start work
label | fa1eaf76-4e0c-5a3e-8050-0731dd095972 |  | note | VERIFICATION ACTIVITY - Notification
label | e5c0fa06-005e-50c4-a4db-d72896fd98d5 |  | note | FREQ. - Before work commences
label | 6736336f-6bb0-50f6-8bf3-17c6d0ecf17b |  | note | ACCEPTANCE CRITERIA - Letter drop to local residents. Greater consultation where required
label | 6f2acadd-3786-56c4-bc3b-e705fd92840e |  | note | INSPECTORATE W/H: Type - H
label | 610fa5a8-2ef7-52af-8f79-52b6be961d8b |  | note | INSPECTORATE W/H: Description - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | 93270e3e-d756-56e7-97c5-96c20e17bfd0 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.6 - Works Extents
label | 34a2c5db-afce-50ca-97b8-d4e430aba8b4 |  | note | VERIFICATION ACTIVITY - Confirmation
label | e0b9cf76-8534-5c56-bd02-e9d2efc1690d |  | note | METHODS OR REFERENCE - Site Visit
label | 19e4916c-5dc5-5773-ad6b-ef3d9fa2c308 |  | note | FREQ. - Before work commences
label | 4efce466-bfb3-5044-8877-629ae1d36358 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and/or Client to agree extents of project
label | 244f408c-b726-5ac1-af46-9744b2735843 |  | note | INSPECTORATE W/H: Type - H
label | 6c09c64c-8e56-56a8-9550-f753c653f965 |  | note | INSPECTORATE W/H: Description - Hold point - Walk over site with Renewals Engineer and/or Renewals Manager and/or NZTA
label | 8e9ac537-a177-56b7-a702-f0772eb38cdb |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.7 - Pavement Marking Records
label | 2a73b7ba-4f1e-524f-b291-d42ebf712cc3 |  | note | VERIFICATION ACTIVITY - Measurment Data
label | 2d95c3f2-9e9f-50cc-bd13-46ac21b5aeb7 |  | note | METHODS OR REFERENCE - Site Measure or Video Viewer
label | 8aaf5702-6401-5f4d-a6a9-413400aa6e78 |  | note | FREQ. - Before work commences
label | 6dc72c54-3939-5f82-be34-fe39dfa162aa |  | note | ACCEPTANCE CRITERIA - Measure existing markings to aid reinstatement
label | 413c27ab-88d2-5b05-a89b-190c9ba5f0ca |  | note | INSPECTORATE W/H: Type - H
label | f1b11420-02ab-51cc-b037-7681c40cfd08 |  | note | INSPECTORATE W/H: Description - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | 13febc97-a13a-5341-be34-5ba5946102bb |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Milling and Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | 7eec6cf1-6179-5609-8d8c-178c48ecf6dd |  | note | VERIFICATION ACTIVITY - Visual plan, BeforeUDig Cable locate (electronic or pothole for line & depth)
label | db459b96-86c2-5b7f-8ff0-c2af896a2502 |  | note | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | 6eb4e16b-31d6-5152-b42d-ce0ff7c93d3a |  | note | FREQ. - Before work commences
label | 8678a0ba-6a2c-57d7-9576-fca40c94e24c |  | note | ACCEPTANCE CRITERIA - Zero service strikes
label | a3605881-7892-5137-ad5c-ba942ef617ea |  | note | INSPECTORATE W/H: Type - H
label | 8bfc9415-a289-5b25-b768-a7c12c886525 |  | note | INSPECTORATE W/H: Description - Hold point - No excavation/milling is to be commenced until services are located and accounted for
label | 10c95106-4832-54c4-b163-8974424f6bc6 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.2 - Stormwater Management
label | 35004db9-4658-547a-b0ec-a7f3888acc60 |  | note | VERIFICATION ACTIVITY - Visual check
label | 270fc6b6-c8f0-5d02-9b32-5e09f11ea82b |  | note | METHODS OR REFERENCE - On Site
label | 646f7b37-15c9-555a-919d-642d7bfc48b1 |  | note | FREQ. - Before work commences
label | e24f95b3-e497-59bc-a370-306a932dcf83 |  | note | ACCEPTANCE CRITERIA - Mudtanks bunded or filtered to prevent mix from dropping in or runoff entering
label | fa12ef6e-1ca2-5591-a4b6-dbb5be31dead |  | note | INSPECTORATE W/H: Type - H
label | 24b5e454-49f5-5cf8-b99d-b0b389f185d8 |  | note | INSPECTORATE W/H: Description - Hold point - No work to be commenced until protections in place
label | 381f15fe-aeed-5c5b-9ced-2d90bf2b0455 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.3 - Traffic Management - Setup
label | d2e9b346-0d24-549e-a79d-3193b0a6310e |  | note | VERIFICATION ACTIVITY - Visual check
label | 2f74cc49-3dfa-5598-93f6-0a4b67ea89d0 |  | note | METHODS OR REFERENCE - Traffic Management Plan
label | 547e8990-fec5-5cfa-88d5-2c79d199c93a |  | note | FREQ. - Before work commences each day
label | c00a9e5c-d730-57aa-9aeb-70290f501714 |  | note | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | 88c6a98f-5047-592d-8601-a6eaac03e992 |  | note | INSPECTORATE W/H: Type - H
label | a5d0aaae-8358-50d0-8503-4dde4bdcd6ce |  | note | INSPECTORATE W/H: Description - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | 3603009f-deb2-58a0-a3e7-4fe2f6ee3992 |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.4 - Milling Depths
label | 833ed0df-c227-5d6a-b2a6-b1ad0b7d6b2d |  | note | VERIFICATION ACTIVITY - Measurement
label | c2614883-3d33-56f2-ab79-6931a7d779c4 |  | note | METHODS OR REFERENCE - On Site
label | 02998170-8d80-5a7c-af31-085e28c43d3d |  | note | FREQ. - Measure each side of milling machine cut
label | d6833779-7de8-5dfa-8845-765b626220f0 |  | note | ACCEPTANCE CRITERIA - Every 10m. Depth matches target
label | a0d88342-5cbb-5120-af9e-2e6fdf822500 |  | note | INSPECTORATE W/H: Type - H
label | deffb7f2-f5a5-50df-85f6-6e9df5dac902 |  | note | INSPECTORATE W/H: Description - Milling String Sheets or photos of depths taken and uploaded to CONQA
label | 8273ee7c-c3f6-5856-97ab-fac81e0a5785 |  | note | RESPONSIBLE PERSON - Site Foreperson / QA
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.5 - Service Covers Preparation
label | d7664dde-3756-563f-9db8-bfcdf68df3d6 |  | note | VERIFICATION ACTIVITY - Visual
label | cd566203-d7eb-5867-b690-fd630b553daa |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 9891f467-36d0-5596-9ceb-8f09e12af1ff |  | note | FREQ. - All Covers
label | fb246ef5-4e12-557a-bb1c-f6af8674e876 |  | note | ACCEPTANCE CRITERIA - Hand excavation around ironwork and adjustment to desired level (if required)
label | be43632b-acaa-5830-903e-b60299e567d5 |  | note | INSPECTORATE W/H: Type - H
label | 3ae47218-16da-577c-bcaa-24b84464794a |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.6 - Additional Surfacing Preparation
label | 14d341a8-f7f4-5b19-9aca-b1d8bf8f167d |  | note | – Side Roads
label | 8e79ecbe-8fb6-5982-8a70-3ba84cb92fc3 |  | note | – Accesses
label | e11c1100-7f0d-5325-bdf6-d2299467beda |  | note | – Driveways
label | 7424cd2b-5461-506e-94e1-c8b2713e4892 |  | note | – Dish Channels
label | 27028f14-d2cf-53b4-9757-57feb6c2aa22 |  | note | – High Shoulders
label | cb80dad1-1f35-5c56-ba41-106b39e0fed8 |  | note | VERIFICATION ACTIVITY - Visual Check
label | 37b16dc6-9285-5cbe-95af-31d2097f7f79 |  | note | METHODS OR REFERENCE - Per Design
label | ad4af6f2-9b5c-5863-8f44-5592d3b37530 |  | note | FREQ. - Before Membraning and Paving
label | e772ac40-a6e5-511b-b5a3-0eb556a4ef95 |  | note | ACCEPTANCE CRITERIA - Have all areas of additional surfacing on the design been prepared, membraned and marked for paving?
label | 467083e6-57ec-54b9-9a1d-7c07eb5354e6 |  | note | INSPECTORATE W/H: Type - H
label | 3cd82958-dde5-5455-8fc9-7f92e6236c0b |  | note | INSPECTORATE W/H: Description - Hold Point – All areas planned for AC are prepared ready for surfacing layer
label | 5a73d632-ed6a-5205-8a16-17366e32cd3d |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.7 - Milling Surface inspection / walkover
label | c53b9e75-1d25-5d26-9df8-48967769fc9d |  | note | VERIFICATION ACTIVITY - Visual Check, proof roll with loaded truck to check deflections
label | 8809863b-addf-50e7-919b-1eaaada41762 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | cb8e024f-2d88-53be-bbff-f87c32a563d6 |  | note | FREQ. - Prior to surfacing
label | 4283584a-b113-5bdd-b672-3988c0673367 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree if any additional overmilling is required
label | 761e50e8-724e-56be-8eee-ad69e2c39772 |  | note | INSPECTORATE W/H: Type - H
label | 133acfc0-52f1-5187-aede-562d4e3008e5 |  | note | INSPECTORATE W/H: Description - Hold point - Inspection and agreement by NZTA
label | 52eba0f8-836d-5ae6-9d44-a05c36dbb49e |  | note | RESPONSIBLE PERSON - Paving Supervisor / Paving Manager
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.8 - Over-Milling
label | 4836ac55-8e3a-5d56-b5b7-4f8a69199dd7 |  | note | VERIFICATION ACTIVITY - Measurement
label | 7eb71ca3-e2eb-50f9-afb9-b50931954073 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 4d5b506a-98ba-560b-b788-2dd5a2af0179 |  | note | FREQ. - Prior to pre-level
label | bc276fe3-d2dc-5c68-bfe7-2f632364b031 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree need and extent of over-milling and infill.
label | c50f4612-c4f0-5906-ae8b-dd70fd39d89a |  | note | INSPECTORATE W/H: Type - H
label | c65eb267-eae4-5804-a156-238cc9a8e17f |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.9 - Pre-Level
label | 5850596b-7c7e-59b3-aeb9-774594549da4 |  | note | VERIFICATION ACTIVITY - Measurement
label | d2ed61c1-c9a4-5df7-8196-c6f643e3fcf4 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 77732963-de27-546a-a9c3-5d0ef283b28c |  | note | FREQ. - Prior to surfacing
label | aa7e315e-7035-5168-9d14-985edb958fe6 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree pre-level extents
label | b6c6a0f8-b51b-5ec7-9b7b-af2c03310002 |  | note | INSPECTORATE W/H: Type - H
label | 4075427a-e9db-5f13-b15f-a8503cbc64ed |  | note | INSPECTORATE W/H: Description - Hold point - Inspection and agreement by NZTA
label | 2669de26-b070-56ba-8ab2-9a0faf9a0800 |  | note | RESPONSIBLE PERSON - Paving Supervisor / Paving Manager
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Paving Structural
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | f965a9f8-21fd-509b-b789-253937157821 |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | 6f903ab5-3bfd-5531-91d8-8bfaad002161 |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | 0d89b448-c2cb-51e3-9f4a-f1a13faf3d9d |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 41778476-3226-57f0-b8e7-8b723ed04b72 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 5580c5e9-1fb1-502c-9437-10dc3f3d0047 |  | note | INSPECTORATE W/H: Type - W
label | d29a6850-6d57-5f40-b66f-349c9819e0fb |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | d70d28da-ed93-5580-816e-3d3434075277 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | 67768def-1045-57ef-b548-00145cc58399 |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | fe7ccdc8-a25a-5c0c-a644-630589c349d5 |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | 5b2e7b0c-945a-50fe-9c19-63f580a12f34 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 2b05ee19-98f0-5909-9edf-0a0b149d3641 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 0def2e88-46cd-5f45-a2cb-8e4966f9ce57 |  | note | INSPECTORATE W/H: Type - W
label | e3205d2e-1f87-5d6d-903b-71150a209c6e |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | b8fa9ff0-a690-555c-838a-e2cc7f192950 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | d855145e-1752-5b48-920c-df183072ba1f |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | 43712261-a02c-5179-be5d-411b8ca2893f |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | 1a3d691f-2796-5c45-944d-64cdd67dd1ca |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | c6deba45-cb22-5240-9b03-6b1e6d4a0e35 |  | note | ACCEPTANCE CRITERIA - Per Mix design
label | 042e5661-6697-58b5-b0e2-9037a6a7c165 |  | note | INSPECTORATE W/H: Type - W
label | 662cd012-481b-5f04-89e8-6a9bf76c9021 |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | 5cfeb997-f81a-546c-bb10-b9ca8994fc0a |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | 3e1075b2-d201-5540-bc15-9f8e48dd2551 |  | note | VERIFICATION ACTIVITY - Visual
label | 975e91d5-8d27-5735-84b6-bc1761bc2f42 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 0ad7cc95-4b1b-5cff-aea8-ef3fccb047f3 |  | note | FREQ. - Prior to Shift
label | 66569f56-a4a1-59bb-b920-6aad1d93749d |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | 2d95ddae-69b9-52ab-ac72-89ec41a07ea7 |  | note | INSPECTORATE W/H: Type - W
label | 7f5976f1-64b1-54ad-b256-1fdb2cee192e |  | note | INSPECTORATE W/H: Description - Paving Plan and Crew Briefing Plan completed prior
label | e2757af4-3935-5806-8336-0bf50f9ec8ba |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | 1d92aefb-a7d6-568d-a0f2-8845ac895624 |  | note | VERIFICATION ACTIVITY - Visual
label | 89d2dfc9-6031-5fe9-a290-3d14dc44e98a |  | note | METHODS OR REFERENCE - NZTA M/10
label | a892f23d-c72e-58dc-ad69-04903b10fb03 |  | note | FREQ. - Prior to Shift
label | e9ba04b7-98e5-588d-8c84-1acc914dc422 |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | 0937e554-15ff-5f91-a5e7-6fe4282642e0 |  | note | INSPECTORATE W/H: Type - W
label | 93cff196-d30c-5c81-9dd2-bb4a2bba21b3 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.4 - Mix Inconsistency and Deficiency
label | 7bb7891e-3606-51f9-9d20-3591e8431442 |  | note | VERIFICATION ACTIVITY - Visual
label | eb172c48-3f9a-537b-a891-5b892797ace0 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 482da265-b2f1-5217-a83c-e0264a9ddcb5 |  | note | FREQ. - Continuous
label | 418332ec-8dce-5909-8ded-e4b6cdf273d9 |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | 5e5ea6e6-dc8a-587c-bd7e-05495c9cfa39 |  | note | INSPECTORATE W/H: Type - H
label | e84056af-fbcb-50ae-befb-dfc9ae89045c |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3.5 - Load Locate
label | 193b0e89-155f-56f3-9a23-c11dc077d6af |  | note | VERIFICATION ACTIVITY - Measurement
label | bf16b7a7-89b1-528d-979a-845ebdd09fc0 |  | note | FREQ. - Every Load
label | 13f23002-0c4b-55c1-9abc-ade3a6234228 |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes:
label | dde9aa5b-136e-5266-986d-9d86a3747627 |  | note | – Truck ID/Rego/Driver
label | f3dba387-7352-5e70-8e97-e47b196349e5 |  | note | – Depart Plant Time
label | 9f255281-9b7b-5b7f-879c-36010cecff48 |  | note | – Arrive Site Time
label | 2b3296b5-ac21-55fe-945b-61205672ac81 |  | note | – AC Temp on Arrival
label | aa27c7c3-b4ba-5f4a-8144-c23ec3475e88 |  | note | – Ground Temp on Arrival
label | 5c43d92b-bd69-5c10-9b72-186ebeaa50ba |  | note | – Tonnage
label | ddd983fd-2235-54dd-a6c8-0cef02a6d144 |  | note | – Run Width
label | aedf6340-7d50-5f7e-9cda-49fa4f214ad8 |  | note | – Estimated Run Length
label | f662ce2f-fe15-5f59-84c5-483f4db00b47 |  | note | – Calculated Area
label | ed946e16-4b36-5365-905e-37b9b09f237e |  | note | – Calculated Average Depth
label | 090dec64-b989-5c12-a53a-768be145afd5 |  | note | INSPECTORATE W/H: Type - W
label | a6d052d0-56dc-57de-809b-5ba9855bd921 |  | note | INSPECTORATE W/H: Description - Per standard practice
label | 4bca48f2-6832-59da-895c-67a807fdc67f |  | note | RESPONSIBLE PERSON - Quality Assurance Engineer
checkpoint-status |  |  | checkpoint | 3.6 - Laying Temperature
label | 3389b758-a2b2-54bb-bd50-f8f5235d2809 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 7f52c667-fdf7-521e-b8b9-fb75c59df127 |  | note | METHODS OR REFERENCE - NZTA M/10
label | bbf00313-cf9a-5341-bfcd-4be2bef011ca |  | note | FREQ. - Every Load
label | b8e578f6-eed3-5229-91f8-4d398eac9c5b |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | fe5fe13c-3ef1-5120-ab4d-b4aed2655726 |  | note | INSPECTORATE W/H: Type - H
label | 7dd30f01-e33f-5ddc-a738-5969f518775e |  | note | INSPECTORATE W/H: Description - Hold point - Reject mix for non-compliant temperatures.
label | 13915174-36b9-5540-9779-fbfffd6d6521 |  | note | RESPONSIBLE PERSON - Quality Assurance Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3.7 - Compaction
label | ea4b4de9-fe7f-53ce-869a-cedea4437975 |  | note | VERIFICATION ACTIVITY - NDM Testing
label | bd0fc176-4edd-5826-bdf4-bc16e57b33d9 |  | note | METHODS OR REFERENCE - NZTA M/10
label | ea0902d6-44ef-5473-842e-64c9707229e0 |  | note | FREQ. - Minimum:
label | 35cec352-a758-5d46-bf59-e2b74de994e2 |  | note | ○ 1 Test per 300m² within Mat.
label | a262319a-65ad-56bc-892b-9e5c64b64ff1 |  | note | ○ 1 Test per 100m of joint.
label | effe4178-20da-508e-93e3-839d88fe68ab |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | 3e5ec3ce-d77b-5b0d-bc7b-2f6833aff004 |  | note | INSPECTORATE W/H: Type - H
label | 9461e56f-3f2a-55dd-b9d0-007da4b11097 |  | note | INSPECTORATE W/H: Description - Hold Point - No Wearing course paved until any non-compliance is sorted. PQI / Core recorded with RP, lane, offset, date, air voids. Core results received within 2 weeks.
label | 5a00902f-febb-5c04-baca-1be33f665c02 |  | note | RESPONSIBLE PERSON - Quality Assurance Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Paving Wearing Course
checkpoint-status |  |  | checkpoint | 4.1 - Production Properties - PSD (Particle Size Distribution)
label | 826a0b6b-47c1-53eb-8c42-f02079e17c73 |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | a8913a5b-c74b-565c-bbca-7612be081997 |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | cdf3e29f-eb96-572f-a5e6-61b16c7d8ce1 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 82e97086-54ae-55f8-a27d-56792598f025 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | f5ad49cb-8b28-5093-aa41-163a6fe19c3e |  | note | INSPECTORATE W/H: Type - W
label | dbd46169-3f3c-5e3c-8e76-69a44b1c5c65 |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | 4582e2a2-8e5e-5a26-b904-853e7380f8a4 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.1 - Production Properties - Binder Content
label | 238281a4-4fe8-5ed6-94e0-d50ac3a470e7 |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | fc710657-ddd5-5719-a2f8-b0e998b2503d |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | 87a079e0-124b-54fd-98f5-d71af0d3d31e |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | e62d1e22-0940-5426-bd8a-02b5d6604017 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | edad46f9-881b-5991-bc62-2694ecc30205 |  | note | INSPECTORATE W/H: Type - W
label | 16dc0470-6256-5d52-8c84-0a3443335fc5 |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | 72e89dc8-5f8b-521e-aa14-fda8ffcb0840 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.1 - Production Properties - Maximum Specific Gravity
label | cdde6683-f463-53fe-ae1a-d966151fd5ba |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | bde20673-d8dd-5f84-b063-3ec2946e84ce |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | 213435f9-de81-5c08-b330-12b0c2453924 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | ea405067-af57-58bd-87a3-972d98a77ff6 |  | note | ACCEPTANCE CRITERIA - Per Mix design
label | 364cdd41-db32-5286-928c-7ef4bf94f911 |  | note | INSPECTORATE W/H: Type - W
label | e80bb954-ba0e-58aa-9e7d-84fcc4394a63 |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | 22987112-dbb4-5411-8ab0-7b400c4098b0 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.2 - Preparation
label | a7a79155-74f5-5422-947a-15211dc5c1df |  | note | VERIFICATION ACTIVITY - Visual
label | 00ba2f9f-cd31-5834-80a5-a3c4c0b8a42e |  | note | METHODS OR REFERENCE - NZTA M/10
label | 0f45e72d-cdd4-5f79-a6a4-e6e7e4485813 |  | note | FREQ. - Prior to Shift
label | 192c1396-1386-5bff-baba-35cfbb119650 |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | 786bc9e7-eed7-5c9e-ab5b-e92a187b27b5 |  | note | INSPECTORATE W/H: Type - W
label | 784d79b0-0163-50d5-89d1-641d06afa01d |  | note | INSPECTORATE W/H: Description - Paving Plan and Crew Briefing Plan completed prior
label | 5e380dcf-7189-5d76-b821-3b1fe0db6a25 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.3 - Joins
label | 26ff77e8-be6f-5ce1-9c5d-0a1898468800 |  | note | VERIFICATION ACTIVITY - Visual
label | 873c9233-ee5d-56dd-affd-3826342f68b6 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 8683b1d9-5412-5ec7-9968-898668bf8139 |  | note | FREQ. - Prior to Shift
label | 1f995a2c-b7ff-554b-92ef-71cdc5ed972e |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | 73ce5b93-4a14-5ba5-a28b-a06aab223a0d |  | note | INSPECTORATE W/H: Type - W
label | bbc006a3-9ed4-5428-b469-06717ff02dbd |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.4 - Membrane Sealing
label | ab7c6fbc-d2d0-5302-9d6f-950a7d5c876e |  | note | VERIFICATION ACTIVITY - Visual
label | 7f72cf20-580b-57ce-9161-d2aa1841356f |  | note | METHODS OR REFERENCE - NZTA M/10
label | c24bba65-1886-56a5-b30d-13a4055250d2 |  | note | FREQ. - Prior to Paving
label | 968d5b0c-ec9e-516a-8b8a-5f997c6d6241 |  | note | ACCEPTANCE CRITERIA - Membrane seal meets design and extent. Sealing Docket record kept
label | a9816313-abf4-55bf-ab0e-0fd10adf5b21 |  | note | INSPECTORATE W/H: Type - H
label | 14d1962c-989c-55c6-a66c-a8485f8a2664 |  | note | INSPECTORATE W/H: Description - Hold Point - No paving until Membrane Done. Ensure correct application of chip & emulsion
label | 3026b0d5-9396-5a09-87fe-2a2db546a352 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.5 - Mix Inconsistency and Deficiency
label | a659606e-9a31-58fc-9025-59846892186d |  | note | VERIFICATION ACTIVITY - Visual
label | d3477f82-9541-5425-824e-fc8d42b10e0b |  | note | METHODS OR REFERENCE - NZTA M/10
label | a7d354e4-82e3-588e-9e36-6c146f0e51ba |  | note | FREQ. - Continuous
label | ec7dac84-2393-5e74-a15f-1c021f2bbbd5 |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | 8bfc1df4-1df3-5f46-be33-4ba9931ac595 |  | note | INSPECTORATE W/H: Type - H
label | 5c8223e0-5820-5d9d-bd8f-a5014f9151cd |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.6 - Load Locate
label | 5aaa9ac7-a6bc-5556-a1c4-b1e232e65b06 |  | note | VERIFICATION ACTIVITY - Measurement
label | 47f780e8-0cd2-52c4-8cd2-b1cadfa99af8 |  | note | FREQ. - Every Load
label | fa128223-5cbd-5982-9ab5-a04755282162 |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes:
label | a1d17b23-5e39-5ef9-a67b-8011206c9faa |  | note | – Truck ID/Rego/Driver
label | a8e28515-ce20-59af-ae8b-8eb0497d2cfd |  | note | – Depart Plant Time
label | f0ce4eb4-9dc3-5014-a3ff-de9a722b61e5 |  | note | – Arrive Site Time
label | 447e249d-0f07-5494-bec4-148be3c33f43 |  | note | – AC Temp on Arrival
label | 14b2aba3-28ca-5339-a57a-05bc55a37ade |  | note | – Ground Temp on Arrival
label | c8b251fd-5ce2-55ef-a5da-6ef20ae6d4c4 |  | note | – Tonnage
label | bdfb5af5-356c-5811-8ba8-b3961f4c72b6 |  | note | – Run Width
label | 0637444e-a75a-5689-bdc4-487d018f486b |  | note | – Estimated Run Length
label | c3ab8c9f-b466-5199-8266-bde37d362b9b |  | note | – Calculated Area
label | 65e5a94b-0442-5653-9ef6-49e6ad7eb635 |  | note | – Calculated Average Depth
label | 6d95730d-bfdd-55ec-8850-2f2ab637726a |  | note | INSPECTORATE W/H: Type - W
label | bf57a3c1-5d7e-5b95-ab20-ccbf062f409c |  | note | INSPECTORATE W/H: Description - Per standard practice
label | ccf45a7b-ff9f-5b53-95cf-4c75332b6654 |  | note | RESPONSIBLE PERSON - Quality Assurance Technician.
checkpoint-status |  |  | checkpoint | 4.7 - Laying Temperature
label | 022f21d5-509b-5696-afad-bce32f4499c6 |  | note | VERIFICATION ACTIVITY - Confirmation
label | a6b55bb5-9e99-5d93-8e99-b08019b38474 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 2d360836-cbdc-5283-8d72-81505fbf4078 |  | note | FREQ. - Every Load
label | c3a0a538-74de-5abb-92d4-aafd97cd3ca9 |  | note | ACCEPTANCE CRITERIA - Based on Mix design
label | 83093558-763c-5766-a9ce-b265a11b8290 |  | note | INSPECTORATE W/H: Type - H
label | b0630c01-cedf-5535-bec4-cceda507b394 |  | note | INSPECTORATE W/H: Description - Hold point - Reject mix for non- compliant temperatures.
label | 54bbf906-af81-5f3e-af49-5bbe71186ae7 |  | note | RESPONSIBLE PERSON - Quality Assurance Technician
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.8 - Compaction
label | e6f86abf-3980-5f6c-91c1-aca2d4ed60c5 |  | note | VERIFICATION ACTIVITY - PQI Non-Nuclear Gauge/Cores. Or Non Distrctive Method Testing.
label | 0269c866-c4fc-51e7-826a-65b62e22b22a |  | note | METHODS OR REFERENCE - NZTA M/10
label | 8933c765-85d5-5ad2-8830-3998d9469235 |  | note | FREQ. - As per Agreed on Contract.
label | 78347c0b-082f-5627-9176-2c0359335dc9 |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | d9f615cc-78b7-5906-8898-c22f3003f102 |  | note | INSPECTORATE W/H: Type - W
label | 6111e1ad-96c9-5496-b73f-3ac2aaf9385b |  | note | INSPECTORATE W/H: Description - PQI / Core recorded with RP, lane, offset, date, air voids. Core results received within 2 weeks.
label | 637deedd-fce7-5e27-8040-e1673983cae1 |  | note | RESPONSIBLE PERSON - Quality Assurance Technician / Paving Manager
checkpoint-status |  |  | checkpoint | 4.9 - Roughness
label | 7b4112f3-17a6-5508-ae83-0a96c554deda |  | note | VERIFICATION ACTIVITY - Visual
label | 6d954057-94ac-5c64-98f7-a4d44abcae99 |  | note | METHODS OR REFERENCE - On Site
label | f5db0627-440a-5f2f-b115-875ff7bb8223 |  | note | FREQ. - Post Construction
label | bddb11ea-8723-5dfd-90ee-7ec8bd5cf409 |  | note | ACCEPTANCE CRITERIA - Agreement with WK as per M10
label | bb35f7c5-b773-575a-b1ba-4c1c63dc499b |  | note | INSPECTORATE W/H: Type - H
label | a9ee0a28-85e1-59a2-9349-7dfecbaee50d |  | note | INSPECTORATE W/H: Description - Site walkover with client to determine ability to comply with straight edge measurement outlined in M10
label | 0a727cf9-80dc-536b-b0d9-6120fc8a43f6 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Site Reinstatement / Clearance
checkpoint-status |  |  | checkpoint | 5.1 - Shoulder Reinstatement (where no K&C)
label | 15caca60-a905-573f-be95-4c6920b10d06 |  | note | VERIFICATION ACTIVITY - Measurement/Visual
label | 45216672-c7a9-5c61-91b1-e7d00b664aec |  | note | METHODS OR REFERENCE - On Site
label | 47367b4b-664f-5c9a-9a3b-cfdb59ca6b5f |  | note | FREQ. - All low shoulder created by paving edge
label | 7f7b852e-262e-5638-9192-6763e7bee5fc |  | note | ACCEPTANCE CRITERIA - Shoulders reinstated to between 1:4 and 1:6
label | b7b65852-5db5-5b83-96a6-7cec2b482df0 |  | note | INSPECTORATE W/H: Type - H
label | 0403c5b5-640c-55e2-a588-f4a99053d3d5 |  | note | INSPECTORATE W/H: Description - Low shoulder created by rural paving is corrected using AP20/40 or DG Mix. Not relevant in kerb and channel scenario.
label | 37218ca5-33c9-51fe-b13c-0906e5c99b68 |  | note | ○ Hold Point - Site TTM/TSL should not be removed until these hazards possible are attended to.
label | 0b73a066-c24e-569e-9921-ce61ae1f0324 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.2 - Post-seal Area Check
label | 2d25172a-b7c4-5520-9235-c69036b7b7e3 |  | note | VERIFICATION ACTIVITY - Measurement
label | 9c7e5021-0143-5089-91cd-4dcb8eb61155 |  | note | METHODS OR REFERENCE - On Site tape- measure
label | e4e01d28-cbf9-50dd-aa22-ce21862caf7b |  | note | FREQ. - After Surfacing
label | 7988876f-bbce-592d-890e-a5ef0a67ec28 |  | note | ACCEPTANCE CRITERIA - Check sealed area meets design
label | 65990c8c-583d-5ceb-9bab-85fd4321a75b |  | note | INSPECTORATE W/H: Type - W
label | d5730895-dad7-5d3e-afe9-d153ceffcdf8 |  | note | INSPECTORATE W/H: Description - Notify Renewals Engineer or Renewals Manager
label | c1704930-7dfd-52e6-bfe5-f1200a674285 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.3 - Service Covers
label | 998bddc9-262c-581c-85df-dc32dee633ef |  | note | VERIFICATION ACTIVITY - Measurement/Visual
label | f95b4344-dd76-563d-a0e7-55f6365eedbb |  | note | METHODS OR REFERENCE - On Site
label | ce6fc2d2-c719-5bb9-a20c-ea7b088fef64 |  | note | FREQ. - After Surfacing
label | f2160c2b-b956-583b-9860-8ed424ecc46a |  | note | ACCEPTANCE CRITERIA - All service covers are checked and adjusted (if necessary) to finished level (+10mm, -0mm)
label | f2c6f5f6-a5a6-50ea-a734-a9d568270405 |  | note | INSPECTORATE W/H: Type - W
label | 8b3d095b-f33d-5d4b-9325-320518c434c1 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.4 - Joint Sealing
label | c5735102-0291-5b95-880f-47d9a156ea81 |  | note | VERIFICATION ACTIVITY - Visual
label | 5c93b19a-c614-5cb0-b408-cd5151dec855 |  | note | METHODS OR REFERENCE - On Site
label | 36cbac95-73db-5c48-b165-28894201e513 |  | note | FREQ. - After Surfacing
label | d007ee31-699b-5ef1-a1ba-4bcbf4b45250 |  | note | ACCEPTANCE CRITERIA - Check cold joints are bandage sealed
label | 39c75b70-9afc-543e-9916-2ea2c60ff75c |  | note | INSPECTORATE W/H: Type - W
label | 3f40b444-eec2-5933-be95-0bd81cddc2b4 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.5 - Road Marking
label | 8bbe1737-0a4d-531a-9b25-b7e21e9d493e |  | note | VERIFICATION ACTIVITY - MOTSAM
label | 715c4abc-5f98-509c-a151-57605ab8aea6 |  | note | METHODS OR REFERENCE - Visual inspection
label | 652eb17f-1e1e-5940-88c3-f845eff22091 |  | note | FREQ. - All markings
label | 42e0ec88-a690-5be5-8951-561f611aebd1 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, or per design
label | 43d35fca-a39b-5fe5-9749-78f9816ef456 |  | note | INSPECTORATE W/H: Type - H
label | a2c27fad-b44d-5b1a-878a-3778a4b3a44b |  | note | INSPECTORATE W/H: Description - Hold point – Site TTM cannot be removed until markings reinstated
label | 354330fd-feca-5362-9349-f5960b5fdee6 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.6 - Other Traffic Services - Marker pegs/ Signs/Markings/RRP Ms Replaced
label | 757e5a64-d5c9-58c5-b8da-0d0f5bcc1cb4 |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | 866a47fd-c5b0-556c-aa7c-d8f89bc0e9d4 |  | note | METHODS OR REFERENCE - Visual inspection
label | a48a4e7e-2b0c-53e4-a8c2-ef643abb3257 |  | note | FREQ. - All signs/markers
label | 4564668b-02fe-5a3f-90a7-0485fbb6747c |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | 0c4e32cc-a03f-543d-9e7d-9fe602926b04 |  | note | INSPECTORATE W/H: Type - H
label | 269d0361-515a-5d47-853b-755b01526f45 |  | note | INSPECTORATE W/H: Description - Hold point – Site TTM cannot be removed until marker pegs, signs, markings and RRPMs reinstated
label | 4103e00c-7233-5f5e-8620-6d649f7ba098 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.7 - Stormwater Management Controls removed
label | 66aaea87-4c65-5676-8395-13dd26271692 |  | note | VERIFICATION ACTIVITY - Visual check
label | 700feddc-5cdc-5238-8f88-bbc2f2374081 |  | note | FREQ. - All installed measures
label | 9b0c984f-8b64-5762-983a-fca23ccb1ec3 |  | note | ACCEPTANCE CRITERIA - Installed controls are removed
label | ad59f9cb-e00c-5991-a8f3-bea88e0ed324 |  | note | INSPECTORATE W/H: Type - H
label | fcb945bc-9161-5aac-ac03-3d059f82dda6 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.8 - Traffic Management Removed
label | 63875070-1c3f-541c-bfb0-a134710ee718 |  | note | VERIFICATION ACTIVITY - Visual check
label | b10ae159-e028-5972-b4cc-a6836c24ea49 |  | note | FREQ. - When safe, after all physical works completed
label | 5f6a7e57-7b0e-5bb8-ae97-6a0cbc00ea94 |  | note | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | 948c8599-7be9-5a1b-8776-f412a2728c4c |  | note | INSPECTORATE W/H: Type - W
label | 178a2b92-466c-5c15-b51c-7eed48ed7090 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.9 - Site left clean & tidy
label | 78bfdb33-669e-531b-a9b8-b0e99d340404 |  | note | VERIFICATION ACTIVITY - Visual check
label | feba8cd5-e7d2-5a00-9ab0-266042786376 |  | note | FREQ. - After vacating site
label | 6287beff-5d87-5479-9a34-f83603884330 |  | note | ACCEPTANCE CRITERIA - Stockpiles removed, Plant removed, Litter cleared from site
label | dbe1ca4f-8b8d-5d75-becf-103e57d4ac0f |  | note | INSPECTORATE W/H: Type - W
label | 6697cbba-fd5f-5072-b0d5-a1f8ebe12acb |  | note | INSPECTORATE W/H: Description - Invite NZTA to carry out joint site inspection to inspect site.
label | 86c27a27-ed29-5b4c-8ed5-6c9cb3d76998 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-group |  |  | section | As Built Records
checkpoint-status |  |  | checkpoint | 6.1 - Collect asset data
label | 49fb6e02-7556-5b9e-b90f-2f12ba27f593 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | d2d857b3-eafb-5157-b651-3bd09baed528 |  | note | FREQ. - During construction
label | bb6abdc2-97c9-5a2e-afc2-1fc6766c7044 |  | note | ACCEPTANCE CRITERIA - All relevant as built information collected.
label | fb3c4b01-c8a4-566d-99ea-6ad9192c53bd |  | note | INSPECTORATE W/H: Type - W
label | c56a3ff7-cd69-589d-9e28-7844a3023777 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 6.2 - Enter asset data into RAMM and/or register(s)
label | ca8c979a-8769-522c-8142-187fa9258907 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | 2411ef54-1e64-542c-b3a9-77737efb7263 |  | note | METHODS OR REFERENCE - RAMM
label | ef53ae45-569d-5956-8a0c-3e16b9626c62 |  | note | FREQ. - At completion of work.
label | f562167c-d772-547b-a46d-2691d487372e |  | note | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.
label | 3c5744c3-ad3f-57d5-ab30-9f4118eed793 |  | note | INSPECTORATE W/H: Type - W
label | dc36181d-3633-5334-af41-043ab2eaf552 |  | note | INSPECTORATE W/H: Description - Data entered by 20th of follow month after month of completion
label | 3f91d134-c4fe-52a0-b709-5071770dea7b |  | note | RESPONSIBLE PERSON - Asset Information Manager
checkpoint-status |  |  | checkpoint | 6.3 - Construction Completion Report
label | 98205ffb-8dac-5e25-b4aa-1f36043cab41 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 318c6d96-2ff6-5ff1-88d2-6f0924a82748 |  | note | METHODS OR REFERENCE - Contract Specification
label | a95f013b-266b-5c63-9f79-18238ecc6775 |  | note | FREQ. - At completion of work.
label | 9262284a-5853-5336-8bed-28b6a92b6252 |  | note | ACCEPTANCE CRITERIA - Checked and approved
label | a0b50861-ed82-5330-b53d-308303d5620a |  | note | INSPECTORATE W/H: Type - W
label | 8c3a8e24-a003-57cd-ada6-d0be8afe37e2 |  | note | INSPECTORATE W/H: Description - Completed within two months after Paving Wearing Course
label | ddada75c-76e1-53e4-948c-f03fd2d79158 |  | note | RESPONSIBLE PERSON - Renewals Engineer/ Renewals Manager
checkpoint-status |  |  | checkpoint | Quality Assurance Close Out by:
text | dc899b89-97ae-57e5-9c6d-7b4ef25cb4ed |  | textbox | (name):
date | 713b69bc-92e2-55dc-b433-e50185d30855 |  | date | Date:
label | 118b348b-6323-5b38-b710-5a9096bf58aa |  | note | This record to contract file.
holdpoint |  |  | signoff | (signature)
checklist-sectioned |  |  | checklist | SNOC ITP Wreys Bush 3 - 670584 ITP v1.1 | itp |  |  |  | Yes | SNOC ITP Wreys Bush 3 - 670584 ITP v1.1 | 9c519232-d606-45de-9e11-bc711a8d33be
checkpoint-group |  |  | section | Preliminary and General
checkpoint-status |  |  | checkpoint | 1.1 - Construction Programme Completion
label | 39795f06-7b3b-568d-a8e6-916c696512a1 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 29c2f373-868f-58cd-969e-3d219fc095f6 |  | note | METHODS OR REFERENCE - Best Practice Contract Specific MMP
label | a272b3c0-5c4a-50ae-8cb4-eb62bb6a46ce |  | note | FREQ. - Before work commences
label | 24921ff7-cc49-5957-b749-fbe127d8298a |  | note | ACCEPTANCE CRITERIA - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date.
label | 749f0483-899f-5d35-9c27-f5e6df7514e5 |  | note | INSPECTORATE W/H: Type - W
label | f6d34422-ce75-5996-a579-6d643ba09250 |  | note | RESPONSIBLE PERSON - Renewals Manager
checkpoint-status |  |  | checkpoint | 1.2 - Approved RQP
label | 75649a87-f457-5029-aec2-5d0bb884006d |  | note | VERIFICATION ACTIVITY - Confirmation
label | 0f5875ab-3de4-5e4d-981c-2b46941257a0 |  | note | METHODS OR REFERENCE - Contract Specification
label | e466feaf-646e-5852-b678-b1d00f560142 |  | note | FREQ. - Before work commences
label | 4d6dd317-89d4-5a14-9dad-83e6b1a0e037 |  | note | ACCEPTANCE CRITERIA - Principal Acceptance according to guidelines in appendix 6.3
label | 253269ec-6e41-5831-819b-2cd15ee85e21 |  | note | INSPECTORATE W/H: Type - H
label | f8d0d739-a2b9-5f42-98b2-70ab2e8cf637 |  | note | INSPECTORATE W/H: Description - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. NZTA to approve
label | ac10a1e5-11d7-5c1c-aeb0-63cd83e4def6 |  | note | RESPONSIBLE PERSON - Renewals Manager
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3 - Traffic Management - TMP
label | a6754014-fb68-55c1-a5ca-f0148a36fa81 |  | note | VERIFICATION ACTIVITY - Visual check
label | a2d0097c-a9e7-5d56-8845-ec4c0af8bd7f |  | note | METHODS OR REFERENCE - CoPTTM
label | 41326aa4-5e09-56b7-a9b8-760ec4431bef |  | note | FREQ. - Before traffic management set up
label | db97ac56-a553-5003-8241-73e7e747453f |  | note | ACCEPTANCE CRITERIA - TMP checked and approved Plans approved, Current EED (if applicable)
label | 024347bf-39e1-59db-a0ff-7acbf645ebf2 |  | note | INSPECTORATE W/H: Type - H
label | 16bf87c3-d197-5f06-b3d5-35d75572928b |  | note | INSPECTORATE W/H: Description - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | adca1f7d-f34f-5d31-ab7d-746fe497377c |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.4 - Mix Design Verification for all mixes Check Laydown Trials are complete and compliant
label | e6880252-b817-54d1-9fd8-c670f7dfcd58 |  | note | VERIFICATION ACTIVITY - Confirmation
label | f3cebf6d-b364-5e70-9953-d3c801effba3 |  | note | METHODS OR REFERENCE - NZTA M/10, P/11, P23
label | 80ad9b49-6542-51ed-b942-171668937c6b |  | note | FREQ. - Before planning commences
label | 24749f35-5cb8-59e5-bfe1-28f63f92ed64 |  | note | ACCEPTANCE CRITERIA - Mix Design compliant, current and relevant. Batching plant production capability is confirmed
label | 74e946b8-12ca-51ee-a9e7-2c56322cfc26 |  | note | INSPECTORATE W/H: Type - H
label | 72903257-a0df-5ccd-b63f-59dbeb1e5c30 |  | note | INSPECTORATE W/H: Description - Hold point - No planning of on-site works shall commenced until the mix design is verified.
label | eb66585d-9ddb-55f1-94ba-453d771b6aae |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.5 - Notification of intention to start work
label | 61d495af-1a17-5780-a192-ceee7c279b99 |  | note | VERIFICATION ACTIVITY - Notification
label | 73613748-931c-5341-9f13-f5f3bae8c52d |  | note | FREQ. - Before work commences
label | 4342a87f-34d6-5cd2-bb58-0544fa45f08b |  | note | ACCEPTANCE CRITERIA - Letter drop to local residents. Greater consultation where required
label | 592c73a9-6e61-5973-9622-cca2fa964cc0 |  | note | INSPECTORATE W/H: Type - H
label | 52faebdc-4f33-5e8c-a224-fb7355b690ff |  | note | INSPECTORATE W/H: Description - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | dbb34191-7a38-586a-ba6e-7030defec121 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.6 - Works Extents
label | 77e5694a-736d-5fa2-bdf0-bec06ffe026d |  | note | VERIFICATION ACTIVITY - Confirmation
label | fe0b024b-3c72-54b5-81b8-bc51142eea05 |  | note | METHODS OR REFERENCE - Site Visit
label | f1f04402-3a67-52cd-9c73-f7913c81483c |  | note | FREQ. - Before work commences
label | 006339ab-60fe-5367-8ade-13a727170b2f |  | note | ACCEPTANCE CRITERIA - Renewals Manager and/or Client to agree extents of project
label | 1e1cc60a-be0f-5f1e-8c4a-4cbe063cc308 |  | note | INSPECTORATE W/H: Type - H
label | 10999f1f-5246-58da-a591-58ca310e0f5a |  | note | INSPECTORATE W/H: Description - Hold point - Walk over site with Renewals Engineer and/or Renewals Manager and/or NZTA
label | a45eeef1-8318-5287-a987-a5599e401a8e |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.7 - Pavement Marking Records
label | ea970682-f0ed-5370-8996-ca8b68d43c70 |  | note | VERIFICATION ACTIVITY - Measurement Data
label | e3ff2b99-4576-596a-92eb-aab7d7248afd |  | note | METHODS OR REFERENCE - Site Measure or Video Viewer
label | 174a5936-9799-5302-b728-21f66dfdefff |  | note | FREQ. - Before work commences
label | 7a24a90b-7c13-5763-9cd1-6780f5a3e099 |  | note | ACCEPTANCE CRITERIA - Measure existing markings to aid reinstatement
label | 196d0584-3f6c-5a54-8684-182b20bbb423 |  | note | INSPECTORATE W/H: Type - H
label | 4d3b4655-c5bf-52a9-a3da-e5258ce66a83 |  | note | INSPECTORATE W/H: Description - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | fed0589d-b1e1-5b5f-8b0f-e2a50a7f5e83 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Milling and Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | 9e49aefd-8f36-55d3-a323-b978842ff297 |  | note | VERIFICATION ACTIVITY - Visual plan, BeforeUDig Cable locate (electronic or pothole for line & depth)
label | 8aba8239-a3cf-525a-86e0-531e8ae41fd4 |  | note | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | cb7a2768-b62d-54ca-bc33-f7d72197dd7e |  | note | FREQ. - Before work commences
label | 25e5af75-8b82-5a26-9356-0351bb977245 |  | note | ACCEPTANCE CRITERIA - Zero service strikes
label | c4618454-6055-54e4-91f4-e82f87ae2327 |  | note | INSPECTORATE W/H: Type - H
label | 98fc451e-75d3-5852-b269-f3385f07ebe5 |  | note | INSPECTORATE W/H: Description - Hold point - No excavation/milling is to be commenced until services are located and accounted for
label | bfb1063f-bac0-597e-b86d-e758466d4d72 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.2 - Stormwater Management
label | 45305b5d-4e78-5640-bd63-d834ce4c6441 |  | note | VERIFICATION ACTIVITY - Visual check
label | 134bf634-1dc9-5bc5-b5cf-e97937136bff |  | note | METHODS OR REFERENCE - On Site
label | 3b966a21-e439-51b3-9b5e-8c948e6e7939 |  | note | FREQ. - Before work commences
label | dc3109b9-c2b8-5bc3-bc1b-bf064243aaf7 |  | note | ACCEPTANCE CRITERIA - Mudtanks bunded or filtered to prevent mix from dropping in or runoff entering
label | f19410fd-de81-5603-a9df-73caf6d24f68 |  | note | INSPECTORATE W/H: Type - H
label | 4dcf7080-9910-5e79-905e-ea8ce8e7f6fe |  | note | INSPECTORATE W/H: Description - Hold point - No work to be commenced until protections in place
label | 46fb5710-c73d-5630-85e1-9b4cba049ecf |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.3 - Traffic Management - Setup
label | 406d4cb8-f589-5475-98ff-6692301b3328 |  | note | VERIFICATION ACTIVITY - Visual check
label | ee988b55-7adf-5084-a271-58f193891e90 |  | note | METHODS OR REFERENCE - Traffic Management Plan
label | 6c6975b4-d7be-5c21-9935-5e28daf1d951 |  | note | FREQ. - Before work commences each day
label | 3d252dd5-57cc-58a2-a217-7d0ca977d8c3 |  | note | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | 448bae74-5948-5986-8d9a-2802c23d9702 |  | note | INSPECTORATE W/H: Type - H
label | b0062f08-4093-5436-a65a-acba2ddb12a1 |  | note | INSPECTORATE W/H: Description - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | f0de2036-8416-51e9-8240-c802dc4f46e9 |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.4 - Milling Depths
label | bc19e6f8-c316-52f9-8892-052f847cadba |  | note | VERIFICATION ACTIVITY - Measurement
label | 3c7d94f2-3e13-564e-8d36-cd13321d3ca4 |  | note | METHODS OR REFERENCE - On Site
label | 07c3def6-609b-5092-9a8c-9c26dc45e731 |  | note | FREQ. - Measure each side of milling machine cut
label | 50c5b80c-f667-5fa9-9f07-d7707d5b832e |  | note | ACCEPTANCE CRITERIA - Every 10m. Depth matches target
label | 2ed719dd-c146-5de8-a6c3-6271064628e5 |  | note | INSPECTORATE W/H: Type - H
label | d88efa6c-a093-5ace-a6a6-92303e5f6086 |  | note | INSPECTORATE W/H: Description - Milling String Sheets or photos of depths taken and uploaded to CONQA
label | 152b94bb-bd72-5cbe-af38-2634986c40c3 |  | note | RESPONSIBLE PERSON - Site Foreperson / QA
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.5 - Service Covers Preparation
label | 8efc74c4-dde4-538e-b003-2c4e1617f8d8 |  | note | VERIFICATION ACTIVITY - Visual
label | f0c2c9e2-6e5b-552f-9a0d-637835fed112 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | b036eef4-2336-5c7e-ae69-3431c668eede |  | note | FREQ. - All Covers
label | 99e23965-c431-5ecd-88ea-18c282bc83f7 |  | note | ACCEPTANCE CRITERIA - Hand excavation around ironwork and adjustment to desired level (if required)
label | 081f083a-368a-5dc5-ba2d-9aaf4190bf4a |  | note | INSPECTORATE W/H: Type - H
label | effbd5fe-2719-5e19-b5ed-1edb73fcabdf |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.6 - Additional Surfacing Preparation
label | a695d6a0-7dfc-5527-922c-7ef82473a08c |  | note | – Side Roads
label | 0d58af08-7c49-5462-a1d0-9781b06678ea |  | note | – Accesses
label | 284b14e0-b105-582e-8f6c-2cfa224dbdc0 |  | note | – Driveways
label | af2fb3cb-ad23-5fd3-9ec2-58aaddf9d784 |  | note | – Dish Channels
label | 3f76f27d-4134-5243-98c9-4d11262721fd |  | note | – High Shoulders
label | 832293eb-b9bb-56f0-afd6-3e7736ff4fef |  | note | VERIFICATION ACTIVITY - Visual Check
label | dcd6587c-43e0-5fce-923e-82638111fda8 |  | note | METHODS OR REFERENCE - Per Design
label | 995bae86-66b6-59a4-8e02-202cd40a43ff |  | note | FREQ. - Before Membraning and Paving
label | 732b3f9b-ff38-575d-9427-a68a5aed58b3 |  | note | ACCEPTANCE CRITERIA - Have all areas of additional surfacing on the design been prepared, membraned and marked for paving?
label | 50d6fa6e-cccb-5750-8373-bdb4699f6b95 |  | note | INSPECTORATE W/H: Type - H
label | b8043933-e7f2-5001-bd3c-88e2acd57ba3 |  | note | INSPECTORATE W/H: Description - Hold Point – All areas planned for AC are prepared ready for surfacing layer
label | 5e161212-933a-52dd-8f33-bbeac10eff9e |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.7 - Milling Surface inspection / walkover
label | 300dc8e7-e039-5eb5-832e-4e537577ccd1 |  | note | VERIFICATION ACTIVITY - Visual Check, proof roll with loaded truck to check deflections
label | 073ff61c-6630-5752-9939-dbe44938f26c |  | note | METHODS OR REFERENCE - On site measurements & photos
label | cd626a52-ac33-55bd-84a0-62313f1571af |  | note | FREQ. - Prior to surfacing
label | ab7c342e-9e83-5f74-b61e-fbe967350c66 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree if any additional overmilling is required
label | bdfed42e-8bda-51f4-96fa-09503e552728 |  | note | INSPECTORATE W/H: Type - H
label | b2a4c36c-4ffc-5a83-9fa7-7771c9a55133 |  | note | INSPECTORATE W/H: Description - Hold point - Inspection and agreement by NZTA
label | 935ca9da-dc7f-52f3-b9ff-6f7f0fbf38fa |  | note | RESPONSIBLE PERSON - Paving Supervisor / Paving Manager
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.8 - Over-Milling
label | bdb67dcc-75e6-5414-b991-58ff198c0bda |  | note | VERIFICATION ACTIVITY - Measurement
label | 9153e4b9-2296-5333-85e4-0e9bf6279054 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | f6e37ada-8dd7-57e1-82a4-ef31f3f15c29 |  | note | FREQ. - Prior to pre-level
label | 94d0f5f6-16d1-5cfd-abd6-8de57e50f376 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree need and extent of over-milling and infill.
label | 7d2580fb-7b46-5367-9e0d-00fef26b5d7c |  | note | INSPECTORATE W/H: Type - H
label | a69d23ef-37a9-5f0f-b410-c6bbc79f55f2 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.9 - Pre-Level
label | 7e7801b6-18b7-59ba-9e22-53a5d5f66119 |  | note | VERIFICATION ACTIVITY - Measurement
label | 054bd257-b064-5bf3-8946-8e48814b8fea |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 899db04a-fc34-5506-9fd2-cd02443d6aed |  | note | FREQ. - Prior to surfacing
label | e1b27df6-50b1-5683-9999-0c684993d60f |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree pre-level extents
label | 367a1e8d-8c91-5e97-9f80-d04a8d74c6d6 |  | note | INSPECTORATE W/H: Type - H
label | 968e2c1e-ce3f-5e0e-85d5-aa6b2ddcdec8 |  | note | INSPECTORATE W/H: Description - Hold point - Inspection and agreement by NZTA
label | 002ffa64-458c-54fc-956d-4924619228df |  | note | RESPONSIBLE PERSON - Paving Supervisor / Paving Manager
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Paving Structural
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | 49ef01ae-d694-52bd-aa6e-c2817c1d3054 |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | 33cf0f6c-2445-58f7-b102-d456b37a39a5 |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | 24f07e06-85e0-52ae-89ab-045186b79169 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 3670e670-9f83-57c5-b846-b6f3ec772bc6 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 2e00853b-8d84-543e-a192-febf7b521801 |  | note | INSPECTORATE W/H: Type - W
label | 1d09d369-13a9-5959-ab7b-a6ec45ffd995 |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | fff1be91-3bf2-53fc-ac8e-649d10b25fcb |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | 545d1ed9-5b55-5d04-93e4-eae7322ae45b |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | d224cdc8-eef4-5cc9-8d57-9aa305cffa58 |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | c373c080-3bf2-5e08-a20c-942910e59822 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 1cd0794a-1721-5c39-972c-9adbe96db0e8 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | b7f76918-d929-53ec-9c99-257d29fe43af |  | note | INSPECTORATE W/H: Type - W
label | 9437ea9e-7705-516e-a72e-0a7e3b5b9ad8 |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | 9f41cc17-9881-584f-9c8b-bee3c8f76f88 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | 05c90913-277f-5829-970c-812ada015f27 |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | 389c4f6a-ea60-5964-8dbd-b4212216429d |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | 8231f00d-01d5-5e81-9635-1eaa282eb307 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 8b42906f-7773-5c21-b530-21b28d3f3e35 |  | note | ACCEPTANCE CRITERIA - Per Mix design
label | 0db4cba6-3dbb-5c7f-ba32-732977c6076e |  | note | INSPECTORATE W/H: Type - W
label | 529f3d18-aaa2-508f-98c3-b3953eb35eec |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | a7d153c6-428a-55a3-af29-f1e7c9b351b0 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | 2a8f5935-6833-5ec4-a18e-1d3447acf53f |  | note | VERIFICATION ACTIVITY - Visual
label | 14d2b0fb-d182-5f89-ba30-27bb48537969 |  | note | METHODS OR REFERENCE - NZTA M/10
label | cae3fb3d-c917-51d4-9b4a-ca5879a0c162 |  | note | FREQ. - Prior to Shift
label | fe824b43-6639-5e31-9837-33090c214211 |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | 2ba5c627-8cd6-575e-91ec-45aa06125ac0 |  | note | INSPECTORATE W/H: Type - W
label | fd5cdb7f-7a8a-5d85-b40d-c0ec4800d121 |  | note | INSPECTORATE W/H: Description - Paving Plan and Crew Briefing Plan completed prior
label | 8de4f3b4-ba09-5932-a184-5d417ced696e |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | 2f5d6a6b-0083-544e-8352-ef9a111c1d06 |  | note | VERIFICATION ACTIVITY - Visual
label | 3249b1e9-e9f6-54d5-af26-5532b4986326 |  | note | METHODS OR REFERENCE - NZTA M/10
label | a352d2be-3db7-55e6-bccd-a26a8e97819a |  | note | FREQ. - Prior to Shift
label | 0cf94fcb-9264-548e-a2ec-48422174dad4 |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | 53fdde72-0f75-5826-8209-3ce922aff06e |  | note | INSPECTORATE W/H: Type - W
label | 654e01e6-83ce-569d-b062-4be5514fa80e |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.4 - Mix Inconsistency and Deficiency
label | b39c0f09-fd0e-5c26-acb5-8cfa8e563e22 |  | note | VERIFICATION ACTIVITY - Visual
label | 7893af11-a6d7-5536-8f0c-8e122ca42d28 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 3602b918-6122-50dd-bac2-a49faa68ff62 |  | note | FREQ. - Continuous
label | c47bdbf2-342f-56d3-b2fe-6f921c3f86ba |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | c311f0f6-6881-54b2-8798-8560077b1918 |  | note | INSPECTORATE W/H: Type - H
label | 9e8db13e-ca88-5ae6-8525-5761c215bdc2 |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3.5 - Load Locate
label | 61be3ba5-6a49-570a-8083-110cca566f75 |  | note | VERIFICATION ACTIVITY - Measurement
label | 5802eebd-b8b0-581a-80e2-5fef9c33304a |  | note | FREQ. - Every Load
label | db2f6e61-b892-504d-b61c-337442cdc88d |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes:
label | ce7a1f00-9a33-5903-b811-82a3eef0a3c7 |  | note | – Truck ID/Rego/Driver
label | 60c4339a-918f-584e-aec3-3fbc535ac766 |  | note | – Depart Plant Time
label | 021db9ec-2a23-5d43-8090-096d26a254bb |  | note | – Arrive Site Time
label | 7a1ec7e6-c390-53a9-891f-75a6bf8299b6 |  | note | – AC Temp on Arrival
label | dc7eb477-57c8-50de-bd2a-3ba235c5fec7 |  | note | – Ground Temp on Arrival
label | 019819cb-a462-5f62-befe-783d7f33a3c1 |  | note | – Tonnage
label | 93043d89-8b79-5439-8248-15008e8d26f1 |  | note | – Run Width
label | 4a3b7949-1416-5f32-9678-5aa858fb2abf |  | note | – Estimated Run Length
label | ed1e95fc-e99a-5e84-a5d3-91d31c634af2 |  | note | – Calculated Area
label | 54065d5d-780c-59d6-887d-87daa6902d7d |  | note | – Calculated Average Depth
label | d2c667ad-43ba-5ba5-af15-21f5366d12ae |  | note | INSPECTORATE W/H: Type - W
label | b4e10bab-44ca-5091-b5ad-230f27ddca05 |  | note | INSPECTORATE W/H: Description - Per standard practice
label | 08274319-602b-5817-bf62-77481610547e |  | note | RESPONSIBLE PERSON - Quality Assurance Engineer
checkpoint-status |  |  | checkpoint | 3.6 - Laying Temperature
label | c0c65fb0-5ad4-54b1-9aa6-c51a35c962d6 |  | note | VERIFICATION ACTIVITY - Confirmation
label | f2d61dbd-6ee4-5263-b9b1-0d3765452833 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 90a477e8-4902-5105-b216-2e96d5a4d092 |  | note | FREQ. - Every Load
label | 3eabffa9-5e0f-5adb-ad3e-6a39ac39b050 |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | 14a10a55-3f41-5a9e-a5fc-20a2bf5f7d70 |  | note | INSPECTORATE W/H: Type - H
label | 88d0b7eb-1646-5f3e-9565-275ee3c6a049 |  | note | INSPECTORATE W/H: Description - Hold point - Reject mix for non-compliant temperatures.
label | 728d58d8-02bd-5b06-b90d-b2e2cb500ef5 |  | note | RESPONSIBLE PERSON - Quality Assurance Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3.7 - Compaction
label | 9456da8b-f9a5-5c59-9d91-c3d9193e97a7 |  | note | VERIFICATION ACTIVITY - NDM Testing
label | adde61ad-edd6-5fcb-b52f-73f0697fc236 |  | note | METHODS OR REFERENCE - NZTA M/10
label | c7a51ce4-8c18-5a51-b34a-78ccf6b8bf0e |  | note | FREQ. - Minimum:
label | f6b8f471-0341-59bd-b46f-d563b48de381 |  | note | ○ 1 Test per 300m² within Mat.
label | ee2cd49d-6a07-5ec0-bdc9-18e33510cf32 |  | note | ○ 1 Test per 100m of joint.
label | 6e6d759d-756b-58d6-96d3-1eaac26cc0d7 |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | 1daa0d05-f171-518d-9a2d-3ddd53fce4c5 |  | note | INSPECTORATE W/H: Type - H
label | baf8582b-557d-5e16-b26d-bf6825d56d12 |  | note | INSPECTORATE W/H: Description - Hold Point - No Wearing course paved until any non-compliance is sorted. PQI / Core recorded with RP, lane, offset, date, air voids. Core results received within 2 weeks.
label | 14fc1323-e5b7-5925-9b20-62f21d83bfb8 |  | note | RESPONSIBLE PERSON - Quality Assurance Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Paving Wearing Course
checkpoint-status |  |  | checkpoint | 4.1 - Production Properties - PSD (Particle Size Distribution)
label | a842cc91-cd4b-5aae-b8c6-c8ac689c32d8 |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | 05ea7a5f-e91f-5253-a7ea-e0f33474ad43 |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | 1b5f5f41-686f-5790-8fa8-dfdeee044187 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 39015779-b071-506d-b6df-243607eb84f4 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 85da71b2-cb9c-5098-b61f-e3539a466564 |  | note | INSPECTORATE W/H: Type - W
label | dd05a0ec-dbe3-5fc1-b0a2-5d07a49c74e4 |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | e229b29c-6886-54b2-afcf-725a7f46d4d1 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.1 - Production Properties - Binder Content
label | 0074cd3e-eacb-5b09-b639-f60a3d67d443 |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | 65ad5a68-e987-5568-9036-67aa49bc03ec |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | db9409a8-3cde-5e29-b734-42b3c045034b |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 9f640cf8-90aa-5082-9f2e-a4eb0c17eda0 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | e10864f6-587f-501b-b0d3-2483fadc0eb2 |  | note | INSPECTORATE W/H: Type - W
label | a3153181-ae5b-5c4f-99dc-2ace2397d2d6 |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | a69a16e7-5d14-580f-9467-ef163397f7a6 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.1 - Production Properties - Maximum Specific Gravity
label | a18854e3-c398-5971-8ef5-48f315b24e83 |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | a7161ad4-4719-5b70-8d7b-1e5be21b02ce |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | 6ae04c73-927c-5bb1-802c-185192055702 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | c8c9abc8-431f-50c0-aea0-e62a6df2a6ac |  | note | ACCEPTANCE CRITERIA - Per Mix design
label | 6901ec2e-251e-5d26-b014-c1b28dd8da58 |  | note | INSPECTORATE W/H: Type - W
label | 36683d1f-766d-5f5e-979e-9d29c9e21d84 |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | bbd0cf56-0e95-5d32-b60c-8dfecdbc7e6f |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.2 - Preparation
label | 371a861e-ace1-5526-a698-652551f67373 |  | note | VERIFICATION ACTIVITY - Visual
label | 99812769-3e9d-5759-8d9d-df8b7d204d80 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 2e9ca223-f3f5-50a5-8307-f1a846802319 |  | note | FREQ. - Prior to Shift
label | a13ad3c2-be54-54ac-b08e-3d498099e665 |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | 37a5a9b8-3aab-5de5-96fc-d7e82ec69c3e |  | note | INSPECTORATE W/H: Type - W
label | 86047f83-3436-55ef-b8e0-6adebbaf1397 |  | note | INSPECTORATE W/H: Description - Paving Plan and Crew Briefing Plan completed prior
label | 52e78d24-5b67-5b36-a859-53d1ea8dc886 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.3 - Joins
label | b084b94e-c908-5e70-90e9-654285a121ba |  | note | VERIFICATION ACTIVITY - Visual
label | a19bcfb4-1941-57ae-98df-869a99d36cba |  | note | METHODS OR REFERENCE - NZTA M/10
label | b74d3038-74d6-5ec8-8778-1111a2ff8465 |  | note | FREQ. - Prior to Shift
label | d15f18db-267f-5b2b-a0ef-65e4f3679c4f |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | a92d7837-b2ee-5141-b3d3-3d904fa7133b |  | note | INSPECTORATE W/H: Type - W
label | b5691391-c428-5fb3-926c-74b8efc56174 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.4 - Membrane Sealing
label | d44d0fdd-901a-5574-9e94-16975d5b8da6 |  | note | VERIFICATION ACTIVITY - Visual
label | eae0d816-3fc8-5647-ba81-493772a19a24 |  | note | METHODS OR REFERENCE - NZTA M/10
label | e959012b-d4ab-5a4e-a618-44640d3bdad6 |  | note | FREQ. - Prior to Paving
label | dd239488-4dc1-509a-94b7-0d3d6e6f15c1 |  | note | ACCEPTANCE CRITERIA - Membrane seal meets design and extent. Sealing Docket record kept
label | 2fdbb7e3-f1f4-5444-ad48-6659826a0b4a |  | note | INSPECTORATE W/H: Type - H
label | a272d75f-3a6c-5298-bc56-ba3f85453450 |  | note | INSPECTORATE W/H: Description - Hold Point - No paving until Membrane Done. Ensure correct application of chip & emulsion
label | dc80dd55-0d1e-55a4-8ee0-eebcb7b5f32a |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.5 - Mix Inconsistency and Deficiency
label | 96d915d6-df17-521c-872f-17a78ec77c36 |  | note | VERIFICATION ACTIVITY - Visual
label | 5d7e1b85-c0a3-5049-a941-a11aebfbbfd2 |  | note | METHODS OR REFERENCE - NZTA M/10
label | c70bb02b-bdb9-5274-945b-20c4e3930c25 |  | note | FREQ. - Continuous
label | d171d9e4-9640-5691-91be-2a469b118d9f |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | ff1f32f4-fc67-5c61-913a-e698693bf50f |  | note | INSPECTORATE W/H: Type - H
label | d57ff75d-c09e-56b6-aed4-dc32065ef3cb |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.6 - Load Locate
label | 1ba569fb-1fc2-5b98-817c-94bee73819d2 |  | note | VERIFICATION ACTIVITY - Measurement
label | b1d8a4ee-dc80-537d-ba03-4315d36efc22 |  | note | FREQ. - Every Load
label | 563ebd12-d47e-5a7b-95a0-d0d8493214e6 |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes:
label | 0eb7f029-d0e8-5a88-97b9-ed006b5561e2 |  | note | – Truck ID/Rego/Driver
label | d8caf900-a89e-558d-8ad2-bef1f486a71e |  | note | – Depart Plant Time
label | 5d8ffae2-40a0-5b77-9841-084a554de5ba |  | note | – Arrive Site Time
label | c30d3bc1-a117-5fff-8222-ca6d818db0eb |  | note | – AC Temp on Arrival
label | 75b0be25-2114-53e7-8ddd-01271f5f7ca3 |  | note | – Ground Temp on Arrival
label | ce867b94-c2ea-5568-8d74-52e2ba9c0b4d |  | note | – Tonnage
label | e6899cb5-ed9b-5dac-a6c8-a9f7a9baa53a |  | note | – Run Width
label | e9a00b1a-b8fa-50a9-b290-2126dbf3ba05 |  | note | – Estimated Run Length
label | ffa357e5-fc73-5fab-b80b-f6cfc00e5747 |  | note | – Calculated Area
label | 9bee5597-eac5-5dc5-aa8a-e832c8bf1942 |  | note | – Calculated Average Depth
label | 90f6dc74-e143-522f-a762-717049156f22 |  | note | INSPECTORATE W/H: Type - W
label | 8a212c0f-4414-52a6-935f-bbdabe5a2ccd |  | note | INSPECTORATE W/H: Description - Per standard practice
label | 0218980a-252f-5836-91b7-0907667e7a2c |  | note | RESPONSIBLE PERSON - Quality Assurance Technician.
checkpoint-status |  |  | checkpoint | 4.7 - Laying Temperature
label | 828c823f-b550-564e-98e3-510d0ae3a8e4 |  | note | VERIFICATION ACTIVITY - Confirmation
label | d1d493c1-d3e0-53b7-8e57-f169c153902d |  | note | METHODS OR REFERENCE - NZTA M/10
label | 1e9e1afd-3ff1-525f-b5e6-9701797082cf |  | note | FREQ. - Every Load
label | ad7a7d32-2509-5353-84af-256a7d34df59 |  | note | ACCEPTANCE CRITERIA - Based on Mix design
label | c57d7ca9-d798-5a5f-a0e6-45323dd8cfe5 |  | note | INSPECTORATE W/H: Type - H
label | 6d116904-6438-5446-9ff9-7529a1d20a6d |  | note | INSPECTORATE W/H: Description - Hold point - Reject mix for non- compliant temperatures.
label | 4904bd11-0965-5746-ad93-ae631b7eacc1 |  | note | RESPONSIBLE PERSON - Quality Assurance Technician
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.8 - Compaction
label | cc407ccc-450a-5a79-9c73-df88881b55ed |  | note | VERIFICATION ACTIVITY - PQI Non-Nuclear Gauge/Cores. Or Non Distrctive Method Testing.
label | 3e79dbba-f7f3-507a-8176-00b96bd000e1 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 82c50981-0a4e-500d-880a-5322b993b08b |  | note | FREQ. - As per Agreed on Contract.
label | 3507ab6d-abc6-53b3-aa71-b3678a31c7a0 |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | f1d11650-0c36-52dd-b0bd-44eecdd32cc6 |  | note | INSPECTORATE W/H: Type - W
label | b7b605df-f181-5279-a558-f1ba616ad6b2 |  | note | INSPECTORATE W/H: Description - PQI / Core recorded with RP, lane, offset, date, air voids. Core results received within 2 weeks.
label | da45c340-d995-59f6-b78b-17a82b2a1cc3 |  | note | RESPONSIBLE PERSON - Quality Assurance Technician / Paving Manager
checkpoint-status |  |  | checkpoint | 4.9 - Roughness
label | e7b76492-be33-5537-8821-760528db91b4 |  | note | VERIFICATION ACTIVITY - Visual
label | 503d5c03-e1d6-5344-a830-0a59accce5c5 |  | note | METHODS OR REFERENCE - On Site
label | 45f15443-6809-5314-b5c6-0cc4e5e6ced6 |  | note | FREQ. - Post Construction
label | 2604c364-c7cc-5fd3-b9e5-554294fb793d |  | note | ACCEPTANCE CRITERIA - Agreement with WK as per M10
label | 06f6e711-bc60-5ba6-8773-5d5653885644 |  | note | INSPECTORATE W/H: Type - H
label | 4191d2f8-cc6e-5d59-a2c5-82653264780a |  | note | INSPECTORATE W/H: Description - Site walkover with client to determine ability to comply with straight edge measurement outlined in M10
label | ccca6dc2-cb7a-53c5-b053-ca8872ce4830 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Site Reinstatement / Clearance
checkpoint-status |  |  | checkpoint | 5.1 - Shoulder Reinstatement (where no K&C)
label | 9d641180-92ea-5b86-82ad-b9c946cc31eb |  | note | VERIFICATION ACTIVITY - Measurement/Visua l
label | 373a5941-0742-5314-ac18-3a1b267998dd |  | note | METHODS OR REFERENCE - On Site
label | fb1146cd-d167-5a47-91ac-4779f7e229b3 |  | note | FREQ. - All low shoulder created by paving edge
label | 6081267e-bcf0-542b-8ce9-2961ca7fbdb7 |  | note | ACCEPTANCE CRITERIA - Shoulders reinstated to between 1:4 and 1:6
label | c81dd6db-cad4-5a10-ae2e-7361e497210a |  | note | INSPECTORATE W/H: Type - H
label | 55cfa45c-c1ca-56bd-ab51-be4d1935fad6 |  | note | INSPECTORATE W/H: Description - Low shoulder created by rural paving is corrected using AP20/40 or DG Mix. Not relevant in kerb and channel scenario.
label | 3b4d37f2-642d-57d6-87ae-44f06a02e029 |  | note | ○ Hold Point - Site TTM/TSL should not be removed until these hazards possible are attended to.
label | c9058522-034e-52be-ab62-789005f05c50 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.2 - Post-seal Area Check
label | fb4505f7-b7d2-5d95-8de0-b96c5903d6ef |  | note | VERIFICATION ACTIVITY - Measurement
label | 8a885fcf-7f08-5b4d-9704-938cf0d8c022 |  | note | METHODS OR REFERENCE - On Site tape- measure
label | 11f6b81a-04e4-5618-9b9f-b8ddb0a1b219 |  | note | FREQ. - After Surfacing
label | 8beddebe-fa18-535f-be8b-bf2628726bdd |  | note | ACCEPTANCE CRITERIA - Check sealed area meets design
label | 76ef3603-74f7-5fbd-bbb5-6ce29edc7133 |  | note | INSPECTORATE W/H: Type - W
label | b2879f90-22dc-5c31-98f2-1c9fa9913672 |  | note | INSPECTORATE W/H: Description - Notify Renewals Engineer or Renewals Manager
label | b1c45d7c-49b7-59da-9548-ceaab1582e34 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.3 - Service Covers
label | 4123c335-4529-5c8d-9423-1e064d06a456 |  | note | VERIFICATION ACTIVITY - Measurement/Visual
label | 66570ade-b7d5-551e-ba23-4dd1eaa0dff5 |  | note | METHODS OR REFERENCE - On Site
label | 3323aea2-9561-5124-8827-a9e9ac249b47 |  | note | FREQ. - After Surfacing
label | f69598e9-8ea9-5dd8-b255-a07c707078fc |  | note | ACCEPTANCE CRITERIA - All service covers are checked and adjusted (if necessary) to finished level (+10mm, -0mm)
label | 174352ed-a5ff-5ec6-ac7a-22d6735dda2a |  | note | INSPECTORATE W/H: Type - W
label | d03ab16a-0d26-5b12-8f83-d12dcec792b3 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.4 - Joint Sealing
label | 324b2cec-c06a-5adf-8aed-6bd57633099f |  | note | VERIFICATION ACTIVITY - Visual
label | a270d607-5b5f-5cd3-837d-f76d5e4f66e7 |  | note | METHODS OR REFERENCE - On Site
label | c89076b0-4981-5e36-bb9f-f7187fc03b14 |  | note | FREQ. - After Surfacing
label | a68763e2-d89b-5a77-b0f4-c14276e3dddf |  | note | ACCEPTANCE CRITERIA - Check cold joints are bandage sealed
label | b24fea1c-6c70-5d1f-a113-2013063b9f1c |  | note | INSPECTORATE W/H: Type - W
label | 75660adc-17b5-5050-b2f8-e06fd1df8e94 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.5 - Road Marking
label | 1833f6e8-2720-5050-8d8c-5e89edcb33cd |  | note | VERIFICATION ACTIVITY - MOTSAM
label | 698b61a6-882f-595a-bbc2-b4324ce7b1d5 |  | note | METHODS OR REFERENCE - Visual inspection
label | afd42b1b-8acb-5ab0-be7f-bd8bdfd4d0fb |  | note | FREQ. - All markings
label | d608618e-3d76-54fb-8a3c-b7b1f14012a5 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, or per design
label | b647ede2-8cde-5044-aa0a-741b39d62428 |  | note | INSPECTORATE W/H: Type - H
label | acf05cd9-78d9-5019-b1e3-5e200562b6ee |  | note | INSPECTORATE W/H: Description - Hold point – Site TTM cannot be removed until markings reinstated
label | 050098b5-6707-54ce-ba08-4315564ce327 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.6 - Other Traffic Services - Marker pegs/ Signs/Markings/RRP Ms Replaced
label | 70a432f0-a4c8-5cb7-8e24-998935d94837 |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | f09b9d3b-60f5-587f-b9e2-bcdec90d9c43 |  | note | METHODS OR REFERENCE - Visual inspection
label | 5ae60fc7-c3c2-5c60-a7fd-fa47235c82d7 |  | note | FREQ. - All signs/markers
label | fa63e751-bdcb-5648-8e81-401ebfc8b096 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | 70079f4a-5943-5fb6-b759-a6e10439b8b9 |  | note | INSPECTORATE W/H: Type - H
label | cbd888c5-6ad6-51d4-b630-95700ed0e54f |  | note | INSPECTORATE W/H: Description - Hold point – Site TTM cannot be removed until marker pegs, signs, markings and RRPMs reinstated
label | 8491115a-3cad-5382-a2fa-6adbfb049c4f |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.7 - Stormwater Management Controls removed
label | d406c6fe-0faf-53f6-b18d-3306bfeeffcd |  | note | VERIFICATION ACTIVITY - Visual check
label | aa4ad0f2-16c6-5bae-baba-1e59219fabc7 |  | note | FREQ. - All installed measures
label | 98985203-2f58-5b84-9cee-d63122c59e46 |  | note | ACCEPTANCE CRITERIA - Installed controls are removed
label | 343d1fa5-cf7e-5145-971e-b2544b4742d6 |  | note | INSPECTORATE W/H: Type - H
label | 37f8faf4-e960-5b93-a231-f1b74a633382 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.8 - Traffic Management Removed
label | 0c76b22f-7b91-556f-9856-f243a621407c |  | note | VERIFICATION ACTIVITY - Visual check
label | c1488799-7df4-5d4c-908f-9b4a5e5bbed1 |  | note | FREQ. - When safe, after all physical works completed
label | 23a1432a-61dc-5414-9d8a-2973e0925bf8 |  | note | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | a71aee36-1310-50ab-8616-bb9fdbc6f8d4 |  | note | INSPECTORATE W/H: Type - W
label | fbe09d11-8b98-589c-a130-217869e0c8e3 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.9 - Site left clean & tidy
label | 69d81ab9-0df3-5203-a176-d767a8b82066 |  | note | VERIFICATION ACTIVITY - Visual check
label | 7872bdd4-b989-5592-a993-960611e1be34 |  | note | FREQ. - After vacating site
label | 16bf73b1-49e5-5519-8728-e878e0e21c13 |  | note | ACCEPTANCE CRITERIA - Stockpiles removed, Plant removed, Litter cleared from site
label | 6cab25a7-8ea2-53e8-9126-384705bf20b0 |  | note | INSPECTORATE W/H: Type - W
label | 700de866-3bbc-59a8-8a60-835b2d91b06a |  | note | INSPECTORATE W/H: Description - Invite NZTA to carry out joint site inspection to inspect site.
label | d229eb91-50a4-56ec-ab66-3eef2620aace |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-group |  |  | section | As Built Records
checkpoint-status |  |  | checkpoint | 6.1 - Collect asset data
label | db993034-8ade-5435-8d0c-b8b5e3b532f1 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | 94a690fb-35eb-5fd5-8c17-f83775055b64 |  | note | FREQ. - During construction
label | 17c84bfb-7cd6-5555-9432-c202744257d4 |  | note | ACCEPTANCE CRITERIA - All relevant as built information collected.
label | e8881e75-b207-58d0-9aca-9a158d0a6fd1 |  | note | INSPECTORATE W/H: Type - W
label | 148df961-6998-50b3-974c-fcc98784da87 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 6.2 - Enter asset data into RAMM and/or register(s)
label | 1d1d13b7-86d1-5ded-98ab-21a6988cf1e7 |  | note | VERIFICATION ACTIVITY - Enter asset data into RAMM and/or register(s)
label | 455a9b2d-7cf9-5814-944a-af0841d705ea |  | note | METHODS OR REFERENCE - RAMM
label | f0876975-1e0b-5145-8def-5b646b29763a |  | note | FREQ. - At completion of work.
label | 81651158-da92-5244-8d04-cba96fdf334a |  | note | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.
label | 4273da57-7178-52ec-b546-a631b8d986c4 |  | note | INSPECTORATE W/H: Type - W
label | 78251917-1c6e-57e8-b4ff-a4652453049e |  | note | INSPECTORATE W/H: Description - Data entered by 20th of follow month after month of completion
label | c4c00df8-11c2-5f6f-a8c7-4625bb1b794a |  | note | RESPONSIBLE PERSON - Asset Information Manager
checkpoint-status |  |  | checkpoint | 6.3 - Construction Completion Report
label | 9725fc49-cb43-52c2-98f9-1df489141532 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 796d74a9-d387-5947-a8d3-2f92136e535e |  | note | METHODS OR REFERENCE - Contract Specification
label | eb3243ff-6baa-5f3b-ab77-5913683714cc |  | note | FREQ. - At completion of work.
label | 9884187a-31cc-5701-9f06-4cd57e17c5a3 |  | note | ACCEPTANCE CRITERIA - Checked and approved
label | 1dcda007-2ecf-5ece-adf0-50584ab2ba92 |  | note | INSPECTORATE W/H: Type - W
label | 2459156b-dc6d-5674-8f6b-d11d73f650e6 |  | note | INSPECTORATE W/H: Description - Completed within two months after Paving Wearing Course
label | ef25993e-8dca-565f-89c5-31ca596fa700 |  | note | RESPONSIBLE PERSON - Renewals Engineer/ Renewals Manager
checkpoint-status |  |  | checkpoint | Quality Assurance Close Out by:
text | a9526cc9-8f09-57ea-8c8e-47e4abb8f429 |  | textbox | (name):
date | 1e35a640-39a4-5dce-abc0-ea9e891f525b |  | date | Date:
label | e2cb594d-fd4f-5102-9b7b-7336727ebf4d |  | note | This record to contract file.
holdpoint |  |  | signoff | (signature)
checklist-sectioned |  |  | checklist | SNOC ITP Earnslaw St - 670581 ITP v1.1 | itp |  |  |  | Yes | SNOC ITP Earnslaw St - 670581 ITP v1.1 | d5f39ecd-3e47-4ede-86b4-c4924fd0dafc
checkpoint-group |  |  | section | Preliminary and General
checkpoint-status |  |  | checkpoint | 1.1 - Construction Programme Completion
label | 8b65edff-32d7-5175-a68c-d0d30227c461 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 022c914c-5507-5e3a-9619-173292e80ef2 |  | note | METHODS OR REFERENCE - Best Practice Contract Specific MMP
label | 582b0b62-b0c6-5e73-a8aa-7c9facf8533e |  | note | FREQ. - Before work commences
label | 3a618549-7331-516a-af71-91a0d5a6c7e1 |  | note | ACCEPTANCE CRITERIA - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date.
label | 82138951-6070-5f84-ad71-87278a52fa8a |  | note | INSPECTORATE W/H: Type - W
label | bdf14bbc-1511-5c98-8d59-ae0696d7a926 |  | note | RESPONSIBLE PERSON - Renewals Manager
checkpoint-status |  |  | checkpoint | 1.2 - Approved RQP
label | 86588cb8-9f48-5516-b08b-e178ded115e8 |  | note | VERIFICATION ACTIVITY - Confirmation
label | d3fbcae7-6194-5ccc-a251-f669b475e091 |  | note | METHODS OR REFERENCE - Contract Specification
label | b3b3221e-ed6d-5f2c-a598-af2f74ef584e |  | note | FREQ. - Before work commences
label | bd764920-192b-5b58-8897-330cb304f1ca |  | note | ACCEPTANCE CRITERIA - Principal Acceptance according to guidelines in appendix 6.3
label | b98f4453-f53c-5318-9234-a98e6dbce868 |  | note | INSPECTORATE W/H: Type - H
label | b6c9ef88-9465-53d9-9010-0e5289ef3fab |  | note | INSPECTORATE W/H: Description - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. NZTA to approve
label | 81e076a9-5382-5182-857a-e426aaab2c62 |  | note | RESPONSIBLE PERSON - Renewals Manager
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3 - Traffic Management - TMP
label | 7332a82d-b3e3-58aa-9802-271f054da75e |  | note | VERIFICATION ACTIVITY - Visual check
label | 718c8f1a-2241-5e4a-b35f-541739b8f31f |  | note | METHODS OR REFERENCE - CoPTTM
label | 0f577260-9cb1-5939-92c1-ed09e5a16206 |  | note | FREQ. - Before traffic management set up
label | c8f74e97-d5c8-5db8-8bd5-c81d69eb0a90 |  | note | ACCEPTANCE CRITERIA - TMP checked and approved Plans approved, Current EED (if applicable)
label | 80c4efe6-d128-5dc2-b661-a830dac30bc6 |  | note | INSPECTORATE W/H: Type - H
label | 737c821c-707c-5289-ad44-23a04dddc962 |  | note | INSPECTORATE W/H: Description - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | 32728e6c-0ec9-595f-a4c3-d4e82c188949 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.4 - Mix Design Verification for all mixes Check Laydown Trials are complete and compliant
label | 8b0248bc-c3ec-5b52-bb79-ee059618b3ac |  | note | VERIFICATION ACTIVITY - Confirmation
label | 0c755d13-40b6-5821-a2ce-8b71bbd71a3c |  | note | METHODS OR REFERENCE - NZTA M/10, P/11, P23
label | de774427-2f81-5ad9-b2a0-5a2acafc862f |  | note | FREQ. - Before planning commences
label | 4bf29bba-6f9e-53ec-8725-11617cb1a1c1 |  | note | ACCEPTANCE CRITERIA - Mix Design compliant, current and relevant. Batching plant production capability is confirmed
label | 17b737f5-2395-5868-a899-cdcafd0c20d4 |  | note | INSPECTORATE W/H: Type - H
label | 3681ba46-a4d8-5d1b-b91a-230cdf9bb325 |  | note | INSPECTORATE W/H: Description - Hold point - No planning of on-site works shall commenced until the mix design is verified.
label | 24d58137-0e6c-566e-88ac-db4eaa6baa3b |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.5 - Notification of intention to start work
label | f9dac3d0-bb55-51d3-bebf-619bd599278c |  | note | VERIFICATION ACTIVITY - Notification
label | 3f17b494-bdfa-5c8a-be2e-1bf1d99418cc |  | note | FREQ. - Before work commences
label | cf236b63-49ac-523c-ac52-d4589e7b675e |  | note | ACCEPTANCE CRITERIA - Letter drop to local residents. Greater consultation where required
label | ae171bc6-2093-5f14-a021-7728c4aa6a53 |  | note | INSPECTORATE W/H: Type - H
label | 61d72f80-e8b0-555f-aa6c-c1e0a09e4bb0 |  | note | INSPECTORATE W/H: Description - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | d68229c5-42fe-58ec-a84c-f58fbb5cc46a |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.6 - Works Extents
label | e6b929e2-1045-5856-8046-f0144232c8b1 |  | note | VERIFICATION ACTIVITY - Confirmation
label | f5e2d855-af20-5f74-b159-f8e7a7c54b97 |  | note | METHODS OR REFERENCE - Site Visit
label | fa73064c-2ac7-58ed-9714-4cb846ca1786 |  | note | FREQ. - Before work commences
label | 5762f201-6f3e-5636-ab9a-8143a0806eda |  | note | ACCEPTANCE CRITERIA - Renewals Manager and/or Client to agree extents of project
label | 582ac3a0-279b-5e6f-8bc0-06c80eab0cfa |  | note | INSPECTORATE W/H: Type - H
label | 52059540-c580-5008-be98-7c31c72ac11a |  | note | INSPECTORATE W/H: Description - Hold point - Walk over site with Renewals Engineer and/or Renewals Manager and/or NZTA
label | 4f05cb51-5fbb-584d-8171-8b5c7790b077 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.7 - Pavement Marking Records
label | 0ce77178-9442-5190-8632-dc164efca19b |  | note | VERIFICATION ACTIVITY - Measurment Data
label | 1a06f2f5-2bc9-5390-80d9-f8a148476221 |  | note | METHODS OR REFERENCE - Site Measure or Video Viewer
label | 175c17d5-4495-5835-ac6e-2ea8defa8cd0 |  | note | FREQ. - Before work commences
label | 730af1c8-fce8-565a-8300-c558fc3b6dbb |  | note | ACCEPTANCE CRITERIA - Measure existing markings to aid reinstatement
label | 55b77e49-89f7-520a-9703-369b2822950e |  | note | INSPECTORATE W/H: Type - H
label | 5b87cc5e-3d87-5520-a1fd-cbf10bb92b31 |  | note | INSPECTORATE W/H: Description - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | c13a7d36-0579-5109-8bf1-b4ad366b6b0d |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Milling and Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | 9787abdf-9f88-5e6d-a40e-395a62c395a9 |  | note | VERIFICATION ACTIVITY - Visual plan, BeforeUDig Cable locate (electronic or pothole for line & depth)
label | cc29af81-061f-52ea-91f6-6672b0680818 |  | note | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | 3978e30b-bd88-5746-ba73-d41bc1bf3aa1 |  | note | FREQ. - Before work commences
label | 66b4cd9e-ba33-5e91-80e2-aa46128b410b |  | note | ACCEPTANCE CRITERIA - Zero service strikes
label | 2cd7c109-cdaa-5326-b03a-a059d9cd5750 |  | note | INSPECTORATE W/H: Type - H
label | 7deac4d2-3e3a-597c-bee4-853fe1f987bf |  | note | INSPECTORATE W/H: Description - Hold point - No excavation/milling is to be commenced until services are located and accounted for
label | 7877fdc1-a8c9-5eb1-9a55-abd30fcd38cb |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.2 - Stormwater Management
label | f3c2f581-0e89-5277-90ae-88c36c31b145 |  | note | VERIFICATION ACTIVITY - Visual check
label | fdefe2e5-0c0a-59b3-bbf3-433a5fb0f5ce |  | note | METHODS OR REFERENCE - On Site
label | efe9f602-8d40-51a8-9e2e-f4aa9db4fa08 |  | note | FREQ. - Before work commences
label | c1dc6b5f-7469-55a2-b746-8d6c0ebc9077 |  | note | ACCEPTANCE CRITERIA - Mudtanks bunded or filtered to prevent mix from dropping in or runoff entering
label | 0ba68a95-10e9-5448-9253-ae9fe8f4e28c |  | note | INSPECTORATE W/H: Type - H
label | 4d3c3fe1-6cf4-51fc-850d-2a084d76d12c |  | note | INSPECTORATE W/H: Description - Hold point - No work to be commenced until protections in place
label | d183bb1c-41b1-5308-8cad-c5d83d98fd48 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.3 - Traffic Management - Setup
label | d7c8c8e9-b70d-52ad-acab-a587ca81d306 |  | note | VERIFICATION ACTIVITY - Visual check
label | b9086739-64e5-5158-9835-f743fde1c2b8 |  | note | METHODS OR REFERENCE - Traffic Management Plan
label | 9edf7102-75a4-5cbd-8383-227b2c6ca14d |  | note | FREQ. - Before work commences each day
label | fe5d9925-94b1-5d15-830b-e360d88f72fd |  | note | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | dcedbf3c-79a2-5e2e-9093-7adb4535f496 |  | note | INSPECTORATE W/H: Type - H
label | feddfed2-c4c6-572f-99be-0861cf473bc5 |  | note | INSPECTORATE W/H: Description - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | 7c8c7a3a-7039-5630-a193-b86a57bf11a5 |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.4 - Milling Depths
label | 4756e95b-5665-573a-b7b8-558f77321ede |  | note | VERIFICATION ACTIVITY - Measurement
label | 18493f69-4af6-5e75-b1c1-1da2ea2054f8 |  | note | METHODS OR REFERENCE - On Site
label | dead4c8f-fc49-5604-9eb6-1f5941db22fe |  | note | FREQ. - Measure each side of milling machine cut
label | e5a668f3-5c29-57e4-a9c7-a0e89f0a64fc |  | note | ACCEPTANCE CRITERIA - Every 10m. Depth matches target
label | a2c2b606-786f-5eec-833c-d27bb4805dad |  | note | INSPECTORATE W/H: Type - H
label | 0b749dd2-f1e3-56e5-ab5a-3d1734df06ea |  | note | INSPECTORATE W/H: Description - Milling String Sheets or photos of depths taken and uploaded to CONQA
label | 710222c4-ac4c-5279-9adb-780182410254 |  | note | RESPONSIBLE PERSON - Site Foreperson / QA
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.5 - Service Covers Preparation
label | 9da9881b-eaed-52f1-a144-31b13a96dd30 |  | note | VERIFICATION ACTIVITY - Visual
label | 45e1b475-f292-5bf1-be6f-77e69ab806df |  | note | METHODS OR REFERENCE - On site measurements & photos
label | a91c294f-4045-53eb-8c99-4a28747e8844 |  | note | FREQ. - All Covers
label | bc09da22-d15b-526a-9131-df223f4630cf |  | note | ACCEPTANCE CRITERIA - Hand excavation around ironwork and adjustment to desired level (if required)
label | 2a67153d-698a-52aa-85b0-82475debca4c |  | note | INSPECTORATE W/H: Type - H
label | f4017152-b17e-5393-bb97-cbd3473bed60 |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.6 - Additional Surfacing Preparation
label | c8a19189-68d3-5d91-bfac-27b5f77b8111 |  | note | – Side Roads
label | 9e2e5755-5a69-58c5-a31d-602306411ea5 |  | note | – Accesses
label | 5c6e6c10-0e4f-57c4-9f7e-a75aad40beb5 |  | note | – Driveways
label | cf1a7757-aa1f-53b0-86a9-9c0912cbee0f |  | note | – Dish Channels
label | db1ced54-e54d-55f4-bcf0-690aca61a96e |  | note | – High Shoulders
label | 13eb5b72-b41b-578a-b568-59830e849309 |  | note | VERIFICATION ACTIVITY - Visual Check
label | 5fd52d0b-276b-5ad7-bd54-54e603fc74e2 |  | note | METHODS OR REFERENCE - Per Design
label | 7443ba76-8ebb-5039-892e-2a2ed2b9dd88 |  | note | FREQ. - Before Membraning and Paving
label | b15431f8-3dce-596d-a015-fdde33afce14 |  | note | ACCEPTANCE CRITERIA - Have all areas of additional surfacing on the design been prepared, membraned and marked for paving?
label | eaaad08a-ca86-5c44-a912-0572ae2cfab7 |  | note | INSPECTORATE W/H: Type - H
label | 0b334e81-f71c-5c9f-a720-e53047e019ba |  | note | INSPECTORATE W/H: Description - Hold Point – All areas planned for AC are prepared ready for surfacing layer
label | 1166f205-cbe9-5b42-abbd-ed25a1f46cec |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.7 - Milling Surface inspection / walkover
label | 005086ac-1b48-5595-be84-ba05da9de466 |  | note | VERIFICATION ACTIVITY - Visual Check, proof roll with loaded truck to check deflections
label | d02d16b9-1945-5881-a14c-e69f41c13ffd |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 84424a87-6a40-54a8-a907-d61183dcdb79 |  | note | FREQ. - Prior to surfacing
label | b4edb7d7-e55b-5513-9f26-c6d3bc4d08f2 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree if any additional overmilling is required
label | 10fff6a7-4a1e-5cce-8f9f-2e710634b085 |  | note | INSPECTORATE W/H: Type - H
label | 2485c2ef-28ad-5fd1-bf74-d6789d221bfa |  | note | INSPECTORATE W/H: Description - Hold point - Inspection and agreement by NZTA
label | f9d9bc00-23af-5cc3-b809-fb90a2686d3d |  | note | RESPONSIBLE PERSON - Paving Supervisor / Paving Manager
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.8 - Over-Milling
label | 0494a3d0-7794-573e-beea-c691e29a4297 |  | note | VERIFICATION ACTIVITY - Measurement
label | 2d5c1c43-680d-5332-846e-837cca7549cf |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 41d2795e-3673-57a0-a759-defd5999d663 |  | note | FREQ. - Prior to pre-level
label | a3223ba9-7e84-5cd2-bfd4-ffc6d9e9c970 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree need and extent of over-milling and infill.
label | e4e826d9-17e5-54d6-8c3b-69fa022c6e0a |  | note | INSPECTORATE W/H: Type - H
label | 11502f6a-0933-53f7-a04a-b072744bca58 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.9 - Pre-Level
label | 1c51c1bc-cd34-5325-94d3-66013afc5971 |  | note | VERIFICATION ACTIVITY - Measurement
label | 5dd321ea-1d44-58ab-a7b0-587825c52ac1 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | f78675c9-498c-5b6b-a01e-467ebfec14f8 |  | note | FREQ. - Prior to surfacing
label | fe023eb0-ae3f-5546-9427-6158981c138a |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree pre-level extents
label | 4b8a1a9c-d658-5945-b8ea-6b958fd73129 |  | note | INSPECTORATE W/H: Type - H
label | dcf6c892-566b-5030-a4cc-3bc87815acbf |  | note | INSPECTORATE W/H: Description - Hold point - Inspection and agreement by NZTA
label | b7c3359f-a613-58c7-af76-3c6218d12d28 |  | note | RESPONSIBLE PERSON - Paving Supervisor / Paving Manager
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.10 - Membrane Sealing
label | 54154def-d286-59b2-a795-f489730e3a16 |  | note | VERIFICATION ACTIVITY - Visual
label | 16e69622-5997-54a7-81f9-72b44d5a23fc |  | note | METHODS OR REFERENCE - On Site
label | 872a7fc7-f121-5317-b373-490ebcc0e931 |  | note | FREQ. - Prior to surfacing
label | 7c331927-e3e2-55cc-bff3-23fbfd6cdc64 |  | note | ACCEPTANCE CRITERIA - Membrane seal meets design and extent. Sealing Docket record kept
label | 98a85859-db83-5242-b209-91695633549b |  | note | INSPECTORATE W/H: Type - H
label | 71234569-8416-5d73-a274-6d9c84474c7a |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Paving Structural
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | 4b292917-c5e4-5b67-9b14-72b861afb6cd |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | 26a512b0-ca75-545d-a663-900a8def4d46 |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | c4e2e705-27cb-5f14-8474-4460956ef157 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 06a05121-cb24-54e2-a39f-d823c403a5af |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | cb9d7f7c-8489-550e-bece-00b7ae776dc4 |  | note | INSPECTORATE W/H: Type - W
label | 8c3cd90a-b8f5-53d9-adbd-77306d649b52 |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | 0fb78d71-1b6a-5e8d-a6d6-35a5fce28eda |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | 2bcb68f7-64da-5f6b-a3a9-82f13e20685c |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | 30dfe63c-d13b-5f5b-ae8d-6e48e2eacebd |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | 5733ebdb-ad8a-527a-b504-8f79622be7d3 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | cb232c0b-bde8-5f6b-904f-13e50afd4629 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | f5422589-7a9a-5024-a365-a90c9b0b95c8 |  | note | INSPECTORATE W/H: Type - W
label | d075955c-12b5-51ff-b2c8-5960444457ca |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | 053e5b53-0f8e-5517-86ba-db83e736dd03 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | 1893d4ac-c9d9-5a05-8553-d92bbc4e411d |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | 9120c788-039a-5b7c-86a6-b1050f6c6b89 |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | 75dd250b-5310-56f4-b50b-ec6b3fbf4c63 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 8e36fbe6-e4e7-5fb9-8d85-1b723ba5cb94 |  | note | ACCEPTANCE CRITERIA - Per Mix design
label | 0df5077a-ce8a-5df2-a792-dddc1c48ade1 |  | note | INSPECTORATE W/H: Type - W
label | 18ce6e21-771f-5f9c-9969-6eb0ee29f183 |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | bf1ab189-7732-59eb-b15d-650a78dba00c |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | 45941dd2-cada-5f07-9698-0aa49cf9a1dc |  | note | VERIFICATION ACTIVITY - Visual
label | 1043acfc-dca5-596f-a03b-33d9b46b9bd9 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 69af61fd-ffba-5ccf-8d9a-fff032ca5fa2 |  | note | FREQ. - Prior to Shift
label | ee634eed-13bb-5da6-8664-782911e13a9f |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | c1674b50-043d-5bee-aa56-54e482909a0d |  | note | INSPECTORATE W/H: Type - W
label | d903344a-4a6d-5e8b-97d7-62bdbf6380ea |  | note | INSPECTORATE W/H: Description - Paving Plan and Crew Briefing Plan completed prior
label | 864394b8-5397-5b01-b3f5-271c69752f82 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | 7c970778-c05e-5225-aa52-8e61db081bc8 |  | note | VERIFICATION ACTIVITY - Visual
label | bb134139-9769-5355-a784-d855586d51bd |  | note | METHODS OR REFERENCE - NZTA M/10
label | c6f96fc3-b981-50d9-8651-e0b89baf0798 |  | note | FREQ. - Prior to Shift
label | 1075ba50-a283-51cb-a24d-c66a2183fa84 |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | e9747f75-e1d3-5a90-8eb1-46f67efd6d65 |  | note | INSPECTORATE W/H: Type - W
label | 8392ee85-e261-547a-9b48-64bb025f7893 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.4 - Mix Inconsistency and Deficiency
label | 18852067-0ac1-5dc2-8660-16700414b341 |  | note | VERIFICATION ACTIVITY - Visual
label | 69b47308-9d82-5ef3-8a78-fc581d3ba80d |  | note | METHODS OR REFERENCE - NZTA M/10
label | 02c802d9-d9c7-5df7-9eb5-294d6460f855 |  | note | FREQ. - Continuous
label | f0e03003-be2d-534e-b29a-069f446b1851 |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | 43529896-ab7e-5eae-af97-d6a3ee80ecd5 |  | note | INSPECTORATE W/H: Type - H
label | 655297fb-bebd-54f8-8997-b7dace0ca3f3 |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3.5 - Load Locate
label | c13c5fe5-8183-5029-bfb7-b0a541e0bf68 |  | note | VERIFICATION ACTIVITY - Measurement
label | e0997cd0-2626-588e-96dc-8c893ccd3fcf |  | note | FREQ. - Every Load
label | c46fa772-4711-56c5-ba61-b84daef4ffb9 |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes:
label | 0e18f844-4f85-5435-9148-a29ec19ba408 |  | note | – Truck ID/Rego/Driver
label | 7cb3f84b-a31d-58ec-8667-ae7b58da00bf |  | note | – Depart Plant Time
label | aed89647-2406-5d0f-93fc-fc752bdc76c4 |  | note | – Arrive Site Time
label | 8632d308-a235-553f-abf6-a2e8d7ab5ec6 |  | note | – AC Temp on Arrival
label | 6e263f8a-d04a-5930-b633-e0504fc4048e |  | note | – Ground Temp on Arrival
label | 2756831e-97d5-54af-98d0-804ee1fd8d75 |  | note | – Tonnage
label | eea5f9ab-9dc9-5bc7-86dc-d8479d8a0338 |  | note | – Run Width
label | f0a24ab3-a21b-5d22-8aeb-b7fbf1b7c787 |  | note | – Estimated Run Length
label | 50bc0eb1-e729-54fe-92ab-ff8ba53ce790 |  | note | – Calculated Area
label | d4a60cde-f1db-5a5c-ae08-4e27b03c62d5 |  | note | – Calculated Average Depth
label | 28eca75b-be65-5f9c-ab13-25b021c307a8 |  | note | INSPECTORATE W/H: Type - W
label | 8b79771a-f7ac-56a1-b897-d66bcac31898 |  | note | INSPECTORATE W/H: Description - Per standard practice
label | 5a15df79-a5dd-599a-8cf2-4afee8fea6c7 |  | note | RESPONSIBLE PERSON - Quality Assurance Engineer
checkpoint-status |  |  | checkpoint | 3.6 - Laying Temperature
label | 7d8f8e8f-8c56-51c7-8753-b6857e01e5db |  | note | VERIFICATION ACTIVITY - Confirmation
label | b702eb0b-6084-5bd0-a5e8-08c118b50746 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 2fb1a63a-ebb5-5d92-8f1e-27e2d1859a7c |  | note | FREQ. - Every Load
label | 36656679-b513-5318-8f0f-a8dd5bd57d58 |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | 5c2ad6d6-aa91-5870-be67-2626a0ac7638 |  | note | INSPECTORATE W/H: Type - H
label | 9a14ae2f-4c93-50f5-9bc6-e13941b048ac |  | note | INSPECTORATE W/H: Description - Hold point - Reject mix for non- compliant temperatures.
label | 62ad6115-614f-539a-b03e-0d803c4f9c50 |  | note | RESPONSIBLE PERSON - Quality Assurance Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3.7 - Compaction
label | 63ad6a08-75a9-537c-b68d-fe0ab4e2c168 |  | note | VERIFICATION ACTIVITY - NDM Testing
label | 5a7aa9e8-cb8a-5d5d-9eb5-d928412d5db0 |  | note | METHODS OR REFERENCE - NZTA M/10
label | d8d87b54-576e-5c4d-a934-8a4c17511c74 |  | note | FREQ. - Minimum:
label | 90f54af2-6308-5a70-be60-d07f353782af |  | note | ○ 1 Test per 300m² within Mat.
label | 886c71fb-52ec-5cc2-af27-f443263a6926 |  | note | ○ 1 Test per 100m of joint.
label | 24b301c2-9091-5c15-befd-8077e82a658a |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | 1c561687-a026-57d9-84ba-a80aa2bebec3 |  | note | INSPECTORATE W/H: Type - H
label | 8b880acb-2f43-5f5d-a6b0-18f650d0624b |  | note | INSPECTORATE W/H: Description - Hold Point - No Wearing course paved until any non-compliance is sorted. PQI / Core recorded with RP, lane, offset, date, air voids. Core results received within 2 weeks.
label | 7e4e14a9-df9e-5f6f-9712-d8a7bb9c3282 |  | note | RESPONSIBLE PERSON - Quality Assurance Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3.8 - Roughness
label | 64779d35-f61a-5507-b634-c695325c8a92 |  | note | VERIFICATION ACTIVITY - N/A
label | d02cff7e-4246-5c63-bb8b-f1eda2cfb9ec |  | note | METHODS OR REFERENCE - N/A
label | 97a8dacd-875b-5e73-8c78-7ffbfeebbc5d |  | note | FREQ. - N/A
label | f88248c8-e919-5d2b-8377-96285647129b |  | note | ACCEPTANCE CRITERIA - N/A
label | f65a3651-f752-5a03-a226-b4598ea01d54 |  | note | INSPECTORATE W/H: Type - H
label | 7f5e9463-64f4-5eb5-b5c2-4529fa8511dd |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Paving Wearing Course
checkpoint-status |  |  | checkpoint | 4.1 - Production Properties - PSD (Particle Size Distribution)
label | f4414ba3-538a-578f-91ee-c90e7403ff70 |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | db2ad5f6-c77c-59cd-a2d8-d881116faf92 |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | 3c216a60-c198-548b-8a9d-4d2947582cc0 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 010f49a7-ade4-5752-a00a-73b15002170e |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | f8b7ed0b-1a62-5ca9-a907-9e5c7cf80229 |  | note | INSPECTORATE W/H: Type - W
label | d2f2f3a9-7d8c-5f6e-b911-87513b237a2e |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | 9bc3c9b2-2aa9-575b-9ac1-310f03a9c2ce |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.1 - Production Properties - Binder Content
label | dbca3cfe-2baa-567e-beb2-826edf4b0f10 |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | 6a64c9b8-cb3e-5025-8c00-66f028446eee |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | bf6048e0-c1d4-56c8-8ce7-fe1ff12eb717 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 9047102f-cf46-5ee9-ad67-2d75ff082b0f |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | d9eb2cdc-b8d8-5602-8e71-b461ad4af1a5 |  | note | INSPECTORATE W/H: Type - W
label | 0c30ce20-a7ca-5170-a2ba-319f7849974c |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | 62aac8cc-60e1-5904-823c-4c8c30acd05c |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.1 - Production Properties - Maximum Specific Gravity
label | 502ae41c-40b5-51ed-9052-1fbae8d00735 |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | 2d566a1a-d24d-5c8a-ad34-c89ba3123e75 |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | 35033ade-1410-55e3-8ff8-0511bdfb9429 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 581718d1-bbce-5274-8dcf-964bc1eb457d |  | note | ACCEPTANCE CRITERIA - Per Mix design
label | 62ffa709-c446-54a4-b982-7bfc09683f72 |  | note | INSPECTORATE W/H: Type - W
label | 0d420fcd-ee55-547e-937b-4c801cd8b8c9 |  | note | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | 9ba08093-6a7c-58e1-a0b9-ed330d863a47 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.2 - Preparation
label | db9ce694-98c2-5a7b-9a28-b13a51ecc231 |  | note | VERIFICATION ACTIVITY - Visual
label | 9d91921c-7ed2-5027-b9a1-65c60d79a3df |  | note | METHODS OR REFERENCE - NZTA M/10
label | 9d5fc123-79f3-52f7-a1cb-dea928db37df |  | note | FREQ. - NZTA M/10
label | c29ffdec-2d35-5ae1-b14f-202df4a14d08 |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | 17426a0f-9450-52b4-8468-fa3e6895bd93 |  | note | INSPECTORATE W/H: Type - W
label | 920dc331-cae0-5833-ae51-5b2059b6e2df |  | note | INSPECTORATE W/H: Description - Paving Plan and Crew Briefing Plan completed prior
label | 5649f2b5-55fb-5b74-8ad3-f627bee097e3 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.3 - Joins
label | bc6b9933-2d1b-56e2-8fee-318827ee33fb |  | note | VERIFICATION ACTIVITY - Visual
label | cba9acc2-56bf-5203-ab47-22803fe0b4a0 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 41c94502-db41-5ec1-ac5f-2dcf93f10740 |  | note | FREQ. - Prior to Shift
label | cc17ef68-c3ac-56f3-954a-80de4e520f6b |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | e56b0226-2ecc-536a-a53e-6226f7a81d87 |  | note | INSPECTORATE W/H: Type - W
label | 60795809-394f-5fb5-8591-0e26b8031008 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.4 - Membrane Sealing
label | 4b1b5789-e907-541b-8e19-511e454df447 |  | note | VERIFICATION ACTIVITY - Visual
label | 570a59ac-7b61-555f-af07-60b3e73bcb31 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 1061e623-a2b7-5128-a1f3-306010424cf4 |  | note | FREQ. - Prior to Paving
label | 7d2d6752-5a0d-514b-82de-f9febaf34dd7 |  | note | ACCEPTANCE CRITERIA - application rate as per TAC design
label | 1a75e803-a8b3-5960-bccf-3d31136d3d54 |  | note | INSPECTORATE W/H: Type - H
label | 71393c8d-f071-5589-8cd7-a37e0c931574 |  | note | INSPECTORATE W/H: Description - Hold Point - No paving until Membrane Done. Ensure correct application of chip & emulsion
label | bae72fe1-29e3-5ccc-8048-12375f46883a |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.5 - Mix Inconsistency and Deficiency
label | c0e051c3-197b-568f-803f-26bd70c74a03 |  | note | VERIFICATION ACTIVITY - Visual
label | 0d4b26e7-bb5c-5352-a50e-9dada32eeeb3 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 80b4e2ba-454c-58fb-a169-11011313d2ac |  | note | FREQ. - Continuous
label | 2825d50e-b19b-5c43-9262-4f5b7be9693c |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | 7a71f686-8b82-5851-a37f-de9c7257656a |  | note | INSPECTORATE W/H: Type - H
label | e2fa872e-4144-52c7-902a-a66456f2aae2 |  | note | RESPONSIBLE PERSON - Site Foreperson
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.6 - Load Locate
label | a5f2a22f-3a3e-5b0d-983c-656858537687 |  | note | VERIFICATION ACTIVITY - Measurement
label | 605a6d97-6eaf-5199-8f9f-bb94fe9b4de1 |  | note | FREQ. - Every Load
label | 2282c527-c9eb-584b-9770-f87e53b94b20 |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes:
label | de1930a8-39fb-5afe-a019-2ebf452d0da3 |  | note | – Truck ID/Rego/Driver
label | a8c0bb17-2bc1-5438-8a11-04bb179d049d |  | note | – Depart Plant Time
label | 40c97456-2c0d-5d68-a32d-ff74c1035890 |  | note | – Arrive Site Time
label | 28d28d4c-626c-5efe-b459-ce7bdc82c66f |  | note | – AC Temp on Arrival
label | ebb9341b-2e46-5231-a31e-41f672637724 |  | note | – Ground Temp on Arrival
label | e12dfc5d-5448-5e25-be2d-827901d12f3c |  | note | – Tonnage
label | 41dc3b6c-af8b-56ba-9591-8488b44d78cf |  | note | – Run Width
label | 0e15d854-041a-59a7-bb86-e51c6e801f40 |  | note | – Estimated Run Length
label | a3487800-313b-5e22-9ccd-7b991b2b7541 |  | note | – Calculated Area
label | 18a78ee9-1bba-5a7a-954a-170f12425e09 |  | note | – Calculated Average Depth
label | e241eda7-20ee-5ce6-9ec8-8ba7ebcfe06c |  | note | INSPECTORATE W/H: Type - W
label | 5b20507a-c5d0-5b2e-9537-bdca8d45ae5a |  | note | INSPECTORATE W/H: Description - Per standard practice
label | f5ca6d69-73cc-5d5b-b7c3-22a57c7dd83e |  | note | RESPONSIBLE PERSON - Quality Assurance Technician.
checkpoint-status |  |  | checkpoint | 4.7 - Laying Temperature
label | 8b649a68-ef73-5e84-908a-afbba6617623 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 822ac64a-c271-58dd-9740-a84fd69862b1 |  | note | METHODS OR REFERENCE - NZTA M/10
label | ca87ab5f-7dab-5ca1-8d17-9633f02a865b |  | note | FREQ. - Every Load
label | 4a944f4c-da8b-5395-b00b-67b0469a6b8c |  | note | ACCEPTANCE CRITERIA - Based on Mix design
label | c2b30e63-3660-57c3-b61b-12827436f75b |  | note | INSPECTORATE W/H: Type - H
label | 8f5f62f7-77a0-51a6-bfb3-8c67ac430eca |  | note | INSPECTORATE W/H: Description - Hold point - Reject mix for non- compliant temperatures.
label | 300f0b28-38a9-5cd2-bab5-a187295e00e0 |  | note | RESPONSIBLE PERSON - Quality Assurance Technician
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.8 - Compaction
label | 34a671c1-44ce-5372-a4a5-b7646e20e416 |  | note | VERIFICATION ACTIVITY - PQI Non-Nuclear Gauge/Cores. Or Non Distrctive Method Testing.
label | 74f2a1d7-c65b-5057-8cc1-ddf47a1d1e9f |  | note | METHODS OR REFERENCE - NZTA M/10
label | 80f24990-e497-5a11-927b-db1b86500539 |  | note | FREQ. - As per Agreed on Contract.
label | c35034ab-f63f-591b-9ad9-c4b2459d3a5b |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | 78f9f8bb-93da-564d-b914-84672e1495a7 |  | note | INSPECTORATE W/H: Type - W
label | 005a1613-dff1-5b29-b749-577e7bcfa9d5 |  | note | INSPECTORATE W/H: Description - PQI / Core recorded with RP, lane, offset, date, air voids. Core results received within 2 weeks.
label | 9f632146-7c15-5076-b66b-ff9768ef4124 |  | note | RESPONSIBLE PERSON - Quality Assurance Technician / Paving Manager
checkpoint-group |  |  | section | Site Reinstatement / Clearance
checkpoint-status |  |  | checkpoint | 5.1 - Post-seal Area Check
label | 5b22f6b0-0626-5bbf-a453-0dec6fbe3002 |  | note | VERIFICATION ACTIVITY - Measurement
label | fed4ea6e-3523-5a10-b3e1-1bdd91e872aa |  | note | METHODS OR REFERENCE - On Site tape- measure
label | 9be6f109-c427-5422-b72a-7758a920d926 |  | note | FREQ. - After Surfacing
label | 499e130f-3583-5c34-8346-3052330e0d71 |  | note | ACCEPTANCE CRITERIA - Check sealed area meets design
label | e79d7873-a5ec-58f0-8dcb-3114963dc0f2 |  | note | INSPECTORATE W/H: Type - W
label | be2bb19a-f1e5-5138-8d92-d5247a6191d8 |  | note | INSPECTORATE W/H: Description - Notify Renewals Engineer or Renewals Manager
label | b898d6b3-af87-5089-8ca2-6dd38e3489d8 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.2 - Service Covers
label | 2a633de8-938a-577a-ae78-6aaffba67817 |  | note | VERIFICATION ACTIVITY - Measurement/Visual
label | 1c502316-a45a-5d52-85d0-b5f5d164a59d |  | note | METHODS OR REFERENCE - On Site
label | c6168b82-6bd3-54e5-9722-f7d9ff1b0ba7 |  | note | FREQ. - After Surfacing
label | e203a73e-b9c0-5fa8-830d-23d98ea19e08 |  | note | ACCEPTANCE CRITERIA - All service covers are checked and adjusted (if necessary) to finished level (+10mm, -0mm)
label | 03528040-a2ff-51b3-a535-b9dfe7f19e96 |  | note | INSPECTORATE W/H: Type - W
label | f29d67b4-4d3b-5c75-97c5-96fd8df0197d |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.3 - Joint Sealing
label | a6fa2327-0578-5486-90fc-8f24c3caf28c |  | note | VERIFICATION ACTIVITY - Visual
label | 9778307c-1620-5172-a170-efc46298edc4 |  | note | METHODS OR REFERENCE - On Site
label | bd5987e3-7584-5db4-95c4-759cb5b70a69 |  | note | FREQ. - After Surfacing
label | 77406faa-1e6e-55c1-9a45-668a2c8ecf71 |  | note | ACCEPTANCE CRITERIA - Check cold joints are bandage sealed
label | 30c7fdd1-f920-5cb3-96f4-996462414c6a |  | note | INSPECTORATE W/H: Type - W
label | 8f0f57e6-9144-5e9f-a9bb-97cc03adc249 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.4 - Road Marking
label | bde24e7d-0159-541e-bb03-f6c8dd0865a3 |  | note | VERIFICATION ACTIVITY - MOTSAM
label | f3c311d9-2b16-51e4-87ae-284d5daefe13 |  | note | METHODS OR REFERENCE - Visual inspection
label | 81182b1c-81e8-5bd5-a824-ad25c547d75b |  | note | FREQ. - All markings
label | 6f413657-8d9e-5ef1-a6d7-b47d1e143c2c |  | note | ACCEPTANCE CRITERIA - Replaced in same position, or per design
label | e6551bf5-13bd-5b11-bb8d-45112b5f523a |  | note | INSPECTORATE W/H: Type - H
label | e10ca7f9-b907-55ad-9d58-b4ad7d86f34b |  | note | INSPECTORATE W/H: Description - Hold point – Site TTM cannot be removed until markings reinstated
label | 287705e0-3068-56ab-8880-8adc674ef534 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.5 - Other Traffic Services - Marker pegs/ Signs/Markings/RRP Ms Replaced
label | 9baf6e09-3d07-5138-95c3-5ef2979766ca |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | d3aa01ca-0361-53b7-a3fe-35c5a28027d1 |  | note | METHODS OR REFERENCE - Visual inspection
label | 8578e4ad-430c-5bb3-b181-9b1b71271f1d |  | note | FREQ. - All signs/markers
label | 91441305-310c-55ff-85e2-2caf87028f52 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | 6deebe79-f358-50cf-97ff-485a9ef79a61 |  | note | INSPECTORATE W/H: Type - H
label | 61ece4a5-e285-5a6a-8c27-dcabdea702a6 |  | note | INSPECTORATE W/H: Description - Hold point – Site TTM cannot be removed until marker pegs, signs, markings and RRPMs reinstated
label | 56faf7cb-caf8-586b-9fc0-e0a2a59ffaa9 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.6 - Stormwater Management Controls removed
label | 3c2bca35-9b4d-5bde-b5b9-fed6e06721a9 |  | note | VERIFICATION ACTIVITY - Visual check
label | 59a2d33c-0406-5111-b101-9f6ba372ffa2 |  | note | FREQ. - All installed measures
label | 7266653b-2b6b-5fa3-91ea-8a8c0e980360 |  | note | ACCEPTANCE CRITERIA - Installed controls are removed
label | ac9eab10-d4e6-586a-ab79-802b92b99214 |  | note | INSPECTORATE W/H: Type - H
label | 967ca127-8158-5881-931a-b720ba03f4d4 |  | note | RESPONSIBLE PERSON - Paving Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.7 - Traffic Management Removed
label | 26fad6e1-24f7-56f7-835f-21a55af0f138 |  | note | VERIFICATION ACTIVITY - Visual check
label | 6cfa9980-3469-5f46-8dda-fb2b7bc9d8a5 |  | note | FREQ. - When safe, after all physical works completed
label | 923963de-eceb-52b6-bef4-a5341f740cec |  | note | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | 00ec7ac8-16b8-5a3a-9919-3d76ae25319e |  | note | INSPECTORATE W/H: Type - W
label | 0ffa6bae-191b-567c-9844-9cc3d7d6c74c |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.8 - Site left clean & tidy
label | 777b52f6-da5b-5ee2-9eb1-59f88e182848 |  | note | VERIFICATION ACTIVITY - Visual check
label | 347a40c5-916b-520d-9793-a1f06971062a |  | note | FREQ. - After vacating site
label | 235a6c0c-3d82-5de2-b407-70985b44dc23 |  | note | ACCEPTANCE CRITERIA - Stockpiles removed, Plant removed, Litter cleared from site
label | 027c02d2-d4ed-5ef1-b641-124aa5ccbb33 |  | note | INSPECTORATE W/H: Type - W
label | dd7edb47-e105-511d-9e8e-66ecf8604eaf |  | note | INSPECTORATE W/H: Description - Invite NZTA to carry out joint site inspection to inspect site.
label | 08182dde-7277-54d3-88c2-d5f8d4346623 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-group |  |  | section | As Built Records
checkpoint-status |  |  | checkpoint | 6.1 - Collect asset data
label | 2c638e17-f78a-563d-b6b8-006c2a60bc66 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | e1b1d486-52d4-554b-b79c-47f8297f1e71 |  | note | FREQ. - During construction
label | dfd5f4d0-c5eb-5629-84d8-1e8c4cf0fb0f |  | note | ACCEPTANCE CRITERIA - All relevant as built information collected.
label | f88081fe-b7b9-5661-a393-57b5df62c943 |  | note | INSPECTORATE W/H: Type - W
label | 9711e96f-42f4-58bd-818e-7246ee5bcf55 |  | note | RESPONSIBLE PERSON - Paving Supervisor
checkpoint-status |  |  | checkpoint | 6.2 - Enter asset data into RAMM and/or register(s)
label | 813e90f0-87e4-50ab-aa94-495dc3355d46 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | c6a88d93-d1b0-50ce-8767-1225786bff80 |  | note | METHODS OR REFERENCE - RAMM
label | aef55495-1520-5e42-bd58-8c32fda8d5bf |  | note | FREQ. - At completion of work.
label | a622779e-888b-515e-93a8-8bb20ec3e64c |  | note | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.
label | e27c0eda-1fb6-53f0-bbb7-da6723292e3c |  | note | INSPECTORATE W/H: Type - W
label | e1bb2ad3-2ace-590d-acfb-6c8865448e59 |  | note | INSPECTORATE W/H: Description - Data entered by 20th of follow month after month of completion
label | daded1d2-e96a-5006-8c4e-18b3a74ade81 |  | note | RESPONSIBLE PERSON - Asset Information Manager
checkpoint-status |  |  | checkpoint | 6.3 - Construction Completion Report
label | df3aff93-f8c2-5390-b81e-d971dcb86397 |  | note | VERIFICATION ACTIVITY - Confirmation
label | aedcb632-cc11-532d-b193-413ac4285ba9 |  | note | METHODS OR REFERENCE - Contract Specification
label | 125159a9-4b3b-5b29-ae7f-9b731c3eb15f |  | note | FREQ. - At completion of work.
label | 9dbc1ce7-f1ff-544d-a581-9b3389ab0d3c |  | note | ACCEPTANCE CRITERIA - Checked and approved
label | a3ff1904-6ae2-5d37-ad4b-9be8e7037c91 |  | note | INSPECTORATE W/H: Type - W
label | d29bfd4d-3023-5b32-a7b8-6c28dbd6d670 |  | note | INSPECTORATE W/H: Description - Completed within two months after Paving Wearing Course
label | bb6e51f2-26a0-587e-b776-696135f0c897 |  | note | RESPONSIBLE PERSON - Renewals Engineer/ Renewals Manager
checkpoint-status |  |  | checkpoint | Quality Assurance Close Out by:
text | 88390d96-d4de-5b37-b669-87eb529fbcb8 |  | textbox | (name):
date | 3b413f35-6443-5787-ab69-af541c205d72 |  | date | Date:
label | 7207d095-20d4-5ac3-aa36-f08f18a41d33 |  | note | This record to contract file.
holdpoint |  |  | signoff | (signature)