## Unbound Granular
|  | PAVEMENT RENEWAL INSPECTION AND TEST PLAN (ITP) – Structural Asphalt with Lean Mix Concrete Sub-base | [6 empty] | Doc No: Pavement Renewals
|  | Site Name: Nith Street | [6 empty] | Rev: A
|  | Location: SH01S RS0923 RP1.280 - 1.515 | [6 empty] | Prepared: | Shaun Magee | Date: | 2024-02-26
[9 empty] | Approved: |  | Date: | Draft for approval
ACTIVITY DESCRIPTION |  |  | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQ. | ACCEPTANCE CRITERIA | INSPECTORATE V/W/H |  |  |  | Responsible Person | RECORDS / REMARKS
[7 empty] | V=VERIFICATION, W=WITNESS, H =HOLD |  |  |  | (print Position) | incl NCR ref
[7 empty] | Type | Assessor | Description |  |  | Sign & date if appropriate
Construction Planning
1 | Construction Programming |  | Acceptance | Best Practice Contract MMP | Prior to construction | Meets client expectations and contractor capability | V |  | To be completed by SouthRoads |  | Construction Manager
2 | Source Material QA Checks: Lean Mixed Concrete - Sub-base Drainage Aggregate Asphalt - Structural base and wearing surface |  | QA Testing and confirmation of latest results | IANZ Lab Testing Records Contract Specification Section 7.3 | Before supply of each material | Lean Mix Concrete mix design has been approved by Design Engineer. Drainage Aggregate 100% passing 37.5mm sieve with all retained on 19mm sieve Asphalt Mix Designs comply with NZTA M10:2020. Asphalt binders comply with NZTA M/1a | V |  | Southern Aggregates Ltd / Central Testing Services to provide results for aggregate Downer to provide results for AC20 and AC14 |  | Aggregates & Environment Manager
3 | Renewal Quality Plan (RQP) |  | Approval | Contract Specification | Prior to construction | Meets contractual requirements | H |  | To be approved by contract management and NZTA |  | Asset Manager
4 | Traffic Management |  | Approval | TMP and CAR | 2-3 weeks prior to construction | Meets requirements of CoPTTM | H |  | To be approved by Road Controlling Authority (RCA) |  | Traffic management Department manager
Set-out / Site preparation
5 | Services |  | Desktop and on site as required | Before U Dig, Service Location Plans | Before work commences | All service risks quantified as per risk register, zero service strikes | H |  | Obtain service plans, service locate if required. Obtain permits if required. |  | Construction Manager
6 | Stormwater Management |  | Visual check | On-site | Before work commences | Mudtanks bunded or filtered to prevent mix or agregates from dropping in or runoff entering | H |  | Hold point - No work to be commenced until protections in place |  | Paving Supervisor
7 | Stakeholder Notification |  | Notification | Project Records | Before work commences | All stakeholders notified | V |  | All stakeholders identified and notified of works |  | Construction Manager
8 | Line Marking Plan |  | Confirmation | Contract Specification | Every Site | Meets requirements of MOTSAM | V |  | To be completed by Downer |  | Southland NOC Asphalt Surfacing Manager
9 | Traffic Management |  | TTM Set Up | Approved TMP | Before work commences | As per TMP | W |  | Approved traffic management set up |  | Traffic Management Department Manager
Excavation
10 | Depth of Excavation |  | Measurement | Per Design | Every 10m each side of excavation | Minimum cut depth 455mm | W |  |  |  | Site Foreperson
11 | Base of Excavation "Fall" |  | Measurement | Per Design | Every 10m across width of excavation | Slope 0.5-1.0% towards inside of curve or towards median island | H |  | Hold Point – Drainage layer cannot be laid until correct cross-slope is achieved and subgrade strength confirmed |  | Site Foreperson
12 | Sub-grade Strength |  | Measurement | Scala Penetrometer | 5m intervals in alternate wheelpaths (10m each wheelpath) | Inferred CBR of top 300mm ≥3% | H |  |  |  | Site Foreperson
Drainage Layer
13 | Filter Fabric - Materials |  | Visual check | On-site | Once | Filter fabric is Bidim A19 or an equivalent performing product | H |  |  |  | Site Foreperson
14 | Filter Fabric - Placement |  | Visual check | On-site | Continuous | Fabric covers excavation. Fabric overlaps minimum 300mm at joints | W |  |  |  | Site Foreperson
15 | Drainage Aggregate |  | Visual check | On-site | Continuous | Drainage aggregate compacted such that it does not displace under foot | W |  |  |  | Site Foreperson
Lean Mix Concrete Sub-base
16 | Concrete Compressive Strength |  | Measurement | Plant Core sample testing | Min 3 cores produced each day of batching | Minimum 7 day compressive strength 7 MPa. Min 28 Day compressive strength 17 MPa. ≤60mm slump | W |  | Hold Point – No construction machinery shall come into contact with the Lean Mix until the minimum UCS has been confirmed |  | Construction Engineer
17 | Concrete Placement | Depth | Measurement | On-site | Every 10m | Concrete depth at or greater than minimum as specified on drawings | W |  |  |  | Construction Engineer
|  | Samples | Visual Check | On-site | Daily | Minimum of 5 concrete cylinders shall be prepared on site for each pour | W |  |  |  | Construction Engineer
18 | Concrete surface |  | Visual Check | On-site | Continuous | Concrete surface shall have a broomed (U2) finish | W |  |  |  | Construction Engineer
19 | Saw Cuts |  | Visual check | On-site | Every 4.2m of slab length, full width | Saw cuts extend full width of concrete slab to depth of 50mm | H |  | Hold Point – No asphalt shall be placed until all sawcuts are completed |  | Construction Engineer
20 | Concrete Curing |  | Measurement | Per design | Daily | Minimum compressive strengthof 7 MPa achieved prior to opening to construction traffic | H |  |  |  | Construction Engineer
21 | Bitac | Surface | Visual check | Installation Guideline | Each saw cut | Surface is dry, clean and free of loose gravel, dust, clay or foreign material | H |  | Hold Point – No asphalt shall be placed until all sawcuts are covered |  | Construction Engineer
|  | Placement | Visual check | Installation Guideline | Each saw cut | Bitac is bonded to concrete and free of creases, bubbles and folds |  |  |  |  | Construction Engineer
Paving - Structural
22 | Production Properties | PSD (Particle Size Distribution) | Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing | ASTM C136-06 / C 117-14 | 1 per 200t or maximum of 3 per production lot | Job Mix Formula and NZTA M/10:2020 Table 5.3 tolerances | W |  | IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance |  | Paving Supervisor
|  | Binder Content | Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method | B19 Issue 6 - 2009
|  | Maximum Specific Gravity | Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures | ASTM D2041/D2041M - 2011
23 | Preparation |  | Visual check | NZTA M/10:2020 | Prior to Shift | Paving plan to be completed for every shift, with dimensions | W |  | Paving Plan and Crew Briefing Plan completed prior |  | Paving Supervisor
24 | Joins |  | Visual check | NZTA M/10:2020 | Prior to Shift | Joins are outside of trafficked wheel paths where possible. | W |  |  |  | Paving Supervisor
25 | Mix Inconsistency and Deficiency |  | Visual check | NZTA M/10:2020 | Continuous | Visually check asphalt surface during paving for areas of segregation | H |  |  |  | Site Foreperson
26 | Load Locate |  | Measurement |  | Every Load | Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth | W |  | Per standard practice |  | Quality Assurance Engineer
27 | Laying Temperature |  | Confirmation | NZTA M/10:2020 | Every Load | Arrival temperature 150°C (±10°) checked for every load | H |  | Hold point - Reject mix for non-compliant temperatures. |  | Quality Assurance Engineer
28 | Compaction |  | NDM Testing | NZTA M/10:2020 | 1 Test per 300m² or min 8 cores per shift within Mat. 1 Test per 100m of joint or min 3 cores per shift. | Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2 | H |  | Hold Point - No Wearing course paved until any non-compliance is sorted |  | Quality Assurance Engineer
Paving - Wearing Course
29 | Production Properties | PSD (Particle Size Distribution) | Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing | ASTM C136-06 / C 117-14 | 1 per 200t or maximum of 3 per production lot | Job Mix Formula and NZTA M/10:2020 Table 5.3 tolerances | W |  | IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance |  | Paving Supervisor
|  | Binder Content | Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method | B19 Issue 6 - 2009
|  | Maximum Specific Gravity | Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures | ASTM D2041/D2041M - 2011
30 | Preparation |  | Visual check | NZTA M/10:2020 | Prior to Shift | Paving plan to be completed for every shift, with dimensions | W |  | Paving Plan and Crew Briefing Plan completed prior |  | Paving Supervisor
31 | Joins |  | Visual check | NZTA M/10:2020 | Prior to Shift | Joins are outside of trafficked wheel paths where possible. | W |  |  |  | Paving Supervisor
32 | Tack Coat |  | Visual check | NZTA M/10:2020 | Prior to Paving | Applied between 0.1 & 0.2l/m² residual | H |  | Hold Point - No paving until tack applied |  | Paving Supervisor
33 | Mix Inconsistency and Deficiency |  | Visual check | NZTA M/10:2020 | Continuous | Visually check asphalt surface during paving for areas of segregation | H |  |  |  | Site Foreperson
34 | Load Locate |  | Measurement |  | Every Load | Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth | W |  | Per standard practice |  | Quality Assurance Engineer
35 | Laying Temperature |  | Confirmation | NZTA M/10:2020 | Every Load | Arrival temperature 150°C (±10°) checked for every load | H |  | Hold point - Reject mix for non-compliant temperatures. |  | Quality Assurance Engineer
36 | Compaction |  | Core Testing | NZTA M/10:2020 | 1 Test per 300m² or min 8 cores per shift within Mat. 1 Test per 100m of joint or min 3 cores per shift. | As per M10:2020 Table 9.1 & 9.2 | H |  |  |  | Quality Assurance Engineer
37 | Roughness |  | NAASRA Testing | CONOC MS | Following Paving | No Rolling 100m average measured at 20m intervals to be >60 NAASRA counts | H |  |  |  | Quality Assurance Engineer
Site Reinstatement / Clearance
38 | Post-seal Area Check |  | Measurement | On Site tape-measure | After Surfacing | Check sealed area meets design | W |  | Notify Renewals Engineer or Renewals Manager |  | Paving Supervisor
39 | Service Covers |  | Measurement/ Visual | On Site | After Surfacing | All service covers are checked and adjusted (if necessary) to finished level | W |  |  |  | Paving Supervisor
40 | Joint Sealing |  | Visual check | On Site | After Surfacing | Check cold joints are bandage sealed | W |  |  |  | Paving Supervisor
41 | Road Marking |  | Visual check | MOTSAM | All markings | Replaced in same position, or per design | H |  | Hold point – Site TTM cannot be removed until markings reinstated |  | Paving Supervisor
42 | Other Traffic Services | Marker pegs/ Signs/Markings/RRPMs Replaced | Visual check | TNZ C/20: 2003 | All signs/markers | Replaced in same position, height etc | H |  | Hold point – Site TTM cannot be removed until marker pegs, signs, markings and RRPMs reinstated |  | Paving Supervisor
43 | Stormwater Management Controls removed |  | Visual check |  | All installed measures | Installed controls are removed | H |  |  |  | Paving Supervisor
44 | Traffic Management Removed |  | Visual check |  | When safe, after all physical works completed | All traffic management removed from site safely | W |  |  |  | Paving Supervisor
45 | Site left clean & tidy |  | Visual check |  | After vacating site | · Stockpiles removed | W |  |  |  | Paving Supervisor | Invite NZTA to carry out joint site inspection to inspect site.
· Plant removed
· Litter cleared from site
As Built Records
46 | As-Builts / RAMM - Pavement |  | Complete and submit all site QA records | RAMM Database | Post-construction | Construction data uploaded to RAMM, as-builts and QA submitted to NZTA | W |  | Process all construction documentation for pavement, surface and drainage works |  | Josh Price - Construction Manager
47 | As-Builts / RAMM - Surfacing |  | Complete and submit all site QA records | RAMM Database | Post-construction | Construction data uploaded to RAMM, as-builts and QA submitted to NZTA | W |  | Process all construction documentation for pavement, surface and drainage works |  | Oliver Begg - Southland NOC Surfacing Engineer
48 | Joint Final Inspection/ Snag list |  | Inspection | Contract Specification | Post-construction | Site is free of defects | V |  | Joint Inpsection by supplier and client |  | Josh Price - Construction Manager/ Justin Reid - MCM NZTA Representative
49 | Construction Completion Report |  | Confirmation | Contract Specification | At completion of work. | Checked and approved | W |  | Completed within two months after Paving Wearing Course |  | Renewals Engineer/ Renewals Manager | Submit Pavement Design Report, Construction Compliance, QMP, Site test results / inspections / activity records, Lessons Learnt, As- Built Plans
| Quality Assurance Close Out by: |  | _______________________________________________ |  |  | Date: _____________
(signature)
________________________________________________
________________________________________________
This record to contract file.