## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SNOC ITP Nith St - Pavement Renewals ITP Rev A | itp |  |  |  |  | SNOC ITP Nith St - Pavement Renewals ITP Rev A
section | Construction Planning
checkpoint | 1 - Construction Programming
label | VERIFICATION ACTIVITY - Acceptance
label | METHODS OR REFERENCE - Best Practice Contract MMP
label | FREQ. - Prior to construction
label | ACCEPTANCE CRITERIA - Meets client expectations and contractor capability
label | INSPECTORATE W/H: Type - V
label | INSPECTORATE W/H: Description - To be completed by SouthRoads
label | RESPONSIBLE PERSON - Construction Manager
checkpoint | 2 - Source Material QA Checks: Lean Mixed Concrete - Sub-base, Drainage Aggregate, Asphalt - Structural base and wearing surface
label | VERIFICATION ACTIVITY - QA Testing and confirmation of latest results
label | METHODS OR REFERENCE - IANZ Lab Testing Records, Contract Specification Section 7.3
label | FREQ. - Before supply of each material
label | ACCEPTANCE CRITERIA - Lean Mix Concrete mix design has been approved by Design Engineer.
label | ○ Drainage Aggregate 100% passing 37.5mm sieve with all retained on 19mm sieve
label | ○ Asphalt Mix Designs comply with NZTA M10:2020. Asphalt binders comply with NZTA M/1a
label | INSPECTORATE W/H: Type - V
label | INSPECTORATE W/H: Description - Southern Aggregates Ltd / Central Testing Services to provide results for aggregate, Downer to provide results for AC20 and AC14
label | RESPONSIBLE PERSON - Aggregates & Environment Manager
checkpoint | 3 - Renewal Quality Plan (RQP)
label | VERIFICATION ACTIVITY - Approval
label | METHODS OR REFERENCE - Contract Specification
label | FREQ. - Prior to construction
label | ACCEPTANCE CRITERIA - Meets contractual requirements
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - To be approved by contract management and NZTA
label | RESPONSIBLE PERSON - Asset Manager
holdpoint | HOLD POINT
checkpoint | 4 - Traffic Management
label | VERIFICATION ACTIVITY - Approval
label | METHODS OR REFERENCE - TMP and CAR
label | FREQ. - 2-3 weeks prior to construction
label | ACCEPTANCE CRITERIA - Meets requirements of CoPTTM
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - To be approved by Road Controlling Authority (RCA)
label | RESPONSIBLE PERSON - Traffic management Department manager
holdpoint | HOLD POINT
section | Set-out / Site preparation
checkpoint | 5 - Services
label | VERIFICATION ACTIVITY - Desktop and on site as required
label | METHODS OR REFERENCE - Before U Dig, Service Location Plans
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - All service risks quantified as per risk register, zero service strikes
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Obtain service plans, service locate if required. Obtain permits if required.
label | RESPONSIBLE PERSON - Construction Manager
holdpoint | HOLD POINT
checkpoint | 6 - Stormwater Management
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - On-site
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Mudtanks bunded or filtered to prevent mix or agregates from dropping in or runoff entering
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold point - No work to be commenced until protections in place
label | RESPONSIBLE PERSON - Paving Supervisor
holdpoint | HOLD POINT
checkpoint | 7 - Stakeholder Notification
label | VERIFICATION ACTIVITY - Notification
label | METHODS OR REFERENCE - Project Records
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - All stakeholders notified
label | INSPECTORATE W/H: Type - V
label | INSPECTORATE W/H: Description - All stakeholders identified and notified of works
label | RESPONSIBLE PERSON - Construction Manager
checkpoint | 8 - Line Marking Plan
label | VERIFICATION ACTIVITY - Confirmation
label | METHODS OR REFERENCE - Contract Specification
label | FREQ. - Every Site
label | ACCEPTANCE CRITERIA - Meets requirements of MOTSAM
label | INSPECTORATE W/H: Type - V
label | INSPECTORATE W/H: Description - To be completed by Downer
label | RESPONSIBLE PERSON - Southland NOC Asphalt Surfacing Manager
checkpoint | 9 - Traffic Management
label | VERIFICATION ACTIVITY - TTM Set Up
label | METHODS OR REFERENCE - Approved TMP
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - As per TMP
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - Approved traffic management set up
label | RESPONSIBLE PERSON - Traffic Management Department Manager
section | Excavation
checkpoint | 10 - Depth of Excavation
label | VERIFICATION ACTIVITY - Measurement
label | METHODS OR REFERENCE - Per Design
label | FREQ. - Every 10m each side of excavation
label | ACCEPTANCE CRITERIA - Minimum cut depth 455mm
label | INSPECTORATE W/H: Type - W
label | RESPONSIBLE PERSON - Site Foreperson
checkpoint | 11 - Base of Excavation "Fall"
label | VERIFICATION ACTIVITY - Measurement
label | METHODS OR REFERENCE - Per Design
label | FREQ. - Every 10m across width of excavation
label | ACCEPTANCE CRITERIA - Slope 0.5-1.0% towards inside of curve or towards median island
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold Point – Drainage layer cannot be laid until correct cross-slope is achieved and subgrade strength confirmed
label | RESPONSIBLE PERSON - Site Foreperson
holdpoint | HOLD POINT
checkpoint | 12 - Sub-grade Strength
label | VERIFICATION ACTIVITY - Measurement
label | METHODS OR REFERENCE - Scala Penetrometer
label | FREQ. - 5m intervals in alternate wheelpaths (10m each wheelpath)
label | ACCEPTANCE CRITERIA - Inferred CBR of top 300mm ≥3%
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold Point – Drainage layer cannot be laid until correct cross-slope is achieved and subgrade strength confirmed
label | RESPONSIBLE PERSON - Site Foreperson
holdpoint | HOLD POINT
section | Drainage Layer
checkpoint | 13 - Filter Fabric - Materials
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - On-site
label | FREQ. - Once
label | ACCEPTANCE CRITERIA - Filter fabric is Bidim A19 or an equivalent performing product
label | INSPECTORATE W/H: Type - H
label | RESPONSIBLE PERSON - Site Foreperson
holdpoint | HOLD POINT
checkpoint | 14 - Filter Fabric - Placement
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - On-site
label | FREQ. - Continuous
label | ACCEPTANCE CRITERIA - Fabric covers excavation. Fabric overlaps minimum 300mm at joints
label | INSPECTORATE W/H: Type - W
label | RESPONSIBLE PERSON - Site Foreperson
checkpoint | 15 - Drainage Aggregate
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - On-site
label | FREQ. - Continuous
label | ACCEPTANCE CRITERIA - Drainage aggregate compacted such that it does not displace under foot
label | INSPECTORATE W/H: Type - W
label | RESPONSIBLE PERSON - Site Foreperson
section | Lean Mix Concrete Sub-base
checkpoint | 16 - Concrete Compressive Strength
label | VERIFICATION ACTIVITY - Measurement
label | METHODS OR REFERENCE - Plant Core sample testing
label | FREQ. - Min 3 cores produced each day of batching
label | ACCEPTANCE CRITERIA - Minimum 7 day compressive strength 7 MPa. Min 28 Day compressive strength 17 MPa. ≤60mm slump
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - Hold Point – No construction machinery shall come into contact with the Lean Mix until the minimum UCS has been confirmed
label | RESPONSIBLE PERSON - Construction Engineer
checkpoint | 17 - Concrete Placement - Depth
label | VERIFICATION ACTIVITY - Measurement
label | METHODS OR REFERENCE - On-site
label | FREQ. - Every 10m
label | ACCEPTANCE CRITERIA - Concrete depth at or greater than minimum as specified on drawings
label | INSPECTORATE W/H: Type - W
label | RESPONSIBLE PERSON - Construction Engineer
checkpoint | 17 - Concrete Placement - Samples
label | VERIFICATION ACTIVITY - Visual Check
label | METHODS OR REFERENCE - On-site
label | FREQ. - Daily
label | ACCEPTANCE CRITERIA - Minimum of 5 concrete cylinders shall be prepared on site for each pour
label | INSPECTORATE W/H: Type - W
label | RESPONSIBLE PERSON - Construction Engineer
checkpoint | 18 - Concrete surface
label | VERIFICATION ACTIVITY - Visual Check
label | METHODS OR REFERENCE - On-site
label | FREQ. - Continuous
label | ACCEPTANCE CRITERIA - Concrete surface shall have a broomed (U2) finish
label | INSPECTORATE W/H: Type - W
label | RESPONSIBLE PERSON - Construction Engineer
checkpoint | 19 - Saw Cuts
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - On-site
label | FREQ. - Every 4.2m of slab length, full width
label | ACCEPTANCE CRITERIA - Saw cuts extend full width of concrete slab to depth of 50mm
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold Point – No asphalt shall be placed until all sawcuts are completed
label | RESPONSIBLE PERSON - Construction Engineer
holdpoint | HOLD POINT
checkpoint | 20 - Concrete Curing
label | VERIFICATION ACTIVITY - Measurement
label | METHODS OR REFERENCE - Per design
label | FREQ. - Daily
label | ACCEPTANCE CRITERIA - Minimum compressive strengthof 7 MPa achieved prior to opening to construction traffic
label | INSPECTORATE W/H: Type - H
label | RESPONSIBLE PERSON - Construction Engineer
holdpoint | HOLD POINT
checkpoint | 21 - Bitac - Surface
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - Installation Guideline
label | FREQ. - Each saw cut
label | ACCEPTANCE CRITERIA - Surface is dry, clean and free of loose gravel, dust, clay or foreign material
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold Point – No asphalt shall be placed until all sawcuts are covered
label | RESPONSIBLE PERSON - Construction Engineer
holdpoint | HOLD POINT
checkpoint | 21 - Bitac - Placement
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - Installation Guideline
label | FREQ. - Each saw cut
label | ACCEPTANCE CRITERIA - Bitac is bonded to concrete and free of creases, bubbles and folds
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold Point – No asphalt shall be placed until all sawcuts are covered
label | RESPONSIBLE PERSON - Construction Engineer
holdpoint | HOLD POINT
section | Paving - Structural
checkpoint | 22 - Production Properties - PSD (Particle Size Distribution)
label | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | FREQ. - 1 per 200t or maximum of 3 per production lot
label | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10:2020 Table 5.3 tolerances
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 22 - Production Properties - Binder Content
label | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | FREQ. - 1 per 200t or maximum of 3 per production lot
label | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10:2020 Table 5.3 tolerances
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 22 - Production Properties - Maximum Specific Gravity
label | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | FREQ. - 1 per 200t or maximum of 3 per production lot
label | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10:2020 Table 5.3 tolerances
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 23 - Preparation
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - NZTA M/10:2020
label | FREQ. - Prior to Shift
label | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - Paving Plan and Crew Briefing Plan completed prior
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 24 - Joins
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - NZTA M/10:2020
label | FREQ. - Prior to Shift
label | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | INSPECTORATE W/H: Type - W
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 25 - Mix Inconsistency and Deficiency
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - NZTA M/10:2020
label | FREQ. - Continuous
label | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | INSPECTORATE W/H: Type - H
label | RESPONSIBLE PERSON - Site Foreperson
holdpoint | HOLD POINT
checkpoint | 26 - Load Locate
label | VERIFICATION ACTIVITY - Measurement
label | FREQ. - Every Load
label | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes:
label | ○ Truck ID/Rego/Driver
label | ○ Depart Plant Time
label | ○ Arrive Site Time
label | ○ AC Temp on Arrival
label | ○ Ground Temp on Arrival
label | ○ Tonnage
label | ○ Run Width
label | ○ Estimated Run Length
label | ○ Calculated Area
label | ○ Calculated Average Depth
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - Per standard practice
label | RESPONSIBLE PERSON - Quality Assurance Engineer
checkpoint | 27 - Laying Temperature
label | VERIFICATION ACTIVITY - Confirmation
label | METHODS OR REFERENCE - NZTA M/10:2020
label | FREQ. - Every Load
label | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold point - Reject mix for non-compliant temperatures.
label | RESPONSIBLE PERSON - Quality Assurance Engineer
holdpoint | HOLD POINT
checkpoint | 28 - Compaction
label | VERIFICATION ACTIVITY - NDM Testing
label | METHODS OR REFERENCE - NZTA M/10:2020
label | FREQ. - 1 Test per 300m² or min 8 cores per shift within Mat. 1 Test per 100m of joint or min 3 cores per shift.
label | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2
label | ○ Join: Air voids JMF +5,-2
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold Point - No Wearing course paved until any non-compliance is sorted
label | RESPONSIBLE PERSON - Quality Assurance Engineer
holdpoint | HOLD POINT
section | Paving - Wearing Course
checkpoint | 29 - Production Properties - PSD (Particle Size Distribution)
label | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | FREQ. - 1 per 200t or maximum of 3 per production lot
label | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10:2020 Table 5.3 tolerances
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 29 - Production Properties - Binder Content
label | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | FREQ. - 1 per 200t or maximum of 3 per production lot
label | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10:2020 Table 5.3 tolerances
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 29 - Production Properties - Maximum Specific Gravity
label | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | FREQ. - 1 per 200t or maximum of 3 per production lot
label | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10:2020 Table 5.3 tolerances
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 30 - Preparation
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - NZTA M/10:2020
label | FREQ. - Prior to Shift
label | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - Paving Plan and Crew Briefing Plan completed prior
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 31 - Joins
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - NZTA M/10:2020
label | FREQ. - Prior to Shift
label | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | INSPECTORATE W/H: Type - W
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 32 - Tack Coat
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - NZTA M/10:2020
label | FREQ. - Prior to Paving
label | ACCEPTANCE CRITERIA - Applied between 0.1 & 0.2l/m² residual
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold Point - No paving until tack applied
label | RESPONSIBLE PERSON - Paving Supervisor
holdpoint | HOLD POINT
checkpoint | 33 - Mix Inconsistency and Deficiency
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - NZTA M/10:2020
label | FREQ. - Continuous
label | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | INSPECTORATE W/H: Type - H
label | RESPONSIBLE PERSON - Site Foreperson
holdpoint | HOLD POINT
checkpoint | 34 - Load Locate
label | VERIFICATION ACTIVITY - Measurement
label | FREQ. - Every Load
label | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes:
label | ○ Truck ID/Rego/Driver
label | ○ Depart Plant Time
label | ○ Arrive Site Time
label | ○ AC Temp on Arrival
label | ○ Ground Temp on Arrival
label | ○ Tonnage
label | ○ Run Width
label | ○ Estimated Run Length
label | ○ Calculated Area
label | ○ Calculated Average Depth
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - Per standard practice
label | RESPONSIBLE PERSON - Quality Assurance Engineer
checkpoint | 35 - Laying Temperature
label | VERIFICATION ACTIVITY - Confirmation
label | METHODS OR REFERENCE - NZTA M/10:2020
label | FREQ. - Every Load
label | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold point - Reject mix for non-compliant temperatures.
label | RESPONSIBLE PERSON - Quality Assurance Engineer
holdpoint | HOLD POINT
checkpoint | 36 - Compaction
label | VERIFICATION ACTIVITY - Core Testing
label | METHODS OR REFERENCE - NZTA M/10:2020
label | FREQ. - 1 Test per 300m² or min 8 cores per shift within Mat. 1 Test per 100m of joint or min 3 cores per shift.
label | ACCEPTANCE CRITERIA - As per M10:2020 Table 9.1 & 9.2
label | INSPECTORATE W/H: Type - H
label | RESPONSIBLE PERSON - Quality Assurance Engineer
holdpoint | HOLD POINT
checkpoint | 37 - Roughness
label | VERIFICATION ACTIVITY - NAASRA Testing
label | METHODS OR REFERENCE - CONOC MS
label | FREQ. - Following Paving
label | ACCEPTANCE CRITERIA - No Rolling 100m average measured at 20m intervals to be >60 NAASRA counts
label | INSPECTORATE W/H: Type - H
label | RESPONSIBLE PERSON - Quality Assurance Engineer
holdpoint | HOLD POINT
section | Site Reinstatement / Clearance
checkpoint | 38 - Post-seal Area Check
label | VERIFICATION ACTIVITY - Measurement
label | METHODS OR REFERENCE - On Site tape-measure
label | FREQ. - After Surfacing
label | ACCEPTANCE CRITERIA - Check sealed area meets design
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - Notify Renewals Engineer or Renewals Manager
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 39 - Service Covers
label | VERIFICATION ACTIVITY - Measurement/Visual
label | METHODS OR REFERENCE - On Site
label | FREQ. - After Surfacing
label | ACCEPTANCE CRITERIA - All service covers are checked and adjusted (if necessary) to finished level
label | INSPECTORATE W/H: Type - W
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 40 - Joint Sealing
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - On Site
label | FREQ. - After Surfacing
label | ACCEPTANCE CRITERIA - Check cold joints are bandage sealed
label | INSPECTORATE W/H: Type - W
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 41 - Road Marking
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - MOTSAM
label | FREQ. - All markings
label | ACCEPTANCE CRITERIA - Replaced in same position, or per design
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold point – Site TTM cannot be removed until markings reinstated
label | RESPONSIBLE PERSON - Paving Supervisor
holdpoint | HOLD POINT
checkpoint | 42 - Other Traffic Services - Marker pegs/Signs/Markings/RRPMs Replaced
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - TNZ C/20: 2003
label | FREQ. - All signs/markers
label | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold point – Site TTM cannot be removed until marker pegs, signs, markings and RRPMs reinstated
label | RESPONSIBLE PERSON - Paving Supervisor
holdpoint | HOLD POINT
checkpoint | 43 - Stormwater Management Controls removed
label | VERIFICATION ACTIVITY - Visual check
label | FREQ. - All installed measures
label | ACCEPTANCE CRITERIA - Installed controls are removed
label | INSPECTORATE W/H: Type - H
label | RESPONSIBLE PERSON - Paving Supervisor
holdpoint | HOLD POINT
checkpoint | 44 - Traffic Management Removed
label | VERIFICATION ACTIVITY - Visual check
label | FREQ. - When safe, after all physical works completed
label | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | INSPECTORATE W/H: Type - W
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 45 - Site left clean & tidy
label | VERIFICATION ACTIVITY - Visual check
label | FREQ. - After vacating site
label | ACCEPTANCE CRITERIA - Stockpiles removed, Plant removed, Litter cleared from site
label | INSPECTORATE W/H: Type - W
label | RESPONSIBLE PERSON - Paving Supervisor
section | As Built Records
checkpoint | 46 - As-Builts / RAMM - Pavement
label | VERIFICATION ACTIVITY - Complete and submit all site QA records
label | METHODS OR REFERENCE - RAMM Database
label | FREQ. - Post-construction
label | ACCEPTANCE CRITERIA - Construction data uploaded to RAMM, as-builts and QA submitted to NZTA
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - Process all construction documentation for pavement, surface and drainage works
label | RESPONSIBLE PERSON - Josh Price - Construction Manager
checkpoint | 47 - As-Builts / RAMM - Surfacing
label | VERIFICATION ACTIVITY - Complete and submit all site QA records
label | METHODS OR REFERENCE - RAMM Database
label | FREQ. - Post-construction
label | ACCEPTANCE CRITERIA - Construction data uploaded to RAMM, as-builts and QA submitted to NZTA
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - Process all construction documentation for pavement, surface and drainage works
label | RESPONSIBLE PERSON - Oliver Begg - Southland NOC Surfacing Engineer
checkpoint | 48 - Joint Final Inspection/ Snag list
label | VERIFICATION ACTIVITY - Inspection
label | METHODS OR REFERENCE - Contract Specification
label | FREQ. - Post-construction
label | ACCEPTANCE CRITERIA - Site is free of defects
label | INSPECTORATE W/H: Type - V
label | INSPECTORATE W/H: Description - Joint Inpsection by supplier and client
label | RESPONSIBLE PERSON - Josh Price - Construction Manager/ Justin Reid - MCM NZTA Representative
checkpoint | 49 - Construction Completion Report
label | VERIFICATION ACTIVITY - Confirmation
label | METHODS OR REFERENCE - Contract Specification
label | FREQ. - At completion of work.
label | ACCEPTANCE CRITERIA - Checked and approved
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - Completed within two months after Paving Wearing Course
label | RESPONSIBLE PERSON - Renewals Engineer/ Renewals Manager
checkpoint | Quality Assurance Close Out by:
textbox | (name):
date | Date:
label | This record to contract file.
holdpoint | (signature)