## Sheet1
checklist | QA 8 - BGS00# |  | Yes | GPL QA 8 - Below Ground Pipework Checklist - Sewer (CNRM)
checkpoint | Principal Contractor Permits Issued
checkpoint | Set out pits trench depths and runs.
textbox | Drawing & Revision # (or Attach photo below)
textbox | Survey setout completed by:
textbox | Manhole Coordinates - enter Eastings & Northings
textbox | Starting IL established - enter IL
button | Survey confirmed drain started at correct IL | Yes, No
button | Drawings attached | Yes, No
checkpoint | Pipes and fittings comply with relevant Authority and Specification.
note | Spec#: AS3500
textbox | Materials used:
button | Approved by Principal | Yes, No
checkpoint | Bedding material, placement and compaction meets specification.
note | Spec#: AS3500
note | 7mm Q-Minus Bedding
checkpoint | Laying and jointing of pipes - RL and fall
button | PVC pipe with Solvent welded joint | Yes, No
button | Fall achieved | Yes, No
checkpoint | Connections to pits and existing services as per spec and Australian Standards
checkpoint | Hydrostatic tests are carried out as required.
button | Air or Water? | Water, Air
note | Inspected and recorded by Independent Certifier or PIC
checkpoint | Mirror tests completed
textbox | Independent testing company:
button | Inspection report attached | Yes, No
checkpoint | Placement and compaction of backfill and material meets spec - attach applicable reports below
tickbox | Civil specification 13.4: Trench Backfill Service trenches shall be backfilled with General Fill (Type B Material) compacted to 98% SDDR within 500mm below the Subgrade Level and to 95% SDDR below this depth in pavement areas. The moisture content of the compacted material shall be within 0% and +3% of SOMC.
tickbox | 5% Stabilised Sand
textbox | Compaction testing completed by:
button | Compaction report attached | Yes, No
checkpoint | Temporary cover provided to open drain.
checkpoint | PVC/ Plastic caps to open ends
checkpoint | As built information updated onto drawings
button | Drain installed as per nominated drawing | Yes, No
button | Invert levels checked by independent surveyor | Yes, No
note | As Built drawings to be updated as required
checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
note | FINAL SIGN OFF - Pass when work completed and signed off by Geschke Supervisor
note | Company: Geschke Group
note | Phone: 03 9798 1619
note | Address: 45 Pacific Drive, Keysborough
note | Project: Clyde North Primary School
note | Principal: Hutchinsons
checkpoint | Foreman/QA Officer Sign-Offs completed - Click to Attach Signature(s) below
button | Geschke Group Signature Sign-Off added below | Yes, No
button | Principal Contractor Representative Sign-Off added below | Yes, No