## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Window Wall Panel Check (per panel) |  |  |  |  | Yes | ZWindow Wall Panel Check (per panel) (old version) | 012c3893-8b3b-4e3b-94db-8315358a6c6d
checkpoint-status |  |  | checkpoint | 1. Glass is in good condition (attach photos).
checkpoint-status |  |  | checkpoint | 2. No defects/scratch/dents/distortion/crack (attach photos)
checklist-flat |  |  | checklist | Pre-installation |  |  |  |  | Yes | Pre-installation | 1607eb0a-419d-4b59-8ecf-69548880557b
checkpoint-status |  |  | checkpoint | IFC drawings received and current revision approved - photo of title block with revision
checkpoint-status |  |  | checkpoint | All hobs have membrane and no physical damage evident
checkpoint-status |  |  | checkpoint | Floor survey completed and levels within acceptable tolerance
checkpoint-status |  |  | checkpoint | Grid lines established and identified
checklist-flat |  |  | checklist | Curtain Wall Panel Check (per panel) |  |  |  |  | Yes | Curtain Wall Panel Check (per panel) (updated) | 206a13f8-d8db-4000-a8b8-f6ef1796f645
checkpoint-status |  |  | checkpoint | 1. Glass is in good condition (attach photos).
checkpoint-status |  |  | checkpoint | 2. Fins are correctly installed to panel in correct position, including the correct fixings are used. (M5*10 SS316 socket head machine screw for vertical fins, M8*25 SS316 socket head machine screw for horizontal fins)
checkpoint-status |  |  | checkpoint | 3. GRC in good condition, no cracks, damage or other defect. Repairable damage to be repaired after agreeing an appropriate on-site remediation approach. GRC has been installed to curtain wall panel as per design
checkpoint-status |  |  | checkpoint | 4. Weather seal rubber is installed in correct position
checkpoint-status |  |  | checkpoint | 5. Panel weep holes are clear and drilled in correct position.
checkpoint-status |  |  | checkpoint | 6. No defects/scratch/dents/distortion/crack
checklist-flat |  |  | checklist | Curtain Wall General Check |  |  |  |  | Yes | Curtain Wall General Check (by section) (updated) | 4850e2eb-5b66-45a8-9e84-51c1f1faf661
checkpoint-status |  |  | checkpoint | 1. Bracket correctly installed and torqued, drift screw installed, confirm no changes were made to brackets during panel installation. Torque requirement for the T-bolt HBC-C 60 N*m, HBC-C-N 185 N*m confirmed as correct
checkpoint-status |  |  | checkpoint | 2. Aluminium gutter plate at typical locations is installed in correct position and are sealed as per the approved design.
checkpoint-status |  |  | checkpoint | 3. Rubber sleeve at corner area/special locations are installed in correct position and are sealed as per the approved design.
checkpoint-status |  |  | checkpoint | 4. Panel installed in correct position and height, with all required accessories .
checkpoint-status |  |  | checkpoint | 5. Expansion gap between panels is consistent.
checkpoint-status |  |  | checkpoint | 6. Slab edge insulation (Thermal insulation: Chaoming 100mm Insulating rock wool / Fire rated insulation: ABM Fire-rated rock wool,) is installed as per manufacturers requirements. No visible gaps and compacted in accordance with manufacturers requirements
checkpoint-status |  |  | checkpoint | 7. Smoke Seals correctly installed and sealed using Sikasil-WS-305 S Fixing type to subhead: 4.2*13 SS316 pan head screw; Fixing type to concrete: Hilti X-P 20 G3 MX concrete nail, spacing 300mm.
checkpoint-status |  |  | checkpoint | 8. Pelmet and skirting installed in position, with pelmet flush with bottom of transom.
checkpoint-status |  |  | checkpoint | 9. Four way stack joint was sealed at sill profile.
checkpoint-status |  |  | checkpoint | 10. Sliding and swing door open and close in good condition & have the correct/approved hardware. / jockey sash
checkpoint-status |  |  | checkpoint | 11. Jockey sash opens to specified width and operates as specified
checklist-flat |  |  | checklist | Window Wall General Check (by section) |  |  |  |  | Yes | ZWindow Wall General Check (by section) (old version) | 5ff69fca-505e-4ad6-badc-bea7c0a898bd
checkpoint-status |  |  | checkpoint | 1. Sub-sill, subhead and supporting structure (if required) in position. Check expansion bolts are used and nuts are tightened (45N*m for M10 bolts, 60N*m for M12 bolts). Confirm correct torque and no changes were made to sub-frame during panel installation. Gutter plate and sleeve is installed in correct position and is sealed.
checkpoint-status |  |  | checkpoint | 2. Gaps between concrete and sub-sill and sub-head are fully sealed & foam installed for wind.
checkpoint-status |  |  | checkpoint | 3. Fins are correctly installed including capping piece and mechanically fixed to panel in correct position, including the correct fixings are used. Fixing type and sizes confirmed correct (M6*20 SS316 socket head machine screw for fins, 4.2*13 SS316 countersunk screw for caps)
checkpoint-status |  |  | checkpoint | 4. Panel installed in correct position and height with all required accessories, rubber seals are installed
checkpoint-status |  |  | checkpoint | 5. Expansion gap between panels is consistent.
checkpoint-status |  |  | checkpoint | 6. Insulation in between supporting steel structure (Thermal insulation: Chaoming 100mm Insulating rock wool / Fire rated insulation: ABM Fire-rated rock wool, is filled as per manufacturers requirements. No visible gaps and compacted in accordance with manufacturers requirements
checkpoint-status |  |  | checkpoint | 7. Flashing installed in correct positions (internal & external as per design) and sealed.
checkpoint-status |  |  | checkpoint | 8. Pelmet and skirting installed in position, with pelmet flush with bottom of transom.
checkpoint-status |  |  | checkpoint | 9. Sliding and swing door open and close in good condition & have the correct/approved hardware / jockey sash
checkpoint-status |  |  | checkpoint | 10. Jockey sash opens to specified width and operates as specified
checklist-flat |  |  | checklist | Curtain Wall Panel Check (per panel) |  |  |  |  | Yes | ZCurtain Wall Panel Check (per panel) (old version) | 6f1f2c86-ae47-4e49-b0d9-fe65c0f2ecda
checkpoint-status |  |  | checkpoint | 1. Glass is in good condition (attach photos).
checkpoint-status |  |  | checkpoint | 2. No defects/scratch/dents/distortion/crack (attach photos)
checklist-flat |  |  | checklist | Window Wall General Check (by section) |  |  |  |  | Yes | Window Wall General Check (by section) (updated) | 721878d8-2cc0-4cc8-a28a-2c35bf19f790
checkpoint-status |  |  | checkpoint | 1. Sub-sill, subhead and supporting structure (if required) in position. Check expansion bolts are used and nuts are tightened (45N*m for M10 bolts, 60N*m for M12 bolts). Confirm correct torque and no changes were made to sub-frame during panel installation. Gutter plate and sleeve is installed in correct position and is sealed.
checkpoint-status |  |  | checkpoint | 2. Gaps between concrete and sub-sill and sub-head are fully sealed & foam installed for wind.
checkpoint-status |  |  | checkpoint | 3. Panel installed in correct position and height with all required accessories.
checkpoint-status |  |  | checkpoint | 4. Expansion gap between panels is consistent.
checkpoint-status |  |  | checkpoint | 5. Insulation in between supporting steel structure (Thermal insulation: Chaoming 100mm Insulating rock wool / Fire rated insulation: ABM Fire-rated rock wool, is filled as per manufacturers requirements. No visible gaps and compacted in accordance with manufacturers requirements
checkpoint-status |  |  | checkpoint | 6. Flashing installed in correct positions (internal & external as per design) and sealed.
checkpoint-status |  |  | checkpoint | 7. Pelmet and skirting installed in position, with pelmet flush with bottom of transom.
checkpoint-status |  |  | checkpoint | 8. Sliding and swing door open and close in good condition & have the correct/approved hardware / jockey sash
checkpoint-status |  |  | checkpoint | 9. Jockey sash opens to specified width and operates as specified
checklist-flat |  |  | checklist | Window Wall Panel Check (per panel) |  |  |  |  | Yes | Window Wall Panel Check (per panel) (updated) | c67afe4b-a4b1-44ed-9f68-dbf61d8e2118
checkpoint-status |  |  | checkpoint | 1. Glass is in good condition (attach photos).
checkpoint-status |  |  | checkpoint | 2. Fins are correctly installed including capping piece and mechanically fixed to panel in correct position, including the correct fixings are used. Fixing type and sizes confirmed correct (M6*20 SS316 socket head machine screw for fins, 4.2*13 SS316 countersunk screw for caps)
checkpoint-status |  |  | checkpoint | 3. GRC in good condition, no cracks, damage or other defect. Repairable damage to be repaired after agreeing an appropriate on-site remediation approach. GRC has been installed to curtain wall panel as per design
checkpoint-status |  |  | checkpoint | 4. Weather seal rubber is installed in correct position
checkpoint-status |  |  | checkpoint | 5.Panel weep holes are clear and drilled in correct position.
checkpoint-status |  |  | checkpoint | 6. No defects/scratch/dents/distortion/crack
checklist-flat |  |  | checklist | Curtain Wall General Check (by section) |  |  |  |  | Yes | ZCurtain Wall General Check (by section) (old version) | e6727fe7-a67f-4fac-a3dd-56add49606fe
checkpoint-status |  |  | checkpoint | 1. Bracket correctly installed and torqued, drift screw installed, confirm no changes were made to brackets during panel installation. Torque requirement for the T-bolt HBC-C 60 N*m, HBC-C-N 185 N*m confirmed as correct
checkpoint-status |  |  | checkpoint | 2. GRC in good condition, no cracks, damage or other defect. Repairable damage to be repaired after agreeing an appropriate on-site remediation approach. GRC has been installed to curtain wall panel as per design
checkpoint-status |  |  | checkpoint | 3. Fins are correctly installed to panel in correct position, including the correct fixings are used. (M5*10 SS316 socket head machine screw for vertical fins, M8*25 SS316 socket head machine screw for horizontal fins)
checkpoint-status |  |  | checkpoint | 4. Gutter plate and sleeve is installed in correct position and is sealed.
checkpoint-status |  |  | checkpoint | 5. Panel installed in correct position and height, with all required accessories rubber seals are installed.
checkpoint-status |  |  | checkpoint | 6. Expansion gap between panels is consistent.
checkpoint-status |  |  | checkpoint | 7. Slab edge insulation (Thermal insulation: Chaoming 100mm Insulating rock wool / Fire rated insulation: ABM Fire-rated rock wool,) is installed as per manufacturers requirements. No visible gaps and compacted in accordance with manufacturers requirements
checkpoint-status |  |  | checkpoint | 8. Smoke Seals correctly installed and sealed using Sikasil-WS-305 S Fixing type to subhead: 4.2*13 SS316 pan head screw; Fixing type to concrete: Hilti X-P 20 G3 MX concrete nail, spacing 300mm.
checkpoint-status |  |  | checkpoint | 9. Pelmet and skirting installed in position, with pelmet flush with bottom of transom.
checkpoint-status |  |  | checkpoint | 10. Four way stack joint was sealed at sill profile.
checkpoint-status |  |  | checkpoint | 11. Sliding and swing door open and close in good condition & have the correct/approved hardware. / jockey sash
checkpoint-status |  |  | checkpoint | 12. Jockey sash opens to specified width and operates as specified