## Sheet1
1 | Construction Programming | Acceptance | Best Practice Contract MMP | Prior to construction | Meets client expectations and contractor capability | V | To be completed by SouthRoads | Construction Manager | 1 - Construction Programming | VERIFICATION ACTIVITY - Acceptance | METHODS OR REFERENCE - Best Practice Contract MMP | FREQ. - Prior to construction | ACCEPTANCE CRITERIA - Meets client expectations and contractor capability | INSPECTORATE W/H: Type - V | INSPECTORATE W/H: Description - To be completed by SouthRoads | RESPONSIBLE PERSON - Construction Manager | 1 - Construction Programming
2 | Source Material QA Checks: Lean Mixed Concrete - Sub-base Drainage Aggregate Asphalt - Structural base and wearing surface | QA Testing and confirmation of latest results | IANZ Lab Testing Records Contract Specification Section 7.3 | Before supply of each material | Lean Mix Concrete mix design has been approved by Design Engineer. Drainage Aggregate 100% passing 37.5mm sieve with all retained on 19mm sieve Asphalt Mix Designs comply with NZTA M10:2020. Asphalt binders comply with NZTA M/1a | V | Southern Aggregates Ltd / Central Testing Services to provide results for aggregate Downer to provide results for AC20 and AC14 | Aggregates CHAR(AMP) Environment Manager | 2 - Source Material QA Checks: Lean Mixed Concrete - Sub-base Drainage Aggregate Asphalt - Structural base and wearing surface | VERIFICATION ACTIVITY - QA Testing and confirmation of latest results | METHODS OR REFERENCE - IANZ Lab Testing Records Contract Specification Section 7.3 | FREQ. - Before supply of each material | ACCEPTANCE CRITERIA - Lean Mix Concrete mix design has been approved by Design Engineer. Drainage Aggregate 100% passing 37.5mm sieve with all retained on 19mm sieve Asphalt Mix Designs comply with NZTA M10:2020. Asphalt binders comply with NZTA M/1a | INSPECTORATE W/H: Type - V | INSPECTORATE W/H: Description - Southern Aggregates Ltd / Central Testing Services to provide results for aggregate Downer to provide results for AC20 and AC14 | RESPONSIBLE PERSON - Aggregates CHAR(AMP) Environment Manager | VERIFICATION ACTIVITY - Acceptance
3 | Renewal Quality Plan (RQP) | Approval | Contract Specification | Prior to construction | Meets contractual requirements | H | To be approved by contract management and NZTA | Asset Manager | 3 - Renewal Quality Plan (RQP) | VERIFICATION ACTIVITY - Approval | METHODS OR REFERENCE - Contract Specification | FREQ. - Prior to construction | ACCEPTANCE CRITERIA - Meets contractual requirements | INSPECTORATE W/H: Type - H | INSPECTORATE W/H: Description - To be approved by contract management and NZTA | RESPONSIBLE PERSON - Asset Manager | METHODS OR REFERENCE - Best Practice Contract MMP
4 | Traffic Management | Approval | TMP and CAR | 2-3 weeks prior to construction | Meets requirements of CoPTTM | H | To be approved by Road Controlling Authority (RCA) | Traffic management Department manager | 4 - Traffic Management | VERIFICATION ACTIVITY - Approval | METHODS OR REFERENCE - TMP and CAR | FREQ. - 2-3 weeks prior to construction | ACCEPTANCE CRITERIA - Meets requirements of CoPTTM | INSPECTORATE W/H: Type - H | INSPECTORATE W/H: Description - To be approved by Road Controlling Authority (RCA) | RESPONSIBLE PERSON - Traffic management Department manager | FREQ. - Prior to construction
ACCEPTANCE CRITERIA - Meets client expectations and contractor capability
INSPECTORATE W/H: Type - V
INSPECTORATE W/H: Description - To be completed by SouthRoads
RESPONSIBLE PERSON - Construction Manager
2 - Source Material QA Checks: Lean Mixed Concrete - Sub-base Drainage Aggregate Asphalt - Structural base and wearing surface
VERIFICATION ACTIVITY - QA Testing and confirmation of latest results
METHODS OR REFERENCE - IANZ Lab Testing Records Contract Specification Section 7.3
FREQ. - Before supply of each material
ACCEPTANCE CRITERIA - Lean Mix Concrete mix design has been approved by Design Engineer. Drainage Aggregate 100% passing 37.5mm sieve with all retained on 19mm sieve Asphalt Mix Designs comply with NZTA M10:2020. Asphalt binders comply with NZTA M/1a
INSPECTORATE W/H: Type - V
INSPECTORATE W/H: Description - Southern Aggregates Ltd / Central Testing Services to provide results for aggregate Downer to provide results for AC20 and AC14
RESPONSIBLE PERSON - Aggregates CHAR(AMP) Environment Manager
3 - Renewal Quality Plan (RQP)
VERIFICATION ACTIVITY - Approval
METHODS OR REFERENCE - Contract Specification
FREQ. - Prior to construction
ACCEPTANCE CRITERIA - Meets contractual requirements
INSPECTORATE W/H: Type - H
INSPECTORATE W/H: Description - To be approved by contract management and NZTA
RESPONSIBLE PERSON - Asset Manager
4 - Traffic Management
VERIFICATION ACTIVITY - Approval
METHODS OR REFERENCE - TMP and CAR
FREQ. - 2-3 weeks prior to construction
ACCEPTANCE CRITERIA - Meets requirements of CoPTTM
INSPECTORATE W/H: Type - H
INSPECTORATE W/H: Description - To be approved by Road Controlling Authority (RCA)
RESPONSIBLE PERSON - Traffic management Department manager