## Structure Internal
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Resource to use
External Works QA
Internal Checklist Ground Floor
|  | G.01 - Semi Covered Outdoor Space |  |  |  | Internal checklists
|  | G.02 - Lounge |  |  |  | Internal checklists
|  | G.03 - Circulation |  |  |  | Internal checklists
|  | G.04 - Stairwell |  |  |  | Internal checklists
|  | G.05 - Store |  |  |  | Internal checklists
|  | G.06 - WC |  |  |  | Internal checklists
|  | G.07 - Comms |  |  |  | Internal checklists
|  | G.08 - Lift |  |  |  | Internal checklists
|  | G.09 - Circulation |  |  |  | Internal checklists
|  | G.10 - Waiting |  |  |  | Internal checklists
|  | G.11 - SVR |  |  |  | Internal checklists
|  | G.12 - Wind Lobby |  |  |  | Internal checklists
|  | G.13 - Café |  |  |  | Internal checklists
|  | G.14 - Nurse Manager |  |  |  | Internal checklists
|  | G.15 - Admin |  |  |  | Internal checklists
|  | G.16 - Waiting |  |  |  | Internal checklists
|  | G.17 - Circulation |  |  |  | Internal checklists
|  | G.18 - Care Suite - Type CS-1 |  |  |  | Internal checklists
|  | G.19 - Care Suite - Type CS-1 |  |  |  | Internal checklists
|  | G.20 - Care Suite - Type CS-1 |  |  |  | Internal checklists
|  | G.21 - Care Suite - Type CS-1 |  |  |  | Internal checklists
|  | G.22 - Circulation |  |  |  | Internal checklists
|  | G.23 - Care Suite - Type CS-1 |  |  |  | Internal checklists
|  | G.24 - Care Suite - Type CS-1 |  |  |  | Internal checklists
|  | G.25 - DLY CON 1 |  |  |  | Internal checklists
|  | G.26 - Service Room |  |  |  | Internal checklists
|  | G.27 - DB CBD |  |  |  | Internal checklists
|  | G.28 - Comms |  |  |  | Internal checklists
|  | G.29 - Nurse Station |  |  |  | Internal checklists
|  | G.30 - Circulation |  |  |  | Internal checklists
|  | G.31 - Care Suite - Type CS-1 |  |  |  | Internal checklists
|  | G.32 - Care Suite - Type CS-1 |  |  |  | Internal checklists
|  | G.33 - Care Suite - Type CS-1 |  |  |  | Internal checklists
|  | G.34 - Circulation |  |  |  | Internal checklists
|  | G.35 - Care Suite - Type CS-1 |  |  |  | Internal checklists
|  | G.36 - Care Suite - Type CS-1 |  |  |  | Internal checklists
|  | G.37 - Care Suite - Type CS-1 |  |  |  | Internal checklists
|  | G.38 - MSR |  |  |  | Internal checklists
|  | G.39 - DB CBD |  |  |  | Internal checklists
|  | G.40 - Circulation |  |  |  | Internal checklists
|  | G.41 - Care Suite - Type CS - 2.2 |  |  |  | Internal checklists
|  | G.42 - Care Suite - Type CS - 2.2 |  |  |  | Internal checklists
|  | G.43 - Care Suite - Type CS-1 |  |  |  | Internal checklists
|  | G.44 - Care Suite - Type CS-1 |  |  |  | Internal checklists
|  | G.45 - Care Suite - Type CS-1 |  |  |  | Internal checklists
|  | G.46 - Circulation |  |  |  | Internal checklists
|  | G.47 - Care Suite - Type CS-1 |  |  |  | Internal checklists
|  | G.48 - Care Suite - Type CS-1 |  |  |  | Internal checklists
|  | G.49 - Dining/Lounge |  |  |  | Internal checklists
|  | G.50 - Circulation |  |  |  | Internal checklists
|  | G.51 - CM Kit |  |  |  | Internal checklists
|  | G.52 - Riser |  |  |  | Internal checklists
|  | G.53 - Riser |  |  |  | Internal checklists
|  | G.54 - Lift |  |  |  | Internal checklists
|  | G.55 - Stairwell |  |  |  | Internal checklists
|  | G.56 - Store |  |  |  | Internal checklists
|  | G.57 - Circulation |  |  |  | Internal checklists
|  | G.58 - Dirty Linen/ Sluice |  |  |  | Internal checklists
Internal checklists
| Internal Checklist Level 1 | 1.01 - Care Suite - Type CS - 2.2 |  |  |  | Internal checklists
|  | 1.02 - Care Suite - Type CS - 2.2 |  |  |  | Internal checklists
|  | 1.03 - Care Suite - Type CS - 2.1B |  |  |  | Internal checklists
|  | 1.04 - Circulation |  |  |  | Internal checklists
|  | 1.05 - Lift |  |  |  | Internal checklists
|  | 1.06 - Stairwell |  |  |  | Internal checklists
|  | 1.07 - Store |  |  |  | Internal checklists
|  | 1.08 - DB CBD |  |  |  | Internal checklists
|  | 1.09 - Comms |  |  |  | Internal checklists
|  | 1.1 - Circulation |  |  |  | Internal checklists
|  | 1.11 - Care Suite - Type CS - 2.1A |  |  |  | Internal checklists
|  | 1.12 - Care Suite - Type CS - 2.1A |  |  |  | Internal checklists
|  | 1.13 - Care Suite - Type CS - 2.1A |  |  |  | Internal checklists
|  | 1.14 - Care Suite - Type CS - 2.1A |  |  |  | Internal checklists
|  | 1.15 - Care Suite - Type CS - 2.1B |  |  |  | Internal checklists
|  | 1.16 - Care Suite - Type CS-1 |  |  |  | Internal checklists
|  | 1.17 - Staff Room |  |  |  | Internal checklists
|  | 1.18 - Lockers |  |  |  | Internal checklists
|  | 1.19 - Nurse Station |  |  |  | Internal checklists
|  | 1.2 - MDR |  |  |  | Internal checklists
|  | 1.21 - Store |  |  |  | Internal checklists
|  | 1.22 - Riser |  |  |  | Internal checklists
|  | 1.23 - DB CBD |  |  |  | Internal checklists
|  | 1.24 - Riser |  |  |  | Internal checklists
|  | 1.25 - Circulation |  |  |  | Internal checklists
|  | 1.26 - Dining/Lounge |  |  |  | Internal checklists
|  | 1.27 - Private Din |  |  |  | Internal checklists
|  | 1.28 - Kitch |  |  |  | Internal checklists
|  | 1.29 - Circulation |  |  |  | Internal checklists
|  | 1.3 - Care Suite - Type CS - 2.1A |  |  |  | Internal checklists
|  | 1.31 - Care Suite - Type CS - 2.1A |  |  |  | Internal checklists
|  | 1.32 - DLY CON 3 |  |  |  | Internal checklists
|  | 1.33 - DB CBD |  |  |  | Internal checklists
|  | 1.34 - Care Suite - Type CS - 2.2 |  |  |  | Internal checklists
|  | 1.35 - Care Suite - Type CS - 2.2 |  |  |  | Internal checklists
|  | 1.36 - Care Suite - Type CS-1 |  |  |  | Internal checklists
|  | 1.37 - Care Suite - Type CS-1 |  |  |  | Internal checklists
|  | 1.38 - Care Suite - Type CS - 2.1A |  |  |  | Internal checklists
|  | 1.39 - Care Suite - Type CS - 2.1A |  |  |  | Internal checklists
|  | 1.4 - Care Suite - Type CS - 2.1A |  |  |  | Internal checklists
|  | 1.41 - Care Suite - Type CS - 2.1A |  |  |  | Internal checklists
|  | 1.42 - Care Suite - Type CS-1 |  |  |  | Internal checklists
|  | 1.43 - Care Suite - Type CS-1 |  |  |  | Internal checklists
|  | 1.44 - Circulation |  |  |  | Internal checklists
|  | 1.45 - Riser |  |  |  | Internal checklists
|  | 1.46 - Cleaners |  |  |  | Internal checklists
|  | 1.47 - Store |  |  |  | Internal checklists
|  | 1.48 - Data Room |  |  |  | Internal checklists
|  | 1.49 - MSB |  |  |  | Internal checklists
|  | 1.5 - MSR |  |  |  | Internal checklists
|  | 1.51 - Riser |  |  |  | Internal checklists
|  | 1.52 - Lift |  |  |  | Internal checklists
|  | 1.53 - Stairwell |  |  |  | Internal checklists
|  | 1.54 - Sluice |  |  |  | Internal checklists

## Structure External
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Resource to use
External Works QA
External Walls Ground Floor
| Stage 1 | Grid 2 | External Framing |  |  | External framing Pre weather line | External framing post weatherline
|  | Grid A ( Grid 1-5 ) | External Framing |  |  | External framing Pre weather line | External framing post weatherline
|  | Grid N ( Grid 1-5 ) | External Framing |  |  | External framing Pre weather line | External framing post weatherline
| Stage 2 | Grid N | External Framing |  |  | External framing Pre weather line | External framing post weatherline
|  | Grid B ( Grid 8-11 ) | External Framing |  |  | External framing Pre weather line | External framing post weatherline
|  | Grid 0 ( Grid 8-11 ) | External Framing |  |  | External framing Pre weather line | External framing post weatherline
| Stage 3 | Grid C ( Grid 5-8 ) | External Framing |  |  | External framing Pre weather line | External framing post weatherline
|  | Grid N ( Grid 5-8 ) | External Framing |  |  | External framing Pre weather line | External framing post weatherline
External Walls First Floor
| Stage 1 | Grid 2 | External Framing |  |  | External framing Pre weather line | External framing post weatherline
|  | Grid A ( Grid 1-5 ) | External Framing |  |  | External framing Pre weather line | External framing post weatherline
|  | Grid N ( Grid 1-5 ) | External Framing |  |  | External framing Pre weather line | External framing post weatherline
| Stage 2 | Grid N | External Framing |  |  | External framing Pre weather line | External framing post weatherline
|  | Grid B ( Grid 8-11 ) | External Framing |  |  | External framing Pre weather line | External framing post weatherline
|  | Grid 0 ( Grid 8-11 ) | External Framing |  |  | External framing Pre weather line | External framing post weatherline
| Stage 3 | Grid C ( Grid 5-8 ) | External Framing |  |  | External framing Pre weather line | External framing post weatherline
|  | Grid N ( Grid 5-8 ) | External Framing |  |  | External framing Pre weather line | External framing post weatherline

## Resources
Type | Name | Values | Prefix | Postfix | Usage Count | User Addable | Template Name

## Exterior checklists
checklist | External Framing ( Pre Weatherline )
checkpoint | General info/comments recorded
checkpoint | Walls in correct location off grid
checkpoint | Walls built within building tolerances.
checkpoint | DPC under bottom plate against concrete
checkpoint | M16 threaded rods/epoxy installed at correct centres
checkpoint | Timber framing installed at correct centres and size of timber as per drwgs
checkpoint | Amount of timber studs per wall type installed and at wall junctions.
checkpoint | All external openings ( doors and windows ) checks, correct openings and approved
checkpoint | Building Hardware installed on exterior face, i.e. tylok plates
checkpoint | Correct lintel sizes installed as per dwgs S1-03 / S8-10
checklist | External Framing ( Post Weatherline )
checkpoint | Plywood strip installed to take steel brick edge angle
checkpoint | Wrap shield installed into window openings with liquid flash
checkpoint | Wrap shield installed to face of weatherline / interstory installed if req
checkpoint | Soffit framing and linings to balconies
checkpoint | Additional nogs for exterior face ( that will be installed from interior )
checkpoint | Rotheblass or Simpson brackets installed as per S1-03

## Internal Checklists
checklist | Interior Framing
checkpoint | Structural Steel QA received and correct
checkpoint | General information recorded
textbox | installed as per wall type
textbox | Correct timber size/treatment installed
checkpoint | DPC installed, checked and correct as per specification
checkpoint | Wall locations checked, correct and approved as per latest revised drawing
checkpoint | Fixings and hold down bolts checked and correct as per structural dwgs
checkpoint | All openings (doors / windows etc) checked - Refer door supplier shop drawings
tickbox | Track locks installed
checkpoint | Wall checked (straight and plumb) and within tolerance
Checkpoint | Spax screws installed as per structural design
checkpoint | Bracing elements installed as per S1-03
checkpoint | Gib quiet ties installed
checkpoint | All relevant nogs (service and special/fixtures) installed, checked and correct
tickbox | Service nogs checked and approved
tickbox | All other nogs checked and approved
checkpoint | All Wall framing checks completed & Inspections carried out
checklist | Timber Architraves & Skirtings & Jamb liners
checkpoint | Type of skirtings as per drawings
checkpoint | Type of architraves installed as per drawings
checkpoint | Have all the architraves/skirtings been installed with consistent even margin?
checkpoint | Jamb liners installed
Checklist | Doors
Checkpoint | Check opening is correct and plumb
Checkpoint | Doors installed within tolerances
Checkpoint | Fire seal installed if fire door
Checkpoint | Floor gap is correct