## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 8f3a6c48-3638-4c4f-b541-c85021edfad5 |  | checklist | ITR. No 02 L34 COMMUNAL 1&2 - Cut Out |  |  |  |  | Yes | ITR. No 02 L34 COMMUNAL 1&2 - Cut Out | 01e4ef9b-a384-4f3a-a843-37cd14421a3b
checkpoint-status | 0c52b1e1-9895-41ba-a21d-587cea8c578c |  | checkpoint | Refer to drawing to determine cable support route and check separation from data/comms services
checkpoint-status | e4e906f0-f6bf-48ad-82c1-e499e5db8ec4 |  | checkpoint | Cut out for light fittings
checkpoint-status | f1873d24-530e-4254-9b00-a77c7c264018 |  | checkpoint | Cut out switches & GPO’s
checkpoint-status | b286d2e8-a7d4-4299-a1be-77310c91d64d |  | checkpoint | Cut out of kitchen joinery
checkpoint-status | 03fb584c-0771-4a39-9535-b598b930d38c |  | checkpoint | Cut out of any TV, DATA, WAP, CCTV
checkpoint-status | 1566063a-a58d-4df9-b0e8-dace77516b51 |  | checkpoint | Install Fire Boxes and hit all 4 tabs in if applicable
checkpoint-status | 880996e9-bea3-494f-a5c6-146c38bc61f0 |  | checkpoint | Ensure Fire caulking is completed by subcontractor
checkpoint-status | 0eba41c5-f411-46b1-94ff-7d36eece4e13 |  | checkpoint | Ensure area is left clean
checklist-flat | 0f62d89e-57a0-4260-831a-65fe04aeeb47 |  | checklist | Toolbox Meeting |  |  |  |  | Yes | Toolbox Meeting | 02f678ac-d80f-4495-9546-b60235e9f9dd
checkpoint-status | decd8a96-685e-4f28-8e50-47e2bd93d09d |  | checkpoint | Details
text | acd446e9-425e-519b-992d-37c653e93b3a |  | textbox | Location
text | 584c8b07-1952-52fb-96b1-d33f22ebebe2 |  | textbox | Supervisor
text | f2df7993-08bd-55a7-b963-f6a24029d7ac |  | textbox | Date
text | 86bf3f4c-4b87-5460-95df-79f833b3d475 |  | textbox | Time
text | aada1ba2-e42e-522a-ae83-93188c9d606e |  | textbox | Persons present
label | 2edb7a82-9792-5c51-b090-590b130131a1 |  | note | Topics discussed
boolean | 8620ec71-f1d1-5bde-a218-01579e56052b |  | tickbox | - Injuries, near misses and incidents
boolean | dcd8d09c-2b0c-5491-af13-836000890d20 |  | tickbox | - Management of major hazards
boolean | eb62f661-8372-533c-a886-19ced59e43bd |  | tickbox | - Compliance with our Vast SWMS
boolean | 109aba20-cfdb-59df-8651-ead89987567b |  | tickbox | - Safety - E.g., Apply LOTO processes when applicable. When Megger testing ensure that no person is working at the other end of cable being tested.
boolean | f3c0de5c-d953-5538-b42c-851b5412762b |  | tickbox | - Housekeeping
text | a8f4766f-f8aa-5b17-80ae-f20aa19b7cdc |  | textbox | Comments from the floor
checklist-flat | ad8dde0f-2fb1-40d2-99e8-7cbf6d261894 |  | checklist | ITP. No 12 Commissioning |  |  |  |  | Yes | ITP. No 12 Commissioning | 05b2bd78-d963-43bd-b281-511119654eea
checkpoint-status | 4f01d6af-9683-4eb4-83fa-a1e7ab55a71a |  | checkpoint | Prior to energising all personnel involved to be inducted into energisation procedure and all steps undertaken to ensure compliance with this procedure
label | ad5961f1-a763-5ff1-be92-6d18acdba959 |  | note | Obtain fresh copies of current light and power drawings and mark up any changes from the working drawings
label | 743dad50-8333-5281-92ef-c349fb8afcbc |  | note | Obtain copy of distribution board schedule to mark up any additions or deletions found whilst commissioning
label | 3a446221-89f4-5c12-9243-3d57676da2a0 |  | note | Visually Check all items
checkpoint-status | 2c312408-aa6c-42d2-80ee-c63441abb2b9 |  | checkpoint | Dead Testing
checkpoint-status | 5c405023-187e-44c5-b76f-acac5c9007aa |  | checkpoint | Live Test
text | 17ebf3f5-d127-51b8-9cd3-50fb20dc60c7 |  | textbox | Record Metrel Results and log
checkpoint-status | 496a316a-2bae-4a41-96dc-70db3e91174a |  | checkpoint | Check operation of all sensors (individually on minimum time setting )
checkpoint-status | 8e02f37b-0f1f-4346-95c9-511ba1632413 |  | checkpoint | Check sensors are set to specified time and lux
checkpoint-status | 597e68e7-2ac3-4c1e-ab8b-cf83b4456750 |  | checkpoint | Fit Cover Plates to GPOs & Switches (take photos)
checkpoint-status | e5d5f83a-2a76-4b8c-8946-90538f103f16 |  | checkpoint | Install switchboard cover / label (take photos)
checkpoint-status | c4ff04c5-465e-439f-97f5-151178131061 |  | checkpoint | Ensure area is left clean
checklist-flat | b9f0a98b-71c8-43d1-b679-97b5d05755d5 |  | checklist | VAST Site Induction |  |  |  |  | Yes | zSYS - VAST Site Induction | 0b084f9e-8ab2-4400-bb4b-8f82c3d3f404
checkpoint-status | d35e1f12-8c86-4596-a630-074cf84a8d8e |  | checkpoint | VAST Employee
text | a92e0bdc-14c9-5f43-be09-94c9211986b5 |  | textbox | Name
text | 65830ed7-391c-5940-bd44-7a1d659c965a |  | textbox | Contact Number
text | 6d07793e-fe71-58b5-bd74-0121ec45cdf7 |  | textbox | Date of Induction
label | 15fcb0cd-e2d0-5cde-94d6-75dcb6ab10ff |  | note | Tick if the following are understood:
boolean | 9688e55f-7d14-5ea8-bdec-fd6073c39c24 |  | tickbox | How to report to the site and who you report to
boolean | 024ad984-6915-53d0-96cb-3a4e39c16a7a |  | tickbox | The working hours on site
boolean | e90a2b52-ee10-501f-be5c-f9b5ef9cde54 |  | tickbox | Who the managers and supervisors are on site
boolean | 5b733b92-e55f-513a-a4ef-b8baa000da6a |  | tickbox | The correct minimum PPE for site
boolean | 39437b27-c37f-502a-9fc0-889b755e09ac |  | tickbox | How safety is communicated on site
boolean | c3c70dc5-9be9-52d6-a1ec-8f465ccb38f5 |  | tickbox | Where to have lunch and where the toilets are
boolean | 93776f10-4999-594f-8a03-025efe72bcb8 |  | tickbox | Where the First Aid Kit is kept and who is the First Aider
boolean | 1af45bb0-5627-5723-b9b8-742f33bf4083 |  | tickbox | The Emergency Plan and the Assembly Area for Emergency Evacuation
boolean | d7f60aba-c1be-51bc-b34e-7a102095b607 |  | tickbox | What the high risk activities and hazards are on site
boolean | 5a9752b7-a648-524e-a83c-82c807f8500e |  | tickbox | How to report WHS & Environmental hazards & issues
boolean | 64a89327-ae63-53e1-b889-8edc80fbd89c |  | tickbox | How to report a safety or environmental accident or incident
boolean | 020240ae-c688-5079-8c50-1fd165d8afc8 |  | tickbox | Housekeeping responsibilities
checkpoint-status | d45dc258-e0de-4052-ba4b-9c930f5236ab |  | checkpoint | EWP Licence - Please take a photo
checkpoint-status | 820be9f2-3239-48ff-b437-a7d5f21f25e5 |  | checkpoint | Current Certificates Sighted - Please take a photo & comment on each attached certificate
checkpoint-status | eb51d785-48ac-4d58-afe5-8ce1dea34739 |  | checkpoint | VAST Employee Signature
checkpoint-status | 2e616716-948f-402d-954b-4fc0acb2483b |  | checkpoint | VAST Supervisor Signature
checklist-flat | 1e8f9802-974c-4abc-93f0-b3a402bc2de5 |  | checklist | ITR No.0 5 GROUND FLOOR Retail Rough In |  |  |  |  | Yes | ITR No.0 5 GROUND FLOOR Retail Rough In V2 | 0f131d8b-907b-4123-acb2-e5055b8f672c
checkpoint-status | b1b9e447-81a6-4cc5-904a-dfe7b27c012a |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | 3160684a-e67c-4ed8-87c2-52920cd7baa8 |  | checkpoint | Attach copy of drawing
checkpoint-status | 3be04f7e-effd-48d3-88bd-b52cf345963b |  | checkpoint | Ensure no other services are in the way of our cat wire and fittings
checkpoint-status | d9dad251-8783-4130-be0b-906de64c33e0 |  | checkpoint | Rough in lighting, Fans, Emg/Exits, sensors on cat wire
checkpoint-status | a450b2ae-2009-4a65-9154-e319c6149162 |  | checkpoint | Rough in of general power
checkpoint-status | 858a907f-6adb-4a41-99cd-2e1fcad67671 |  | checkpoint | Rough in of any Hand Dryers and HWS to Amenities if applicable
checkpoint-status | 9ffd17e1-fb01-4205-a314-76f4db8a4484 |  | checkpoint | Rough in lighting feed to DB
checkpoint-status | 9d69018e-e962-465d-ac85-535123a500bf |  | checkpoint | Rough in power feed to DB
checkpoint-status | 6fd0909b-7e4b-4957-9820-e723fc03a0e0 |  | checkpoint | Rough in HWS feed to DB if applicable
checkpoint-status | eb1aa97f-89b3-42f7-9c0d-6ba47e0bf4b0 |  | checkpoint | Rough in of tenancy sub main with 8mt coiled on tray for future re location
checkpoint-status | 787b77d6-0cf2-46cf-ae1d-6d7e688d478f |  | checkpoint | Rough in 1x coax from comms room with 6mt coiled
checkpoint-status | bc450a10-5b06-4f7f-a55a-6827a87d7dbd |  | checkpoint | Rough in of any access control
checkpoint-status | a45435b7-9414-4376-af7e-6fc7d3276eae |  | checkpoint | Ensure all rough in has been ticked off on plans once completed
checkpoint-status | 37dae5e5-3caf-4514-9e67-9fa2a44f4f89 |  | checkpoint | Ensure area is left clean
checklist-flat | 1bc5a512-5f42-43b0-b8f5-ce6171f8f8dd |  | checklist | ITP No. 14 Installation of Temp Lights/Power |  |  |  |  | Yes | ITP No. 14 Installation of Temp Lights/Power | 12923875-09aa-4d33-9631-667481e7f628
checkpoint-status | 63e8b102-927f-4038-85c9-6c75def4ab91 |  | checkpoint | Area accessible & ready
checkpoint-status | f6fbc513-8a9f-443f-aaaf-b57c7412e6ee |  | checkpoint | Rough in cable
checkpoint-status | f30e821c-8538-4284-90b1-2fc9a1e812f7 |  | checkpoint | CABLING MUST BE SUPPORTED AND PROTECTED FROM DAMAGE. CONSTRUCTION WIRING TAPE MUST BE FITTED AT EVERY 5 METRES. TEMPORARY WIRING MUST NOT BE INSTALLED WITH PERMANENT CABLING
checkpoint-status | df0f799a-6036-470e-aa69-7f8c8f6a5bb2 |  | checkpoint | Fit off plug base and or powerpoint/isolator
checkpoint-status | d9d77e6e-c326-4d01-a1f9-b82834df21f2 |  | checkpoint | Install light fitting, exit/emg, power
checkpoint-status | 128ff4c7-6bb1-4b88-911d-d0a0c6541a6d |  | checkpoint | Terminate cable to temp board. Ensure temp board is isolated! Test Test Test
checkpoint-status | e959c029-11c6-4875-9636-dc2daea713af |  | checkpoint | Test & commission
label | ea4ec0cf-f5f9-5f28-bfdf-8e7206a717ac |  | note | Lodge non prescribed certificate of electrical safety
checklist-flat | 69d1f956-247e-4494-b649-67d0a0ac4932 |  | checklist | ITR No.7 Hallway - Fit Off Electrical |  |  |  |  | Yes | ITR No.13 Hallway - Fit Off Electrical | 24c64aaa-194f-49c3-a25c-b3f817f6b978
checkpoint-status | a5ec1bd7-0cd9-4e0f-b8bd-6158206e3e55 |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | 0f6b971e-1799-41b1-b25b-51b637f02bf4 |  | checkpoint | Fit off all Lights
checkpoint-status | 34b06b76-f275-40db-adff-53e15ca6ad98 |  | checkpoint | Fit off all Sensors and SET TIME TO MINIMUM
checkpoint-status | b2684887-ad58-4574-b346-443e38412e51 |  | checkpoint | Fit off all EX/EMG’s
checkpoint-status | 7d2f70ae-837c-4f69-8a01-a33daa6ab7f6 |  | checkpoint | Label all EX/EMG’s as per plan number
checkpoint-status | 7a39be5e-0627-4736-81d3-3a68e8b3f1f3 |  | checkpoint | Fit off all Cleaners GPOs
checkpoint-status | a267f2c1-682c-4dbd-a99b-186f02aa4f55 |  | checkpoint | Fit off all Comms Riser GPOs
checkpoint-status | 9f15eb7f-5bc8-41b6-b0fc-9df9dc9ddfce |  | checkpoint | Fit off water meter GPOs
checkpoint-status | fae5cf6e-a4de-43c3-8054-054a45bc2a48 |  | checkpoint | Ensure area is left clean
checklist-flat | e6bf18ca-4fc1-432b-89d1-e5f577f39619 |  | checklist | ITR No.0 5 L12 POOL- Rough In |  |  |  |  | Yes | ITR No.02 L12 POOL- Rough In V2 | 2d4682c7-5af8-435d-be48-756701903821
checkpoint-status | 7a3223f9-385b-4f95-a202-1439d123bcfa |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | d6cc5949-e345-4b80-b520-68df1a5ec7d6 |  | checkpoint | Attach copy of drawing
checkpoint-status | e503a86b-0e08-4931-8761-87126fa5db2f |  | checkpoint | Rough in 6mm Earth to Pool Reo
checkpoint-status | 25cbcafe-eefb-4c83-8deb-46cb7d0d975b |  | checkpoint | Rough in of lighting
checkpoint-status | 92452c32-cdea-4e83-86f3-51322fc4e34a |  | checkpoint | Rough in of exits
checkpoint-status | 1beb990a-ff43-4534-bc70-6ce5e93b268c |  | checkpoint | Rough in of general power
checkpoint-status | 797bf26e-8848-405f-9767-5ebd4f8719f5 |  | checkpoint | Rough in of any isolators
checkpoint-status | e4eb7911-e0b7-4515-bae1-fe1486b709db |  | checkpoint | Rough in lighting feed
checkpoint-status | 396aa164-add4-4324-92e8-270620deef61 |  | checkpoint | Rough in power feeds
checkpoint-status | 2e29798a-4353-44c8-b70e-8d7923f3a7f5 |  | checkpoint | Rough in of CCTV
checkpoint-status | 0d1d7a58-1389-4b48-b133-53da1afe5ae1 |  | checkpoint | Rough in of any access control
checkpoint-status | a0c2d2fb-32b6-405d-b2a9-8f4d8be25e7b |  | checkpoint | Ensure all rough in has been ticked off on plans once completed
checkpoint-status | e33d50a3-8d03-44a0-87f1-18c51a826453 |  | checkpoint | Ensure area is left clean
checklist-flat | fb407478-c60d-4016-8175-a63f6aff2395 |  | checklist | ITP No. 19 Installation of Temp Boards |  |  |  |  | Yes | ITP No. 19 Installation of Temp Boards | 32ee1893-f6b6-4df4-b4c5-8b9e66f9fa6d
checkpoint-status | 7e318865-6385-4c0b-86af-e676a6a5bafc |  | checkpoint | Area accessible & ready
checkpoint-status | e9c07443-8770-4cd6-be47-5ecb2396739a |  | checkpoint | Position and fix switchboard to deck on 350mm threaded rod and feet & ensure it's level
checkpoint-status | 84f5f87b-bdcf-49d4-9fbb-70cfbebdd424 |  | checkpoint | Drill 50mm hole on a join and ensure there is no timber underneath & install 50mm conduit
checkpoint-status | e73b0ab6-3e78-436c-8aeb-dd2afe95d8a0 |  | checkpoint | Cabling must be supported and protected from damage. construction wiring tape must be fitted at every 5 metres.
checkpoint-status | a157377b-0c37-4d83-8538-9aba1af90622 |  | checkpoint | Terminate Sub Main to downstream temp board below. Ensure temp board is isolated! Test Test Test
checkpoint-status | 4339b245-5ad6-4456-a742-e3b2744c75f0 |  | checkpoint | Test & commission new temp board
checkpoint-status | f6bd368c-0941-4bd7-830b-cdb3edca227c |  | checkpoint | Install temp light to side of new temp board
checkpoint-status | acbf51b7-26c8-42d6-920a-259313679586 |  | checkpoint | Install A3 laminated sign on face of temp board with floor plan and where the board is fed from
label | 8856c776-9d54-5202-91f9-4900da502b06 |  | note | Lodge non prescribed certificate of electrical safety
checkpoint-status | 52a4dc22-35da-4175-bf06-e290b8ffbbe3 |  | checkpoint | RCBO'S must be fully tested initially and then tested every month with results recorded and c/b’s labelled
checklist-flat | d06873a8-184b-4106-9a40-522ff78453e3 |  | checklist | ITR No.3 Apartment - Electrical Fit Off |  |  |  |  | Yes | ITR No.13 Apartment - Electrical Fit Off | 36fb7844-fe57-4a59-bb4a-03ff7dfa6005
checkpoint-status | dfc78bf2-b67e-4961-ac1f-094f1ef0aac5 |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | 32855991-1c9a-4b6f-92c2-3ecd72d48be7 |  | checkpoint | Fit Off Downlights
checkpoint-status | 36e9bba3-ff6d-4969-86dd-f43cd0d6f027 |  | checkpoint | Fit Off Track Light if applicable
checkpoint-status | 1b4658aa-3079-4149-b06c-311313642b45 |  | checkpoint | Fit Off Smoke Detectors ( leave tab & dust cover on )
checkpoint-status | be453f16-2995-46bb-a889-37d94efc36e9 |  | checkpoint | Fit off joinery GPO's & install cover plates.
checkpoint-status | 4d484d66-1168-4b67-9461-001705116219 |  | checkpoint | Fit off Laundry GPO & switch
checkpoint-status | 37e7d167-f3ac-480f-9f8c-b6bd9c03b10b |  | checkpoint | Fit off all GPOs - Install cover plates & switches where required
checkpoint-status | abce2ef4-cc5a-4f40-8708-b6c80327bebb |  | checkpoint | Fit off light switches
checkpoint-status | 24d90609-5771-4bc6-af55-cf8140f7207b |  | checkpoint | Fit off TV Point
checkpoint-status | 051634bb-43d0-428a-a3c8-8d69ce81776a |  | checkpoint | Fit Off Data Points
checkpoint-status | 3ada87d6-948d-4fef-aa39-681539d9599a |  | checkpoint | Fit Off WP GPO ( if applicable )
checkpoint-status | dde3fac2-ceab-4999-8abc-f99f03511ad6 |  | checkpoint | Fit off Intercom Handset
checkpoint-status | 9aa82000-95b7-4f4f-a981-d84e724ec588 |  | checkpoint | Fit Off Kitchen LED Strip
checkpoint-status | b14829eb-3a20-4ae9-9537-8fe1e0753ba0 |  | checkpoint | Install Oven
checkpoint-status | f2602774-f067-42b0-8807-888bc000709f |  | checkpoint | Ensure area is left clean
checklist-flat | a93bc58a-e43f-4e99-be48-d0257bbeda67 |  | checklist | ITR. No 02 GYM Cut Out |  |  |  |  | Yes | ITR. No 02 GYM Cut Out | 3709e8e3-e12a-4908-a954-bf0f4728eb7d
checkpoint-status | c4fdb9ef-9ba2-4df5-8b27-c4a7f424f862 |  | checkpoint | Refer to drawing to determine cable support route and check separation from data/comms services
checkpoint-status | 0187189d-11d5-4b08-ba90-995340a8d0a5 |  | checkpoint | Cut out for light fittings
checkpoint-status | 2f796290-e783-40b9-985b-c33ce411b777 |  | checkpoint | Cut out switches & GPO’s
checkpoint-status | 1ade7759-4d48-4e8d-8d40-1dd4df6ec28d |  | checkpoint | Cut out of TV,WAP, CCTV
checkpoint-status | e47b100a-94df-4fdb-9b6c-1afac4ac901a |  | checkpoint | Install Fire Boxes and hit all 4 tabs in if applicable
checkpoint-status | 43fd1b71-7ff0-47fb-87d1-d6b7f8ff3e28 |  | checkpoint | Ensure Fire caulking is completed by subcontractor
checkpoint-status | 254f1ce4-0a22-4339-ba9d-381425f0a9dc |  | checkpoint | Ensure area is left clean
checklist-flat | bd5161e9-4a3a-4a89-a3e4-abe24364579d |  | checklist | ITP. No 12 Install DB's - Terminate Sub Main Cables |  |  |  |  | Yes | ITP. No 12 Install DB's - Terminate Sub Main Cables | 3782f857-d6f5-43ed-93ec-d087e9f9440c
checkpoint-status | 4b70b76c-95e6-4dab-8a13-580b1fdc643b |  | checkpoint | Delivery check for damage, paint finish, dimensions and doors against approved shop drawing
checkpoint-status | 47d002fa-3424-4d0b-ba9f-7f09675246da |  | checkpoint | Locate & fix into position
checkpoint-status | 852b6801-17b6-44ab-a535-6effa69528e8 |  | checkpoint | Install sub mains cabling as appropriate eg. glands, tray, duct
checkpoint-status | 6f80e138-96f2-4159-a81b-c9284ce4c70f |  | checkpoint | Install lugs and terminate
label | 401a573e-f763-515c-9208-022483cc96ba |  | note | Any cables not terminated prior to energisation must be removed from the cubicle at origin and have ends covered in heatshrink
label | b852d57f-aef3-54ee-bf40-192b40747546 |  | note | At destination cables must be covered in heat shrink and be contained in a junction box
checklist-flat | 510fff39-0039-4a01-9424-eef8e4afbff8 |  | checklist | ITR No.1 Apartment Rough In of Electrical Services |  |  |  |  | Yes | ITR No.1 Apartment Rough In of Electrical Services V2 | 38a5c0bb-b5bb-49dd-9a7e-4dab44703984
checkpoint-status | af1be884-e487-494f-bf76-e26de00adc79 |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | a2631f45-a117-4efd-bdf1-cdd526e9bbb4 |  | checkpoint | Attach copy of drawing
checkpoint-status | f4137e93-d561-40e2-8e97-2c875c207d8e |  | checkpoint | Rough in Hard Actives to all switches
checkpoint-status | 7f8da244-8a8d-4855-8d18-f6d2a848b299 |  | checkpoint | Rough in of Switched Actives from switches to lights & Fit off Quick connects whilst on ladder
checkpoint-status | d057594c-ef58-4a00-8e4b-68b2296f20da |  | checkpoint | Rough in GPOs
checkpoint-status | 4d2310e9-3bfb-4750-b00f-60ccf4b5b97a |  | checkpoint | Rough in of all kitchen general power (including island bench) above bench, gas cooktop, fridge, microwave, rangehood & dishwasher
checkpoint-status | b5a87d7a-a481-4b3d-a5da-f483a4a1d09b |  | checkpoint | Rough in Oven
checkpoint-status | 468a0f70-a81e-48a7-b835-6d06f1bc03b7 |  | checkpoint | Rough in track lighting
checkpoint-status | 4ccf2711-b9c8-4ae3-91ab-f62649b2bd0e |  | checkpoint | Rough in kitchen led strip to rangehood off nearest kitchen/AB Power Point
checkpoint-status | c5238084-5086-4b8d-8e73-21b82ebf8ef9 |  | checkpoint | Rough in all internal lights
checkpoint-status | d42f6a8e-61fc-4a6b-a6a3-aac4244bdfc5 |  | checkpoint | Rough in smoke detector and interconnect to other detectors.
checkpoint-status | 03b6b581-d225-4e3f-9332-fd9ad30e455d |  | checkpoint | Rough in bathroom fans off power circuit and HA loop at fan
checkpoint-status | 8fc02522-a1c0-40be-8a90-6e53969c00c3 |  | checkpoint | Rough in WM/DR and install SDI from dryer gpo to laundry switch
checkpoint-status | c1da7729-1ffc-4c92-a9f9-b21296cd5e76 |  | checkpoint | Rough in WP GPO to balcony if applicable
checkpoint-status | e1319925-1f12-47e7-818e-b15f827e696d |  | checkpoint | Rough in intercom patch lead to LBNCO hub
checkpoint-status | 9ab2f4bf-7a24-424c-9438-ccfa7c17bc9c |  | checkpoint | Rough in tv points to LBNCO hub
checkpoint-status | 3879d15a-84c7-4f1d-9b4c-71eb047231b7 |  | checkpoint | Rough in data points to LBNCO hub
label | ce51df45-1b46-5791-9d94-a8bd86e590db |  | note | Ensure Sub Mains are at Switchboard Location
checkpoint-status | 14d8f8e1-2bea-442f-9191-202edc709181 |  | checkpoint | Install switchboard & fit off
button | a83bced8-a6f0-561a-be1c-453f18534b89 |  | button | Install 150mm stud protecting sub main and earth with nut & bolt | Yes,No,N/A
button | 38fd4cc3-e6e3-5f6d-9b09-4056fa297bdb |  | button | Install 2.5mm earth tags | Yes,No,N/A
button | dd0e64fe-5b16-53a5-a071-289a29ff95ac |  | button | Fire caulk sub main into DB and all cable entries | Yes,No,N/A
button | c42b5c4e-bdc7-50e8-a3a3-f27e9587742a |  | button | Fit off 4 pin plug base | Yes,No,N/A
checkpoint-status | 563da93a-6960-494b-bae6-a7402f61cfcc |  | checkpoint | Ensure all Quick Connects are fit off
button | 510701eb-39d7-5658-b423-6571a637ed6e |  | button | Ensure all cables are neat, taped to studs and easily accessible for cut out | Yes,No,N/A
button | 4f463ce9-5901-5518-8332-97b4eb5e5438 |  | button | Ensure all cables are clearly labelled at DB and at party walls | Yes,No,N/A
checkpoint-status | 5e144dfe-b9b8-49cd-8fbe-751420564f36 |  | checkpoint | Ensure area is left clean
checklist-sectioned | c753d542-9cbb-4e96-bd51-3d3ae4900ba0 |  | checklist | ITP No. 01 Conduit in Slab |  |  |  |  | Yes | ITP No. 01 Conduit in Slab | 3d8d7b1c-5a64-4c41-aa20-ff74503e9e80
checkpoint-group | fb36ba72-9222-465f-9d77-abf620b1052f |  | section | Preparation
checkpoint-status | 654aa30c-46a6-42d1-a552-7c9587e5458a |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | dbad5182-46a4-4835-95b6-7aeb135b84bc |  | checkpoint | Determine origin and destination of riser cupboards
checkpoint-status | cd49ec25-16cc-4e2b-8e59-ea7c944875e2 |  | checkpoint | Check clear of other services, penetrations etc
checkpoint-status | a3294b22-9bb3-4f1c-aea8-98fce6e6b5da |  | checkpoint | Check cable size to verify conduit size
checkpoint-status | 33a1d051-0d1e-417b-985c-1ec9b99e382c |  | checkpoint | Mark out positions of junction boxes, orange flanges and penetrations where necessary
checkpoint-status | 9f33084d-7071-4217-99f2-353e6eafd294 |  | checkpoint | Check if expansion joints are required
checkpoint-group | 3ad24412-28e9-45f4-b667-b364398fd1fd |  | section | Installation
checkpoint-status | eede911e-7769-4410-aedc-4e07273f9fff |  | checkpoint | Installation of sleeves for stair lights - NOTE (feeds level 12 & 34)
checkpoint-status | e0ba01a1-f9ec-49fc-8fe9-9598dfc321e2 |  | checkpoint | Core conduit sleeves given to Oracle Core workers for installation
checkpoint-status | 4458e080-d0bd-4016-9005-677d25466831 |  | checkpoint | Installation of foam at riser cupboards if applicable. Foam to be duct taped and secured down to deck.
checkpoint-status | fe40c024-85f3-4df7-8bc8-9078a64e1c29 |  | checkpoint | Install junction boxes, flanges and conduits with glue
checkpoint-status | fac3dc0a-55c5-446e-828c-4d3456d5ca60 |  | checkpoint | Install 25mm or 32mm conduit from riser to each apartment DB
checkpoint-status | f24d4d1b-132a-4d3c-9a87-ef48d1cabefb |  | checkpoint | Install timber and conduit box for track lighting and conduit to be brought back to plaster ceiling
checkpoint-status | 6a7c9b6d-5bb2-44fc-a0e9-913a7309b798 |  | checkpoint | Install 25mm conduit from kitchen to island bench where applicable
checkpoint-status | 4a51314c-434e-45b2-95b3-fb6459e98efc |  | checkpoint | Install reo turned up in riser cupboard for earthing of the slab
checkpoint-status | 2c88f5a4-c55f-475a-8ebc-040204e30039 |  | checkpoint | Install any temp conduits where necessary for alimak lighting and temp toilets
checkpoint-status | 0478f181-ddc4-4f25-bbb2-c2ab372f3bdd |  | checkpoint | Install reo for pool turned up at an accessible spot on level 12
checkpoint-status | 707a989f-f0f0-4cda-a1fc-89031a884182 |  | checkpoint | Install 32mm conduit on level 12 deck for accessible lift- refer to level 12 power plan
checkpoint-status | 8097f715-f0ba-4d1c-bead-61403f3388f0 |  | checkpoint | Ensure all conduits are 50mm above deck
checkpoint-status | 0834d62b-e90f-4e97-a776-c8c8f0053f57 |  | checkpoint | Ensure all conduits are tied and secured
checkpoint-status | a9cba722-8460-4b74-9a9f-0083eca7ca36 |  | checkpoint | Ensure all conduits for the next pour are through to the next deck
checkpoint-status | 032c0f8a-1f1a-4b55-97ce-7de9c36ca4cd |  | checkpoint | Clean any mess left on deck
checkpoint-status | 911c6382-181f-46e1-84fd-09512e0d6c6f |  | checkpoint | Final walk through and mark up plan of conduit runs for as builts.
checklist-flat | 3960a082-73d3-4c55-9b19-5d57ad094f63 |  | checklist | ITR No.0 5 L12 LOUNGE/DINING- Rough In |  |  |  |  | Yes | ITR No.02 L12 LOUNGE/DINING- Rough In V2 | 3fbc1537-1563-4701-a2f6-6c8a4d0f477b
checkpoint-status | 2ee540d7-4ac0-435d-8a66-224a79e09bf3 |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | 01689955-2684-4165-a3f5-0d441a6e30f6 |  | checkpoint | Attach copy of drawing
checkpoint-status | 7687632e-abec-42b6-8bda-d0900814ffab |  | checkpoint | Ensure no other services are in the way of our cat wire and fittings
checkpoint-status | 8c5e850d-fc1d-4375-a1d5-dae242cf820d |  | checkpoint | Rough in lighting, Fans, Emg/Exits, sensors on cat wire
checkpoint-status | 76e4af79-0744-4e13-a4f1-51368f189a06 |  | checkpoint | Rough in of general power
checkpoint-status | db3a1941-c7c9-4494-b659-48228e0bfe32 |  | checkpoint | Rough in of kitchen power INCLUDING any dedicated circuits
checkpoint-status | d7df95a8-f811-4a5e-90b8-321a05158397 |  | checkpoint | Rough in of any Exhaust Fans, Hand Dryers and HWS to Amenities if applicable
checkpoint-status | 7eba54af-4bd2-43c5-af72-ac5bb4319793 |  | checkpoint | Rough in lighting feed
checkpoint-status | 6fdfa9be-f7e5-43e9-83ae-7d9b64e32c63 |  | checkpoint | Rough in power feeds
checkpoint-status | 6a688cb9-7853-4bf2-abfc-8d4b97f94cbe |  | checkpoint | Rough in HWS feed to DB if applicable
checkpoint-status | f51abe5e-8a41-413b-9b33-33b18883bd7e |  | checkpoint | Rough in TV, CCTV, WAP
checkpoint-status | eaa59e29-8286-4335-984c-40388232ae64 |  | checkpoint | Rough in of any access control
checkpoint-status | 4b5fb9a6-89c7-4bfe-8ea5-7e355f483894 |  | checkpoint | Ensure all rough in has been ticked off on plans once completed
checkpoint-status | 99327d93-3360-45e8-8900-91fa5019d335 |  | checkpoint | Ensure area is left clean
checklist-flat | 3370ba79-1158-4cdf-8868-65d57e79723c |  | checklist | Documents |  |  |  |  | Yes | zSYS - Documents (old version) | 462223dd-1d8e-4870-a5c4-670871848c07
checkpoint-status | 48bd296f-3d5b-4803-953a-9c1e48997426 |  | checkpoint | Attach Document
checklist-flat | 15f587a9-12a3-4440-8ead-9b9f7a729f3c |  | checklist | ITR. 12 Switchboard Commissioning |  |  |  |  | Yes | zSYS - ITR. 12 Switchboard Commissioning (old version) | 48825b6a-6c31-45c8-8a26-4fbd6ea94732
checkpoint-status | 339372b4-8802-409d-ac35-468579314893 |  | checkpoint | Prior To Energising All Personnel Involved To Be Inducted Into Energisation Procedure And All Steps Undertaken To Ensurecompliance With This Procedure
checkpoint-status | 81f1b60e-45e6-43f1-a5fc-4b0fb6bbc560 |  | checkpoint | Refer To As Installed Drawings
checkpoint-status | 5819828b-b53c-4f53-823f-5cf25390f72b |  | checkpoint | Obtain Copy Of Switchboard Schedule And Schematic Drawings
checkpoint-status | 159e1e87-d911-4942-9489-6e26d4f371c0 |  | checkpoint | Mark Up Any Additions Or Deletions Found Whilst Commissioing
checkpoint-status | 76236304-3ec3-4d32-94f4-63b6421d7405 |  | checkpoint | Complete Visual Checks
checkpoint-status | c2f9782f-083c-4ee2-807d-209a0de9ace2 |  | checkpoint | Refer To Mandatory Testing From As/Nzs 3000:2018 8.3.3 Below
checkpoint-status | 00b91733-1f1e-4437-a06c-e45f1259b3bd |  | checkpoint | Complete Mandatory Tests Using Metrel Tester, Save And Log Results On Tester
checkpoint-status | 2b12a846-cf0e-40da-90e3-4ad02553ddc1 |  | checkpoint | Any Failed Results To Be Rectified Saved And Logged On Tester
checkpoint-status | 3454e879-85d0-40d4-930c-5432e7534345 |  | checkpoint | Ensure Correct Opertation Of All Control/Equipment Installed In Switchboard
checkpoint-status | 08788112-b9f4-40b0-a77e-afaa9a3da4ab |  | checkpoint | Ensure Vast Witness Test Has Been Completed
checkpoint-status | d34d263e-1fc9-4105-a1a2-b134a7e87425 |  | checkpoint | Ensure Escutcheons, Pole Fillers, Fixing Screws Are Reinstated
checkpoint-status | abfdc64c-8639-45c8-a0d0-53d9557e3cb7 |  | checkpoint | Ensure No Access To Live Parts
checkpoint-status | a99987a3-faa9-4257-a195-36a7fb13baaf |  | checkpoint | Complete Switchboard Schedules On Vast Template, Install And Fix To Allocated Postion In Switchboard
checkpoint-status | 9712a94d-46d8-437a-bcab-2b6bc374433c |  | checkpoint | Download Test Results From Metrel Tester And Save To Project Folder
checkpoint-status | e6071971-0a13-4b98-bef1-228e18970f17 |  | checkpoint | Complete Certificate Of Electrical Safety And Save To Project Folder
checklist-flat | 8722c2e5-1aad-4917-b768-054ea44f6f4b |  | checklist | ITR No.7 - L34 PLANT- Fit Off |  |  |  |  | Yes | ITR No.13 - L34 PLANT- Fit Off | 4ecce727-31c9-444d-96e1-be0602ad1c9a
checkpoint-status | 987b6eae-30b5-4b0f-b530-29802e4437cf |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | 34edba7a-def1-4e5f-8e4e-784a32ca6fa9 |  | checkpoint | Fit off all Lights
checkpoint-status | 13012a1c-32dc-47ab-ac7c-2a62c9d8db5e |  | checkpoint | Fit off all EX/EMG’s
checkpoint-status | 4f996e6a-4b53-4d2f-91e9-71abba6c27ab |  | checkpoint | Label all EX/EMG’s as per plan number
checkpoint-status | ee3ab5b5-8ac6-442b-9a84-5dd88c14be6d |  | checkpoint | Fit off all GPOs
checkpoint-status | d8ffd42a-f480-4591-87c3-0c3c500115a4 |  | checkpoint | Ensure all fit off has been ticked off on plans once completed
checkpoint-status | 21cb1edb-c745-4424-abd2-4e23132f453f |  | checkpoint | Ensure area is left clean
checklist-flat | 569d5d0c-6391-444b-a1f7-a14fcb4fcbb1 |  | checklist | ITR No.05 L34 COMMUNAL 1&2- Rough In |  |  |  |  | Yes | ITR No.02 L34 COMMUNAL 1&2- Rough In V2 | 54d946ce-ae51-453a-84ec-12098ef45560
checkpoint-status | 6b3fd226-fca7-4461-b58f-72b2eece0a01 |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | c44a0ee3-4299-4491-bc24-15983b646b75 |  | checkpoint | Attach copy of drawing
checkpoint-status | b405262d-5abe-4d5a-844e-9aa49d57848b |  | checkpoint | Ensure no other services are in the way of our cat wire and fittings
checkpoint-status | b0b722f3-8b95-417f-bf2a-80f0adddef35 |  | checkpoint | Rough in lighting, wall lights, ex/emg
checkpoint-status | 5625b883-d584-46dc-a703-5b8a63cd5ceb |  | checkpoint | Rough in of general power
checkpoint-status | a082427c-824d-4c34-8a65-e5a6c7b169b2 |  | checkpoint | Rough in of kitchen power INCLUDING any dedicated circuits
checkpoint-status | ebe3b2a6-4b15-4b58-b34e-df13416a9cba |  | checkpoint | Rough in of any Exhaust Fans, Hand Dryers and HWS to Amenities if applicable
checkpoint-status | ef00bfb1-ef44-4cf7-b9ff-eb5861184ec3 |  | checkpoint | Rough in lighting feed
checkpoint-status | 85d2081b-d9f1-4172-995f-bd44b5f608e3 |  | checkpoint | Rough in power feeds
checkpoint-status | e038399a-2729-4b9c-ae90-76412e49d2c5 |  | checkpoint | Rough in any TV,DATA, CCTV, WAP
checkpoint-status | ddf1c527-1afc-4f79-8ee2-52e6951ae241 |  | checkpoint | Rough in of any access control
checkpoint-status | b27372fb-8ff8-4ab8-9ec8-182067d97209 |  | checkpoint | Ensure all rough in has been ticked off on plans once completed
checkpoint-status | 63ae6c94-f483-42ad-8585-fcb1d8f84c49 |  | checkpoint | Ensure area is left clean
checklist-flat | d6f68c21-9ca0-416c-8059-10633735c2e8 |  | checklist | ITP No. 20 Decommission Temporary Power Board |  |  |  |  | Yes | ITP No. 20 Decommission Temporary Power Board | 56867010-5434-4ae6-8838-f6720478d122
checkpoint-status | 6fbb9059-d1d9-4730-b1cd-7631632a84f0 |  | checkpoint | Determine what the temporary board is controlling and confirm what action is required before board can be decommissioned.
label | f56ca11a-2ee4-54e6-83a6-f572f173c541 |  | note | De-commission form issued to builder, 48 hours notice to be given
checkpoint-status | b80c7e40-d5a4-4ae9-b4aa-54b45a07fc3c |  | checkpoint | Sign off builders checklist
checkpoint-status | f55e82df-5884-4923-8f82-6f7b52e42e36 |  | checkpoint | Safety Committee Inspection
checkpoint-status | b35a8d7e-bc67-4272-909b-7a4b3f816358 |  | checkpoint | Final approval to be given by builder
checkpoint-status | 75bc8d82-5f47-4a9c-b24c-ca3cb23e154e |  | checkpoint | Perform voltage test to ensure power supply has been isolated
checkpoint-status | 34f41781-8c75-41ec-99f7-91b2b955771a |  | checkpoint | Disconnect supply cables
checkpoint-status | 7a7461fe-d965-4fa2-8cd1-b55243fc38aa |  | checkpoint | Fire sealing of penetrations
checkpoint-status | 62683517-9c98-4a50-9e79-a8656a8eb793 |  | checkpoint | Remove temporary board
checkpoint-status | 0d933450-729a-450e-8704-0532a01385aa |  | checkpoint | Update temporary power board register
checklist-flat | b82fe91a-6e87-4085-8bb2-ef16cc49a763 |  | checklist | ITP. No 13 Commissioning of DB's- TENANCY |  |  |  |  | Yes | ITP. No 13 Commissioning of DB's- TENANCY | 79dc15a8-0c9d-4410-a007-303058adcdb0
checkpoint-status | b36246f4-c60f-450f-8f92-4fc6611d4496 |  | checkpoint | Prior to energising all personnel involved to be inducted into energisation procedure and all steps undertaken to ensure compliance with this procedure
label | ea06224a-3636-5423-88c9-47eca353a63c |  | note | Obtain fresh copies of current light and power drawings and mark up any changes from the working drawings
label | bae029af-6cb8-5417-ac6c-fc2306c0e9aa |  | note | Obtain copy of distribution board schedule to mark up any additions or deletions found whilst commissioning
label | d6dc4c39-07b0-5bfd-8251-3266c0b5cc3f |  | note | Visually Check all items
checkpoint-status | 7264f7aa-6ad7-46b5-bee9-66cd4fa87287 |  | checkpoint | Dead Testing
checkpoint-status | 45aa6a0b-16e2-4078-b937-750043d64aa2 |  | checkpoint | Live Test
text | 9986d4c9-ab5f-5b56-9926-3234b1997a87 |  | textbox | Record Metrel Results and log
checkpoint-status | b9024561-9a0b-4c3a-b132-22af61c2b995 |  | checkpoint | Fit Cover Plates to GPOs & Switches (take photos)
checkpoint-status | 2784d0c7-44fd-4feb-9a4a-a545627f7b9f |  | checkpoint | Install switchboard cover / label (take photos)
checkpoint-status | 79e37df3-96b4-4ef0-9340-a1fd679b52fe |  | checkpoint | Ensure area is left clean
checklist-flat | b9426256-961f-4b6a-8ca7-f716765050dd |  | checklist | ITR. No 02 Tenancy Cut Out |  |  |  |  | Yes | ITR. No 02 Tenancy Cut Out | 7eefd0c7-8a5b-4559-b029-01af75141000
checkpoint-status | 2ac68a1c-260b-4c8f-8d53-1f88d413b4d3 |  | checkpoint | Confirm sizes of all fittings prior to cut out
checkpoint-status | 84c68118-db94-4e6f-9b5d-3f471044ccf9 |  | checkpoint | Cut out all sensors,emg/exits, light fittings
checkpoint-status | 059e64ab-ee1f-49fa-bead-19f31a99e594 |  | checkpoint | Cut out all gpos
checkpoint-status | 03c469df-718f-4ac8-a39e-648f8f8eee3b |  | checkpoint | Cut out all switches/isolators
checkpoint-status | 628842ce-3667-48ac-a75b-00f39c69dbd8 |  | checkpoint | Cut out any CCTV/DATA
checkpoint-status | 9eef73cc-9346-4ae8-8ba1-d00108d36fd3 |  | checkpoint | Locate all cables
checkpoint-status | cfb3a785-efe4-4e39-ba00-9e87fa86e81b |  | checkpoint | Install Fire Boxes and hit all 4 tabs in if applicable
checkpoint-status | 62e49c64-152d-4c37-bf7a-6f30530e2472 |  | checkpoint | Ensure area is left clean
checklist-flat | 1150baae-fb89-429e-8b7c-177eb9c6fb65 |  | checklist | ITR. No 04 Apartment Commissioning |  |  |  |  | Yes | ITR. No 04 Apartment Commissioning | 7ef74c2c-0827-44da-a530-99f1f22a0b70
checkpoint-status | a8783f2f-85d6-4f8f-8a2a-e674fe8bfd56 |  | checkpoint | Energisation permit completed prior to energisation
checkpoint-status | a6753faf-bcc6-4133-b058-7adb97f65221 |  | checkpoint | Visual Check all items
checkpoint-status | 8a2f5f96-4ae3-4401-88f4-0bcd16ea1ff5 |  | checkpoint | Dead Testing
checkpoint-status | 039a086a-67b1-4699-80e1-32fa69aae913 |  | checkpoint | Live Test
checkpoint-status | 2fa4bf7a-5c83-43ee-b4e5-98335e5516ba |  | checkpoint | Record Metrel Results and log
checkpoint-status | 54b07ec5-9005-43f6-ad08-08f0a4f48fa6 |  | checkpoint | Test 4 pin plug base for switching
checkpoint-status | a306b1b1-5bc0-4a0d-9d8e-cd3f66be09fe |  | checkpoint | Check light switches for correct switching functions
checkpoint-status | fdda2bd6-48a0-4779-944e-a35824b29e56 |  | checkpoint | Fit Cover Plates to GPOs & Switches (take photos)
checkpoint-status | 752ec3c8-6cfa-4d2a-a296-feee9e369a2e |  | checkpoint | Install switchboard cover / label (take photos)
checkpoint-status | 98f16b7a-2db0-452d-98bf-5a48ef3e543b |  | checkpoint | Remove battery tabs on smoke detectors ( after MFB certification )
checklist-flat | 24fd261b-72e2-4475-9277-f03043a71b4b |  | checklist | Documents |  |  |  |  | Yes | Documents | 81281be7-e697-4423-8c13-f1ce5ad20fa7
checkpoint-status | 4efceb2d-6bed-468b-83e8-a839b3ee18c5 |  | checkpoint | Attach Document
checklist-flat | dde90936-c7dd-40b7-88ad-10c62d7283bf |  | checklist | ITP. No 12 Install DB's & Terminate (TENANCY) |  |  |  |  | Yes | ITP. No 12 Install DB's & Terminate (TENANCY) | 83100ef1-18c2-4536-a29c-600143a6bdeb
checkpoint-status | 788babb4-44e0-4b42-bc0b-02bc63905abf |  | checkpoint | Delivery check for damage, paint finish, dimensions and doors against approved shop drawing
checkpoint-status | 8e6aa4c1-ab2f-4719-9882-935531b91cea |  | checkpoint | Locate & fix into position
checkpoint-status | c37474e9-fd47-4863-a8d3-7f0be57b0375 |  | checkpoint | Install sub mains cabling and leave a 8mt coil on tray
checkpoint-status | 3ca8f872-51ff-4862-809a-04936b2e0e2b |  | checkpoint | Install lugs and terminate
checkpoint-status | 7470a56d-c202-42c0-bfa7-0c061a18e4a6 |  | checkpoint | Fit off sub circuits
checkpoint-status | a169e556-4d47-4528-be3f-a762c7ee337e |  | checkpoint | Fit off of any Mechanical sub main to mech board if applicable
label | bd39aa22-d4ea-5e72-ae12-0f9d9bf192b5 |  | note | Any cables not terminated prior to energisation must be put in connectors and labelled
checkpoint-status | e5014e43-5bd8-4dab-a64a-68c4caef587a |  | checkpoint | Vacuum board
checklist-flat | f10ca17f-8db4-4bc9-8067-5c5a14eeb71d |  | checklist | ITR No.0 5 Ground Rough In (vehicle access/main switch room) |  |  |  |  | Yes | ITR No.0 5 Ground Rough In (vehicle access/main switch room) V2 | 8c50132e-0867-457a-a136-1f3401e540ee
checkpoint-status | 413df5d7-a18c-40c4-89e7-39594a66fbeb |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | 0abf5379-aa2d-47fa-a787-c56271ed2f44 |  | checkpoint | Attach copy of drawing
checkpoint-status | e6cf7608-bfc8-4e10-8b2c-5c412b246527 |  | checkpoint | Rough in of all lighting circuits- inc Emg/Exits and sensors
checkpoint-status | 0036ce93-b34f-456c-8342-1fab75a08424 |  | checkpoint | Rough in of all external wall lights
checkpoint-status | ecd3331c-6583-4f14-8622-40ccb6e46e77 |  | checkpoint | Rough in of all power circuits
checkpoint-status | 95e8f462-0c2a-4452-96a9-2354e05cf5d4 |  | checkpoint | Rough in all lighting feeds and label on plan
checkpoint-status | 13db40d4-858d-4038-8954-7fc866743e4f |  | checkpoint | Rough in all power feeds and label on plan
checkpoint-status | 2b9c0700-aa13-42bd-a59b-50a6088640f8 |  | checkpoint | Installation of cable tray from MSR
checkpoint-status | 3c540537-20e8-431d-853b-1b19dbe88816 |  | checkpoint | Rough in CCTV
checkpoint-status | 6619f421-c0df-478f-8b92-5e1b016c5f52 |  | checkpoint | Check for clashes with other services
checkpoint-status | 3090faea-88a1-4021-9831-7520b005681f |  | checkpoint | Level fire caulked by contractor
checkpoint-status | 4b123816-ae84-4a72-9d61-ce8871bce3a6 |  | checkpoint | Ensure area is left clean
checklist-flat | dd4a8afb-bdcd-4081-a650-8ec4f082a518 |  | checklist | ITR No.0 5 Tenancy- Rough In |  |  |  |  | Yes | ITR No.0 5 Tenancy- Rough In V2 | 8f630c92-436a-4543-83d3-60598e4e9691
checkpoint-status | 6cd530b7-777c-4835-b2fb-6b640e715c0e |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | 0305d230-f648-49b5-8088-5e28faf44692 |  | checkpoint | Attach copy of drawing
checkpoint-status | 24c05113-a01e-4445-9af1-5f6de4637395 |  | checkpoint | Ensure no other services are in the way of our cat wire and fittings
checkpoint-status | bfbb89ea-09c8-4d69-8fca-513ce6778ef5 |  | checkpoint | Rough in lighting, Emg/Exits, sensors back to the switch board
checkpoint-status | 4e89c858-85cf-4bf9-bfbd-a4417d370e99 |  | checkpoint | Rough in of lighting switch panels twin actives back to switch board
checkpoint-status | 9954275e-cd83-4867-89db-22e33c452624 |  | checkpoint | Rough in of general power
checkpoint-status | 5a4f66b7-6b33-4c7d-9011-4537ee1115ea |  | checkpoint | Install cable tray to plan
checkpoint-status | ac6d09d1-6b1b-4972-ada8-f8840b4f86d4 |  | checkpoint | Rough in of tenancy sub main with 8mt coiled on tray for future re location
checkpoint-status | 1dfeaefd-120e-4c7e-8d47-2a4236f42bb7 |  | checkpoint | Rough in of Mechanical sub main if applicable
checkpoint-status | 1838057d-740e-4e05-b8ae-bfa811ca574a |  | checkpoint | Rough in coax from with 6mt coiled
checkpoint-status | 8c82a2eb-170e-4e5e-8dce-8d1a30a728dd |  | checkpoint | Rough in of intercom
checkpoint-status | fc2191b8-6830-48ae-a6ea-5a1f0e2aee8a |  | checkpoint | Rough in of any access control
checkpoint-status | 68494ce4-7b65-43d4-912e-bab5a7e3b208 |  | checkpoint | Ensure all rough in has been ticked off on plans once completed
checkpoint-status | 55f29cdc-0401-4e92-93bb-a13d8874924e |  | checkpoint | Ensure area is left clean
checklist-flat | 75440135-23a2-4af7-9855-b7d344960b53 |  | checklist | ITR No.7 - L34 COMMUNAL 1&2- Fit Off |  |  |  |  | Yes | ITR No.13 - L34 COMMUNAL 1&2- Fit Off | 90dda3c1-b839-4c07-bc14-9c1856a78ec6
checkpoint-status | 0897ae54-b608-48cb-ab47-35892eb68f8e |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | 9cd4589c-8e06-4415-bd2f-49a1d6d1e612 |  | checkpoint | Fit off all Lights
checkpoint-status | 7c2bfbe1-e6f5-4782-a3b1-50eb7665b2f2 |  | checkpoint | Fit off all switch panels
checkpoint-status | ebaafa28-19f0-4abf-a6fc-89c57930b317 |  | checkpoint | Fit off all EX/EMG’s
checkpoint-status | 0f1345c2-7c00-440b-84a3-04f51c9d2890 |  | checkpoint | Label all EX/EMG’s as per plan number
checkpoint-status | aa76d56c-fa9a-4430-b112-c72d8638004d |  | checkpoint | Fit off all GPOs
checkpoint-status | 8b7d383b-fe24-47f0-aa3f-aedee222ab9a |  | checkpoint | Fit off of 4 pin plug base
checkpoint-status | 6da0a395-8e9d-4345-98cc-e33a0a87af46 |  | checkpoint | Fit off of all kitchen joinery
checkpoint-status | a3667f64-cdab-400d-aa5b-1fda1709b65c |  | checkpoint | Fit off of any TV & Data points
checkpoint-status | 5290bc6a-9999-4e19-812b-25f2b320d906 |  | checkpoint | Fit off of any WAP & CCTV
checkpoint-status | 10272bbb-e9e4-42ac-9583-88b34a130f5b |  | checkpoint | Ensure all fit off has been ticked off on plans once completed
checkpoint-status | 493da61e-464c-44ad-b70f-3e24a6351fde |  | checkpoint | Ensure area is left clean
checklist-flat | 7e2adece-0796-468e-b3d3-608d5513ded8 |  | checklist | ITR No.7 - TENANCY Fit Off |  |  |  |  | Yes | ITR No.13 - TENANCY Fit Off | 91567b6f-61b1-4395-9ffb-a699fdc791ac
checkpoint-status | b2ff8966-4fc9-4d28-b8b0-8537df028709 |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | f73e8af2-fbb5-463d-a0a5-54c45c0ac120 |  | checkpoint | Fit off all Lights
checkpoint-status | 550eb31e-4444-4ba0-8989-2603d8d93f04 |  | checkpoint | Fit off all Sensors and SET TIME TO MINIMUM
checkpoint-status | d01278aa-d554-4f75-ba32-75a9b9bf7f23 |  | checkpoint | Fit off of switch panels
checkpoint-status | 39f16d35-de55-4ed7-9cbf-a2eece22dca9 |  | checkpoint | Fit off all EX/EMG’s
checkpoint-status | d36228ec-055f-4184-96be-092c1755014e |  | checkpoint | Label all EX/EMG’s as per plan number
checkpoint-status | 02f5dd38-30e4-4880-a2f9-48cfcb31a863 |  | checkpoint | Fit off all GPOs
checkpoint-status | 8358c953-e0e2-44fb-b349-187ad5752e3b |  | checkpoint | Ensure all fit off has been ticked off on plans once completed
checkpoint-status | 9189f507-7759-4d09-83ef-b0822e265e9b |  | checkpoint | Ensure area is left clean
checklist-flat | 4157e8a9-aa43-428f-bdbf-37735326b427 |  | checklist | ITR No.05 L34 PLANT- Rough In |  |  |  |  | Yes | ITR No.02 L34 PLANT- Rough In V2 | 9387feb8-eda1-4f2f-a149-e60bd9fa2a6f
checkpoint-status | 212eb4d6-ca9c-47bc-a2c8-b384a78e0822 |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | 441b4752-eb32-49dd-861b-6d5ce51e299e |  | checkpoint | Attach copy of drawing
checkpoint-status | 51ce1097-01b6-43d1-b975-774ee8b83b36 |  | checkpoint | Ensure no other services are in the way of our cat wire and fittings
checkpoint-status | a5fa03af-569f-47eb-84d6-24c9b4d04c92 |  | checkpoint | Rough in lighting
checkpoint-status | 1c21045d-1cf5-4b97-8633-13493ddc132b |  | checkpoint | Rough in of general power
checkpoint-status | 8b51ece0-8d89-40c1-8016-3eecd78443b6 |  | checkpoint | Rough in lighting feed
checkpoint-status | 5360fff2-59df-479c-a3ad-8f33bd9e5ec6 |  | checkpoint | Rough in power feeds
checkpoint-status | 94bf16b8-8b85-469d-8622-41fdf5132bc9 |  | checkpoint | Rough in of any access control
checkpoint-status | 21a85dfc-6860-4f02-bde3-d99e64f6e447 |  | checkpoint | Ensure all rough in has been ticked off on plans once completed
checkpoint-status | 45cf17d6-d9fd-4978-a15c-116e14e54a43 |  | checkpoint | Ensure area is left clean
checklist-flat | b920721a-976a-4b7b-bdc7-7a976b9768cf |  | checklist | ITP. No 12 Install DB's & Terminate (pool) |  |  |  |  | Yes | ITP. No 12 Install DB's & Terminate (pool) | 96b8b89a-c77d-4244-8d64-98b67483fb71
checkpoint-status | 92fa202c-6ac4-48e8-8763-f3b50a963265 |  | checkpoint | Delivery check for damage, paint finish, dimensions and doors against approved shop drawing
checkpoint-status | d56441bb-e828-4004-9a4d-9d536c58a5fc |  | checkpoint | Locate & fix into position
checkpoint-status | 414dc2b3-b7ac-48b2-baa0-c10145545cce |  | checkpoint | Install sub mains cabling
checkpoint-status | 8338c1d7-2fa2-4eac-9b1e-2b7820d3a150 |  | checkpoint | Install lugs and terminate
checkpoint-status | 0c54dd7f-77b4-493b-bdbc-34cb96efe92f |  | checkpoint | Fit off sub circuits
label | adeaa90c-e384-5de3-aeb8-f49bed9f95d8 |  | note | Any cables not terminated prior to energisation must be put in connectors and labelled
checkpoint-status | ad6a6f32-8228-488d-ad75-79de6104ecad |  | checkpoint | Vacuum board
checklist-flat | 754720dc-e2fd-4f56-813a-3a9c8338a59f |  | checklist | ITR No.0 5 GROUND FLOOR Retail Rough In |  |  |  |  | Yes | zSYS - ITR No.0 5 GROUND FLOOR Retail Rough In V1 | 973f94d9-0307-4764-9516-da7b88e391d6
checkpoint-status | b59546c4-0e7a-4ae0-9521-0731099ef391 |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | b6e4fe70-d761-45c0-ad8c-68f8dd374de0 |  | checkpoint | Ensure no other services are in the way of our cat wire and fittings
checkpoint-status | a0e49784-a914-4610-9ad8-85fc96d7b0b3 |  | checkpoint | Rough in lighting, Fans, Emg/Exits, sensors on cat wire
checkpoint-status | bd44e735-6c57-441a-b96f-73beedfbf3f3 |  | checkpoint | Rough in of general power
checkpoint-status | 4107b712-99ba-40e1-a128-bbe091060afa |  | checkpoint | Rough in of any Hand Dryers and HWS to Amenities if applicable
checkpoint-status | 2cb6ae22-a5c3-492b-b402-db80f4b172d2 |  | checkpoint | Rough in lighting feed to DB
checkpoint-status | 4662abd0-2161-427d-becb-df0c2031e2b8 |  | checkpoint | Rough in power feed to DB
checkpoint-status | 0d18d15a-b931-4ca4-affb-26acb454626c |  | checkpoint | Rough in HWS feed to DB if applicable
checkpoint-status | 4b726a37-ac82-4b9b-9fd2-81a6e4ad7f02 |  | checkpoint | Rough in of tenancy sub main with 8mt coiled on tray for future re location
checkpoint-status | f83f841c-2078-46e0-bfc6-83e11da9c2f4 |  | checkpoint | Rough in 1x coax from comms room with 6mt coiled
checkpoint-status | 34c97ede-82aa-4794-a713-d44e557412b5 |  | checkpoint | Rough in of any access control
checkpoint-status | 8aaf61c0-8ee3-4711-b3e9-bc948a07a852 |  | checkpoint | Ensure all rough in has been ticked off on plans once completed
checkpoint-status | 08bfb418-a834-4f64-87f8-b0a21fccd4d7 |  | checkpoint | Ensure area is left clean
checklist-flat | 4d1c8ef2-d93b-44e1-9c19-3795e9d2ed45 |  | checklist | ITR No.7 Ground Fit Off (lobby/back of house) |  |  |  |  | Yes | ITR No.13 Ground Fit Off (lobby/back of house) | 97d8d9f7-91c1-427d-a597-008432eb9ad7
checkpoint-status | 4df6d776-d512-4faf-a971-683500b2b82d |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | b6239eab-456b-498a-b01b-a3ee661fee7e |  | checkpoint | Fit off all Lights
checkpoint-status | 2475ff73-a3ed-4a73-8d5c-1276783c9786 |  | checkpoint | Fit off all Sensors and SET TIME TO MINIMUM
checkpoint-status | 65faea7a-ee2a-4643-b780-7bfd7aba437c |  | checkpoint | Fit off all EX/EMG’s
checkpoint-status | 6e191202-7d8f-40c0-bb4c-adc2dad58253 |  | checkpoint | Label all EX/EMG’s as per plan number
checkpoint-status | 324fd203-587d-4c11-80e6-bf3837b2fe34 |  | checkpoint | Fit off all GPOs
checkpoint-status | 4b926d2e-c14c-45a2-8bad-21b91932c1db |  | checkpoint | Fit off of all isolators (hand dryers, refuse room 3 phase)
checkpoint-status | 98873abd-d5a1-4172-beb3-3d6f3b6fff55 |  | checkpoint | Fit off Earth clamp to water meter assembly
checkpoint-status | e283e763-c277-4548-a732-95d598413f9a |  | checkpoint | Fit off of comms room power
checkpoint-status | 3981c063-8f81-4e2b-80bf-4423e78a46a3 |  | checkpoint | Ensure all fit off has been ticked off on plans once completed
checkpoint-status | 6f5c89e2-fb6f-4249-88a0-92d7e19f1872 |  | checkpoint | Ensure area is left clean
checklist-flat | 993e1e0e-77cf-4cc5-98c5-6f50250cb197 |  | checklist | ITR No.0 5 Ground Rough In (vehicle access/main switch room) |  |  |  |  | Yes | zSYS - ITR No.0 5 Ground Rough In (vehicle access/main switch room) V1 | adf939e0-63d9-4f40-8738-bc44706e45ba
checkpoint-status | 4af93409-fc96-4c3c-b212-88946bb85e55 |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | 4b62fe7c-1475-4462-bb14-6ff1f307b288 |  | checkpoint | Rough in of all lighting circuits- inc Emg/Exits and sensors
checkpoint-status | ee867d11-fb78-48e4-b082-06048fd90f06 |  | checkpoint | Rough in of all external wall lights
checkpoint-status | 67f9d97c-735d-4354-bd26-8d02af3362bc |  | checkpoint | Rough in of all power circuits
checkpoint-status | 6585cd51-54ad-4066-aefa-a0f78423ed91 |  | checkpoint | Rough in all lighting feeds and label on plan
checkpoint-status | 2923bda7-d272-47eb-aada-424870bf60b1 |  | checkpoint | Rough in all power feeds and label on plan
checkpoint-status | 4b5c4e64-92eb-4556-8bf1-f456961414f9 |  | checkpoint | Installation of cable tray from MSR
checkpoint-status | e8894225-a011-431c-b384-fcaf3bb6752a |  | checkpoint | Rough in CCTV
checkpoint-status | 6acd7abd-2e2f-4f99-97e1-c0b8a2e43051 |  | checkpoint | Check for clashes with other services
checkpoint-status | f8678395-73bd-4288-9de8-ecee5d4796c7 |  | checkpoint | Level fire caulked by contractor
checkpoint-status | 4e2c7f65-f305-47af-a2c5-3bb2cb153384 |  | checkpoint | Ensure area is left clean
checklist-flat | fd4c3c5a-9d53-4e05-847e-8d3c3be3d93b |  | checklist | ITR No.0 5 L12 Outdoor Area- Rough In |  |  |  |  | Yes | ITR No.02 L12 Outdoor Area- Rough In V2 | b2dacf84-4fae-4ce8-a62e-1d98071ced00
checkpoint-status | 22831f68-d7e6-4b23-a941-1601fed1cb28 |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | ef47ff6a-072f-4a33-b5a5-78a32eb91171 |  | checkpoint | Attach copy of drawing
checkpoint-status | 566c95b2-db04-4879-aeb1-34ad9db9f9df |  | checkpoint | Rough in of wall lights
checkpoint-status | 62d90ebc-da5e-4cc6-9fde-42ee042f6f18 |  | checkpoint | Rough in of exits
checkpoint-status | b50aca44-454c-4c2a-a556-2176bb3fe57e |  | checkpoint | Rough in of general power
checkpoint-status | 0761175d-59ab-4a4c-bcb4-c4cd1eb5e358 |  | checkpoint | Rough in of 2 BBQ circuits
checkpoint-status | 3026ba88-1e30-4aa4-9269-0e917117a469 |  | checkpoint | Rough in of any isolators
checkpoint-status | db1b89a3-c404-49cc-bd37-6874b4a58ace |  | checkpoint | Rough in lighting feed
checkpoint-status | c44bf130-de50-4f47-8ce6-ff4a13c3e40b |  | checkpoint | Rough in power feeds
checkpoint-status | 7537bd50-fdea-438f-897c-5c67cdde3b34 |  | checkpoint | Rough in HWS feed to DB if applicable
checkpoint-status | 4b3e24c8-09ca-417a-83bd-fd0885312630 |  | checkpoint | Rough in of CCTV
checkpoint-status | 37975518-97ca-4f07-a395-9f9f208e779d |  | checkpoint | Rough in of any access control
checkpoint-status | 18fd7e1b-d660-46c4-8713-31b34790f44e |  | checkpoint | Ensure all rough in has been ticked off on plans once completed
checkpoint-status | f1c29911-a903-4fdd-a91d-8ca680a9423f |  | checkpoint | Ensure area is left clean
checklist-flat | 2349eb90-4121-4676-842e-e5a4988c5608 |  | checklist | ITR No.7 Ground Fit Off (vehicle access/main switch room) |  |  |  |  | Yes | ITR No.13 Ground Fit Off (vehicle access/main switch room) | b56047a4-44e4-40ac-97ea-66525feca3e3
checkpoint-status | 6a54a366-a3a0-4fd0-a51c-29291a4ce476 |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | b2f464e6-4d68-496f-bb85-e8d0d665ad75 |  | checkpoint | Fit off all Lights
checkpoint-status | fb887541-b2e7-41aa-93fa-d80b97c051f8 |  | checkpoint | Fit off all EX/EMG’s
checkpoint-status | 651f6814-9646-4bb4-b4dd-2909b4988590 |  | checkpoint | Label all EX/EMG’s as per plan number
checkpoint-status | f3598873-9ca3-46a9-882c-355d63019c56 |  | checkpoint | Fit off all GPOs
checkpoint-status | 9a536ad6-0824-47e6-aeaf-9d53542b5dd6 |  | checkpoint | Fit off of Roller Door Isolators
checkpoint-status | 7b442c90-1b7e-4e17-ab3f-6f7046c7936a |  | checkpoint | Fit off of CCTV
checkpoint-status | 26c23150-a565-4dd0-be28-5bcbff67b5d9 |  | checkpoint | Ensure all fit off has been ticked off on plans once completed
checkpoint-status | 35f1dfba-e26f-4b76-8548-0f9cda095f4c |  | checkpoint | Ensure area is left clean
checklist-flat | b647dd9d-2a0d-4940-a8a2-23af82dc85b1 |  | checklist | ITR. No 02 OUTDOOR AREA - Cut Out |  |  |  |  | Yes | ITR. No 02 OUTDOOR AREA - Cut Out | b96dbfc0-f218-44ab-a989-1af301b78c95
checkpoint-status | 1fd97582-0b2e-4ddf-a11c-3db3f620cb8c |  | checkpoint | Refer to drawing to determine cable support route and check separation from data/comms services
checkpoint-status | e2c83698-701c-4597-b187-e06efa5056a2 |  | checkpoint | Cut out for light fittings
checkpoint-status | 04bed92b-7fe0-4339-95f1-64b67c1927d6 |  | checkpoint | Cut out GPO’s
checkpoint-status | c3f66479-9462-4290-99da-b83b45d6db8f |  | checkpoint | Cut out of CCTV
checkpoint-status | b7bbeeb2-b170-41ad-99f7-f97438145c2b |  | checkpoint | Install Fire Boxes and hit all 4 tabs in if applicable
checkpoint-status | cf3155b0-1cfc-4e74-8008-94170a77bb2f |  | checkpoint | Ensure Fire caulking is completed by subcontractor
checkpoint-status | 0c8015c1-9c0a-492b-9f39-8e72217fc892 |  | checkpoint | Ensure area is left clean
checklist-flat | 9cc872ed-1e70-499b-b668-416d6474a4ca |  | checklist | ITR No.7 - OUTDOOR AREA- Fit Off |  |  |  |  | Yes | ITR No.13 - OUTDOOR AREA- Fit Off | ba44e1da-94aa-48dd-97e4-ae79d6ea4da1
checkpoint-status | 9f6da0d3-f51b-4305-84e9-b3befd7b6c6f |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | 8fab8fb7-22f6-48ee-938e-ed658f15d629 |  | checkpoint | Fit off all Lights
checkpoint-status | b682a015-7ad9-49d3-9794-ce4f0d7d5ef7 |  | checkpoint | Fit off all EX/EMG’s
checkpoint-status | a4c2ed3b-f0f5-4690-83e6-4885228ead73 |  | checkpoint | Label all EX/EMG’s as per plan number
checkpoint-status | 5bbabdd3-65e5-4b44-9358-70ce14deb9d3 |  | checkpoint | Fit off all GPOs
checkpoint-status | 1194d6c6-4ce3-4e92-aa71-e69f0008411d |  | checkpoint | Fit off of isolators
checkpoint-status | 246ba14e-7431-4622-9da6-6045a702c66a |  | checkpoint | Fit off of CCTV
checkpoint-status | 6be8266a-bc4f-4fab-9040-f8efbac27b23 |  | checkpoint | Ensure all fit off has been ticked off on plans once completed
checkpoint-status | f8286a3c-9e91-4732-b7c9-82b990d76abd |  | checkpoint | Ensure area is left clean
checklist-flat | a92ee252-b413-41ff-bfdc-32f7d5ac78f3 |  | checklist | ITR No.02 Hallway Rough In |  |  |  |  | Yes | ITR No.02 Hallway Rough In V2 | bd0794b2-b4e7-47c3-aca4-927135b7429b
checkpoint-status | 1efcf904-a50a-4b51-a82f-946572c59fa6 |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | 5f277334-2489-4222-93e3-d6cb7c8a06d4 |  | checkpoint | Attach copy of drawing
checkpoint-status | 5825b1e8-04ab-48b6-ac8c-846492d9ac3a |  | checkpoint | Mark out all public L+P in hallway
checkpoint-status | d22a73d1-3520-4e95-935b-12a460255202 |  | checkpoint | Rough in lighting, Emg/Exits and sensors
checkpoint-status | 9660f863-abf8-4ede-825a-3c22968e5394 |  | checkpoint | Rough in general power OC1
checkpoint-status | 9a5f06b7-169b-4005-a043-43051928768a |  | checkpoint | Rough in cleaners power & water meter power OC2
checkpoint-status | 7256f5bc-cf03-4936-9843-41e938e7ee22 |  | checkpoint | Rough in of any Hand Dryers and HWS to Amenities
checkpoint-status | b597934e-9673-4beb-93a2-a9eba3e36d77 |  | checkpoint | Rough in comms riser power
checkpoint-status | 0ae3cd8d-a801-4cb4-8945-e39418e1e008 |  | checkpoint | Rough in lighting feed to first emergency point opposite elec riser OC1
checkpoint-status | 9fbcb78e-d0c9-471b-99b9-feea88577170 |  | checkpoint | Rough in lighting feed to emergency at commercial lift OC2
checkpoint-status | d515292e-1acd-403c-a0ac-ce3254bee3f3 |  | checkpoint | Rough in power feed to first cleaners point near elec riser
checkpoint-status | bb2a9d4e-430d-4350-a984-2f76f4437a7b |  | checkpoint | Rough in all apartment sub mains from riser to apartment DBs and LABEL
checkpoint-status | a6d10319-0ff6-48fb-8bf1-928e35fdd39d |  | checkpoint | Rough in stair doors access control
checkpoint-status | 04ac6ffa-a858-45da-9d36-b85654e253bb |  | checkpoint | Rough in any relevant comms/access control from one floor to another ( Backbone )
checkpoint-status | 403fdabd-99fb-480f-9b73-e85e139fbe82 |  | checkpoint | Check for clashes with other services
checkpoint-status | 89c33d76-0224-482b-9908-aeaadd0cffeb |  | checkpoint | Level fire caulked by contractor
checkpoint-status | f3f303e9-fe8f-450e-91bb-d985f8f2d423 |  | checkpoint | Fit off plug bases & quick connects
checkpoint-status | a4695afb-c2bd-44d5-849a-10673294c0e6 |  | checkpoint | Ensure area is left clean
checklist-flat | 421abc2f-aff4-4692-8396-607ed5b51399 |  | checklist | VAST Site Induction |  |  |  |  | Yes | zSYS - VAST Site Induction (old version) | c20d6f81-48a6-4fc6-87b8-a164936620a2
checkpoint-status | 484d217c-5157-41e1-ab70-d472c995f5df |  | checkpoint | VAST Employee
text | a0926760-c5b2-510e-945e-d49918dfee5b |  | textbox | Name
text | 7f56172b-d752-5d15-a885-1b9883ba24f5 |  | textbox | Contact Number
text | 12387fb9-e9c4-5501-b346-bbe7119fae36 |  | textbox | Date of Induction
label | c203cd75-13d5-53d7-9fcc-dc1dca498248 |  | note | Tick if the following are understood:
boolean | 6bbaa396-948d-5207-b431-8a018eee4761 |  | tickbox | How to report to the site and who you report to
boolean | 1e32e803-12e5-5b84-9605-5f2d4af51aca |  | tickbox | The working hours on site
boolean | 448bc8df-3cc5-5eb4-ae32-e8720ea81487 |  | tickbox | Who the managers and supervisors are on site
boolean | 42832778-b65d-53e7-a7a7-978e587fef82 |  | tickbox | The correct minimum PPE for site
boolean | fc4af3b4-0449-5462-a315-b69f21f34180 |  | tickbox | How safety is communicated on site
boolean | c815c54b-c7f6-5148-854c-73e2e79628b2 |  | tickbox | Where to have lunch and where the toilets are
boolean | a4c47da8-15ca-59ec-9636-9200788095e3 |  | tickbox | Where the First Aid Kit is kept and who is the First Aider
boolean | e9df7948-0a91-5caa-99c3-7602ca2f7fc7 |  | tickbox | The Emergency Plan and the Assembly Area for Emergency Evacuation
boolean | 5766791f-ba8b-5aeb-9cff-bfb1c612ac88 |  | tickbox | What the high risk activities and hazards are on site
boolean | 01ca9c4b-6171-5c5c-ba22-13ff6a79894e |  | tickbox | How to report WHS & Environmental hazards & issues
boolean | 98c191de-09ad-50df-84c8-866eff1f55c9 |  | tickbox | How to report a safety or environmental accident or incident
boolean | 16b9ef28-8c10-5a9a-bf37-efd459e03cd1 |  | tickbox | Housekeeping responsibilities
checkpoint-status | 37f73d27-6663-419a-85ea-c6f814389584 |  | checkpoint | EWP Licence - Please take a photo
checkpoint-status | a46477ac-eeb4-4fd1-8b8c-50d266358318 |  | checkpoint | Current Certificates Sighted - Please take a photo & comment on each attached certificate
checkpoint-status | b24d3d9b-3245-46a5-b97e-29500fb67e8e |  | checkpoint | VAST Employee Signature
checkpoint-status | 18863848-2126-44cd-8f9b-a0d5c8592d42 |  | checkpoint | VAST Supervisor Signature
checklist-flat | e6d0c59a-b639-41d2-90f8-01b69bb6e7a6 |  | checklist | Pre Start Meeting V2 |  |  |  |  | Yes | Pre Start Meeting V2 | c27eb2e4-4775-4d75-b364-4abfcaa7a409
checkpoint-status | 83072a95-3b8f-4e92-893e-bdd178c6a678 |  | checkpoint | Details
text | 8d6955b3-6b74-5c3b-b128-509a44a29ea3 |  | textbox | Conducted by
text | 40e810f9-9808-569c-9fcc-a4775b45464e |  | textbox | Area
checkpoint-status | 9687ede3-0c61-4f1b-9cbf-43d2b03b3d10 |  | checkpoint | Any Safety Concerns from last meeting - add comments if required
text | 29cb16fa-86c4-555f-ae84-e30a2505fcf6 |  | textbox | Today's weather
text | 728d3194-c5be-506e-9bc5-ba65707dc153 |  | textbox | Today's work is
text | 7d490730-09aa-53fa-83e6-91f92a575993 |  | textbox | Newly Identified Hazards Are
text | 945fab80-2c2e-5e28-a9ea-708af371c86c |  | textbox | Control measures are
checkpoint-status | c04e1ca9-cee1-4b04-afe4-c792f65d31f9 |  | checkpoint | Scope of work for the day was discussed and understood
checkpoint-status | 955712b8-b703-4b76-9962-295695e309bd |  | checkpoint | Major High Risk Activities are understood and controlled in a SWMS
checkpoint-status | 7d151477-0bd6-48a5-92ff-00961fe7f739 |  | checkpoint | Relevant Permits to Work are in place and understood
checkpoint-status | 41654bec-7380-441e-92a7-832088042e91 |  | checkpoint | Tools and equipment are in good working order
checkpoint-status | 424d2e43-9a5d-4aaf-9b26-4fb7d736a060 |  | checkpoint | All electrical equipment displays current test tags
checkpoint-status | f87d6b42-77f8-4c45-8119-171d8293b427 |  | checkpoint | Appropriate PPE for tasks is understood and available
checkpoint-status | a94519e9-1e58-44a6-8cd2-b2a60165285f |  | checkpoint | Housekeeping and clean-up has been discussed and is understood
checkpoint-status | f2bea2f7-da25-4a29-ac63-078d5bd56e0e |  | checkpoint | SWMS Reviewed
select | 0d4cc119-a65a-5376-aa45-e7dade6a9d5a |  | dropdown | SWMS | 001 Conduit Installation - Placed prior to pouring concrete, 002 Conduit Installation - In ground, 003 Conduit Installation - Walls & ceilings, 005 Using portable ladders, 006 Intstalling light fittings, 007 Installation of switchboards, 008 Installation of lighting looms, 009 Installation of cable supports, 010 Installation of mains, 011 Installation of switchboard connections, 012 Installation of sub mains, 013 Installation of power & lighting cabling, 014 Installation of power points, 015 Manual Handling, 016 Working with elevated work platforms, 017 Erecting & using mobile scaffolfds, 018 Dismantling mobile scaffolds, 019 Working at heights, 020 Installation of new work in existing switchboards, 021 Working in risers, 022 Installation of pyrotenax (MIMS) cable, 023 Isolation & testing of energy sources, 024 Installation of equipment racks, 025 Installation of fibre optic cable, 026 Installation of trunk cabling, 027 Installation of outlet cabling, 028 Installation of outlets, 029 Working on energised low voltage equipment / appartus, 030 Installing ceiling mounted lights & speakers, 031 Installation of new racks / cabinets, 032 Heat shrink cable joints & lugs, 033 Installation of SELV cabling (data / security / nurse call, etc), 034 Installation of data / tv / nurse call points, 035 Installing light poles, 036 Trenching with small excavator, 037 Installation of grid connected photovoltaic system, 038 Energise & commission installation, 039 Test & tag electrical equipment
boolean | a4e782f4-e860-5e72-ae66-ed3335b8a0c4 |  | tickbox | David Interligi
boolean | df0563c3-6301-50ba-8cf2-04f35d6491be |  | tickbox | Michael Borg
boolean | 82f99218-962a-5a6b-b6e7-dae746998c8b |  | tickbox | Rob Pellegrino
boolean | 86bee32b-9b05-59e1-bfc0-97d5f3345b72 |  | tickbox | Adrian Sibbing
boolean | ffec0905-ea44-5518-b6be-9a6bcd1e4073 |  | tickbox | John Wolosz
boolean | 9f318978-14f4-500b-9f15-93a47bc81f0c |  | tickbox | Lochy Brannelly
boolean | 1cab6eea-310e-599e-8c58-551866e9173e |  | tickbox | Damon Guy
boolean | 7019d514-1f60-5901-99c9-79e101917d8f |  | tickbox | Jake Condon
boolean | 25291336-e351-5320-abca-fa2d6bb32725 |  | tickbox | Julian Cannata
boolean | 2392441c-5d64-5e9d-a612-4c435c6c8514 |  | tickbox | Devilliers Duvenage
boolean | ba2c3b79-3bf0-5067-baf0-63263b910793 |  | tickbox | David Currie
boolean | 1d0f20ac-40cd-576a-80f6-4c3ecc653f7b |  | tickbox | Steve Price
checkpoint-status | 602a59db-eb82-41b9-a4ff-f8a617740a7e |  | checkpoint | Signed off by Supervisor
checklist-flat | 0b6f1f44-2c4f-4ac5-a6f5-f5709e6e883c |  | checklist | ITR No.7 - POOL- Fit Off |  |  |  |  | Yes | ITR No.13 - POOL- Fit Off | c72fcfb4-2fd5-4fc3-91f5-af0c3a6b706a
checkpoint-status | 0faee3fd-ee22-4c2d-84f8-9d31c848ce1d |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | a4702156-4040-4566-9559-5630842fc54c |  | checkpoint | Fit off earth clamp to pool reo
checkpoint-status | 6256fe1c-699d-47b6-9340-3baf351d1cad |  | checkpoint | Fit off all Lights
checkpoint-status | b5e79a97-0a82-42f6-a07f-fc67db6ced3d |  | checkpoint | Fit off all EX/EMG’s
checkpoint-status | 29e9ff15-62d0-46cc-8476-b713ff888569 |  | checkpoint | Label all EX/EMG’s as per plan number
checkpoint-status | a99982e1-f671-4a01-8612-bd592a76cc47 |  | checkpoint | Fit off all GPOs
checkpoint-status | 2953b68a-1dc7-445a-bd77-b7001db8556c |  | checkpoint | Fit off of isolators
checkpoint-status | b39e32bf-34e3-402a-998e-8d99a1efb469 |  | checkpoint | Fit off of CCTV
checkpoint-status | 3551eeea-8aae-4ad5-b205-d13b539fd938 |  | checkpoint | Ensure all fit off has been ticked off on plans once completed
checkpoint-status | 6fd43586-5d67-47ff-b74c-0d27ef00b7fd |  | checkpoint | Ensure area is left clean
checklist-flat | f16d64ff-dc71-4e2a-a9ff-4fcd642d016b |  | checklist | Drawings / Documents |  |  |  |  | Yes | Drawings / Documents | c85e276d-5718-4f86-8699-6e31c3554583
checkpoint-status | 8d2a8c0a-40bc-4427-b6f2-cee454e7151f |  | checkpoint | Attach Drawings / Document
checklist-flat | 72562268-bb16-4ca8-8e1d-e46c4ac52d43 |  | checklist | ITR No.7 - RETAIL TENANCY Fit Off |  |  |  |  | Yes | ITR No.13 - RETAIL TENANCY Fit Off | ceac4878-5d88-4325-8642-c845b113cbfe
checkpoint-status | 2a544947-2fec-470e-bf54-1535ac6b5fb3 |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | 79a41843-c341-4b72-9fb3-339aab227d8c |  | checkpoint | Fit off all Lights
checkpoint-status | cced6816-63c2-4668-bd97-f8c06c0248a4 |  | checkpoint | Fit off of 4 pin plug
checkpoint-status | d1f9a873-836d-400b-9ac1-d0a4a6e10468 |  | checkpoint | Fit off all Sensors and SET TIME TO MINIMUM
checkpoint-status | b6fd643a-ea64-4f9e-a703-9b096003b95a |  | checkpoint | Fit off all EX/EMG’s
checkpoint-status | e1b05a59-67ea-4755-80de-69bc67d0abda |  | checkpoint | Label all EX/EMG’s as per plan number
checkpoint-status | 769e108d-3330-4cbb-85f2-06bda39feb24 |  | checkpoint | Fit off all GPOs
checkpoint-status | 5adf1e7c-900c-4d05-b588-bf506f7ae517 |  | checkpoint | Fit off of all isolators (signs, hand dryers, hws)
checkpoint-status | 03cdaa8e-e21f-4c94-9091-325f5abfe024 |  | checkpoint | Ensure all fit off has been ticked off on plans once completed
checkpoint-status | 6ea39f7e-2525-4500-9c2b-a2d10d9b0a7b |  | checkpoint | Ensure area is left clean
checklist-flat | 9d996139-3a88-40d0-a318-6fd9598da83e |  | checklist | ITR No.7 - LOUNGE/DINING Fit Off |  |  |  |  | Yes | ITR No.13 - LOUNGE/DINING Fit Off | d4d9346a-660b-45f7-a4ee-3b1a70a16110
checkpoint-status | 01cf6ed5-55b6-4661-8d88-b68467d4a7bb |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | 6a1aa364-05d4-4e76-a84b-1f170e3a72c9 |  | checkpoint | Fit off all Lights
checkpoint-status | 0e2f0682-c47a-453a-adc4-13baf49aa93d |  | checkpoint | Fit off all switch panels
checkpoint-status | 05b9a006-a1a9-4b31-b08b-9c2511ef15b6 |  | checkpoint | Fit off all EX/EMG’s
checkpoint-status | ea64432a-ffa4-4756-afad-8fe75689cf6a |  | checkpoint | Label all EX/EMG’s as per plan number
checkpoint-status | ca1aafc2-934b-414b-9a79-8596ed82a80f |  | checkpoint | Fit off all GPOs
checkpoint-status | d3adf752-1ab9-4837-bcaa-42a0a4e1caba |  | checkpoint | Fit off of 4 pin plug base
checkpoint-status | 84112aba-fefe-4278-a9a4-e80a44582d18 |  | checkpoint | Fit off of all kitchen joinery
checkpoint-status | 88fc2adc-be2a-4fb7-8733-778adfa026e6 |  | checkpoint | Fit off of TV points
checkpoint-status | 4e69cfd7-2783-45f1-af60-8249b181b489 |  | checkpoint | Fit off of WAP & CCTV
checkpoint-status | ad9bc6f6-0300-46fa-a351-899b515cfd00 |  | checkpoint | Ensure all fit off has been ticked off on plans once completed
checkpoint-status | cc4fd9ee-c66b-4ff9-aed4-72dc36147072 |  | checkpoint | Ensure area is left clean
checklist-flat | c1a953f8-59ad-443d-875b-f55d046923c2 |  | checklist | ITR. No 02 LOUNGE/DINING - Cut Out |  |  |  |  | Yes | ITR. No 02 LOUNGE/DINING - Cut Out | d5606f5a-f7fe-44c1-9f65-963edfebbcc9
checkpoint-status | cbd186f9-834d-47b3-8bf0-bc063b987858 |  | checkpoint | Refer to drawing to determine cable support route and check separation from data/comms services
checkpoint-status | 80089ea8-7a98-401a-9149-c6a65aaa57a7 |  | checkpoint | Cut out for light fittings
checkpoint-status | 45978dfb-85ad-4be3-8e60-4f523c36358a |  | checkpoint | Cut out switches & GPO’s
checkpoint-status | a118d29e-cd65-49d2-afc9-056fea510b1c |  | checkpoint | Cut out of kitchen joinery
checkpoint-status | e0266632-dfe1-49d0-949c-eff886978e88 |  | checkpoint | Cut out of TV,WAP, CCTV
checkpoint-status | 991ebfc6-0a22-461a-8ed3-8654d45f3efc |  | checkpoint | Install Fire Boxes and hit all 4 tabs in if applicable
checkpoint-status | 27563bc2-ed66-4a91-bdcf-2b3e354fe21e |  | checkpoint | Ensure Fire caulking is completed by subcontractor
checkpoint-status | c4866815-0b06-416e-82c6-58b672b1cedc |  | checkpoint | Ensure area is left clean
checklist-flat | 05675a45-2ed3-46af-a80e-b03e4f0edb30 |  | checklist | ITR No.0 5 Ground Rough In (lobby/back of house) |  |  |  |  | Yes | zSYS - ITR No.0 5 Ground Rough In (lobby/back of house) V1 | d5924586-c4d1-42c4-a678-70dbfbd9e3d6
checkpoint-status | ae4146ef-ae94-4895-a179-6c88c842582c |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | 8bd73949-11e6-405a-8aa8-58404aa048e7 |  | checkpoint | Mark out all public L+P
checkpoint-status | 0c774632-6b27-4880-ab52-b272952b226e |  | checkpoint | Rough in of all lighting circuits- inc Emg/Exits and sensors
checkpoint-status | 5591ae61-bf91-4e31-a5cc-ff6c5d0ee330 |  | checkpoint | Rough in of all external lighting
checkpoint-status | 446c163e-bcdc-40f1-be31-43753236464b |  | checkpoint | Rough in of all power circuits
checkpoint-status | e11095b2-ef7b-4312-ab7a-c81f989d6955 |  | checkpoint | Rough in comms riser power
checkpoint-status | 754c88f8-5934-467b-aa98-be16bcfb8a8f |  | checkpoint | Rough in all lighting feeds and label on plan
checkpoint-status | 35370130-8b73-4885-84a1-d0e1a17ac97d |  | checkpoint | Rough in all power feeds and label on plan
checkpoint-status | 97e916eb-682a-491f-af6d-91dd799b57b2 |  | checkpoint | Rough in of 4 mm min Earth to water meter assembly
checkpoint-status | f2b62125-5fdf-41e2-968a-fa314d29a743 |  | checkpoint | Rough in OC2 commercial lift lobby light & power
checkpoint-status | b40242b9-64bf-40ac-8805-0bf5f158a387 |  | checkpoint | Rough in of DDA lift
checkpoint-status | 60b67760-4d9a-4fb0-855a-dba551f83434 |  | checkpoint | Rough in refuse room 3 phase compactor conveyor belt
checkpoint-status | 58e5c815-75d1-46e0-a9d6-1ef9285d18ce |  | checkpoint | Rough in refuse room 3 phase compacting machine
checkpoint-status | 1d43540f-5757-416a-a70b-fe067a13a3bb |  | checkpoint | Installation of comms cable tray
checkpoint-status | 9b4b1bde-af60-4484-a789-9428ed31c851 |  | checkpoint | Rough in stair doors access control
checkpoint-status | 2bdcb39a-a0f5-45b2-8946-7ad42c097d51 |  | checkpoint | Rough in CCTV
checkpoint-status | 42edf764-466e-4aa8-94f8-83266b03035b |  | checkpoint | Check for clashes with other services
checkpoint-status | 94beea78-a43f-4117-863f-864273b8dc1b |  | checkpoint | Level fire caulked by contractor
checkpoint-status | 971a1a68-8e52-4925-853f-88a3bc3b8c21 |  | checkpoint | Fit off plug bases & quick connects
checkpoint-status | 8a1284d4-6cb6-4d5c-8cd1-14d678d54c36 |  | checkpoint | Ensure area is left clean
checklist-flat | 0156547c-72e2-4bcb-87db-59990271503a |  | checklist | Toolbox Meeting |  |  |  |  | Yes | zSYS - Toolbox Meeting | dc7d0fb8-8513-473e-b260-f0dc73589caa
checkpoint-status | a2a8cc77-0964-4384-af19-70138a4505ad |  | checkpoint | VAST toolbox meeting completed
text | 95ee751f-4852-5a0f-be1a-17eed17bfdc9 |  | textbox | Supervisor
text | fb34cdf2-e1fe-5609-a99d-d91d27ae9ee6 |  | textbox | Persons present
boolean | 874ef4f0-8edc-535c-8614-a53b22b6ec0a |  | tickbox | Injuries, near misses and incidents
boolean | 3c0c9f0f-18a5-5c9a-ae6b-34ed582c5ff1 |  | tickbox | Management of major hazards
boolean | ebc5720c-27b2-5cf0-a881-0eb5958b710c |  | tickbox | Compliance with our Vast SWMS
boolean | 1592f8ae-9da4-5179-9acd-029f1e205ecc |  | tickbox | Safety
boolean | b2b80e8a-e337-559d-b669-ed7ba7e1c223 |  | tickbox | House Keeping
boolean | e3de645e-9543-53af-be78-83e4738767bf |  | tickbox | PPE (HARD HATS & GLASSES ON AT ALL TIMES)
text | 001a0577-0f5d-5536-b9da-067768bd3cfb |  | textbox | Comments
checklist-flat | 16f9ceb6-e0f0-46d0-b9fd-23105a47645b |  | checklist | ITR No.7 - GYM Fit Off |  |  |  |  | Yes | ITR No.13 - GYM Fit Off | e27e057e-5746-4948-bfdf-22b301c25e9f
checkpoint-status | 349d5b9d-5108-4ba8-a3d7-374f116dd90e |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | 50290a64-2a8a-479e-8a25-a4726928c1e7 |  | checkpoint | Fit off all Lights
checkpoint-status | 5c647846-6dd3-4c3b-92ea-59cd53796c27 |  | checkpoint | Fit off all switch panels
checkpoint-status | fff13fa2-fbb1-4f83-a5a5-fb726780f725 |  | checkpoint | Fit off all EX/EMG’s
checkpoint-status | cc300c17-0dbe-43ee-9ed9-5f32d56e5ef1 |  | checkpoint | Label all EX/EMG’s as per plan number
checkpoint-status | 24b55cea-f2c0-42e7-bda0-b5d65307a9c8 |  | checkpoint | Fit off all GPOs
checkpoint-status | d6930338-2141-4935-962f-b8ca404128b7 |  | checkpoint | Fit off of TV points
checkpoint-status | 6862ee5b-6b1f-4d26-9b87-1020917a6faa |  | checkpoint | Fit off of WAP & CCTV
checkpoint-status | 58af5ecf-b4db-4bf4-b38c-8245cccf16c5 |  | checkpoint | Ensure all fit off has been ticked off on plans once completed
checkpoint-status | 613fd63f-3464-4b5c-bc9e-13ffff874f96 |  | checkpoint | Ensure area is left clean
checklist-flat | b7c2af52-f1a8-48bb-a6c2-703c44207527 |  | checklist | ITR No.02 Hallway Rough In |  |  |  |  | Yes | zSYS - ITR No.02 Hallway Rough In V1 | e2c7d9c3-166f-4fc2-83af-8fc8366d3e29
checkpoint-status | c140a205-dce2-46d4-9ba5-4715ec70bb38 |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | 8d2d1d83-6a37-475f-88d6-4a822a515821 |  | checkpoint | Mark out all public L+P in hallway
checkpoint-status | 728e9d10-5f43-496e-93da-0539943fb277 |  | checkpoint | Rough in lighting, Emg/Exits and sensors
checkpoint-status | 5b09f0a0-4d04-42b8-a913-7d767a77980a |  | checkpoint | Rough in general power OC1
checkpoint-status | 59805a0b-99d0-46d7-9b30-fb9e00e9374a |  | checkpoint | Rough in cleaners power & water meter power OC2
checkpoint-status | c52d7a33-db77-4eac-a1b0-c32b52b8a9f9 |  | checkpoint | Rough in of any Hand Dryers and HWS to Amenities
checkpoint-status | 18e7407a-2124-42dd-9f96-7eb86b90843c |  | checkpoint | Rough in comms riser power
checkpoint-status | d77af5f4-6a6a-4606-a274-878180b334a5 |  | checkpoint | Rough in lighting feed to first emergency point opposite elec riser OC1
checkpoint-status | 96e9c3e2-a5b2-412c-bc24-32941e33f546 |  | checkpoint | Rough in lighting feed to emergency at commercial lift OC2
checkpoint-status | 0ed1d162-7354-4dc5-872d-b5f9ecb7cad5 |  | checkpoint | Rough in power feed to first cleaners point near elec riser
checkpoint-status | e61870a7-bcaa-4198-9bb8-3a7f165c4130 |  | checkpoint | Rough in all apartment sub mains from riser to apartment DBs and LABEL
checkpoint-status | b7ddcfbc-69b8-4fef-ad47-2eef1cc471ce |  | checkpoint | Rough in stair doors access control
checkpoint-status | 923ddd6a-725d-4756-a44a-96a18adf325d |  | checkpoint | Rough in any relevant comms/access control from one floor to another ( Backbone )
checkpoint-status | 8ea97d4c-9d8a-478b-817f-e8e2e77d3b62 |  | checkpoint | Check for clashes with other services
checkpoint-status | 94abcedf-434b-4c2e-ac12-999a45738f2b |  | checkpoint | Level fire caulked by contractor
checkpoint-status | cb54c10f-0990-4cfa-9254-68813b3b40b2 |  | checkpoint | Fit off plug bases & quick connects
checkpoint-status | 40e54c9b-482f-4dc3-8450-c93a59cf5011 |  | checkpoint | Ensure area is left clean
checklist-flat | d77adec2-9ea2-4056-b7da-ca8ed7ec46a6 |  | checklist | ITR. No 02 Hallway Cut Out |  |  |  |  | Yes | ITR. No 02 Hallway Cut Out | e8ba7e09-fbd2-4d16-968f-ef5d804e2863
checkpoint-status | 8a7704cb-a4c1-469e-b9bd-7750b770560c |  | checkpoint | Confirm sizes of all fittings prior to cut out
checkpoint-status | af449685-ddda-4174-8ad0-54787e4a5535 |  | checkpoint | Cut out all sensors,emg/exits, light fittings
checkpoint-status | bda2a5ff-5ee6-42ac-92fa-91bd9fdbcf92 |  | checkpoint | Cut out all cleaners gpos
checkpoint-status | 6b6308b0-f5ca-4217-a8a8-a73bd096b652 |  | checkpoint | Cut out any CCTV
checkpoint-status | 11ce29dc-1849-45d4-b198-84708b3eb427 |  | checkpoint | Ensure electric strike cable is in press metal frame cut out
checkpoint-status | 2aa02ffa-46bd-4fe3-be80-43cf9ddba440 |  | checkpoint | Locate all cables
checkpoint-status | 2b587f55-dafe-4eb6-80bc-24d378df12ec |  | checkpoint | Install Fire Boxes and hit all 4 tabs in
checkpoint-status | 071e0ad0-2040-400a-bf4f-91d77000c7ca |  | checkpoint | Ensure area is left clean
checklist-flat | 85870a40-004c-49a8-a413-16a2aac3d9b4 |  | checklist | ITR No.0 5 Ground Rough In (lobby/back of house) |  |  |  |  | Yes | ITR No.0 5 Ground Rough In (lobby/back of house) V2 | f032174d-c1e9-4f2c-b7f3-9c2174707cab
checkpoint-status | 34734347-f557-4eaa-9e43-6308482fff09 |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | e034a3ef-62c7-4732-aff5-f8a27912e18a |  | checkpoint | Attach copy of drawing
checkpoint-status | 35004186-90f3-42d0-8472-b9ffefcbed2a |  | checkpoint | Mark out all public L+P
checkpoint-status | daffa922-7849-40c1-9300-0f4af3b340d7 |  | checkpoint | Rough in of all lighting circuits- inc Emg/Exits and sensors
checkpoint-status | 41410665-e0da-45dc-83b7-514f6940f1e1 |  | checkpoint | Rough in of all external lighting
checkpoint-status | f8ba3ee1-ccb1-4c55-bb1b-9d23e2d499d4 |  | checkpoint | Rough in of all power circuits
checkpoint-status | fb9f27df-b5ef-42ab-8c56-239a4ccf5d02 |  | checkpoint | Rough in comms riser power
checkpoint-status | da71590a-a92e-4f5b-9801-6893e5d89b4c |  | checkpoint | Rough in all lighting feeds and label on plan
checkpoint-status | e576dec0-0f72-4f84-b0e9-494f61a93980 |  | checkpoint | Rough in all power feeds and label on plan
checkpoint-status | 7e8f24fb-938e-4fb0-978e-4d1deff6183c |  | checkpoint | Rough in of 4 mm min Earth to water meter assembly
checkpoint-status | c1a1d5b7-8902-4a51-832f-95d9c4ef6cd1 |  | checkpoint | Rough in OC2 commercial lift lobby light & power
checkpoint-status | 908ebf20-b41b-4e46-83f2-11f306e032e9 |  | checkpoint | Rough in of DDA lift
checkpoint-status | ac56cbb6-8cf6-427b-b9d8-ffefba7de202 |  | checkpoint | Rough in refuse room 3 phase compactor conveyor belt
checkpoint-status | 97c1a284-0c94-4897-b711-fae08377fa30 |  | checkpoint | Rough in refuse room 3 phase compacting machine
checkpoint-status | 1b1d79d3-2028-46cf-9023-9d0982aeb3a4 |  | checkpoint | Installation of comms cable tray
checkpoint-status | f2999aa7-b040-4be9-b137-4e2ff4d3da50 |  | checkpoint | Rough in stair doors access control
checkpoint-status | d1ff192a-7163-48ce-ae82-ac6af3f027f2 |  | checkpoint | Rough in CCTV
checkpoint-status | cf693a6a-8a10-4180-b895-d0634b629e6f |  | checkpoint | Check for clashes with other services
checkpoint-status | 730be8f2-06ae-42fd-8fed-68d2b44a52ff |  | checkpoint | Level fire caulked by contractor
checkpoint-status | 1852ecaa-0054-4e52-874a-a64fb5671f12 |  | checkpoint | Fit off plug bases & quick connects
checkpoint-status | adef49d3-8816-4a47-9511-f7ebbf9cb24f |  | checkpoint | Ensure area is left clean
checklist-flat | 932401d4-d848-4468-9961-8f1106a2ef42 |  | checklist | ITR No.0 5 GYM- Rough In |  |  |  |  | Yes | ITR No.02 GYM- Rough In V2 | f7738b79-9919-4c8f-b111-963d1d79cd02
checkpoint-status | 8b3e262e-11e0-466c-9905-8cdc010b41b9 |  | checkpoint | Area clear, tidy and accessible
checkpoint-status | bc90af13-57ad-4e3e-a94c-e8a032ca2a25 |  | checkpoint | Attach copy of drawing
checkpoint-status | c874c905-616d-457d-89d0-5a00a888a330 |  | checkpoint | Ensure no other services are in the way of our cat wire and fittings
checkpoint-status | 58f9a5d7-1f87-4999-a7f7-75c34ce9f361 |  | checkpoint | Rough in lighting, Emg/Exits back to the switch board
checkpoint-status | 028dfb68-547a-444f-a0dd-4aa96b2da4e8 |  | checkpoint | Rough in of lighting switch panels twin actives back to switch board
checkpoint-status | f1f452c0-f715-4f1f-9cc2-e0f94df2c5f1 |  | checkpoint | Rough in of general power
checkpoint-status | 5c4de36a-bb1e-4f15-8f31-55563cb0e3b3 |  | checkpoint | Rough in of TV points
checkpoint-status | 62c30c0b-2e22-4641-93ff-b2eed7b0b59a |  | checkpoint | Rough in of WAP
checkpoint-status | b80d9f68-bb01-4dec-8148-c72ba4d8f2bb |  | checkpoint | Rough in of CCTV
checkpoint-status | 3e06f3ad-01b9-4d7c-927b-be26d022d04d |  | checkpoint | Rough in of any access control
checkpoint-status | 82e4bc8e-cfd0-4858-9188-2d2f0aaffdf6 |  | checkpoint | Ensure all rough in has been ticked off on plans once completed
checkpoint-status | 815e2b1a-68ff-4470-a7f5-ddf93ced952d |  | checkpoint | Ensure area is left clean
checklist-flat | a4cc2729-abaf-4d6b-a334-22b8213918d9 |  | checklist | ITR. No 02 Apartment Cut Out |  |  |  |  | Yes | ITR. No 02 Apartment Cut Out | fc67e30b-c899-4ce8-b9ed-94094d8b5051
checkpoint-status | 6241b0e1-c5b3-4f5e-9772-755b2e02f98b |  | checkpoint | Refer to drawing to determine cable support route and check separation from data/comms services
checkpoint-status | be3c67f3-7e81-484b-a563-90cc76dddb45 |  | checkpoint | Cut out for light fittings
checkpoint-status | 5f810c54-39f3-4fa6-8b07-4f834940cf33 |  | checkpoint | Cut out smoke detectors
checkpoint-status | 8e9eea63-e404-4510-af28-b715dacaebb3 |  | checkpoint | Cut out kitchen to kitchen plan
checkpoint-status | d229ef55-c3e2-497a-b8c1-cd70eb7806e6 |  | checkpoint | Cut out switches & GPO’s
checkpoint-status | 7fac9d13-9822-4336-ad2f-24b7d2a1782d |  | checkpoint | Ensure Wall light is in correct position
checkpoint-status | 830b42c7-ba2e-4048-a416-e90ba6461e22 |  | checkpoint | Ensure kitchen outlets are in correct position
checkpoint-status | 42b7b614-cb7e-42b3-8939-256ad20c947f |  | checkpoint | Install Fire Boxes and hit all 4 tabs in
checkpoint-status | 37c20fd1-9aac-4241-846c-e8a59b4396af |  | checkpoint | Ensure Fire caulking is completed by subcontractor
checkpoint-status | 3c7009f0-69dd-4fae-903a-ebaa17753135 |  | checkpoint | Ensure area is left clean