## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ITP - CONOC Operations - Emergency Works: Clearance of a Small Slip | itp |  |  |  | Yes | ITP - CONOC Operations (General) - Emergency Works: Clearance of a Small Slip | 01234f3d-481f-45e7-9dfa-177cfcd08ace
checkpoint-status |  |  | checkpoint | 1 - Planing
label | 1b52b8bf-8a68-565a-bf41-85f276868f79 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 2da82559-1058-572b-8310-4644dd605d82 |  | note | Accept / Reject Criteria - As per Specification
label | af998e19-33c6-54da-861c-31453055ca40 |  | note | Frequency Of Inspection Or Test - In-process
label | 3ede966f-214a-5bfa-a922-a1e2f3d673a9 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP102
label | a7bf5a87-2883-5e53-b6b7-553c096c5d79 |  | note | Records Required - NO
label | 4467c8c0-2754-522b-9201-1dec55b460ba |  | note | ENGINEER - R
label | 97a30e13-edca-5cff-a849-7f539eda6a92 |  | note | SUPERVISOR - R
label | 3bd7b70b-1a46-5638-bef5-0b2743a989e9 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Preparation
label | dea312ff-183e-510e-9674-64427184e6aa |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 5d22f0ec-69dc-57ec-849e-1defb7b49653 |  | note | Accept / Reject Criteria - As per Specification
label | 09ab27a8-cfa5-5586-8593-e0f605c62cbc |  | note | Frequency Of Inspection Or Test - In-process
label | b6eff20b-be54-5a4e-8777-bcd193743297 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP102
label | 7ebb7ea8-6e58-5564-8a5c-c6f1f803f688 |  | note | Records Required - NO
label | bf069eb0-12f6-5e02-8c93-55216e0dbfa5 |  | note | ENGINEER - W(10%)
label | f4a943ee-89be-5414-9465-531d4d49ff7e |  | note | SUPERVISOR - R
label | 49c266ac-3f7e-581b-8d96-856d1c2579ba |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Clearing
label | ae2f42dd-c00b-5928-94f5-5d1ecbf600d5 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 72a45205-e93e-5ada-b325-5432eab0ba79 |  | note | Accept / Reject Criteria - As per Specification
label | 00eae858-2b70-5c65-ac7a-22fb7c7b4eaf |  | note | Frequency Of Inspection Or Test - In-process
label | 037356bd-afca-5185-8366-d581fc7ed550 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP102
label | 8ef40fe3-cb41-565d-85cc-24d951d12a89 |  | note | Records Required - NO
label | 4ee9cfa3-003e-5ce2-82ae-a243af705233 |  | note | ENGINEER - W(10%)
label | 244b3df9-f223-5593-8c49-7c2b095fd227 |  | note | SUPERVISOR - R
label | 432aa051-5dff-5b8f-a357-6bc557533888 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Test and Check
label | 5e028f75-b572-5b7c-9ba6-883f6c0d2dab |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 9d647324-371a-5fcb-a359-9fcf2db7747b |  | note | Accept / Reject Criteria - As per Specification
label | c555bc9d-8983-5572-bc73-3fcc3d591866 |  | note | Frequency Of Inspection Or Test - In-process
label | d57785e4-696e-5028-b456-81e4c99f7c9d |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP102
label | 0cd955f0-2eab-5f83-90f5-51dbb739b4bf |  | note | Records Required - YES
label | abc7e2d3-31e3-596e-b29b-b565e6e89534 |  | note | ENGINEER - W(10%)
label | 2dd990d4-9d74-5670-ba59-850e23f4e8b8 |  | note | SUPERVISOR - R
label | 10622bc5-c411-5ed5-ac3f-c080e54768be |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations (Heavy and Light Maintenance) - Deep Pothole Repair in a Sealed Pavement Premix Method | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy and Light Maintenance) - Deep Pothole Repair in a Sealed Pavement Premix Method | 016a9e8d-b544-4338-abf1-fa8134a5b0a6
checkpoint-status |  |  | checkpoint | 1 - Prepare Hole
label | 596b6dbd-6c18-5f76-b212-964b3bffff63 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | ea5c192a-883d-5f73-8f4a-f18aa64dd250 |  | note | Accept / Reject Criteria - As per Specification
label | 99a531f0-3a6b-5872-962d-8916e5765281 |  | note | Frequency Of Inspection Or Test - In-process
label | 5a3a66c5-0d35-51b8-bbb4-8362d066f77f |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP033
label | 8f36de32-f0d7-5673-a619-61a90b1eb9c2 |  | note | Records Required - NO
label | b25b9fa7-62f1-5705-9f41-fe2b8cd12525 |  | note | DOWNER ENGINEER - R
label | e319a113-3bf6-522c-b02b-80ee8b2bbfc1 |  | note | SUPERVISOR - R
label | b47ed759-79cd-58dd-ba1f-93921210ebc3 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Filling Hole
label | e31cd8e8-0fce-5cf0-abb2-f8ae2b5da07a |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | e9e4a604-7211-5fe3-8202-ff3b0dde5416 |  | note | Accept / Reject Criteria - As per Specification
label | 2ad5f7cd-7b7b-5a11-8d08-495c283972e6 |  | note | Frequency Of Inspection Or Test - In-process
label | 4a75695d-5af7-5bb3-a5d9-6b5a53738d5c |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP033
label | 91cf4afa-6347-5a26-bc86-a2a71d6b4d39 |  | note | Records Required - NO
label | 54d566e2-0b81-5911-987a-725ce8eb5b37 |  | note | DOWNER ENGINEER - R
label | dfdab639-e562-572e-ad4a-393bc3508d8c |  | note | SUPERVISOR - R
label | 7cb39965-a244-576e-8715-70536577e12f |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Blinding
label | cbe38ae7-0906-5a0a-990d-b84412f1b0d3 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | f209f2f9-e6a4-5383-a402-7e0fae790c04 |  | note | Accept / Reject Criteria - As per Specification
label | 77b074d4-e345-5c11-9ac6-905bb4daebdf |  | note | Frequency Of Inspection Or Test - In-process
label | 3e28eb67-e0a3-5bd9-bf1d-f8bb3de7653f |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP033
label | fc08ade4-1d1a-5b5c-9f09-0037e4476717 |  | note | Records Required - NO
label | c58697df-4363-5099-80a6-33c0ebb1cb2a |  | note | DOWNER ENGINEER - R
label | 899b2196-7f48-58b3-99d1-507b063a929b |  | note | SUPERVISOR - R
label | 9a23f036-e6e5-5662-aaf5-528124ec8553 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Test and Check
label | 9dbba008-d631-5f2d-a783-c6b6f998df95 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 24eb1969-6713-5b9e-9f67-40472d0d8883 |  | note | Accept / Reject Criteria - As per Specification
label | 91f7927c-925d-529d-a099-6d6f08883461 |  | note | Frequency Of Inspection Or Test - In-process
label | 979e1899-1e0a-58d8-b61b-4be968044ff3 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP033
label | 99f97eb8-3eb6-53ca-95ec-cdb269a78c57 |  | note | Records Required - NO
label | 56451e79-0704-51ac-8543-a8ffc6914593 |  | note | DOWNER ENGINEER - W(10%)
label | 3240433e-9c15-5e86-9287-ef6f72ac45ea |  | note | SUPERVISOR - R
label | 842fb39f-2f9d-5564-9fdd-c07124313bd6 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations - Install a Culvert Headwall Using a Precast Concrete Headwall | itp |  |  |  | Yes | ITP - CONOC Operations (General) - Install a Culvert Headwall Using a Precast Concrete Headwall | 060a9db9-dbd5-4ec2-880d-0c5dc2040750
checkpoint-status |  |  | checkpoint | 1 - Prepare the Site
label | 90b2c467-998a-52ab-9adb-dd5848ee09e4 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | cc27c02d-a8ba-5fb0-a545-d4f611debed0 |  | note | Accept / Reject Criteria - As per Specification
label | 672656e6-1342-5665-a318-8598edaf8142 |  | note | Frequency Of Inspection Or Test - In-process
label | dea3d888-f7dc-5586-a212-b095a908e780 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP084
label | 424c203c-80bf-532f-a1c8-c4aa4d1af424 |  | note | Records Required - NO
label | 585c20af-cccf-5cb4-aff6-1274339ba62b |  | note | ENGINEER - R
label | 55f6f477-4995-5a74-aead-d2b95067f86c |  | note | SUPERVISOR - R
label | 3520df14-8a63-5b32-b043-b8f20dcd6689 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Setting Out
label | a3d6f77d-197b-52b8-8bc9-dc33cbb53cce |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 40eb4fb9-2035-5de8-9a6c-e32cf5b1a5ee |  | note | Accept / Reject Criteria - As per Specification
label | ea011552-6d6d-5c04-bf81-8279c96fcf73 |  | note | Frequency Of Inspection Or Test - In-process
label | 59461f6c-ef65-51bb-b1c4-249d59de62f9 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP084
label | 2121ba24-adf8-599c-9c99-4563d487c749 |  | note | Records Required - NO
label | a12cbe2d-9962-51ae-b619-e4fb6bae2c9f |  | note | ENGINEER - R
label | 284aa8e1-4a48-55d9-bb20-92cd7fd6b59f |  | note | SUPERVISOR - R
label | 4d399891-67b8-55fd-8d14-260f1cee2405 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Prepare the Foundation
label | 8e87db6a-e3da-5ab7-9857-8787da00fde0 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 9cf5df73-71fc-5215-8178-6a8f60824cf0 |  | note | Accept / Reject Criteria - As per Specification
label | 50e1df0e-ef84-5684-8329-ba23ffd2fdad |  | note | Frequency Of Inspection Or Test - In-process
label | ba24d9cc-bb12-5c2a-ae0b-4fd512eb3ef3 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP084
label | effc698e-18cc-53af-ada1-af4963c68656 |  | note | Records Required - NO
label | dd9dceae-1f6d-5fd6-8410-db78e20ba2ea |  | note | ENGINEER - R
label | 7d112e17-b2e3-5fa5-aa0e-9f351af4b2c3 |  | note | SUPERVISOR - R
label | 4b69f6d5-47a1-5af5-b694-24314f88fd52 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Install Headwall
label | 55101a18-23d5-55ae-a49a-da92654167f8 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | bec54c68-a900-5572-bec2-ade0c3c8fb24 |  | note | Accept / Reject Criteria - As per Specification
label | 3db09fbe-1c74-533a-9a43-a192d8b2bd75 |  | note | Frequency Of Inspection Or Test - In-process
label | 2f499619-4520-51e1-8690-545d4254130f |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP084
label | d60cc290-00ce-593d-8938-0b564ae1028d |  | note | Records Required - YES
label | 0f229236-9c8b-51a1-9bd4-420b8bbbeaa5 |  | note | ENGINEER - W(10%)
label | 19697ebc-841d-556a-8819-a24673f51c72 |  | note | SUPERVISOR - R
label | e0d80000-8959-5247-8ec8-fcd3eaf28da0 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Apron Extension (If Required)
label | 7024f52c-219d-50d8-9d94-72b79ef30b27 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 8ed2fed1-ee6f-5099-8d86-1fefc8aeaae8 |  | note | Accept / Reject Criteria - As per Specification
label | c3a1b0eb-b2ab-5681-b1e2-87c0fc6b51d1 |  | note | Frequency Of Inspection Or Test - In-process
label | 1f5d0e57-8ae0-5ac6-8657-687c23fb5511 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP084
label | 2df3c5b2-6707-5119-9859-e0ee2931083b |  | note | Records Required - YES
label | fb4e3bf9-e0a5-58e4-b023-ab9f0ce6ec16 |  | note | ENGINEER - W(10%)
label | f831bff4-27a6-533c-b2bb-5751ee142769 |  | note | SUPERVISOR - R
label | 61b42aca-6458-5687-b5d6-1522b2bc728c |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Backfilling
label | c68aee4e-c73f-53bd-9f0f-d9aa8a3790a4 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | fe98b4ff-d3c1-58c4-99cd-b9ca0e4e59dc |  | note | Accept / Reject Criteria - As per Specification
label | 382bda88-fc5d-5179-832d-3bb0eb971ff3 |  | note | Frequency Of Inspection Or Test - In-process
label | 3acb36f9-80e4-5637-872e-8ef3f0755f6b |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP084
label | b251a945-3593-5f1f-801c-efde75a8f0af |  | note | Records Required - YES
label | fd7ef8eb-474f-5dc0-8ee4-a098e30b8c8f |  | note | ENGINEER - W(10%)
label | 5b89b83e-6078-5d00-a040-d4389181f224 |  | note | SUPERVISOR - R
label | e6c41397-b076-523c-94a7-ceaf092a7842 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Barriers
label | 45d5f5e9-8b19-526b-ba5e-88d06bf6ff8f |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 6fd55e81-bf40-589c-8271-ce266e7a85d6 |  | note | Accept / Reject Criteria - As per Specification
label | bfe4fc58-1d08-5207-bd7d-b456a7e581b9 |  | note | Frequency Of Inspection Or Test - In-process
label | 2dc289a9-ae64-59ff-bb08-5e1a9dd3fb02 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP084
label | eab95424-417e-5b5b-b661-377014b6f8ec |  | note | Records Required - YES
label | 626d0b0a-56f5-5efd-b845-928227335169 |  | note | ENGINEER - W(10%)
label | 9f1b179b-86a3-5eca-a265-4500c12798dc |  | note | SUPERVISOR - R
label | 119176f3-fdcd-527e-9324-3b3c390707ee |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Test and Check
label | 74b370d6-03a2-54ef-9544-d425a754997d |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | fe681445-89c0-5b35-916a-6d23ab080f63 |  | note | Accept / Reject Criteria - As per Specification
label | 150a3bd4-b2fb-5769-9a23-fd942a15a3d0 |  | note | Frequency Of Inspection Or Test - In-process
label | 6d2bb323-6042-5fbe-8390-bdbab7439104 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP084
label | e564c9ef-ed22-5eca-91ef-208053e551b3 |  | note | Records Required - YES
label | 8a08a9af-33d6-5e66-82f6-83d1a2afbcba |  | note | ENGINEER - W
label | aa1b0ca8-4cc9-5b01-9655-02b48ba69717 |  | note | SUPERVISOR - R
label | 40cc5075-95e2-527e-b93b-2e4c45015562 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC NETWORK - Guard Rail W Type Repair Section of Rail and Wooden Posts | itp |  |  |  | Yes | ITP - CONOC NETWORK - Guard Rail W Type Repair Section of Rail and Wooden Posts | 06def72d-16a3-46c0-b481-612cc888d368
checkpoint-status |  |  | checkpoint | 1 - Prepare the Site
label | 7835fb92-9367-53ad-b7b9-5e9d21ec0f75 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 27099429-15d1-58d2-b6d2-a92a159e6c51 |  | note | Accept / Reject Criteria - As per Specification
label | da4a99a2-c73b-5242-ac44-879706f8cfc4 |  | note | Frequency Of Inspection Or Test - In-process
label | 20ef918c-8c64-54b0-a9b2-b2f803f2af59 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP140
label | c03d78ed-aeb3-5706-9af7-741ff3e1f08c |  | note | Records Required - NO
label | 972bf3e1-c15d-5756-a213-3b45294a4d5c |  | note | ENGINEER - R
label | 7876cc43-e509-5532-bc84-d0249557e699 |  | note | SUPERVISOR - R
label | 4aaa17dd-80f0-5f33-bcb3-352e867b0dba |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Assemble Rails
label | b416041b-b0f0-5297-9cce-4f62fd7097ab |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 18f78a31-49d7-591f-b571-8266f082860e |  | note | Accept / Reject Criteria - As per Specification
label | 05bfa2a4-ee13-5dbb-90cf-8a794848e9e0 |  | note | Frequency Of Inspection Or Test - In-process
label | bd6bcacd-8e6e-57d8-a2b6-2312d1b3d7a2 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP140
label | 74512c94-5e5c-56d0-b961-9e15ba164e92 |  | note | Records Required - NO
label | 304137a8-ab71-5c7c-8287-29235e48f5d7 |  | note | ENGINEER - R
label | 1b25d49f-b996-54f1-a50d-bdf8aae705c8 |  | note | SUPERVISOR - R
label | 75bbf0e4-5af4-5e9b-aa1c-5a181eb1e368 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Install Posts
label | 5b8920cf-7a95-5fca-bb63-64130cad200a |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 16961876-9ba4-512c-bdbb-ffaa502c5422 |  | note | Accept / Reject Criteria - As per Specification
label | d19dd1e9-8400-5af8-912c-0bded2c0f331 |  | note | Frequency Of Inspection Or Test - In-process
label | c74b856e-52e8-5659-85e5-0ae11aa125b2 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP140
label | 5b41c636-c908-53cf-be0d-6337c8b61324 |  | note | Records Required - NO
label | 415271bd-726b-50c1-aa07-8dbb51950a53 |  | note | ENGINEER - W(10%)
label | 4fd311f2-db22-5472-9750-392e2ac9c492 |  | note | SUPERVISOR - R
label | ed483f1f-ee54-5780-9ac1-e0bf50a1331b |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Finishing
label | 555521af-2e5c-5c70-8432-5b3c8adf7c61 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | b3c14f26-5fff-500c-b0b2-6b4cecf8952c |  | note | Accept / Reject Criteria - As per Specification
label | a9f13ddc-6bb2-5555-b103-f4af168f6fb4 |  | note | Frequency Of Inspection Or Test - In-process
label | 7de6cee8-0b51-5c65-a737-47a957405e06 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP140
label | a1654fc9-c3cb-5a37-a69b-9150f70af8ea |  | note | Records Required - NO
label | 48b290c7-db8d-5dd2-8c39-466fa1a3995a |  | note | ENGINEER - W(10%)
label | ff7ae918-6bf6-5da3-bea4-7e3c71447f84 |  | note | SUPERVISOR - R
label | bcfb3971-ae7a-5888-83d3-bda1c9200ad6 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Test and Check
label | c9dfa01b-08b8-5166-bfcb-624738d5c30c |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | b2a0fdb1-ab7d-53a4-a119-c9f4e0670b55 |  | note | Accept / Reject Criteria - As per Specification
label | e71d9a9f-b452-5e5b-bb95-efdc68f4113a |  | note | Frequency Of Inspection Or Test - In-process
label | c8189358-73b3-58d3-b89d-2f6b4e782125 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP140
label | a266ded5-020b-5000-9d53-9e0f249dcff7 |  | note | Records Required - YES
label | 0a74917e-675d-50c1-aeb8-6cc329bf19fb |  | note | ENGINEER - W(10%)
label | 6384339b-922c-5edd-9cc2-c1cf770be6b5 |  | note | SUPERVISOR - R
label | af0a6849-5d0f-5edf-a341-9e148ed5c629 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations - Clearing Snow - Grader Method | itp |  |  |  | Yes | ITP - CONOC Operations (General) - Clearing Snow - Grader Method | 09191ff6-74b5-4b82-90f8-c80cb3db2d56
checkpoint-status |  |  | checkpoint | 1 - Snow Clearance
label | 2bcb6fbf-5763-5f0b-a7aa-81235eb4ad0a |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 4a46eb0d-7761-508e-ba93-6c55d292ff24 |  | note | Accept / Reject Criteria - As per Specification
label | 63b05225-13e9-5357-acc0-3bd9ef6223c3 |  | note | Frequency Of Inspection Or Test - In-process
label | d4b5d1de-4889-5cf2-bbab-2277706aeab2 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP105
label | 41038203-cf27-5b98-bee3-3c4d44d8c5b9 |  | note | Records Required - NO
label | 0763b9be-4fdc-5c4c-b452-4e88aceb5351 |  | note | ENGINEER - R
label | 546ea360-07df-5085-a103-90a57cb92fda |  | note | SUPERVISOR - R
label | 7e0b7d05-5ffa-50c6-8d62-38918b29cdbe |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Prepare
label | be0b9baf-a5ca-5420-834c-d364fa6ebe1a |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 58421f87-de57-5f55-9ae3-469fdaf36c4e |  | note | Accept / Reject Criteria - As per Specification
label | 859f4e08-4cec-5709-ae85-658f3dffb322 |  | note | Frequency Of Inspection Or Test - In-process
label | 93d3b8c4-474b-57df-be46-c1db95319fe7 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP105
label | c2eebfa4-474c-5a5c-ac51-91dab8ed2d83 |  | note | Records Required - NO
label | 6ded286e-34d3-51e7-82ea-0ea940976539 |  | note | ENGINEER - R
label | 081765c8-e7bf-55d5-b8a2-d6ccea6a4b84 |  | note | SUPERVISOR - R
label | a95bfd56-cc58-56ff-bf3c-7e5414032b0c |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Operation
label | 558a05ed-3234-58a0-855d-530595bdbff1 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 685abd4b-07d1-58dd-a480-73120fb4b096 |  | note | Accept / Reject Criteria - As per Specification
label | 38705173-65f2-54e8-b6c0-a9366a7064b9 |  | note | Frequency Of Inspection Or Test - In-process
label | f6a67a7c-f39d-57a4-b10a-6a37659dcfb5 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP105
label | fbae7d88-3b9d-51ff-b72c-87177d1b53d6 |  | note | Records Required - NO
label | b6d9c93e-1903-5aba-92f5-0540cea22ffc |  | note | ENGINEER - W(10%)
label | e52b9399-8412-5688-a20c-97e3ad7d9f57 |  | note | SUPERVISOR - R
label | 55bb0a36-7a24-5bda-9a13-da9a5d957eee |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Maintenance
label | 19c45b1e-4527-5503-b525-1bbb7e0b8397 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 1229d4ed-3859-5250-9be3-2f7fbe633471 |  | note | Accept / Reject Criteria - As per Specification
label | 35712484-9143-58ef-a901-15bef0e34e5e |  | note | Frequency Of Inspection Or Test - In-process
label | e3f06cb8-4f53-51a7-937f-7956a7f9f6a0 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP105
label | 1476d92f-d298-5929-ad7f-8fd4e5655090 |  | note | Records Required - NO
label | 9bc9d0c4-3561-5c46-b76e-93ba8319c5c0 |  | note | ENGINEER - W(10%)
label | e7a3695b-e402-5589-81e7-657c9770e51f |  | note | SUPERVISOR - R
label | 79113772-7c0e-5f89-8fff-85d52f4d8416 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Communication and Report
label | 8b887c4c-9adf-5dc4-b8f8-8e500deaebf1 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 2285fd18-c491-52ce-8c27-0525494610c1 |  | note | Accept / Reject Criteria - As per Specification
label | 29ae95ad-7688-5f59-a959-5e02638b1ad1 |  | note | Frequency Of Inspection Or Test - In-process
label | 6bcc3e4b-6d9e-574f-95a8-bff9e65b36eb |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP105
label | cbb61f18-dd33-59a2-bcd9-ba4e6b811a00 |  | note | Records Required - NO
label | 917ee913-ff1a-5028-b5b8-f37b2b603085 |  | note | ENGINEER - W(10%)
label | 0d669eb4-8e2c-5bd4-b188-03de01fa4cf8 |  | note | SUPERVISOR - R
label | 21d7f1f6-892f-59e5-8ac3-4f2c8c0bbf09 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Incident Reporting
label | 5c6b271f-887f-5e02-92e2-974decdfed7f |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | e5a6adbf-ade2-50da-8edd-0463235c0af2 |  | note | Accept / Reject Criteria - As per Specification
label | 9ba4d001-72a2-5c3d-8284-7ecaab8454a5 |  | note | Frequency Of Inspection Or Test - In-process
label | 7864f0bd-e17d-5b66-86f5-d8a7e4db8ccc |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP105
label | b4c153d5-45c2-5327-8978-6c780441e2f0 |  | note | Records Required - NO
label | 1380f6fe-664e-5967-972e-b1e6d44d85d7 |  | note | ENGINEER - W(10%)
label | 56183e82-7312-5fde-aa83-b06aa969a9df |  | note | SUPERVISOR - R
label | 8b5400cb-4b19-5d82-9c6e-03b241ed6b5b |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Test and Check
label | bfff115f-19ac-5c75-bcb2-c355f91fef46 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 9f934546-9779-5e4a-8ba0-704b41107369 |  | note | Accept / Reject Criteria - As per Specification
label | 4ad23ba9-80ce-59c9-ad69-7bab1143a3be |  | note | Frequency Of Inspection Or Test - In-process
label | 22d6bbc1-1fda-5c4f-87f8-a5155c00e78f |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP105
label | c8d554e4-d883-5f91-aa80-fe1908d42ba2 |  | note | Records Required - YES
label | 8e7cb013-033f-5edb-add8-ea4a9e740434 |  | note | ENGINEER - W(10%)
label | 048e422f-1fe3-5604-89a6-669d92fbe35e |  | note | SUPERVISOR - R
label | 91c926d9-cd36-5f8e-88b1-ac0d753fca00 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - Moa - Thin Asphalt Paving |  |  |  |  | Yes | ITP - Moa - Thin Asphalt Paving | 0af0a936-1fb9-4cee-8d1a-4a0475d340b8
checkpoint-group |  |  | section | 1 - Preliminary and General
checkpoint-status |  |  | checkpoint | 1.1 - Construction Programme Completion
label | e5a47dc3-eac8-5e2c-939d-ca1c7da01622 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 8fd3e1b7-1e73-540d-92cc-e9bbfe007d3b |  | note | METHODS OR REFERENCE - Best Practice Contract Specific MMP
label | 445beb03-98ae-50a5-8017-7fe66cdf9e94 |  | note | FREQ. - Before work commences
label | 60ce3adc-9d99-5111-a343-72298a536c8a |  | note | ACCEPTANCE CRITERIA - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date.
label | ab807ccc-f495-5a54-995e-bd4ad3e3c109 |  | note | INSPECTORATE W/H - Type: - W
label | b5147645-33fb-50f1-9fc9-93c94b0dbf96 |  | note | Responsible Person - Renewals Manager
checkpoint-status |  |  | checkpoint | 1.2 - Approved RQP
label | d67baba6-7aa7-53a6-a4a0-1b159ec7d25d |  | note | VERIFICATION ACTIVITY - Confirmation
label | 9206f4ed-bde2-512e-9923-802568e36c2f |  | note | METHODS OR REFERENCE - Contract Specification
label | 462455a6-ea09-56a6-be23-524b1228fb69 |  | note | FREQ. - Before work commences
label | 1fd456ac-2bc8-5849-ad40-89a1a16a391a |  | note | ACCEPTANCE CRITERIA - Principal Acceptance according to guidelines in appendix 6.3
label | 4d80752b-a0b5-5921-bdbc-aa4ed7ffbf57 |  | note | INSPECTORATE W/H - Type: - H
label | 73395db5-e69e-5b21-8f79-875f9f7615d0 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. NZTA to approve
label | b9549828-9ecb-5f0c-af5a-f9d82128b493 |  | note | Responsible Person - Renewals Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Traffic Management - TMP
label | 00c644c6-9b47-5970-b973-bef7a060afa9 |  | note | VERIFICATION ACTIVITY - Visual check
label | a422b884-4e9b-5a42-8fe8-8944421e7eea |  | note | METHODS OR REFERENCE - CoPTTM
label | 53de7bdd-794d-558e-972e-16f1b7af98df |  | note | FREQ. - Before traffic management set up
label | 95774250-0aca-5bad-82b2-7eeab9e2781e |  | note | ACCEPTANCE CRITERIA - TMP checked and approved Plans approved Current EED (if applicable)
label | 3a47a23a-4803-547b-b07f-2d28f4651414 |  | note | INSPECTORATE W/H - Type: - H
label | 8ae7dc7e-a5da-52b5-87ea-f23978d2ffad |  | note | INSPECTORATE W/H - Description: - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | 785b5221-19d7-5705-8a78-1f774b4f0af6 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Mix Design Verification for all mixes Check Laydown Trials are complete and compliant
label | d1370529-0c5a-5b37-b1d6-02073993783d |  | note | VERIFICATION ACTIVITY - Confirmation
label | b7f079d3-e76d-5f09-a477-bf5bcdb7351b |  | note | METHODS OR REFERENCE - NZTA M/10, P/11, P23
label | f399609c-9eb2-5b48-9d27-5395b134d7a8 |  | note | FREQ. - Before planning commences
label | 898dd335-9519-55f1-a4db-510f520ad326 |  | note | ACCEPTANCE CRITERIA - Mix Design compliant, current and relevant. Batching plant production capability is confirmed
label | 274432b3-c9c6-53c6-abad-f205eab6fcdf |  | note | INSPECTORATE W/H - Type: - H
label | cd1d5928-5e96-5f2f-ba54-32ff4a4b4eeb |  | note | INSPECTORATE W/H - Description: - Hold point - No planning of on-site works shall commenced until the mix design is verified.
label | 51ca756e-ef78-5c00-acf4-1712922ec0c9 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Notification of intention to start work
label | 26fb7c51-c8ef-56e6-bddf-8dcf2c924519 |  | note | VERIFICATION ACTIVITY - Notification
label | e4f083de-e8ef-5a14-8c29-661f361894ea |  | note | FREQ. - Before work commences
label | be0588a9-0290-501c-bad7-ea5282d7d6fa |  | note | ACCEPTANCE CRITERIA - Letter drop to local residents. Greater consultation where required
label | a02d4c36-0c0a-5e33-8bda-ea303b7c2e72 |  | note | INSPECTORATE W/H - Type: - H
label | 915ca15b-e900-5c6b-91f0-1628e0633197 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | 78a24fa4-4663-5a5e-b707-66e05b04eb6d |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Works Extents
label | c42d16f6-41c1-5b04-b83e-190f6831f589 |  | note | VERIFICATION ACTIVITY - Confirmation
label | ae47221f-598d-5ac1-8800-f679ef1cce16 |  | note | METHODS OR REFERENCE - Site Visit
label | 3ca8b3ab-c7dd-5098-9aee-9db3ba8544ea |  | note | FREQ. - Before work commences
label | f8dac946-7635-529c-a43d-f3be32c75d22 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and/or Client to agree extents of project
label | 31a00a6e-eeee-5751-9570-5d072b8cecd8 |  | note | INSPECTORATE W/H - Type: - H
label | d4549bf6-df89-5c83-91ea-36fb462014a6 |  | note | INSPECTORATE W/H - Description: - Hold point - Walk over site with Renewals Engineer and/or Renewals Manager and/or NZTA
label | 5b9257a4-b695-51de-b846-885cfe8f8397 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - Pavement Marking Records
label | 53033fc4-f9a9-5253-bdb0-dcea096cef42 |  | note | VERIFICATION ACTIVITY - Measurment Data
label | 1dba4f0d-4781-5e26-b6d0-93f6ebb5a18f |  | note | METHODS OR REFERENCE - Site Measure or Video Viewer
label | c8fc9de9-b781-5a69-b054-792adc10a9c4 |  | note | FREQ. - Before work commences
label | aae71b81-ad30-5481-b34b-7da199379fba |  | note | ACCEPTANCE CRITERIA - Measure existing markings to aid reinstatement
label | eef56b5b-b581-5e5a-9d7c-3b23c530aadc |  | note | INSPECTORATE W/H - Type: - H
label | 5e927f13-eccc-53c5-8948-737fc9db0a2f |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | 0a355f1e-cc6f-5a89-b63e-d8596f6775cc |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Milling and Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | a6ba41bb-c3af-58ef-8cff-1c3517645bf0 |  | note | VERIFICATION ACTIVITY - Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth)
label | 97280a75-f3ed-5d9d-af9c-f8ac6503181a |  | note | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | 743b7da9-0ecd-52d2-a78a-167935f1442c |  | note | FREQ. - Before work commences
label | 77aa6d01-214b-5ad7-abb9-1ce02db0a779 |  | note | ACCEPTANCE CRITERIA - Zero service strikes
label | 9afee536-bb64-5dbb-8a3a-a4c08cf04722 |  | note | INSPECTORATE W/H - Type: - H
label | 8509aaf6-3ddd-5f08-992b-b1e92ba68235 |  | note | INSPECTORATE W/H - Description: - Hold point - No excavation/milling is to be commenced until services are located and accounted for
label | fe25baa2-c378-548d-81e0-b3fa74fb7980 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Stormwater Management
label | 3144b3ec-fe73-54cb-9df9-b4d585eb04e0 |  | note | VERIFICATION ACTIVITY - Visual check
label | 93ebae2e-7071-5abc-a659-f25d86a4b52f |  | note | METHODS OR REFERENCE - On Site
label | ea359fed-db9e-55e7-a844-05027771a0b8 |  | note | FREQ. - Before work commences
label | 8dacb8b7-2eb0-5b96-b6e9-9af3d361c8c1 |  | note | ACCEPTANCE CRITERIA - Mudtanks bunded or filtered to prevent mix from dropping in or runoff entering
label | ba524faf-4028-585d-8ea4-bd45fae5359b |  | note | INSPECTORATE W/H - Type: - H
label | b05ee2d6-bbda-5bc8-a565-1e9d2accddc1 |  | note | INSPECTORATE W/H - Description: - Hold point - No work to be commenced until protections in place
label | 30537ed0-5ad4-5466-a35d-90bc4a21b712 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Traffic Management - Setup
label | 182d2ef9-6422-506c-9b38-625aeb0ea46a |  | note | VERIFICATION ACTIVITY - Visual check
label | a2544c38-7b71-5ae5-ae72-cb4789aa4ee1 |  | note | METHODS OR REFERENCE - Traffic Management Plan
label | d1e7fd5b-c648-596c-a8f9-1a860135ac3b |  | note | FREQ. - Before work commences each day
label | 92924472-084a-526d-a07d-ca4886c8cd5a |  | note | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | cad64bcd-b7a9-56bc-bd95-14cb3bbef38f |  | note | INSPECTORATE W/H - Type: - H
label | e707966f-5402-521e-8b40-6a8eae2ca9dd |  | note | INSPECTORATE W/H - Description: - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | d1fe89a3-a63c-5784-8676-b0a174d4012c |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Milling Depths
label | 15360013-2117-5297-8ff4-0b7f6b3ec10e |  | note | VERIFICATION ACTIVITY - Measurement
label | d31474dc-a52f-5a1c-bb63-7542e55edaca |  | note | METHODS OR REFERENCE - On Site
label | b5497bb9-b51c-5828-b2a3-53d956100ba6 |  | note | FREQ. - Measure each side of milling machine cut
label | 3c7ecf0f-ade9-55a6-8225-5a5ce171153a |  | note | ACCEPTANCE CRITERIA - Every 10m. Depth matches target
label | b8a8f6b7-225e-5563-9676-6a4c628b8b7a |  | note | INSPECTORATE W/H - Type: - H
label | 908f7010-7e9a-5d89-a5ed-3fcd061adcbb |  | note | Responsible Person - Site Foreperson / QA
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Service Covers Preparation
label | 6e3313a1-da83-5ba3-b4c1-1d9aafa11256 |  | note | VERIFICATION ACTIVITY - Visual
label | ca26c359-b250-54f6-b752-24de65d451ca |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 1d31df14-3b4f-5f10-b116-2b9d50a09270 |  | note | FREQ. - All Covers
label | 52c4732f-4032-5c40-9bbe-740272c3e8ad |  | note | ACCEPTANCE CRITERIA - Hand excavation around ironwork and adjustment to desired level (if required)
label | 38a59846-4177-5da6-9731-ee15d8f8e636 |  | note | INSPECTORATE W/H - Type: - H
label | d8be3337-fd9b-527f-be7d-196ec4e853dc |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Additional Surfacing Preparation
label | 36cee319-fe37-5e17-b14f-0d4384cf019f |  | note | Side Roads; Accesses; Driveways; Dish Channels; High Shoulders
label | 6878cc4c-6a21-5b8a-89d8-31e6a13b0e11 |  | note | VERIFICATION ACTIVITY - Visual Check
label | f0c4b534-5b6c-5b00-b334-ede276c87644 |  | note | METHODS OR REFERENCE - Per Design
label | efdf6e6e-4612-5eb3-81c8-be926a4dc072 |  | note | FREQ. - Before Membraning and Paving
label | c1f109f0-4234-5df5-bf7e-b0e579568dde |  | note | ACCEPTANCE CRITERIA - Have all areas of additional surfacing on the design been prepared, membraned and marked for paving?
label | b7d41622-5e28-55c9-ad19-f0e9ffd71ef9 |  | note | INSPECTORATE W/H - Type: - H
label | c044dc51-451d-568b-ae03-dd3f59d36e66 |  | note | INSPECTORATE W/H - Description: - Hold Point – All areas planned for AC are prepared ready for surfacing layer
label | fd9bde63-a593-5884-b520-2fbf0fd66396 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Over-Milling
label | 9de2fe44-c334-5769-b899-c9adaa5bbe40 |  | note | VERIFICATION ACTIVITY - Measurement
label | 8b2bc519-123b-588b-8720-ebbaa592358c |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 9166e640-cd56-53eb-b25e-d513c306745e |  | note | FREQ. - Prior to pre-level
label | 775a3480-874e-5977-9fa0-e5fb36834a76 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree need and extent of over-milling and infill.
label | 83b0abf0-98fa-502e-8bde-b53d762536c1 |  | note | INSPECTORATE W/H - Type: - H
label | 37b7619d-231d-5763-a73f-4bcff908ef7b |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Pre-Level
label | 4d63610b-8748-5e48-a06a-eff62bdb384f |  | note | VERIFICATION ACTIVITY - Measurement
label | a67a4d07-3c58-559b-91de-efb962a2ac14 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 266efe5c-fa93-5af9-ab4a-c6fd8f5cdbba |  | note | FREQ. - Prior to surfacing
label | aec37c12-1f0e-503c-91f0-e89daa1cd370 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree pre-level extents
label | bdeb4cf4-d406-5360-a7d5-2db210d5a2eb |  | note | INSPECTORATE W/H - Type: - H
label | 0f489535-a4a6-5119-90e6-7541430833b6 |  | note | INSPECTORATE W/H - Description: - Hold point - Inspection and agreement by NZTA
label | fffcf423-8405-58a5-ab8c-9180719418c9 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.9 - Membrane Sealing
label | 6de2cd92-ed9f-5505-98e7-c6bda74d618f |  | note | VERIFICATION ACTIVITY - Visual
label | 00be538c-352b-50c0-b060-cabe2710bfd8 |  | note | METHODS OR REFERENCE - On Site
label | 1528a428-7556-5a93-8666-9546d02b66f8 |  | note | FREQ. - Prior to surfacing
label | 77d2781e-b14b-55ac-99cb-64177c4b0eed |  | note | ACCEPTANCE CRITERIA - Membrane seal meets design and extent. Sealing Docket record kept
label | ceac61a3-c350-5e5f-b34d-5423b26566ea |  | note | INSPECTORATE W/H - Type: - H
label | 968a90f6-87c3-52a3-91f0-ec5711442bc8 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Paving Structural
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | 7309eda2-7c05-53d6-b24a-b846afed8c87 |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | c3a309fd-3381-56bd-aeca-5ed7b7afc624 |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | 94a80904-1c8f-5821-99e4-59e7f8d59843 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | cbd9a5f4-6985-576c-8d5e-132531b8e9ef |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 09859ca6-b921-54f0-a585-e98833203e93 |  | note | INSPECTORATE W/H - Type: - W
label | e72fff16-51a5-5226-b5be-b338b8d2d7c9 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | fcbf0389-ed2e-5729-9744-d5167f2eee43 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | e7a7deb6-65f6-5581-85b3-6e6b98fa6867 |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | 20b699d2-d923-573f-a21f-4aa5a5382a5f |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | 15caa127-004c-52a3-a0c5-c910854727e9 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | c6718bb4-2392-55ad-982d-a1e4f18cea6c |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 2a012ef8-946d-5694-863e-d243ea877dff |  | note | INSPECTORATE W/H - Type: - W
label | f9ed3887-144c-57b8-875e-99d32c9f4665 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 99ecbd61-f00e-5c1f-96d9-f8d3c7db7798 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | 73ddd465-41a7-585d-923a-c477b73de86a |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | a4563f3b-ce98-5cb6-8eee-34705244f0f8 |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | fa6e3497-d0fc-5f07-a08b-55024980876c |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 83cb464f-3882-5406-93be-39353fe8b3ae |  | note | INSPECTORATE W/H - Type: - W
label | a9c156b5-236f-51da-aea7-48d70ecebe93 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 0d537c8d-4a7c-54e1-8114-d7c454ce7cc3 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | 2c80dc56-c171-5ef7-b00d-e13952d1e78c |  | note | VERIFICATION ACTIVITY - Visual
label | 4d64cd65-ed3a-5a1a-b0bd-02b20471229d |  | note | METHODS OR REFERENCE - NZTA M/10
label | 376a7345-06a3-585c-8aab-dac7ae133bd1 |  | note | FREQ. - Prior to Shift
label | 6a40524f-9741-59d7-bf43-3e0705db41f7 |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | a568b24c-1c2a-52a0-97d9-e283b59fbe43 |  | note | INSPECTORATE W/H - Type: - W
label | 5c7fd7f1-ade8-5f1f-b17e-4298616ed9d2 |  | note | INSPECTORATE W/H - Description: - Paving Plan and Crew Briefing Plan completed prior
label | bc938376-bf43-5fee-9bb5-dd776363795b |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | da4eb85d-d26a-5056-8d40-e1ff6c57ae16 |  | note | VERIFICATION ACTIVITY - Visual
label | 822a632c-a9d6-515a-9b80-72a575b050ad |  | note | METHODS OR REFERENCE - NZTA M/10
label | 366dc686-e5b2-5f07-bf6c-549cefe386ae |  | note | FREQ. - Prior to Shift
label | 1210be89-e5c5-595e-b34f-06b740e65c55 |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | 5e4dc515-f52d-59ff-97ee-42ab1308ab5c |  | note | INSPECTORATE W/H - Type: - W
label | c1252e5f-c91f-505a-8c96-d278063a7991 |  | note | Responsible Person - Paving Supervisor / QA Engineer
checkpoint-status |  |  | checkpoint | 3.4 - Mix Inconsistency and Deficiency
label | 7a853e72-862d-5c63-a934-832e1579948f |  | note | VERIFICATION ACTIVITY - Visual
label | 273b1042-041f-5846-a241-653905353e4a |  | note | METHODS OR REFERENCE - NZTA M/10
label | f8cef7fd-13a0-5ddc-9b7f-6e8d16bf8c00 |  | note | FREQ. - Continuous
label | 363e34b8-1ef1-5008-ba48-9f4e94cf2628 |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | 6dece53e-33de-5ada-acf3-8fff18998552 |  | note | INSPECTORATE W/H - Type: - H
label | e733a95d-2bdb-5f80-9fc4-623032d73ed0 |  | note | Responsible Person - Site Foreperson / QA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Load Locate
label | c60e28cc-241a-5c39-b3c1-cddabbc137d8 |  | note | VERIFICATION ACTIVITY - Measurement
label | 58ebfaa4-53c7-5e21-970e-45c7bbc42807 |  | note | FREQ. - Every Load
label | 69b7a511-7e6c-5f24-ae74-a95b79497bd1 |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
label | cb582573-22a2-5c3a-a624-7d4b69db479e |  | note | INSPECTORATE W/H - Type: - W
label | fae2e8b3-8086-5210-99fb-5b45a99d9e8b |  | note | INSPECTORATE W/H - Description: - Per standard practice
label | 5d659ff2-f791-5ee9-91bd-af7de4c2b769 |  | note | Responsible Person - Quality Assurance Engineer
checkpoint-status |  |  | checkpoint | 3.6 - Laying Temperature
label | 8668451a-a92e-5657-9de6-88a46c7833ff |  | note | VERIFICATION ACTIVITY - Confirmation
label | 8fe82c43-1e49-5136-b2ea-53ea79932e7b |  | note | METHODS OR REFERENCE - NZTA M/10
label | e73928cb-e4e8-5bd5-a352-0454e7514256 |  | note | FREQ. - Every Load
label | de457b84-0b41-5e64-8020-43b8a1177992 |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | 92f56778-ebcb-5be3-981b-5358e32548d0 |  | note | INSPECTORATE W/H - Type: - H
label | cb539a86-c1d4-5ef9-ac67-96c3ab6b35be |  | note | INSPECTORATE W/H - Description: - Hold point - Reject mix for non-compliant temperatures.
label | 1e99bded-35ae-54b3-a6a5-e478a6429b9a |  | note | Responsible Person - Quality Assurance Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Compaction
label | 18984bf6-06dd-528d-8e70-72ad0acad72f |  | note | VERIFICATION ACTIVITY - NDM Testing
label | 00e7ba55-0492-5968-a9cf-5f0860d380cb |  | note | METHODS OR REFERENCE - NZTA M/10
label | c5d30f95-3ebd-5281-af7b-b76b522eb149 |  | note | FREQ. - Minimum: 1 Test per 300m² within Mat. 1 Test per 100m of joint.
label | 9e07beab-f208-5714-b00e-257641df6570 |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | fa98e3a4-89d2-5999-88c1-8bb786fa44ab |  | note | INSPECTORATE W/H - Type: - H
label | ebf68f31-3bb8-56ff-b9df-451a2b893a9f |  | note | INSPECTORATE W/H - Description: - Hold Point - No Wearing course paved until any non-compliance is sorted
label | 6727f2ec-430d-5025-a8f3-fbe877ab962c |  | note | Responsible Person - Quality Assurance Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Roughness
label | d7c6baa5-73a5-5737-bbae-457a12f49224 |  | note | VERIFICATION ACTIVITY - NASSRA Testing
label | 5cd0197d-9ec9-5191-8ade-9e36f71159ea |  | note | METHODS OR REFERENCE - Contract Specification
label | 502eaa71-102b-5eef-b0ac-73e6f8a789b8 |  | note | FREQ. - post construction
label | f994a193-fe18-5aef-884e-64720d2ca8b8 |  | note | ACCEPTANCE CRITERIA - NASSRA rolling meter average under 60, max of 70
label | 87894842-0d6d-5f99-b1e9-e663f2e72dbf |  | note | INSPECTORATE W/H - Type: - H
label | 001c0d18-c816-56ad-b9cd-e997886b8649 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Paving Wearing Course
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | 1642a48d-eef7-509b-a6bc-8b83ab95f2d5 |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | 43811bf9-931a-5234-a0f4-beba20154444 |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | 986a01f9-f27d-5405-b5a1-99926f6f548e |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 54520552-142e-53e3-b2c0-da509616b6e8 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | e72f8f1b-75f4-561c-8d77-93295a680a84 |  | note | INSPECTORATE W/H - Type: - W
label | 523c5154-5bf5-583e-aeaf-df27d5037107 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 472fedbf-742f-52a9-8121-0ec026cc3f71 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | 60aadc18-7546-5783-9568-512dec36f353 |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | 03ac7f48-9d69-5e90-840b-a2c9c556bae8 |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | 6b701724-3b14-5cb9-99b5-3d679fcda99d |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | d6a4c6ce-b97e-5456-afe4-7fd8987d56c9 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | b76fdf8c-d11e-5c70-a550-cf61f860f41a |  | note | INSPECTORATE W/H - Type: - W
label | 817b0911-8b15-5370-b851-aec05b60aed1 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | b7dec04b-e89a-53f4-8907-758eda393bbe |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | e4470957-2194-597d-9340-6fc272e50dba |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | 0941cb9e-87e8-52df-baaf-af1197b2dcef |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | b07b2db6-c1ae-575c-979c-7595ac1822ee |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 6e1a9d1e-915b-5289-b819-397f02387e2d |  | note | ACCEPTANCE CRITERIA - Per Mix design
label | a35db62b-2e37-51d9-b56f-2946fb9ac328 |  | note | INSPECTORATE W/H - Type: - W
label | 4f28411f-9e4e-56f5-abd2-38921445f619 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | b27f107d-5321-5b9c-8b66-6c88dd961d64 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | 1bf09610-60fe-50cb-b2ea-7e07891e4e85 |  | note | VERIFICATION ACTIVITY - Visual
label | e9ec18b4-ed36-5198-8a9b-b68af35b926d |  | note | METHODS OR REFERENCE - NZTA M/10
label | 82462564-1e2a-5fbe-967d-1e83578ac5ac |  | note | FREQ. - Prior to Shift
label | ffceb027-db3a-5dc4-8d63-c36cfc4a7e97 |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | f3fc6924-b9a3-5c0e-bbf4-8c55a5065e24 |  | note | INSPECTORATE W/H - Type: - W
label | aec868df-787e-50c5-b968-9269fbb76542 |  | note | INSPECTORATE W/H - Description: - Paving Plan and Crew Briefing Plan completed prior
label | 2ceba2a8-8df3-51e4-bcc1-ee89c8685c47 |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | 1c3680bc-321c-5117-a458-cee1e6b0030b |  | note | VERIFICATION ACTIVITY - Visual
label | e5d43fea-eb8e-5c6d-ad9f-b44666cba2d2 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 62df9e4c-b207-5704-8f75-e7d2931f1756 |  | note | FREQ. - Prior to Shift
label | d21e4f9e-c1b5-54db-9ba4-7ff1817d9e1d |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | fc6e5f8f-7b42-5a98-9513-6c6b04052857 |  | note | INSPECTORATE W/H - Type: - W
label | 051ad0f6-ba8c-57ad-b487-533f8d702e90 |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.4 - Grade 3 Membrane Sealing
label | 1080d11c-5fdb-5528-864f-8954fad69710 |  | note | VERIFICATION ACTIVITY - Visual
label | 8a59a916-9492-5e01-a33b-340a6654dc70 |  | note | METHODS OR REFERENCE - NZTA M/10
label | db693b71-5331-5efc-bc50-51c0c88eb604 |  | note | FREQ. - Prior to Paving
label | acdf07a7-d523-5dc8-9cf7-c4d62df3196b |  | note | ACCEPTANCE CRITERIA - Applied 2.0l/m² residual
label | fa92f62b-decc-5f52-a8fb-e55937773578 |  | note | INSPECTORATE W/H - Type: - H
label | 3ed6947f-6bc3-59bd-8037-8c00c85cbf50 |  | note | INSPECTORATE W/H - Description: - Hold Point - No paving until Membrane Done.
label | 25478ac6-eac9-5801-ad23-b482cc95a10a |  | note | Responsible Person - Paving Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Mix Inconsistency and Deficiency
label | b059abce-5aba-54e6-9335-1ad5fa6692d5 |  | note | VERIFICATION ACTIVITY - Visual
label | 97b25d54-8305-510b-904b-5893f6adbdd8 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 24f5cdd3-a910-5de3-b0ec-ea4f5736eb84 |  | note | FREQ. - Continuous
label | 54c69b32-2658-57dd-9f0c-af4366e60cab |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | ee53deca-b4fc-5ae0-a09e-2dd9213255c1 |  | note | INSPECTORATE W/H - Type: - H
label | bfd95b52-694b-5412-a9c9-791a323d0849 |  | note | Responsible Person - Site Foreperson / QA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Load Locate
label | de1229fb-d22b-57e1-a21b-6c8f3e063612 |  | note | VERIFICATION ACTIVITY - Measurement
label | 25c72d1d-cfa2-555c-8b59-160a3c2143bf |  | note | FREQ. - Every Load
label | 86c1b827-9e43-53e7-a9eb-4e6bbde15365 |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
label | 581673b5-6208-5974-a08b-1bac0f5ee269 |  | note | INSPECTORATE W/H - Type: - W
label | ac7b8135-bb0a-5b17-91d1-7f304e60f080 |  | note | INSPECTORATE W/H - Description: - Per standard practice
label | 2bb22bc4-3e45-54b6-b656-402542afa68e |  | note | Responsible Person - Quality Assurance Technician.
checkpoint-status |  |  | checkpoint | 3.7 - Laying Temperature
label | f31061ac-066e-5323-bc82-c4909c4d004b |  | note | VERIFICATION ACTIVITY - Confirmation
label | 7e2ab270-8516-5514-8ab4-a36eb08a072b |  | note | METHODS OR REFERENCE - NZTA M/10
label | ad8d6263-315f-5dbd-941a-b07d7ffbe101 |  | note | FREQ. - Every Load
label | 91951b3a-862e-5559-8786-88e3cd729217 |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | 49f1680b-44d5-5354-856d-05c9c310a1fe |  | note | INSPECTORATE W/H - Type: - H
label | 42f9c974-c56a-5631-9630-fad8dc130ab0 |  | note | INSPECTORATE W/H - Description: - Hold point - Reject mix for non-compliant temperatures.
label | e9f98ea8-f1ac-5d3d-880b-f8d1616e1762 |  | note | Responsible Person - Quality Assurance Technician
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Compaction
label | 6b2f3f63-176b-572f-954f-de77a34c7d52 |  | note | VERIFICATION ACTIVITY - PQI Non-Nuclear Gauge/Cores. Or Non Distrctive Method Testing.
label | 39db2127-c000-54d2-a1f7-ad5f8b17313f |  | note | METHODS OR REFERENCE - NZTA M/10
label | f76570af-dc0f-55fb-b0f7-cb2019fd4f73 |  | note | FREQ. - Minimum: 1 Test per 300m² within Mat. 1 Test per 100m of joint. Minimum 8 cores on Mat and 3 on Joints as Per M10:2020.
label | 813d2f75-dc70-50fe-8588-1de31728f99f |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | f16c3efe-a498-5b3d-a75f-41e7122757aa |  | note | INSPECTORATE W/H - Type: - W
label | c4d2ad0c-3247-547a-838a-b6961ccab395 |  | note | Responsible Person - Quality Assurance Technician
checkpoint-group |  |  | section | 4 - Site Reinstatement / Clearance
checkpoint-status |  |  | checkpoint | 4.1 - Post-seal Area Check
label | fa82d66a-5840-5308-8cb1-1094f8147ed4 |  | note | VERIFICATION ACTIVITY - Measurement
label | e15208c6-cd7b-5b18-8025-7eee18ec5dcc |  | note | METHODS OR REFERENCE - On Site tape-measure
label | 2f84d3a3-61c7-50c9-8c3f-3afb5434de50 |  | note | FREQ. - After Surfacing
label | e170cb7f-2bad-557d-ad4e-fd1e8bd57eee |  | note | ACCEPTANCE CRITERIA - Check sealed area meets design
label | d8e7c0f3-8ca3-5cb7-a256-32fe8a69c37e |  | note | INSPECTORATE W/H - Type: - W
label | 9a037d2d-0e06-580e-91b9-314244f58238 |  | note | INSPECTORATE W/H - Description: - Notify Renewals Engineer or Renewals Manager
label | 4363e4cf-a8c8-53d1-8301-2b88e038f81d |  | note | Responsible Person - QA Engineer
checkpoint-status |  |  | checkpoint | 5.3 - Service Covers
label | 9fea93d1-5b7a-5d0f-b40e-d1479bca3b7e |  | note | VERIFICATION ACTIVITY - Measurement/Visual
label | 107c6113-517b-5c7e-9ee5-ed9f959a2db9 |  | note | METHODS OR REFERENCE - On Site
label | 7ad19063-df25-59a1-8313-7d16f31e3475 |  | note | FREQ. - After Surfacing
label | 44e10c3b-2f26-501d-8108-8abb94720f25 |  | note | ACCEPTANCE CRITERIA - All service covers are checked and adjusted (if necessary) to finished level
label | 8691f9a0-df7f-59a4-8e69-a2b743e870b0 |  | note | INSPECTORATE W/H - Type: - W
label | 469189ee-9cb1-5100-9776-79e9c4cccea3 |  | note | Responsible Person - Paving Supervisor / Foreman
checkpoint-status |  |  | checkpoint | 5.4 - Joint Sealing
label | d90816d9-95b1-5e75-89f3-dc905669cc2f |  | note | VERIFICATION ACTIVITY - Visual
label | fd817192-4f98-55d9-bb68-a4e6c1f89609 |  | note | METHODS OR REFERENCE - On Site
label | dbe87b29-2c13-5cb2-bad4-d5935da60ca1 |  | note | FREQ. - After Surfacing
label | 0d8b0d79-934f-53c1-810e-d6315be90b1f |  | note | ACCEPTANCE CRITERIA - Check cold joints are bandage sealed
label | a45c0db4-e318-51f8-876f-6d5bca79c7e4 |  | note | INSPECTORATE W/H - Type: - W
label | 4f90eef2-d4ef-542b-bd25-96c224e22644 |  | note | Responsible Person - Paving Supervisor / Foreman
checkpoint-status |  |  | checkpoint | 4.2 - Road Marking
label | b58fb145-6be4-5686-bbc9-2e58bf7e4589 |  | note | VERIFICATION ACTIVITY - MOTSAM
label | 73710bdd-01ac-5569-89b0-bc3f122279a5 |  | note | METHODS OR REFERENCE - Visual inspection
label | 2ae95875-7ebf-5093-9f39-4b9368eb39a4 |  | note | FREQ. - All markings
label | c13018f3-f437-585f-9b2d-4e01f14f4664 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, or per design
label | c86d644b-9ecc-5232-a336-dedbfd8b3080 |  | note | INSPECTORATE W/H - Type: - H
label | 26b2998e-1458-5506-b743-b04f1fe77eac |  | note | INSPECTORATE W/H - Description: - Hold point – Site TTM cannot be removed until markings reinstated
label | 616466ed-8eab-5ab6-9bc5-162b13253ff9 |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 - Other Traffic Services - Marker pegs/ Signs/Markings/RRPMs Replaced
label | 0e853e58-51f8-5236-a084-513da86857ce |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | f2a56252-4be8-52af-9bf2-be78e1373f45 |  | note | METHODS OR REFERENCE - Visual inspection
label | a384a617-083c-57c8-8671-d5551f8ba78b |  | note | FREQ. - All signs/markers
label | d2fc16a3-2619-52ca-b836-cb709d7c8f3f |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | 9f952322-80e2-5441-b87a-f7873609246c |  | note | INSPECTORATE W/H - Type: - H
label | 2ce87fcb-296d-5b45-84df-8eefc168b86b |  | note | INSPECTORATE W/H - Description: - Hold point – Site TTM cannot be removed until marker pegs, signs, markings and RRPMs reinstated
label | 64037183-8380-5410-bece-8c22b9169299 |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Stormwater Management Controls removed
label | 423ab3e4-2843-5b4b-a2f9-0e615a591f54 |  | note | VERIFICATION ACTIVITY - Visual check
label | 609dfbde-e365-5a06-850e-ed9aacf01677 |  | note | FREQ. - All installed measures
label | 3f68dea0-59d6-5c6c-b5ad-6d87778c50b0 |  | note | ACCEPTANCE CRITERIA - Installed controls are removed
label | 29512998-ca5d-5323-ba03-a729f17fc08b |  | note | INSPECTORATE W/H - Type: - H
label | 09519b74-d674-532b-9433-52cfd197cba8 |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Traffic Management Removed
label | 1f613a41-6d7b-527e-bab3-c73941df29a7 |  | note | VERIFICATION ACTIVITY - Visual check
label | e4427cca-45c8-586d-ae10-c3afd74e36ec |  | note | FREQ. - When safe, after all physical works completed
label | 19ade4b0-e892-50f1-ab79-7e613498613b |  | note | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | 8f16852a-8c3e-529b-b3ff-c3fd426a5d2d |  | note | INSPECTORATE W/H - Type: - W
label | 6b62dd27-62a8-5e31-953f-7fff0a8ca584 |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.6 - Site left clean & tidy
label | 4c6b4601-a603-57c1-af8d-0a9b21937eb8 |  | note | VERIFICATION ACTIVITY - Visual check
label | 9348bdf7-1d0e-5e39-b6a2-14301559c67a |  | note | FREQ. - After vacating site
label | cd462e59-e0dd-528f-bca7-290aa3a6c4cd |  | note | ACCEPTANCE CRITERIA - Stockpiles removed; Plant removed; Litter cleared from site
label | a543253b-469b-5d4d-86b6-acd073624567 |  | note | INSPECTORATE W/H - Type: - W
label | 24fbc2c0-5f4f-5221-a8d6-bcfc8167c790 |  | note | INSPECTORATE W/H - Description: - Invite NZTA to carry out joint site inspection to inspect site.
label | b4e48fee-7e22-5bfe-843c-4b945e4243e4 |  | note | Responsible Person - Paving Supervisor
checkpoint-group |  |  | section | 5 - As Built Records
checkpoint-status |  |  | checkpoint | 5.1 - Collect asset data
label | 4647faa8-e12b-51d8-843c-138f1a841899 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | bfd956db-4525-5936-958b-da616c45ee32 |  | note | FREQ. - During construction
label | 61e14425-8870-5050-95fa-aa9e01ebd084 |  | note | ACCEPTANCE CRITERIA - All relevant as built information collected.
label | ce0ec53f-41da-5cda-a465-0598e8996f1b |  | note | INSPECTORATE W/H - Type: - W
label | 052a72a2-c499-5d43-9251-b7573480faa9 |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.2 - Enter asset data into RAMM and/or register(s)
label | 2b4aa054-2409-5b0e-ab63-a2e45db49193 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | 03cac003-4046-5ac2-9490-6c95a18d0719 |  | note | METHODS OR REFERENCE - RAMM
label | 8c0ab7dd-6301-589b-bd04-104d36712f2c |  | note | FREQ. - At completion of work.
label | 2260d9ab-2ece-507c-beef-c24252446d6a |  | note | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.
label | da046030-64ec-5b2c-9f7f-2273ccc4d64a |  | note | INSPECTORATE W/H - Type: - W
label | e473ffa1-09de-5be6-997d-a0bdb37433f7 |  | note | INSPECTORATE W/H - Description: - Data entered by 20th of follow month after month of completion
label | 8bac7dd9-1d6b-5f83-a469-12ce8925264c |  | note | Responsible Person - Asset Information Manager
checkpoint-status |  |  | checkpoint | 5.3 - Construction Completion Report
label | 155ba25c-1a3e-5986-bb66-0d73cedfcda4 |  | note | VERIFICATION ACTIVITY - Confirmation
label | a173f1c3-79a6-51ae-a808-eae4cc883207 |  | note | METHODS OR REFERENCE - Contract Specification
label | 6fcfa020-80eb-582b-adaa-71bca647af71 |  | note | FREQ. - At completion of work.
label | 4048e20d-8e80-5ec7-a786-944365f761cb |  | note | ACCEPTANCE CRITERIA - Checked and approved
label | d00aea50-8e2c-5e91-a00b-18b18902ab3f |  | note | INSPECTORATE W/H - Type: - W
label | 5a09ae95-7058-52b8-be13-ef956dd2618c |  | note | INSPECTORATE W/H - Description: - Completed within two months after Paving Wearing Course
label | e10edc23-7867-54fb-b440-0d5ebf607397 |  | note | Responsible Person - Renewals Engineer/ Renewals Manager
checkpoint-no-status |  |  | checkpoint | Quality Assurance Close Out
text | b9b216e8-ef88-5c13-9ae4-73323490fbad |  | textbox | Quality Assurance Close Out by - Name:
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair Low Shoulder - Grading | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair Low Shoulder - Grading | 0c80dcb3-e70a-40dc-b429-f341d1b777e7
checkpoint-status |  |  | checkpoint | 1 - Prepare
label | 1e4aca58-a992-5be2-bbd2-3d7731b37b60 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | acb6e734-d7ac-5334-9724-8240ac3ec7e7 |  | note | Accept / Reject Criteria - As per specification
label | a3ef260f-86c5-553a-b7bf-bbb0cdba9cc1 |  | note | Frequency Of Inspection Or Test - In-process
label | 9836a643-bc90-56e8-9609-979a823f5d10 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP037
label | c2e49714-30f2-5905-89d1-f14a5f7bd029 |  | note | Records Required - NO
label | 9a0f3fd4-1452-5dcb-b44c-8e333009f932 |  | note | DOWNER ENGINEER - R
label | 2334d3a2-673e-5893-8ba5-a7f58ffaf133 |  | note | SUPERVISOR - R
label | 95724052-cc0a-5062-a07e-f0b18e0d9f1a |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Remove EMP
label | a751120b-96e5-53ab-ae5b-70866c396755 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 491cb46f-7216-513c-a3aa-231c7cfa9c35 |  | note | Accept / Reject Criteria - As per specification
label | 3a005c5b-74ea-5510-8c42-f2ac16a974f6 |  | note | Frequency Of Inspection Or Test - In-process
label | f0d63694-5b3b-549a-94a8-834f3eb59938 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP037
label | ea6513ca-168a-5a28-ad85-f35800f5cd61 |  | note | Records Required - NO
label | e458c610-4b6c-5b27-a240-4105e06db3a9 |  | note | DOWNER ENGINEER - R
label | 99cd72e9-c66e-57ae-b7c0-629f588a7a9d |  | note | SUPERVISOR - R
label | 18ed8b00-8b40-5c76-90ec-ba9b9073437c |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Initial Cut and Grader Steup
label | 97523e7d-910b-5456-8be4-8a30dd051ec7 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 09784434-df70-52c5-9ade-0096b57f89fd |  | note | Accept / Reject Criteria - As per specification
label | 0d1a3740-2bd7-50e4-bb7a-c277fb30784a |  | note | Frequency Of Inspection Or Test - In-process
label | f0176432-7f63-50d7-82dd-d477bc64f55c |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP037
label | 0c9a70cd-8276-5dc1-858c-c838c6ea423b |  | note | Records Required - NO
label | 84c5bf19-ae7f-535f-a3cf-772719318558 |  | note | DOWNER ENGINEER - R
label | aba1e4e7-c04f-5585-a100-9e2e6812508d |  | note | SUPERVISOR - R
label | 421ccf41-0d45-5c62-9330-e0754917abd1 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Final Shape and Trim
label | e3a27004-011d-513a-9b4e-6fa425b387d8 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | a3f53aae-520f-5133-a1bf-6c98bc708607 |  | note | Accept / Reject Criteria - As per specification
label | a308b6fd-b4df-525a-8bcd-8e33bff35477 |  | note | Frequency Of Inspection Or Test - In-process
label | 0c1ca099-1e9e-561c-81ce-fd4b5fe72d8b |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP037
label | d4077907-8088-5f30-95e2-2440d906bb70 |  | note | Records Required - NO
label | 18cbf325-d615-5bcc-b007-4cd5d18f10d1 |  | note | DOWNER ENGINEER - W(10%)
label | 9095ebee-30cf-5509-a00c-c8419cc78274 |  | note | SUPERVISOR - R
label | d6ad456b-566d-5fdc-a3a0-fe5dfa0c3ffd |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Test and Check
label | d5502cd3-0978-5a80-9b22-02342f6b7cfe |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | cce8cecf-c4c7-5e05-a634-47af6dd57f30 |  | note | Accept / Reject Criteria - As per specification
label | dca2b471-3a6c-5f61-a90c-0d3e143f3251 |  | note | Frequency Of Inspection Or Test - In-process
label | 3d821d1a-27ef-5101-9a87-6693dc37b737 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP037
label | a74c462a-93ac-52d1-9547-a7488472bd4b |  | note | Records Required - NO
label | a53b3ef7-d831-5aa3-a6c4-d70b3785851d |  | note | DOWNER ENGINEER - W(10%)
label | 01bba890-02e3-500e-8618-3ee72af979c8 |  | note | SUPERVISOR - R
label | 2d055829-611a-5210-80f7-7e3a9412742a |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair Surface Depression - Machine Premix Method | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair Surface Depression - Machine Premix Method | 0fc450c1-2efa-44d6-a3e1-28766db60ea5
checkpoint-status |  |  | checkpoint | 1 - Prepare
label | fb311b0b-ed51-5b2d-a0ab-787611414530 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | bbef735d-c02f-575f-85f2-e6ab699c51e8 |  | note | Accept / Reject Criteria - As per specification
label | 1efcd6d7-9984-5ed7-ac27-4315f0ab4ff8 |  | note | Frequency Of Inspection Or Test - In-process
label | 669457bd-1312-5b01-a81e-4a01deafdd05 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP040
label | fe611335-d496-5d68-b791-ce6ddf91cd35 |  | note | Records Required - NO
label | dd5851de-ce79-5e85-acc8-235c7ba40685 |  | note | DOWNER ENGINEER - R
label | f2090399-1ed6-54b1-a091-10169b45f67a |  | note | SUPERVISOR - R
label | 82dfee32-859d-5ba5-b7ca-d96b3d0a3139 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Milling
label | e6b06aeb-c8b9-57a0-b480-76c3d4c555ce |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 9eb99f2d-eca4-58a2-b372-54197f110696 |  | note | Accept / Reject Criteria - As per specification
label | 5856b0cf-1725-505d-b8d2-ea4b64fe4404 |  | note | Frequency Of Inspection Or Test - In-process
label | 52a645a3-0b25-5b7b-b8f4-0d206d75074c |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP040
label | 6fe68221-ffcc-55ac-9148-9be02cd34d9f |  | note | Records Required - NO
label | 2685e783-f641-5aca-a938-c8586edbc1a0 |  | note | DOWNER ENGINEER - W(10%)
label | a963ef93-3ffb-5091-918a-b524e8ce840f |  | note | SUPERVISOR - R
label | 611e3ece-8a42-59ff-969a-a7150c072168 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Application of Binder (Tack Coat)
label | 5904349c-0f1f-50af-93bd-6a9ef09ccc10 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 9949ac0a-528f-5b91-b95a-91ea890fbd6b |  | note | Accept / Reject Criteria - As per specification
label | 16a49d04-20d8-5dfb-85cc-cd05400db9d7 |  | note | Frequency Of Inspection Or Test - In-process
label | 825b3fa2-7932-569b-a37e-403f7d579e84 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP040
label | c9d628b8-4df6-5043-b570-d0f2e4c898f9 |  | note | Records Required - NO
label | 61d69fe6-3e65-5734-845b-6cd2b209cd77 |  | note | DOWNER ENGINEER - W(10%)
label | 643b90c9-59fb-54a7-879e-257030e9345f |  | note | SUPERVISOR - R
label | 5cddaf04-6f89-525f-8947-debac8ce530b |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Base Levelling
label | 1f36659e-7182-5272-b1fa-6781278729e5 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | d0f690d3-2d51-5619-aa63-d0a055c569bc |  | note | Accept / Reject Criteria - As per specification
label | 73fa754a-f909-5859-a7ef-fcae7c2c66a7 |  | note | Frequency Of Inspection Or Test - In-process
label | 7488429d-5054-5c61-b12a-ceb35a1afa67 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP040
label | ae5dc5e9-989e-5ca9-8fa2-2859f13e31e3 |  | note | Records Required - NO
label | ece9c504-4f70-5c1e-91d9-335e2cf3d896 |  | note | DOWNER ENGINEER - W(10%)
label | 2a1db078-db14-5d71-b58b-4329dd46cab2 |  | note | SUPERVISOR - R
label | be9fea13-b2b2-54a4-9583-3f14c9bbb0e7 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Layer Premix Material
label | cfdff108-773c-578e-bf76-7fc1263d61ea |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | ffca81f1-f2a3-515e-b390-416348b0adaa |  | note | Accept / Reject Criteria - As per specification
label | 7bd38f56-1fb3-5243-9e18-c35b186df04b |  | note | Frequency Of Inspection Or Test - In-process
label | 597ab99f-457c-5a1e-870c-fd381acc1f84 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP040
label | 18605fdd-6076-5179-a789-ca7ffc5a34a5 |  | note | Records Required - NO
label | 44c0488b-0797-5e6c-aeb5-e2871145e7ef |  | note | DOWNER ENGINEER - W(10%)
label | cd3c545d-e98b-5003-9a15-47e73e06efa3 |  | note | SUPERVISOR - R
label | c00cdb21-52cd-5c5a-91ba-10c543cab582 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Final Compaction
label | e6c9aec4-0b00-5474-a5c8-3ed01bd1d6f0 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | f6fa565a-9c73-5f6e-8249-a8aaf5681b40 |  | note | Accept / Reject Criteria - As per specification
label | a485acf3-6b7b-5477-b59d-cab809f8ebe0 |  | note | Frequency Of Inspection Or Test - In-process
label | 6657ba4c-1921-5947-b40e-7da03bff0bcc |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP040
label | b58a0bad-9800-5691-85df-5e18a11bc66d |  | note | Records Required - NO
label | fe451b66-134b-5b4a-bab4-fc773a7cac3b |  | note | DOWNER ENGINEER - W(10%)
label | 3528b44f-c344-5ef8-91b8-e29055b1de2f |  | note | SUPERVISOR - R
label | 0dbf7796-740c-52ef-8425-d045c0f8e863 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Blinding
label | 9e66a5a9-c915-588d-89c2-2d231c106e84 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | dc8d1b45-73e2-5921-ae32-4f6d0d371481 |  | note | Accept / Reject Criteria - As per specification
label | ec13a8f3-7e36-5923-b723-3fa65765d089 |  | note | Frequency Of Inspection Or Test - In-process
label | 72ef32d3-72c8-56b3-8dee-05f0a68f0dbf |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP040
label | b30a81f6-e536-53bd-9fd9-f568a9c8c089 |  | note | Records Required - NO
label | 4b42e5ee-75ba-5b18-8ae3-3e9139af072d |  | note | DOWNER ENGINEER - W(10%)
label | b1f55828-ed14-5fd4-bbb2-174bdabc1c2f |  | note | SUPERVISOR - R
label | 7f06cf96-1fe0-579e-84f2-643f5f8b4f79 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Test and Check
label | 4457fc71-b7f0-5ead-8009-ea71473990bc |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 9a72146c-94d0-5053-9c49-8ad107df42fb |  | note | Accept / Reject Criteria - As per specification
label | 923c533d-f1f1-5b34-9d4e-d045be14a824 |  | note | Frequency Of Inspection Or Test - In-process
label | 38c95b2d-d2d1-5211-b153-9faa667507bd |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP040
label | 88bf6578-1b81-5e91-b969-0d68e2e20b4b |  | note | Records Required - NO
label | 29bc1848-07f3-520f-9ad7-39be92726056 |  | note | DOWNER ENGINEER - W(10%)
label | 6a71378a-7a33-5c6b-9ee1-a396f4dc051a |  | note | SUPERVISOR - R
label | e81d4f9e-0870-5dea-8e03-49accf9a0c9e |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations - Grit - Application by Hand | itp |  |  |  | Yes | ITP - CONOC Operations (General) - Grit - Application by Hand | 11323da5-75ba-44ae-bd32-32512adcc074
checkpoint-status |  |  | checkpoint | 1 - Spreading Grit
label | 77a1292d-4136-52b3-8a91-aa8ae95c7270 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 22c45e76-87be-596b-ae5f-d2e219ba4ccb |  | note | Accept / Reject Criteria - As per Specification
label | eeb839ea-f656-5fc5-adfc-f5c5d966f9a6 |  | note | Frequency Of Inspection Or Test - In-process
label | d4eb522c-0c8b-5a45-9c48-c9e1a0176569 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP110
label | a2392318-a65b-5b28-a194-6f26cec2adfd |  | note | Records Required - NO
label | c81ef3f2-3fb4-53ad-82ab-38cf4632da45 |  | note | ENGINEER - R
label | b0a90745-1962-5ac0-be4b-1f4b92d45645 |  | note | SUPERVISOR - R
label | 515fe54d-dfad-50f4-a145-eac0d5d31328 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Preparation
label | aacf70a5-8489-5d62-9c89-6dcb15fa7bf8 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | d81179c1-b4ce-5df0-9841-a442a625d244 |  | note | Accept / Reject Criteria - As per Specification
label | 4f6afcf8-0e42-5e4f-b626-065a9cc1c297 |  | note | Frequency Of Inspection Or Test - In-process
label | 58b90b7c-4096-5f2d-8421-dd44db17aaaf |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP110
label | 944c5839-1767-5552-8283-4af32a3bab13 |  | note | Records Required - NO
label | 371991ce-b8ca-5ccd-932f-be2f8475e2b6 |  | note | ENGINEER - R
label | acc89473-95bb-5a4e-9e93-c8c9912f9834 |  | note | SUPERVISOR - R
label | a6a60d90-c662-52da-bb98-210f56dcdce0 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Sign Management
label | 1e3c4749-a245-5953-96bf-8828e19a3ae6 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | eee15cf5-b431-5d0c-992a-951f2d3837c7 |  | note | Accept / Reject Criteria - As per Specification
label | ead168da-1d7b-5507-a41e-63242bdbd569 |  | note | Frequency Of Inspection Or Test - In-process
label | 4fb3ba46-1e36-5fa3-a1f3-c3b406781671 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP110
label | d8011c7b-02da-5368-b578-d8c617627325 |  | note | Records Required - NO
label | eee6b8ce-7fc8-56aa-8fe5-b77537397618 |  | note | ENGINEER - W(10%)
label | 0146b1fa-0dd8-52fd-8060-3b98cda5777f |  | note | SUPERVISOR - R
label | 2a60937d-b0b5-5016-91ae-b5b1c085f6ca |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Operation
label | 7fc1c508-f839-513d-9232-68df0629a035 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 8a4218fa-1985-573b-9594-41723fbd81bc |  | note | Accept / Reject Criteria - As per Specification
label | 717de218-dc51-5779-82d5-b4bb2aa6fb89 |  | note | Frequency Of Inspection Or Test - In-process
label | cb882ab3-0267-5d2e-97e1-1a80e49e49b0 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP110
label | aa88b0a8-acb8-514a-942e-ae79a9a1c6fd |  | note | Records Required - NO
label | 869df8ce-d96c-5615-b029-453817696a24 |  | note | ENGINEER - W(10%)
label | 86dac234-edd4-546f-814f-236e5b022a71 |  | note | SUPERVISOR - R
label | 77852545-17d0-5449-839f-64cbde129917 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Recovery of Chip
label | 843798d4-4105-5199-bda5-736ea6e392c2 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 0b4467d3-d644-5c92-a000-8e704573d95e |  | note | Accept / Reject Criteria - As per Specification
label | 197b64b5-8d1e-5e5d-8cd5-759d17b999fd |  | note | Frequency Of Inspection Or Test - In-process
label | b12ce412-8991-5fa3-ad2a-eb427d69777f |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP110
label | d511488d-8baf-5891-8712-2cab44df049a |  | note | Records Required - NO
label | 86dc1efd-ba5a-53db-9207-73c601a9fd57 |  | note | ENGINEER - W(10%)
label | e09294f0-7744-504d-95aa-c7e4c1c617b8 |  | note | SUPERVISOR - R
label | f17c5676-1606-594d-bf00-7d44560f4939 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Disposal of Unlifted Material
label | 739acf6b-e1d8-5d39-96ac-baa8f5388236 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 8e05945d-37d8-5869-9114-f4a6fb979aa3 |  | note | Accept / Reject Criteria - As per Specification
label | 38ca959c-e449-578f-a79b-b6b460e39e15 |  | note | Frequency Of Inspection Or Test - In-process
label | c37fc37f-58f1-5a32-82f8-1091062346e5 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP110
label | 196e4efd-ec11-5c47-a165-914bc1821bc0 |  | note | Records Required - NO
label | 1e9c2d34-f0d8-56a6-8843-4e9c71cdc51c |  | note | ENGINEER - W(10%)
label | 02955a76-21d8-59bd-a014-f3f130c8b616 |  | note | SUPERVISOR - R
label | 17c8de58-ea23-5dd9-90cc-972941e03245 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Incident Reporting
label | 93a5cb6a-c195-5ce0-8749-735c8fde5bbf |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 8650addb-dfac-5eb1-980d-70730cec88ea |  | note | Accept / Reject Criteria - As per Specification
label | 9643b1e8-b8ec-5814-bf66-6ac13c8885cd |  | note | Frequency Of Inspection Or Test - In-process
label | 0c140c48-6410-502f-8ce4-1401e3e5ef60 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP110
label | 4db0481f-8450-5a93-b557-3325db8a3f9f |  | note | Records Required - NO
label | 8e939bb9-0a14-5e7e-a025-770a9d7ff11d |  | note | ENGINEER - W(10%)
label | 278a3706-ea87-5205-b3b0-9618aa983fb6 |  | note | SUPERVISOR - R
label | ee310da9-b7e9-5893-ac66-71d618afe5a6 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Test and Check
label | b7394353-695f-5484-a9fd-8e4f4b6a5e0d |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 27e232aa-cf72-58d0-9bc3-d723f9d53fcd |  | note | Accept / Reject Criteria - As per Specification
label | b0b787d6-f537-5d88-bfec-6f8251049252 |  | note | Frequency Of Inspection Or Test - In-process
label | 95a0f276-148a-5dfd-ac76-da1486fe8dc1 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP110
label | 601113df-9c11-568a-823c-a14fc78ea8c9 |  | note | Records Required - YES
label | 51f4da91-bda3-512c-ad6b-ce0370d0aafe |  | note | ENGINEER - W(10%)
label | 49ae629e-6cbd-51b9-94f9-1e9b9d8f1b07 |  | note | SUPERVISOR - R
label | 1e5bd3cd-ef9b-5235-b7f2-4e8fed71c687 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | DG-DM-FM052 Dayworks Order (Inc Site Diary) |  |  |  |  | Yes | Add DG-DM-FM052 Dayworks Order (Inc Site Diary) | 11ed5753-55e8-41ab-b57f-d95955331076
checkpoint-group |  |  | section | SECTION 1 - WORK DETAILS
checkpoint-status |  |  | checkpoint | Work Details
text | 8210cd56-7457-5cc3-8953-0bc38636a75b |  | textbox | Project Name:
text | 15f405a4-7dc0-52e2-b489-42973e6d2174 |  | textbox | Project No:
text | 92c64a2a-385d-5f74-be73-f8a0cd89c72d |  | textbox | Dayworks Order No:
text | 80c1e163-567f-5ee3-832a-c87064638ff0 |  | textbox | Contract No:
date | 7409723d-d7d4-5ccd-85d6-1ef73ae83c1f |  | date | Date of Work:
text | bf069ab0-70d8-5d10-ba28-be53b27215eb |  | textbox | Weather AM:
text | 674c82de-fc9b-5d3e-b91c-2df5d3247c5f |  | textbox | Weather PM:
text | c6f67cd2-ed9d-5acc-ba27-6ce248d3ba70 |  | textbox | Weather Impact:
text | aadb0ba1-2366-5109-a1ab-e57338c852aa |  | textbox | Work Description:
text | c21bc518-7999-5beb-b36b-90ab943fc824 |  | textbox | Subcontractor Activities:
text | 5bbda91b-40e7-53d9-a055-b90ac22e3514 |  | textbox | Vistors to Site
text | e3b9848a-bff3-57ca-8d0a-874b3b3221ba |  | textbox | Delays to Progress
checkpoint-group |  |  | section | SECTION 2 - DAYWORKS ORDER DETAILS
checkpoint-status |  |  | checkpoint | Dayworks Order Details
text | 7c15fd81-3c90-5298-a319-46a931b1d25c |  | textbox | Downer Labour, Plant, Equipment and Materials:
text | c4f0d217-58a8-5a8c-8df2-18e5e8d37768 |  | textbox | Hours/ Quantity:
checkpoint-status |  |  | checkpoint | Sub-Contractor, Plant, Equipment and Materials
text | bbbf6ea7-1eac-5963-b59a-a7a6e24c312e |  | textbox | Sub-Contractor, Plant, Equipment and Materials:
text | 9249605d-2be4-5e7e-9738-f573bf4e176e |  | textbox | Hours/ Quantity:
checkpoint-group |  |  | section | SECTION 3 - SITE DIAGRAM / PHOTOS
checkpoint-status |  |  | checkpoint | Site Diagram / Photos
checkpoint-group |  |  | section | SECTION 4 - OTHER NOTES
checkpoint-status |  |  | checkpoint | Other Notes
checkpoint-group |  |  | section | SECTION 5 - APPROVALS
checkpoint-status |  |  | checkpoint | Subcontractor
text | 3830546b-6c95-5f9e-b694-0fa10cc85232 |  | textbox | Authorised By:
date | 788226b2-bcc6-5a22-9164-5580bd3c24b9 |  | date | Date:
holdpoint |  |  | signoff | Signature
checkpoint-status |  |  | checkpoint | Downer
text | 0b9e9751-e5c6-5154-b8e7-e1aa7520711f |  | textbox | Authorised By:
date | 4271eab4-af75-5a96-81a1-38b6142f3f19 |  | date | Date:
holdpoint |  |  | signoff | Signature
checklist-sectioned |  |  | checklist | DG-DM-FM053 Daily Report |  |  |  |  | Yes | Add DG-DM-FM053 Daily Report | 12e6ea8b-b82a-4b53-8aa3-782c169bf1ef
checkpoint-group |  |  | section | SECTION 1 - SHIFT DETAILS
checkpoint-no-status |  |  | checkpoint | INSTRUCTIONS
label | 077b3e26-65c1-50ad-bd63-e6a6a3d152bd |  | note | ○ Use this form to record all relevant data from the daily diary to provide a clear, concise and searchable record of the day’s events.
checkpoint-status |  |  | checkpoint | Shift Details
date | 481702d3-3e0c-58e9-b123-90de07f6b972 |  | date | Date:
select | 82deb78f-a285-5c6c-a7e2-247be734fb1f |  | dropdown | Day: | Mon,Tues,Wed,Thurs,Fri,Sat,Sun
text | cb72f50e-5d5f-5b10-8034-3b40f324f69c |  | textbox | Customer Rep:
select | f0700843-e59e-5220-b59e-13a014ef545b |  | dropdown | Shift: | Day,Afternoon,Night
checkpoint-group |  |  | section | SECTION 2 - WEATHER (for comparison with BOM data)
checkpoint-status |  |  | checkpoint | Condition
select | 876c5bcb-7a6a-50b9-82a6-3b73a1aea002 |  | dropdown | Normal: | Impact: Yes,Impact: No
select | 144f4740-a94c-59b4-941b-c5961d41ea9a |  | dropdown | Extreme Temp: | Impact: Yes,Impact: No
select | bc6b6dfd-6afb-54a6-aab6-a1a675295cd0 |  | dropdown | Extreme Winds: | Impact: Yes,Impact: No
select | 049f001e-ee65-585c-a4dd-ce4ca229ca44 |  | dropdown | Rain: | Impact: Heavy,Impact: Moderate,Impact: Low
select | eb32cb7a-eda9-5991-a3e9-87712533b1ba |  | dropdown | Rate of Work: | Impact: No Affect,Impact: Slowed,Impact: Halted
checkpoint-group |  |  | section | SECTION 3 - SCOPE OF WORK PROGRESS
checkpoint-status |  |  | checkpoint | Scope of Work Progress
label | 6144cb48-5eec-506b-8ba2-3eae8b618597 |  | note | (Refer to scope of work, work packs & WBS & include rework). Ensure all daily time capture WBS codes are detailed below.
text | 718162a2-f003-5bd4-9bd7-22ea3d7d3663 |  | textbox | WBS/ Work Package No.
text | 2f61bf23-cc4f-5d1e-9700-6c8665c79546 |  | textbox | Quantity/ Location
text | f38786ed-2925-5bf3-b838-3097d8693aa0 |  | textbox | Description/ Notes
checkpoint-group |  |  | section | SECTION 4 - OUT OF SCOPE WORK (VARIATION WORK)
checkpoint-status |  |  | checkpoint | Out of Scope Work (Variation Work)
label | 6a3b029c-5a2f-5aa4-9cbd-a66ff5515123 |  | note | ○ All variations must be followed up with a formal Record of Conversation or Site Instruction for project record purposes.
text | f8431901-1b53-50b1-84be-55a1d5c0c25f |  | textbox | Area/ Work Package No.
text | e89109fc-54f7-5c14-933f-f875cbe38ba6 |  | textbox | Description
radio | 7a973bad-f84e-5059-8721-752e2e979ec6 |  | radio | Request Type | Verbal,Written
text | 16385e1c-f65d-5de0-a16f-e8b1a3cb45c3 |  | textbox | From
text | 0f18a9b9-cc71-5828-85cf-ea07b7e1d160 |  | textbox | Approved By
checkpoint-group |  |  | section | SECTION 5 - DELAYS
checkpoint-status |  |  | checkpoint | Delays
label | b7c4eb5a-6bc6-5e5f-8982-7e020460736a |  | note | ○ Reason Codes
label | 48f8f1ad-9834-5186-a209-9408df0550f0 |  | note | (1) Industrial Action
label | 21e5a576-befb-58a4-bf41-ac99d315715a |  | note | (2) No Access
label | ebbb2162-5a81-5382-935f-5625220f293a |  | note | (3) Plant/Equipment Shortage/ Breakdown
label | ebc13821-d121-5dca-9f3a-f4cb47822c44 |  | note | (4) Weather
label | a004bf87-fbf3-5683-93e6-bb9bab18c2ea |  | note | (5) Customer
label | 7c72fdf4-fdba-5fb4-ab55-1dd759e80851 |  | note | (6) Material Shortage
label | 6bd91af7-f4b4-5d5c-85c1-4ffd410a572b |  | note | (7) Labour Shortage
label | a1278e7f-ecfc-55c6-97c5-f1cce0259ae2 |  | note | (8) Rework
label | 9da12243-fec1-5b50-9a2e-a0d932dfae3c |  | note | (9) Other
text | 77278ee3-5740-5bfe-85eb-39dc398d2f34 |  | textbox | WBS/ Work Package No.
select | e5cc2c1b-6e9b-5c6c-937e-1317aa77e037 |  | dropdown | Code | (1) Industrial Action,(2) No Access,(3) Plant/Equipment Shortage/ Breakdown,(4) Weather,(5) Customer,(6) Material Shortage,(7) Labour Shortage,(8) Rework,(9) Other
text | 84e0cdbb-0a82-5de8-95e2-1fc3671c7446 |  | textbox | Start
text | e5cdbc03-0591-58db-95e9-79fde336a4dc |  | textbox | End
text | a4c8f2e1-30de-5317-8c78-055172bafc38 |  | textbox | Location
text | 071529b1-dfb1-538b-85dc-eb8d83a1dfc7 |  | textbox | Details
checkpoint-status |  |  | checkpoint | Delay Notification (Internal)
text | ef0d97ec-335c-5ae1-812c-b58f7c5dab9d |  | textbox | Who was notified?
radio | 99ea895f-ed18-50a8-b14d-2d49269ac255 |  | radio | Method: | Verbal,Written (Email/ Formal Notice)
text | 70ed8f8a-0122-5bb1-a0a2-70f0645b98f7 |  | textbox | Time:
date | cfcc6ce8-78e9-596b-bb67-cc390da978bc |  | date | Date:
text | 10bea916-571d-5d73-94f4-9fc3a961aec5 |  | textbox | Document Reference No:
checkpoint-group |  |  | section | SECTION 6 - SITE INSTRUCTIONS, REQUESTS OR DIRECTIVES
checkpoint-status |  |  | checkpoint | Site Instructions, Requests or Directives
label | 8a235cb8-b440-52b9-806f-00024a973f1e |  | note | ○ Include site instructions to subcontractors and instructions from the customer to Downer. All verbal instructions must be followed up with a formal Record of Conversation or Site Instruction for project record purposes.
text | 630b7fe1-4704-551f-8218-097359122d7d |  | textbox | Area/ WBS/ Work Package No.
text | 055a973c-c5af-5daf-8aac-174f2abc2784 |  | textbox | Instruction No. (or N/A)
text | bbc9a133-f999-5da9-be34-814517f10f46 |  | textbox | From
text | 73f13869-f9bc-5796-ac03-505c4daa46d3 |  | textbox | Recipient
text | c63d49cd-5155-5f80-9853-3b5601190415 |  | textbox | Description
checkpoint-group |  |  | section | SECTION 7 - WORK CREW ABSENTEES
checkpoint-status |  |  | checkpoint | Work Crew Absentees
text | e27bd4b0-6f19-587f-b9d8-1cf317691f48 |  | textbox | Names:
checkpoint-group |  |  | section | SECTION 8 - SUBCONTRACTORS
checkpoint-status |  |  | checkpoint | Subcontractors
label | acfdf3ab-2ef4-51ed-98cc-a98540c84427 |  | note | ○ Note all subcontractors working on site for the day
text | 49c479cc-c522-5b88-bf1e-5f8f7c003583 |  | textbox | Subcontractor(s) Used
text | 8792f352-da7b-57c9-8273-e177515d2c10 |  | textbox | Details/ Work/ Location
text | 8c93370c-8481-5291-93c8-3b6ec11c401f |  | textbox | No. People
text | 76d6726e-e335-53e7-9922-b689b64694c8 |  | textbox | Total Hours
checkpoint-group |  |  | section | SECTION 9 - ZERO HARM INCIDENTS OR ISSUES
checkpoint-status |  |  | checkpoint | Zero Ham Incidents or Issues
label | 6c596e4d-0b7a-5682-807b-e95899d10a2f |  | note | ○ Briefly detail any incidents for the day.
text | a6952255-cea8-5a7a-b8c5-80acddfb069b |  | textbox | Description
text | 0cd62bcb-b70b-5cf0-bf50-a13c7e674c5e |  | textbox | Who was notified?
text | 55bf9d3e-6f79-52ff-9710-e23e49c1e2f6 |  | textbox | Time Notified?
checkpoint-group |  |  | section | SECTION 10 - COMPLETION RECORD
checkpoint-status |  |  | checkpoint | Completed By:
text | 92c624f2-224d-593d-b49e-dded4ec2a484 |  | textbox | (Name)
holdpoint |  |  | signoff | Signature
checkpoint-status |  |  | checkpoint | Checked By:
text | 41355901-5e2d-543f-96eb-dd86972cba76 |  | textbox | (Name)
holdpoint |  |  | signoff | Signature
checklist-sectioned |  |  | checklist | ITP - Abbotsford O_Bridge - Thin Asphalt Paving |  |  |  |  | Yes | ITP - Abbotsford O_Bridge - Thin Asphalt Paving | 140ab71c-ed8d-476e-95f2-1d07299d6824
checkpoint-group |  |  | section | 1 - Preliminary and General
checkpoint-status |  |  | checkpoint | 1.1 - Construction Programme Completion
label | 1b3480b3-3e66-5eec-9055-c0c88759ba71 |  | note | VERIFICATION ACTIVITY - Confirmation
label | c866fd42-6110-521b-a3d0-b6573769fc45 |  | note | METHODS OR REFERENCE - Best Practice Contract Specific MMP
label | c9e1596e-59e2-53bd-a3bf-6efa11579e9f |  | note | FREQ. - Before work commences
label | 8a1caa85-6ccc-5a35-8fb2-3466fbfd61ba |  | note | ACCEPTANCE CRITERIA - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date.
label | e9c632ae-922c-5607-a643-80f28fd1ebd2 |  | note | INSPECTORATE W/H - Type: - W
label | 4ecec88d-f01b-52f3-a6ab-b50c03914e99 |  | note | Responsible Person - Renewals Manager
checkpoint-status |  |  | checkpoint | 1.2 - Approved RQP
label | bb1ad1ee-134c-5752-82ab-ccf677264c0b |  | note | VERIFICATION ACTIVITY - Confirmation
label | 5187be98-8236-5d8c-91ba-6edb3163e1ee |  | note | METHODS OR REFERENCE - Contract Specification
label | 522f6cbe-39a6-5f11-b0cc-775a5b9d3e05 |  | note | FREQ. - Before work commences
label | eff0030d-a30b-5212-b846-43e5c3b9ab34 |  | note | ACCEPTANCE CRITERIA - Principal Acceptance according to guidelines in appendix 6.3
label | 93916117-5c6c-5692-be38-2e0de846dd9d |  | note | INSPECTORATE W/H - Type: - H
label | 8780a739-cebe-56d8-b55b-db08cc004a4c |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. NZTA to approve
label | 6942b688-7f27-58cb-9031-287ecfaf0dca |  | note | Responsible Person - Renewals Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Traffic Management - TMP
label | b59be5e6-8958-5eca-956d-0a537cdbe094 |  | note | VERIFICATION ACTIVITY - Visual check
label | da0e2818-4452-5ea3-9f6d-18984cae52f2 |  | note | METHODS OR REFERENCE - CoPTTM
label | 6a9ad896-bc1a-5357-92a8-85a0b402c235 |  | note | FREQ. - Before traffic management set up
label | 3a501386-041f-5517-b13a-61462503f8ea |  | note | ACCEPTANCE CRITERIA - TMP checked and approved Plans approved Current EED (if applicable)
label | 412490d5-1ac9-5759-a2fe-029ebbd332b1 |  | note | INSPECTORATE W/H - Type: - H
label | e87e5361-fa85-5132-99e8-e58e55c743d9 |  | note | INSPECTORATE W/H - Description: - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | 00d43908-caba-5ce3-8f2d-c051ee03a5e7 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Mix Design Verification for all mixes Check Laydown Trials are complete and compliant
label | cfcb8dac-7ad5-5b6b-86c8-c400aadb35cf |  | note | VERIFICATION ACTIVITY - Confirmation
label | fd999b8c-a4a5-5cac-9b52-e6ee8ee731bf |  | note | METHODS OR REFERENCE - NZTA M/10, P/11, P23
label | 5f7a3c5e-6c57-59fb-ae33-efadd52c7825 |  | note | FREQ. - Before planning commences
label | 1aa254b1-3aba-5ac5-a7c8-e157c5f0cd65 |  | note | ACCEPTANCE CRITERIA - Mix Design compliant, current and relevant. Batching plant production capability is confirmed
label | e1a63660-dc77-5834-a377-6b559a24e8cb |  | note | INSPECTORATE W/H - Type: - H
label | 5c2d95b9-3007-54e2-bb18-40e96ae4909d |  | note | INSPECTORATE W/H - Description: - Hold point - No planning of on-site works shall commenced until the mix design is verified.
label | f6dd4c51-8065-55ce-b969-8f1fc637e54c |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Notification of intention to start work
label | c52df27a-99d0-53cc-a581-8d74726b80e8 |  | note | VERIFICATION ACTIVITY - Notification
label | 8e77dad5-d38e-5c92-b426-f1edb0aa500e |  | note | FREQ. - Before work commences
label | 7844e7f0-4ec1-566a-bc00-cca5b9b6a3cc |  | note | ACCEPTANCE CRITERIA - Letter drop to local residents. Greater consultation where required
label | 4618fc59-9b65-56e5-b40f-b8f8dbc4a19c |  | note | INSPECTORATE W/H - Type: - H
label | 48403537-68fd-567b-a003-6994be8f4be3 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | 64aee648-7887-56dd-8475-330a6b5d6bcd |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Works Extents
label | 12d45ab9-ffe7-54f7-900b-484d4e0f3abd |  | note | VERIFICATION ACTIVITY - Confirmation
label | 4bc11caf-7660-52d2-803a-00e39d5ce984 |  | note | METHODS OR REFERENCE - Site Visit
label | e68965f6-f6ec-5fa8-b182-bb9a117a26d5 |  | note | FREQ. - Before work commences
label | 781fa31a-d4e4-552b-af8b-c8678183c3e8 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and/or Client to agree extents of project
label | 3f2fa235-c7ad-5dbc-9da2-d4309958df01 |  | note | INSPECTORATE W/H - Type: - H
label | 3de9d1ad-2707-5606-96c2-39770c23b7ce |  | note | INSPECTORATE W/H - Description: - Hold point - Walk over site with Renewals Engineer and/or Renewals Manager and/or NZTA
label | 7d04ed1f-8d38-5200-885d-571ce77b458f |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - Pavement Marking Records
label | f7fb81ab-ea52-5f2a-be53-d443e0479e9b |  | note | VERIFICATION ACTIVITY - Measurment Data
label | 8ec2ad39-0c1b-593c-8712-7edd56c6dca8 |  | note | METHODS OR REFERENCE - Site Measure or Video Viewer
label | 97c3e371-623f-5301-a7a6-80cd866a7852 |  | note | FREQ. - Before work commences
label | 66ebfe4d-66ef-5294-916c-defb6c8004b7 |  | note | ACCEPTANCE CRITERIA - Measure existing markings to aid reinstatement
label | d5e12da0-e1fb-5abd-8408-6827be550663 |  | note | INSPECTORATE W/H - Type: - H
label | 4f6655fa-a6c9-50b1-b926-944ffeaebe8e |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | 27c3f858-d567-5ed9-9199-5bf52a61b396 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Milling and Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | 3f3e36e4-c874-59fe-ac8c-03ac77b13bd2 |  | note | VERIFICATION ACTIVITY - Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth)
label | 53b97573-10ba-54e4-b6cc-289afd576a3b |  | note | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | 85ec5ec4-a387-5d3c-a793-ce04f552d158 |  | note | FREQ. - Before work commences
label | 0b803904-efe1-5f07-96fd-db893057269e |  | note | ACCEPTANCE CRITERIA - Zero service strikes
label | 2cf3f275-3c27-5af9-a562-a28923b6e0a4 |  | note | INSPECTORATE W/H - Type: - H
label | c75cc1e5-2a66-5ce3-b519-a6589b1f5edd |  | note | INSPECTORATE W/H - Description: - Hold point - No excavation/milling is to be commenced until services are located and accounted for
label | f96411d9-d582-5661-a745-d9fe3ae337bd |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Stormwater Management
label | 12185cea-024f-51f6-8a7e-2f50252d094d |  | note | VERIFICATION ACTIVITY - Visual check
label | f69ab32e-f8bb-5574-b8ef-96332c1d7ef8 |  | note | METHODS OR REFERENCE - On Site
label | 97efb333-0954-5789-8b21-4840c3ff6cbe |  | note | FREQ. - Before work commences
label | 4b616037-eeaa-5e08-b42b-8cd9fa31f9d6 |  | note | ACCEPTANCE CRITERIA - Mudtanks bunded or filtered to prevent mix from dropping in or runoff entering
label | 76602a25-11d1-5291-badf-b68739ff232f |  | note | INSPECTORATE W/H - Type: - H
label | bf825dac-334b-5d78-96ae-ab9ec2432f94 |  | note | INSPECTORATE W/H - Description: - Hold point - No work to be commenced until protections in place
label | 5466f847-3d84-5814-ad9b-6fa2bd9e0251 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Traffic Management - Setup
label | f63e0099-7e52-5378-84e2-571d71815206 |  | note | VERIFICATION ACTIVITY - Visual check
label | 12f70250-df76-592f-97d3-a7cf435a7513 |  | note | METHODS OR REFERENCE - Traffic Management Plan
label | 46bb9d8c-c02a-58fc-9bba-75d485c5bd5e |  | note | FREQ. - Before work commences each day
label | 96e72199-5d34-5e2f-bf6b-54143bfa45da |  | note | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | 65ec40bc-5a8c-54ef-8f73-f8f4c7ae1162 |  | note | INSPECTORATE W/H - Type: - H
label | d7124cee-33d6-53ba-90d8-9f1d676c339a |  | note | INSPECTORATE W/H - Description: - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | e79befbc-1db9-5ab4-a8fa-86745cac167d |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Milling Depths
label | 30f80559-d673-58ad-93f1-98c0f25c8841 |  | note | VERIFICATION ACTIVITY - Measurement
label | d6ec9d70-71fb-5bcb-a104-27ab74c621c3 |  | note | METHODS OR REFERENCE - On Site
label | e547efb9-662c-5fc7-a2d0-8ef0d125a3b9 |  | note | FREQ. - Measure each side of milling machine cut
label | 0035be4b-b2b7-5fe2-95c7-38c533f86127 |  | note | ACCEPTANCE CRITERIA - Every 10m. Depth matches target
label | 7eee2b5d-1d8e-50ba-99ad-c60733f597db |  | note | INSPECTORATE W/H - Type: - H
label | 562489ff-d99b-5d12-a292-730360bded04 |  | note | Responsible Person - Site Foreperson / QA
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Service Covers Preparation
label | 2edf0865-17a4-5b13-930a-4d5f4ff77af8 |  | note | VERIFICATION ACTIVITY - Visual
label | 0861d18d-95f5-55ca-b488-710edec44153 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 522b4331-fbad-5783-8fc2-b86d31d8e0eb |  | note | FREQ. - All Covers
label | 20da8139-03bb-588c-950d-55a913a6b3c1 |  | note | ACCEPTANCE CRITERIA - Hand excavation around ironwork and adjustment to desired level (if required)
label | 99a85233-20cd-5ac5-96f6-db1a0cf7361e |  | note | INSPECTORATE W/H - Type: - H
label | f77cc219-1106-5cb6-849f-59ae214c731e |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Additional Surfacing Preparation
label | 82f5e9d7-a9d2-511d-be2a-b167c6d4c366 |  | note | Side Roads; Accesses; Driveways; Dish Channels; High Shoulders
label | 242c8474-34ea-5b45-96fe-6652bb00acf2 |  | note | VERIFICATION ACTIVITY - Visual Check
label | 570bb367-2bd7-59dc-a095-fefd305acbab |  | note | METHODS OR REFERENCE - Per Design
label | 384ea74f-35d6-50f9-958f-77d8e9736cba |  | note | FREQ. - Before Membraning and Paving
label | 2bf0a5f4-662d-5d9a-9652-3e63196b89fc |  | note | ACCEPTANCE CRITERIA - Have all areas of additional surfacing on the design been prepared, membraned and marked for paving?
label | 434a7c2c-a59e-55da-a9e3-b9643ad5a686 |  | note | INSPECTORATE W/H - Type: - H
label | 1850442e-0ba1-5758-9169-f2e6ab5ef31e |  | note | INSPECTORATE W/H - Description: - Hold Point – All areas planned for AC are prepared ready for surfacing layer
label | bb60dc2f-8030-567d-b3db-b1cc037f52ec |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Over-Milling
label | 9dbed6ec-c52f-5cc6-ac9a-402ee7d81b99 |  | note | VERIFICATION ACTIVITY - Measurement
label | da12eaba-6c55-5140-b83f-b5f928e6e342 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 0a3a83fa-dc53-5d51-822a-79b90dea31a9 |  | note | FREQ. - Prior to pre-level
label | 23d10a7e-d3b1-5845-ad50-938f70c9d502 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree need and extent of over-milling and infill.
label | 6fcdd4e5-1645-504a-8d22-0efd49b92039 |  | note | INSPECTORATE W/H - Type: - H
label | 7db01d10-d3d8-5d8e-b8b5-5e4c5f6b2dcd |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Pre-Level
label | 88f04a71-9a35-5fa6-86dc-09d144d3369f |  | note | VERIFICATION ACTIVITY - Measurement
label | 48fec03e-b888-52fa-a370-f4310152c16f |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 1bab8e74-b0de-5e13-814f-a3819dc505da |  | note | FREQ. - Prior to surfacing
label | afddbbdf-20c6-560a-9713-c24945727f66 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree pre-level extents
label | 9deca9b8-b85f-5f29-b141-fa6214a91cc3 |  | note | INSPECTORATE W/H - Type: - H
label | a0e659d2-e6fe-5cf3-b6ff-78df564afcc7 |  | note | INSPECTORATE W/H - Description: - Hold point - Inspection and agreement by NZTA
label | 4d79a23e-e08c-56d3-ac99-3dc21ca01c70 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.9 - Membrane Sealing
label | 67571fb8-e618-5f81-ad2e-9bcc8e2a89ae |  | note | VERIFICATION ACTIVITY - Visual
label | 544c6fbd-de14-5192-b44d-f0bbfbc021fd |  | note | METHODS OR REFERENCE - On Site
label | 9c98e83f-b9fb-5672-9c6a-a9a56d51d6cd |  | note | FREQ. - Prior to surfacing
label | 803bb811-64fe-5e80-bedc-dbb37bc88be5 |  | note | ACCEPTANCE CRITERIA - Membrane seal meets design and extent. Sealing Docket record kept
label | 4d1550e4-883f-52ea-bab8-5e2a45afe81b |  | note | INSPECTORATE W/H - Type: - H
label | d7723e64-87b5-57ab-a043-e72eb7aa0747 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Paving Structural
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | 10724905-13e8-5de6-af81-37e031675904 |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | ce0095b5-ae63-59c3-b1ff-2adba4b5aa70 |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | eb6a09d7-4655-5d76-a0a7-490c3267c65a |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | b482d1f0-3277-5c95-a48e-8051cc72e879 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 80289207-3ae3-5729-969a-d042f2ab6b95 |  | note | INSPECTORATE W/H - Type: - W
label | c70e110a-6ee1-52c6-b18f-c31fe2e2bc70 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | f5fa5bdd-d687-5a0e-b044-17d4afa5ee0b |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | 8b45c99d-e30c-571e-8b8b-18e66a0700b7 |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | e479d62e-6758-5b69-b178-6f503cd14356 |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | a14c0815-b947-5df0-a14c-bbb9892e9902 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 750ddb1d-86cf-54c2-bbda-bcaafb8ed194 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 56d89617-84b7-5a48-8f34-26b685a9f49d |  | note | INSPECTORATE W/H - Type: - W
label | 3f5ec364-c726-514c-b1bf-46b1d11616cb |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | c51fffae-2286-5c15-a0a2-d0be7edf00b6 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | ed381384-fd73-56cf-a81d-1d4fc8c9cba4 |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | b2803039-9120-5bc6-a4ef-6529535b735d |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | 122cf8d2-2bd7-50e4-a07d-37b7a0c42578 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 69d4ef2c-e1cf-5a52-b165-26cb150679ac |  | note | INSPECTORATE W/H - Type: - W
label | 6929b612-d232-526f-9df9-757586d57600 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | bece06e9-cab8-5fe0-8a92-c6b80316f9bf |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | 65294798-0ce0-5a27-a99d-9d403280bcf0 |  | note | VERIFICATION ACTIVITY - Visual
label | 3d93f357-b924-5f57-b193-48cb0c22b6e9 |  | note | METHODS OR REFERENCE - NZTA M/10
label | bed9fded-9067-56c3-ac5b-a4ddf28ac516 |  | note | FREQ. - Prior to Shift
label | a9ddde18-6544-530c-b6a3-65671d1219dc |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | 2438f126-3b41-56cb-9e12-91ea6caedc2d |  | note | INSPECTORATE W/H - Type: - W
label | b0062ae7-9248-5e4b-83bd-5246bf36922e |  | note | INSPECTORATE W/H - Description: - Paving Plan and Crew Briefing Plan completed prior
label | 3adeedea-94a3-5f72-996f-0c3332b6bc64 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | ac77301b-1e32-58e9-82d7-e8c6967d9d1f |  | note | VERIFICATION ACTIVITY - Visual
label | f0b43a12-31c6-5cf1-8466-ee2fe02177eb |  | note | METHODS OR REFERENCE - NZTA M/10
label | dede5dea-2ad2-540c-8c6a-0763ba81083c |  | note | FREQ. - Prior to Shift
label | 3b370886-5746-51a3-9ee4-24e67a7bec55 |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | 6efa345b-d2e3-5d32-9503-3c3c00c40e0d |  | note | INSPECTORATE W/H - Type: - W
label | c36cefbc-f368-5252-9001-25d1708eeb13 |  | note | Responsible Person - Paving Supervisor / QA Engineer
checkpoint-status |  |  | checkpoint | 3.4 - Mix Inconsistency and Deficiency
label | 6d714913-3ee0-5d86-8704-eedc389ef403 |  | note | VERIFICATION ACTIVITY - Visual
label | 50839e85-4791-5d1b-a11e-06a4a6b47a14 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 076868cc-895a-5c9b-aa28-ae43a2940dc0 |  | note | FREQ. - Continuous
label | 35a5daf8-d841-5fa1-bc14-bd34b05d2d38 |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | d4f0342a-430e-5758-8f3b-74d7852498f8 |  | note | INSPECTORATE W/H - Type: - H
label | 0783b83f-b8eb-5c89-922f-23506631e265 |  | note | Responsible Person - Site Foreperson / QA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Load Locate
label | ddbfd122-40ee-558f-9952-3527b28c827d |  | note | VERIFICATION ACTIVITY - Measurement
label | 587c944c-8e85-5509-b8ec-88fb14bd6811 |  | note | FREQ. - Every Load
label | 55051535-d529-59a1-8740-4dd7df7239ae |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
label | eb08d09c-a4df-5a3a-be48-b9e3de2a4786 |  | note | INSPECTORATE W/H - Type: - W
label | e299556c-7c33-56dd-8b6a-7e329277329c |  | note | INSPECTORATE W/H - Description: - Per standard practice
label | 5597b393-bafb-53d8-a544-244df896aa9a |  | note | Responsible Person - Quality Assurance Engineer
checkpoint-status |  |  | checkpoint | 3.6 - Laying Temperature
label | 9ee1916e-b0e2-503b-ad39-543e51053560 |  | note | VERIFICATION ACTIVITY - Confirmation
label | d38c7c66-bba6-5224-90f2-34181ac7576c |  | note | METHODS OR REFERENCE - NZTA M/10
label | 186185de-86c6-50af-ab04-052c023c3597 |  | note | FREQ. - Every Load
label | 9f813cf6-1e09-5b47-bf76-c8063b1374e5 |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | 12057c41-4974-5e18-b395-661f6b014f0f |  | note | INSPECTORATE W/H - Type: - H
label | fd79104a-f992-50f5-9b1c-ea49d639acf5 |  | note | INSPECTORATE W/H - Description: - Hold point - Reject mix for non-compliant temperatures.
label | e815deb7-7165-5b1d-ab6e-ab291fd47aff |  | note | Responsible Person - Quality Assurance Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Compaction
label | 898dbde8-22e3-5cc5-8d6e-a92bf274a265 |  | note | VERIFICATION ACTIVITY - NDM Testing
label | 5a58b69c-e1a2-5479-ad1f-0dd2b6e076f8 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 2067332d-3f52-5550-aaa9-bc57043fe568 |  | note | FREQ. - Minimum: 1 Test per 300m² within Mat. 1 Test per 100m of joint.
label | 1fe61c78-b389-59e4-85c1-217ed1e2c272 |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | f35b51c3-cc14-508d-ba2f-a490cc47a083 |  | note | INSPECTORATE W/H - Type: - H
label | 87cb23f6-ca0a-59f2-bfff-59d6950ca8aa |  | note | INSPECTORATE W/H - Description: - Hold Point - No Wearing course paved until any non-compliance is sorted
label | b40d62bb-ed2d-5aeb-bc5d-61cb66a1e22f |  | note | Responsible Person - Quality Assurance Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Roughness
label | 105cf652-8bce-5dae-8238-bd8e1b44ea3a |  | note | VERIFICATION ACTIVITY - NASSRA Testing
label | 02e1a883-b61d-5781-8ca1-ebfade7c3d06 |  | note | METHODS OR REFERENCE - Contract Specification
label | 0ee98e83-3f01-5aec-b18d-b15e2eb8f064 |  | note | FREQ. - post construction
label | d5073729-f084-5c19-8df6-a77853c99d4e |  | note | ACCEPTANCE CRITERIA - NASSRA rolling meter average under 60, max of 70
label | 1bfd626e-d4df-56d0-b6f7-6a509c78fcf2 |  | note | INSPECTORATE W/H - Type: - H
label | 6481995a-a8ec-5a31-9f12-8ca9bc86c37f |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Paving Wearing Course
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | dbbaccec-524a-55fb-a69c-4689631728f8 |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | 5ad50853-0585-53c6-86d1-906699cb6872 |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | 1a8c2aa2-fa7c-54c4-bd39-025f740cace0 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 8f59621c-e1e7-5450-8710-cb2ee8cafadd |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | f6eee6a9-d3f1-5452-8ddc-bb829daee8a2 |  | note | INSPECTORATE W/H - Type: - W
label | b861d3e8-ab4e-53dc-9bcd-61913b3f0f93 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 74617878-0951-5e7f-99d5-ca5192865ad4 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | 152b8552-1d28-5c25-a49b-5c8ebce2c619 |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | 4256d472-b2a5-5564-b969-3c06b87d0513 |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | 95483718-a5c9-5eab-8461-a033f567af8d |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 8d1a5f4c-6972-512f-abc7-35262f5d21c2 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | a620a552-5621-5613-9090-18c14c54a7f0 |  | note | INSPECTORATE W/H - Type: - W
label | e91a8cc6-503e-5d4f-b6a0-123483478c7a |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 27869662-6f68-561d-aa63-b5178b0b3b49 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | 8d17cdcb-59a0-51be-aeae-0e1741568816 |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | 434db7f9-f4b5-54d7-9a23-356f41ec3ec4 |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | 690836f3-13ec-545c-9aaf-541547b074e0 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 792d56ad-a8f6-5419-89c4-b8046b0462af |  | note | ACCEPTANCE CRITERIA - Per Mix design
label | f7cb19ab-63e9-5ae1-9dca-27a975d41eff |  | note | INSPECTORATE W/H - Type: - W
label | da7f515b-d25a-5375-9eca-d46e4dbdd325 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | b3254c31-53cf-5c9a-b1cf-77f2f7ffc50b |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | 5642da01-814e-5379-a851-8ad21797101b |  | note | VERIFICATION ACTIVITY - Visual
label | e75e1ad8-f775-527a-af63-2b7d206c5a96 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 091a6d13-7280-573d-97bf-2fe9659cc3aa |  | note | FREQ. - Prior to Shift
label | decbadf7-2961-539b-84ec-278db742fa16 |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | 8e5d0c67-764c-54a2-8d52-01368f1fb41c |  | note | INSPECTORATE W/H - Type: - W
label | 125b6141-179e-51f4-a0f0-2134b09d6c74 |  | note | INSPECTORATE W/H - Description: - Paving Plan and Crew Briefing Plan completed prior
label | fd7c7972-edf5-5fe8-8549-082557b4be2d |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | 43e6d3c7-ffd2-556e-8d2d-d0f009674c0e |  | note | VERIFICATION ACTIVITY - Visual
label | 1aeef65e-7e24-5d5c-a0f5-a8e832f6b3dd |  | note | METHODS OR REFERENCE - NZTA M/10
label | d0d7ad97-eea2-511e-9c85-4ab96c101d71 |  | note | FREQ. - Prior to Shift
label | 3e0ec26b-2deb-562d-abff-ccee4458511b |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | 6e608def-3f0b-5e04-9cce-69ec36788cbf |  | note | INSPECTORATE W/H - Type: - W
label | 3f057510-51ac-5017-b7d6-980ec43e56cf |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.4 - Grade 3 Membrane Sealing
label | fd25aadc-bec7-5919-b706-fc2a5c222b7e |  | note | VERIFICATION ACTIVITY - Visual
label | 00e4f6a2-9b09-51b5-a8b2-a0c812496f01 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 864b3a80-5418-5c0c-a1c9-7c4ef838d01a |  | note | FREQ. - Prior to Paving
label | 8943973f-8019-5455-aad5-c23a4b182055 |  | note | ACCEPTANCE CRITERIA - Applied 2.0l/m² residual
label | 3ef49ea3-2aea-500d-9701-2ef2ec0a4c2f |  | note | INSPECTORATE W/H - Type: - H
label | fcef96d8-e8fe-598c-9004-41a2ed5da21b |  | note | INSPECTORATE W/H - Description: - Hold Point - No paving until Membrane Done.
label | b50c844d-02d0-5366-937b-d8a7246b11c6 |  | note | Responsible Person - Paving Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Mix Inconsistency and Deficiency
label | 21dae416-bb91-5787-9210-b97297c7a0e7 |  | note | VERIFICATION ACTIVITY - Visual
label | 243a0d68-4c2e-5048-aaf0-f7fcb1437bf3 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 83b56eea-6891-548d-88e3-3935c908e2eb |  | note | FREQ. - Continuous
label | 8b61285f-8574-5212-96ec-f1e43529205b |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | 7c6babe1-93c1-53af-b317-6a7dec73ba8f |  | note | INSPECTORATE W/H - Type: - H
label | ee8211dc-8a8a-5298-a511-3f2a98a895a6 |  | note | Responsible Person - Site Foreperson / QA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Load Locate
label | 7015a863-d73e-52e9-8c01-5e936b11ed77 |  | note | VERIFICATION ACTIVITY - Measurement
label | d4837397-6dd2-5b70-9973-670c89fba0a6 |  | note | FREQ. - Every Load
label | 4dbaada3-1ec9-5032-bee5-b60cee80011e |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
label | 8b523256-192b-56f9-8cba-bbb20dfdbd51 |  | note | INSPECTORATE W/H - Type: - W
label | 72d71d99-5850-5d98-a333-47bac1c47968 |  | note | INSPECTORATE W/H - Description: - Per standard practice
label | b2b267bf-32c9-562c-90b6-bc616f739d28 |  | note | Responsible Person - Quality Assurance Technician.
checkpoint-status |  |  | checkpoint | 3.7 - Laying Temperature
label | 2cd8a914-f2bb-5165-bbfc-bf0a85ea3b03 |  | note | VERIFICATION ACTIVITY - Confirmation
label | a75b32be-eee4-5383-a37e-ec20bd4e18ac |  | note | METHODS OR REFERENCE - NZTA M/10
label | 3c9586c8-f1d7-51d1-97b2-7dced4eda250 |  | note | FREQ. - Every Load
label | e8687c74-a850-56b5-b61a-d398cd21a7c1 |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | 9ce04cbd-beea-5fcf-a06d-2ce4a8e78c98 |  | note | INSPECTORATE W/H - Type: - H
label | d99da891-3c9b-5065-948c-a6e7f11bdaa6 |  | note | INSPECTORATE W/H - Description: - Hold point - Reject mix for non-compliant temperatures.
label | c9a8075a-8205-5daf-b489-457f6fbdc2b6 |  | note | Responsible Person - Quality Assurance Technician
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Compaction
label | 92974f4c-2c14-5b99-9a28-012c7b3c06f9 |  | note | VERIFICATION ACTIVITY - PQI Non-Nuclear Gauge/Cores. Or Non Distrctive Method Testing.
label | 0d251c2d-b6c8-54fa-bff8-6b84189d1df7 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 534372ea-70a9-5163-bd57-0865714fff52 |  | note | FREQ. - Minimum: 1 Test per 300m² within Mat. 1 Test per 100m of joint. Minimum 8 cores on Mat and 3 on Joints as Per M10:2020.
label | 765bf3fe-5584-5209-9c83-758ddd72096c |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | 454e78ac-3838-52bc-832e-2c2417d8c6fd |  | note | INSPECTORATE W/H - Type: - W
label | a07d9b61-1847-5ffb-bb1c-4d1186b5e21f |  | note | Responsible Person - Quality Assurance Technician
checkpoint-group |  |  | section | 4 - Site Reinstatement / Clearance
checkpoint-status |  |  | checkpoint | 4.1 - Post-seal Area Check
label | b70da393-fd43-5a79-ae7d-644a051dcc65 |  | note | VERIFICATION ACTIVITY - Measurement
label | 905ab442-3a71-5115-a01c-943f14f4d584 |  | note | METHODS OR REFERENCE - On Site tape-measure
label | 743c1cf6-687a-52ac-95ac-72e8af565345 |  | note | FREQ. - After Surfacing
label | 1cce9830-2860-5ca5-a489-36511c68f9f2 |  | note | ACCEPTANCE CRITERIA - Check sealed area meets design
label | 9321cb40-4bd4-53f0-b1fb-04023bc4a408 |  | note | INSPECTORATE W/H - Type: - W
label | 2fca9232-0a5a-5743-b220-0452ba4b608a |  | note | INSPECTORATE W/H - Description: - Notify Renewals Engineer or Renewals Manager
label | 32bcbd27-08dc-5e8d-b8e5-fc7bdf41e3fe |  | note | Responsible Person - QA Engineer
checkpoint-status |  |  | checkpoint | 5.3 - Service Covers
label | d5b8293b-3535-5bcd-bdce-a94c8cad4e0f |  | note | VERIFICATION ACTIVITY - Measurement/Visual
label | 24453053-8244-5a23-a945-b3833181133c |  | note | METHODS OR REFERENCE - On Site
label | d701bc9f-4ffa-5a26-8a9f-b97cec90402d |  | note | FREQ. - After Surfacing
label | f8f15d3a-ecc0-5685-bf9a-c655156999cc |  | note | ACCEPTANCE CRITERIA - All service covers are checked and adjusted (if necessary) to finished level
label | cfd36178-1cd2-562a-9f34-a0f7c33146aa |  | note | INSPECTORATE W/H - Type: - W
label | cec10649-deaf-5b57-a3a1-70e8eda8998c |  | note | Responsible Person - Paving Supervisor / Foreman
checkpoint-status |  |  | checkpoint | 5.4 - Joint Sealing
label | d72471be-3159-567e-bc95-7bb8b1ba677a |  | note | VERIFICATION ACTIVITY - Visual
label | 1970995a-bdbf-587c-a6ae-ffb8a3b64fb4 |  | note | METHODS OR REFERENCE - On Site
label | ab3a9971-4b0f-5fd4-afe2-eb00f6202fc5 |  | note | FREQ. - After Surfacing
label | 6aa910dd-364a-5fc6-a5b9-2761e74679a9 |  | note | ACCEPTANCE CRITERIA - Check cold joints are bandage sealed
label | b8853822-a0f2-5b34-9301-d6af6bfa7feb |  | note | INSPECTORATE W/H - Type: - W
label | e482ce0b-26fc-5319-b2dd-9a1e9519629a |  | note | Responsible Person - Paving Supervisor / Foreman
checkpoint-status |  |  | checkpoint | 4.2 - Road Marking
label | 32aa85c9-b76a-59c5-afed-3f48622432e9 |  | note | VERIFICATION ACTIVITY - MOTSAM
label | 5462a6b9-6bfa-55bb-9924-316e3c2ff25c |  | note | METHODS OR REFERENCE - Visual inspection
label | 815f9dfb-50b9-5ea8-9cfc-d718f2d1637e |  | note | FREQ. - All markings
label | 50c29b76-7689-5033-8fd6-c310b6958ca1 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, or per design
label | 7e24ebc7-b4cd-5d87-afea-05066c2150cb |  | note | INSPECTORATE W/H - Type: - H
label | e102f787-b76c-54e0-a8ee-f4a29d19780e |  | note | INSPECTORATE W/H - Description: - Hold point – Site TTM cannot be removed until markings reinstated
label | 164193db-771e-5247-af52-7dd5f03727d7 |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 - Other Traffic Services - Marker pegs/ Signs/Markings/RRPMs Replaced
label | cd962b98-0f6d-5ac6-8933-60ca09c3e56b |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | ca53a09e-3393-5da5-9ab3-68885d54ab06 |  | note | METHODS OR REFERENCE - Visual inspection
label | faf00281-2afd-5b67-b8c3-1196cc9763a8 |  | note | FREQ. - All signs/markers
label | 56dddc49-7e25-5ca0-81c5-4a36e8c62955 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | 7004a4db-2809-5809-9ef5-a38c539278fd |  | note | INSPECTORATE W/H - Type: - H
label | f28ce120-811c-5e0d-ade1-852e211df91b |  | note | INSPECTORATE W/H - Description: - Hold point – Site TTM cannot be removed until marker pegs, signs, markings and RRPMs reinstated
label | 91abb698-94cd-5651-bc83-521f4c2e8dc9 |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Stormwater Management Controls removed
label | 717e209d-bb85-5af5-9077-939e5d3a2a24 |  | note | VERIFICATION ACTIVITY - Visual check
label | 09e1fc74-7b19-5993-9366-8af8088c418f |  | note | FREQ. - All installed measures
label | f8168914-06da-5171-be45-84269ce2a945 |  | note | ACCEPTANCE CRITERIA - Installed controls are removed
label | 67316859-0ad6-5542-815f-984cbfa1e7b3 |  | note | INSPECTORATE W/H - Type: - H
label | f0c5e996-1623-5aad-b06b-1c126224f280 |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Traffic Management Removed
label | 38c8f4df-f9a0-5b4a-82e4-9fc7baabff48 |  | note | VERIFICATION ACTIVITY - Visual check
label | 50574530-c7d2-516b-88e1-3e3b6c1cab0d |  | note | FREQ. - When safe, after all physical works completed
label | b0aaace1-bc27-5af0-8774-e4ba8ffa9c45 |  | note | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | ca2960c1-1ba1-5849-a3b0-590dbcd486a3 |  | note | INSPECTORATE W/H - Type: - W
label | 50706959-65da-571b-87a9-d17534332fe8 |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.6 - Site left clean & tidy
label | 2f169c7b-3c2d-55a7-ba16-558014d801df |  | note | VERIFICATION ACTIVITY - Visual check
label | a0559804-8bc1-5c6c-a7aa-75cb73ce639d |  | note | FREQ. - After vacating site
label | e099b1a7-d3a9-5620-bd62-93a22239b72f |  | note | ACCEPTANCE CRITERIA - Stockpiles removed; Plant removed; Litter cleared from site
label | 3a1b1b04-d8d1-5d38-9dc2-dcc6269d3d26 |  | note | INSPECTORATE W/H - Type: - W
label | 2070b169-4c51-5e84-bd05-f328c2b045cc |  | note | INSPECTORATE W/H - Description: - Invite NZTA to carry out joint site inspection to inspect site.
label | e38fadcd-8d10-516d-8797-7665cf81ca1b |  | note | Responsible Person - Paving Supervisor
checkpoint-group |  |  | section | 5 - As Built Records
checkpoint-status |  |  | checkpoint | 5.1 - Collect asset data
label | 1f3e3f50-30f5-5b3d-a052-a9e69dbf459e |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | a61d50b1-2c76-5110-aba9-ce67e0441fd1 |  | note | FREQ. - During construction
label | dba70a24-e724-53fb-bd69-6910e6aa3797 |  | note | ACCEPTANCE CRITERIA - All relevant as built information collected.
label | e0995cf1-1ce4-5849-b719-c3c66959c645 |  | note | INSPECTORATE W/H - Type: - W
label | 977e3b0b-bf1a-50dd-af2f-37787b60f5c4 |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.2 - Enter asset data into RAMM and/or register(s)
label | 70f28e5f-68a7-55a4-b6de-06f577e40e77 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | db0ebeb2-e46b-56dd-8300-6d769ae346e3 |  | note | METHODS OR REFERENCE - RAMM
label | c0a7cdc0-a76d-57a4-889e-bfc6f1cf1984 |  | note | FREQ. - At completion of work.
label | 9b24dcad-7335-5d7a-9d07-fd37ee8601de |  | note | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.
label | 0227dd80-ea67-585f-b0f9-653bc42a3994 |  | note | INSPECTORATE W/H - Type: - W
label | 934bea45-50f1-5cb4-961c-3c567447eac8 |  | note | INSPECTORATE W/H - Description: - Data entered by 20th of follow month after month of completion
label | ddc4e1bf-43ad-503a-a597-90876ac3cd33 |  | note | Responsible Person - Asset Information Manager
checkpoint-status |  |  | checkpoint | 5.3 - Construction Completion Report
label | 3a454b46-6374-587a-9560-d0dc516547f2 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 7fc7f0da-dbc8-52da-b62c-6e853d3b0839 |  | note | METHODS OR REFERENCE - Contract Specification
label | 4e0e0290-637e-55e3-a9b7-09078a355c21 |  | note | FREQ. - At completion of work.
label | d48a626d-ff5a-5178-b401-03d56332cf00 |  | note | ACCEPTANCE CRITERIA - Checked and approved
label | f3d2d887-0345-5574-9e76-15a4ec343eec |  | note | INSPECTORATE W/H - Type: - W
label | af02ec94-e718-56fa-a0b0-34f8058114ab |  | note | INSPECTORATE W/H - Description: - Completed within two months after Paving Wearing Course
label | 5eb343ad-d9d7-5153-999e-2660e9bd5f32 |  | note | Responsible Person - Renewals Engineer/ Renewals Manager
checkpoint-no-status |  |  | checkpoint | Quality Assurance Close Out
text | e0e63b40-1d93-5ba4-88d0-1c95dcf23af2 |  | textbox | Quality Assurance Close Out by - Name:
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | ITP - CONOC NETWORK - Sealed Pavement Repair - Insitu Stabilisation | itp |  |  |  | Yes | ITP - CONOC NETWORK - Sealed Pavement Repair - Insitu Stabilisation | 162082d4-afe3-44dc-a5fb-0bd760905d5f
checkpoint-status |  |  | checkpoint | 1 - Site Preparation
label | 3992afb4-030c-5efd-9003-c5b80fe11775 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 03fe9a27-20b9-53b1-a36f-ac5070544232 |  | note | Accept / Reject Criteria - Avoid Seal Joint within the wheel path
label | a6db548f-3358-51bd-81c3-7437caa1fe1a |  | note | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | d5843954-71cc-5b8a-bf61-d3068900e37b |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP031/Ground Distrubance Permit
label | a03d290b-9924-5c05-8a8d-e3aeeb92e9b5 |  | note | Records Required - NO
label | 514409d7-c09c-5efe-8708-8e8e76493f84 |  | note | ENGINEER - W(10%)
label | 66e2032e-423c-5499-b200-5e657dcde8ae |  | note | SUPERVISOR - R
label | 55730fce-c440-5be9-bf9e-24b62492ddb6 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Asphalt Pavement
label | 97865ebc-7fc2-5331-ac47-26ad1cd2e085 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 7bbf8ead-795f-51b5-94d2-849c58982722 |  | note | Accept / Reject Criteria - If greater than 50mm deep, remove asphalt from site and dipose of properly
label | 079876a5-d33c-5e72-8736-4f22abb4f9d3 |  | note | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | 1fc20000-6244-58fa-b2c8-dc9201ceed59 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP031
label | 01a3c696-6e22-5f35-b65b-4252f4fbf812 |  | note | Records Required - NO
label | e1b6f213-7521-5e84-a02c-45b614082504 |  | note | ENGINEER - R
label | bca61946-beaf-5301-b77c-5cba56be94b8 |  | note | SUPERVISOR - R
label | ae7cee2e-fe61-5c51-bb05-5b3e3e7cd22f |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Depressions
label | 9af652cd-a122-5e16-934e-5b8fc0931dd3 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 04c58d2f-06eb-50f5-b0f8-0b845b971580 |  | note | Accept / Reject Criteria - Compact lightly (2 passes)
label | 1b0c7215-4e66-547f-afef-88d3895fffc9 |  | note | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | afe515f9-d75f-5941-92e5-d7dab21742f9 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP031
label | c7a1dcd8-20f7-5501-9d33-c7272407e782 |  | note | Records Required - NO
label | 8cf1a6f6-beac-5de3-9972-df870df72bbd |  | note | ENGINEER - R
label | 10767d76-89ed-53f7-8044-4dd09d76e686 |  | note | SUPERVISOR - R
label | 0db5c3c6-9be1-50b1-b99d-71870cc37d18 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Cement Application Quantity
label | 8cd4ddfc-d12a-5758-aeda-91c1df8653ce |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 17b47bdd-c677-52c3-b663-272044fc33c5 |  | note | Accept / Reject Criteria - As per specification
label | 716b59d6-65ac-58a2-a9f1-bd412bf845c0 |  | note | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | 8e8cdbab-6c4b-5ae6-88f3-95416dbdceb5 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP031
label | bbd9865d-af18-5655-8d39-d8a50a47b0c0 |  | note | Records Required - YES
label | 1d77ac1e-020a-5166-b663-52f37ce46778 |  | note | ENGINEER - W(10%)
label | 0d106356-70cf-564f-9c52-7ddddb16c6b6 |  | note | SUPERVISOR - R
label | 5540e577-4aba-5c2d-9816-668e16fa05a0 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Spread Cement
label | 3d2edb4c-3e23-5eb3-b41c-9f793acfd073 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | c907bf2f-9f98-594c-9058-d6a1d5ab7e51 |  | note | Accept / Reject Criteria - Too much or too little could cause failure
label | 55618348-bc05-5862-8b6f-6e77cfb5f128 |  | note | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | e143ab6c-4164-56e4-978d-5176de8416d0 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP031
label | 1beb429f-97c1-5154-b8ec-e18fa2426f5c |  | note | Records Required - NO
label | 2841ffc0-8a94-5596-9628-01233fdca566 |  | note | ENGINEER - W(10%)
label | 241e0e94-b13a-5950-88ad-b4bc0786cf82 |  | note | SUPERVISOR - R
label | c6d690e3-096a-550a-b353-034035f70b6a |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Roatry Hoeing
label | 4e79c5ce-2c1e-5160-8c62-3633143081f5 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 81d068b4-ee44-5a2f-b5da-3076fc294f0d |  | note | Accept / Reject Criteria - Start from the edge of the patch and hoe the entire area at design depth
label | 0db40429-2f7c-5fe0-9707-9ebb14775e77 |  | note | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | cd5fe897-b854-5e33-a20f-397183d33a0f |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP031
label | 64d76be3-61ba-5eef-91d8-d9ffa622bd5a |  | note | Records Required - NO
label | 0fe45f12-3519-5ef8-a1d3-56402da8c6c3 |  | note | ENGINEER - W(10%)
label | 54472c1b-1163-5d54-a947-a0a057b98210 |  | note | SUPERVISOR - R
label | ef702af4-dc45-530d-81e9-7d2fc6041b33 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Make Edge as Straight as possible
label | dd3d1302-8e20-51b5-a92e-58a764f19d35 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 6b3ef65d-09d0-53ee-b5fa-c1f145ba85d0 |  | note | Accept / Reject Criteria - Aim to have material with a max. size 40mm
label | 210e2fe4-f0e7-5568-8b0e-5fa49864071c |  | note | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | 2375f3ac-5cac-546a-bd28-587d1b6769e8 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP031
label | beb9a926-4c3b-5e75-8d9f-13210b7157dc |  | note | Records Required - NO
label | c08e9360-1495-5b2e-966c-e5dd25f46858 |  | note | ENGINEER - W(10%)
label | 9c37d5c2-ccc3-519c-817f-dfafa7296247 |  | note | SUPERVISOR - R
label | 3aa0540b-f436-5c3d-a612-2782994a168f |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Water Application
label | 78c6f6a0-74fc-5a90-966f-0bc9899de85c |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | d2f8dae4-07d2-55c9-b0d4-1e74dd846396 |  | note | Accept / Reject Criteria - Add enough water to make the material sticky
label | 8906a1db-53f5-5d5d-93b7-7a51c50ce55f |  | note | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | b5cc36c4-786c-5a7e-8b8f-22d770580428 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP031
label | 02b6ccf6-fc80-55c1-957b-addfe7c37426 |  | note | Records Required - NO
label | ed5cbacd-6a6d-5244-a4e4-e1382c5afb7e |  | note | ENGINEER - W(10%)
label | c81298a2-261c-5910-8962-0904b7e26212 |  | note | SUPERVISOR - R
label | aeb25eec-0b0d-5fa5-9221-b89d60015437 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Initial Compaction
label | 39dbda90-c8ec-54c7-b086-8654b1357fef |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | f1562b14-8739-503d-b6aa-e60d63a63ef7 |  | note | Accept / Reject Criteria - High Amplitude 5 passes Low Amplitude 3 passes No Vibration 1 pass
label | f843e4bb-d30e-541c-90dc-3796225adbf0 |  | note | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | 63825ed7-51bf-53d9-ba48-929bc814c44d |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP031
label | 188a55ed-5785-59b1-8108-f8d308e3d9f0 |  | note | Records Required - YES
label | 262b57d6-7e92-5868-b43b-b7c40160007a |  | note | ENGINEER - W(10%)
label | f9452c06-9e22-51ad-89f8-457eb3922eb0 |  | note | SUPERVISOR - R
label | d815e6f1-2005-5a20-851c-13ebec1463bf |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Trim Shape & Final Compaction (Clegg Hammer Reading)
label | 146419f8-0d5a-59e7-bbd5-57951d57d39c |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | e65473f7-9639-50c9-a069-1b6e3da9e35b |  | note | Accept / Reject Criteria - Clegg Hammer reading 35 CIV
label | 1da22ee9-36a8-5afc-8b92-2eb0536c76de |  | note | Frequency Of Inspection Or Test - After every 1m
label | ea15b4cc-7277-5f0c-bdb6-eec13c2b1b8b |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP031/Clegg Log
label | 4c0c886e-3969-516d-85fe-8775ea5306a7 |  | note | Records Required - YES
label | 111a4a67-8340-55cc-b62f-99f56434855c |  | note | ENGINEER - W
label | 11cde2c0-d9e7-5966-b34c-0bd0131be175 |  | note | SUPERVISOR - W(10%)
label | 4e8d1938-5bd5-5c4a-97a5-5e54079d1e12 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Surfacing
label | 453888f1-d65b-5988-853b-b5350410ce47 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 88cb228c-ee72-59a8-b6df-2095be67f6c2 |  | note | Accept / Reject Criteria - Chip Seal refer GP047/Premix refer GP041
label | 85d63542-658b-5734-b9af-955526927068 |  | note | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | f0b5145d-79b7-5faa-bca6-9b2d55929011 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP031
label | 4510f014-ba3b-57be-8c15-cc6e9c99f3db |  | note | Records Required - YES
label | 169e11c6-8108-58d4-be55-e11e6bf09b39 |  | note | ENGINEER - R
label | 2fdd5f38-0512-5b5c-b752-f531e3153004 |  | note | SUPERVISOR - R
label | d679988c-6646-509a-8f8d-0edf8f16fb4b |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 - Test and Check
label | 4c3d0382-0af6-5ee0-a218-b8325dee6bb4 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | e3033e9f-7226-5e44-a876-1f27ab7dcbe0 |  | note | Accept / Reject Criteria - No more than 10mm depression with 2 meter straight edge
label | 9fb44bf7-980c-5186-af33-a6c918443ad1 |  | note | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | 64e81b12-e787-5f0d-a1f3-19d2cfefc8af |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP031
label | 4404e43c-fef1-5170-9eab-a6efdac2fb98 |  | note | Records Required - NO
label | d612f9c7-0019-5ec0-b765-88ec581aefc6 |  | note | ENGINEER - W(10%)
label | 861325dd-703c-560a-bda0-1e7df3b58339 |  | note | SUPERVISOR - R
label | 997985bb-b75d-5d12-8587-4d0e42839585 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations - Removal of High Shoulders | itp |  |  |  | Yes | ITP - CONOC Operations (General) - Removal of High Shoulders | 19b0632a-7291-4eb3-bdd2-0c4ff3c7a304
checkpoint-status |  |  | checkpoint | 1 - Prepare
label | d439d71b-d36a-5e81-a6a0-88aa7570cbe6 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | c186d45a-9639-5b1b-8b9c-080b25b2733f |  | note | Accept / Reject Criteria - As per specification
label | 41885f24-2876-5602-876f-fb5ba7de5d71 |  | note | Frequency Of Inspection Or Test - In-process
label | 43760b39-492e-5711-9f42-1689e3e53adf |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP091
label | 06be0fe9-24d5-5f72-a8da-5392c8abd232 |  | note | Records Required - NO
label | ae216909-ae7d-5d1d-8941-ec5baef52f01 |  | note | ENGINEER - R
label | 45c77950-52da-5cf1-8a27-e84197d97913 |  | note | SUPERVISOR - R
label | 9623ead8-ce7a-5788-bc8f-90cecf174729 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Remove EMP (Edge Marker Posts)
label | bc8a60a1-15f0-575f-bbad-02df00b832ff |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 2cab0586-4696-5b34-ac96-8c5df269ee17 |  | note | Accept / Reject Criteria - As per specification
label | 2ab61c21-0bc4-51e5-be4c-6a4fb314c622 |  | note | Frequency Of Inspection Or Test - In-process
label | 7c80f93c-1608-5f6d-9e01-2b7ea3c964bc |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP091
label | a455ce48-a9f3-5afa-ab83-afda6d5985e5 |  | note | Records Required - NO
label | e9ac20a0-873c-5793-841d-8a488e7666ab |  | note | ENGINEER - W(10%)
label | d9750ddd-464b-5dae-b367-7031b3989a29 |  | note | SUPERVISOR - R
label | e66e3ad8-8454-5937-8c6e-34d8f4f5cdab |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Cutting Shoulders
label | d9a7ed76-0f1d-579e-8b2d-f2aaadfb0e8b |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | a89a118a-934c-5bb6-af79-c596c1d17ff6 |  | note | Accept / Reject Criteria - As per specification
label | db161fe9-4032-52fb-a2b2-7364b5d1b42f |  | note | Frequency Of Inspection Or Test - In-process
label | 8b30132c-ab40-5fd6-84a8-ff13b5c99cc9 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP091
label | 38fa2452-5c53-5af1-b190-857674c982a0 |  | note | Records Required - NO
label | 880912b1-640d-5723-9c38-7b9fc95399fb |  | note | ENGINEER - W(10%)
label | a966b0ed-1aea-5244-a0e7-c78bf6d2404d |  | note | SUPERVISOR - R
label | 6d1558a4-005e-560f-b242-be2494668698 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Cart Material
label | a29a17b3-465a-5889-9703-96e59fd60d02 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | c2a3d41b-abee-5b25-91b5-d24274fc9a55 |  | note | Accept / Reject Criteria - As per specification
label | 771aac61-ffaa-5c93-83cc-93c3ad7cb6b6 |  | note | Frequency Of Inspection Or Test - In-process
label | 83a8850f-0232-5b06-bf4f-f302abf5d6ed |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP091
label | 3595ecb2-26ca-56e5-a05a-1bb0860aa5fc |  | note | Records Required - YES
label | 2dfd6211-f102-5a56-bd47-113e146861d7 |  | note | ENGINEER - W(10%)
label | 661bd82e-aaca-5694-ad69-5175d763eb8f |  | note | SUPERVISOR - R
label | abec100e-afd9-5813-a2ee-f5d5b5ec5b9e |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair Surface Depression - Hand Premix | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair Surface Depression - Hand Premix | 1c184063-8efb-4594-a410-772ab46ff6a2
checkpoint-status |  |  | checkpoint | 1 - Prepare
label | 8bcd9ad2-9d66-52e7-a88e-ecb8320cb369 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 2587dba2-c425-5a34-8d95-2b701dfff7d6 |  | note | Accept / Reject Criteria - As per specification
label | 6c67b729-19ff-5a10-b7b1-5f265d7d1316 |  | note | Frequency Of Inspection Or Test - In-process
label | b8c1b8fd-589a-5d9d-a425-c15fa2145dc1 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP039
label | b3d8bb33-98aa-5c73-8eb3-c7fa70b0b88e |  | note | Records Required - NO
label | 363547a1-7dd1-58a8-9850-f552daddedbc |  | note | DOWNER ENGINEER - R
label | 88ce14a3-9fbe-54f1-b5c6-29ccde161a40 |  | note | SUPERVISOR - R
label | 01dc7e18-6d34-5a43-a317-512da3f6f6a5 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Application of Blinder (Tack Coat)
label | b541dae7-bb46-5efc-9b7c-03a4f004db8c |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | dd361d8b-c71c-59bd-9d0d-9b8898860c28 |  | note | Accept / Reject Criteria - As per specification
label | 256351db-59ba-5173-a7ab-7bf933c0aa4d |  | note | Frequency Of Inspection Or Test - In-process
label | 2ba66b9c-9254-511e-9142-365fb4a1e615 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP039
label | d8b435cf-88e9-5077-bbeb-d74e22a8a83a |  | note | Records Required - YES
label | 1999b74d-bf57-5cef-9f64-9448c65e7ae6 |  | note | DOWNER ENGINEER - W(10%)
label | 29252b05-ed83-54b4-a592-2557a7539fe3 |  | note | SUPERVISOR - R
label | ca9c3ead-94a3-5a91-94af-ccc3fce135f4 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Spreding Premix Material
label | 8106dd2f-9c21-5146-89bb-71648e3de858 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | beb84f8e-dd90-50c8-baba-6001b7913fad |  | note | Accept / Reject Criteria - As per specification
label | 768d1c5b-1efc-51de-9406-5bbff58739b6 |  | note | Frequency Of Inspection Or Test - In-process
label | 80b33761-da0c-5280-8ecc-8d7f8c49ed1e |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP039
label | 29c3651e-de18-584c-93bc-e7292b198e12 |  | note | Records Required - NO
label | c0bd428b-a9d6-5a6d-b81f-9a768e1728ca |  | note | DOWNER ENGINEER - W(10%)
label | fefc162f-edde-5b44-b679-56a690cfef2e |  | note | SUPERVISOR - R
label | b262ef46-01df-5215-9d9c-a334b7101931 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Final Shape and Trim
label | eba3f464-0d42-59ed-a16f-a5f4b0977ef4 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 98e27021-bcaf-5805-b52b-af07b127dfea |  | note | Accept / Reject Criteria - As per specification
label | dcf2255d-19e7-5672-aaba-0bdd1b42214a |  | note | Frequency Of Inspection Or Test - In-process
label | 119fdaaf-e75d-586e-9403-078bcde8e0e7 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP039
label | c9d8ffc4-2048-5968-b6b7-aebb65cf248c |  | note | Records Required - NO
label | 8d089032-276f-53cb-8f68-6d415f9cfc77 |  | note | DOWNER ENGINEER - W(10%)
label | de5dd8f9-9f11-56b6-94ba-a6106d4af1c3 |  | note | SUPERVISOR - R
label | 959f8050-cb36-5fcb-9c3d-bfdf6f5dd924 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Blinding
label | d134a1be-1163-5c97-9ccf-aaac3c61b067 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 57ca3af6-ad00-53d8-82fe-d5fe6fb745fd |  | note | Accept / Reject Criteria - As per specification
label | c4ce9253-abca-5e15-8bc2-f9cf804da187 |  | note | Frequency Of Inspection Or Test - In-process
label | c65b5c4b-a742-5b57-a04c-71b717506e73 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP039
label | 29b15037-3136-5cae-9c23-d3f4b30d1e89 |  | note | Records Required - NO
label | 38cbf95f-7126-5fc0-bb18-fe62c5c284bd |  | note | DOWNER ENGINEER - W(10%)
label | 00e8fa11-ca2e-5da7-9bd8-c41cdc079d5c |  | note | SUPERVISOR - R
label | d123ff4b-c4af-5b2f-b893-c652d1af8578 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Test and Check
label | b398c0ea-a123-5dd5-bdb2-3108f6055df4 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 9854b6f0-ffee-54ce-93b6-0e1759f07cbd |  | note | Accept / Reject Criteria - As per specification
label | 08b4c78d-7a08-5dbf-addd-694c8a84975c |  | note | Frequency Of Inspection Or Test - In-process
label | 768a1538-3881-5bc7-bcfa-a8009ce6a669 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP039
label | 4fc601da-a45e-5d50-8583-d45b82500692 |  | note | Records Required - NO
label | 638582c8-4fd5-5260-a72e-05e191d64839 |  | note | DOWNER ENGINEER - W(10%)
label | a546d815-ce36-5bda-844f-2b5cf0036355 |  | note | SUPERVISOR - R
label | 86a8e38e-f406-5d46-ac3d-3ade4d291a7b |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair of Stripping or Scabbing: Applying Additional Chip | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair of Stripping or Scabbing: Applying Additional Chip | 21d5c957-2caf-4574-8115-308ced1d9bd5
checkpoint-status |  |  | checkpoint | 1 - Prepare
label | ef44fc64-dd4d-515d-8e45-6cd5e995121b |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 58608828-b6e8-5d87-ad21-cd27048ebef5 |  | note | Accept / Reject Criteria - As per Specification
label | 03c1d34f-fc80-5edb-b6d8-cf7f9f3425d6 |  | note | Frequency Of Inspection Or Test - In-process
label | 5eac14d6-d588-503c-ad17-94477f34a9bf |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP045
label | a8b0b5ae-2ab6-5968-878d-d47fc1de9823 |  | note | Records Required - NO
label | 30b872c6-1f42-55e5-8e81-069d9878d0aa |  | note | DOWNER ENGINEER - R
label | 26592274-f456-51e2-93a6-1db638962015 |  | note | SUPERVISOR - R
label | 1b071c30-8855-5a14-83cb-f86af8465148 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Solvent and Chip Method
label | 4426c02a-caa2-5cf5-b0e2-84f77bf2cefd |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | ad1a7876-b33b-5fad-866d-e7ba0d13538f |  | note | Accept / Reject Criteria - As per Specification
label | d6243ffb-021d-5763-97d1-ee4b42d38d3e |  | note | Frequency Of Inspection Or Test - In-process
label | 496479c6-266f-55ae-b599-e66d4eed4d7a |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP045
label | 91380738-6e33-5646-899b-03fcec01a6be |  | note | Records Required - YES
label | 272482c4-2757-53c1-9207-83143f5a1d43 |  | note | DOWNER ENGINEER - W(10%)
label | 21f7cd5c-d12a-5166-9a41-0a8646cd55c7 |  | note | SUPERVISOR - R
label | 8724661f-a2b6-5ad6-ab16-02270c20c002 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Emulsion and Chip Method
label | ec2d7fa5-a5f4-5c70-9ef4-19c1fb83af06 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | d616893e-1530-5cfd-9f4c-00c23946b55f |  | note | Accept / Reject Criteria - As per Specification
label | 5c3627d6-56a7-5ee7-bd06-f2333e58fb40 |  | note | Frequency Of Inspection Or Test - In-process
label | ffddebfb-3cb6-56a3-85a7-ca817f8b1ae3 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP045
label | 58d7fd6d-17c6-55eb-9cdc-4b9a0994dcc8 |  | note | Records Required - YES
label | 78e3dc0c-6cdd-5bdb-b1be-4267f670cb43 |  | note | DOWNER ENGINEER - W(10%)
label | 4d027660-c22e-594a-9ad8-8bc5b4a0d056 |  | note | SUPERVISOR - R
label | 541d0d02-f284-5c83-8997-ca08fe681690 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Test and Check
label | 84918fc6-1c0d-51d2-9416-016dbc859960 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 763dfcbe-ba26-5858-a5ab-49cdbb4fcb09 |  | note | Accept / Reject Criteria - As per Specification
label | 031315da-69db-572b-ae00-0d108d76ce09 |  | note | Frequency Of Inspection Or Test - In-process
label | 9f777b5d-7bf8-5818-99b5-95c3c8bb70b1 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP045
label | 44d16bea-894f-5164-9300-1b9d0d1a1789 |  | note | Records Required - YES
label | 0d53d0dc-8ae2-5695-870c-a7090883a3b1 |  | note | DOWNER ENGINEER - W(10%)
label | acd0dac1-3f6f-544f-926f-6b85c834fd1d |  | note | SUPERVISOR - R
label | 143bbb59-85e5-5414-814c-c3057bfa01d4 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations - Application of Liquid Calcium Magnesium Acetate (CMA) | itp |  |  |  | Yes | ITP - CONOC Operations (General) - Application of Liquid Calcium Magnesium Acetate (CMA) | 2341e404-bd62-4683-b9f6-7b3f6c57ba67
checkpoint-status |  |  | checkpoint | 1 - Preparation
label | 2aff1bb7-e2d8-5161-bf96-9ab21a4e675d |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | f850ab1f-52cb-57b4-a142-70e37eb5ef78 |  | note | Accept / Reject Criteria - As per Specification
label | f1f5d544-57c7-502b-b181-3e127edf015f |  | note | Frequency Of Inspection Or Test - In-process
label | e2e6bf9d-e3b8-549a-bae1-829d40e366cf |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP092
label | 1bfe9548-1e66-5a1c-806d-764e31b11176 |  | note | Records Required - NO
label | 08a0a206-74fe-5436-9d93-44b234936c0b |  | note | ENGINEER - R
label | c05a0159-ef0a-5653-ad54-db943dad64af |  | note | SUPERVISOR - R
label | 231ea213-f223-53fa-9d1b-bdaed0e2cca6 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Application
label | 1efed905-1f72-5c8b-ac49-69a1d6a324a4 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 98ede9f9-ff2f-5079-a962-1877bc1b4ecc |  | note | Accept / Reject Criteria - As per Specification
label | 750e0bd0-64a0-5d1d-b855-6fac2350c50d |  | note | Frequency Of Inspection Or Test - In-process
label | 9b532653-a82f-5555-a970-775d0e690867 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP092
label | f1df2a09-2472-5d34-b176-11c3bb30cf69 |  | note | Records Required - NO
label | 88f96535-7062-5fe8-ab01-2f6d17132f45 |  | note | ENGINEER - W(10%)
label | c23e774e-7cb4-5804-aaf6-6b7c4d4f79be |  | note | SUPERVISOR - R
label | 83768159-7fdf-5cc4-a29b-3d46191d0c30 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Test and Check
label | ed5c3187-5abb-5eeb-a95f-6d1a7ee0cb6b |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 96cb3c1b-752c-5646-8360-084c8c7e796b |  | note | Accept / Reject Criteria - As per Specification
label | be04fd5b-64f1-5f62-a317-62d7104f9272 |  | note | Frequency Of Inspection Or Test - In-process
label | 245b6aad-7ddf-518a-b49d-d1c446f6871b |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP092
label | 8501c173-19e6-5f3f-83d4-d09702389a63 |  | note | Records Required - YES
label | e8e0ea04-d207-5ee7-a604-ee7e97823d7e |  | note | ENGINEER - W(10%)
label | 82dd92a7-5985-589e-a1b7-07933871329e |  | note | SUPERVISOR - R
label | d787e055-4958-52bb-abd6-25cfdda89e5f |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations (Heavy and Light Maintenance) - Grading Unsealed Road - Light | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy and Light Maintenance) - Grading Unsealed Road - Light | 2378ae82-28bc-40ed-8610-9012e502a6dc
checkpoint-status |  |  | checkpoint | 1 - Prepare
label | 7d4228d2-48b0-5959-9621-ce4bb878fe7c |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | fde64e07-2337-5446-8edd-5f5ae87b914d |  | note | Accept / Reject Criteria - As per specification
label | 7d46d11e-5691-57e4-b3e3-b230da09df63 |  | note | Frequency Of Inspection Or Test - In-process
label | b994b556-2537-5332-a0f0-454e7f1c0752 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP060
label | a6c883ee-86ea-589b-b20e-9f5aba792aaf |  | note | Records Required - NO
label | b9ce344c-5670-5dd3-ac1a-ce608fcbac64 |  | note | DOWNER ENGINEER - R
label | 1334639d-fe0f-56c4-bd60-a962af75fec3 |  | note | SUPERVISOR - R
label | 3d8dd050-9aee-5f77-92da-f53aea499fd8 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Grader Operation
label | 40f76a3a-16e9-513c-af29-a66ae8f5fe0d |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 79704a1a-5a31-5539-9998-963652d0aefa |  | note | Accept / Reject Criteria - As per specification
label | a7f2cfeb-4736-5675-914e-01935d8a1502 |  | note | Frequency Of Inspection Or Test - In-process
label | f05824ac-120e-51ea-8f7d-880b552eef0a |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP060
label | dc378054-29ae-5cae-8b07-04d8915cb670 |  | note | Records Required - NO
label | ba06f46e-28c4-5afa-bdde-d49a08224b9b |  | note | DOWNER ENGINEER - R
label | 2bce600e-b832-58d9-ac9d-2756fef70f7e |  | note | SUPERVISOR - R
label | 5b957656-8849-5510-ae3f-5d4627aef033 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Grader Set-up
label | 00e7002c-b066-526f-a186-a4ae9d0e3da5 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | d0db90b9-e67b-522c-9e01-97fdf474226d |  | note | Accept / Reject Criteria - As per specification
label | 3e279bb4-9d20-517d-910c-9fe794a55e0e |  | note | Frequency Of Inspection Or Test - In-process
label | 5d2ec05e-362d-52d6-9402-144412bc2a7f |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP060
label | aada1dc7-7d36-55ab-8ef8-216730ef315e |  | note | Records Required - NO
label | 516009ad-3ede-5fa3-8fc8-ad7a23e34fcd |  | note | DOWNER ENGINEER - R
label | e844efdb-2e2d-5d6c-9ae3-4d0e526718b0 |  | note | SUPERVISOR - R
label | 97ca261b-356c-580c-8778-05408ecc1944 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Super Elevation on Corners
label | a95973bd-9779-598d-ae80-305c1db5785f |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | df69888d-0530-502f-a4f6-5492a73a28d1 |  | note | Accept / Reject Criteria - As per specification
label | bc924c63-3d52-59c5-a59b-affd2604a32e |  | note | Frequency Of Inspection Or Test - In-process
label | 171dab0b-5082-5cc4-833a-afece5b32382 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP060
label | 5eb47bcd-bc19-5eca-a80a-8ad1ecdc7948 |  | note | Records Required - YES
label | b92a2694-d933-5d4e-8fe1-4b236a02c30e |  | note | DOWNER ENGINEER - W(10%)
label | 9971001e-7843-51a1-9ed6-58487e080d9c |  | note | SUPERVISOR - R
label | 4de2efe0-07e7-5360-9086-9457427fbc64 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Fisrt Pass
label | c4d6d943-89af-52da-9592-94a324586b11 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | c6929bde-0bf9-5739-bbf9-a5f9aecbc6ee |  | note | Accept / Reject Criteria - As per specification
label | 01c2c8fc-66b8-5a6e-bd62-f963c0a9f249 |  | note | Frequency Of Inspection Or Test - In-process
label | bc5af066-8bf3-5720-a699-6a690cceb9a9 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP060
label | ffd09d9e-12a7-5ce4-aca4-44e7cb63e168 |  | note | Records Required - NO
label | 2b49b6a3-6aa9-5dab-9849-a694e101b60a |  | note | DOWNER ENGINEER - W(10%)
label | 11923678-4c9d-54ba-9b3a-aca2c7abe571 |  | note | SUPERVISOR - R
label | 002279db-35e1-59ed-99ce-b6f3d360fd26 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Second Pass
label | 8fb797af-7f2b-548d-a085-e424fc92583f |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 5571ee17-5497-5c25-9b36-298dba561d46 |  | note | Accept / Reject Criteria - As per specification
label | e7759e11-dcb1-507a-92bf-793225646bd2 |  | note | Frequency Of Inspection Or Test - In-process
label | f66c62cb-0936-5e64-9852-eec34711d7a4 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP060
label | 42be37d7-eeaa-5454-8bd4-9d4a28cd098f |  | note | Records Required - NO
label | 30ac5666-67e4-58bd-a390-abf02416586b |  | note | DOWNER ENGINEER - W(10%)
label | bbdd5b37-37ff-5037-aa6f-8ccbf21e84b0 |  | note | SUPERVISOR - R
label | 78a907ab-ee5e-5df9-bc74-2d1bc8e658c9 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Third Cutting Pass (Optional depending on width of road)
label | ad2465d7-6706-5584-ab68-4e3ee5f0252d |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | aebefca7-0b26-5c43-a1e0-11a806a696cb |  | note | Accept / Reject Criteria - As per specification
label | 287227f1-d712-5679-96ed-185d3e319ef4 |  | note | Frequency Of Inspection Or Test - In-process
label | 8741889f-ed17-55f8-b0ea-11b71f5976a8 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP060
label | 5eef8d5f-aa1c-5696-be7e-653f20e09d58 |  | note | Records Required - NO
label | 44089a95-c456-5e3b-bf8b-93ff07a4b6d6 |  | note | DOWNER ENGINEER - W(10%)
label | 24ee3976-31fb-5e90-b612-fed28aec4482 |  | note | SUPERVISOR - R
label | 7953f503-629d-52a4-9a85-1605bc6655b8 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Spreading Pass 1-2
label | a63df52f-ae4a-5a48-9738-8261a6461897 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 5bdf6e4a-546d-599a-83b0-09853c36f05a |  | note | Accept / Reject Criteria - As per specification
label | e08e5139-185e-5602-be35-a45e677a50b5 |  | note | Frequency Of Inspection Or Test - In-process
label | 40f70a84-95e5-5d61-b289-be78db42842e |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP060
label | 0220f8af-0c84-52c6-a854-7eefabe2606d |  | note | Records Required - NO
label | b35d919f-7316-5858-9fb0-3bc5a5064924 |  | note | DOWNER ENGINEER - W(10%)
label | 975897d3-6242-584a-a584-c5f911158eb8 |  | note | SUPERVISOR - R
label | dff2d165-9b89-5fa1-b9f7-55fa8765ac55 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Things to Watch for
label | c6a679eb-7a33-5208-abe4-48f0170ccd4d |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 5bde98f0-6fbd-5400-91ae-8a7d17291aab |  | note | Accept / Reject Criteria - As per specification
label | 531e314f-fd77-57a6-9911-dae8fbe568e2 |  | note | Frequency Of Inspection Or Test - In-process
label | d60465ca-4af4-5d7c-9ba5-450e5177ae80 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP060
label | b18c03c0-5859-5648-b443-0ecf317263f4 |  | note | Records Required - NO
label | dbffc3ff-9ac3-53d6-b2da-8477e6bc3795 |  | note | DOWNER ENGINEER - R
label | 6b934c5b-89e4-533e-acfd-08a5a750b8ec |  | note | SUPERVISOR - R
label | 71b6c652-cb2f-5ce9-88f0-873dabd2762e |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Test and Check
label | 6a9c54f3-0a46-511e-8c44-f3658d933f98 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 13df98c9-13e1-55e2-a9e2-232da10bee3d |  | note | Accept / Reject Criteria - As per specification
label | 41d2266d-5f8e-52ed-b1f7-e5b487d2aadc |  | note | Frequency Of Inspection Or Test - In-process
label | fa3a5636-ce55-5bc5-acf9-077c6bf8d43a |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP060
label | de7c95d9-2e62-59d4-a25c-3d9ca229d941 |  | note | Records Required - NO
label | 19c32805-6842-587b-b8f3-4cdc37d4e031 |  | note | DOWNER ENGINEER - W
label | 8c048ae1-2fc2-52f2-b29a-841956d16ca2 |  | note | SUPERVISOR - R
label | 34727f77-9e0f-5532-8d32-f4dc58730d34 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair Low Shoulder - Material Replacement | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair Low Shoulder - Material Replacement | 24112068-d9d3-4d95-bb75-c03d28d11c89
checkpoint-status |  |  | checkpoint | 1 - Prepare
label | b146794a-1f8f-52a4-b67d-e23b835d7aa8 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 715e1ebc-16af-5734-8a26-ab80099d4611 |  | note | Accept / Reject Criteria - As per specification
label | 75b908c9-f343-5e5b-b478-7f6cc4ecab1e |  | note | Frequency Of Inspection Or Test - In-process
label | 953af07b-82e9-5a99-8c52-66b918feff2b |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP038
label | 6c106fe9-887e-5cfb-bfe9-8c2887efa7ed |  | note | Records Required - NO
label | 349c08e3-ff2e-5943-a930-d80dfb7d28ca |  | note | DOWNER ENGINEER - R
label | 22dd2041-20ff-56a4-a57e-3ce37c6d8580 |  | note | SUPERVISOR - R
label | 1cbb668e-39df-59af-acd6-92a41bf4818a |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Scarify
label | 92eb5170-baaf-5b13-9295-c397cedda219 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 6e338a4c-fdff-58b3-ad82-5dad7c81443b |  | note | Accept / Reject Criteria - As per specification
label | 8c121b59-48ab-5297-8669-035063805e85 |  | note | Frequency Of Inspection Or Test - In-process
label | 9d142b65-4c11-5931-a687-e1cd1ae6ceb9 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP038
label | 7b94b694-7ecf-5aa3-b513-eaf6c8dc5193 |  | note | Records Required - NO
label | 222b942b-fc14-5610-b890-1812576052a1 |  | note | DOWNER ENGINEER - R
label | 4259297c-5157-512b-bdd9-dea584553782 |  | note | SUPERVISOR - R
label | 22fe35e5-be39-5dc4-91d5-2e58e4d66b0c |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Spread Makeup Metal
label | 991ae20f-3430-54a7-9ddf-3648f26f4001 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 6282a64b-b14f-5bbc-b703-ae63ae8604a2 |  | note | Accept / Reject Criteria - As per specification
label | 1ff08e0b-8a23-5ebd-a6a8-f178011f6177 |  | note | Frequency Of Inspection Or Test - In-process
label | 517b372c-cafa-51f8-954c-5bacf91793b4 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP038
label | 1faebf1d-a750-5fa6-9c86-caa97f96cfde |  | note | Records Required - NO
label | f47140a9-f699-5e79-ae3e-38305cfe87a0 |  | note | DOWNER ENGINEER - W(10%)
label | 221bced8-0d5a-5989-95bb-a3b3ee9ce21f |  | note | SUPERVISOR - R
label | cd6e8da5-2bc3-5312-ad3c-5c89344de2ad |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Fianl Shape and Trim
label | d9f1b0cd-8b92-5d1d-886d-81bf1d065513 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | dcb2a8b9-ac60-5f31-b100-48cd76888799 |  | note | Accept / Reject Criteria - As per specification
label | 3407c45d-e10b-59b0-912f-1f7bcdcce17f |  | note | Frequency Of Inspection Or Test - In-process
label | e7e29310-1f50-5c46-9c66-7d950624f25b |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP038
label | 3a07f103-be98-5273-90b0-c3fbfbc1a604 |  | note | Records Required - NO
label | c88e5cf9-0d8d-59d0-b1ee-966277d71571 |  | note | DOWNER ENGINEER - W(10%)
label | 02dfec33-d1af-5223-a6fe-629dea2ab993 |  | note | SUPERVISOR - R
label | 72e32c03-5eb6-5030-bd33-2bc4dbaf11da |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Test and Check
label | df97dd76-aa9d-57c8-9f7b-9776ed2d7ab7 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 7d710af0-356b-55d5-8987-a0fa9bc65a70 |  | note | Accept / Reject Criteria - As per specification
label | de7902cf-f79c-5fe2-8263-7efcf36732db |  | note | Frequency Of Inspection Or Test - In-process
label | 65ed49a4-3e16-5ba0-a035-05da28231784 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP038
label | 2498d613-9226-5f31-982e-f5707da0853e |  | note | Records Required - NO
label | 48993cb2-cb7e-50ff-bae4-54041fda7914 |  | note | DOWNER ENGINEER - W(10%)
label | ff3bee82-f08b-5a70-9085-0664910c73d3 |  | note | SUPERVISOR - R
label | e2759b07-440e-5853-9514-edecf759f145 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - Centennial Ave - Thin Asphalt Paving |  |  |  |  | Yes | ITP - Centennial Ave - Thin Asphalt Paving | 269ce6a7-d3b5-487d-83c0-d49eff8fb54f
checkpoint-group |  |  | section | 1 - Preliminary and General
checkpoint-status |  |  | checkpoint | 1.1 - Construction Programme Completion
label | 45aabba3-d774-56bb-b0ac-d1858bcb844e |  | note | VERIFICATION ACTIVITY - Confirmation
label | 070fea38-b256-5725-ae55-ddb5f429c1b1 |  | note | METHODS OR REFERENCE - Best Practice Contract Specific MMP
label | 26cb26fb-a030-580a-b2de-7e4377bf32e2 |  | note | FREQ. - Before work commences
label | 1f1b6c25-da9f-5994-81a9-6f59e40a7120 |  | note | ACCEPTANCE CRITERIA - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date.
label | 20a80630-b440-5d61-9256-2691c1b2e17c |  | note | INSPECTORATE W/H - Type: - W
label | 765d79ac-1ea3-5f56-ade9-65ab7389a5fa |  | note | Responsible Person - Renewals Manager
checkpoint-status |  |  | checkpoint | 1.2 - Approved RQP
label | 25538cfa-0808-55e2-9946-c1db1a7af76e |  | note | VERIFICATION ACTIVITY - Confirmation
label | f4cec16a-b859-5aa5-9e5c-f77adf1b0e95 |  | note | METHODS OR REFERENCE - Contract Specification
label | 296dc8fe-c6bd-5a00-8cff-406c82aae91e |  | note | FREQ. - Before work commences
label | 384930f2-10a9-51b6-809c-0064d19bb564 |  | note | ACCEPTANCE CRITERIA - Principal Acceptance according to guidelines in appendix 6.3
label | 294bbfdc-d8a7-5976-8bd5-42a46e130508 |  | note | INSPECTORATE W/H - Type: - H
label | d9f788fd-9ae1-5eff-99c8-05bfe9d67cc5 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. NZTA to approve
label | b45b06d9-70aa-5497-bba3-e1b951d845c6 |  | note | Responsible Person - Renewals Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Traffic Management - TMP
label | ddd04f63-e9cb-53a3-9b85-9ecd39dedf02 |  | note | VERIFICATION ACTIVITY - Visual check
label | 0ccfe6cb-1e67-5bfa-a08a-a7210790e2ef |  | note | METHODS OR REFERENCE - CoPTTM
label | b01a2643-13f5-5d68-916c-15280981abf0 |  | note | FREQ. - Before traffic management set up
label | db52523d-ed8e-566e-a744-64f9d1a260a6 |  | note | ACCEPTANCE CRITERIA - TMP checked and approved Plans approved Current EED (if applicable)
label | 8c69b6f0-fa21-51ba-89d9-4b276056d193 |  | note | INSPECTORATE W/H - Type: - H
label | 832376f5-2c59-58a9-bcbe-06541bb5f2dd |  | note | INSPECTORATE W/H - Description: - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | 94f0ca49-faee-562f-9262-c9afc4be228d |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Mix Design Verification for all mixes Check Laydown Trials are complete and compliant
label | b46d9f3d-3808-52af-8f7d-2d2fd3f57750 |  | note | VERIFICATION ACTIVITY - Confirmation
label | e5a2a762-c4f4-5539-b340-bbd064471822 |  | note | METHODS OR REFERENCE - NZTA M/10, P/11, P23
label | 92047854-9fbf-54ab-a510-ab2d8a6fd3ce |  | note | FREQ. - Before planning commences
label | db0ac486-083f-5289-8e6c-81f639ccbf74 |  | note | ACCEPTANCE CRITERIA - Mix Design compliant, current and relevant. Batching plant production capability is confirmed
label | e2bb4fed-58e9-5770-9926-660f0040cf5c |  | note | INSPECTORATE W/H - Type: - H
label | d47f0f9f-30e5-5f59-b56f-59f6a1d79a74 |  | note | INSPECTORATE W/H - Description: - Hold point - No planning of on-site works shall commenced until the mix design is verified.
label | 94362d6a-daa7-59dc-baf1-c0e13042fcbd |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Notification of intention to start work
label | ff8e38ab-972e-5a5a-9d8e-1f8f4fbce7ec |  | note | VERIFICATION ACTIVITY - Notification
label | ca44c78e-b9a7-5029-b5fe-74e6587d0e43 |  | note | FREQ. - Before work commences
label | 0bf4cecc-1b25-5881-91ec-d8fdc834d0b5 |  | note | ACCEPTANCE CRITERIA - Letter drop to local residents. Greater consultation where required
label | fb1f1c85-74f1-5243-bd3d-0ef09122f339 |  | note | INSPECTORATE W/H - Type: - H
label | ccda78b4-05cf-59db-b49a-7eb35a43916d |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | 43acb650-87a6-5c24-b1dc-7a9649089e0b |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Works Extents
label | 48d66443-bcaa-55bb-8576-9a0020bbdafc |  | note | VERIFICATION ACTIVITY - Confirmation
label | 86fa33b4-a2c2-5daa-ab24-bc849c7e3da9 |  | note | METHODS OR REFERENCE - Site Visit
label | 6d7517ef-7030-5561-91d0-72e103539639 |  | note | FREQ. - Before work commences
label | d966109c-a19a-558d-b231-b598d5880708 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and/or Client to agree extents of project
label | 5be20614-2dd7-55e4-9599-a8a1402a3ecc |  | note | INSPECTORATE W/H - Type: - H
label | 7a13d8e2-a457-530c-860f-690b4044056a |  | note | INSPECTORATE W/H - Description: - Hold point - Walk over site with Renewals Engineer and/or Renewals Manager and/or NZTA
label | 88a83ea7-4335-515b-bcfa-be9d1d2a9663 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - Pavement Marking Records
label | 0efa8aa0-ca69-540f-b57f-3e9686c562f9 |  | note | VERIFICATION ACTIVITY - Measurment Data
label | 1daeae27-0157-52b0-a757-86b4268624ea |  | note | METHODS OR REFERENCE - Site Measure or Video Viewer
label | 87913b53-3ef1-5453-8d42-61db0a679347 |  | note | FREQ. - Before work commences
label | e4b4fdde-c04b-54f7-bdbe-2fd9cd9a15f6 |  | note | ACCEPTANCE CRITERIA - Measure existing markings to aid reinstatement
label | e93d37eb-c501-577c-9afd-ecfb3de99d79 |  | note | INSPECTORATE W/H - Type: - H
label | f6a9a589-3681-51a4-8d5c-050ee0e4dafd |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | bd741066-2f9d-5e0b-87f2-bd58c35c415f |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Milling and Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | 62d2af50-cf9c-57d2-ba58-55cd3b8ec306 |  | note | VERIFICATION ACTIVITY - Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth)
label | 74a9d4d4-205b-569e-a1e7-7a10a62f6b9a |  | note | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | 8960be8c-8970-5686-82a3-9a27128d9e06 |  | note | FREQ. - Before work commences
label | 5f5bf8e9-c879-5189-84e9-261f1491dd76 |  | note | ACCEPTANCE CRITERIA - Zero service strikes
label | 1e67b12e-7e62-5f33-aae8-bba2004d4295 |  | note | INSPECTORATE W/H - Type: - H
label | 7cef9f30-6445-5645-927d-ee62cdf05d90 |  | note | INSPECTORATE W/H - Description: - Hold point - No excavation/milling is to be commenced until services are located and accounted for
label | 8763e2ba-9300-5346-9b02-62b6f345dce7 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Stormwater Management
label | be29c889-fb53-5541-be56-c7645a4347e6 |  | note | VERIFICATION ACTIVITY - Visual check
label | e050eb8d-348e-56b4-8a20-e115f81d73ec |  | note | METHODS OR REFERENCE - On Site
label | 2f5aafef-0ab5-51b8-864f-589d569726d5 |  | note | FREQ. - Before work commences
label | 5aab5637-a06a-5237-bf39-61e10e0296be |  | note | ACCEPTANCE CRITERIA - Mudtanks bunded or filtered to prevent mix from dropping in or runoff entering
label | 9223623f-dd8a-5c03-95e0-49cd0bb40dba |  | note | INSPECTORATE W/H - Type: - H
label | 7e77b515-2b56-58ab-8457-2ff373690352 |  | note | INSPECTORATE W/H - Description: - Hold point - No work to be commenced until protections in place
label | d787f158-a8e9-5d3c-bbd2-11acdb83296c |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Traffic Management - Setup
label | 0fda16be-23c7-55e4-a538-f4f23af962cd |  | note | VERIFICATION ACTIVITY - Visual check
label | c733bc2a-1c9c-51d4-ad04-440548b8b87d |  | note | METHODS OR REFERENCE - Traffic Management Plan
label | c451c1f7-25d9-5410-951a-bf413501dec4 |  | note | FREQ. - Before work commences each day
label | 298523d9-af6e-57e7-a282-02e438e828a3 |  | note | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | 889566fd-347f-5219-bf26-3aeb14bf06d1 |  | note | INSPECTORATE W/H - Type: - H
label | 69e8bf46-3a81-5014-8d2f-1d0e9edc7135 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | b3816179-afcd-5823-a05e-29027d1fc47c |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Milling Depths
label | 0e7d1f0e-79c2-5729-a44d-be06a4882101 |  | note | VERIFICATION ACTIVITY - Measurement
label | ee782aeb-e4c5-5f72-aff1-c8e756dd8a68 |  | note | METHODS OR REFERENCE - On Site
label | 86d43755-98f6-59de-9a22-4be40942ef77 |  | note | FREQ. - Measure each side of milling machine cut
label | c0511e0a-6031-54a8-b510-5cb3736e19f9 |  | note | ACCEPTANCE CRITERIA - Every 10m. Depth matches target
label | b8ece920-64f2-5c81-bf12-6f78e0060135 |  | note | INSPECTORATE W/H - Type: - H
label | 9a633163-c080-52ea-948e-f933d1dc3382 |  | note | Responsible Person - Site Foreperson / QA
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Service Covers Preparation
label | bb7ee495-e72e-587b-8c17-27c1b0de5087 |  | note | VERIFICATION ACTIVITY - Visual
label | e33367db-428f-567a-a359-f0e80e51734b |  | note | METHODS OR REFERENCE - On site measurements & photos
label | e448aee4-cb6f-54d6-8a96-a7f98e10e4bd |  | note | FREQ. - All Covers
label | 03502f9d-f908-5146-9514-5562b9b2909e |  | note | ACCEPTANCE CRITERIA - Hand excavation around ironwork and adjustment to desired level (if required)
label | 82874e2d-d538-5e3b-97cf-398b64a257df |  | note | INSPECTORATE W/H - Type: - H
label | f7e9512d-816f-5762-9374-f7c48eab8c5b |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Additional Surfacing Preparation
label | 4a8ca6df-a46d-5331-9984-053f09a1fed6 |  | note | Side Roads; Accesses; Driveways; Dish Channels; High Shoulders
label | 90de8cb6-9754-5f7e-b76e-501aec070830 |  | note | VERIFICATION ACTIVITY - Visual Check
label | b8464741-7671-5fd6-9aec-fedb86c88bce |  | note | METHODS OR REFERENCE - Per Design
label | 157e773c-e448-5c18-ae41-1f1cca3f671c |  | note | FREQ. - Before Membraning and Paving
label | 88512b35-cfde-5f15-93d4-e52e4debc814 |  | note | ACCEPTANCE CRITERIA - Have all areas of additional surfacing on the design been prepared, membraned and marked for paving?
label | c54667eb-01b8-5129-a364-d946a93976be |  | note | INSPECTORATE W/H - Type: - H
label | cf807298-743a-5868-b510-dc5776c402f1 |  | note | INSPECTORATE W/H - Description: - Hold Point – All areas planned for AC are prepared ready for surfacing layer
label | a1094af0-bcfb-501e-82cd-1fda264b75ec |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Over-Milling
label | b4be963b-6656-56aa-9360-e0a5892e8cca |  | note | VERIFICATION ACTIVITY - Measurement
label | 748054c7-08f6-57ce-b51f-b169232dcebf |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 0bf8bedb-e2db-5ad3-ab93-bee37735d965 |  | note | FREQ. - Prior to pre-level
label | 1dba2ff7-6161-54f6-a1c2-ea8f1cd16a04 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree need and extent of over-milling and infill.
label | 9624a8c1-1962-5593-a3ad-8fe008e94279 |  | note | INSPECTORATE W/H - Type: - H
label | 8eb931ba-668f-5fb5-b4dd-5b965694f2f5 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Pre-Level
label | c1488c25-cf4f-5ca4-98e5-57da960bd3d4 |  | note | VERIFICATION ACTIVITY - Measurement
label | 83c566d6-19ec-50d9-ab7e-25b27c454cf0 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 0f249912-c4b1-5b20-b974-877b75ae94ae |  | note | FREQ. - Prior to surfacing
label | b735bbae-1b3a-5ff9-95d9-cb9414cabaa4 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree pre-level extents
label | 6e7fe806-3d66-5073-9bb9-ea5f3251dde4 |  | note | INSPECTORATE W/H - Type: - H
label | c19a46c4-f0e7-5996-99b7-0938f6dafda9 |  | note | INSPECTORATE W/H - Description: - Hold point - Inspection and agreement by NZTA
label | 16d87fc8-5f78-5358-a66c-939011e63890 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.9 - Membrane Sealing
label | 6c3a8844-d8e3-5fd2-a48b-8ae1f405cd89 |  | note | VERIFICATION ACTIVITY - Visual
label | a631562c-f539-5880-8a86-86dcf267c421 |  | note | METHODS OR REFERENCE - On Site
label | f833c4ed-d73d-5eae-8a60-18623e7be341 |  | note | FREQ. - Prior to surfacing
label | 51e60aca-31b6-5013-bc9e-3609ba522fa9 |  | note | ACCEPTANCE CRITERIA - Membrane seal meets design and extent. Sealing Docket record kept
label | c3312bf4-456e-5fbf-93ae-504374235e96 |  | note | INSPECTORATE W/H - Type: - H
label | 149c8d3f-e943-58aa-a766-97b2dd144620 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Paving Structural
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | e04b0f63-b8d5-5c04-ad20-bf479f2f9e03 |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | 0781fa4d-60d9-5db8-8653-1bca6b8cbfba |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | 9af28027-6eb9-5000-84eb-af9614d8208e |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 86c692fb-b307-58bb-ab46-f24778c79eee |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 7111e8cd-40cb-590f-afb1-3afbdb092932 |  | note | INSPECTORATE W/H - Type: - W
label | 6ae7f087-2b04-529d-bc89-7f787f042ae0 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | d32bbddb-96a0-5158-82ef-22ad178ebeb0 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | 1bdb2b62-6af5-5407-a960-51a82fb4e62c |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | 9801c800-d843-5bef-b7a7-50e2d52aea1c |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | 547ddfcf-df59-5782-b21d-68289747f77e |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 2388446e-6d9f-5e36-894e-fefb4fe72fbc |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | bcda886e-a8fa-5823-88f4-52937956d88d |  | note | INSPECTORATE W/H - Type: - W
label | 63e5f749-4761-5974-b737-b38819e09b98 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 140e373f-7e30-516c-bae1-a5c0fe873191 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | 04463df3-1be4-5580-b158-e90a4844c0e2 |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | e74ad924-59cc-5940-ac5f-04a9b8e8d228 |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | 09a12708-f57c-5e66-a0fb-56c107950cf3 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | f65a18d6-fffc-5a30-adcd-bb87a40dbab9 |  | note | INSPECTORATE W/H - Type: - W
label | 3b48a9ff-ef55-5e86-a4b1-e5bf1ed835b6 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 5086876d-7307-576e-9bad-3f9152cd6d53 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | f5e1b85c-8a39-5599-b108-d9bb31c9247c |  | note | VERIFICATION ACTIVITY - Visual
label | 734356db-a84e-5e56-bace-ec5952105b54 |  | note | METHODS OR REFERENCE - NZTA M/10
label | cedb7b32-c867-5ced-886e-fb75a1fe127c |  | note | FREQ. - Prior to Shift
label | 4c72cdd1-17e3-539f-b605-9493ff374849 |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | 8a6135f9-92d7-5fdc-b7f8-1a5a8ca30b36 |  | note | INSPECTORATE W/H - Type: - W
label | 67f56d7a-23f2-516f-ac54-0e2b08d28f0e |  | note | INSPECTORATE W/H - Description: - Paving Plan and Crew Briefing Plan completed prior
label | a3a220d0-c3ec-5844-9184-32f05a107fe3 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | d66cfe1f-b3fc-573d-ab82-95c73f84a10f |  | note | VERIFICATION ACTIVITY - Visual
label | b1f8a6a0-0021-55ea-a197-d3d3c31fe805 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 4f3d88e8-3868-5d8e-b33e-5457320a8481 |  | note | FREQ. - Prior to Shift
label | 31357df0-a2b3-51c1-bfa1-36894611f257 |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | f73a4774-eca5-5e92-9d55-3a8cc4a0212e |  | note | INSPECTORATE W/H - Type: - W
label | d2f8979c-d8fa-5533-93f9-ae2faf3f9a65 |  | note | Responsible Person - Paving Supervisor / QA Engineer
checkpoint-status |  |  | checkpoint | 3.4 - Mix Inconsistency and Deficiency
label | 5f357b9c-a26d-5940-beb5-e57efba5afb6 |  | note | VERIFICATION ACTIVITY - Visual
label | 87700dc2-4267-5f29-99de-0d27653b6bbe |  | note | METHODS OR REFERENCE - NZTA M/10
label | bcba4f2a-6e49-544b-8dfe-6de35af3eb7b |  | note | FREQ. - Continuous
label | 9cf6b8f4-cb9d-565d-89af-d5482169ae6c |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | f299d78d-3681-5cb1-a211-7ff9694926fc |  | note | INSPECTORATE W/H - Type: - H
label | 3b2e8e47-7443-5697-b025-819f7ac8a6b4 |  | note | Responsible Person - Site Foreperson / QA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Load Locate
label | 35817765-7ea6-57b1-b696-c79215fb4735 |  | note | VERIFICATION ACTIVITY - Measurement
label | 5638cbb8-418a-52d1-98a5-787c6a7cde28 |  | note | FREQ. - Every Load
label | fd4320e5-7464-56bd-a260-f5c88685083f |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
label | a6e4c933-c1b5-540d-855b-a0afa8198045 |  | note | INSPECTORATE W/H - Type: - W
label | bbb16d90-7132-5926-a6e8-9bc414355bee |  | note | INSPECTORATE W/H - Description: - Per standard practice
label | 4c72c6f0-268d-5116-8f37-8b678c7f0a27 |  | note | Responsible Person - Quality Assurance Engineer
checkpoint-status |  |  | checkpoint | 3.6 - Laying Temperature
label | 470743c9-b155-5e56-9b51-719aa0ac13f1 |  | note | VERIFICATION ACTIVITY - Confirmation
label | e58ff471-e58d-5f56-993d-3fe5caa67ea6 |  | note | METHODS OR REFERENCE - NZTA M/10
label | e6a308f6-d871-5b06-bbe4-334993014a54 |  | note | FREQ. - Every Load
label | 94dba3b0-03a7-5477-afc0-787a49b4d113 |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | 136091e8-de35-53e0-b75b-66d63dfbd038 |  | note | INSPECTORATE W/H - Type: - H
label | fe7dae82-0510-55b2-8841-049951ed5d54 |  | note | INSPECTORATE W/H - Description: - Hold point - Reject mix for non-compliant temperatures.
label | e804fb43-fd40-5b1e-b012-8fc12cdb2174 |  | note | Responsible Person - Quality Assurance Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Compaction
label | df323eac-6f2d-560a-9639-b1b5e7d8192a |  | note | VERIFICATION ACTIVITY - NDM Testing
label | df2929a1-ccf4-529e-bacd-e0100440e4ae |  | note | METHODS OR REFERENCE - NZTA M/10
label | 9eb8003b-1ef5-5a39-880c-a9971751ab21 |  | note | FREQ. - Minimum: 1 Test per 300m² within Mat. 1 Test per 100m of joint.
label | e63445ab-39a1-572f-bf81-7d1ea8978dd0 |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | 6a9dd9d6-b90a-5099-8275-5028e3ba5b8e |  | note | INSPECTORATE W/H - Type: - H
label | b8841f98-9001-522e-9cd2-13af6bd1ea8c |  | note | INSPECTORATE W/H - Description: - Hold Point - No Wearing course paved until any non-compliance is sorted
label | 1342e37c-843a-58c1-bb28-423356d110ae |  | note | Responsible Person - Quality Assurance Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Roughness
label | 77b0ece7-c07b-58dd-944c-4b6122626fa4 |  | note | VERIFICATION ACTIVITY - NASSRA Testing
label | 6bca9383-2009-532e-bea4-c57b7288bdf2 |  | note | METHODS OR REFERENCE - Contract Specification
label | a01b84b0-2150-5e00-904f-9aafc1e1eb82 |  | note | FREQ. - post construction
label | 05f4e2af-365d-50d2-99a0-55940b884b8a |  | note | ACCEPTANCE CRITERIA - NASSRA rolling meter average under 60, max of 70
label | 14648da3-6f0f-527e-b8a6-053dec634f06 |  | note | INSPECTORATE W/H - Type: - H
label | 68032333-870d-54d0-b8d7-f44ecf3981ce |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Paving Wearing Course
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | 54be3d78-714f-5989-a8f4-8d302718268a |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | e9079680-4bc8-587f-a8a1-4322c0081e36 |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | 6f88c574-2210-55de-ad02-5e3df78937e1 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | a2e3661b-8751-51e1-88e5-3bcd496dd71e |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 6f4499a4-ff8b-57eb-b331-eef2ceb53ae5 |  | note | INSPECTORATE W/H - Type: - W
label | a1744fb7-ba82-518e-b832-beb70623689b |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 2083c5e1-1e68-5602-9879-36d068e7a44b |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | b091ba95-3619-55ec-9bfa-7aeb2c532c94 |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | de32bee4-2a5f-5114-b94c-51b3a7ef5aea |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | a59253d8-eae8-53fa-8f72-cf8c7b7be802 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 15ef1363-4530-504c-a3d2-14cf6429030e |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | c58ff9a6-f54b-5192-98d5-3e9aaa2a71f4 |  | note | INSPECTORATE W/H - Type: - W
label | fd23248d-fe56-5a93-bc8c-689108dc7aa8 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 8fdd0efc-1d45-5750-903d-f6ed40aac528 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | 1f320489-f6fc-5986-9cb3-85c73eac67b2 |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | 8f3b599a-4890-5886-978d-14dedeb7863e |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | 431ad697-e026-580f-96b1-0fb9b8af3254 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 2a8368f3-0df9-5901-9adc-25026ddc3c31 |  | note | ACCEPTANCE CRITERIA - Per Mix design
label | 0287d376-8a85-52c3-b89d-726a560141d8 |  | note | INSPECTORATE W/H - Type: - W
label | 32461152-b31c-5311-a7d8-082191ea1b1e |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 1bd9f6aa-eef2-5b8c-b045-d1b9325d5bdd |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | 0973fe80-fb4d-542e-bca1-2167957ec09d |  | note | VERIFICATION ACTIVITY - Visual
label | 34640184-abf8-5485-86e4-2bbd1b6d10ba |  | note | METHODS OR REFERENCE - NZTA M/10
label | df762839-8ddf-5de6-abcc-6591084f24da |  | note | FREQ. - Prior to Shift
label | ea79388a-b336-5fe2-9f92-ad3a401c8b26 |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | f35d1f7f-b5ff-54d0-89ee-570a14c38d40 |  | note | INSPECTORATE W/H - Type: - W
label | e563b8fc-7d42-5f68-ae0c-74955e56dab7 |  | note | INSPECTORATE W/H - Description: - Paving Plan and Crew Briefing Plan completed prior
label | 4f63db2a-5fc3-5032-82ba-2d12c564bb6b |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | 751fe9c5-ac95-5084-819e-60002af17b74 |  | note | VERIFICATION ACTIVITY - Visual
label | 9e7e661b-836e-5108-91d9-e26a7a36941e |  | note | METHODS OR REFERENCE - NZTA M/10
label | dda5f98c-294c-5f74-ab73-15fb61a1d838 |  | note | FREQ. - Prior to Shift
label | b081462d-1b99-5907-82be-f6e4437636b4 |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | 27827ab0-939a-548f-91ab-fb490bd15773 |  | note | INSPECTORATE W/H - Type: - W
label | c19f714a-4ad7-59a7-a068-138310c06c07 |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.4 - Grade 3 Membrane Sealing
label | 818b6346-fcee-50c3-8548-5d09c54bf95b |  | note | VERIFICATION ACTIVITY - Visual
label | 149c67ad-3796-55e4-ad8e-33e22a02b744 |  | note | METHODS OR REFERENCE - NZTA M/10
label | e0b6c7cb-def7-5703-924f-5d6443f8ba31 |  | note | FREQ. - Prior to Paving
label | e3451a0c-de4b-5eca-b246-69d7092254ef |  | note | ACCEPTANCE CRITERIA - Applied 2.0l/m² residual
label | da0a0417-7cb0-5421-842d-4a96bb00b016 |  | note | INSPECTORATE W/H - Type: - H
label | 598859c5-ccc1-51a9-a907-498d63fc8c7a |  | note | INSPECTORATE W/H - Description: - Hold Point - No paving until Membrane Done.
label | 98c51a5b-9a51-5cc9-a672-1d9f36e55496 |  | note | Responsible Person - Paving Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Mix Inconsistency and Deficiency
label | 9a790043-d02c-5464-8095-c62c91b0872f |  | note | VERIFICATION ACTIVITY - Visual
label | 096c6d13-a86b-54b5-81b7-5fb9b607ff11 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 8911c287-064f-5123-bdd7-bcdac4cb1938 |  | note | FREQ. - Continuous
label | 71db2e68-359a-5305-9b12-702e0b21c232 |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | a9a6266b-ffb8-57cf-a7e8-269c2af5183a |  | note | INSPECTORATE W/H - Type: - H
label | baa362fe-eb64-57a8-8ed0-8fa91d743c48 |  | note | Responsible Person - Site Foreperson / QA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Load Locate
label | 7e9cd4e6-aaeb-5b26-ada3-32150ce13ad8 |  | note | VERIFICATION ACTIVITY - Measurement
label | 71762881-45e3-5e89-a4a3-e96f47b4f29e |  | note | FREQ. - Every Load
label | 779c525c-bbe6-51d3-8470-0728030fcd05 |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
label | ae48ab99-3b73-5ed1-844f-75655720fede |  | note | INSPECTORATE W/H - Type: - W
label | b9e581f7-ee9c-5f36-9abe-2c7ead38ce1a |  | note | INSPECTORATE W/H - Description: - Per standard practice
label | 525b3cf9-c37c-5aad-8cec-a1c6030609f4 |  | note | Responsible Person - Quality Assurance Technician.
checkpoint-status |  |  | checkpoint | 3.7 - Laying Temperature
label | 34aa5cb5-1376-552e-9cdb-f2fb71102c47 |  | note | VERIFICATION ACTIVITY - Confirmation
label | fd85f017-71d8-55d3-adb8-3938888ec021 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 67ddce5b-6673-5a69-a574-b799d0d6ccd7 |  | note | FREQ. - Every Load
label | 7e925874-6d69-5512-bcd8-abf443b6bfd4 |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | 7397dbe0-d176-539f-9432-d33310c8d47e |  | note | INSPECTORATE W/H - Type: - H
label | 069727b2-95d2-582e-bc85-d3478d86b73e |  | note | INSPECTORATE W/H - Description: - Hold point - Reject mix for non-compliant temperatures.
label | be45e9e1-7d0b-545c-9748-2001a6ac2dba |  | note | Responsible Person - Quality Assurance Technician
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Compaction
label | d3b2e42b-1dbe-5602-9ecc-11b6e5e99608 |  | note | VERIFICATION ACTIVITY - PQI Non-Nuclear Gauge/Cores. Or Non Distrctive Method Testing.
label | cb50acfd-5edd-5782-af34-319e309961ad |  | note | METHODS OR REFERENCE - NZTA M/10
label | 9c66e4c5-ba5b-5869-8443-cacc54903698 |  | note | FREQ. - Minimum: 1 Test per 300m² within Mat. 1 Test per 100m of joint. Minimum 8 cores on Mat and 3 on Joints as Per M10:2020.
label | 3d97b1ba-6370-5da4-8076-e68a47497144 |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | 5293c2a2-dc57-5dc7-848a-66d6a703aa16 |  | note | INSPECTORATE W/H - Type: - W
label | df75734d-27e9-52b5-8484-7d0413a1abb9 |  | note | Responsible Person - Quality Assurance Technician
checkpoint-group |  |  | section | 4 - Site Reinstatement / Clearance
checkpoint-status |  |  | checkpoint | 4.1 - Post-seal Area Check
label | b46867f4-6cd2-563f-ad0f-74340aa7d09b |  | note | VERIFICATION ACTIVITY - Measurement
label | 630b4442-9eb6-57ba-aaa0-3b127631b7d1 |  | note | METHODS OR REFERENCE - On Site tape-measure
label | 56ad3eeb-1531-586b-99a2-b8858e56b4a5 |  | note | FREQ. - After Surfacing
label | 435761e8-1ced-57c9-a52d-9bd1a4df28a8 |  | note | ACCEPTANCE CRITERIA - Check sealed area meets design
label | 5dc95455-2247-5da1-9214-def3faf1a8b9 |  | note | INSPECTORATE W/H - Type: - W
label | b5f6b5e7-35cc-5c12-9795-7d471bee90bd |  | note | INSPECTORATE W/H - Description: - Notify Renewals Engineer or Renewals Manager
label | b2c6002d-59cb-5af2-bd44-455929610e79 |  | note | Responsible Person - QA Engineer
checkpoint-status |  |  | checkpoint | 5.3 - Service Covers
label | b196175b-fffa-5f35-8df0-d09a81ff28a5 |  | note | VERIFICATION ACTIVITY - Measurement/Visual
label | 35bcc986-f7eb-5669-bb6b-3b67d7b1d6e3 |  | note | METHODS OR REFERENCE - On Site
label | 9afd7577-715e-5057-b393-1837b45252c6 |  | note | FREQ. - After Surfacing
label | c66ee5b0-90e5-5042-896f-1c9fc8f8fa1e |  | note | ACCEPTANCE CRITERIA - All service covers are checked and adjusted (if necessary) to finished level
label | 9aa86794-076e-55cf-a67f-015ee4913eb2 |  | note | INSPECTORATE W/H - Type: - W
label | 98d058c6-c58c-5eba-84c9-1dbec1c68b71 |  | note | Responsible Person - Paving Supervisor / Foreman
checkpoint-status |  |  | checkpoint | 5.4 - Joint Sealing
label | 1b4d940e-7abd-51ea-8ee2-4dac0dc19c53 |  | note | VERIFICATION ACTIVITY - Visual
label | 3784f5a0-2c13-5c49-8977-44a864d86062 |  | note | METHODS OR REFERENCE - On Site
label | 654053ca-496a-5e87-aa81-8beeb1000793 |  | note | FREQ. - After Surfacing
label | ff0b094e-2398-5344-b75c-22abc647d0a3 |  | note | ACCEPTANCE CRITERIA - Check cold joints are bandage sealed
label | 4e03a641-01d7-5148-8b0f-523e507e7e02 |  | note | INSPECTORATE W/H - Type: - W
label | 357ed9bb-b0b4-55b1-abbb-55eef3a38d67 |  | note | Responsible Person - Paving Supervisor / Foreman
checkpoint-status |  |  | checkpoint | 4.2 - Road Marking
label | f7b93c23-2bbe-519d-bb00-25fc59868988 |  | note | VERIFICATION ACTIVITY - MOTSAM
label | 44c65e88-4583-5647-a8f6-c68d5c9d1157 |  | note | METHODS OR REFERENCE - Visual inspection
label | b3cd46f3-e65a-560f-ad8e-b5692153f64d |  | note | FREQ. - All markings
label | a73e1ca3-a9f9-5b5c-80b0-84e0cb8c6b26 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, or per design
label | 8ac70ea5-9903-562f-9bcc-f128b047a08e |  | note | INSPECTORATE W/H - Type: - H
label | 044bf61c-63a2-5b08-8713-f0b6e6d16385 |  | note | INSPECTORATE W/H - Description: - Hold point – Site TTM cannot be removed until markings reinstated
label | 2275fc19-169d-56a3-ac8f-95c7893cf49a |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 - Other Traffic Services - Marker pegs/ Signs/Markings/RRPMs Replaced
label | d219b915-d845-5abc-94d7-f5242cec1326 |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | 307e7825-c81c-5ca9-bb3c-27972509258f |  | note | METHODS OR REFERENCE - Visual inspection
label | 8a842a1f-5e25-5721-8e8e-54b6d5230c6d |  | note | FREQ. - All signs/markers
label | 0d7e0c0a-e18b-50bf-9aa5-a572c2b864e9 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | aa67cc2d-68ee-5f8f-8a90-dac870deb5f7 |  | note | INSPECTORATE W/H - Type: - H
label | 8a1bb05e-1ac9-5594-ab8b-11095e02d2ed |  | note | INSPECTORATE W/H - Description: - Hold point – Site TTM cannot be removed until marker pegs, signs, markings and RRPMs reinstated
label | d53bf256-2731-538a-88b2-86cc5844d19f |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Stormwater Management Controls removed
label | 0a6246b4-048c-5290-b0e4-062883a384d9 |  | note | VERIFICATION ACTIVITY - Visual check
label | e9dabc13-7727-5eec-b71b-f41588303a82 |  | note | FREQ. - All installed measures
label | ae85a09d-29d2-5923-b5bc-4cbf0ce16423 |  | note | ACCEPTANCE CRITERIA - Installed controls are removed
label | 617bf363-c60e-5fd4-842a-e7e8d9be050e |  | note | INSPECTORATE W/H - Type: - H
label | fd484ffe-b4cf-5f1b-b9ee-68052888f5fe |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Traffic Management Removed
label | b1294eeb-aeae-5a7f-a36a-9f71769b220a |  | note | VERIFICATION ACTIVITY - Visual check
label | 8771ebed-a940-5f72-90b8-dbcda4484e47 |  | note | FREQ. - When safe, after all physical works completed
label | 10a0d380-01b4-55bc-a94e-620e920c955f |  | note | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | 45cf4d0c-2401-5180-83c5-220b112856f7 |  | note | INSPECTORATE W/H - Type: - W
label | 6b86d27c-7586-5894-b2be-47da6b51c2b8 |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.6 - Site left clean & tidy
label | b19f25f2-7270-517b-8bd3-071c7d32ae3f |  | note | VERIFICATION ACTIVITY - Visual check
label | fe037795-0deb-566e-b1bf-0eb9bbe78f7a |  | note | FREQ. - After vacating site
label | 62c2fec2-8fd9-5a5e-934f-f9ca5036ddb8 |  | note | ACCEPTANCE CRITERIA - Stockpiles removed; Plant removed; Litter cleared from site
label | 27661d1f-d9ea-54f9-bf61-b8c8105fed0b |  | note | INSPECTORATE W/H - Type: - W
label | 4eb768bd-8e5b-53d5-a54c-e3cffb2414a7 |  | note | INSPECTORATE W/H - Description: - Invite NZTA to carry out joint site inspection to inspect site.
label | f8dc8f20-92f7-5a93-86d7-920ca99fabdf |  | note | Responsible Person - Paving Supervisor
checkpoint-group |  |  | section | 5 - As Built Records
checkpoint-status |  |  | checkpoint | 5.1 - Collect asset data
label | 828a7b25-53b5-5fe2-9b61-e674b7762dbd |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | 4bda332b-1d41-5e72-a112-4f1d09d7543c |  | note | FREQ. - During construction
label | 0afa11e3-e49d-5599-a3eb-f5f214616d0b |  | note | ACCEPTANCE CRITERIA - All relevant as built information collected.
label | 4be15d41-e213-5a73-b45e-20bf03f47372 |  | note | INSPECTORATE W/H - Type: - W
label | 33634bce-4a63-54ba-b1ff-531f2b5f51ad |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.2 - Enter asset data into RAMM and/or register(s)
label | 48c6e22b-c337-5995-8967-3e8f119aa889 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | 283d4ce2-3540-5887-938d-abc87bb38f81 |  | note | METHODS OR REFERENCE - RAMM
label | 07369062-7580-50e9-a95d-31cd9d7c5cf2 |  | note | FREQ. - At completion of work.
label | e4269d17-0530-5d1d-83a8-00340abf6b9e |  | note | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.
label | 360c7c3c-6403-5650-9340-0d6ec86e0b83 |  | note | INSPECTORATE W/H - Type: - W
label | ca627926-679e-5311-9ac8-fd22b296c54f |  | note | INSPECTORATE W/H - Description: - Data entered by 20th of follow month after month of completion
label | d5c120a1-6c7b-513c-965f-f34355602bd1 |  | note | Responsible Person - Asset Information Manager
checkpoint-status |  |  | checkpoint | 5.3 - Construction Completion Report
label | 5fa9fe94-92d5-577a-91e5-8f7903c8a84b |  | note | VERIFICATION ACTIVITY - Confirmation
label | b7435a98-c215-5ebd-9aaa-108a11938b77 |  | note | METHODS OR REFERENCE - Contract Specification
label | da10a13d-e37a-5846-8d80-cd2d30acf5e1 |  | note | FREQ. - At completion of work.
label | ed7957d5-4fea-57de-9308-204e5562841d |  | note | ACCEPTANCE CRITERIA - Checked and approved
label | 2e4cca25-6a45-5332-9ca6-ec20b2a71b82 |  | note | INSPECTORATE W/H - Type: - W
label | b8ff0cc8-e1b9-5b00-8d10-9d02bcbb8836 |  | note | INSPECTORATE W/H - Description: - Completed within two months after Paving Wearing Course
label | 75448c8c-d4c6-5885-9488-ac7f6806321a |  | note | Responsible Person - Renewals Engineer/ Renewals Manager
checkpoint-no-status |  |  | checkpoint | Quality Assurance Close Out
text | 8dd22bae-c669-5e5a-abc3-dc6831f58a0d |  | textbox | Quality Assurance Close Out by - Name:
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | ITP - CONOC Operations (Heavy and Light Maintenance) - Grading Unsealed Road - Heavy | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy and Light Maintenance) - Grading Unsealed Road - Heavy | 27dfae30-92c5-43a6-8dc6-14423a08cdf4
checkpoint-status |  |  | checkpoint | 1 - Prepare
label | 35130ce7-f359-5117-b3f0-722e0e662911 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | c37020c3-8169-5a0f-a390-bd1014ef33ca |  | note | Accept / Reject Criteria - As per Specification
label | cff1e00f-375c-573e-966e-988845581322 |  | note | Frequency Of Inspection Or Test - In- process
label | fdf00d4e-38bd-5e8b-a427-174e369e965f |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | 141dfc06-4890-58fb-b06e-9d541c8dc1f5 |  | note | Records Required - NO
label | ca6fe167-36d4-5d68-94b3-0e798a187028 |  | note | DOWNER ENGINEER - R
label | a0eded41-ba73-5da2-8cb1-4dfa89c401d0 |  | note | SUPERVISOR - R
label | 7962ea31-8a24-5f60-8582-a37285e7834a |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Grader Operation
label | b926448d-5bc1-5448-979c-91b9263b7737 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 6c6f8b7c-34d8-536c-9b60-8eb4f8bec0ce |  | note | Accept / Reject Criteria - As per Specification
label | dcea6fb3-f8f7-5c3c-989e-ad8d946e06d4 |  | note | Frequency Of Inspection Or Test - In- process
label | 6cfbaeeb-e2b0-5274-bfee-4944c99597f9 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | 3ee7563e-ba96-5fd8-b7f5-a8f373fc7394 |  | note | Records Required - NO
label | ab2d9311-93d8-5111-8b2f-4a201f16ab5d |  | note | DOWNER ENGINEER - R
label | 457f72fa-84ca-5f3a-98fe-652b41ddd673 |  | note | SUPERVISOR - R
label | d03e0907-db90-58e7-b576-5d410bf9c553 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Grader Set-up
label | 2e07335b-0048-51ee-adc4-586ac813a2ca |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 8e957411-781e-5264-af52-335ded42880b |  | note | Accept / Reject Criteria - As per Specification
label | 684f9bf8-e86f-52f3-93c6-dd5fba88fb60 |  | note | Frequency Of Inspection Or Test - In- process
label | 82ba1aa1-7b4c-55ed-b337-31d9c2856182 |  | note | Spec. Ref, Procedure Or Method Statement - In- process
label | f71a3cb6-78fd-5440-92f9-3ffbc39b2b92 |  | note | Records Required - NO
label | 122364be-61c9-5876-b167-9ddbaa151446 |  | note | DOWNER ENGINEER - R
label | 0f11ae38-de91-56cc-9e97-fa589c63beb7 |  | note | SUPERVISOR - R
label | 50f60e63-affd-54cf-a18e-f8893bb0cd07 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Super Elevation on Corners
label | 03a01166-57cd-5918-abd7-1be824d57a6b |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 8ac88f11-802c-5f73-b0d3-3686e8f57fac |  | note | Accept / Reject Criteria - As per Specification
label | d7db1a92-684b-515b-8949-a8354217d958 |  | note | Frequency Of Inspection Or Test - In- process
label | 5f8d19ee-f9dd-525a-94b4-47e1b7d815bf |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | 4722965a-651d-5050-88d5-ba99a4fd7482 |  | note | Records Required - YES
label | c5847b0c-9b93-5ff7-b477-a1d8dbcb5850 |  | note | DOWNER ENGINEER - W(10%)
label | 5e4f5131-837d-5ce1-a9aa-4fda19e19ae0 |  | note | SUPERVISOR - R
label | 69f843f6-1fbc-534f-b40d-c6e3923b3925 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - First Pass
label | 9f9a18a3-c330-5c55-8b53-f9f403c0de33 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | cbf1af6b-f180-56fc-b000-fb2614250b4e |  | note | Accept / Reject Criteria - As per Specification
label | e9141f3f-5c17-5095-a8b1-ee8d80f1414c |  | note | Frequency Of Inspection Or Test - In- process
label | 5f3b0e5d-7ee2-5381-b64b-17597a0f042f |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | 5f9e279e-0466-5a03-9c14-6425b5ead822 |  | note | Records Required - NO
label | 4f534c73-d6e4-540b-b04d-89f531575ea0 |  | note | DOWNER ENGINEER - W(10%)
label | c134af49-c575-5e8b-a2f4-f398cd04a721 |  | note | SUPERVISOR - R
label | 0070fd55-a0f4-50c1-beb3-4684f74375b7 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Second Pass
label | ebdf26dd-e96e-5953-8fbc-52c5846076d0 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | d9713ae4-c491-5a2a-b75e-614a27f7e6d6 |  | note | Accept / Reject Criteria - As per Specification
label | f8be9e21-bafa-5470-a6b4-fa43071adb90 |  | note | Frequency Of Inspection Or Test - In- process
label | af7f08ff-9610-5546-b142-932c7902d96b |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | 74f54a70-5a72-571c-9df2-93a9ba9c5cd2 |  | note | Records Required - NO
label | 0dabc798-bfa9-5907-a497-818e011f9404 |  | note | DOWNER ENGINEER - W(10%)
label | 2c23fdc7-1a2b-57be-bf32-4ca7076216f7 |  | note | SUPERVISOR - R
label | 59f5a914-4e19-5b36-acd1-231b5609cb9d |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Cut outs
label | c52edfe9-2c4a-5510-8194-e0bb6621402f |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 3edc3429-3575-500b-a825-360b8a6161cb |  | note | Accept / Reject Criteria - As per Specification
label | 0225066f-3242-5a4c-b323-346bcdbf5cf1 |  | note | Frequency Of Inspection Or Test - In- process
label | f06fe67b-7bbc-583b-a1a9-b62f6962e70c |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | 8ddd0b1b-ca89-5e70-ab20-24c86cbdf12a |  | note | Records Required - NO
label | d1e45394-e5ab-58ed-83f9-b484a4eb7169 |  | note | DOWNER ENGINEER - W(10%)
label | 867f2d3a-d79b-538b-b458-cf84b4abb03b |  | note | SUPERVISOR - R
label | 15a38731-3186-583d-9804-89d6277217af |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Third Pass Grader Set-up
label | 766dea65-0e3b-50ad-9232-c4989f2b64c3 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 83a5fff1-7eb0-5c24-ae21-f476c9cc2a8d |  | note | Accept / Reject Criteria - As per Specification
label | 633d360c-b142-5cfe-8466-f13324c20d47 |  | note | Frequency Of Inspection Or Test - In- process
label | 5967819e-10b3-5531-9b5a-cbac0179a198 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | 58803e93-02bc-549d-853b-1d485050249a |  | note | Records Required - NO
label | 4be7d718-25fb-55b1-9b36-fdc2852854fc |  | note | DOWNER ENGINEER - W(10%)
label | 62785a8d-ea7e-5dde-bec7-43d054355014 |  | note | SUPERVISOR - R
label | 257ba14b-2410-56a7-a889-5dd1611f3f17 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Fourth Pass
label | f84041c8-c466-561d-a171-5b97bd018540 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 321e49b0-ac52-54ee-8594-b462b1521f32 |  | note | Accept / Reject Criteria - As per Specification
label | 9ead14d3-e5eb-5ca4-bbd3-cf4cb71b5cb0 |  | note | Frequency Of Inspection Or Test - In- process
label | 6422ef98-d7c7-5271-8db8-a26d1c7c0ed6 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | b52d94fd-e290-5c62-9ec8-13109539ee85 |  | note | Records Required - NO
label | 92e056e9-d666-5062-ab35-aa7927d56332 |  | note | DOWNER ENGINEER - W(10%)
label | 535dbe77-be57-56d8-b8b0-11acb1fa951a |  | note | SUPERVISOR - R
label | 7afc2bdb-462e-59ab-addc-c3cbc2b6aeae |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Extra Pass
label | ecb49812-25a3-553c-8cbd-8008dd191a6f |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 6245bff4-b06f-5d03-ac01-64adb144be3f |  | note | Accept / Reject Criteria - As per Specification
label | 171914ee-64aa-50cf-9523-92f1641264ee |  | note | Frequency Of Inspection Or Test - In- process
label | aa9db432-1fb0-558d-96b9-ee200c1217d7 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | 0ebb8949-c4dd-5838-9799-13de531e0ea5 |  | note | Records Required - NO
label | c0dbb4b5-bb8e-524c-9bf0-200effda7367 |  | note | DOWNER ENGINEER - W(10%)
label | 274d09d9-e06b-5481-b0e0-a1b2aa77bf32 |  | note | SUPERVISOR - R
label | 8dfb5424-e8a0-5ba7-893c-1713690c4416 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Spreading Passes 1-2
label | 0634ef7a-8a54-533b-9b18-3e1c3373efab |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 46a52a28-9e7a-53c9-a0ee-eb307847da65 |  | note | Accept / Reject Criteria - As per Specification
label | 5fe4537c-232b-51c7-b9bd-fb70a9094aba |  | note | Frequency Of Inspection Or Test - In- process
label | 399f6140-3f36-57b1-9131-4d33d3517b44 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | c94ce238-d3dd-531c-b56f-1446e7dcdfce |  | note | Records Required - NO
label | 75021be1-e279-5204-9cb6-b3465ae400ec |  | note | DOWNER ENGINEER - W(10%)
label | 63c72aba-fb90-5cc0-9734-9be5d3e212e8 |  | note | SUPERVISOR - R
label | bf631dbb-f360-50f6-9c80-97d448b9c906 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 - Compaction
label | 78d49cc2-3583-5adc-9c01-cf3e41dc14d9 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | bce7216d-0e90-507e-bc08-de1b415e592a |  | note | Accept / Reject Criteria - As per Specification
label | 64f26db3-0efc-5b71-aecd-0285c3777983 |  | note | Frequency Of Inspection Or Test - In- process
label | 71032131-a1ff-51e4-af6f-d51442a27b4d |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | b17f3fb7-2063-52cd-9c1d-e9f77525655f |  | note | Records Required - YES
label | 0fbf1aac-e5a5-5d51-8f35-239e848e821c |  | note | DOWNER ENGINEER - W(10%)
label | a159a33d-b5b6-5c82-be5f-693ef3d7571a |  | note | SUPERVISOR - R
label | 365a43c4-da74-5ba4-b841-e4717a0bb626 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13 - Issues
label | 358ff6b7-c9af-52e0-8660-1231b76fa236 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | c95f6975-ec9b-5bcc-96c4-22667cb5982b |  | note | Accept / Reject Criteria - As per Specification
label | b069ff30-7872-5594-b044-b54f24e54ea3 |  | note | Frequency Of Inspection Or Test - In- process
label | a592b46d-40d1-51d2-a4f8-e81ebab83770 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | 47ed803d-950e-588f-a685-8b9612b837d0 |  | note | Records Required - NO
label | 3d40f58d-5ca7-5c40-a82f-6dcb842083f7 |  | note | DOWNER ENGINEER - W(10%)
label | 3b398c81-c872-5f31-86fc-6efcdd806def |  | note | SUPERVISOR - R
label | 30fd09cc-73bd-59d4-b40f-6456858e4ce6 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 14 - Test and Check
label | 71768c35-86e1-5e42-b0ca-f8fd1cd42e28 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 974ef483-cf85-5975-995c-db66982d16c7 |  | note | Accept / Reject Criteria - As per Specification
label | 558b8bdf-309f-5b94-a25e-cc02d42d8c5a |  | note | Frequency Of Inspection Or Test - In- process
label | 770a5fac-952a-5842-a3c0-561abd6f758a |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | 3b285342-337b-5b6a-a857-c2cca4dee15a |  | note | Records Required - YES
label | a67197bd-332a-57ce-af5f-145d7a8ab3b5 |  | note | DOWNER ENGINEER - W(10%)
label | ecb126b0-a98c-5292-9622-27bd20f31a91 |  | note | SUPERVISOR - R
label | ec6313fd-eddf-54d6-9765-0f1d6ffef711 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC NETWORK - Culvert and Drainage Inspection | itp |  |  |  | Yes | ITP - CONOC NETWORK - Culvert and Drainage Inspection | 294c1399-889d-4c98-92ef-d0832f4a6db2
checkpoint-status |  |  | checkpoint | 1 - Calibration
label | b07731ad-26bb-5071-8a7d-07418e7c3c01 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 51c8723e-0080-548a-abd9-300631c4bfe6 |  | note | Accept / Reject Criteria - As per specification
label | 115bf65e-1d21-5cd0-abb3-d0e892c7b004 |  | note | Frequency Of Inspection Or Test - In-process
label | 8244dcdd-f80d-5fd0-8849-2793468d951d |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP080
label | 56e7d4d6-a6b9-5a61-b670-61279b4e06c5 |  | note | Records Required - YES
label | d9951ceb-47ca-5e48-bbba-7b5597a579c8 |  | note | ENGINEER - W(10%)
label | 7ca6f770-b40d-5e50-9ba1-065bb0167f5d |  | note | SUPERVISOR - R
label | a226aef5-ea59-5677-b006-2fc8bae6aa91 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Inspection
label | 232d73d8-1316-5dcc-89af-af77e9c1456b |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 6a9b8951-aab6-500f-9009-7da30a7a69fe |  | note | Accept / Reject Criteria - Use the Drainage Inspection Guide
label | 8fe47aee-d816-5fc9-b4fd-4c78d5f98a01 |  | note | Frequency Of Inspection Or Test - In-process
label | ce97f02a-b2b7-5a29-a8c7-79748b98bf9e |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP080
label | 7ef1cd04-c853-529a-9ff0-e60a709fb746 |  | note | Records Required - YES
label | 73c29ec7-ae35-5c90-8c61-798c74d3cc53 |  | note | ENGINEER - W(10%)
label | 4b8814f3-2f20-524c-af24-f69be6b76ede |  | note | SUPERVISOR - R
label | 13094d32-58da-55c5-a579-f8590132e8d7 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations - Install a Subsoil Drain Fabric Wrapped Strip Type | itp |  |  |  | Yes | ITP - CONOC Operations (General) - Install a Subsoil Drain Fabric Wrapped Strip Type | 3661f08d-5197-49ba-844e-f68cbe7077de
checkpoint-status |  |  | checkpoint | 1 - Prepare the Site
label | 2631c300-1c03-5579-a1e2-7c1d1c6e8da6 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 47af76ea-6b6d-5516-b3a4-45de28fae9e8 |  | note | Accept / Reject Criteria - As per Specification
label | 42b08f2b-2524-527f-b67b-a184c4c6de5e |  | note | Frequency Of Inspection Or Test - In- process
label | ffe4c2ea-8ca1-5968-8af5-bc5e5da3b15c |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP088
label | 10e67fc1-1e09-5e6e-ab91-368c7988f6b9 |  | note | Records Required - NO
label | 61d9e73a-89d9-56d6-b7da-eb82978b9745 |  | note | ENGINEER - R
label | 6d63f519-2851-57e0-b3e3-7a4737f2b461 |  | note | SUPERVISOR - R
label | c516e5ca-bf24-529b-948d-1d8c1f985108 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Prepare Base
label | b98569ec-0afb-5186-8f06-ab7af222a8f1 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | f8a79175-301e-5280-a4d7-18b8b7f9346c |  | note | Accept / Reject Criteria - As per Specification
label | b223290e-6215-562d-a623-68437e97e35a |  | note | Frequency Of Inspection Or Test - In- process
label | 7ba37116-8e70-5bcc-bc97-bfd2e98cfee1 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP088
label | 27e24836-f728-5f48-a375-54fa0f37607f |  | note | Records Required - NO
label | 9dfd4a47-36a0-53e7-98df-75b885fd7341 |  | note | ENGINEER - W(10%)
label | 1415c739-2f70-59c3-bacb-c3a427ff8665 |  | note | SUPERVISOR - R
label | 06051026-2ee8-526e-bd32-5a17f7fa04e9 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Lay Filter Fabric Wrap
label | f02d2a80-d291-5a4b-87c0-6f8597bd52d3 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 85bd487f-d28f-5df9-94c9-0f25af573d57 |  | note | Accept / Reject Criteria - As per Specification
label | 739c754a-065f-5263-800e-1eedae73a861 |  | note | Frequency Of Inspection Or Test - In- process
label | f1d0924d-4f88-563f-b6bf-7b296045e2fc |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP088
label | 6ce30b47-c4bc-5990-9ceb-98dd3c94fd22 |  | note | Records Required - NO
label | 3f92627b-58ae-5f63-8e54-28c79ffd8937 |  | note | ENGINEER - W(10%)
label | 157f627a-b579-5be5-8428-1a052c021918 |  | note | SUPERVISOR - R
label | 1dd9bb7f-99ec-54a4-a828-4c80910280f3 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Lay Bedding Material
label | d50a1000-29ab-5ecd-b8c6-f6dcee1679bb |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 5d627dc0-4e67-5b09-a35b-32cb87ba02d4 |  | note | Accept / Reject Criteria - As per Specification
label | 8845b880-704a-5a6a-bf70-fd7c7327f653 |  | note | Frequency Of Inspection Or Test - In- process
label | ef81b309-b2c8-526d-b9f2-af2cf009fa65 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP088
label | 7de52606-b405-553b-ad56-1858051eb8d1 |  | note | Records Required - NO
label | b74a105f-714e-52f8-9d26-53a244798624 |  | note | ENGINEER - W(10%)
label | a9b9f366-fbc8-524d-abbe-ee35c9fd192b |  | note | SUPERVISOR - R
label | 8f540500-8b54-5b85-ba19-72d7154b4260 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Lay Strip Drain
label | 24d64bb5-ae25-5f44-af19-e071c764a97a |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | da8432d3-440c-561c-ab1e-d7ceb5c64455 |  | note | Accept / Reject Criteria - As per Specification
label | ea66ad97-365f-50b3-9ef7-bb2e960f8857 |  | note | Frequency Of Inspection Or Test - In- process
label | 23f7256d-a059-5560-969f-2938d7a57c9b |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP088
label | 7e61c956-902c-5350-b5d9-5b507c1bb6f0 |  | note | Records Required - NO
label | 5101b1d0-397d-507b-bb8e-0b3c822d2e0b |  | note | ENGINEER - W(10%)
label | 6b7475fa-48e6-5116-994d-9871788e8d1d |  | note | SUPERVISOR - R
label | 7ef38dcc-2ccb-5272-b7d8-f8ff4f74ec1f |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Outlet Control
label | b4f70ee7-c621-50e3-a254-885062815f29 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 2019a30a-5949-5536-adfa-34201dd6aadf |  | note | Accept / Reject Criteria - As per Specification
label | ce979df0-06d0-51e1-beb0-1ccc4e6ad504 |  | note | Frequency Of Inspection Or Test - In- process
label | 5ee556eb-90c9-5532-b498-cb7c7dc86f04 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP088
label | 700faf4d-4729-5fc8-9781-5b8ca7329a52 |  | note | Records Required - NO
label | 4ab31fc3-1390-5bc7-be0a-3beb92d04eae |  | note | ENGINEER - W(10%)
label | 7753ce79-25c5-548d-bc17-959ab00cf9a6 |  | note | SUPERVISOR - R
label | e0ecea3d-31db-5324-8f59-fbdad8e00561 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Test and Check
label | 7a939feb-3c0e-56d2-876d-1994824a6f5a |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 2ce4e096-c345-5461-a86e-fc052e8e0ced |  | note | Accept / Reject Criteria - As per Specification
label | 74a1c862-7d03-530c-a518-6acf6b6d7fa5 |  | note | Frequency Of Inspection Or Test - In- process
label | cc1dbeab-8585-55e8-abbd-887bdb3dd035 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP088
label | fd21e38d-619a-5b82-89d4-b8c64a313b44 |  | note | Records Required - YES
label | d136c444-5822-5b3f-8f91-fbcc5dddbdf7 |  | note | ENGINEER - W(10%)
label | dff04e47-a8bc-5e87-a6e2-505e025096e8 |  | note | SUPERVISOR - R
label | d7cb1061-2917-5f22-9ac2-5745b7419fb5 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations - Install a Reno Mattress | itp |  |  |  | Yes | ITP - CONOC Operations (General) - Install a Reno Mattress | 3928bdb0-75c0-4b6b-b7ac-e66d6d9e73d1
checkpoint-status |  |  | checkpoint | 1 - Prepare Base
label | b68886fc-620b-51a1-bc6b-8103d2dc1408 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 1e8422a8-8ad5-55d2-97d1-50d5f334f2b4 |  | note | Accept / Reject Criteria - As per specification
label | 80b6c980-0b16-5591-99b6-7f5cf52868f7 |  | note | Frequency Of Inspection Or Test - In-process
label | 2deddf97-1303-59bf-9b57-4f816cb8a6bc |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP087
label | 40896600-3b27-5bd6-a70d-0e86fec38135 |  | note | Records Required - NO
label | 1c1018db-956c-523b-a439-13eccf62ce4a |  | note | ENGINEER - R
label | 86998ff7-55ea-514d-a28e-765817ce5910 |  | note | SUPERVISOR - R
label | ff9fd93c-31ea-5718-a103-a3845f168484 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Prepare Foundation
label | cc06c871-f082-58fb-998a-eb81d522ff0c |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | cce12e26-88a9-5bba-9a4a-a3b82aee0668 |  | note | Accept / Reject Criteria - As per specification
label | 2518a5f6-f771-5ff2-876a-5916d5a8b0bd |  | note | Frequency Of Inspection Or Test - In-process
label | 722448a0-f0dc-5e5b-bc28-218d15888129 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP087
label | 8283466e-efa3-508d-be5a-d063a3486fd6 |  | note | Records Required - NO
label | 087fdfd9-d0b2-5a49-8f05-d57099d4c4f3 |  | note | ENGINEER - W(10%)
label | 1e135ec7-81d7-570f-88a7-16051fa34e43 |  | note | SUPERVISOR - R
label | d4bb0784-a622-5f9a-98a7-1b72e7340f27 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Prepare Wire Basket
label | 9bd083b3-80da-57a2-8c44-49bf637747d9 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | da90e7f7-173d-5ae6-9bc7-c56305f28a56 |  | note | Accept / Reject Criteria - As per specification
label | f0972320-cb2c-51f3-87fe-4002773e8664 |  | note | Frequency Of Inspection Or Test - In-process
label | 3f88f173-529d-5e6e-8fdf-f17afd4e73dc |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP087
label | f04953ce-e253-5a73-863a-08fbf2f32a69 |  | note | Records Required - NO
label | fd3fea5a-834c-54f9-8840-2c6d33fd599a |  | note | ENGINEER - W(10%)
label | ad727183-800e-5172-9023-6ff3eb48f822 |  | note | SUPERVISOR - R
label | 9e3d1a65-28b1-5c52-8784-59738d65eb46 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Filling the Reno Mattress
label | 0429ff93-a6d2-5b80-ae87-2b94489304fe |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 856faaf8-d80f-5840-acfc-36acfba8dd8e |  | note | Accept / Reject Criteria - As per specification
label | a19db417-f232-5b7f-84a7-77176d3e19ed |  | note | Frequency Of Inspection Or Test - In-process
label | 77efeb22-913a-5809-a25b-fc25f6218024 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP087
label | 27e0eca1-283c-5dfa-9b50-0720333a591b |  | note | Records Required - NO
label | ac87a2a3-91f8-53fe-b587-b5ef2c77fab4 |  | note | ENGINEER - W(10%)
label | c1f8ffbd-fd45-565f-b394-0c09e4751fdc |  | note | SUPERVISOR - R
label | fd15697a-3607-5fe7-bf4b-6ad165198f27 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Backfilling
label | cebfb191-6bd8-5dc6-acc3-0349336143b8 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 14f6771b-9dc5-52dd-8302-31f01f2ba949 |  | note | Accept / Reject Criteria - As per specification
label | 146829df-7c58-5423-af33-4c367ce92dbc |  | note | Frequency Of Inspection Or Test - In-process
label | 78ce2d46-0bf1-51f9-ac63-13fcdb0d7943 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP087
label | 85b42a9a-8671-5b67-97d8-161af1bfc044 |  | note | Records Required - NO
label | f07a3fce-c805-5104-84e8-79d82230fdb0 |  | note | ENGINEER - W(10%)
label | 678f26d2-10a8-584d-a9a0-18d4a714bbed |  | note | SUPERVISOR - R
label | 9c5ac066-3336-5964-9838-627c5a5257b5 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Test and Check
label | 4fbfa634-6e5f-5f1a-ba82-26373aedaf9a |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | b4daa51d-d0e2-5765-b9dc-a66cae03ecdb |  | note | Accept / Reject Criteria - As per specification
label | 99663dc8-2445-5071-89eb-cd668379193d |  | note | Frequency Of Inspection Or Test - In-process
label | 84f83241-e904-5587-ad5e-d366e7423210 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP087
label | a3abfeb2-847f-5d03-8d0c-b2999973d1e5 |  | note | Records Required - YES
label | f924db8d-c439-543c-b198-91bc136c2a63 |  | note | ENGINEER - W(10%)
label | cb3ad38e-406e-5b74-bdfc-9026147a52d4 |  | note | SUPERVISOR - R
label | f8ae1228-d664-564e-9ae1-ee5bdc9a9d4b |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - Ravendwon - Thin Asphalt Paving |  |  |  |  | Yes | ITP - Ravendwon - Thin Asphalt Paving | 3ca14a67-001e-46b1-8573-ade578384eb8
checkpoint-group |  |  | section | 1 - Preliminary and General
checkpoint-status |  |  | checkpoint | 1.1 - Construction Programme Completion
label | 55e9af48-0a25-5a71-b962-f7b8f35570c6 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 0d181604-1608-5c54-a5fa-83cd5d71912c |  | note | METHODS OR REFERENCE - Best Practice Contract Specific MMP
label | d44504d1-6e5e-5e91-9184-93081482dfbd |  | note | FREQ. - Before work commences
label | 38038a6b-de50-590c-bef5-ce888e72bcb0 |  | note | ACCEPTANCE CRITERIA - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date.
label | b6f52a63-7234-53f7-8a53-d5e5b9b35863 |  | note | INSPECTORATE W/H - Type: - W
label | cc77ddf9-80cc-5636-98bb-0b712c0e6ed5 |  | note | Responsible Person - Renewals Manager
checkpoint-status |  |  | checkpoint | 1.2 - Approved RQP
label | 6cbf6a72-632c-5361-bdb4-33ffec17db3c |  | note | VERIFICATION ACTIVITY - Confirmation
label | 8a16b51c-4fe4-571c-a98e-c1e365bf177e |  | note | METHODS OR REFERENCE - Contract Specification
label | 16be31e1-829f-5d92-ae1a-0dc54607eec2 |  | note | FREQ. - Before work commences
label | 1d540b99-97ad-5202-80d6-191d195b50be |  | note | ACCEPTANCE CRITERIA - Principal Acceptance according to guidelines in appendix 6.3
label | d94f025d-20b8-5cfc-a1a4-548a0dd0b2ed |  | note | INSPECTORATE W/H - Type: - H
label | 8cadcb51-010b-5fd8-9bf9-9f86fde6d654 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. NZTA to approve
label | e84bad3b-7754-573d-8731-2c152302e0b3 |  | note | Responsible Person - Renewals Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Traffic Management - TMP
label | c85c185b-7832-5a2f-9574-b3a3d7a94dc0 |  | note | VERIFICATION ACTIVITY - Visual check
label | 663ab78f-3885-590d-b55c-8531fda451af |  | note | METHODS OR REFERENCE - CoPTTM
label | 1d5f1fae-812a-5833-9942-91f9242c4862 |  | note | FREQ. - Before traffic management set up
label | ae834cbe-9c39-5ab1-8af9-51d0361f965b |  | note | ACCEPTANCE CRITERIA - TMP checked and approved Plans approved Current EED (if applicable)
label | ac7b4592-6da5-55fc-8e5d-10888061d38c |  | note | INSPECTORATE W/H - Type: - H
label | dd8aa6e7-ca26-56cb-a16d-f4b3fb02365d |  | note | INSPECTORATE W/H - Description: - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | 0ccfa185-75e8-574f-91a2-292b910f8097 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Mix Design Verification for all mixes Check Laydown Trials are complete and compliant
label | d5deb1cf-db07-54b2-b501-17cd9b7c05ca |  | note | VERIFICATION ACTIVITY - Confirmation
label | 623894c0-93cd-55cb-b309-bb1f70a251c5 |  | note | METHODS OR REFERENCE - NZTA M/10, P/11, P23
label | 694eff2d-e152-5cb6-99ed-6371756e1f17 |  | note | FREQ. - Before planning commences
label | ff5a2604-8760-5b4b-80d9-c2c0ce9dbdfa |  | note | ACCEPTANCE CRITERIA - Mix Design compliant, current and relevant. Batching plant production capability is confirmed
label | 0fd47778-57c2-5076-b2f2-154bc46ec8f6 |  | note | INSPECTORATE W/H - Type: - H
label | 1363c4d3-025a-5201-8ea8-ddd14e65ecb5 |  | note | INSPECTORATE W/H - Description: - Hold point - No planning of on-site works shall commenced until the mix design is verified.
label | a0d8fce8-8e93-5e54-9166-a17216a82a3b |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Notification of intention to start work
label | e8e0a8b6-4b8f-5582-b8a9-78d309513a44 |  | note | VERIFICATION ACTIVITY - Notification
label | 6788e62d-ef80-5762-aef0-d6d2b67102cb |  | note | FREQ. - Before work commences
label | 52e00308-5076-5859-8601-c617a370dfd6 |  | note | ACCEPTANCE CRITERIA - Letter drop to local residents. Greater consultation where required
label | cab2ee45-c397-5066-b761-4232ad67a555 |  | note | INSPECTORATE W/H - Type: - H
label | 8119abab-da55-5b82-ab00-c1dfae236d12 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | 53cc5661-a129-5c2e-a93e-bd1fc58d678f |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Works Extents
label | 8f548ecc-0859-50b6-8d09-27b057eef314 |  | note | VERIFICATION ACTIVITY - Confirmation
label | aaf67aed-dead-5877-994b-58f68a4f796a |  | note | METHODS OR REFERENCE - Site Visit
label | a785ac81-0725-5c5b-b5b2-b5c748dd7c83 |  | note | FREQ. - Before work commences
label | 8e06ef61-8da8-585a-85bf-5486d07d43d9 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and/or Client to agree extents of project
label | 68097cfd-d885-592b-9963-2df9bed2d6f5 |  | note | INSPECTORATE W/H - Type: - H
label | 425c1e50-70c8-532a-8cd8-978a4a65f559 |  | note | INSPECTORATE W/H - Description: - Hold point - Walk over site with Renewals Engineer and/or Renewals Manager and/or NZTA
label | b5432856-1243-5d0b-b9ad-571878024352 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - Pavement Marking Records
label | 628de5ea-ae78-5390-bc68-2fb9e2dad035 |  | note | VERIFICATION ACTIVITY - Measurment Data
label | 917be1f0-4eb8-5dc5-97e2-12b03ba3355f |  | note | METHODS OR REFERENCE - Site Measure or Video Viewer
label | 8040d6b1-4816-551b-a6bc-e8e5aef01606 |  | note | FREQ. - Before work commences
label | d0b198d0-03ab-52d9-a63e-abe5fee39cdc |  | note | ACCEPTANCE CRITERIA - Measure existing markings to aid reinstatement
label | 26f0779b-61d6-53b2-ba1b-def1215f16be |  | note | INSPECTORATE W/H - Type: - H
label | 7f920f4c-0d92-56d4-9f90-4b9fdcfb6275 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | d7d8d9b8-af4f-5291-9d48-e5d9e9492f45 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Milling and Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | 28da5ee3-10c1-5c73-89ae-6db0e2ed3f2d |  | note | VERIFICATION ACTIVITY - Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth)
label | aba20c04-aa16-545a-ac2f-4dede5d3fada |  | note | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | 7ab86011-7634-575b-8722-d72013888b7d |  | note | FREQ. - Before work commences
label | 984cddee-783f-58e8-a5c1-86464ab522ab |  | note | ACCEPTANCE CRITERIA - Zero service strikes
label | 002e9d6d-72fa-5826-be1b-c4c327fd66c7 |  | note | INSPECTORATE W/H - Type: - H
label | 35930e22-a3f4-54e2-88b8-ed412a03b31e |  | note | INSPECTORATE W/H - Description: - Hold point - No excavation/milling is to be commenced until services are located and accounted for
label | ae28985c-03fa-5625-9b73-9a4c703f34f3 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Stormwater Management
label | df78eaca-aecb-5d72-aeb3-ab22d2ecaed3 |  | note | VERIFICATION ACTIVITY - Visual check
label | a85765b0-b52d-550b-9609-716eaaeeeb70 |  | note | METHODS OR REFERENCE - On Site
label | 14e49b72-abc5-5093-9a15-e9e9b834f5cf |  | note | FREQ. - Before work commences
label | f530b4b1-19e2-5080-9061-acc7eda54609 |  | note | ACCEPTANCE CRITERIA - Mudtanks bunded or filtered to prevent mix from dropping in or runoff entering
label | 22c1a64d-f470-5bf6-a4bc-404d94d67c4c |  | note | INSPECTORATE W/H - Type: - H
label | b0cdb171-c2bb-5e6d-927f-fef4deaf61bf |  | note | INSPECTORATE W/H - Description: - Hold point - No work to be commenced until protections in place
label | b452482e-5fa7-5e11-8a9d-941c54c14bd4 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Traffic Management - Setup
label | f0193dcf-6240-57da-86f3-e342d493a135 |  | note | VERIFICATION ACTIVITY - Visual check
label | e943d67c-e7c7-53a6-994b-e7bda322d2d2 |  | note | METHODS OR REFERENCE - Traffic Management Plan
label | dc717068-75eb-59f8-ad51-6dcf9213cb00 |  | note | FREQ. - Before work commences each day
label | b4425b3d-68d3-58f6-b40f-bff8ac6ef6d0 |  | note | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | c6cc514f-4ec8-5f0d-b35a-a4bdae021263 |  | note | INSPECTORATE W/H - Type: - H
label | aa67f0e6-618b-5b70-a90d-6c1c349c7321 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | de69ba3d-15eb-50e5-8eb8-47d09d0ea5ef |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Milling Depths
label | 4f8e924a-41b6-5c61-a57a-6a0a11e7be82 |  | note | VERIFICATION ACTIVITY - Measurement
label | 1f7cb1bc-0290-5285-bf68-8367f644a6e6 |  | note | METHODS OR REFERENCE - On Site
label | 09d24b8c-6b00-51fd-a332-62205fe8d685 |  | note | FREQ. - Measure each side of milling machine cut
label | e43f1f19-01f8-5749-a007-1c7bf2d4e732 |  | note | ACCEPTANCE CRITERIA - Every 10m. Depth matches target
label | e1bbf306-4b36-575f-b074-370ec61b9c6f |  | note | INSPECTORATE W/H - Type: - H
label | c64454ab-c365-56d4-91b5-39911754813f |  | note | Responsible Person - Site Foreperson / QA
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Service Covers Preparation
label | 18436f2a-966e-5d6f-98f7-f8f199a128c1 |  | note | VERIFICATION ACTIVITY - Visual
label | f1033ebd-5cf3-583c-a089-647f9a73b9f2 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | eb1fde4b-7c01-5b83-954c-9922de670c0b |  | note | FREQ. - All Covers
label | abb4b890-e178-5308-a858-f2385acb9166 |  | note | ACCEPTANCE CRITERIA - Hand excavation around ironwork and adjustment to desired level (if required)
label | da8f87b4-2e6a-5b91-85c4-c73d6485a185 |  | note | INSPECTORATE W/H - Type: - H
label | 43725da7-5532-5055-be74-7a212bb57617 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Additional Surfacing Preparation
label | c794a427-c05d-50a4-ad72-f1a20a11e6c9 |  | note | Side Roads; Accesses; Driveways; Dish Channels; High Shoulders
label | 72c4a41c-8051-51b0-b587-be9539a9c3eb |  | note | VERIFICATION ACTIVITY - Visual Check
label | f0540536-7fe2-5e87-a027-cdbc5e8d6d0a |  | note | METHODS OR REFERENCE - Per Design
label | 6fd4463d-164e-5931-99ba-77b51eb9232c |  | note | FREQ. - Before Membraning and Paving
label | f4246110-1650-5c5c-876a-aab0dd7f36ac |  | note | ACCEPTANCE CRITERIA - Have all areas of additional surfacing on the design been prepared, membraned and marked for paving?
label | 10ae6476-f03a-5b56-9bcc-db12d058f891 |  | note | INSPECTORATE W/H - Type: - H
label | 298a168e-a7d5-50fb-81b7-b9dd21019f89 |  | note | INSPECTORATE W/H - Description: - Hold Point – All areas planned for AC are prepared ready for surfacing layer
label | fc602bed-33ef-5b25-8df3-05e8fd37171f |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Over-Milling
label | 735a54d1-5048-5168-836c-c952f3f62563 |  | note | VERIFICATION ACTIVITY - Measurement
label | c73d058d-eafd-50c1-9b95-30b39bf7e671 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 00a79efa-05d9-5182-9390-62e29a0e4136 |  | note | FREQ. - Prior to pre-level
label | b5b7be8f-fdef-583a-84af-7d18dfc32686 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree need and extent of over-milling and infill.
label | a6e2a8a5-376a-5d5b-b302-8ec94e91b95b |  | note | INSPECTORATE W/H - Type: - H
label | bce8d3e0-04ae-5ba8-8456-485db6b34ce8 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Pre-Level
label | 388f5318-47fb-52ce-bc3b-91c0e54cd654 |  | note | VERIFICATION ACTIVITY - Measurement
label | fcca9386-3cdd-5821-bdf9-1b8ec3c39b50 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | d089d173-69d9-5bd7-b29f-bf1944153c07 |  | note | FREQ. - Prior to surfacing
label | 4f2a722c-9f20-5eb3-bb3d-4d16b7d63f40 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree pre-level extents
label | 2c21bfe2-040e-5205-bb9c-af827c4c5376 |  | note | INSPECTORATE W/H - Type: - H
label | 94a1532a-a29b-54b1-859e-861a3deaa22e |  | note | INSPECTORATE W/H - Description: - Hold point - Inspection and agreement by NZTA
label | 8153d850-b78a-5685-a2f7-a42420a9a753 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.9 - Membrane Sealing
label | f376b272-4455-507f-906c-e58be5e547f1 |  | note | VERIFICATION ACTIVITY - Visual
label | f4af48d7-bafb-5852-9c0a-2ad1fd353186 |  | note | METHODS OR REFERENCE - On Site
label | c68a37a4-507c-57e4-b1ec-cd6d95d07d8a |  | note | FREQ. - Prior to surfacing
label | 83a6feac-9d92-51cd-a8aa-1b536c99e29e |  | note | ACCEPTANCE CRITERIA - Membrane seal meets design and extent. Sealing Docket record kept
label | 17988b97-eb95-5e75-b2bf-f831a0820b8d |  | note | INSPECTORATE W/H - Type: - H
label | c6b9d74d-1961-5972-afa5-66fceaaefb34 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Paving Structural
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | 650f86d8-48d9-51eb-bfec-e92ddfe4ce95 |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | 75bf15de-3c12-59c8-a665-cb2159fabe1a |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | 7e01cc5a-c960-5869-b600-e6d320fa59ff |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | cd141f09-f76b-5f72-afd1-574e1c3c5492 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | aa7cb8c2-75be-546e-bf65-da28026ddedb |  | note | INSPECTORATE W/H - Type: - W
label | 0bc59495-2ae4-55cb-8692-d3a61185be1d |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 37ec56aa-2809-52de-9480-ded2b21c284e |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | 25685b3d-f163-5517-8e56-972e83367db2 |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | 3b31748d-341b-5839-9e02-5031dd011de9 |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | 8a745550-a0fd-523f-85f5-b0c0b9a2f04a |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | f5421695-4ddf-5c6a-acdd-68d1892f27e4 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 5a55ebc2-7e33-533e-8a33-19bf8b6970f3 |  | note | INSPECTORATE W/H - Type: - W
label | 917f8f04-1c30-55dd-8b65-f9fe0f60719e |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 72219b52-2e5e-5614-bd52-e421c88b540a |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | 66d4993a-b347-5657-ab9a-cc501fcc08f9 |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | 593ad8d5-7ee5-562f-9b2d-520685255415 |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | d93f9f00-b814-570a-9c8b-5c94d13750f3 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | d8201050-cd5f-5c0a-8e65-ddfece5f1c5d |  | note | INSPECTORATE W/H - Type: - W
label | 686fd92b-2348-5d07-bec7-f9ab13ff8d1c |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | abcaee2e-9bb7-59da-90b7-60c36e87aadc |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | 21951be2-bea0-5fdc-ba65-2c81ef9eb74c |  | note | VERIFICATION ACTIVITY - Visual
label | 6543add0-1e28-56fe-9b7b-6f1830645954 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 0770fde2-09db-5b1c-9571-620eda295e9d |  | note | FREQ. - Prior to Shift
label | 6290e6f5-75a2-5be4-9878-f731a5beeef7 |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | a9d67bf3-b8fe-505c-b3b7-ad661b6da8cb |  | note | INSPECTORATE W/H - Type: - W
label | 6d12f7cb-a4ce-5b91-9609-449ddd0bee72 |  | note | INSPECTORATE W/H - Description: - Paving Plan and Crew Briefing Plan completed prior
label | d7962300-455f-5316-80ad-e4c690ada0e3 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | 5fb8c59e-1a64-54cf-bd27-12e042506741 |  | note | VERIFICATION ACTIVITY - Visual
label | aae0f6b9-6329-5189-baeb-1e732e8338ed |  | note | METHODS OR REFERENCE - NZTA M/10
label | 511e9145-6da9-5125-9452-427100496da5 |  | note | FREQ. - Prior to Shift
label | d5a7b346-ea4e-5bd7-bceb-760d9d0a608d |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | b4dce6a7-8ab3-5058-b8e9-0b15afa479cb |  | note | INSPECTORATE W/H - Type: - W
label | 76416869-e0c8-5340-bb1a-f5fc12837f40 |  | note | Responsible Person - Paving Supervisor / QA Engineer
checkpoint-status |  |  | checkpoint | 3.4 - Mix Inconsistency and Deficiency
label | 2bc50c5b-3115-5922-930e-b15890339e04 |  | note | VERIFICATION ACTIVITY - Visual
label | 601a40e8-4888-5b0a-9f28-590b40e5e4a8 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 54695906-883f-597a-bbc3-11c9642cd96e |  | note | FREQ. - Continuous
label | c4214898-5b8e-5549-a369-774772ebc62c |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | db8b97a4-aacb-5415-afac-dfbd1488a68a |  | note | INSPECTORATE W/H - Type: - H
label | 0ea7e77e-a92c-5e59-a010-d02dbf38d13f |  | note | Responsible Person - Site Foreperson / QA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Load Locate
label | a08f6340-0c3e-5f49-ace1-c0343d28864f |  | note | VERIFICATION ACTIVITY - Measurement
label | 5eef14bc-ff89-5532-93c6-44fd7c31a2eb |  | note | FREQ. - Every Load
label | a8351cd9-11c2-5ca1-91c9-3fb203f7ee88 |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
label | 53618648-72af-57ba-8af4-33c4895ae91d |  | note | INSPECTORATE W/H - Type: - W
label | 96ff8a44-18af-5585-91b5-8b6d4c1b0478 |  | note | INSPECTORATE W/H - Description: - Per standard practice
label | 1616098e-e28f-5b44-8aec-3a1b907ba95b |  | note | Responsible Person - Quality Assurance Engineer
checkpoint-status |  |  | checkpoint | 3.6 - Laying Temperature
label | 801c281a-ffdb-5cd0-acca-62945260d2d7 |  | note | VERIFICATION ACTIVITY - Confirmation
label | a5c084fb-870b-5abd-b5e6-cc8a2992cb37 |  | note | METHODS OR REFERENCE - NZTA M/10
label | e5de5f66-a7c3-5fc3-842a-9a5ab8bb28a3 |  | note | FREQ. - Every Load
label | 4a03e2f2-96c1-57e9-b56f-a28875bac825 |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | fcf34d43-ca39-50e5-9584-f0fb49b62fe3 |  | note | INSPECTORATE W/H - Type: - H
label | e71c2ce2-35f5-52d5-9275-e646f2e31fbf |  | note | INSPECTORATE W/H - Description: - Hold point - Reject mix for non-compliant temperatures.
label | 7d49f0bf-8f4b-54e9-9bc3-1e912d3855b1 |  | note | Responsible Person - Quality Assurance Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Compaction
label | 78ae3150-c587-543a-90fa-88df62c3c96b |  | note | VERIFICATION ACTIVITY - NDM Testing
label | 597b67b9-a3d5-5aed-a985-e8ead64a6d4b |  | note | METHODS OR REFERENCE - NZTA M/10
label | 8a7ec5f9-808a-5899-a28f-81298d3d02fc |  | note | FREQ. - Minimum: 1 Test per 300m² within Mat. 1 Test per 100m of joint.
label | eee99d4a-3a20-58ed-be54-77aadd13e7cd |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | fd54b97a-567f-550b-bdfe-4d2d8b966119 |  | note | INSPECTORATE W/H - Type: - H
label | e122e668-c9c6-589b-9944-c5a8acff6766 |  | note | INSPECTORATE W/H - Description: - Hold Point - No Wearing course paved until any non-compliance is sorted
label | edb498c2-ff47-5a13-9fee-d8d5d51250cc |  | note | Responsible Person - Quality Assurance Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Roughness
label | b412d2bb-e3ce-5ab8-aba6-3532ec543e36 |  | note | VERIFICATION ACTIVITY - NASSRA Testing
label | c33d1d76-21a7-5545-a669-2d3006051f5a |  | note | METHODS OR REFERENCE - Contract Specification
label | 421ff490-c735-52f5-b3c1-6a294dae655c |  | note | FREQ. - post construction
label | aa45704d-b437-5dc2-805f-d93f6ff75479 |  | note | ACCEPTANCE CRITERIA - NASSRA rolling meter average under 60, max of 70
label | 0b97a106-ff90-5465-8043-fc5974050ae1 |  | note | INSPECTORATE W/H - Type: - H
label | b53bfbe5-eaf8-5fc3-8e4c-9f237ef2702d |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Paving Wearing Course
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | cf23ce8c-b5c8-507e-afe1-4ec26f2e0c8b |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | cc6c5b13-4133-5ef6-8208-43c78f52e40d |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | 6f368b39-f90e-59dd-99dd-f804bc87c835 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 193aebde-a1fb-5719-bd92-309566a06d7c |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | db50e3b3-7b7b-5871-b1b9-8021123397f9 |  | note | INSPECTORATE W/H - Type: - W
label | 11264f68-71a6-57b0-9dae-f618b052d842 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 369ac8d2-3129-59c8-80f8-f4db35c46d3d |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | f546066b-f81d-5cef-a6a6-e313ae58bf21 |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | e24a8efe-b242-5cb7-8779-8b01bf9479d4 |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | 19ed3f80-c948-50b6-9d28-3d004e0d1024 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | adf75938-9cae-50b5-8b0d-e23c2e728d80 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | e4e63186-448c-5ba3-97e2-748263eee1ac |  | note | INSPECTORATE W/H - Type: - W
label | 14df608a-b9fe-5104-b2b2-77bf1e295080 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 048a3c8f-bd93-52e1-a4c6-36abca4b68ac |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | 8cefc3dc-49a2-5db5-9b1a-4c2509beecba |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | b0f6be11-5a2c-5c8e-87f3-457d083d6158 |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | 4ec9f8c3-f91a-5d1f-8394-bb531c8c06be |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | d7aaa5fb-1976-5174-beb4-af12e5a3e1b1 |  | note | ACCEPTANCE CRITERIA - Per Mix design
label | a8cf9234-7c4a-57e9-8fca-4673d6f88463 |  | note | INSPECTORATE W/H - Type: - W
label | 7471e926-7760-5037-ab1c-cc30d55fc015 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 47038896-bc49-5a77-917a-52fdb1d2b985 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | cc35dd3a-fe5f-585f-9826-532c993bf79e |  | note | VERIFICATION ACTIVITY - Visual
label | 7b7e714c-a211-5c6e-b59c-0979675a4849 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 33992129-3e5e-5e97-8c8a-1b87fa6e6a14 |  | note | FREQ. - Prior to Shift
label | dc0b5856-fc65-5c8a-9226-2a6b2a6a5721 |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | 91f26547-09fb-58a9-902e-0f24e25b9b43 |  | note | INSPECTORATE W/H - Type: - W
label | e4520c50-ff07-5d83-9bdd-6b23b09fd967 |  | note | INSPECTORATE W/H - Description: - Paving Plan and Crew Briefing Plan completed prior
label | e5810670-a423-5af5-97ad-5a8f2897a77d |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | ebf59fac-3b5e-5cbe-b13c-81c529f40b0c |  | note | VERIFICATION ACTIVITY - Visual
label | e1a26171-44dc-512e-87e3-ead36bda421b |  | note | METHODS OR REFERENCE - NZTA M/10
label | d2637896-27bb-51f4-bf3d-6ef568e46b15 |  | note | FREQ. - Prior to Shift
label | 90dfbf21-b10f-5c7f-a6f5-2ed8ec975a9e |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | 3787c4a2-921b-5d56-9799-6e0db8769042 |  | note | INSPECTORATE W/H - Type: - W
label | 68b3d942-7d06-525f-82e0-ecfc92668720 |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.4 - Grade 3 Membrane Sealing
label | f5a12a4c-e989-56de-bb96-b6192ac217f6 |  | note | VERIFICATION ACTIVITY - Visual
label | e297723f-51d9-572f-9acf-1a1ff6320aa5 |  | note | METHODS OR REFERENCE - NZTA M/10
label | c0abcbc5-d9e6-52cc-9b85-42a10ab5ee07 |  | note | FREQ. - Prior to Paving
label | 2897f91e-93a6-5322-8fda-cec561dfdcb6 |  | note | ACCEPTANCE CRITERIA - Applied 2.0l/m² residual
label | 089d14ef-5d2e-5e5c-96b6-6781f5d318a7 |  | note | INSPECTORATE W/H - Type: - H
label | 2aeb14c9-3f2f-5a41-94ef-214c19db798d |  | note | INSPECTORATE W/H - Description: - Hold Point - No paving until Membrane Done.
label | 1c81617e-58a9-585f-a0af-d1a7caf7c251 |  | note | Responsible Person - Paving Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Mix Inconsistency and Deficiency
label | 037fa937-891e-5ea1-8247-f6ed005dd747 |  | note | VERIFICATION ACTIVITY - Visual
label | d4c9d000-a9dd-571f-80c4-e5714ef215a5 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 63d58f6b-fc87-5378-8345-b8a10d0dd23d |  | note | FREQ. - Continuous
label | 0b339337-aa42-5277-a416-48f07bf0b235 |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | 46c584d5-ceee-5183-b053-3d7609492159 |  | note | INSPECTORATE W/H - Type: - H
label | e7e81350-b415-5742-9139-75f102d7e51a |  | note | Responsible Person - Site Foreperson / QA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Load Locate
label | d1201d0f-da2a-5419-9a7a-eadac09aa996 |  | note | VERIFICATION ACTIVITY - Measurement
label | d6cf57d3-5d7b-533f-89fe-3714e4a31692 |  | note | FREQ. - Every Load
label | 68e82a6d-ea41-5b9b-bcfd-94a0849ce842 |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
label | 8a191476-6cc8-587f-8941-b28afa42d855 |  | note | INSPECTORATE W/H - Type: - W
label | 89cc41de-b5cc-5471-b7e7-5b066ebe07e6 |  | note | INSPECTORATE W/H - Description: - Per standard practice
label | cf0ce6c5-35e5-50a1-ba62-ba8d6cf3f38e |  | note | Responsible Person - Quality Assurance Technician.
checkpoint-status |  |  | checkpoint | 3.7 - Laying Temperature
label | e89fea1c-b08e-5e1c-8f58-b4f88b90351f |  | note | VERIFICATION ACTIVITY - Confirmation
label | 2d756d17-2157-575c-b696-b4593d918251 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 9b97fa0e-a1d4-5a41-882e-a5328648f9a9 |  | note | FREQ. - Every Load
label | 095a6a7d-adea-5fad-ba2c-0b91868d5806 |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | 89792b85-950c-5c60-935d-33bdf0bce21c |  | note | INSPECTORATE W/H - Type: - H
label | c54abc81-2107-527f-bdea-1add35168279 |  | note | INSPECTORATE W/H - Description: - Hold point - Reject mix for non-compliant temperatures.
label | 1bfa07a4-6e05-5a0e-b622-7fdbb836f64a |  | note | Responsible Person - Quality Assurance Technician
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Compaction
label | 5c1d3b2b-c515-5669-abf3-e20887fb0fc7 |  | note | VERIFICATION ACTIVITY - PQI Non-Nuclear Gauge/Cores. Or Non Distrctive Method Testing.
label | 46db51e3-1f4c-54fa-9f6d-2f0b164a8f6e |  | note | METHODS OR REFERENCE - NZTA M/10
label | 26c93c13-33c0-5a1a-ab4f-892c9da75f6a |  | note | FREQ. - Minimum: 1 Test per 300m² within Mat. 1 Test per 100m of joint. Minimum 8 cores on Mat and 3 on Joints as Per M10:2020.
label | 8e33e350-ae98-52d5-ac51-239a38326176 |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | d2330f61-d5f8-5586-a235-52df52db05ef |  | note | INSPECTORATE W/H - Type: - W
label | 202096c3-cbc1-5b25-8097-c750b33d22cf |  | note | Responsible Person - Quality Assurance Technician
checkpoint-group |  |  | section | 4 - Site Reinstatement / Clearance
checkpoint-status |  |  | checkpoint | 4.1 - Post-seal Area Check
label | 7c95170b-9af9-55a0-8069-8bbe6f1bb367 |  | note | VERIFICATION ACTIVITY - Measurement
label | 951bbe7f-833b-528b-9fd7-9837561cb87e |  | note | METHODS OR REFERENCE - On Site tape-measure
label | e9a7a542-0a91-5b71-91f4-b09ed7dcf5d1 |  | note | FREQ. - After Surfacing
label | 1c161b32-dfd5-58f2-9700-89890fc03540 |  | note | ACCEPTANCE CRITERIA - Check sealed area meets design
label | db681860-9403-53cf-9f89-fbd81b45183a |  | note | INSPECTORATE W/H - Type: - W
label | 0d5bf555-5644-5f62-b1b7-d0d87a168c72 |  | note | INSPECTORATE W/H - Description: - Notify Renewals Engineer or Renewals Manager
label | 8d4afc29-1aad-54e6-821c-8dd160256961 |  | note | Responsible Person - QA Engineer
checkpoint-status |  |  | checkpoint | 5.3 - Service Covers
label | c0220bd0-3ff4-553a-8dfe-00ac81d3803f |  | note | VERIFICATION ACTIVITY - Measurement/Visual
label | 2b1bf4a4-44ab-5c5a-90b2-ff0a09d0dbf3 |  | note | METHODS OR REFERENCE - On Site
label | 5757557f-8384-5510-8e63-9c06be8af4e5 |  | note | FREQ. - After Surfacing
label | e49f82ce-2e20-5e1d-8806-bd48decd1d59 |  | note | ACCEPTANCE CRITERIA - All service covers are checked and adjusted (if necessary) to finished level
label | ea38bb64-0541-5240-b4cc-bba5ac88a87f |  | note | INSPECTORATE W/H - Type: - W
label | 997c1750-e4b8-551f-b257-f69e2e81f0d0 |  | note | Responsible Person - Paving Supervisor / Foreman
checkpoint-status |  |  | checkpoint | 5.4 - Joint Sealing
label | 2b6e1755-6cc1-5897-adb1-b74c24aa94f7 |  | note | VERIFICATION ACTIVITY - Visual
label | 2850a229-66d3-5f04-8e37-b71cf3663f24 |  | note | METHODS OR REFERENCE - On Site
label | de001bee-49ec-5b6a-8975-bff5c3a382a9 |  | note | FREQ. - After Surfacing
label | 367d91af-93c5-5f9b-a18a-67e0d5023bcb |  | note | ACCEPTANCE CRITERIA - Check cold joints are bandage sealed
label | a495660f-1428-5225-803f-775c60ed2238 |  | note | INSPECTORATE W/H - Type: - W
label | 701c1bee-d29d-5019-973b-cb68bef04b6e |  | note | Responsible Person - Paving Supervisor / Foreman
checkpoint-status |  |  | checkpoint | 4.2 - Road Marking
label | e62d6600-ec4b-5ea4-9676-352b5c0df912 |  | note | VERIFICATION ACTIVITY - MOTSAM
label | 73494be7-1d22-5b3b-9df5-ab582985217f |  | note | METHODS OR REFERENCE - Visual inspection
label | a4a74486-40f0-5bac-b425-5beedd755970 |  | note | FREQ. - All markings
label | 87a9e6c4-978e-5614-8f65-1119f93c89cd |  | note | ACCEPTANCE CRITERIA - Replaced in same position, or per design
label | ae3182e4-1cfe-5a2c-8931-7c98e28c2c3f |  | note | INSPECTORATE W/H - Type: - H
label | b97e38a2-4caa-53d9-91a6-45f0b53205c9 |  | note | INSPECTORATE W/H - Description: - Hold point – Site TTM cannot be removed until markings reinstated
label | 3333c3ba-a16f-532f-af5b-9463017095a0 |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 - Other Traffic Services - Marker pegs/ Signs/Markings/RRPMs Replaced
label | ae7b4fcb-1fde-5410-9a57-aaab15051c34 |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | c00b9971-d6f0-5855-9200-744b75ff8d6a |  | note | METHODS OR REFERENCE - Visual inspection
label | 1f365431-f7b0-5819-aa4f-b28c16ff781b |  | note | FREQ. - All signs/markers
label | b681bd5e-1681-517f-be9f-1d4be566e773 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | 8d7211f1-34e7-5a8d-a8b5-d399c164c2c7 |  | note | INSPECTORATE W/H - Type: - H
label | bdeedf32-e94c-50a3-b888-849195b53e3e |  | note | INSPECTORATE W/H - Description: - Hold point – Site TTM cannot be removed until marker pegs, signs, markings and RRPMs reinstated
label | a3bbe038-c165-524d-8e35-1eade9c4d952 |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Stormwater Management Controls removed
label | 819a365e-47f4-52bf-a411-530610c9ba49 |  | note | VERIFICATION ACTIVITY - Visual check
label | 21f3aaae-6904-527f-8455-5c666b2eb7f6 |  | note | FREQ. - All installed measures
label | 6c1f0e91-7ddd-5338-9871-a1b43eced8b6 |  | note | ACCEPTANCE CRITERIA - Installed controls are removed
label | f5346616-5b0e-5124-90d7-5177d8958c7f |  | note | INSPECTORATE W/H - Type: - H
label | f4bdd9d8-d5d7-54ce-bd49-84ab3715fda1 |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Traffic Management Removed
label | 339ad735-9257-5d55-9a11-73e92096f4dc |  | note | VERIFICATION ACTIVITY - Visual check
label | f18f332f-cb64-507d-b580-3a9799acdcdc |  | note | FREQ. - When safe, after all physical works completed
label | 5cf8fa1d-422a-5419-880d-88fa13d88f36 |  | note | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | c0903fbe-e4d1-50f4-99ba-227873b06861 |  | note | INSPECTORATE W/H - Type: - W
label | 2ffe56b2-4818-53c6-8bc3-4c44cb91f85e |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.6 - Site left clean & tidy
label | 05028502-f726-507c-af3f-7cb615e0bbdb |  | note | VERIFICATION ACTIVITY - Visual check
label | 49b26596-2f04-57c8-beb2-cde744188e73 |  | note | FREQ. - After vacating site
label | b1859496-bf0e-5f8a-ad80-60553d13e761 |  | note | ACCEPTANCE CRITERIA - Stockpiles removed; Plant removed; Litter cleared from site
label | 29b9fa2c-7796-5fe9-ae6c-88dbb326c74f |  | note | INSPECTORATE W/H - Type: - W
label | 366787cf-e781-54b8-924b-1b33ab1bd284 |  | note | INSPECTORATE W/H - Description: - Invite NZTA to carry out joint site inspection to inspect site.
label | e140d453-b950-5b8f-91a4-7135dcfe25f6 |  | note | Responsible Person - Paving Supervisor
checkpoint-group |  |  | section | 5 - As Built Records
checkpoint-status |  |  | checkpoint | 5.1 - Collect asset data
label | d16fb025-b8d6-53e9-80ff-5b4703c023d5 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | 19238281-7189-5f9d-bd2d-2dac52e74bd2 |  | note | FREQ. - During construction
label | 21f2b5ee-9562-5d0b-bf1c-59f70cc6acc5 |  | note | ACCEPTANCE CRITERIA - All relevant as built information collected.
label | faad9ebe-ced7-5b20-9fc1-fdf951e4d650 |  | note | INSPECTORATE W/H - Type: - W
label | 15882811-fa43-5d84-8870-6f38737441ea |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.2 - Enter asset data into RAMM and/or register(s)
label | 03b66ba7-8f0d-5547-b679-86d20f7f7290 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | 4dd5e72d-1f7d-5699-bcfa-dd16a988fe7f |  | note | METHODS OR REFERENCE - RAMM
label | 242b04cc-fa0b-5781-a509-99af348eb200 |  | note | FREQ. - At completion of work.
label | 2f3592f1-9a9a-5c4e-862a-b413af3536a2 |  | note | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.
label | 622f5b50-3a50-5c94-b122-e31b2315a199 |  | note | INSPECTORATE W/H - Type: - W
label | f1ee17d9-5f42-5174-a57d-bdd77471dc85 |  | note | INSPECTORATE W/H - Description: - Data entered by 20th of follow month after month of completion
label | a2c26a28-960f-544b-9737-aa18348271ac |  | note | Responsible Person - Asset Information Manager
checkpoint-status |  |  | checkpoint | 5.3 - Construction Completion Report
label | 7d841b64-005b-544c-981d-592ba7f64f63 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 232d6927-2162-5cae-8f0b-c636162b8c36 |  | note | METHODS OR REFERENCE - Contract Specification
label | 86a6690c-229b-578d-a646-0ec79941f2ee |  | note | FREQ. - At completion of work.
label | f8347b20-1f70-5181-b79a-8bab28bc93c5 |  | note | ACCEPTANCE CRITERIA - Checked and approved
label | aa2318b5-fb05-5662-a46b-0d5fdee87f9b |  | note | INSPECTORATE W/H - Type: - W
label | 40c757ff-6b4b-544e-afa6-4a82cf503789 |  | note | INSPECTORATE W/H - Description: - Completed within two months after Paving Wearing Course
label | 544d1764-815d-5bb2-8445-5eec2cb212fa |  | note | Responsible Person - Renewals Engineer/ Renewals Manager
checkpoint-no-status |  |  | checkpoint | Quality Assurance Close Out
text | 31df205e-f5a5-585f-9b02-68234d3777e3 |  | textbox | Quality Assurance Close Out by - Name:
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | ITP - CONOC Operations - Mixing Calcium Magnesium Acetate (CMA) | itp |  |  |  | Yes | ITP - CONOC Operations (General) - Mixing Calcium Magnesium Acetate (CMA) | 3ce951a3-f566-49a2-a849-e4359b8daa9a
checkpoint-status |  |  | checkpoint | 1 - CMA Preparation
label | 57716364-5955-5390-9fe2-fee3dcbc729d |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | b55a7568-6940-5002-aea1-4d89a35cd4a4 |  | note | Accept / Reject Criteria - As per Specification
label | dcedc077-6baa-5e7c-aacc-c2114f745b74 |  | note | Frequency Of Inspection Or Test - In-process
label | 789b7f9e-e27c-5623-972b-1bd80433e5dd |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP108
label | 5d4fa5aa-1346-5c73-92b0-e1b3e27228f7 |  | note | Records Required - NO
label | 26041ebd-6afb-5ced-96a2-4c483122ea9a |  | note | ENGINEER - R
label | 4087473a-5572-5faa-84f8-c989afa352f7 |  | note | SUPERVISOR - R
label | 6906eff1-d972-5088-924c-8f6dade7fabc |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Mixing
label | 955c36e7-cc47-591b-844d-aaa366dd6121 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | fc99213a-71e6-5beb-8bd0-b9ea20031f52 |  | note | Accept / Reject Criteria - As per Specification
label | 6749bae1-99a9-50c2-80ac-42577ba2d0c7 |  | note | Frequency Of Inspection Or Test - In-process
label | d18b165e-e56d-5daa-acf9-2a76d36f33b3 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP108
label | 3c36b2b4-ee22-5070-8aa6-3710e32f1916 |  | note | Records Required - NO
label | 75a35e00-ba7e-5870-9791-e200d5f8837a |  | note | ENGINEER - W(10%)
label | 4a3dcc1a-7193-5186-ae6c-26e03c7e7f15 |  | note | SUPERVISOR - R
label | 18c01c27-981d-5c49-890f-9dc9db881f83 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Decanting
label | cf9308d4-3848-5840-8ce7-603e6a6acc17 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 644f58e9-f172-5d3c-88bb-69f25d5517d4 |  | note | Accept / Reject Criteria - As per Specification
label | 1dc689d3-8bbe-55f3-b307-da4329fb8e83 |  | note | Frequency Of Inspection Or Test - In-process
label | 182c4ec9-f959-5682-99ae-d3e6d672450a |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP108
label | 59658bb9-46a5-5670-8af1-ece7818cfc06 |  | note | Records Required - NO
label | d53abf16-cb3a-5219-b239-d0f6a4fdf5fc |  | note | ENGINEER - W(10%)
label | 8ae27ee7-c3f7-569a-be9a-d028ce9b36b7 |  | note | SUPERVISOR - R
label | 0f1bc803-0df2-572c-a954-a7452057e4e2 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Holding Tank
label | a1b7b5d4-c777-5c0f-a8c9-7bf5828bbdb8 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 52d588fc-ccc1-57ea-9328-29a0ea4ffe24 |  | note | Accept / Reject Criteria - As per Specification
label | f79dc433-4fdd-5588-a192-3ecba44f8ad8 |  | note | Frequency Of Inspection Or Test - In-process
label | f1d5bcb5-32aa-5958-bb2c-2dfd885662f0 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP108
label | 11f0216f-500d-5294-adfb-4b9c46f8c37f |  | note | Records Required - NO
label | c2cfeaaa-142d-5aa6-b855-60fbdce24da8 |  | note | ENGINEER - W(10%)
label | e134a0e3-f03d-5a85-b386-643542c5b2f6 |  | note | SUPERVISOR - R
label | fa16fbf3-0a69-51bc-91a1-50e416940906 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Test and Check
label | 0aa64e3d-c3c3-5a5f-a2b2-5b5df893edfd |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 40459d72-bb54-5b99-a9c6-99a50d739284 |  | note | Accept / Reject Criteria - As per Specification
label | 14e98c81-5ac4-5674-add5-c890fdc53a8c |  | note | Frequency Of Inspection Or Test - In-process
label | 8a1ea30b-de7b-5693-8d35-47b5332291c4 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP108
label | 1a3a4cf8-d8c6-58b4-879d-d95c16e5b206 |  | note | Records Required - YES
label | 0c539514-a4dc-5a10-808b-ed7c1fba0718 |  | note | ENGINEER - W(10%)
label | 967f3457-e369-519e-abfc-f37d01961124 |  | note | SUPERVISOR - R
label | c38d4aff-25ce-5d37-a759-6c74525fd673 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - Severn St - Thin Asphalt Paving |  |  |  |  | Yes | ITP - Severn St - Thin Asphalt Paving | 3eb194ba-ea1c-41d6-8ef8-2f65a0759cec
checkpoint-group |  |  | section | 1 - Preliminary and General
checkpoint-status |  |  | checkpoint | 1.1 - Construction Programme Completion
label | b048ff3d-571d-54c7-a109-ebe690c34c1b |  | note | VERIFICATION ACTIVITY - Confirmation
label | 7a26f0c6-54dd-59b3-9a87-cc639fc1422a |  | note | METHODS OR REFERENCE - Best Practice Contract Specific MMP
label | 785dccce-6c26-5412-8912-9dee3bb94622 |  | note | FREQ. - Before work commences
label | 55fb7e68-d5e9-5f59-a806-5f114e6ade2e |  | note | ACCEPTANCE CRITERIA - Construction Completion will be the lesser of the completion date according to the pavement classification risk profile (documented in the contract specific MMP) or the contract completion date.
label | 1a98b733-4c75-50bf-9679-bb6a5ae866a8 |  | note | INSPECTORATE W/H - Type: - W
label | 0c39c218-2e58-54d0-a62b-74aef9868915 |  | note | Responsible Person - Renewals Manager
checkpoint-status |  |  | checkpoint | 1.2 - Approved RQP
label | b91d8d06-c418-5c10-962d-6deb344f1c47 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 79164f78-71b5-5981-ade9-0364f6c1ccc4 |  | note | METHODS OR REFERENCE - Contract Specification
label | 98a1ed9a-b90f-5874-8627-cebd272b936b |  | note | FREQ. - Before work commences
label | aaae0abd-0860-519b-a768-3f550b421f36 |  | note | ACCEPTANCE CRITERIA - Principal Acceptance according to guidelines in appendix 6.3
label | 4bd627dc-a10a-5318-84f8-79a79fb9ab97 |  | note | INSPECTORATE W/H - Type: - H
label | 26d6d5d2-9c8b-53c1-8498-92d5e947292d |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. NZTA to approve
label | 872bdb73-3117-5b1f-abeb-b04bd2c2d06e |  | note | Responsible Person - Renewals Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Traffic Management - TMP
label | c246b823-75dd-57ad-99a3-159149917f73 |  | note | VERIFICATION ACTIVITY - Visual check
label | 56472599-fdac-5156-96e9-83478306d6d4 |  | note | METHODS OR REFERENCE - CoPTTM
label | f319132e-61c1-50c1-9898-ece03a6ee049 |  | note | FREQ. - Before traffic management set up
label | 2edeb705-da77-5bd2-be98-a33c29b4e238 |  | note | ACCEPTANCE CRITERIA - TMP checked and approved Plans approved Current EED (if applicable)
label | 80dca2bb-fd47-573a-8cd9-8ba560ff1a52 |  | note | INSPECTORATE W/H - Type: - H
label | 7518c9a9-0908-53a7-a659-cb6f9378a619 |  | note | INSPECTORATE W/H - Description: - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | 6511f43e-4d18-5a57-b4e3-2a6bebdff582 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Mix Design Verification for all mixes Check Laydown Trials are complete and compliant
label | ad1b65d9-0e0e-56ef-bc3c-50ff5c5f07a1 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 5af1a068-eaff-5962-9863-69e15969aa1e |  | note | METHODS OR REFERENCE - NZTA M/10, P/11, P23
label | a81e4b5f-5747-5fe8-a9f6-5fb7f5283bfd |  | note | FREQ. - Before planning commences
label | 8dda8cca-1519-5a93-a96e-0d573a8e6331 |  | note | ACCEPTANCE CRITERIA - Mix Design compliant, current and relevant. Batching plant production capability is confirmed
label | 7667a1ce-53f0-513b-856e-144bb7a083e1 |  | note | INSPECTORATE W/H - Type: - H
label | d5fef411-1721-5f4d-8f73-1d082b482503 |  | note | INSPECTORATE W/H - Description: - Hold point - No planning of on-site works shall commenced until the mix design is verified.
label | 5e3161a6-b1c1-5a67-95ae-a50bed7a5a9f |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Notification of intention to start work
label | 4b66d659-a86c-5c19-bf6a-caa6f443d704 |  | note | VERIFICATION ACTIVITY - Notification
label | 39b9467f-721f-5976-9f49-56eabc0b2513 |  | note | FREQ. - Before work commences
label | 7babe528-ef59-5369-bb3d-61fdf9020698 |  | note | ACCEPTANCE CRITERIA - Letter drop to local residents. Greater consultation where required
label | ec5d43ac-980c-5ba8-bdaa-04de449f6896 |  | note | INSPECTORATE W/H - Type: - H
label | 92cc62b5-2b09-5285-bf1f-d155cef369f2 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | 76492246-9684-508c-b93f-3afcdf527159 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Works Extents
label | b9d325be-39f0-5e37-a2ff-5f646cd4384d |  | note | VERIFICATION ACTIVITY - Confirmation
label | b5a681fb-85ab-559f-82d6-9668efc70d7a |  | note | METHODS OR REFERENCE - Site Visit
label | 6834ae4e-0168-530d-b000-0b8c828bcce3 |  | note | FREQ. - Before work commences
label | 29ebd273-1c5e-5f43-b3c9-f93c909eb039 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and/or Client to agree extents of project
label | 709126be-53b9-5826-b7fd-a0dcddcb16bb |  | note | INSPECTORATE W/H - Type: - H
label | f473c8a8-ae0b-5f63-b04c-d55829b8df5d |  | note | INSPECTORATE W/H - Description: - Hold point - Walk over site with Renewals Engineer and/or Renewals Manager and/or NZTA
label | 3545f37f-ffad-5d41-955d-fd75d3ee2d84 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - Pavement Marking Records
label | 8b02921e-2776-5b26-a0cc-fcdb5530ee00 |  | note | VERIFICATION ACTIVITY - Measurement Data
label | 1b561331-4ab1-5c29-b043-6aee006d40ce |  | note | METHODS OR REFERENCE - Site Measure or Video Viewer
label | 33955205-67b0-5ee0-a837-b21e8581eabc |  | note | FREQ. - Before work commences
label | bcf8aa0d-8fc5-5179-ae3d-c95e7b2a71ec |  | note | ACCEPTANCE CRITERIA - Measure existing markings to aid reinstatement
label | 2973cae7-85bc-500e-b420-1e77e932c967 |  | note | INSPECTORATE W/H - Type: - H
label | 383727b8-8fde-5420-ab43-09a8149c25ba |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | 3f8d4656-fe75-5dc8-9505-832f3264ef45 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Milling and Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | 0319d1a5-ffa7-53ee-ab0a-88ea47c3fca0 |  | note | VERIFICATION ACTIVITY - Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth)
label | 72e77e1a-a8dd-5cfd-bf1c-e724af35c697 |  | note | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | 1909d8e9-5bcf-5f74-b345-729f6fdceda8 |  | note | FREQ. - Before work commences
label | 00ba1197-7cb5-53ae-b1a6-01a1cb9fd725 |  | note | ACCEPTANCE CRITERIA - Zero service strikes
label | 61eef8af-073b-5710-8514-e98b85a5d7cd |  | note | INSPECTORATE W/H - Type: - H
label | bb2dea7a-9c8d-5fb9-91ba-7800c8442ca9 |  | note | INSPECTORATE W/H - Description: - Hold point - No excavation/milling is to be commenced until services are located and accounted for
label | 3fd27ca1-f6ec-5caa-ac83-945e25878726 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Stormwater Management
label | 0059ae07-2898-5f4a-b258-a7c86efeadbd |  | note | VERIFICATION ACTIVITY - Visual check
label | be41963a-5573-5ec9-b6d6-b5dfbf1f8a3f |  | note | METHODS OR REFERENCE - On Site
label | d7018d69-ead7-5659-a77c-5bf893826698 |  | note | FREQ. - Before work commences
label | b80a0869-73bb-53c9-8b41-340fddc7301f |  | note | ACCEPTANCE CRITERIA - Mudtanks bunded or filtered to prevent mix from dropping in or runoff entering
label | 1ea421c6-be7e-5eee-8aea-c05d821bf17d |  | note | INSPECTORATE W/H - Type: - H
label | 2f0f68ce-3091-5b10-8d02-d4afe57fc5eb |  | note | INSPECTORATE W/H - Description: - Hold point - No work to be commenced until protections in place
label | 997c3605-261e-5b2c-9742-bf6219186047 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Traffic Management - Setup
label | 430c2310-0c7c-5a01-a945-a7589cbd7fed |  | note | VERIFICATION ACTIVITY - Visual check
label | 47af5982-2321-579e-b966-b09037509e04 |  | note | METHODS OR REFERENCE - Traffic Management Plan
label | e0ec8992-f8f4-540e-89fc-277aa3f18cb1 |  | note | FREQ. - Before work commences each day
label | 74a3d33a-e6b3-56c1-8713-427606685afc |  | note | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | 2c7d3728-bc44-537b-ac01-33a0e900ec53 |  | note | INSPECTORATE W/H - Type: - H
label | ec27889c-68c6-595f-bbf3-d0d3e816d383 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | e02d0f4f-d5ba-5b2d-bf0b-3e4b7d1c8d48 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Milling Depths
label | dd228dee-6014-5177-9acc-8d2073e1679a |  | note | VERIFICATION ACTIVITY - Measurement
label | 399147ee-4f60-58a8-a8ff-a4a2d6d6d582 |  | note | METHODS OR REFERENCE - On Site
label | 449dcc4e-abdc-5f4c-8676-af0a73edc317 |  | note | FREQ. - Measure each side of milling machine cut
label | 604e25dc-a77a-58c0-bc8e-7d36d194edeb |  | note | ACCEPTANCE CRITERIA - Every 10m. Depth matches target
label | 6a7226a6-fa34-5a3d-a10d-21f76f7437c8 |  | note | INSPECTORATE W/H - Type: - H
label | 72168ab7-8fcd-5867-9f1c-d654e608e20b |  | note | Responsible Person - Site Foreperson / QA
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Service Covers Preparation
label | a3801646-7704-5710-a1d5-d78193397b10 |  | note | VERIFICATION ACTIVITY - Visual
label | bfe7dff0-195a-5d6d-a982-7d05eec0c088 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 535caf45-f278-54fd-bab1-7785261cde1c |  | note | FREQ. - All Covers
label | bde75b05-63ad-5cbb-82e2-b46e0649af86 |  | note | ACCEPTANCE CRITERIA - Hand excavation around ironwork and adjustment to desired level (if required)
label | bbc104d1-b195-53ac-9f81-1794c34f4827 |  | note | INSPECTORATE W/H - Type: - H
label | b7d24c91-3dcf-539c-af1a-b9916f6501c6 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Additional Surfacing Preparation: Side Roads; Accesses; Driveways; Dish Channels; High Shoulders
label | f61c5fe6-64c8-5f1f-9adb-b58cbb47cfd7 |  | note | VERIFICATION ACTIVITY - Visual Check
label | a39d9d38-efec-56c8-96ca-d9d8e832f305 |  | note | METHODS OR REFERENCE - Per Design
label | 76019f8b-8bfd-5014-9257-8897e6c4b95f |  | note | FREQ. - Before Membraning and Paving
label | 5951ff20-4067-5b94-b1b1-67fcd79a3a5e |  | note | ACCEPTANCE CRITERIA - Have all areas of additional surfacing on the design been prepared, membraned and marked for paving?
label | e316b77b-1d2c-5cbb-9493-db772e4c0abe |  | note | INSPECTORATE W/H - Type: - H
label | 6d3e3296-a789-5ccd-9242-fdbe5f877192 |  | note | INSPECTORATE W/H - Description: - Hold Point – All areas planned for AC are prepared ready for surfacing layer
label | 59230f50-aa03-5c24-bb03-fe85c6dd4358 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Over-Milling
label | 15eb938e-588b-52df-97a2-975fac489ecb |  | note | VERIFICATION ACTIVITY - Measurement
label | a31bc197-3610-5817-b081-b17fa0b96436 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | f8fddf2b-ec22-5982-9f86-4fd01d658838 |  | note | FREQ. - Prior to pre-level
label | 55e0942b-f3cc-5ec1-89b0-4cf25e0d29c8 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree need and extent of over-milling and infill.
label | 34bb0533-6756-526f-ae7a-2881e7585c75 |  | note | INSPECTORATE W/H - Type: - H
label | 3e08297d-c834-53b5-80ff-1c1467ec8e4f |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Pre-Level
label | d77d2f89-a629-54f2-a39f-5b2add2e4d98 |  | note | VERIFICATION ACTIVITY - Measurement
label | c1f50997-f2cb-5b20-ba0b-2bf956099bd8 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 1ac8038a-8f0f-5dcc-a280-e7e78a6c0427 |  | note | FREQ. - Prior to surfacing
label | 2fae1877-2787-5e6a-8ad1-d12c9594dbad |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree pre-level extents
label | c14c0673-6c51-59f8-9c17-7b22ae6b3334 |  | note | INSPECTORATE W/H - Type: - H
label | c2dcf1f4-54c3-56e5-b46d-488179d3c8e3 |  | note | INSPECTORATE W/H - Description: - Hold point - Inspection and agreement by NZTA
label | f66425e2-4d0a-5ed4-9634-7981e017a41c |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.9 - Membrane Sealing
label | cb55b1f1-6e7d-55e1-86d2-7e627f52d13f |  | note | VERIFICATION ACTIVITY - Visual
label | 9b1e3bc5-a667-5001-8322-76c81924933a |  | note | METHODS OR REFERENCE - On Site
label | 9bedb28a-865d-5239-9a70-cdf61396a477 |  | note | FREQ. - Prior to surfacing
label | eb3b8a1a-3d39-52d6-949c-b856ed1d9350 |  | note | ACCEPTANCE CRITERIA - Membrane seal meets design and extent. Sealing Docket record kept
label | c2e2297a-349c-52d1-b019-4c369cef4720 |  | note | INSPECTORATE W/H - Type: - H
label | 4dab7589-59c1-54d6-87df-59c094d18c89 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Paving Structural
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | b8965405-6d99-55c4-843c-4695cfb852d4 |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | 01eeb95b-cf8c-5669-80a5-0a45cbe0c9da |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | 9f595a2b-4bd4-5627-8929-d8abf8c4730e |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 543b8db7-dc33-57d8-8e38-c6f2961b6aae |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | c7bd07d4-d2aa-537e-a193-c329ef9dc845 |  | note | INSPECTORATE W/H - Type: - W
label | b4c43439-ebe6-5e9d-927e-bec4084ae1e3 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-conformance
label | 64ac1489-57ea-5b7d-a5ce-fc55a94dbb35 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | fed06b1f-ded5-52fc-ab24-a6d017b4fb78 |  | note | VERIFICATION ACTIVITY - Quantitative Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | 4db16101-ea5a-5bd3-92af-fe21ec67d450 |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | d3c1c20c-d8ac-5014-bfa2-fbfb267b46ea |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 9579bd0b-e465-5a3a-82c3-f9a730f410ab |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | f4122ed6-df7b-5f56-8c34-8f202e6e230d |  | note | INSPECTORATE W/H - Type: - W
label | 134a60e4-0cbe-5774-8140-66a34a00b926 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-conformance
label | dc99c5f6-8c3d-50bc-a2e3-f3d42cade664 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | 0818847b-b6ca-587e-98bc-0b847012eeef |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | 5f19d32a-e1d9-5345-8e3e-4f5fc8f69393 |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | 4dddf06e-6d26-5ad1-afea-a9cabfe1e12c |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | f1b013dc-4c01-5325-a050-438f70fd80a7 |  | note | INSPECTORATE W/H - Type: - W
label | 92190af5-1291-520e-9bb8-6c8a149782a7 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-conformance
label | 293128e1-f1c2-58a5-b0e4-83dfa9a438ea |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | 38209d72-27a0-5ebb-bb23-9fcccea639e1 |  | note | VERIFICATION ACTIVITY - Visual
label | ba113bed-be40-5305-8e44-bbe00d7e927f |  | note | METHODS OR REFERENCE - NZTA M/10
label | 7f180792-1741-5810-80bd-e0cd73ddc4a6 |  | note | FREQ. - Prior to Shift
label | e0e5b945-eaa4-5f62-a160-633b9ba0a87b |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | a92d3016-8e8d-558f-b38a-5361418a0161 |  | note | INSPECTORATE W/H - Type: - W
label | 82545be0-ce77-5f02-9e3a-5b691b52ec42 |  | note | INSPECTORATE W/H - Description: - Paving Plan and Crew Briefing Plan completed prior
label | dc4b93bd-98c8-5e63-986a-426019507ac2 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | 2a526286-c80f-5eb2-9bcd-ccefe7c0983e |  | note | VERIFICATION ACTIVITY - Visual
label | 4a198c07-381d-5ff8-aacd-31d43254e25f |  | note | METHODS OR REFERENCE - NZTA M/10
label | 4f57c8da-607b-523a-ba1c-c6c6055d3f88 |  | note | FREQ. - Prior to Shift
label | 895b36ca-7ba0-5220-b8bc-2d11da1bcfa2 |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | ea1c7ec0-7e72-500d-b1c5-2072ce685c4e |  | note | INSPECTORATE W/H - Type: - W
label | 9f5e267d-bb6d-5325-900a-91eb9b78e160 |  | note | Responsible Person - Paving Supervisor / QA Engineer
checkpoint-status |  |  | checkpoint | 3.4 - Mix Inconsistency and Deficiency
label | 972844c1-9894-53ec-845f-70be08dec287 |  | note | VERIFICATION ACTIVITY - Visual
label | e3628e0b-efcb-5f39-a7d7-b565ba7bac7b |  | note | METHODS OR REFERENCE - NZTA M/10
label | da1db261-d3b2-5ea7-bec5-423c73670549 |  | note | FREQ. - Continuous
label | 6b7a632e-1b8e-58d1-b01c-60b9422d2b92 |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | d0d9f93f-a9fe-5541-8e97-f03079682d59 |  | note | INSPECTORATE W/H - Type: - H
label | 03ffc841-3663-5d98-85f8-35483c8f42db |  | note | Responsible Person - Site Foreperson / QA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Load Locate
label | 1e5652d3-1136-5616-b724-4672fd494845 |  | note | VERIFICATION ACTIVITY - Measurement
label | 86376c65-a01d-5d50-9f6c-7a31da518a41 |  | note | FREQ. - Every Load
label | 501d9584-310f-5290-b09c-a684fb82ab6a |  | note | ACCEPTANCE CRITERIA - Each load can be identified to a location using a diagram.
label | 54b7590b-9a1a-51b0-8093-98f090448865 |  | note | Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
label | a40109c6-db6b-5355-afcd-e3d8020db3e0 |  | note | INSPECTORATE W/H - Type: - W
label | 5ffa9f89-51c7-5413-8af4-6752720bf342 |  | note | INSPECTORATE W/H - Description: - Per standard practice
label | bed93a10-5d87-54a1-9084-2f3e21c841bf |  | note | Responsible Person - Quality Assurance Engineer
checkpoint-status |  |  | checkpoint | 3.6 - Laying Temperature
label | eb960fa0-0283-5714-be28-9d7b89bb7ed7 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 3d4b2f2a-25fc-56e8-94a6-8c66097b5d63 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 6ce8ec63-5b33-5199-a19e-ad7947da4b5a |  | note | FREQ. - Every Load
label | 5ea49ebe-0220-59a8-9ce8-50e02a753f2b |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | 6317b939-58cd-552f-9074-6f849578c4a3 |  | note | INSPECTORATE W/H - Type: - H
label | 302d6929-8990-5848-96c1-97d1285b6f79 |  | note | INSPECTORATE W/H - Description: - Hold point - Reject mix for non-compliant temperatures.
label | 0818b639-9eef-5828-ad90-b798938c0633 |  | note | Responsible Person - Quality Assurance Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Compaction
label | 8262b3a9-f10a-5823-82c9-15503d5d3d4e |  | note | VERIFICATION ACTIVITY - NDM Testing
label | 0596fff1-0db1-51c8-87be-980797b0c617 |  | note | METHODS OR REFERENCE - NZTA M/10
label | aa4fd5f1-ea95-5abe-aa26-49f1dd9366c3 |  | note | FREQ. - Minimum: 1 Test per 300m² within Mat. 1 Test per 100m of joint.
label | a50ca9d9-1ec6-5424-b719-6fd8e42e90ab |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | 95f20440-ad66-5c88-b01d-359ce35e6b9d |  | note | INSPECTORATE W/H - Type: - H
label | a6fb35c8-3c22-5c0c-a96f-605c751c9a17 |  | note | INSPECTORATE W/H - Description: - Hold Point - No Wearing course paved until any non-compliance is sorted
label | 23178e76-b6b6-51e8-a5cb-039a8607d738 |  | note | Responsible Person - Quality Assurance Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Roughness
label | 0e7fb19a-379f-535a-8185-85f7cfd97558 |  | note | VERIFICATION ACTIVITY - NASSRA Testing
label | 67f91e08-ec7f-5468-8436-f6d112c4d614 |  | note | METHODS OR REFERENCE - Contract Specification
label | 62c0265a-b047-5710-b5a5-25ba3533dbef |  | note | FREQ. - post construction
label | de9ad519-a7f1-572c-9704-3de581fae193 |  | note | ACCEPTANCE CRITERIA - NASSRA rolling meter average under 60, max of 70
label | 5c00a02f-ae9b-5d39-afcc-5fef666723a9 |  | note | INSPECTORATE W/H - Type: - H
label | e7209c09-e734-50ac-b6ce-da973a9a2440 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Paving Wearing Course
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | 9d3e97b1-f290-5273-b2ba-e0323d05a7d9 |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | 96ced299-09bc-5fae-af5d-719e81c6bbfe |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | a99c16c5-eba8-5bea-a921-414d975d5a07 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 7a83d412-d54d-5191-bd6a-c186d27fa7c0 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | ed095811-a23f-5dae-95e4-c10878e540f0 |  | note | INSPECTORATE W/H - Type: - W
label | 45c6073c-15fd-5b61-a073-ade5401498a7 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-conformance
label | 0bf386b3-ee4f-5e34-98b5-4d222386d2fd |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | dba31ed7-678e-52a1-b84c-9e5444bc5d4e |  | note | VERIFICATION ACTIVITY - Quantitative Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | 88218426-0077-5a46-93a8-0f2010451650 |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | 43a0dee6-a64e-5049-9159-6bfe54cc9142 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | c639efe0-3993-5624-97a7-3479cfaf3f2c |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | f1e2c4f8-7dfe-5f0f-b0d5-32a2d247cb6c |  | note | INSPECTORATE W/H - Type: - W
label | 583d3d6f-1e9a-5d79-8ad3-5ea490147cc9 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-conformance
label | 8640f220-ddb2-5414-94f5-9bbe975daf3c |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | d6ff4a3d-7fa1-539d-ad28-e5381e1097e3 |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | 2689a9cb-ab94-5d3c-b8b9-2d20fc56fa60 |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | 30690bbc-23dc-5b40-994e-fb461c8272d6 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 1e41acd0-5cc0-5442-8bce-1dc8cc07bdbe |  | note | ACCEPTANCE CRITERIA - Per Mix design
label | b39d0b50-6b1f-5335-afd7-69999068f944 |  | note | INSPECTORATE W/H - Type: - W
label | 00852de5-ef0e-50c3-b4c3-b2d9fc06492d |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-conformance
label | 80568d58-ae1b-541a-91f2-a45f49e0f99f |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | 9e4fcb8b-9475-55ce-a827-1ac8f7573567 |  | note | VERIFICATION ACTIVITY - Visual
label | 3214f7e5-ee08-5d44-903e-9bbbc26fabc1 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 540942c5-46c4-56d7-ba49-a139d94e56a3 |  | note | FREQ. - Prior to Shift
label | 28fceda9-bf83-5ebf-8c52-52c162eaf0d1 |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | 02f778dc-a7bc-5b41-af18-72fd4bd49647 |  | note | INSPECTORATE W/H - Type: - W
label | acbb4f80-171f-5035-a54d-5363a45b354d |  | note | INSPECTORATE W/H - Description: - Paving Plan and Crew Briefing Plan completed prior
label | 6b273d87-d334-5789-a34b-04f2db03ad66 |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | 45ea5583-1e53-57b5-b66a-c2e162f4ac00 |  | note | VERIFICATION ACTIVITY - Visual
label | e8b2e68e-25b3-5c95-89db-73bb5dc416da |  | note | METHODS OR REFERENCE - NZTA M/10
label | 5fb763aa-850b-5fb8-9279-fd7dce94bc81 |  | note | FREQ. - Prior to Shift
label | c0fe37dd-4847-5acd-985d-a77b4acd81a9 |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | f64abb7d-aef4-5750-b4da-c9e437db999f |  | note | INSPECTORATE W/H - Type: - W
label | 49319fa2-4a38-55e8-af3d-3562a69a6f40 |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.4 - Grade 3 Membrane Sealing
label | 779aa4dc-01ba-596f-8bf9-1a752fc30287 |  | note | VERIFICATION ACTIVITY - Visual
label | dd95905f-dcbf-57d5-bf7e-72cfb4900a92 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 0367f2c6-0222-58d3-9ddf-4b1b93c85d17 |  | note | FREQ. - Prior to Paving
label | 461b2ebb-5a16-57a1-86fa-817b05b08ca0 |  | note | ACCEPTANCE CRITERIA - Applied 2.0l/m² residual
label | 6efa7939-7317-5755-bf69-fa18168c8937 |  | note | INSPECTORATE W/H - Type: - H
label | 38ad3169-911c-5fc5-a7ad-7aa17380d54b |  | note | INSPECTORATE W/H - Description: - Hold Point - No paving until Membrane Done.
label | b4d55a69-3f4b-543f-8276-a4585b322954 |  | note | Responsible Person - Paving Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Mix Inconsistency and Deficiency
label | 48c0a930-643b-5f7c-a56d-4f115d011795 |  | note | VERIFICATION ACTIVITY - Visual
label | 832f3f31-57ea-5709-bd20-26d954a6a507 |  | note | METHODS OR REFERENCE - NZTA M/10
label | d50d215b-2e23-5579-8c4c-75d05572bb14 |  | note | FREQ. - Continuous
label | 09276878-acf5-5806-8dd7-9da6765d7b5a |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | 79750ea8-5f2e-54ae-876e-2d05f42dfad6 |  | note | INSPECTORATE W/H - Type: - H
label | 4709231b-bb42-50e6-abc9-ea0bc3e3e784 |  | note | Responsible Person - Site Foreperson / QA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Load Locate
label | 674b6817-ffd1-55ba-979e-4edb5165287c |  | note | VERIFICATION ACTIVITY - Measurement
label | 3c5becbe-e305-59bc-b61c-5ce0e4cb0e55 |  | note | FREQ. - Every Load
label | 10a87f65-bb6d-53d5-9288-ec6cae651f07 |  | note | ACCEPTANCE CRITERIA - Each load can be identified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
label | 3b3047f0-418b-5b1f-838d-cff6b9d7eae4 |  | note | INSPECTORATE W/H - Type: - W
label | fc9c3b6a-3937-54e0-8b92-e77990a8401b |  | note | INSPECTORATE W/H - Description: - Per standard practice
label | 1a195f72-c635-5c2c-b1f8-9e481180a6aa |  | note | Responsible Person - Quality Assurance Technician.
checkpoint-status |  |  | checkpoint | 3.7 - Laying Temperature
label | f289f369-255d-5640-a674-77a6df74d54c |  | note | VERIFICATION ACTIVITY - Confirmation
label | 72edbbb9-2f50-57c5-b2cf-d63a48a40eb3 |  | note | METHODS OR REFERENCE - NZTA M/10
label | d22f035f-93c1-5948-9f09-097d8ace8457 |  | note | FREQ. - Every Load
label | cf5d3686-3e7e-5e4c-a4e5-8b70bd088684 |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | 2f0d1df0-dba2-573c-8073-bc7f37143118 |  | note | INSPECTORATE W/H - Type: - H
label | e47d0371-eb27-572b-8f77-e7a8e149e824 |  | note | INSPECTORATE W/H - Description: - Hold point - Reject mix for non-compliant temperatures.
label | c44f705c-b459-5c7a-9e83-5f2a4a2b80b6 |  | note | Responsible Person - Quality Assurance Technician
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Compaction
label | b970e958-9be1-5415-a6ad-1eb3c2540e20 |  | note | VERIFICATION ACTIVITY - PQI Non-Nuclear Gauge/Cores. Or Non Destructive Method Testing.
label | 0b574c61-86d4-556b-be34-05975cea5c6a |  | note | METHODS OR REFERENCE - NZTA M/10
label | d4199149-a80e-5731-ad0e-9a1905df5d75 |  | note | FREQ. - Minimum: 1 Test per 300m² within Mat. 1 Test per 100m of joint. Minimum 8 cores on Mat and 3 on Joints as Per M10:2020.
label | 5040accd-2b17-5f61-bf70-2144b827d12f |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | d50f852d-397c-56cf-92e5-11d101254716 |  | note | INSPECTORATE W/H - Type: - W
label | 4c491caa-3f57-5909-a0b4-7935db42736f |  | note | Responsible Person - Quality Assurance Technician
checkpoint-group |  |  | section | 4 - Site Reinstatement / Clearance
checkpoint-status |  |  | checkpoint | 4.1 - Post-seal Area Check
label | 1120c01a-0c73-5b7c-b135-7bdcf3751c6e |  | note | VERIFICATION ACTIVITY - Measurement
label | 47c52044-0571-5f25-bfd3-f4c1e74d5736 |  | note | METHODS OR REFERENCE - On Site tape-measure
label | 53a719e5-1ea4-5e3c-87e5-0c30a67f7f65 |  | note | FREQ. - After Surfacing
label | a41a40ea-fd31-57cb-b6ba-3d347a3eaea5 |  | note | ACCEPTANCE CRITERIA - Check sealed area meets design
label | 3d3c9ae4-f0bc-524c-8da7-2f538a889094 |  | note | INSPECTORATE W/H - Type: - W
label | d406a5ac-f9c4-5cd1-a777-08cb763ef5f7 |  | note | INSPECTORATE W/H - Description: - Notify Renewals Engineer or Renewals Manager
label | 92957aa6-aac4-521b-8044-ed20d6720fb8 |  | note | QA Engineer
checkpoint-status |  |  | checkpoint | 5.3 - Service Covers
label | 101fe0c0-5fdd-51ab-baa3-ccd5f59d9b78 |  | note | VERIFICATION ACTIVITY - Measurement/Visual
label | 55a36cbe-4c43-5edb-beb7-78aaed610807 |  | note | METHODS OR REFERENCE - On Site
label | b1ebcd64-2d20-51de-98d8-44813279f2fc |  | note | FREQ. - After Surfacing
label | d55a5da8-5776-5ad4-a7e3-6b01d5dfc534 |  | note | ACCEPTANCE CRITERIA - All service covers are checked and adjusted (if necessary) to finished level
label | e94944e3-9ed1-537f-a921-8b6452939328 |  | note | INSPECTORATE W/H - Type: - W
label | d5c4972b-2a25-5cc5-8f02-f4286236fc9e |  | note | Responsible Person - Paving Supervisor / Foreman
checkpoint-status |  |  | checkpoint | 5.4 - Joint Sealing
label | b03d7fb8-a059-58bc-b5f1-6b740863837b |  | note | VERIFICATION ACTIVITY - Visual
label | 3a2c3da9-3b88-5f53-b0cc-21b423e8bd80 |  | note | METHODS OR REFERENCE - On Site
label | 19e2ca32-19d5-54bc-b17d-8d195b83d179 |  | note | FREQ. - After Surfacing
label | d80a03f7-4400-5ffc-b308-68f484c88804 |  | note | ACCEPTANCE CRITERIA - Check cold joints are bandage sealed
label | f259e762-52a3-5c1f-8c57-ae95aae68d44 |  | note | INSPECTORATE W/H - Type: - W
label | 42dfc985-1231-516c-a646-231be79020f6 |  | note | Responsible Person - Paving Supervisor / Foreman
checkpoint-status |  |  | checkpoint | 4.2 - Road Marking
label | 4d178aba-4713-577b-ae7e-aa18a90ed787 |  | note | VERIFICATION ACTIVITY - MOTSAM
label | fd812527-bdab-5401-af94-1d3b3a697829 |  | note | METHODS OR REFERENCE - Visual inspection
label | 4372fc91-cfa0-5b3d-9280-0dbea6b0add9 |  | note | FREQ. - All markings
label | ba448d46-3c00-5906-a13d-e60157fce40e |  | note | ACCEPTANCE CRITERIA - Replaced in same position, or per design
label | 84559e63-ad8b-5dc2-8746-024766aa490b |  | note | INSPECTORATE W/H - Type: - H
label | 17207555-23a3-5072-a502-73e762634e44 |  | note | INSPECTORATE W/H - Description: - Hold point – Site TTM cannot be removed until markings reinstated
label | d101c57b-ce16-5647-a786-7e6a1a129449 |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 - Other Traffic Services - Marker pegs/ Signs/Markings/RRPMs Replaced
label | ba1f9f08-af70-5316-956a-71abfb8e1250 |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | cf886b41-8a7d-5263-8b5d-1412b059ba9d |  | note | METHODS OR REFERENCE - Visual inspection
label | 1c5f0149-466f-5ca4-9ba7-147f2791f359 |  | note | FREQ. - All signs/markers
label | c1d4862a-fb32-590d-8e9a-75f52aa216cb |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | 72dc9a80-0842-5e8b-b03d-6f3885d7854a |  | note | INSPECTORATE W/H - Type: - H
label | d589158c-8f0b-5b54-99a9-56c36bcd4f87 |  | note | INSPECTORATE W/H - Description: - Hold point – Site TTM cannot be removed until marker pegs, signs, markings and RRPMs reinstated
label | 3b18f183-b4bc-5b70-8788-a1dd157d78a2 |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Stormwater Management Controls removed
label | 72c2bca7-9033-5894-a1de-e52f8d8083f8 |  | note | VERIFICATION ACTIVITY - Visual check
label | 9d6ce987-418d-5dd5-a154-0fe5132bef42 |  | note | FREQ. - All installed measures
label | fb6ff0d2-d735-5057-ab1a-e7b362ba47db |  | note | ACCEPTANCE CRITERIA - Installed controls are removed
label | 3c5ca0be-7577-54c8-be7d-f2d1937d4ab9 |  | note | INSPECTORATE W/H - Type: - H
label | aa4b7867-bc82-55e1-9fc7-ccea3d654f2b |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Traffic Management Removed
label | 533df7cd-4929-5305-b90a-b519584c04ac |  | note | VERIFICATION ACTIVITY - Visual check
label | acd9dfba-f6eb-5d9b-a794-f4048b1f6ef9 |  | note | FREQ. - When safe, after all physical works completed
label | fc8e1de1-63ad-5164-9536-1b4c5228c323 |  | note | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | d180ae2a-9727-5c6c-bbc0-5f08c23b0487 |  | note | INSPECTORATE W/H - Type: - W
label | d951479b-cc1c-5db4-99a5-1effcb897764 |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.6 - Site left clean & tidy
label | 8f60a9bf-99df-54ea-a043-e91321e53547 |  | note | VERIFICATION ACTIVITY - Visual check
label | 7cc0fcf3-edb3-502f-9351-b1cd0411bfae |  | note | FREQ. - After vacating site
label | 8d1ef424-254d-550c-9368-087b29fba09c |  | note | ACCEPTANCE CRITERIA - Stockpiles removed; Plant removed; Litter cleared from site
label | 5564db1d-e30e-5d79-8641-26012d0a6c6b |  | note | INSPECTORATE W/H - Type: - W
label | 54a5dd2b-ab0b-53d5-aff2-af55aea12d2b |  | note | INSPECTORATE W/H - Description: - Invite NZTA to carry out joint site inspection to inspect site.
label | df500250-3248-51b8-80da-ca29bb208e31 |  | note | Responsible Person - Paving Supervisor
checkpoint-group |  |  | section | 5 - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.1 - Collect asset data
label | 2b3139c9-d354-5d90-b59a-5e4d1799f128 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | e68b4fca-1dee-5ed7-86a8-078cc00f0579 |  | note | FREQ. - During construction
label | 422ab3b6-76d5-56de-bf50-37a76a686906 |  | note | ACCEPTANCE CRITERIA - All relevant as built information collected.
label | 615f556d-bddc-54d6-a97f-2b5e72674138 |  | note | INSPECTORATE W/H - Type: - W
label | cd54c550-a7b9-554d-9c0b-cc7b06c9efe0 |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.2 - Enter asset data into RAMM and/or register(s)
label | 44114565-ec68-50b5-989a-f8dea32d1c35 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | defa35e8-2445-5442-b58c-630d8a6121eb |  | note | METHODS OR REFERENCE - RAMM
label | 3d4924b3-f7c7-5e64-b063-3c25c41a5529 |  | note | FREQ. - At completion of work.
label | c7db6bfc-0bd4-508d-a679-b28a160fa161 |  | note | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.
label | 9fe9ae20-9752-5a92-859c-fe7f8bcf4b40 |  | note | INSPECTORATE W/H - Type: - W
label | 0150d643-9714-52da-b544-84c70b87a88f |  | note | INSPECTORATE W/H - Description: - Data entered by 20th of follow month after month of completion
label | b09dc773-ddb2-5d24-884a-efb132b997d4 |  | note | Responsible Person - Asset Information Manager
checkpoint-status |  |  | checkpoint | 5.3 - Construction Completion Report
label | a114c80d-839a-556e-8ec5-859367292fdd |  | note | VERIFICATION ACTIVITY - Confirmation
label | 7ab24e9d-23da-5f48-8d6c-2a91d950fed6 |  | note | METHODS OR REFERENCE - Contract Specification
label | 146764bf-0df3-5cbc-8bdb-d6e9d0139200 |  | note | FREQ. - At completion of work.
label | 0a0daeb5-4152-505a-9ef6-b612db66bd16 |  | note | ACCEPTANCE CRITERIA - Checked and approved
label | 6a0f0aa2-868b-54f9-8ac0-4b9583672e8a |  | note | INSPECTORATE W/H - Type: - W
label | 72fe6be7-58d3-5711-88ff-f705273f2638 |  | note | INSPECTORATE W/H - Description: - Completed within two months after Paving Wearing Course
label | a4e3f02f-3158-5f4c-9f95-9332228a8ed3 |  | note | Responsible Person - Renewals Engineer/ Renewals Manager
checkpoint-no-status |  |  | checkpoint | Quality Assurance Close Out
text | 7dba1367-b73d-54f4-aefa-03690ad919bf |  | textbox | Quality Assurance Close Out by - Name:
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | ITP - CONOC Operations (Heavy and Light Maintenance) - Adjust a Surface Box - Not a Manhole | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy and Light Maintenance) - Adjust a Surface Box - Not a Manhole | 405d1968-1e8a-45a3-8a74-ef0797cbbcc3
checkpoint-status |  |  | checkpoint | 1 - Prepare
label | 3ee177f6-d558-5988-8db0-8bbceecba37a |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 3556e272-7c92-55ca-987b-7f58acc28802 |  | note | Accept / Reject Criteria - As per specification
label | a57c8a8c-8014-5d63-8c2e-2dbe127e7cbb |  | note | Frequency Of Inspection Or Test - In-process
label | 77f91cd2-0a63-5389-adb2-b7a54826b2cb |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP035
label | f2e0480b-3871-524f-9d81-44299cd27e7b |  | note | Records Required - NO
label | 174665b6-5e23-59d8-8704-04e34064d017 |  | note | DOWNER ENGINEER - R
label | 1df48eb2-40d0-55ba-8b99-e010b497db93 |  | note | SUPERVISOR - R
label | 255c6c20-950e-5948-9e5c-a70880887d0f |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Excavation
label | 895ea91e-9f87-5122-a83d-70f0aff33d9d |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | ffa9dbd4-5f60-5dd3-8970-ddd3e74ea2e3 |  | note | Accept / Reject Criteria - As per specification
label | 148c2826-043b-5c18-b1bb-095117f71adc |  | note | Frequency Of Inspection Or Test - In-process
label | a8898aba-4572-561b-8053-386308367a60 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP035
label | 7d54e6c9-f34a-58d1-83d2-843fb32f1a1e |  | note | Records Required - NO
label | 79c1a860-a167-5c30-8260-4b45ebb43873 |  | note | DOWNER ENGINEER - W(10%)
label | 16272c06-9902-592b-a48c-84980129ccea |  | note | SUPERVISOR - R
label | 82d1bf1d-004b-5582-8b9c-1a166562d95d |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Replace Risers
label | ee6be062-d8ea-5588-835d-9d5463be7a67 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 71eaa5e0-7dc2-54db-b0f2-e4ba6b3b5191 |  | note | Accept / Reject Criteria - As per specification
label | f78905f1-247d-5dae-895e-277d8be22ec4 |  | note | Frequency Of Inspection Or Test - In-process
label | 5773dd9f-da77-548f-9c80-1686bd8aca42 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP035
label | 8f2a3e0b-30c8-5bf0-ad4d-47f80097d8fa |  | note | Records Required - NO
label | b6504d20-0102-5cf7-a444-99d80b80a390 |  | note | DOWNER ENGINEER - W(10%)
label | 18dadf58-5d3d-59c5-9a1e-3cb6225af24c |  | note | SUPERVISOR - R
label | 2575155a-f8c9-535f-9f18-5fe21f957d57 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Backfill around the Riser (Clegg Hammer)
label | 1618854e-d965-56bc-85ce-ebf6e72bb63b |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 01b7408f-5b1b-5838-ac02-1cd4ef2ecb55 |  | note | Accept / Reject Criteria - As per specification
label | b2629229-d9f9-5756-9984-23c95829b315 |  | note | Frequency Of Inspection Or Test - In-process
label | e0f7f0b7-22ca-50dd-8fad-043eec553759 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP035
label | 62105292-5002-58d6-a7c5-4feaa19cf651 |  | note | Records Required - YES
label | fb42ca92-4605-5375-aa9a-15f79f6d9900 |  | note | DOWNER ENGINEER - W(10%)
label | bed28594-4b9e-501c-ae28-077f8ad518aa |  | note | SUPERVISOR - R
label | 422d4503-ffce-53f4-8117-9d2aa47e07ca |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Final Shape and Trim
label | 7ccebba4-c393-5655-8388-7a278e03364a |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 44018ae5-c448-58f9-9433-b769bbd0f377 |  | note | Accept / Reject Criteria - As per specification
label | c2b65245-8e5e-5bbd-b140-a81d6e60ab9f |  | note | Frequency Of Inspection Or Test - In-process
label | d3936648-840c-582d-9442-581017fc1ae1 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP035
label | 02c113b9-55ce-5b80-9fa0-2eba21fce6b0 |  | note | Records Required - NO
label | 760e9b3a-6351-58ca-8ddc-a3e55b4c6d10 |  | note | DOWNER ENGINEER - W(10%)
label | 5400f3cc-19b7-58aa-b5e9-d7d05579d6b4 |  | note | SUPERVISOR - R
label | 4d14290f-154b-5210-964d-49cb921c261a |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Surfacing
label | 5e2d5c36-2bec-5336-a443-d472fe53af94 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 96320a59-201b-595e-9f82-07ad6132d978 |  | note | Accept / Reject Criteria - As per specification
label | fa990618-d694-5532-87a4-b4e5573fbafa |  | note | Frequency Of Inspection Or Test - In-process
label | 626360ee-fc9c-5cf0-abd2-740b17d9d93f |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP035
label | eb05498a-9d66-5bf9-8243-62e0298816bb |  | note | Records Required - NO
label | 1feefaf1-d71c-5376-a5af-1d73ded1fc84 |  | note | DOWNER ENGINEER - W(10%)
label | 608b9380-1343-5682-a743-40a5cdbb87d7 |  | note | SUPERVISOR - R
label | e84fb1f6-a7f8-5ddf-8f09-494a163dfe46 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Surface Cover Painting
label | 80a6efb4-3197-5ad8-8046-7bf45d090fd0 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 308ec819-b30b-59d2-bac0-55c75a27518e |  | note | Accept / Reject Criteria - As per specification
label | e5edb8dc-2f9c-5f5c-8566-a59f54762b7a |  | note | Frequency Of Inspection Or Test - In-process
label | 06d09d13-eb1c-500a-a436-abd47b1aa80f |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP035
label | 25941bd9-c910-5757-85c1-76346d26a57e |  | note | Records Required - NO
label | c46ba8dd-19dc-53ea-be3f-8d783bc53778 |  | note | DOWNER ENGINEER - W(10%)
label | a2410c63-cb2f-53e7-9f72-19d7daf051c1 |  | note | SUPERVISOR - R
label | 7495c312-1605-59ac-8b82-353e5a35d35c |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Test and Check
label | bd9832be-6574-5bad-b5e0-19ab8834f01c |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 5e237a2f-f7a5-562b-aacf-0719c81a44ee |  | note | Accept / Reject Criteria - As per specification
label | f1ce75e1-78a9-538e-8e89-0f0d077c6e75 |  | note | Frequency Of Inspection Or Test - In-process
label | e9d29927-7c7f-51ed-a599-0244c560b83e |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP035
label | 7c0221a9-119f-5c5c-a1da-939b8290e345 |  | note | Records Required - NO
label | 86296920-980c-58ec-b9bc-462f53e267c4 |  | note | DOWNER ENGINEER - W(10%)
label | 99c6fed8-8466-521a-8b22-66a3b2c4f9fd |  | note | SUPERVISOR - R
label | 2d414e7d-eebf-5bc5-9cd6-16712d4e331a |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - CONOC Construction (Heeney Creek Rehabilitation) - PAVEMENT RENEWALS - Unbound Granular | itp |  |  |  | Yes | ITP - CONOC Construction (Heeney Creek Rehabilitation) - PAVEMENT RENEWALS - Unbound Granular | 41462a8c-fc6a-4450-a09f-cf16f57a09e1
checkpoint-group |  |  | section | 1 - Preliminary and General
checkpoint-status |  |  | checkpoint | 1.1 - Construction Program Completion
label | f31d7897-49e2-586e-9adb-fbdad1956f98 |  | note | Controlled By : (Position) - Project Manager
label | ac79792f-a649-5307-b68e-76dd68474062 |  | note | Accept / Reject Criteria - Best Practice Contract Specific MMP
label | c948b239-7c70-5c7f-8954-0a8879a02ae2 |  | note | Frequency Of Inspection Or Test - Before work Commence
label | c7b04cab-7f4d-51ea-ae16-9a058b518474 |  | note | Spec. Ref, Procedure Or Method Statement - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date.
label | a074e589-dd60-59f6-b261-376f1664c240 |  | note | Records Required - YES
label | f5be2025-699c-5eb7-91bb-c638bb5ebec4 |  | note | DOWNER ENGINEER - W
label | decc901f-cb05-51e7-a459-d35a14586752 |  | note | SUPERVISOR - R
label | 230c4fd3-e6ca-55bb-8ed5-7aa6d77e68ce |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 - Approved RQP
label | 2d052e35-644a-5614-8871-1fc35ccf3df0 |  | note | Controlled By : (Position) - NZTA Maintenance Contact Manager
label | 38de3e82-c6f3-5f4c-90c0-a8c8b12dd915 |  | note | Accept / Reject Criteria - Contract Specification
label | 01b8ea70-5a30-59ac-9e8a-74638ef8f077 |  | note | Frequency Of Inspection Or Test - Before work Commence
label | 6effa205-5f22-5bdc-8008-bc73fc7c4b7a |  | note | Spec. Ref, Procedure Or Method Statement - Principal Acceptance according to guidelines in appendix 6.3
label | d610d2d9-cd83-5fc3-b15a-9c8c3f920031 |  | note | Records Required - YES
label | 3249bdd8-ee30-5525-9214-770eb1a85ebc |  | note | DOWNER ENGINEER - H
label | beee396d-3c5f-5316-aedc-20d2cf5355be |  | note | SUPERVISOR - R
label | c179e093-8ddd-59c9-9e48-46faf4ff68ba |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Traffic Management/TMP
label | a0570704-7cf7-5746-870e-60367a28f687 |  | note | Controlled By : (Position) - Project Manager
label | 6f3085b9-717a-599b-a5b7-d3c33b47d140 |  | note | Accept / Reject Criteria - CoPTTM
label | 97c68a7e-3ef3-54bd-86d5-14373c14e31b |  | note | Frequency Of Inspection Or Test - Before Traffic Management Setup
label | ae6c0b58-6529-5418-b0d9-ccf96070ca8e |  | note | Spec. Ref, Procedure Or Method Statement - TMP checked and approved, Plans approved, Current EED (if applicable)
label | 1ad04f67-1df4-55f2-a41c-84820471ce68 |  | note | Records Required - YES
label | 76535e5c-6190-5e9e-b1e4-a2e41f8491fa |  | note | DOWNER ENGINEER - H
label | 4ea99356-487c-5307-a4a7-dabebafd0501 |  | note | SUPERVISOR - R
label | 9028a2a7-c527-535d-92a6-09cf61142707 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Notification of intention to start work
label | b5c3fb5a-8106-5a84-aefc-2f4ec9f8342a |  | note | Controlled By : (Position) - Project Manager
label | c9902e4d-6925-5e44-b1c2-fd3c9c461790 |  | note | Accept / Reject Criteria - Notification
label | 850cca66-eb66-5c71-b9c1-42ff879c9c43 |  | note | Frequency Of Inspection Or Test - Before work commences
label | f89d6933-88b3-58f6-8816-ad0f0daeecd1 |  | note | Spec. Ref, Procedure Or Method Statement - Letter drop to local residents. Where required and defined by SWAMP, VMS, social media/media advertising
label | 601adfa5-7b06-5daf-81a0-19c507ab21f2 |  | note | Records Required - YES
label | fe3a2745-81b9-55e7-9064-fc3e55ef9756 |  | note | DOWNER ENGINEER - H
label | e8a60871-97a1-55ec-b5ba-ffe31cd85f23 |  | note | SUPERVISOR - R
label | 4c82a8b7-df4d-5081-af2f-7b20e6d71021 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Setout/Site Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Setout/Survey
label | d93ece3f-855a-5c09-b159-5e74f3285ad6 |  | note | Controlled By : (Position) - Project Manager
label | 20233c62-3d5f-5ec7-8116-240ced0d3569 |  | note | Accept / Reject Criteria - Best Practice
label | 50d634ff-1434-5253-8a82-e1793e25ae50 |  | note | Frequency Of Inspection Or Test - Per installation
label | 2aac37f7-711e-5d7c-a9e7-f543223fa549 |  | note | Spec. Ref, Procedure Or Method Statement - Survey Records
label | db5a19b7-a812-5454-ac97-9511284eecd3 |  | note | Records Required - YES
label | 6e6ec420-1ee5-5fb5-a756-2a37e1f57b54 |  | note | DOWNER ENGINEER - W
label | 31d4a051-9ab7-5745-b397-0f4a5107f311 |  | note | SUPERVISOR - R
label | 9b157eae-e2c2-5737-b71c-41b75d93ea5f |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Permit to dig/Authority to Work/close approach permits
label | 9f63d57f-67e0-558f-ac5f-5adbaf3e3787 |  | note | Controlled By : (Position) - Construction Foreman
label | 7f5efd8c-080c-5906-adf4-7a8f25beb2f1 |  | note | Accept / Reject Criteria - Downer Permit to work or Equvilent
label | 7880c13a-ddd2-5dc6-9460-edec90af3932 |  | note | Frequency Of Inspection Or Test - Before work commences
label | 457dd935-c35f-575f-86f9-ad6544a091f5 |  | note | Spec. Ref, Procedure Or Method Statement - Organisational approval
label | a93c2c65-f0e3-5bd8-87bd-5a312ed21cd3 |  | note | Records Required - YES
label | 196f1d93-0f47-5d02-9255-7909963c20eb |  | note | DOWNER ENGINEER - H
label | aa96c8c5-5265-5a67-b50c-6b52ba586100 |  | note | SUPERVISOR - R
label | 86e0ee37-1489-55e1-a9bd-83287031baa9 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Cultural/Heritage Risk Assessment
label | 5ea56429-6da4-5c81-8e04-fd8c76b878fd |  | note | Controlled By : (Position) - Project Manager
label | 40e0c81d-4f23-5e83-8ae4-0f432db76f11 |  | note | Accept / Reject Criteria - WK Cultural & Heritage Risk Model
label | 23f3f8e1-7a2a-5ff8-8c54-428e93109a2b |  | note | Frequency Of Inspection Or Test - Before work commences
label | 060b55c6-f71c-5070-840d-92a12728e9ac |  | note | Spec. Ref, Procedure Or Method Statement - Local kiwi has been notified of intent to start work
label | 856a9279-3e74-51da-b2fd-bd29ec434d50 |  | note | Records Required - YES
label | f8b97442-3718-556f-974d-31896bb755d7 |  | note | DOWNER ENGINEER - H
label | b0523089-a7c9-5af3-bd67-2b60b72393da |  | note | SUPERVISOR - R
label | 27d240a4-0e65-59a0-9a95-1846c5ad2474 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Archaeological Risk
label | bf1f3ba7-436c-580f-b687-0bcc1be3a319 |  | note | Controlled By : (Position) - Project Manager
label | ce023ddd-9a43-5c31-b55f-c1277c10428a |  | note | Accept / Reject Criteria - WK Cultural & Heritage Risk Model
label | 5b74bab2-af03-5ec2-8df1-f23bc379618d |  | note | Frequency Of Inspection Or Test - Before work commences
label | 9b7ec3f8-05e0-5e14-99ca-f0b0d408f2e9 |  | note | Spec. Ref, Procedure Or Method Statement - Toolbox meeting held covering accidental discovery protocol
label | 6add77b2-f32e-5484-9842-4e29fa0bc6da |  | note | Records Required - YES
label | 39975965-eafe-5f87-86a9-0905d04df056 |  | note | DOWNER ENGINEER - H
label | 74d40c6f-b2b4-5d55-bc3c-e5bd146ebfd8 |  | note | SUPERVISOR - R
label | cc27bfe2-d35f-58e6-9273-5e5c1498fc9f |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Traffic Management Setup
label | a5cf51ec-01d8-5792-8347-b8c36bc0bdfb |  | note | Controlled By : (Position) - Construction Foreman/STMS
label | 47328ecb-ca04-5860-8969-4610dacc84cb |  | note | Accept / Reject Criteria - Traffic Management Plan
label | 358710dd-8b1c-5fff-87f8-4f8182c73e29 |  | note | Frequency Of Inspection Or Test - Before work commences each day
label | 7dde0a4e-d8e6-5c5c-9cca-a6fe2b4a6250 |  | note | Spec. Ref, Procedure Or Method Statement - Traffic management complies with TMP
label | 9fe83eeb-5d46-59d8-bdf3-b8ab018658f3 |  | note | Records Required - YES
label | e7ac1c7b-1021-52fe-a907-29c8150bc1de |  | note | DOWNER ENGINEER - H
label | f5d1e554-b1dd-5143-8e35-ee16d6710d1e |  | note | SUPERVISOR - R
label | 33ec97a0-aca2-52a0-9bdd-823a89eda88e |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Machine Control Survey Control
label | c74ee89a-b6e4-5fed-9065-bc797a90253e |  | note | Controlled By : (Position) - Construction Foreman
label | b48bbf5f-d673-5b15-bfbd-1cce4fcbd8ff |  | note | Accept / Reject Criteria - On Site/Measurement
label | d74918ff-47e9-5994-98fc-3e345898af10 |  | note | Frequency Of Inspection Or Test - Before using machine control
label | d2bce248-012d-5114-bc6a-f0865ce18a5e |  | note | Spec. Ref, Procedure Or Method Statement - Verification of survey control points and setup
label | 811b867b-63e0-585d-bfad-80e6a843eb04 |  | note | Records Required - YES
label | dba6ded8-8ac8-57b8-bf4c-8ead977f84de |  | note | DOWNER ENGINEER - H
label | c0c4ac54-b54f-5b4b-a019-3364887f3d47 |  | note | SUPERVISOR - R
label | 08b7fea0-c216-5066-b03a-cdbabf38138a |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Machine Control Accuracy Verification
label | 1908e179-b466-5559-a835-42aa14631c8a |  | note | Controlled By : (Position) - Construction Foreman
label | a852b35c-ab84-5ad5-97bf-045f1f6e1252 |  | note | Accept / Reject Criteria - On Site/Measurement
label | b2b169ef-86b9-5f8b-a9a4-65983e55aa65 |  | note | Frequency Of Inspection Or Test - Before using machine control
label | 27c2c4c6-a605-5faf-acb2-ef4e2c4f9a31 |  | note | Spec. Ref, Procedure Or Method Statement - Verification of survey control points and setup
label | fb1b0069-09b2-5ee3-8e22-89a275bc6eed |  | note | Records Required - YES
label | 120e6602-13f5-51d7-90d5-6aece920bf01 |  | note | DOWNER ENGINEER - H
label | 2d62d558-4c4f-5e3f-a5c6-687150643d6a |  | note | SUPERVISOR - R
label | 49dda570-4bd7-5de2-b284-23469f04024f |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Prepare String Sheet (Digital)
label | f4cfc2a4-3b38-55fb-b3a0-c98de8db8048 |  | note | Controlled By : (Position) - Project Manager
label | af86ae20-c72c-5a2b-ad60-78187efdccfe |  | note | Accept / Reject Criteria - On Site/Measurement
label | 28ce52f6-8c1f-5066-b066-d31da6e81039 |  | note | Frequency Of Inspection Or Test - Before using machine control
label | 7b0e30ec-d70d-5a66-b283-b0d51a52043f |  | note | Spec. Ref, Procedure Or Method Statement - Digital design set-out data is consistent with on site marks
label | fd27f368-a94b-52a7-bd3f-a8404c884ed1 |  | note | Records Required - YES
label | d5ebece5-656e-5d9a-8347-a84ed8e2c106 |  | note | DOWNER ENGINEER - H
label | 621c9da3-5c0c-5e5b-b6a6-125d3488963a |  | note | SUPERVISOR - R
label | d8bed841-b147-5892-86b7-e96af1d0dd97 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Preparatory Work (3.1 - Earthwork and Stripping)
checkpoint-status |  |  | checkpoint | 3.1.1 - Shoulder Stripping
label | 9c734d44-b428-583a-9e89-cef938ee9005 |  | note | Controlled By : (Position) - Construction Foreman
label | 487e6bf9-a591-51e9-999c-821f7bc6bbd2 |  | note | Accept / Reject Criteria - On site/Visual Check
label | fa863432-498e-552d-96b5-c3964cdee609 |  | note | Spec. Ref, Procedure Or Method Statement - Shoulder stripping completed
label | 8014097a-40bd-5eeb-a42a-cd4502104472 |  | note | Records Required - YES
label | 09fff4fa-30b1-52f7-bfd3-b609198bf629 |  | note | DOWNER ENGINEER - W
label | f5193fc7-8a62-5096-aa9e-34f2751e59a2 |  | note | SUPERVISOR - R
label | f99cd510-5db9-573b-8452-4cc6f33203c6 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.2 - Cut/Excavation
label | a6342a64-45f3-57e4-bcfd-4726b0c31776 |  | note | Controlled By : (Position) - Project Manager
label | 74fe993f-9318-561a-8ade-1b45a3bc80df |  | note | Accept / Reject Criteria - On Site/Measurement
label | a1948486-b526-54e4-95f0-9bce2b9ebd3b |  | note | Frequency Of Inspection Or Test - Tape measure from set-out or existing CL, as per design
label | 808cbf94-12d3-5f36-8bbf-6b9a6439d8b8 |  | note | Spec. Ref, Procedure Or Method Statement - Meets design drawings of cross-sectional extent
label | 4ccc9eaa-b174-5746-80e0-de56d671b513 |  | note | Records Required - YES
label | 48cc5e2b-d305-5145-92e8-07a2ab2c6b33 |  | note | DOWNER ENGINEER - H
label | 30048891-9460-5217-b09e-37b2f9bca652 |  | note | SUPERVISOR - R
label | 49cc263b-6ebc-53b3-8ea6-24debb4de4f2 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Preparatory Work (3.2 - Drainage Structure)
checkpoint-status |  |  | checkpoint | 3.2.1 - Other Structures
label | e9cb22ef-b045-5f49-ad2b-22953f7233c1 |  | note | Controlled By : (Position) - Project Manager
label | bb46d544-eb38-55d7-8dc7-0da90fc36b1d |  | note | Accept / Reject Criteria - On site/Visual Check
label | 39c302a2-460e-5390-8e7b-f8e3cc37e7ff |  | note | Frequency Of Inspection Or Test - Continues
label | 0a1c0f30-7b72-530b-b30e-c83606badb16 |  | note | Spec. Ref, Procedure Or Method Statement - Constructed to design drawings and relevant standards
label | 2a2d3fe0-fcbd-53be-911e-ec15298de99b |  | note | Records Required - YES
label | b08267ad-8f61-5340-b9a7-72e5174ce4a4 |  | note | DOWNER ENGINEER - H
label | bb26860b-b44b-5593-9a88-5225db39740a |  | note | SUPERVISOR - R
label | ff0a4b72-a8d1-5e63-b013-765daf49d4f2 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Preparatory Work (3.3 - Ancillary Work)
checkpoint-status |  |  | checkpoint | 3.3.1 - Ancillary Items as per design
label | 857028b3-ffdc-5dc8-937e-6acb1235e8de |  | note | Example:
label | d7a97c88-cdba-5178-b487-c7bc248103a2 |  | note | – Rock Benching
label | 4185e866-4ab7-5048-b6b4-ec75e51f1c05 |  | note | – Signage
label | 00acfcf3-9c74-5d7b-84e8-c2cce13fc736 |  | note | – Vegetation/Trees
label | 29b4fb30-b6e3-5135-be00-3328011e2322 |  | note | – Kerb and Channel
label | 372ad021-06fa-5429-ae2b-6b180668a5c7 |  | note | – Underground Services
label | 36904865-5807-5da0-abe7-40a831c1dc73 |  | note | – Service Covers
label | bf74282a-bae7-5003-a4cd-219fb2cd932e |  | note | Controlled By : (Position) - Project Manager
label | c17b4027-734e-5576-ae55-908117576ac4 |  | note | Accept / Reject Criteria - Visual Check
label | da07b11e-5e00-5b12-8da1-5b3c0a524fa3 |  | note | Frequency Of Inspection Or Test - Once
label | 3e8b9c8c-f055-59c9-9a33-5da04cf7e964 |  | note | Spec. Ref, Procedure Or Method Statement - Constructed to design drawings and relevant standards
label | 79e66a3f-d582-54b7-b2ba-6fd894569988 |  | note | Records Required - YES
label | 79042cbc-842e-523c-9e27-e4eab55e60c2 |  | note | DOWNER ENGINEER - H
label | fa59d145-9ac3-5825-a88e-e977e600aab5 |  | note | SUPERVISOR - R
label | 2351031c-8850-51f2-af8f-6c4b50dc053c |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Preparatory Work (3.4 - SubSoil Drainage)
checkpoint-status |  |  | checkpoint | 3.4.1 - Subsoil Drain Construction
label | 1ba7c43d-998c-5e7c-897b-959752ee9890 |  | note | Controlled By : (Position) - Construction Foreman
label | 8c2d85ef-f924-5e11-9ef3-84445e575130 |  | note | Accept / Reject Criteria - Visual Check
label | c21711ff-fa10-5d1b-9406-99a2e9848a82 |  | note | Frequency Of Inspection Or Test - each site
label | 593e3d31-bbba-568f-80cf-a1371fffe9c7 |  | note | Spec. Ref, Procedure Or Method Statement - As per design drawings and/or NZTA F/2 Specification (if required or specified)
label | 799798fe-3de5-529a-ad18-d06cb4009965 |  | note | Records Required - YES
label | 26a9327f-0515-5f8e-8c72-08f46674a929 |  | note | DOWNER ENGINEER - W
label | 62277c6f-6aeb-5b1d-a025-ca4995214afa |  | note | SUPERVISOR - R
label | 18493aa0-653b-5587-8c78-50d5724d78d4 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4.2 - Inlets/Outlets
label | ccb51f0d-d5de-5937-85d1-fb0014ee8e95 |  | note | Controlled By : (Position) - Construction Foreman
label | c978b71b-446f-518e-a177-695d2dc5b101 |  | note | Accept / Reject Criteria - Visual Check
label | 7dfd5658-57ee-5e87-94ae-fe7c1dc996a9 |  | note | Spec. Ref, Procedure Or Method Statement - Connect to sump/catchpit, Concrete Apron, Open Channel, Inspection Eyes.
label | 5c603f6e-da34-5c36-a002-b7588805726d |  | note | Records Required - YES
label | 58c2490e-a4ad-5642-9d67-6db897a59c83 |  | note | DOWNER ENGINEER - W
label | ff074a59-71e2-5ff9-b7b4-d1bd7faa0981 |  | note | SUPERVISOR - R
label | 2ebfc674-9964-57cf-8b55-47952fe835a0 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Preparatory Work (3.5 - Pavement Widening and Digouts)
checkpoint-status |  |  | checkpoint | 3.5.1 - Excavation
label | 19a71712-f239-5108-b2ec-11533ecfb163 |  | note | Controlled By : (Position) - Construction Foreman
label | deac5d75-7b10-5180-b03d-be596e999f97 |  | note | Accept / Reject Criteria - Onsite/Scala Test
label | 43d3c18f-95dd-5dbb-8fc7-578a48079f63 |  | note | Frequency Of Inspection Or Test - Scala Test at each Chainage (L & R Shoulders)
label | ba0c61b8-738e-56f8-8884-14a3a570641c |  | note | Spec. Ref, Procedure Or Method Statement - Subgrade CBR to be valiodated with design report. See section 5.4 refer to existing depth
label | 6967fd9b-4901-5b81-a598-c871985a4d53 |  | note | Records Required - YES
label | 409a58dd-8a90-53bc-a9a9-1fd6847863ba |  | note | DOWNER ENGINEER - H
label | 829c836d-3dba-5efc-bacf-64c4ded18b3b |  | note | SUPERVISOR - R
label | b9e3282b-5662-51ec-be06-2cb318fcb8d8 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5.2 - Subbase Material Properties
label | 2ffacc25-6724-57cb-934d-2b62722350c2 |  | note | Controlled By : (Position) - Project Manager
label | 5d6d4dcf-ee09-5218-9ec2-55f079c2a35f |  | note | Accept / Reject Criteria - TNZ M/3. 1986 (Lab Testing where instructed as part of M/3 Guidance)
label | 342f7658-1cc1-5f7a-99fb-5c7c004df00c |  | note | Frequency Of Inspection Or Test - Once
label | 18adaeb1-c2d0-50f8-ac94-e91bee19499e |  | note | Spec. Ref, Procedure Or Method Statement - Meet speeding design requirements or NZTA M/3 guidance
label | 6a2e1f55-9e61-5991-a8c2-f1bcc4a1d2a8 |  | note | Records Required - YES
label | 0ebbe9e6-5d2f-5c5f-9b83-270f88bd06e9 |  | note | DOWNER ENGINEER - H
label | 21aaa655-594a-50e8-9436-252e60753d63 |  | note | SUPERVISOR - R
label | 2122b163-687f-58a6-bd97-8feaf4989e95 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5.3 - Density Lab testing in accordance with B/2. Only required if new subbase construction is within the carriageway line. If no compaction testing under sealed shoulders. (1)
label | 63e5e247-9299-5520-99aa-37c673b24e29 |  | note | Controlled By : (Position) - Project Manager
label | 9fe55fd9-4e23-5953-b7a7-c3169a8fd4af |  | note | Accept / Reject Criteria - OWC as determined in the lab.
label | 4690a803-276b-53b7-a3d6-80491125a334 |  | note | Frequency Of Inspection Or Test - The lesser of:
label | 889b9a94-7dd4-5e76-9e71-97cb35d9bbb4 |  | note | a) 1 test per stockpile or new seam
label | 2b171354-26bb-516b-b01a-7090c878d8ba |  | note | b) 1 test every 5000m2 (in place)
label | 08bee9ad-2a75-58bb-87b5-aebac98a747b |  | note | Spec. Ref, Procedure Or Method Statement - NZS 4407:1991 Solid Density Test 3.7, TNZ B/2: 2005
label | 8420d4cb-500a-54d8-9800-2e7d5df8332e |  | note | Records Required - YES
label | 1841fce1-a248-5471-b275-b54a7a215f03 |  | note | DOWNER ENGINEER - H
label | cd237359-60c4-53ad-80f8-67ec0328fd7b |  | note | SUPERVISOR - R
label | f2cd1bce-719b-54ec-9b08-cabf0eb07be5 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5.3 - Density Lab testing in accordance with B/2. Only required if new subbase construction is within the carriageway line. If no compaction testing under sealed shoulders. (2)
label | 14f9b906-8cfa-5c4f-86ce-59e2bca5b37a |  | note | Controlled By : (Position) - Project Manager
label | 7b9d1d93-5880-553a-b356-187654b530a7 |  | note | Accept / Reject Criteria - When sampling stockpile for lab, take NDM for W/C offset. Record moisture content and take sample from beneath NDM to dry in the oven. (Two W/C readings and samples)
label | e1593aa2-f30c-5f2b-a1d9-6d0d4e30c8e6 |  | note | Frequency Of Inspection Or Test - The lesser of:
label | 78fcb66c-1902-584b-9f59-b3b99a3db394 |  | note | a) 1 test per stockpile or new seam
label | 86fe2200-ffec-5d54-a2d8-4b6fd4e4a206 |  | note | b) 1 test every 5000m2 (in place)
label | 668b5fee-6e0b-5e84-bf01-849b2f6488fe |  | note | Spec. Ref, Procedure Or Method Statement - NZS 4407:1991 W/C Test 3.7, TNZ B/2: 2005
label | 1ac0641a-6ebe-5530-a3ad-bafc011e2989 |  | note | Records Required - YES
label | 293ea682-a2bf-593b-8026-270f1d45c4be |  | note | DOWNER ENGINEER - H
label | 0e9ad409-bf33-54dc-b2e1-078f13f8bf28 |  | note | SUPERVISOR - R
label | 2bd5c0fd-6be5-535f-88f6-6758166a853f |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5.3 - Density Lab testing in accordance with B/2. Only required if new subbase construction is within the carriageway line. If no compaction testing under sealed shoulders. (3)
label | 8982cdf3-19b5-5fd6-bd5b-5e7faa4b5411 |  | note | Controlled By : (Position) - Project Manager
label | 50df6f6d-a58b-5c83-ab3a-060c308f8992 |  | note | Accept / Reject Criteria - MDD as the higher of the two results from lab and field. Ensure plateau test is done at OWC from Lab Value and with NDM moisture offset.
label | 829abb7c-a166-57c2-8666-d6694b072ad9 |  | note | Frequency Of Inspection Or Test - The lesser of:
label | 959c8a12-81aa-5ffc-a3cc-2a560182a623 |  | note | a) 1 test per stockpile or new seam
label | ec4e23dc-1bd9-5413-a65d-80fb4836e97e |  | note | b) 1 test every 5000m2 (in place)
label | d013d680-67ed-5320-9c35-8bb5bd14b83e |  | note | Spec. Ref, Procedure Or Method Statement - NZS 4402: 1986 MDD and W/C Test 4.1.3, TNZ B/2: 2005
label | 8f7b30e0-0b7f-55d0-b36c-7f1abb16e482 |  | note | Records Required - YES
label | 444fa27d-e4b3-5749-bde9-746aa68007a1 |  | note | DOWNER ENGINEER - H
label | 2fc3e5cb-d7c3-5700-8000-117bb000b8d0 |  | note | SUPERVISOR - R
label | b9c94dfb-0d03-5f5f-b540-fe305becd925 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5.4 - Construction only required when new construction is in carriageway lane. If no compaction testig under sealed shoulders
label | 06ad8478-8d7a-55f2-a173-d94c94186a7b |  | note | Controlled By : (Position) - Project Manager
label | 0c09ad24-980d-5383-9f49-3adfba765580 |  | note | Accept / Reject Criteria - Subbase:
label | 0491c903-0bf0-5f1f-9db8-820faade9b58 |  | note | ○ Average ≥ 95% MDD
label | 5efba8a8-745d-59b5-9c24-da6e5553c2d1 |  | note | ○ Minimum ≥ 92% MDD
label | a3bbd849-f170-50dd-b689-afe87b0375d5 |  | note | Frequency Of Inspection Or Test - 5 test per homogenious lot of upto 1000m2 of laid pavement
label | 00342c4b-ca04-568d-a349-cab4c8e9855b |  | note | Spec. Ref, Procedure Or Method Statement - NZS 4407: 1991 Test 4.2.2. TNZ B/2: 2005
label | 7b53c071-f437-5070-ac94-c7fcdb401980 |  | note | Records Required - YES
label | effcf0fa-e353-53d0-97eb-cd880d3faf8c |  | note | DOWNER ENGINEER - H
label | 538647f2-bbc3-57f8-bb4f-1236a06a4158 |  | note | SUPERVISOR - R
label | 78b2fa3e-4e00-5071-8f06-a4be86e47204 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4 - Pavement Including Sealed Shoulders (4.1 - Imported Basecourse Material Testing)
checkpoint-status |  |  | checkpoint | 4.1.1 - Production Properties - Note: Running course to be produced from the same type and source of material as the basecourse. (1)
label | 8f102f36-7fa4-5867-95ac-0d9db1f944c3 |  | note | Controlled By : (Position) - Project Manager
label | 308d1326-6d49-5494-ac9e-a6acdf902b85 |  | note | Accept / Reject Criteria - 1 - 400m3 – 2 tests
label | 6772f3aa-0339-54cf-86b9-fe6f32a6d8d1 |  | note | ○ 400 - 1500m3 - 3 tests
label | 06bdc85e-6209-575a-a4f7-e0890186f88b |  | note | ○ 1500 - 4000m3 – 4 tests
label | 61ab97c4-875f-5a89-824a-fd458983b9a0 |  | note | ○ >4000m3 – 1 test per 1000m3
label | 30d8a73b-d96d-5bd1-80ac-0026aad6b686 |  | note | Frequency Of Inspection Or Test - TNZ M/4: Cl.4.2.3
label | 67b22443-bd21-5ad0-a65a-a6f16c185793 |  | note | Spec. Ref, Procedure Or Method Statement - TNZ M/4:2006, NZS 4407 :1991 Test 3.8.1
label | 327fb4f5-500a-5801-9bf0-ebc4d87bcdfa |  | note | Records Required - YES
label | ca49ee6a-5053-5166-8561-60bbfd102edc |  | note | DOWNER ENGINEER - H
label | 079f942c-06a2-50f5-8609-468c0e8884ed |  | note | SUPERVISOR - R
label | faae3109-9834-5048-93a3-4545307445d9 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.1.1 - Production Properties - Note: Running course to be produced from the same type and source of material as the basecourse. (2)
label | 040b4fd9-0ff6-5f36-8e72-083e55af7188 |  | note | Controlled By : (Position) - Project Manager
label | 8e7e0a73-c06d-5551-9b82-80a424aef4c4 |  | note | Accept / Reject Criteria - 1 - 400m3 – 2 tests
label | d8b76769-310f-55b4-90c5-895f1361bdec |  | note | ○ 400 - 1500m3 - 3 tests
label | 515a268b-27b0-5325-bca3-5a068c6de457 |  | note | ○ 1500 - 4000m3 – 4 tests
label | 622beff4-3638-523a-8618-3c9f81f39265 |  | note | ○ >4000m3 – 1 test per 1000m3
label | 5dc9f336-57cd-5cbd-abe6-0d7d3bc4d508 |  | note | Frequency Of Inspection Or Test - Aggregate broken face content in each of the three aggregate fractions between 37.5mm and 4.75mm ≥ 70% by weight and has 2 or more broken faces
label | d7a5d24c-5adf-5e97-bd51-5d01ca19ad3f |  | note | Spec. Ref, Procedure Or Method Statement - TNZ M/4: 2006, NZS 4407 :1991 Test 3.14
label | 9c85c17f-9837-5fff-9a71-8aa0ce7a160e |  | note | Records Required - YES
label | 35365e2a-16f9-543d-af9c-4be467b1bc72 |  | note | DOWNER ENGINEER - H
label | 93f7718a-da99-54d0-816f-e953964d5a0d |  | note | SUPERVISOR - R
label | fcd73d07-1803-5d39-af38-c0765a992e16 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.1.1 - Production Properties - Note: Running course to be produced from the same type and source of material as the basecourse. (3)
label | 619bc95e-aba0-5dd6-a5d4-b0388c268b84 |  | note | Controlled By : (Position) - Project Manager
label | e45b8e3e-d40f-58e8-9694-691ca333c6b3 |  | note | Accept / Reject Criteria - 1 - 400m3 – 2 tests
label | de35554c-0de1-5968-986c-04d878af425c |  | note | ○ 400 - 1500m3 - 3 tests
label | b5bc6d0e-0d09-59a0-b69e-4a2d3af930c4 |  | note | ○ 1500 - 4000m3 – 4 tests
label | 077f7269-112e-5723-937c-2937a21d90aa |  | note | ○ >4000m3 – 1 test per 1000m3
label | 5b404430-4322-51dd-ae74-5e3122c2898f |  | note | Frequency Of Inspection Or Test - Sand equivalent > 40
label | 19317d05-a9ea-5cee-b1fd-233864eb275d |  | note | Spec. Ref, Procedure Or Method Statement - TNZ M/4: 2006, NZS 4407 :1991 Test 3.6
label | 7395d071-cfa5-520b-8d0e-ceadaf858281 |  | note | Records Required - YES
label | d719342c-da27-5d44-9228-4e425d119ccc |  | note | DOWNER ENGINEER - H
label | d47d1ddf-652e-52f3-95d9-30e755aedb34 |  | note | SUPERVISOR - R
label | 9c2e7200-fdd3-598b-8961-0d841c774509 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.1.1 - Production Properties - Note: Running course to be produced from the same type and source of material as the basecourse. (4)
label | 8ed3081b-5a5b-57a2-b7e5-b3e321bf021e |  | note | Controlled By : (Position) - Project Manager
label | 441f873c-4463-5d22-8e17-2ff50856f804 |  | note | Accept / Reject Criteria - 1 - 400m3 – 2 tests
label | fdb58255-dd73-5aaa-9541-9cfac2e0e40d |  | note | ○ 400 - 1500m3 - 3 tests
label | b45bb44f-0a38-5261-bfa0-755aa41fcdba |  | note | ○ 1500 - 4000m3 – 4 tests
label | 5388985f-07af-5f23-808d-9c6c278a397b |  | note | ○ >4000m3 – 1 test per 1000m3
label | 54d35738-79a2-5183-9570-6313ccb0e0f6 |  | note | Frequency Of Inspection Or Test - NB Downer Policy that only SE compliant basecourse allowed unless stabilised
label | 819d9e50-4f67-5411-9c99-5e7a058d061b |  | note | Spec. Ref, Procedure Or Method Statement - TNZ M/4: 2006, NZS 4407 :1991 Test 3.6
label | bfa84789-3ce5-5fff-80f3-99d240d0c89e |  | note | Records Required - YES
label | 058d3334-3830-57d8-8bd2-0fdc259659ad |  | note | DOWNER ENGINEER - H
label | 1a19bd31-ea00-537f-b566-65b1dad060a5 |  | note | SUPERVISOR - R
label | a5cbb8f0-e2f5-560d-8380-da65667571e2 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.1.1 - Production Properties - Note: Running course to be produced from the same type and source of material as the basecourse. (5)
label | ee62643f-5c71-5718-8169-2d6c1591ff87 |  | note | Controlled By : (Position) - Project Manager
label | 14c79fee-0cbd-537d-b645-70c0fa10575f |  | note | Accept / Reject Criteria - 1 - 400m3 – 2 tests
label | 664f7f2d-d787-5e99-80de-c6d2f2821d95 |  | note | ○ 400 - 1500m3 - 3 tests
label | 331fb8db-4e11-5e3b-939e-ea2d45a7203c |  | note | ○ 1500 - 4000m3 – 4 tests
label | 0067ac99-4cd5-5a02-9551-2dabdce5bac3 |  | note | ○ >4000m3 – 1 test per 1000m3
label | 05d1e6f3-e70d-5dcd-93fe-c914c85d1272 |  | note | Frequency Of Inspection Or Test - PI ≤ 5
label | 58f140e7-96a7-57eb-8236-b0e8e7b95f73 |  | note | Spec. Ref, Procedure Or Method Statement - TNZ M/4: 2006/NZS 4407:1991 Test 3.4
label | b17b8af3-1266-54e6-bb45-b408ecda7bae |  | note | Records Required - YES
label | 5989ac11-6846-5c4d-af71-563423ea0fd4 |  | note | DOWNER ENGINEER - H
label | e6b3a449-b4dd-5879-a3ce-a88c474c7fcd |  | note | SUPERVISOR - R
label | 015efb25-f2e0-5c6d-808b-29ad6405fe0d |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.1.2 - B/02 Lab Testing (1)
label | e9df1ead-aaf3-5f37-9064-4fef0e6ce47c |  | note | Controlled By : (Position) - Project Manager
label | 38bf433b-2500-5c26-9639-0769fb59e894 |  | note | Accept / Reject Criteria - The lesser of:
label | 4678d4c7-16b5-54c7-83b7-50bf21c04a8f |  | note | a) 1 test per stockpile or new seam
label | c49b8bc6-3821-5ef0-b9b6-75b89506be05 |  | note | b) 1 test every 5000m2 (in place)
label | 6228440d-1f7d-5b3f-a15f-816a71dc84d5 |  | note | Frequency Of Inspection Or Test - OWC as determined in the lab.
label | 2c102e50-445c-5347-aa67-689f351fb2ba |  | note | Spec. Ref, Procedure Or Method Statement - NZS 4407:1991 Solid Density Test 3.7, TNZ B/2: 2005
label | 33cfcd24-8e43-53d6-8503-4da064e0ebb3 |  | note | Records Required - YES
label | 57952af9-62bb-5108-a6da-af7f09e2212e |  | note | DOWNER ENGINEER - H
label | fc0bbb8a-954b-542c-a96b-8f7007876c70 |  | note | SUPERVISOR - R
label | f63641d2-cbc2-5710-90e3-846f868b97e5 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.1.2 - B/02 Lab Testing (2)
label | 23bf2fca-8540-5f23-8696-f1b11fd33b63 |  | note | Controlled By : (Position) - Project Manager
label | 954ba547-06a0-5a40-add0-0d6bb9a4b282 |  | note | Accept / Reject Criteria - The lesser of:
label | 03591193-b5f5-5f59-89d1-bdbb8308a0a8 |  | note | a) 1 test per stockpile or new seam
label | 57770051-74fd-5cef-a2b4-707d190aea86 |  | note | b) 1 test every 5000m2 (in place)
label | b04b38b6-93ca-5e06-b543-b2c742f1df52 |  | note | Frequency Of Inspection Or Test - When sampling stockpile for lab, take NDM for W/C offset. Record moisture content and take sample from beneath NDM to dry in the oven. (Two W/C readings and samples)
label | 66dc22da-2c27-59c1-aaa7-bfbd403b747f |  | note | Spec. Ref, Procedure Or Method Statement - NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005
label | e4ccbcbd-d28a-5c2f-adc1-0c555b62f44f |  | note | Records Required - YES
label | 0fb29395-82dd-5c4e-abda-94bce384ee97 |  | note | DOWNER ENGINEER - H
label | 98eda607-ee21-5af7-82cf-2a4ef85b5983 |  | note | SUPERVISOR - R
label | 4467c58a-23e1-5e95-92f5-27de9eaeeeeb |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.1.2 - B/02 Lab Testing (3)
label | df70c0a0-77a2-56cd-96ee-4bf3e5a102ad |  | note | Controlled By : (Position) - Project Manager
label | e52ed476-d6a0-516f-a35d-54ff11eac29a |  | note | Accept / Reject Criteria - The lesser of:
label | a7e5f772-ebff-5da1-bef4-416b177de110 |  | note | a) 1 test per stockpile or new seam
label | 5ef753b9-d2ab-5f42-adf9-28b1e51e26a2 |  | note | b) 1 test every 5000m2 (in place)
label | 4e1641b6-6142-5450-8d30-f5edab0cfea0 |  | note | Frequency Of Inspection Or Test - MDD as the higher of the two results from lab and field Ensure plateau test is done at OWC from Lab Value and with NDM moisture offset
label | cd9d9617-738a-50b8-bb83-34c92a2c837e |  | note | Spec. Ref, Procedure Or Method Statement - NZS 4402: 1986 MDD and W/C Test 4.1.3 TNZ B/2: 2005
label | cdb9006a-b333-5346-aed9-39e3ea36c3c3 |  | note | Records Required - YES
label | 13d54edc-4221-5d26-be02-6e90e87df4d4 |  | note | DOWNER ENGINEER - H
label | 567da260-608f-5179-b621-d0d1d8b5d328 |  | note | SUPERVISOR - R
label | 62859fe3-f2c3-5888-9475-5726c50e826e |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.1.3 - Source Properties Note: Running course to be produced from the same type and source of material as the basecourse (1)
label | f9acfaf5-9112-5cb3-a548-c24548f891c9 |  | note | Controlled By : (Position) - Project Manager
label | 721e1c15-e4e7-5048-b720-eac59958a9cd |  | note | Accept / Reject Criteria - Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve
label | 7ddf3558-cae3-5261-8b3c-4636d5ca5bf3 |  | note | Frequency Of Inspection Or Test - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | ea20a42d-e4b8-5788-908c-53ecceddb9b3 |  | note | Spec. Ref, Procedure Or Method Statement - TNZ M/4: 2006, NZS 4407 :1991 Test 3.10
label | 5ba6e3a1-4a7c-596e-af56-0c2e0b3aa2f2 |  | note | Records Required - YES
label | f67cfe9a-9ad1-5524-9d8a-5d780c8e6535 |  | note | DOWNER ENGINEER - H
label | 74a70337-0037-5beb-ac2c-8364394b4be9 |  | note | SUPERVISOR - R
label | d01eb8b2-84d5-5afe-848e-12152bd137cd |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.1.3 - Source Properties Note: Running course to be produced from the same type and source of material as the basecourse (2)
label | db3434fb-a403-5748-a267-698ae8814114 |  | note | Controlled By : (Position) - Project Manager
label | b7eab27a-336a-5c41-b629-d2a12743a982 |  | note | Accept / Reject Criteria - Soaked CBR ≥ 80% when compacted/tested in accordance with both tests
label | 4986a954-eebf-5e60-b898-108f07fe60ff |  | note | Frequency Of Inspection Or Test - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | ff7749d8-00fc-57db-b32f-2541fa2776a1 |  | note | Spec. Ref, Procedure Or Method Statement - NZS 4402: 1986 Test 4.13
label | a764a4fc-eabe-5629-844d-95a98c829dc8 |  | note | Records Required - YES
label | 38605389-0f4b-5c74-b679-b195b70c67a1 |  | note | DOWNER ENGINEER - H
label | 6d61074b-e5e7-5b94-9e30-0737149aabdc |  | note | SUPERVISOR - R
label | 50375cc2-8dc4-5667-9739-6d4897973fbb |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.1.3 - Source Properties Note: Running course to be produced from the same type and source of material as the basecourse (3)
label | f1ca97dd-478e-52d1-b134-1f71d4c589c5 |  | note | Controlled By : (Position) - Project Manager
label | d5f345af-dce3-5178-b041-83150e69a595 |  | note | Accept / Reject Criteria - Must have quality index of AA, AB, AC, BA, BB or CA
label | d1b8b986-ba91-5301-971a-93dee8b40e57 |  | note | Frequency Of Inspection Or Test - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | 4ebcbf94-5860-5744-82fd-ab86f1db58ae |  | note | Spec. Ref, Procedure Or Method Statement - NZS 4407: 1991 Test CBR 3.15
label | 2aa82676-62b1-5573-838d-959b3e8b0373 |  | note | Records Required - YES
label | 7dd06bdf-0748-50f7-af81-ac4c48a4a590 |  | note | DOWNER ENGINEER - H
label | 49107347-9784-5b52-b981-05f555c913d8 |  | note | SUPERVISOR - R
label | 37866d09-6531-55d0-9f3c-5289e51397bd |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.1.3 - Source Properties Note: Running course to be produced from the same type and source of material as the basecourse (4)
label | 388890cd-8f13-5b08-ac17-30c95860540e |  | note | Controlled By : (Position) - Project Manager
label | 0dbf03ae-f2a9-5416-8eb9-a7394d40acf9 |  | note | Accept / Reject Criteria - T15 Specification
label | 122f35f9-805d-58a4-8a29-e9bece69cdd0 |  | note | Frequency Of Inspection Or Test - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | 16826d82-0d03-5c09-b1e2-fea663b6335a |  | note | Spec. Ref, Procedure Or Method Statement - TNZ M/4: 2006
label | fc4e3af6-e880-51c7-bb7d-6c556d1164e7 |  | note | Records Required - YES
label | bd54c54a-34e9-5b36-b7ea-7b62af877301 |  | note | DOWNER ENGINEER - H
label | 30cee3d3-2564-5b19-827e-df88ccfaef94 |  | note | SUPERVISOR - R
label | 0f856615-4910-59af-b29a-8cb94f348e1c |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.1.3 - Source Properties Note: Running course to be produced from the same type and source of material as the basecourse (5)
label | 62917154-b506-506d-92d4-b60a3b2ce2d5 |  | note | Controlled By : (Position) - Project Manager
label | 88318644-28aa-58fd-9187-20a4daf12db4 |  | note | Accept / Reject Criteria - T15 Specification
label | 97de0c59-c8bc-5f46-983d-0d6f21e81cb4 |  | note | Frequency Of Inspection Or Test - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | f6926ed8-9c08-5265-b65b-d3e0781aaaa2 |  | note | Spec. Ref, Procedure Or Method Statement - TNZ M/4:2006
label | 76c932ad-06cd-5aa2-ab77-60b7a2482f39 |  | note | Records Required - YES
label | 7bed57c4-0203-5a2e-b996-8b459baccc32 |  | note | DOWNER ENGINEER - H
label | 76b0561d-c927-5a57-b59b-e108c9f6a350 |  | note | SUPERVISOR - R
label | b13b90f5-0d2b-5622-b43e-88df59809962 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4 - Pavement Including Sealed Shoulders (4.2 - Construction QA)
checkpoint-status |  |  | checkpoint | 4.2.1 - Pavement Surface Scarification
label | a906a2a7-efe6-5396-9ccc-b5af9a0210b9 |  | note | Controlled By : (Position) - Project Manager
label | a72413f5-4ae1-5b55-b2e6-df9b18e1c6ba |  | note | Accept / Reject Criteria - Overview of underlying defects that may required digout/replace
label | 7f5b4585-d6c0-5793-897f-281345a10804 |  | note | Frequency Of Inspection Or Test - Visual Inspection after milling
label | dcdb9760-2e94-56fa-8ac5-2c1ffd22fe68 |  | note | Spec. Ref, Procedure Or Method Statement - Photographic condition of surface condition and visual inspection record
label | 4a6f89e6-d3a0-5e1a-a3ea-e2d3408b9274 |  | note | Records Required - YES
label | e835ba7c-ffa6-5cef-b132-be9225243e80 |  | note | DOWNER ENGINEER - H
label | b371c57e-841c-5d71-b0eb-c95954c4ef8c |  | note | SUPERVISOR - R
label | 947fe922-050c-588e-89c0-aea31a3a41a9 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2.2 - Pavement Surface Milling
label | eeb76225-4a52-5180-92d2-f0f88e489e5c |  | note | Controlled By : (Position) - Project Manager
label | 3fec2d40-12e0-5697-8cb7-6a099630fc09 |  | note | Accept / Reject Criteria - Depth gauge every 60m. Sample record of cement by weight every 60m.
label | 0c14c5b7-d744-5c0b-9492-182dc0d7a5fe |  | note | Frequency Of Inspection Or Test - Visual Inspection during/after milling
label | a74db105-e9cf-579e-b6ad-5206e16f7e1b |  | note | Spec. Ref, Procedure Or Method Statement - Photographic record of milled surface, data records of cement spread and milling depth. Cement 5% by weight (20.52kg/m²). Milling Depth 180mm.
label | 36a483e8-d8b3-5fef-878e-c220cbe83129 |  | note | Records Required - YES
label | 0aa3c697-376a-56b4-90ea-7ef71ee05e1d |  | note | DOWNER ENGINEER - H
label | 933a3ccd-e74d-53b4-88db-e1677d69e6e3 |  | note | SUPERVISOR - R
label | b8444bd8-afd2-55e9-9cdc-49376739cadb |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2.3 - Compaction
label | 926f73b2-f1b9-5e7b-b5b3-ec4e48c952c9 |  | note | Controlled By : (Position) - Project Manager
label | d1322a4a-c4fd-5f63-a58e-8c26a8394469 |  | note | Accept / Reject Criteria - Basecourse:
label | a2133d87-550a-5a2c-a1ef-25236ebc8830 |  | note | ○ Average ≥ 98% MDD
label | 1d0c2e14-a3f7-5c22-be94-fbb72a056023 |  | note | ○ Minimum ≥ 95% MDD
label | 44326329-d65f-5e37-b7b2-ffa6853d4b27 |  | note | Frequency Of Inspection Or Test - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | 4ed10d59-5e63-5e1f-9e64-2eda08bf501b |  | note | Spec. Ref, Procedure Or Method Statement - NZS 4407: 1991 Test 4.2.2. TNZ B/2: 2005
label | e16b218c-dac7-54dd-a2c7-701788a86b8f |  | note | Records Required - YES
label | 4e289a45-a1ff-5d69-b14c-d68b64ab03d4 |  | note | DOWNER ENGINEER - H
label | 8860f681-7d4f-585d-99f8-21d6c74d3e71 |  | note | SUPERVISOR - R
label | 592a3646-7a79-5902-94ec-5e5595b6ada4 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2.3 - Degree of Saturation (DOS)
label | 994d785a-fb7a-51d9-b002-357c2dc3bcc3 |  | note | Controlled By : (Position) - Project Manager
label | 8ecbdf4d-c812-5bdf-b471-d15149a3caab |  | note | Accept / Reject Criteria - Subbase:
label | 48c2a005-b2b3-5ad6-9022-ab94e8a7b966 |  | note | ○ Average ≥ 95% MDD
label | d71b6e8e-9d24-52dd-b6c7-4eb8d53f3fae |  | note | ○ Minimum ≥ 92% MDD
label | a204c832-55f4-5881-9df1-a2d79029268a |  | note | Frequency Of Inspection Or Test - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | f03d2c15-3f62-51c3-b920-6186a94604b7 |  | note | Spec. Ref, Procedure Or Method Statement - NZS 4407: 1991 Test 4.2.2. TNZ B/2: 2005
label | 64a826a8-bc26-5cec-b306-3f3598c178d1 |  | note | Records Required - YES
label | d9c5762b-3d81-5838-9260-def7a85ad6d4 |  | note | DOWNER ENGINEER - H
label | 45fcdfc7-339e-5c9d-94aa-a43d94761180 |  | note | SUPERVISOR - R
label | 28603540-505b-572e-ba48-6d6e4690ff7c |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2.4 - Surface shape/profile Layer thickness (1)
label | 3b02bc64-f505-521e-8b26-92fd9f9831ae |  | note | Controlled By : (Position) - Project Manager
label | 1424cbcc-1b7b-59bc-861c-51d0d31fc728 |  | note | Accept / Reject Criteria - Visual inspection, Cut/fill tolerance check, Straight edge
label | e439783b-cb19-5715-886b-50bf0114943f |  | note | Frequency Of Inspection Or Test - 1 test per 60m
label | 0f86af62-fdd0-59a0-9ffc-9650f9c6d202 |  | note | Spec. Ref, Procedure Or Method Statement - ≤10mm variance from 3m straight edge.
label | 82163442-657e-5530-896b-6494560c3823 |  | note | Records Required - YES
label | 11d7b2c0-b794-50bb-a670-12854d43a25b |  | note | DOWNER ENGINEER - H
label | b27cd8e5-1f86-5802-a999-17fbe015968a |  | note | SUPERVISOR - R
label | 926828e5-a0c4-5e96-a00e-531ad75c2c22 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2.4 - Surface shape/profile Layer thickness (2)
label | 22927f31-a4f5-58c7-88be-29f54a6b75b6 |  | note | Controlled By : (Position) - Project Manager
label | cec90565-3f2b-508f-b0c3-d7a33b985ff8 |  | note | Accept / Reject Criteria - Visual inspection, Cut/fill tolerance check, Straight edge
label | 26b48738-fb52-5d37-bd75-391cef92c653 |  | note | Frequency Of Inspection Or Test - 1 test per 60m
label | ce4dd740-6f0a-5aab-a682-607f95550bbc |  | note | Spec. Ref, Procedure Or Method Statement - Gradual deviations
label | c0c11d78-d65f-570e-b3ed-e120c4af7840 |  | note | Records Required - YES
label | 8d6d5222-dd59-53c9-bd76-c5c0d2ad289f |  | note | DOWNER ENGINEER - H
label | 1f4e73ec-6273-5783-baac-86035a4b6a42 |  | note | SUPERVISOR - R
label | b4eb0d2e-3d37-542c-a105-21fa826a13d4 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2.4 - Surface shape/profile Layer thickness (3)
label | e2922b57-bcb3-554b-afe8-01037bb2e07e |  | note | Controlled By : (Position) - Project Manager
label | 1c6d6bf1-b321-5ce4-805a-1507230727e2 |  | note | Accept / Reject Criteria - Visual inspection, Cut/fill tolerance check, Straight edge
label | c1e31670-63f4-5c9e-93bf-273621130db7 |  | note | Frequency Of Inspection Or Test - 1 test per 60m
label | f2c093df-2e7f-5d99-ab81-e67ca9982e73 |  | note | Spec. Ref, Procedure Or Method Statement - No ponding if crossfall > 1%
label | 05f5ebbf-e1c9-5a4c-a0fe-d3ef48472583 |  | note | Records Required - YES
label | 203f74df-599f-5ae1-adbf-dab8d9fdde93 |  | note | DOWNER ENGINEER - H
label | 5d52f061-0043-53cf-ae4c-af1bd67ee507 |  | note | SUPERVISOR - R
label | c3e17140-5125-55c5-93b4-7259278943c3 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2.4 - Surface shape/profile Layer thickness (4)
label | baeb868f-89ea-52d8-8805-fbd9907738ac |  | note | Controlled By : (Position) - Project Manager
label | ace4f59b-38b3-5bae-9d99-b11117b1da07 |  | note | Accept / Reject Criteria - Visual inspection, Cut/fill tolerance check, Straight edge
label | 7e825797-67d8-5cc8-a473-412c20949613 |  | note | Frequency Of Inspection Or Test - 1 test per 60m
label | d189e078-d1c6-5677-8c60-5e14d00085f1 |  | note | Spec. Ref, Procedure Or Method Statement - Overlay Thickness meets design but not >200mm OHS
label | 7bd986b9-ad95-5e05-b083-0bc675bb6576 |  | note | Records Required - YES
label | f3fb6158-3ffd-56b0-8a7f-2b6c81d1c21d |  | note | DOWNER ENGINEER - H
label | d50d6fe7-1590-5f49-8d15-69a7cf4ca470 |  | note | SUPERVISOR - R
label | 1a249490-600f-5521-9025-9a25601e4964 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2.4 - Surface shape/profile Layer thickness (5)
label | 7bd13a22-4282-56de-902a-402f31c0c2a2 |  | note | Controlled By : (Position) - Project Manager
label | 6bf4b412-555e-50d7-926a-d0ef822b5659 |  | note | Accept / Reject Criteria - Visual inspection, Cut/fill tolerance check, Straight edge
label | cf5ddcb4-d8a4-5bae-8409-bcdb4e406d6b |  | note | Frequency Of Inspection Or Test - 1 test per 60m
label | 8cc19e97-709b-5df7-a632-b699ea2b6451 |  | note | Spec. Ref, Procedure Or Method Statement - Finished crossfall between any 2 points more than 2m apart transverse to centreline ±0.5% of design
label | d630c1f4-765c-5f6d-a803-c9c4e3d6ef72 |  | note | Records Required - YES
label | 5f2b22d0-0c0b-58e9-96f0-4cebc87adf60 |  | note | DOWNER ENGINEER - H
label | a7bb95a2-c7de-5075-b9e1-904bd75772cf |  | note | SUPERVISOR - R
label | b45a6255-7026-5ed8-86f5-ca8caa27f8f9 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2.4 - Surface shape/profile Layer thickness (6)
label | f8b3cb6f-803f-59ec-b63b-b6bb992929c7 |  | note | Controlled By : (Position) - Project Manager
label | 371234f5-a16f-54e6-9da3-ab944f615bf0 |  | note | Accept / Reject Criteria - Visual inspection, Cut/fill tolerance check, Straight edge
label | cf1fae94-e0cc-543c-9e49-6c78801e9ba0 |  | note | Frequency Of Inspection Or Test - 1 test per 60m
label | 9dfeda4b-7119-5076-bb1f-00010b92288f |  | note | Spec. Ref, Procedure Or Method Statement - Where lift pegs are used: -5mm +15mm or ±5mm at lip of concrete channel OR GPS level controlled grader
label | ed1dc177-0b13-58e8-80a1-abfc83044f05 |  | note | Records Required - YES
label | a14a6987-7d60-5c3e-a3c1-f79b569d9502 |  | note | DOWNER ENGINEER - H
label | 42a07a84-7d61-5ce1-b22f-665985346527 |  | note | SUPERVISOR - R
label | db4679ea-76b5-5ed3-be12-3b743e636dc2 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2.4 - Tolerances: width unconstrained
label | f019ad66-4fc2-5ab6-9562-62fef589b205 |  | note | Controlled By : (Position) - Project Manager
label | 5c225d0d-b277-5ccc-9e44-356473ea4e78 |  | note | Accept / Reject Criteria - (-20mm / -100mm)
label | c0134db5-6c31-58cc-804a-28f37249c146 |  | note | Frequency Of Inspection Or Test - 2 at every lift peg or per 180 m2
label | 17d4f03d-d027-5371-9fd4-dc0276d55362 |  | note | Spec. Ref, Procedure Or Method Statement - Confirm offset from lift pegs
label | a4208fa8-0d32-5dd3-a61b-d050247f5d77 |  | note | Records Required - YES
label | 8a80f08b-b5cd-5577-9627-d8074ea6b10f |  | note | DOWNER ENGINEER - H
label | 5dc5aea6-d81f-5573-9746-bc05ca4d71e4 |  | note | SUPERVISOR - R
label | 0dcda755-7efe-5b66-baaa-d53f418ffb02 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2.4 - Tolerances: width constrained
label | eb345fa0-aa79-5d6b-b6d5-038e884cf226 |  | note | Controlled By : (Position) - Project Manager
label | 4911ddaa-9dfd-53a8-bc93-9aaac16b537d |  | note | Accept / Reject Criteria - Zero
label | 71f5f7cc-0fe6-54b2-8699-038dfe4c40d7 |  | note | Frequency Of Inspection Or Test - 3 at every lift peg or per 180 m2
label | b53a5be9-bb75-5358-9cb2-cc29550d018b |  | note | Spec. Ref, Procedure Or Method Statement - Stringline or Topo Survey from Leveling system on Grader/lift pegs
label | 1a5e0915-9acf-5ddb-936d-6ce1601cbd6c |  | note | Records Required - YES
label | 053bdeaa-9740-5c86-9511-3d1637aae060 |  | note | DOWNER ENGINEER - H
label | d97e51bd-fad1-5f54-aa15-8b79cb276447 |  | note | SUPERVISOR - R
label | 213ddda1-a91b-50ae-ab87-32576bdaa5c2 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2.4 - Visual appearance
label | 8ce60368-165d-59d2-bcd0-3bd50da664f8 |  | note | Controlled By : (Position) - Project Manager
label | 764fed02-6f9d-5105-a252-1c38cfca3be3 |  | note | Accept / Reject Criteria - No Loose Chip Remaining
label | d9eb1575-4115-5940-a461-ddcac25e61e6 |  | note | Frequency Of Inspection Or Test - Immediately prior to sealing
label | 050b0498-e524-519b-8f16-fe78d30e46d3 |  | note | Spec. Ref, Procedure Or Method Statement - Stringline or Topo Survey from Leveling system on Grader/lift pegs
label | 722794b6-f0c7-518d-be34-6d64a19a7e09 |  | note | Records Required - YES
label | 9b0c2eb5-2e37-596d-a080-db371b047f66 |  | note | DOWNER ENGINEER - H
label | 1176abf3-e2bb-5d92-afe0-2fb2ab3adcff |  | note | SUPERVISOR - R
label | 0e5c612b-f95f-501c-aa1f-420daab1821f |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5 - Shoulder and addition Surfacing Preparation
checkpoint-status |  |  | checkpoint | 5.1 - Slope
label | ee11f817-b81a-5027-b172-6565eccac201 |  | note | Controlled By : (Position) - Project Manager
label | 6c728bee-7c08-52ed-bfa7-59771e82d914 |  | note | Accept / Reject Criteria - Slopes consistent and is at 20% (1:5) grade
label | 1dfbb00e-c199-5918-be78-22d196d179e1 |  | note | Spec. Ref, Procedure Or Method Statement - Visual inspection with smart level
label | d36913f8-f071-5b77-a0a9-0b96114b509b |  | note | Records Required - YES
label | 7d2f755b-6a2e-5d3b-bbf5-d6bfe5554255 |  | note | DOWNER ENGINEER - H
label | a5448864-ca4b-517e-81a0-bce35fa0da69 |  | note | SUPERVISOR - R
label | 197d2cc9-9cd9-5012-a745-d5f6bce5f90a |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 - Compaction
label | e65786eb-559a-5c58-ba78-55ea3c6b399b |  | note | Controlled By : (Position) - Project Manager
label | d9849ec9-f0e9-5d83-a518-f72e27da06a9 |  | note | Accept / Reject Criteria - Vehicles can drive on shoulders without significant indentation/soft surface
label | 002a07c9-d03b-5f88-b137-2ec787f3d67c |  | note | Frequency Of Inspection Or Test - All shoulders
label | 1e7ba0f3-6523-5018-8e6a-54f8f5e84454 |  | note | Spec. Ref, Procedure Or Method Statement - Drive over 4T, check wheeltracks
label | 537d625a-d5ea-55f9-8079-d618e4a5b156 |  | note | Records Required - YES
label | 794241c5-d557-5c0b-a369-348a9cfdf1ef |  | note | DOWNER ENGINEER - H
label | 23ac1627-d1d5-5d5f-993e-2ffb659c20fd |  | note | SUPERVISOR - R
label | bfec6327-5805-58bc-b6bf-bce051fe512f |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Additional Surfacing Preparation
label | 3d4bc2c0-4f6a-5764-8e31-b1ed8edd6ca2 |  | note | – Side Roads
label | 26b33125-441f-5c80-a74b-bbc25c9070d0 |  | note | – Accesses
label | 962b969e-9b57-5cad-99d2-2e57e705a370 |  | note | – Driveways
label | 66845eb4-c103-51d0-98d3-3be3400f7695 |  | note | – Dish Channels
label | b181976d-2924-5fd8-9d5a-ab489da660b6 |  | note | – High Shoulders
label | 0773572a-9ac5-5532-abf4-4b95b7bf4c3e |  | note | Controlled By : (Position) - Project Manager
label | 48b8ef81-bfc4-5515-b2e1-6bbf44140fd0 |  | note | Accept / Reject Criteria - Have all areas of additional surfacing on the design been prepared and marked for sealing?
label | 5b50fde6-f8ca-52a6-bedb-67e68a0fb6e6 |  | note | Frequency Of Inspection Or Test - Before/During Sealing
label | d0b9fa22-b393-55a4-950d-1cf8ce15c8b7 |  | note | Spec. Ref, Procedure Or Method Statement - Per Design
label | 519714cb-77d2-5eec-b498-caaa57047366 |  | note | Records Required - YES
label | 3a628aa5-f48a-5555-a5d0-c0187da04685 |  | note | DOWNER ENGINEER - H
label | ecbbc8a1-14fe-5d3c-a318-afca7930e5e7 |  | note | SUPERVISOR - R
label | 1e03a66d-826b-5f97-8774-6bec64e6754c |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Soiling
label | 9266b077-d5d1-50f5-9bca-1ea0435dd22d |  | note | Controlled By : (Position) - Construction Foreman
label | b1def3bf-dcc4-5a80-bf11-ca4eda6baa14 |  | note | Accept / Reject Criteria - Soiling has been done where required
label | 72ccc18e-48d8-543f-a28c-bd68df94cdda |  | note | Frequency Of Inspection Or Test - All areas requiring grassing
label | 81eb9216-c522-5f1e-adad-f74c3dc6a7f0 |  | note | Records Required - YES
label | 911bb38b-ff4c-500e-aeab-3d6de79591d9 |  | note | DOWNER ENGINEER - W
label | 4f298d52-6019-504c-a85a-3992fdb04edb |  | note | SUPERVISOR - R
label | 7ba33ad3-f1aa-57ae-ae2c-0ba434d61462 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 - Grassing
label | 08ebc28f-2386-562b-9199-4368036704c0 |  | note | Controlled By : (Position) - Construction Foreman
label | 7102d53d-de62-567e-955d-a8b1b167a4ad |  | note | Accept / Reject Criteria - Grassing has been done where required
label | 8e5874f4-7b9f-5a73-aa84-a24fbe1f9ab7 |  | note | Frequency Of Inspection Or Test - All areas requiring grassing
label | 2623e457-b22c-5800-b283-6fb055da381d |  | note | Records Required - YES
label | 40700b99-9f3e-5807-9555-fe202b260c8e |  | note | DOWNER ENGINEER - W
label | d2b4a8b8-ba01-5032-84e8-b26384014e76 |  | note | SUPERVISOR - R
label | 97bdf0a6-f9ca-5d1d-964a-61716f641e05 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6 - Pavement finishing and Surfacing
checkpoint-status |  |  | checkpoint | 6.1 - Completed construction pavement surface = Mosaic surface, Pre-sealing walkover and checks (1)
label | 88009188-35c9-5bdb-a20c-3a1f7eea5402 |  | note | Controlled By : (Position) - NZTA Maintenance Contact Manager
label | e92fd993-9cb1-56c4-b059-1b6dd9bc68cc |  | note | Accept / Reject Criteria - The large aggregate is held in place by a matrix of smaller aggregates. The smaller aggregate is held firmly in place by fine material. The matrix does not displace under normal trafficking or sweeping.
label | 37e58c6d-7d2a-526e-9d82-499de04c5bc8 |  | note | Frequency Of Inspection Or Test - Overview of site for tight mosaic surface
label | 061c3f6f-9686-5b54-a32f-e012fb791ca3 |  | note | Spec. Ref, Procedure Or Method Statement - A clean macro texture with a tight mosaic surface as per Chapter 7 Chipsealing in NZ
label | e841f934-33a3-524e-b928-c032e3ba506d |  | note | Records Required - YES
label | 47883521-a5dc-5f92-aa3c-d85514ad384d |  | note | DOWNER ENGINEER - H
label | 237eabee-9073-50b9-8d47-dcdd400f920d |  | note | SUPERVISOR - R
label | 6c75ee03-fb94-52ab-a221-e17fab0d4552 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.1 - Completed construction pavement surface = Mosaic surface, Pre-sealing walkover and checks (2)
label | 595e1dd5-19e0-54bd-9fe1-45e424e791db |  | note | Controlled By : (Position) - NZTA Maintenance Contact Manager
label | 46ce72ba-239b-5aa1-a4e6-4049298fa1a7 |  | note | Accept / Reject Criteria - All other necessary checks have been done & accepted
label | edd0d0a3-968f-5a76-b7c1-3a6a51e46b8e |  | note | Frequency Of Inspection Or Test - Before sealing
label | 7a1fc5fc-2c26-5a16-96a3-104f7c59e20b |  | note | Records Required - YES
label | a9d0d8cb-3dfd-5d80-9adf-c7cfba246f39 |  | note | DOWNER ENGINEER - H
label | 23041e02-01ad-561e-b4d8-7c25fd65927e |  | note | SUPERVISOR - R
label | 58ce5f32-1770-5a75-a018-4a53aca4c640 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.1 - Completed construction pavement surface = Mosaic surface, Pre-sealing walkover and checks (3)
label | b79c6509-df95-54b8-8314-beed526c3305 |  | note | Controlled By : (Position) - NZTA Maintenance Contact Manager
label | fd1d6d3a-55cf-562c-bba6-2193a9f214fb |  | note | Accept / Reject Criteria - See Sealing ITP
label | 10cf239f-71e0-5a4f-a28d-89eb70472d48 |  | note | Frequency Of Inspection Or Test - See Sealing ITP
label | d1d8f7dc-95d7-5be2-9e45-24042a251ea5 |  | note | Spec. Ref, Procedure Or Method Statement - See Sealing ITP
label | 60208648-a62d-587e-ada7-b80d802e7ceb |  | note | Records Required - YES
label | d6f934d3-f958-5b25-a0ae-64497e0bfee3 |  | note | DOWNER ENGINEER - H
label | d9d1c3cf-1f36-5b78-a4ce-a779c7cfa7f1 |  | note | SUPERVISOR - R
label | 291011f8-e0cc-552b-a3a5-2c1bbb30471b |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2 - Pre-seal Area Check
label | 0bd614f4-c10b-5dbf-926f-399e98db89a8 |  | note | Controlled By : (Position) - NZTA Maintenance Contact Manager
label | ef1cb5d0-b5ed-5bfa-a96a-67d0104bfef2 |  | note | Accept / Reject Criteria - Check prepared and marked area for sealing against design to check whether full area of design ready for surfacing
label | a6929b8e-23ed-5a6e-8594-21fe97b4fed5 |  | note | Frequency Of Inspection Or Test - Before sealing
label | 36446932-3f28-5a8d-bb1f-fccc22fab452 |  | note | Spec. Ref, Procedure Or Method Statement - On Site tape-measure
label | 6db942e3-85cb-5db5-a900-478d8ed73638 |  | note | Records Required - YES
label | 91ad2a60-9123-5682-bda6-7af8f490189a |  | note | DOWNER ENGINEER - H
label | 748bc61a-2ba3-510f-9171-1661592f54d5 |  | note | SUPERVISOR - R
label | 6876b585-ddea-5e56-9bd5-fcfe0dd35501 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.3 - Sealing TMP and aftercare process
label | 06b5b038-bcb6-5789-a221-cf42903a979f |  | note | Controlled By : (Position) - Sealing Manager
label | 50d541a4-a94b-5726-94f1-c2513f201b8f |  | note | Accept / Reject Criteria - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | 60479b3d-b241-5a03-a60f-bffd808eb72e |  | note | Frequency Of Inspection Or Test - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | bfb17789-b915-5d17-89ca-f7c41e63a633 |  | note | Spec. Ref, Procedure Or Method Statement - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | 0d8a07dd-e9ce-572c-ac28-1a32e71472a1 |  | note | Records Required - YES
label | 0102c772-12ad-5545-8595-a26ff91ba079 |  | note | DOWNER ENGINEER - W
label | 365d1d6f-4fbe-552d-8f8c-11a0ea30f2b1 |  | note | SUPERVISOR - R
label | 44b80c9a-9236-5ec2-b779-ada9bc182cf7 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.4 - Sweeping of Sealing works and handover to Roadmarkers
label | 7a51aca5-40de-5a06-88c1-6434869f3edc |  | note | Controlled By : (Position) - Sealing Manager
label | a9a3855f-f0da-501b-80ef-83289c892e2c |  | note | Accept / Reject Criteria - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | a69396b1-679a-5321-90cc-17b21ecb4364 |  | note | Frequency Of Inspection Or Test - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | 21ede985-9c7f-5591-9825-f07cb924814c |  | note | Spec. Ref, Procedure Or Method Statement - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | a19cfb8d-98ab-5612-bba6-e83aad9d34bd |  | note | Records Required - YES
label | 230bdc49-17b6-5919-9db9-a50391601bca |  | note | DOWNER ENGINEER - H
label | 8ae26534-367a-5df8-9f09-91a55063e34e |  | note | SUPERVISOR - R
label | c28e1c7d-561f-5fef-853a-dbd487be06ff |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.5 - Post-seal Area Check
label | db95e4c1-9ee4-5f20-876b-f9429dd430a6 |  | note | Controlled By : (Position) - NZTA Maintenance Contact Manager
label | 5daf8de3-7cdb-55f7-b670-9f8ecb0448f8 |  | note | Accept / Reject Criteria - Check sealed area meets design
label | a4018434-97b5-5bf0-a576-9547de367384 |  | note | Frequency Of Inspection Or Test - After Surfacing
label | 0fc6a8c8-a094-5b24-af89-7a0e8e569692 |  | note | Spec. Ref, Procedure Or Method Statement - On Site tape-measure
label | 3fe91f75-05e8-5030-bc2d-3505f7350cda |  | note | Records Required - YES
label | bf2ef58a-2bec-53cc-a6ef-976ee560f38a |  | note | DOWNER ENGINEER - W
label | fa169ad3-ed5d-52d4-bc16-bbd4c0d39c0e |  | note | SUPERVISOR - R
label | 9f14ccdb-46c6-5d9a-9009-12a39f80ed0a |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7 - Improvements
checkpoint-status |  |  | checkpoint | 7.1 - Improvement guardrails singnage footpaths
label | 16ff5295-0f44-56ed-92f2-c3668efa2dee |  | note | Controlled By : (Position) - Project Manager
label | b6370ef1-9486-5d5f-82d7-69c171671cdb |  | note | Accept / Reject Criteria - Replaced in same position, height etc
label | babc0002-bc4a-5c0b-9d86-7ece4456943a |  | note | Frequency Of Inspection Or Test - All signs/marker
label | 1bca461d-55fc-5cee-812f-ebbffb25cff1 |  | note | Spec. Ref, Procedure Or Method Statement - Visual inspection/TNZ C/20: 2003
label | 35aea109-921f-5118-8719-16098721ce65 |  | note | Records Required - YES
label | 821d03b4-943b-5fa9-bfff-efb975c39e2d |  | note | DOWNER ENGINEER - H
label | b557f0c7-6a9e-58c9-a421-783e0e9d9428 |  | note | SUPERVISOR - R
label | 572b0101-ac88-5471-b58e-593d2f120909 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 8 - Site Reinstatement/Clearance
checkpoint-status |  |  | checkpoint | 8.1 - Roadmarking
label | 1515c815-a2dd-5de0-9454-dec634e02ff0 |  | note | Controlled By : (Position) - Project Manager
label | bd347f0c-8301-5b1d-87f9-3b9307b341b4 |  | note | Accept / Reject Criteria - Visual Inspection
label | 2d446532-6ab7-5193-a610-211de45407e1 |  | note | Frequency Of Inspection Or Test - All markings
label | f6d4addb-88a5-5fc2-b36e-ca00e357220f |  | note | Spec. Ref, Procedure Or Method Statement - Replaced in same position, or per design/MOTSAM
label | ff0e5ea9-3ef7-55fb-88b8-d5ced808c37b |  | note | Records Required - YES
label | 05ae1bba-2c7f-5d15-843d-c126ff39e405 |  | note | DOWNER ENGINEER - H
label | 1a685cd7-9661-5764-83f1-da37b602df51 |  | note | SUPERVISOR - R
label | b44c4ec3-e0fc-5a9d-a526-a3b73472af2c |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.2 - Traffic Services, Marker pegs/ Signs/Markings/RRPMs Replaced
label | a1af448e-fde7-57b3-867a-32d6393d6953 |  | note | Controlled By : (Position) - Construction Foreman
label | fe25aa90-289f-5966-a284-80e67369a19c |  | note | Accept / Reject Criteria - Visual inspection
label | 2381bb36-64ee-5366-8d58-df6693edd31b |  | note | Frequency Of Inspection Or Test - All signs/markers
label | 58e27cd7-1a9d-5e39-aa18-b1f924bde572 |  | note | Spec. Ref, Procedure Or Method Statement - Replaced in same position, height etc/TNZ C/20: 2003
label | 16d2c382-8ac8-56f6-94a1-77b2b4ceadd8 |  | note | Records Required - YES
label | 9668c3a4-a0a3-5633-8afc-77bf8f7d76c3 |  | note | DOWNER ENGINEER - H
label | df18c70b-97c2-5c55-856a-049e44769241 |  | note | SUPERVISOR - R
label | b22819f4-ed21-592a-97b4-c80d3c1f7ea1 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.3 - Draine Cleared
label | 3819b391-f98d-51a4-b466-c3295c27625d |  | note | Controlled By : (Position) - Construction Foreman
label | d27a4733-ad9e-59d8-913a-d3346e54d256 |  | note | Accept / Reject Criteria - Visual inspection
label | 99295fd0-3309-5e2e-a628-4d49a270bb49 |  | note | Frequency Of Inspection Or Test - All drains, after all other works
label | c55a0947-6de8-5619-9490-f019a2f133e2 |  | note | Spec. Ref, Procedure Or Method Statement - Drains are cleared and culvert ends and side (accessway) culverts installed or reinstated
label | 00ed8d1d-8344-5bc0-a1a0-c91fba201236 |  | note | Records Required - YES
label | eb90435e-5092-5669-9b63-8d894150b719 |  | note | DOWNER ENGINEER - W
label | 01a06ae7-e214-5d33-bc98-adb033f59809 |  | note | SUPERVISOR - R
label | 75b0c5ec-1440-57a4-8de0-e68bb86d4d0c |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.4 - Envirnomental Controls Removed
label | 026de75b-6d3f-5986-8889-8ce96c7f68fa |  | note | Controlled By : (Position) - Construction Foreman
label | 2274f938-f0d5-5dfe-a9f3-49cc63acc748 |  | note | Accept / Reject Criteria - Visual check
label | 61c88a74-1738-5759-ab83-63b3111b9601 |  | note | Frequency Of Inspection Or Test - All installed measures
label | e549c61a-1749-5cac-a6c8-bee5658f17e6 |  | note | Spec. Ref, Procedure Or Method Statement - Any silt fences or other controls are removed
label | 94766262-842b-5815-ac9f-5750219c439b |  | note | Records Required - YES
label | 33492164-1b36-5082-97c7-5f873cb38f7e |  | note | DOWNER ENGINEER - W
label | f02fd453-8ef2-5bab-aa2d-0ec9f78ac857 |  | note | SUPERVISOR - R
label | fbd7b544-c74c-53db-8e57-a3fbc5440f0c |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.5 - Traffic Management Removed
label | 008a2371-e150-5c5f-886f-34f03dc11576 |  | note | Controlled By : (Position) - Construction Foreman
label | c519a591-ebb9-56d9-bb21-89378e489570 |  | note | Accept / Reject Criteria - Visual check
label | 9e35a736-2020-5665-a3fd-f7ce7c30c76b |  | note | Frequency Of Inspection Or Test - When safe, after all physical works completed
label | 2655b1e8-e98d-5499-9e86-e85975614f1c |  | note | Spec. Ref, Procedure Or Method Statement - All traffic management removed from site safely
label | e81da04b-9895-5d4e-baa4-172492ad6500 |  | note | Records Required - YES
label | e40ab95a-88bf-54e7-a27a-d15dd83ef263 |  | note | DOWNER ENGINEER - W
label | f4d79ad6-ba7b-5a7b-84fa-0a3d2df03c2d |  | note | SUPERVISOR - R
label | 97298050-58ca-5831-8707-be660d8edc17 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.6 - Site left clean & tidy
label | 7033f7f1-0246-5f4b-8775-5082ca14c3aa |  | note | Controlled By : (Position) - Construction Foreman
label | b4e2d53f-94fb-5674-a5c3-fefde6bfa868 |  | note | Accept / Reject Criteria - Visual check
label | b1543ddb-0568-52cf-99db-4a804c3f3ba7 |  | note | Frequency Of Inspection Or Test - After vacating site
label | 71a437f9-bc35-52e4-8757-51cf85040018 |  | note | Spec. Ref, Procedure Or Method Statement - Stockpiles removed, Plant removed, Litter cleared from site
label | befb8635-8e04-5398-9fbf-ff1d44042626 |  | note | Records Required - YES
label | 72dce761-dc1a-5ac9-9adb-ee644ad51a12 |  | note | DOWNER ENGINEER - W
label | d054ba8f-0871-5096-bace-e0babb3be8bd |  | note | SUPERVISOR - R
label | 241585ca-fa74-5e46-b86b-433bd0a8d36d |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 9 - As Built Records
checkpoint-status |  |  | checkpoint | 9.1 - Collect asset data
label | 2a4596c9-f496-5d13-9ee2-6332b1e993d9 |  | note | Controlled By : (Position) - Renewal Enginerr
label | db8021b7-d395-59db-b564-d3a7e7cbbe06 |  | note | Frequency Of Inspection Or Test - During construction
label | c30f3270-ee7a-5775-ae65-1a8847e4a1d8 |  | note | Spec. Ref, Procedure Or Method Statement - All relevant as built information collected. SHDOM (SM050)
label | baa874b7-086d-5fa3-81f5-1bb1a203a0f9 |  | note | Records Required - YES
label | 659c2d8e-fd18-5a78-a01d-4f5f616a6887 |  | note | DOWNER ENGINEER - W
label | e806932d-eded-5fd8-851d-72c3529b7fb8 |  | note | SUPERVISOR - R
label | 0dfcf733-8748-505f-a76e-e23008f88580 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.2 - Enter asset data into RAMM and/or register(s)
label | 3573fce6-3810-5193-903d-142ceccddeae |  | note | Controlled By : (Position) - Asset Information Manager
label | aaf7cb19-0185-5609-8bff-106503e76873 |  | note | Accept / Reject Criteria - RAMM
label | a785685c-8336-5264-93a2-8c035f264275 |  | note | Frequency Of Inspection Or Test - At completion of work.
label | ef27f8fd-f57e-5d57-9950-f8cef69d29ff |  | note | Spec. Ref, Procedure Or Method Statement - All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.SHDOM (SM050)
label | 7e20a466-e1be-562b-8bb8-9beee4e21c56 |  | note | Records Required - YES
label | 9748d3a7-5e79-5f2f-8e7b-532b47c8280c |  | note | DOWNER ENGINEER - W
label | 910e1d8e-f0d1-5d96-8816-131f5349d1b5 |  | note | SUPERVISOR - R
label | 94b63e6e-a737-5434-a2e1-47897b0275c4 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.3 - Construction Completion Report
label | 8f46e0df-9b63-5fa2-85d0-ce5da88b4c6f |  | note | Controlled By : (Position) - Project Manager/Renewal Manager
label | 1ececb46-dfd4-512a-aba8-64ddba5d875b |  | note | Accept / Reject Criteria - Contract Specification
label | e6a878f8-6a1e-572a-a938-212d3ed0eed3 |  | note | Frequency Of Inspection Or Test - At completion of work.
label | 9cfbebc2-625d-5ba1-b630-332e9577bc84 |  | note | Spec. Ref, Procedure Or Method Statement - Checked and approved
label | 50fa0718-72b8-5d9f-aea5-8a259af6c66c |  | note | Records Required - YES
label | 22d042aa-6be2-5155-903e-6c05d213ab91 |  | note | DOWNER ENGINEER - W
label | b4e68a78-6b92-5614-a4f2-24fd2a75adb2 |  | note | SUPERVISOR - R
label | 8f985e96-766d-58e1-8a18-8074ddbdff51 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair Surface Depression - Rip and Remake Method | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair Surface Depression - Rip and Remake Method | 4c71266f-d8ed-4eab-883c-d299547b79b0
checkpoint-status |  |  | checkpoint | 1 - Prepare
label | 8c8a82ed-18e5-5a5e-9278-c548c6dd9c40 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | b79905e6-c424-514e-a882-7fd69228f468 |  | note | Accept / Reject Criteria - As per specification
label | 0ae9514c-6f28-5dca-8bf4-d6de6e734ae5 |  | note | Frequency Of Inspection Or Test - In-process
label | 4e2d78a1-ae0f-532e-a241-33efbfbad65e |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP042
label | 42d7efc9-eeff-5cda-9a16-5ffc0ddfaa25 |  | note | Records Required - NO
label | e52b3ecd-84ff-5744-9468-5c5415ba2cee |  | note | DOWNER ENGINEER - R
label | f5957dd4-a310-5320-8be6-840fd6fc4a9a |  | note | SUPERVISOR - R
label | 37d91faa-eefa-524a-a12b-b46162cab548 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pavement Layer
label | 5eb33c2b-8e36-526a-849c-8fab460f1f1c |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | de4d875d-84ab-5d41-94b4-039eafad584a |  | note | Accept / Reject Criteria - As per specification
label | 181c9d57-b68c-5e09-be98-de9abf49d5ef |  | note | Frequency Of Inspection Or Test - In-process
label | 93b65e01-42c8-5912-9212-81c47706eb2d |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP042
label | 2b928dff-816d-5ce4-8067-97fabc39e1ab |  | note | Records Required - NO
label | b7c99f70-c18c-52cd-9683-348259cdea17 |  | note | DOWNER ENGINEER - R
label | 2eb30ead-9e47-54be-8a24-b8cde3c1cffa |  | note | SUPERVISOR - R
label | 479c08e3-771d-59dd-a65c-b1772740d3f3 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Final Shape and Trim
label | fbabadef-e36d-555c-9898-dfedaf6e55d1 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | b4b2af0a-5993-5844-a937-9deee7add7ba |  | note | Accept / Reject Criteria - As per specification
label | ad78142e-c226-5b62-a457-560c24a4c84e |  | note | Frequency Of Inspection Or Test - In-process
label | ca5c6ccc-f3d5-5b63-b1f2-ae021222868a |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP042
label | 811cc1fa-9fd4-5fa8-9425-bf733a189c0f |  | note | Records Required - NO
label | 34bdc36b-8adb-53a1-90c9-72cd91f5c6c4 |  | note | DOWNER ENGINEER - R
label | 1b583005-84bf-5ee8-a2e2-c4e3362d4bc9 |  | note | SUPERVISOR - R
label | 60dbb1e3-49a2-58bf-a336-b48303916d06 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Surfacing
label | 6081ab6a-78fc-518a-8393-4a57617c43e1 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | b57a3fcf-5455-5a99-b940-5d52839e743f |  | note | Accept / Reject Criteria - As per specification
label | 70e65453-b361-52a5-bb85-abe8ed1029bc |  | note | Frequency Of Inspection Or Test - In-process
label | 38f243aa-09ba-539c-98cc-fffa30130d90 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP042
label | aaa3d6d1-c13c-527d-8227-d84bec2731b5 |  | note | Records Required - YES
label | 44a36d4d-26bb-5b5c-8891-d7ca6723de45 |  | note | DOWNER ENGINEER - W(10%)
label | 3fdee527-d19c-523b-853a-b0563e70b379 |  | note | SUPERVISOR - R
label | d29133a7-646a-53eb-b1e9-e8c6fff4966e |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Test and Check
label | 197dea71-8bdb-54c5-acf1-22b3171865bd |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | d991192e-fccf-536a-abaf-e35c02ecc704 |  | note | Accept / Reject Criteria - As per specification
label | 108ff247-ce01-5c33-9c08-0f8760e9b501 |  | note | Frequency Of Inspection Or Test - In-process
label | 9812827c-b91a-5709-aa36-5392091f1f09 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP042
label | 5aaf20e7-68f4-50e5-8805-1486828b0766 |  | note | Records Required - YES
label | 86825636-7927-552f-af63-4d7f340378ea |  | note | DOWNER ENGINEER - W(10%)
label | 4f34d29a-1e59-5c77-9d12-bed9e66ea052 |  | note | SUPERVISOR - R
label | 914091fe-1e89-53e7-b744-5d450cd517a5 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC NETWORK - Guard Rail W Type Install Rail and Wooden Posts | itp |  |  |  | Yes | ITP - CONOC NETWORK - Guard Rail W Type Install Rail and Wooden Posts | 4e21fd7c-9713-4577-8349-16fe06a86798
checkpoint-status |  |  | checkpoint | 1 - Prepare the Site
label | 3bb5b7b7-fffa-5999-92aa-62995e9e93dc |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 79cbe2d4-846e-5212-a533-0485f40c1896 |  | note | Accept / Reject Criteria - As per Specification
label | dca16ac1-2659-5e81-9137-16ed2ed47c49 |  | note | Frequency Of Inspection Or Test - In-process
label | 759a944f-494b-51c2-89ad-ea88ec528bbe |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP138
label | 4c9f525d-b592-5bd2-a6eb-687d32263ae7 |  | note | Records Required - NO
label | e784c2db-6157-5835-8c60-8151ea86b2ee |  | note | ENGINEER - R
label | ea811c44-d2dc-5838-b5db-bc83150d4092 |  | note | SUPERVISOR - R
label | cd1d42d0-91b0-5851-8a3e-3757db4e8cee |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Place Posts
label | 4b174d5a-04a5-514f-8a58-f8094684179b |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 4f242332-8909-53b2-bdb7-8777208747e5 |  | note | Accept / Reject Criteria - As per Specification
label | 64adbbb3-9e36-504d-bcad-e1b3e4ef8db0 |  | note | Frequency Of Inspection Or Test - In-process
label | 083643f2-a302-56d3-8c82-707c9bd93f67 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP138
label | dd90cc72-b33c-552d-b84c-2b8a99f78774 |  | note | Records Required - NO
label | bd52515b-ce2f-5566-b5f4-8426b1fa3444 |  | note | ENGINEER - R
label | 215aafdf-f235-554f-beaf-c9c5ffd26b03 |  | note | SUPERVISOR - R
label | f7687b59-f772-5acc-be6d-2725da997f85 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Erect Guardrail
label | d6b6e4b8-5449-5990-a479-4d88cc5978d6 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 8f0a22c4-744b-5752-bbc5-aa441dcf023d |  | note | Accept / Reject Criteria - As per Specification
label | a158503b-2733-5e12-af26-ac540aa1e1db |  | note | Frequency Of Inspection Or Test - In-process
label | 8296717a-5259-546d-a8d4-4f58bcc0a6f7 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP138
label | a1bdda85-7d54-578b-bc1a-545097df5907 |  | note | Records Required - NO
label | a315e7bd-01e4-54e0-b11b-b6fe0c3bc29c |  | note | ENGINEER - W(10%)
label | fca5d4ad-893c-5b03-9ecc-c73c6bcb0595 |  | note | SUPERVISOR - R
label | 18f12f51-12e9-5f35-968d-2666acfe3774 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Finishing
label | ccb7ea23-a80a-597e-8ed8-46188fc81722 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 7ea9ab35-6f90-5dbe-bed2-a08be89f22e5 |  | note | Accept / Reject Criteria - As per Specification
label | 2b75e0df-54c7-5f79-b625-dbe21eae36ac |  | note | Frequency Of Inspection Or Test - In-process
label | 3b739f07-35f8-59da-84b8-4f28887dfa7d |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP138
label | 1266248e-b431-58a4-b94c-a108b1c68c82 |  | note | Records Required - NO
label | 1f1ba181-13cd-5d06-97f0-1d1d9e122893 |  | note | ENGINEER - W(10%)
label | 1deb8a38-56a2-5e14-ab27-e49ab227224c |  | note | SUPERVISOR - R
label | 2792b6dd-45b2-5f1f-872d-905b990562e2 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Test and Check
label | 1719b85e-6e20-504e-a767-b5e05758c872 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | dbff60fc-ba8b-591c-8abe-224a93119cc7 |  | note | Accept / Reject Criteria - As per Specification
label | 0111bf1a-9561-5857-8dce-ac72557e542b |  | note | Frequency Of Inspection Or Test - In-process
label | 4a462ddb-aef2-5426-bbf5-d6defc742e82 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP138
label | ad737a93-5a96-56ac-9877-1d4a5445addd |  | note | Records Required - YES
label | c8fb51ae-b3a9-5a0b-bba7-8ed45136e0fb |  | note | ENGINEER - W(10%)
label | 8c8e863d-ba8a-5529-9d2a-a4b34794d7bd |  | note | SUPERVISOR - R
label | f1365273-0cd5-5abe-aca1-a0799d2af71f |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations (Heavy and Light Maintenance) - First Coat - Two Coat Chip Seal (Hand Spray Method) | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy and Light Maintenance) - First Coat - Two Coat Chip Seal (Hand Spray Method) | 5174486f-3121-4fc8-8c22-b62a2d670ec7
checkpoint-status |  |  | checkpoint | 1 - Weather
label | 8a393c95-e9d0-5cf5-a4c8-8b1e49e38819 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 979d72c6-0f68-5df9-b6da-dc9f0ddaee42 |  | note | Accept / Reject Criteria - As per Specification
label | cf075623-8380-56dd-8f09-9f6221a216fe |  | note | Frequency Of Inspection Or Test - In-process
label | e68789af-42e2-5376-978e-c651bbd4fb01 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP047
label | 7c9dd50f-8670-55ee-98a2-192096b31ee9 |  | note | Records Required - NO
label | b9938d2d-bb05-5ade-be41-79e1f62a4f81 |  | note | DOWNER ENGINEER - R
label | f2bbef51-4dba-5015-9fe1-ca582cda8060 |  | note | SUPERVISOR - R
label | 1caf42d4-30b3-51f2-962a-eb2b55c5baa2 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Site Preparation
label | 6306d1fa-83ce-5615-915a-13cf41effe84 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | d46a8154-6940-5583-9390-2d36d085147e |  | note | Accept / Reject Criteria - As per Specification
label | f5c6e7d7-b783-5019-a4c9-d37282cf5268 |  | note | Frequency Of Inspection Or Test - In-process
label | 6d8853d8-0f90-5196-99d9-642c9ad9f723 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP047
label | 300d0840-2b6d-58e1-9fb0-53a0b549d3ba |  | note | Records Required - NO
label | ae26c8f9-ae1d-555a-bd8a-9cc2d8ef995e |  | note | DOWNER ENGINEER - R
label | 5129a02d-6e05-564d-9fae-590426228d2c |  | note | SUPERVISOR - R
label | 848709dd-1c70-5a04-93a8-7981c3fc6f63 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Binder Spray - First Coat
label | c8fe9a84-9fba-5e8e-b4b8-a23cec7549f4 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 94b7fdff-9516-5626-96a7-fe55f0e3cec2 |  | note | Accept / Reject Criteria - As per Specification
label | 23d0f611-293d-526e-a4c8-51f0b7815519 |  | note | Frequency Of Inspection Or Test - In-process
label | 44c42f56-5b71-589c-aeac-b8119bb019f8 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP047
label | f32f0d98-ae00-5490-9eae-24b9f0e71335 |  | note | Records Required - YES
label | 0f87de99-6ca6-5904-be88-ad88f8ee3a3b |  | note | DOWNER ENGINEER - W(10%)
label | d1a948ad-6161-53a0-91a7-6f6bf3a96a02 |  | note | SUPERVISOR - R
label | 7cbb9e58-aa67-5288-a6df-538a7ec58499 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Spreading Chip first Coat
label | 434da2c5-4ff3-51cb-bba6-999716309a4b |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | e8cef755-dadb-5ffe-a8d1-b65e1817bcab |  | note | Accept / Reject Criteria - As per Specification
label | 201dc81d-a114-5361-af12-6564f80aa425 |  | note | Frequency Of Inspection Or Test - In-process
label | f62fca34-a2be-5b28-85ec-211b876cccca |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP047
label | 7f68d618-e989-52c0-8cdd-18ce504e4b19 |  | note | Records Required - YES
label | a2017411-f6e7-56f5-9be7-d275e664300b |  | note | DOWNER ENGINEER - W(10%)
label | af4fa648-7f60-55e0-a86b-530e71fa4bc8 |  | note | SUPERVISOR - R
label | 722b3a18-cdcb-54f4-8204-363a6a8278f5 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Prepare for Second Coat
label | efc34aff-a798-5a30-9d31-df44119698c1 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | a0d1a7eb-a259-53e8-81d9-f673d25face6 |  | note | Accept / Reject Criteria - As per Specification
label | f5534fee-ec90-5bc5-bed2-a17c280e06d2 |  | note | Frequency Of Inspection Or Test - In-process
label | 0f4000d3-c7f7-5b2d-a4b1-8bce5f3c74d5 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP047
label | 07692f25-3ee5-52f9-abca-6f30667114ae |  | note | Records Required - YES
label | d8dad471-84ab-56fd-876e-9fc8aca81343 |  | note | DOWNER ENGINEER - W(10%)
label | 2fc296f4-9be2-5da6-b597-edd586756361 |  | note | SUPERVISOR - R
label | 8e13ddc9-e198-50c8-8989-0fe4da762176 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Second Coat
label | e49913b5-3ee3-537e-95f4-852d28a499e7 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | b3217f6e-a003-54e8-b510-f2cd6ce3ec26 |  | note | Accept / Reject Criteria - As per Specification
label | 88f867f8-e7b2-5898-8098-8f629bd1c65c |  | note | Frequency Of Inspection Or Test - In-process
label | 1dcb05ee-a023-5459-9158-290764d30184 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP047
label | ef594dcc-6c40-5591-847b-07937a6753e9 |  | note | Records Required - YES
label | 65f08c8e-9c96-5f13-aac7-3c935db61aef |  | note | DOWNER ENGINEER - W(10%)
label | 791b6651-aaff-508b-a080-f8d31c15e6ce |  | note | SUPERVISOR - R
label | 2739fa85-dc49-586c-800d-05f3fd8bea60 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Site Monitoring
label | 3c940d49-e057-5e50-9daf-093fc674563a |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 9a9d6957-8745-5a0a-a2d8-aeb77ba59843 |  | note | Accept / Reject Criteria - As per Specification
label | 99180b59-6944-5557-ae28-af1388836b21 |  | note | Frequency Of Inspection Or Test - In-process
label | 7c868897-9e76-5a9c-b69c-dbaf9872c644 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP047
label | 8635dc55-72ef-561c-b8dd-5b8ebd5055e5 |  | note | Records Required - NO
label | 9db57eac-112e-5fba-acf3-88124dc11f5a |  | note | DOWNER ENGINEER - W(10%)
label | 2652b9c2-3676-50d0-b778-b3cfdd3df4ad |  | note | SUPERVISOR - R
label | 4d86e31b-7998-5363-bb2c-eeaa307d90cb |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Sweeping and Marking
label | 520702e3-b5cc-5224-8f1d-d2fbbcaeec4b |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 4f2216e8-647a-5cb5-9e5e-0715c43d07e6 |  | note | Accept / Reject Criteria - As per Specification
label | 67f514aa-0a61-57c1-9154-2f934d83692b |  | note | Frequency Of Inspection Or Test - In-process
label | 721989d5-fde9-5e60-9021-2954a5956057 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP047
label | dcb4d307-c464-56d3-958e-1e0ab78e50c4 |  | note | Records Required - NO
label | 115b0a6c-95ce-5476-a6ec-3b1a7aa0383c |  | note | DOWNER ENGINEER - W(10%)
label | 0a62a68c-be22-5ebd-b275-d6595ac89253 |  | note | SUPERVISOR - R
label | 38b1590d-ebda-5286-bb61-f22242211c9b |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Test and Check
label | d979e31c-f75f-54b4-bed5-94b78bc93b33 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 02ed01fe-764b-56ad-a343-4af702789f7b |  | note | Accept / Reject Criteria - As per Specification
label | cc6a2796-a139-59f2-8aad-8a706c1e9d29 |  | note | Frequency Of Inspection Or Test - In-process
label | 5b48bd7c-60fb-5d95-ae60-c9a9a3442573 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP047
label | e5ece45d-7027-54a7-bf0d-ac2da4165ba8 |  | note | Records Required - NO
label | 48f20624-4e67-5491-b2c9-3f538c9cd1d8 |  | note | DOWNER ENGINEER - W(10%)
label | 8a3eb543-4874-5d78-a448-a38f5d8bd397 |  | note | SUPERVISOR - R
label | f065cdea-8c88-531f-bc69-b67fe4d64869 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair of Bleeding - Flushing Binder Applying Additional Chip | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair of Bleeding - Flushing Binder Applying Additional Chip | 5555cf5d-602c-4d92-9909-509db7ad40ec
checkpoint-status |  |  | checkpoint | 1 - Prepare
label | 477671a5-202a-5783-88b0-90acfa310e76 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 90d29f07-e910-56a9-ad77-3f89c7054e95 |  | note | Accept / Reject Criteria - As per specification
label | eb17f32e-c599-5dcd-8525-d8793e65c04e |  | note | Frequency Of Inspection Or Test - In-process
label | 91ebb8fe-2cc0-590a-bf65-3f8cc2cc4208 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP043
label | 830f2f53-0cfb-56ae-a774-0dc51a09f83f |  | note | Records Required - NO
label | 19adfd94-b2c5-515c-af16-44da4199229d |  | note | DOWNER ENGINEER - R
label | b9ff8ceb-2480-55a1-aaaa-7b786f1b261e |  | note | SUPERVISOR - R
label | 97b39c2f-a5a7-5eb4-bfb5-7fa221b1477e |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Solvent Spraying
label | 7e505189-93ff-5c8e-8436-a18730296bbc |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 2d2e32e6-f44c-5391-919d-efdc334e2175 |  | note | Accept / Reject Criteria - As per specification
label | 45cbbc96-c1c0-54bc-8370-71e839fcdcfd |  | note | Frequency Of Inspection Or Test - In-process
label | c9efeefe-1fe3-5fb4-babd-135c59cf8900 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP043
label | fcaf4a76-ab12-5b8c-997e-e560d27a05f4 |  | note | Records Required - YES
label | 425ac419-9c62-54b1-8da0-05ccba4b542c |  | note | DOWNER ENGINEER - R
label | f7db0232-ce63-5d36-bf63-fb85ba2ff7c7 |  | note | SUPERVISOR - R
label | be49fd22-926d-59df-97f5-b744478c5da2 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Chip Application
label | 517041e3-7341-57b5-87ec-2950c6b7a237 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 9c36769a-fcc5-5471-a100-e4778265184a |  | note | Accept / Reject Criteria - As per specification
label | 93c90c57-ae5a-5dd4-9873-d6afdab5067f |  | note | Frequency Of Inspection Or Test - In-process
label | 26f59a2c-a2e3-5135-8f3b-da4f835359ec |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP043
label | 7b8358dd-df5a-5041-8743-ec4bc6759637 |  | note | Records Required - YES
label | 3bb1142d-2dda-56bb-ab8b-7ae4a4e09bef |  | note | DOWNER ENGINEER - W(10%)
label | fbf12241-2518-52ca-9ed8-9491660f28e7 |  | note | SUPERVISOR - R
label | 5f93915a-1e62-5016-a505-b48a1a2ad428 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Test and Check
label | 09da6173-49b4-5294-9040-4ebfb4d04be1 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 058542c3-050a-5bf9-910a-578810568cb7 |  | note | Accept / Reject Criteria - As per specification
label | 5a4495cf-dae1-55f4-8fa9-eeb1690718e5 |  | note | Frequency Of Inspection Or Test - In-process
label | cb8abd80-f5b7-5791-8b10-55353ac13719 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP043
label | 63084814-0699-5b2a-8e1e-a4e8ec2aed07 |  | note | Records Required - YES
label | 21e14fdb-4fac-55b4-874f-d312343cc9bd |  | note | DOWNER ENGINEER - W(10%)
label | 31391a23-1d02-5a9c-addc-d1e99643d5d1 |  | note | SUPERVISOR - R
label | ce039108-a980-5cc6-a3a8-ade594184e33 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations - Install a Flume - Nestable Corrugated Steel or HDPE | itp |  |  |  | Yes | ITP - CONOC Operations (General) - Install a Flume - Nestable Corrugated Steel or HDPE | 5569f797-9b55-45aa-bbe4-9ae73f0837af
checkpoint-status |  |  | checkpoint | 1 - Prepare Base
label | 2fbb50a2-610e-5e44-b441-d3ce303a62d2 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 73bd9bb3-fac1-512c-b854-8a5d17ed38b3 |  | note | Accept / Reject Criteria - As per specification
label | b9350d15-68d6-50ff-9824-ef98c9834852 |  | note | Frequency Of Inspection Or Test - In-process
label | 8250e32a-75a9-55ef-9ec5-46964e552057 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP086
label | a786944b-3b98-53ec-81a7-ac1e06a0ed54 |  | note | Records Required - NO
label | 635e655c-7988-548d-a7cf-ae86925b0473 |  | note | ENGINEER - R
label | 39feed07-c8e1-5215-963e-94a893503f82 |  | note | SUPERVISOR - R
label | 188c97a7-e6fb-5957-abeb-90d8130472cc |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Trestle Construction (to bridge over low spots)
label | 7dd74e53-2863-5877-bc6c-6e53f2cf357e |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 52fd6677-0c0e-5ef2-a60e-3b24b6faf47f |  | note | Accept / Reject Criteria - As per specification
label | 31695016-ff67-55aa-ad71-8fc18ad356f8 |  | note | Frequency Of Inspection Or Test - In-process
label | ebae5224-1c92-5627-96ea-86dfc3a095f1 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP086
label | ed0c043c-54e4-50eb-ae80-36c0ce04092c |  | note | Records Required - NO
label | 6367e171-2bec-5f9d-b291-7a51b7325d00 |  | note | ENGINEER - R
label | d368d9bc-9de3-58c9-b8b5-ba91fae64d3b |  | note | SUPERVISOR - R
label | 489336bc-fd20-52d6-984c-28a82ff703ce |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Install Flume
label | 3781e75f-ca72-51ed-9852-de4d5c462dd1 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 9c92692c-8016-54be-87d7-5e535968853e |  | note | Accept / Reject Criteria - As per specification
label | 0aa6fbc2-446c-5b92-a116-2b1723306546 |  | note | Frequency Of Inspection Or Test - In-process
label | 17b57d0a-c709-5514-814d-07a407dfcacf |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP086
label | c904137b-671f-5cb9-865e-82033c3868cc |  | note | Records Required - NO
label | 579f06bc-0164-5862-a275-cc79e768e74c |  | note | ENGINEER - W(10%)
label | 57dcf8e6-96c8-5a0b-8183-697af226194c |  | note | SUPERVISOR - R
label | 0bbc1755-19c4-5375-9972-a6eecc9e0f70 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Join Flume
label | 9f84f9a2-a4bc-5449-87bc-e82702c1e26a |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 25587147-d796-5045-b107-750b422ce513 |  | note | Accept / Reject Criteria - As per specification
label | cc560403-49f0-5b4b-b211-9944f8289ad6 |  | note | Frequency Of Inspection Or Test - In-process
label | 9fb355f6-3a64-52e6-aa44-9a6dbe7fd9fa |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP086
label | 26d406d1-4f60-5d9d-aed7-a6a9eb84bd0a |  | note | Records Required - NO
label | dab97e04-d35b-5c7f-bf84-04d5cd9f8202 |  | note | ENGINEER - W(10%)
label | c37fc1ef-8bf2-530e-a98e-8f8845c8477a |  | note | SUPERVISOR - R
label | 8ee8a393-4f32-5421-95c8-ff7354e2ffc9 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Fix Flume to Slope
label | e0dcad9a-dbd1-5850-ac76-4aab0d1ea639 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 988969e3-578f-59fe-9426-b5c9e2efbe59 |  | note | Accept / Reject Criteria - As per specification
label | 0b47e11f-6cb3-5ddf-97cc-f33e9d2f59b7 |  | note | Frequency Of Inspection Or Test - In-process
label | c42a8d8e-7076-5721-ae29-00789aab9364 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP086
label | a5e9742c-edae-598c-b0d6-0ff7ff0ee96b |  | note | Records Required - NO
label | 7da0aad3-9d2c-5d67-bab4-30560d88822b |  | note | ENGINEER - W(10%)
label | 8257c268-1aba-5cc3-b643-dda4805222dc |  | note | SUPERVISOR - R
label | 127384eb-6264-593c-8cb5-aa3ba79cb656 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Align Flume
label | d25b8f62-2a21-5e05-932f-f422bbe17cc1 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 39ec3fc0-1660-55df-8a25-53d87b39126b |  | note | Accept / Reject Criteria - As per specification
label | a509d3a7-9bd6-5859-9d83-fbf8a82959b0 |  | note | Frequency Of Inspection Or Test - In-process
label | 8b211385-c58c-5f93-aaf2-a4daeb7b31d7 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP086
label | 73ebd5dc-50a9-51e6-a729-7692d7ccd25d |  | note | Records Required - NO
label | 94b2c520-e9e0-551f-95bb-5572362921b2 |  | note | ENGINEER - W(10%)
label | 8ca3d3ec-33d0-58a7-a28e-17cbfd40fe8d |  | note | SUPERVISOR - R
label | 3dd47e78-985b-5f55-aeff-09e25d37946d |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Outlet Control
label | eb1d40b0-fed1-547a-9e34-2aa2839e16b4 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | d2c62b5d-bc79-5eba-b790-72e925736755 |  | note | Accept / Reject Criteria - As per specification
label | 3d667a6a-1d61-5184-a32a-0378c5f2ecde |  | note | Frequency Of Inspection Or Test - In-process
label | 5366d94e-7198-586f-b665-d41e2d7ad19f |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP086
label | 682e7b63-af19-5753-b051-c2880677a82e |  | note | Records Required - NO
label | 39084957-9e4b-5a38-9ad4-8f9396816333 |  | note | ENGINEER - W(10%)
label | 67403c8b-e84a-5021-9118-eda7012fb363 |  | note | SUPERVISOR - R
label | 1266f23d-a72f-535e-9c4f-cef90dd0a016 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Test and Check
label | 5a8ed389-8237-5425-b758-e706ae55b0fe |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 18dcbdf2-830f-5cc2-8a9e-2bd4251730b3 |  | note | Accept / Reject Criteria - As per specification
label | 18918104-9936-5d60-b654-115a51fca3d0 |  | note | Frequency Of Inspection Or Test - In-process
label | 32228703-cbb9-5214-a91c-c14ffca08bc1 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP086
label | 369f8eec-5a39-505c-80e5-8c5b99171cc7 |  | note | Records Required - YES
label | 389c2828-fd78-54a9-8e0d-3a9ea4c7f7a6 |  | note | ENGINEER - W
label | cd2dbfb8-f1dc-5762-b058-4c096fb13de7 |  | note | SUPERVISOR - R
label | 578a53e3-63cb-5bf1-92d5-ffb23d41f99a |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations (Heavy and Light Maintenance) - Unsealed Roads - Construct an Unsealed Pavement | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy and Light Maintenance) - Unsealed Roads - Construct an Unsealed Pavement | 5c035004-385e-4a85-ade5-80759bed5d47
checkpoint-status |  |  | checkpoint | 1 - Prepare
label | 08973feb-f897-514f-96e8-9923506c9b5f |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | a60ecd05-0899-5471-b88a-5a00674e4291 |  | note | Accept / Reject Criteria - As per specification
label | e897df8c-d87f-5dc4-9034-812037523504 |  | note | Frequency Of Inspection Or Test - In-process
label | 31bb2044-b8af-5519-a81d-be2ae95781d1 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP066
label | 49f67176-6333-58c1-a695-3ea3d3121114 |  | note | Records Required - NO
label | dc0b40d3-492a-53d2-8d3f-309359aa18ca |  | note | DOWNER ENGINEER - R
label | 36d230b9-3fe0-5656-96d2-b1994268d73d |  | note | SUPERVISOR - R
label | 75b2829a-1d8c-5428-80f0-d698272f46a0 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Base Preparation
label | 4280c77a-4810-5885-a957-6b091110357a |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | a51bbc6f-374f-5b10-a6cd-a039de96b416 |  | note | Accept / Reject Criteria - As per specification
label | 37cc53cb-8897-5dec-8949-7c1492b10edf |  | note | Frequency Of Inspection Or Test - In-process
label | cefcb2f4-1552-57b2-b92e-a4c24a4dff29 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP066
label | 749b9cfd-416f-5c55-ba39-754a356870f3 |  | note | Records Required - NO
label | 54d0619d-f28a-5f18-ab9e-9911dc316489 |  | note | DOWNER ENGINEER - R
label | 8131f08f-554c-5560-aeb1-fb80c677fc22 |  | note | SUPERVISOR - R
label | 183f9c8c-5ee0-576d-83cf-f0423143a539 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Metal Spreading
label | 436f9c9c-94b1-57b5-9162-0b78468d70e1 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | dddff906-939f-5d94-89c3-91d019a99339 |  | note | Accept / Reject Criteria - As per specification
label | 663e7a3e-c9b1-5e8b-8666-f435985107d9 |  | note | Frequency Of Inspection Or Test - In-process
label | fd18ded5-5bca-5b45-b750-44fd23502139 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP066
label | 17bdaafd-241f-523b-bff4-67bf339d3b12 |  | note | Records Required - NO
label | 75e25012-a6a4-554b-8418-72f72af4b574 |  | note | DOWNER ENGINEER - W(10%)
label | 86dc8ead-3d50-50f8-b5f3-32e91472eea5 |  | note | SUPERVISOR - R
label | 5a4b7e90-71ba-54b2-b768-f159186d1eda |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Moisture Content
label | fafef8f1-2726-51aa-9189-17a8273f1303 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | cbc585b3-7a2d-5904-bb10-ad3986dd8050 |  | note | Accept / Reject Criteria - As per specification
label | 3d759d35-b9f0-5005-900c-01b0071ef517 |  | note | Frequency Of Inspection Or Test - In-process
label | e510b71b-35ff-5bd7-8d82-9ca108039dfc |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP066
label | 98859be1-78d5-5cf3-97b7-ec7a9873eeac |  | note | Records Required - YES
label | 8d66dc01-cfb5-5be2-abbf-cf050bc5519d |  | note | DOWNER ENGINEER - W(10%)
label | 9813182b-d410-5e7a-aef1-046e855be6a8 |  | note | SUPERVISOR - R
label | 860e7d1e-6e20-51ca-a69c-57de288099fb |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Compaction
label | 67620b31-31cd-5745-86b5-7499688403bd |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | ee39f7ad-e262-5028-9b02-5a8df36c33b0 |  | note | Accept / Reject Criteria - As per specification
label | e50bd182-645b-555a-b5e9-6d311f281853 |  | note | Frequency Of Inspection Or Test - In-process
label | a8153a09-2fc5-5e37-899d-78c5225134cc |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP066
label | 4435b552-03e5-5ef6-b51f-6e11224bbf2c |  | note | Records Required - YES
label | c0410c6b-b65e-594b-81f1-c1252b1c0aa4 |  | note | DOWNER ENGINEER - W(10%)
label | 5e3ece44-6f83-514d-bdca-c86383d56e91 |  | note | SUPERVISOR - R
label | bd677ce4-a6f8-571f-91e0-6defdc37854e |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Running Course
label | 04e42d10-4f14-5deb-8e11-1316931a29f9 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 48b86560-23ed-5a4e-853e-6ff040d8083b |  | note | Accept / Reject Criteria - As per specification
label | bf7a18fb-e849-5ddd-895d-4f25697b60eb |  | note | Frequency Of Inspection Or Test - In-process
label | 7254d0f2-6c9b-5dd5-ab69-6a714b9cd585 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP066
label | 9964dca1-1a41-502c-a879-694b76a2e4d6 |  | note | Records Required - YES
label | 00b34653-a9e8-50c9-854f-47739dd3bef8 |  | note | DOWNER ENGINEER - W(10%)
label | 47c86011-baad-5788-8a2b-b46cfae70fa8 |  | note | SUPERVISOR - R
label | a7ce90ab-25a9-5ce5-bd83-cdc0e98ffc3a |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Test and Check
label | 1720169c-9d1d-57c7-a137-1638c9a27fbc |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 3055e0e7-4fbc-5c82-8bae-aa44623a96ab |  | note | Accept / Reject Criteria - As per specification
label | 25d440f2-b3f2-5e0b-9c37-0cd41ab352bb |  | note | Frequency Of Inspection Or Test - In-process
label | 8ba631de-c245-5b84-abfc-2f0bcf0f589f |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP066
label | 73b439fd-24f7-5845-8c52-0ed329f2c7c4 |  | note | Records Required - YES
label | 1e8afed1-6cd5-5f3b-b963-d47224d66a55 |  | note | DOWNER ENGINEER - W(10%)
label | 6921eb10-2d8b-5fdf-a733-40b738d9f729 |  | note | SUPERVISOR - R
label | d5676a88-06df-5400-8d98-3d6a83dae5e4 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - Port Chalmers - Thin Asphalt Paving |  |  |  |  | Yes | ITP - Port Chalmers - Thin Asphalt Paving | 5c17fc3c-d1bd-4f8d-a1c0-e4cc0de65453
checkpoint-group |  |  | section | 1 - Preliminary and General
checkpoint-status |  |  | checkpoint | 1.1 - Construction Programme Completion
label | 8ed8cb02-4c30-5d58-837c-fd022d5469aa |  | note | VERIFICATION ACTIVITY - Confirmation
label | b26b9abd-5a7a-517f-96bf-e6e9c00073a8 |  | note | METHODS OR REFERENCE - Best Practice Contract Specific MMP
label | 94505268-ea61-5d8d-8a92-7a985e04eb89 |  | note | FREQ. - Before work commences
label | ebbc9cb9-49f4-595f-b336-877432e6c22b |  | note | ACCEPTANCE CRITERIA - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date.
label | 3576e9da-3a07-5865-a3e3-3a4255e3c612 |  | note | INSPECTORATE W/H - Type: - W
label | ed641569-fe3c-5a31-ab52-2753f033bf78 |  | note | Responsible Person - Renewals Manager
checkpoint-status |  |  | checkpoint | 1.2 - Approved RQP
label | cd054bdf-fca6-579d-b93b-75b3b7751a5a |  | note | VERIFICATION ACTIVITY - Confirmation
label | 12b917c9-71ab-51e2-ade4-ecddec5cb3bf |  | note | METHODS OR REFERENCE - Contract Specification
label | 3892f8d8-424f-559a-9d2a-5b89185fae43 |  | note | FREQ. - Before work commences
label | 48536836-f219-50e4-9b71-4784545c494a |  | note | ACCEPTANCE CRITERIA - Principal Acceptance according to guidelines in appendix 6.3
label | 3753106b-7917-593b-be61-b09fa0a7a353 |  | note | INSPECTORATE W/H - Type: - H
label | 4c68e7e5-4bf5-5290-baa6-14abc006dd11 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. NZTA to approve
label | e2130931-f3ac-5153-a9be-b977a3d84004 |  | note | Responsible Person - Renewals Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Traffic Management - TMP
label | b02574ba-4aa0-5e58-890c-dca6b55890aa |  | note | VERIFICATION ACTIVITY - Visual check
label | ceef1d46-8188-5c64-bebf-491afa8b75af |  | note | METHODS OR REFERENCE - CoPTTM
label | dca121a2-3248-5a22-8e05-59ef8051f230 |  | note | FREQ. - Before traffic management set up
label | bc5585aa-ef90-5b98-b506-d0c3d9fd38b9 |  | note | ACCEPTANCE CRITERIA - TMP checked and approved Plans approved Current EED (if applicable)
label | 8fbb6909-bcd3-5267-a86f-60eccc579c1b |  | note | INSPECTORATE W/H - Type: - H
label | 0514bd94-9930-5f06-9020-13e196eb388c |  | note | INSPECTORATE W/H - Description: - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | 4b36caca-3e1c-57d5-bfef-4f066536d78e |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Mix Design Verification for all mixes Check Laydown Trials are complete and compliant
label | bc47cb96-0de5-5177-9777-4a9c23a628d5 |  | note | VERIFICATION ACTIVITY - Confirmation
label | cc78d55b-c81c-5468-bc5c-8ee3da8ba782 |  | note | METHODS OR REFERENCE - NZTA M/10, P/11, P23
label | 73b327f9-5584-59c0-a72e-b888d3169187 |  | note | FREQ. - Before planning commences
label | 14b7d094-aeda-5b72-8ec0-1e111d939dc9 |  | note | ACCEPTANCE CRITERIA - Mix Design compliant, current and relevant. Batching plant production capability is confirmed
label | 07c37978-a61a-543e-a103-03803c6c07de |  | note | INSPECTORATE W/H - Type: - H
label | d751e1b7-301a-503b-9c0d-ba69460efc88 |  | note | INSPECTORATE W/H - Description: - Hold point - No planning of on-site works shall commenced until the mix design is verified.
label | 2631fa99-1ec6-531e-93b0-eade3a966a36 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Notification of intention to start work
label | d0921976-636a-5f3e-846d-938fb24a286f |  | note | VERIFICATION ACTIVITY - Notification
label | a82fc98b-6ce4-522e-8b37-be282b90f2ad |  | note | FREQ. - Before work commences
label | 7846b52f-dcf9-5ffc-9096-7b91a2ff17e6 |  | note | ACCEPTANCE CRITERIA - Letter drop to local residents. Greater consultation where required
label | f60b2e5e-8176-5fab-b708-38b10f73498f |  | note | INSPECTORATE W/H - Type: - H
label | 70950104-9a98-5fc0-b036-9e89a1e85b3a |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | 87fa9a8c-04bc-54c1-8f3f-4e2455e9a103 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Works Extents
label | ab546914-57e5-5daa-9e38-93a6c1acf724 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 95a0846e-dd05-5c0c-9cfe-992e691b33d5 |  | note | METHODS OR REFERENCE - Site Visit
label | 5a98707e-0ba8-56ed-b3b7-05a3393c83c4 |  | note | FREQ. - Before work commences
label | d00a614d-4197-5226-ae0b-f485e11b91cf |  | note | ACCEPTANCE CRITERIA - Renewals Manager and/or Client to agree extents of project
label | 4c1e47fe-a904-573d-8156-0409092f1323 |  | note | INSPECTORATE W/H - Type: - H
label | eb56ed47-6f27-5dbf-94cc-5f991c78112a |  | note | INSPECTORATE W/H - Description: - Hold point - Walk over site with Renewals Engineer and/or Renewals Manager and/or NZTA
label | 62421b4e-beb7-52f1-8f5a-14af392a805a |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - Pavement Marking Records
label | 24da2483-a9fa-5ec3-be82-de993bfd2fa4 |  | note | VERIFICATION ACTIVITY - Measurment Data
label | b1499f21-b23c-5438-a3e0-747fa4587f37 |  | note | METHODS OR REFERENCE - Site Measure or Video Viewer
label | f5677acd-0186-53c0-9ac1-be7ba6a5bdc7 |  | note | FREQ. - Before work commences
label | 4fc8e5ee-7313-531e-b97f-846f9b2e2845 |  | note | ACCEPTANCE CRITERIA - Measure existing markings to aid reinstatement
label | 2ea36a34-d4f0-587e-a415-bc8b5a337926 |  | note | INSPECTORATE W/H - Type: - H
label | 1c1e8448-ee66-5398-813a-40f6ab471c1e |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | a7ed5950-285b-5943-9f1a-87744183a75e |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Milling and Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | 4c71ef8c-b931-5d69-99b8-3761cc5326cb |  | note | VERIFICATION ACTIVITY - Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth)
label | 9950ae4f-d74a-51b0-9ab8-c37ad5965b83 |  | note | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | e3ef2dee-5786-564a-9b3f-ff45e4be624a |  | note | FREQ. - Before work commences
label | b7396106-d1a9-5b2a-8325-02c9b839dd64 |  | note | ACCEPTANCE CRITERIA - Zero service strikes
label | d1faae2b-edf1-5aa2-8ac3-ba46f6f652e4 |  | note | INSPECTORATE W/H - Type: - H
label | 0dd28e7b-76a9-59a3-80bf-a7984eb8d6a6 |  | note | INSPECTORATE W/H - Description: - Hold point - No excavation/milling is to be commenced until services are located and accounted for
label | 5096f3ec-1110-527d-8ac2-6e1d7dd2a07b |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Stormwater Management
label | dd916ae3-8f17-5b77-a486-fbe2d12f3b5a |  | note | VERIFICATION ACTIVITY - Visual check
label | 962f2204-aa25-599b-a4a5-acb77075f8f2 |  | note | METHODS OR REFERENCE - On Site
label | 8440e9ea-99b6-571c-bd50-e68a7b88ba1d |  | note | FREQ. - Before work commences
label | 64f576e1-98fe-5f28-bfb2-95076f190cd6 |  | note | ACCEPTANCE CRITERIA - Mudtanks bunded or filtered to prevent mix from dropping in or runoff entering
label | 2a6c36e5-7dfc-54c0-ba47-b0308481d5e0 |  | note | INSPECTORATE W/H - Type: - H
label | 0a2503bc-cdcc-553f-aef5-25320155b646 |  | note | INSPECTORATE W/H - Description: - Hold point - No work to be commenced until protections in place
label | f824d322-6bd4-53e0-97de-5898d340b776 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Traffic Management - Setup
label | 81349a37-dd7d-5806-8e72-83db04e5c062 |  | note | VERIFICATION ACTIVITY - Visual check
label | 4c4c43de-9e1a-5ef7-9bdf-d090ae0c4c3a |  | note | METHODS OR REFERENCE - Traffic Management Plan
label | b7abe45f-c10d-5542-bbdc-467db9a497ce |  | note | FREQ. - Before work commences each day
label | 59755713-41eb-5235-b0b1-db8f10c48825 |  | note | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | 5e9c5619-c248-5c2d-a625-35424588a84d |  | note | INSPECTORATE W/H - Type: - H
label | ccd14d66-bad6-5c65-803a-e5ec236f04c1 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | 8d4034fc-cad2-5bac-bb94-f37d12422711 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Milling Depths
label | de9ea0c0-b1ed-594b-bc08-6546c479deae |  | note | VERIFICATION ACTIVITY - Measurement
label | fabffb5b-3986-58ca-96c1-71787ae9c4ed |  | note | METHODS OR REFERENCE - On Site
label | 57f70753-bc76-5871-94b6-c415764e9331 |  | note | FREQ. - Measure each side of milling machine cut
label | 1c5c3e43-5fc7-5933-aed9-abf50a3d7c0d |  | note | ACCEPTANCE CRITERIA - Every 10m. Depth matches target
label | 319019df-6cf1-51d6-b958-ae4dfe4f46d5 |  | note | INSPECTORATE W/H - Type: - H
label | 2d6bd6a9-b4c1-5851-b4d9-564ea8b794ab |  | note | Responsible Person - Site Foreperson / QA
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Service Covers Preparation
label | 8006e444-781c-5ecf-b150-8eb179128ec3 |  | note | VERIFICATION ACTIVITY - Visual
label | 11cb74e4-30b7-5e91-a813-8d905b587a83 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 504a3a54-8504-5919-b012-aee1eb22cd3e |  | note | FREQ. - All Covers
label | 4dcb4a96-0418-567a-931a-dcf0f8f201b0 |  | note | ACCEPTANCE CRITERIA - Hand excavation around ironwork and adjustment to desired level (if required)
label | a2cf91d4-6a97-52d3-b869-5dc6a321bc64 |  | note | INSPECTORATE W/H - Type: - H
label | 36a20eb3-5799-5d3c-815f-695c766cff02 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Additional Surfacing Preparation
label | 4e47f144-3467-5bbd-a4e7-0c84bf230cd0 |  | note | Side Roads; Accesses; Driveways; Dish Channels; High Shoulders
label | 109a3596-f429-5a99-93bc-8c9fe24fadf5 |  | note | VERIFICATION ACTIVITY - Visual Check
label | f5e34701-d340-5d81-8228-0c4b1e0ac7e0 |  | note | METHODS OR REFERENCE - Per Design
label | f4120bac-e874-5858-b306-c79997c4fb3d |  | note | FREQ. - Before Membraning and Paving
label | a10d89ad-e8c4-5d23-8679-8c6d8aa176ac |  | note | ACCEPTANCE CRITERIA - Have all areas of additional surfacing on the design been prepared, membraned and marked for paving?
label | 6ea12b07-2351-5a44-9aee-77b89270cb6e |  | note | INSPECTORATE W/H - Type: - H
label | 8956ad35-4315-5a0c-b946-fdb4a529b670 |  | note | INSPECTORATE W/H - Description: - Hold Point – All areas planned for AC are prepared ready for surfacing layer
label | 9ac93551-f57e-56cf-87a4-0d65de4f2987 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Over-Milling
label | 46620238-53b1-52b3-afbf-734f9c8055b2 |  | note | VERIFICATION ACTIVITY - Measurement
label | 61a50f58-6b76-5881-8a02-d4f9fa7f43cf |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 16c0db18-56dc-50c2-9855-b5ca03003867 |  | note | FREQ. - Prior to pre-level
label | 08bcc732-8b7a-5ef9-90ee-6760b3faaab7 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree need and extent of over-milling and infill.
label | 32972abb-da55-5a16-b9f2-ddb3c369c8f5 |  | note | INSPECTORATE W/H - Type: - H
label | e6cd2609-4338-5c4f-b72d-2bfe29e4d0be |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Pre-Level
label | e0ae8c11-fa1d-59eb-9bc4-828d2d3ee023 |  | note | VERIFICATION ACTIVITY - Measurement
label | 0dd11cff-7d6e-5296-b039-0486f2f50f28 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 3c8e8ef9-6cd2-5395-934e-289bad080866 |  | note | FREQ. - Prior to surfacing
label | ca40fd57-2ee1-5e8c-ba0c-75efddb648d0 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree pre-level extents
label | 93ab85cf-e1d7-569c-912b-eaa2acf4da7a |  | note | INSPECTORATE W/H - Type: - H
label | 4b98d289-024b-5211-8d96-77c1a5f93d5a |  | note | INSPECTORATE W/H - Description: - Hold point - Inspection and agreement by NZTA
label | 5f43f0af-c3b8-5ed5-b50b-ca24e931dba0 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.9 - Membrane Sealing
label | dbeb7308-674d-5205-bd94-e59ac574b25e |  | note | VERIFICATION ACTIVITY - Visual
label | 3808897b-98e1-5db0-9027-a410cffe427e |  | note | METHODS OR REFERENCE - On Site
label | d714259a-6a3e-59ee-b992-778ed68c11df |  | note | FREQ. - Prior to surfacing
label | 5dba691c-c21d-583c-bee2-3b67ac2959fd |  | note | ACCEPTANCE CRITERIA - Membrane seal meets design and extent. Sealing Docket record kept
label | 9863e827-49ca-537e-863b-8cb766c575bc |  | note | INSPECTORATE W/H - Type: - H
label | 1ca9d1a9-b1ba-5d55-bd84-904f0adafba4 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Paving Structural
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | 3e4e313e-18ac-5157-8172-af245550875b |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | f70e4a63-6010-5610-88fa-e9776d418884 |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | f4fba50f-243a-5c30-b0cb-c8d10e314e46 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 91ffca16-7ae5-5924-80e7-c9aac782bd89 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 12d62cf2-6b68-5ef4-9a59-0592148b24e2 |  | note | INSPECTORATE W/H - Type: - W
label | 64482d8e-8f2e-52ff-9000-db9a60405dc7 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 04573a42-924c-54aa-9c0f-9ac5a54e1013 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | 8585124d-9321-5ff1-a776-3fd0cc984f37 |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | 89e38d5e-3b26-5c50-b411-9e3a2d086a58 |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | 700c23b9-8a7b-595d-852a-6684d70eba78 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | d8c6eb6a-35a0-5b8c-9b4a-8a25f133bb4b |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 1ef0b2b2-3c15-59c7-a344-47a203262b63 |  | note | INSPECTORATE W/H - Type: - W
label | df6ab63e-90d6-5b86-a83c-4399ddd997e5 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 361c0405-5c94-50dd-8786-81dd3871ecaa |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | ad0a5cd1-2923-5334-8e73-9dd41377d844 |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | b0fa7e42-b958-5577-adf5-3134428226d7 |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | f108afdd-3ffa-5b6e-9d52-edafcd0f67e8 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | dafdf45a-e829-5e2a-8b6e-63537c53a291 |  | note | INSPECTORATE W/H - Type: - W
label | ea3eb961-0027-5a85-8fbf-e678e21da1fd |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | fb49db99-a68e-5d02-8549-3575af1bca60 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | 3087c425-ed8f-5d45-96c9-2b5eb7f941a9 |  | note | VERIFICATION ACTIVITY - Visual
label | 1aac3d34-65b2-5327-b135-842381bec3a9 |  | note | METHODS OR REFERENCE - NZTA M/10
label | fa89df84-026d-52df-8883-0909434480f6 |  | note | FREQ. - Prior to Shift
label | 44152cd1-f6db-5395-a161-191b9b15120a |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | 10aee1e3-828e-5537-a56f-81201567a827 |  | note | INSPECTORATE W/H - Type: - W
label | c4b50dc7-a48b-5281-8fe5-7c40e1b701ab |  | note | INSPECTORATE W/H - Description: - Paving Plan and Crew Briefing Plan completed prior
label | bb5b572f-5ae4-5b7f-8118-8ceb4f73efaa |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | 61a1d052-6932-5475-8efc-d60a7e15c2cc |  | note | VERIFICATION ACTIVITY - Visual
label | b87a38fc-e5bc-5492-86bd-8333e2f11c95 |  | note | METHODS OR REFERENCE - NZTA M/10
label | e61bacee-b4ff-5b77-8186-2c500890b062 |  | note | FREQ. - Prior to Shift
label | a5f22bdc-7156-5c82-87f1-e6784f32ce7b |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | 6031d07d-320a-5e22-a4af-468cf2e21c63 |  | note | INSPECTORATE W/H - Type: - W
label | 055f1736-32e0-5b64-a1cb-31685e29abcb |  | note | Responsible Person - Paving Supervisor / QA Engineer
checkpoint-status |  |  | checkpoint | 3.4 - Mix Inconsistency and Deficiency
label | 30caa121-6725-5856-b2be-34b4e4646cb0 |  | note | VERIFICATION ACTIVITY - Visual
label | 27f51b1a-22e4-5c50-813a-9c8d3deaa1a3 |  | note | METHODS OR REFERENCE - NZTA M/10
label | d47a1820-b0c1-543b-a96a-31cb7617a0a9 |  | note | FREQ. - Continuous
label | 720b7be4-cdac-5c1d-a472-8c0738fda87e |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | 50c0295f-ef83-5723-a080-1a67e6c057bd |  | note | INSPECTORATE W/H - Type: - H
label | de06b386-9e4a-5625-85f2-cd4cc67874b6 |  | note | Responsible Person - Site Foreperson / QA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Load Locate
label | 9192e097-3829-5454-8188-e05d57111670 |  | note | VERIFICATION ACTIVITY - Measurement
label | 9cac7bac-d734-58c3-aaf7-f42ac13eafc0 |  | note | FREQ. - Every Load
label | 72675d6e-fbd2-5d22-8add-75df2365f2d1 |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
label | b745020e-84dd-517c-87f7-aac4dd12af55 |  | note | INSPECTORATE W/H - Type: - W
label | dc83580b-9f93-50e4-a6e3-93183c26e5f2 |  | note | INSPECTORATE W/H - Description: - Per standard practice
label | 41c890d4-df72-56ed-bfc7-cdeb5565cc24 |  | note | Responsible Person - Quality Assurance Engineer
checkpoint-status |  |  | checkpoint | 3.6 - Laying Temperature
label | f382e319-61e0-54fc-b8e2-e922dbc70fff |  | note | VERIFICATION ACTIVITY - Confirmation
label | 7e8aba10-ed84-55db-b30f-a27c10cbd639 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 910d3473-ccce-5f2d-ac8c-3881a1ad5af1 |  | note | FREQ. - Every Load
label | bb8b4b0a-b63d-5243-a18c-3dac7f90c765 |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | 91f15652-9d63-5196-8943-231f03c34e5d |  | note | INSPECTORATE W/H - Type: - H
label | a9ebf9ff-ca1d-58e7-a765-1c0f74b5e5be |  | note | INSPECTORATE W/H - Description: - Hold point - Reject mix for non-compliant temperatures.
label | a0a92405-420b-5b1c-8c5e-e53c2d7dea44 |  | note | Responsible Person - Quality Assurance Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Compaction
label | bda84bbb-ec1b-5d5d-bb46-3abe2d0ce42a |  | note | VERIFICATION ACTIVITY - NDM Testing
label | 4f071c3d-db90-5ec0-84f3-23c75b9ce4f1 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 3d920f70-b015-56e7-adee-d39ea903e4b6 |  | note | FREQ. - Minimum: 1 Test per 300m² within Mat. 1 Test per 100m of joint.
label | 26a1a30f-eb25-5c5a-be40-22d9223edcfe |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | 36d91336-c04e-5e41-a603-b9c43963ee8a |  | note | INSPECTORATE W/H - Type: - H
label | 9afdaaf5-e610-524e-80e0-b7e1a879224b |  | note | INSPECTORATE W/H - Description: - Hold Point - No Wearing course paved until any non-compliance is sorted
label | 87549620-d9a8-5b93-96e4-aeb8c2bc3e19 |  | note | Responsible Person - Quality Assurance Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Roughness
label | 67503c86-3c76-5809-bd99-c4a5e25ae573 |  | note | VERIFICATION ACTIVITY - NASSRA Testing
label | 8cca5db0-4e11-52a7-a59e-b3c6fa779546 |  | note | METHODS OR REFERENCE - Contract Specification
label | e941862f-b413-5e1b-911e-47d950cee5d9 |  | note | FREQ. - post construction
label | 3953c6bd-1251-57bf-a817-6c966b7e5211 |  | note | ACCEPTANCE CRITERIA - NASSRA rolling meter average under 60, max of 70
label | cc824b7c-5984-5055-b635-81abc4bed951 |  | note | INSPECTORATE W/H - Type: - H
label | 90b88350-990c-535a-9940-384681e79f43 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Paving Wearing Course
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | 84e7e372-ac48-5586-a558-e3dd29273b96 |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | 3f5e5701-6347-5d74-bbad-2a7598ce34e2 |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | d388c4ad-646b-5283-b2a6-eed794f7890d |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 6df487cc-eafb-588a-ba3c-28acdb619bd3 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | e0923236-b6e7-53b2-9c20-7a6926fde742 |  | note | INSPECTORATE W/H - Type: - W
label | 45447b8f-cc32-59d3-9d52-5e0f6f9ce04d |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 91be7615-eaf4-5613-8721-cfc68919478b |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | df98e0a2-c96b-5e1c-bda5-5d311ca5978c |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | 44149027-6c41-5b60-84a8-b08001de509a |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | 292dc182-df75-5cb7-a7b0-a46a341674b8 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 6910859c-3271-568c-b49c-60323dc9c108 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 4e5c7e67-ce40-5b24-87be-944e42d67a53 |  | note | INSPECTORATE W/H - Type: - W
label | 8e77ee27-8b1a-5eb9-9baf-366b360338a9 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 0a841318-f827-5024-8f00-b2e1f174adc7 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | 9e4e5592-64ea-50ff-946d-5111d8828164 |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | e469af56-db87-533d-8f5e-51a89ded9736 |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | 739380a9-fc3d-56ec-8747-5bd47b71b253 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | a0ce257b-97cb-5027-a629-e8aea3509cb4 |  | note | ACCEPTANCE CRITERIA - Per Mix design
label | 3e627516-5923-58a7-a9c8-33f7df34950f |  | note | INSPECTORATE W/H - Type: - W
label | f6935e6b-f055-591d-a012-38a3d96396c1 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 102c5957-3ad6-5ed7-b24b-696a7ae4e7d8 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | bdf61070-6f26-5bed-ad05-27c3e24e258c |  | note | VERIFICATION ACTIVITY - Visual
label | 1f26a035-6bc3-5a28-b050-fad30a136da6 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 9ed464bf-d6d9-5c23-bfe0-870c2a685b95 |  | note | FREQ. - Prior to Shift
label | 4c0cb5c4-ed6b-555e-8ebf-cba30c51521e |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | 10aaccd3-d3a6-5bf1-876f-24db4d2f5cc2 |  | note | INSPECTORATE W/H - Type: - W
label | 1d0c4a77-394d-5435-a0e5-1ddbb4eba966 |  | note | INSPECTORATE W/H - Description: - Paving Plan and Crew Briefing Plan completed prior
label | fd9c92b0-5380-5cfb-b9a1-03fd0c7cc18b |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | 24fa653a-f63a-5957-bfc0-33589717fe42 |  | note | VERIFICATION ACTIVITY - Visual
label | b5bc9a02-eaf8-5f54-b8b4-ceb6c5e804c0 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 7b9f3c03-20c5-5f44-af94-160178185350 |  | note | FREQ. - Prior to Shift
label | 20909c46-c830-51d9-a602-38587d9ab64a |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | 6781254c-45d0-5b99-9ed6-c2b0d147cc5c |  | note | INSPECTORATE W/H - Type: - W
label | 91c256f7-87ba-5d7b-98f0-e4826d1d0d36 |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.4 - Grade 3 Membrane Sealing
label | defd81f5-08e8-5313-9c20-85830e82dd99 |  | note | VERIFICATION ACTIVITY - Visual
label | 82fec835-cdce-5a65-965d-bcaf061120af |  | note | METHODS OR REFERENCE - NZTA M/10
label | a09eb394-313d-5464-95d8-e035de4ced96 |  | note | FREQ. - Prior to Paving
label | ca8ee5d0-f4b1-5a9b-9ee1-bce2a15f72ac |  | note | ACCEPTANCE CRITERIA - Applied 2.0l/m² residual
label | d5998b4e-7cb1-5dff-8ef0-ac6fca7b675c |  | note | INSPECTORATE W/H - Type: - H
label | 4c2d91a0-5562-5bbd-be67-398a2afdaa27 |  | note | INSPECTORATE W/H - Description: - Hold Point - No paving until Membrane Done.
label | 9ad61a72-cc1f-59a0-87c4-aa6b0d36ec7d |  | note | Responsible Person - Paving Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Mix Inconsistency and Deficiency
label | afe0d1fb-869a-5a16-91e3-32a9891443c5 |  | note | VERIFICATION ACTIVITY - Visual
label | d96295b5-56ae-57b5-b330-40871d3ef69a |  | note | METHODS OR REFERENCE - NZTA M/10
label | 22b3c1d5-b1a2-57d7-a657-3c8a191bd063 |  | note | FREQ. - Continuous
label | 970d7ed6-64c0-58c6-a2ab-72975621f3d8 |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | c1b236e2-6c39-5237-9910-cc65eca671b6 |  | note | INSPECTORATE W/H - Type: - H
label | 8fb117a9-f92f-5ca7-92af-3db460f196b0 |  | note | Responsible Person - Site Foreperson / QA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Load Locate
label | f44a1523-3d00-5466-98b0-4972d5a08622 |  | note | VERIFICATION ACTIVITY - Measurement
label | 83909feb-fe55-593e-8ecb-e5541fdd4aeb |  | note | FREQ. - Every Load
label | 542215e9-bb90-5d40-bc6a-8534b7b878e9 |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
label | 96a1c70d-2203-5c6d-ab81-fd8d2ce53d16 |  | note | INSPECTORATE W/H - Type: - W
label | df6ebca9-0698-5856-95da-eb0ac3192eaa |  | note | INSPECTORATE W/H - Description: - Per standard practice
label | d3f2b468-f191-554f-aa66-bb6adb65f609 |  | note | Responsible Person - Quality Assurance Technician.
checkpoint-status |  |  | checkpoint | 3.7 - Laying Temperature
label | e3a9baec-8b2b-5ce8-bd31-52e94a378e44 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 30cd813b-e7ed-5fcf-a72a-1b29da5c0c85 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 3eefa4b1-d9ad-5285-a43b-a34ec231ea61 |  | note | FREQ. - Every Load
label | 6bb02551-9318-5165-bae7-ebc2a28ab811 |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | e3ec6b93-9edf-5d44-8437-089296e9b487 |  | note | INSPECTORATE W/H - Type: - H
label | d20ebfc5-5722-5018-9b18-ba826e00a54e |  | note | INSPECTORATE W/H - Description: - Hold point - Reject mix for non-compliant temperatures.
label | 333ae5c4-affc-529b-bca4-945b78db5ee5 |  | note | Responsible Person - Quality Assurance Technician
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Compaction
label | 352ca40b-9766-5ffd-a72c-c559fbea1263 |  | note | VERIFICATION ACTIVITY - PQI Non-Nuclear Gauge/Cores. Or Non Distrctive Method Testing.
label | 610c5e19-7aff-5280-9ea5-8b3c4493b955 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 5bc3fed3-83eb-50d2-a524-e84377be37b6 |  | note | FREQ. - Minimum: 1 Test per 300m² within Mat. 1 Test per 100m of joint. Minimum 8 cores on Mat and 3 on Joints as Per M10:2020.
label | 68196d92-774e-525e-8ce5-d84659f758fa |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | 3dd39457-21be-5bac-adaf-935d7a0f8758 |  | note | INSPECTORATE W/H - Type: - W
label | ed05d65b-32d4-568e-8259-3d129430cb74 |  | note | Responsible Person - Quality Assurance Technician
checkpoint-group |  |  | section | 4 - Site Reinstatement / Clearance
checkpoint-status |  |  | checkpoint | 4.1 - Post-seal Area Check
label | 083f6620-976e-5d08-a20b-b9a4bb804a32 |  | note | VERIFICATION ACTIVITY - Measurement
label | a6100754-b063-5c9f-92e2-d73c973c5a61 |  | note | METHODS OR REFERENCE - On Site tape-measure
label | eca2b33c-34b3-5fa9-a45a-51e58f400b4b |  | note | FREQ. - After Surfacing
label | 6bebb172-e957-59f5-b52b-0055e59c988d |  | note | ACCEPTANCE CRITERIA - Check sealed area meets design
label | 2768fa3a-bd66-5ba8-809e-d1cdea7b4b87 |  | note | INSPECTORATE W/H - Type: - W
label | ee918b94-4861-543f-8629-390b46ca8611 |  | note | INSPECTORATE W/H - Description: - Notify Renewals Engineer or Renewals Manager
label | 1181469f-932c-53f3-8f66-f973ce3aa157 |  | note | Responsible Person - QA Engineer
checkpoint-status |  |  | checkpoint | 5.3 - Service Covers
label | a6caac65-6aad-5529-9bac-4fc7ab7bab0b |  | note | VERIFICATION ACTIVITY - Measurement/Visual
label | 3c799213-3e09-5e7c-8869-cdc6072ebc3c |  | note | METHODS OR REFERENCE - On Site
label | 2be8f677-b703-59c7-ab64-0eb919779fd8 |  | note | FREQ. - After Surfacing
label | 9551314d-340e-5c2b-bc77-3102e2ab272f |  | note | ACCEPTANCE CRITERIA - All service covers are checked and adjusted (if necessary) to finished level
label | ed5924ca-cdc0-54f9-abfe-d8f81d1ba86c |  | note | INSPECTORATE W/H - Type: - W
label | 88a47544-3e74-5201-a3ed-d7ed8c86e95f |  | note | Responsible Person - Paving Supervisor / Foreman
checkpoint-status |  |  | checkpoint | 5.4 - Joint Sealing
label | 41243c3b-8bf8-5685-a018-6b232bbb420f |  | note | VERIFICATION ACTIVITY - Visual
label | 4c915f83-b929-5297-8646-029c5778cdb5 |  | note | METHODS OR REFERENCE - On Site
label | a6d3c4da-6d9b-5f98-b919-8be8ee38df0e |  | note | FREQ. - After Surfacing
label | 6c7b6274-3aea-518f-bd15-92df9de3c87b |  | note | ACCEPTANCE CRITERIA - Check cold joints are bandage sealed
label | 8292ac8a-1ecf-5ec2-86e9-a3dd7c73842f |  | note | INSPECTORATE W/H - Type: - W
label | bdd0a158-e5c9-5609-924b-65e2ee24101b |  | note | Responsible Person - Paving Supervisor / Foreman
checkpoint-status |  |  | checkpoint | 4.2 - Road Marking
label | bd083069-49c6-551b-9e46-b12774c0084e |  | note | VERIFICATION ACTIVITY - MOTSAM
label | 20301122-f8ae-5ce3-9e53-4c040efcc266 |  | note | METHODS OR REFERENCE - Visual inspection
label | 45537192-aedc-5d11-85a9-ccfa517329e0 |  | note | FREQ. - All markings
label | 80cf650b-ddcc-5066-bec9-e801f0026ea6 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, or per design
label | 203a3cf8-4554-5104-8519-a5a2c4444e69 |  | note | INSPECTORATE W/H - Type: - H
label | 4b56d579-509f-5306-bf38-63b244b7a59a |  | note | INSPECTORATE W/H - Description: - Hold point – Site TTM cannot be removed until markings reinstated
label | 29c425ae-5186-578f-acf1-efc26271395c |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 - Other Traffic Services - Marker pegs/ Signs/Markings/RRPMs Replaced
label | 7268169d-69ed-51d0-b10e-b548d07c0cbb |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | d6e6cb02-6e9e-5799-8e61-4356044e302c |  | note | METHODS OR REFERENCE - Visual inspection
label | b6ba3623-de03-5456-b38f-38e6031a912c |  | note | FREQ. - All signs/markers
label | 7b601765-35b5-510d-b3e6-ba467388ab02 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | a8ca6f96-fe31-55c0-af15-38db53797c9a |  | note | INSPECTORATE W/H - Type: - H
label | 0fe82b0a-2ebd-52ed-817d-61b361ad96e5 |  | note | INSPECTORATE W/H - Description: - Hold point – Site TTM cannot be removed until marker pegs, signs, markings and RRPMs reinstated
label | 0b184052-913c-5146-bcae-cddd8aa168a0 |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Stormwater Management Controls removed
label | 3e9b6fe0-14b9-5617-b395-860f98c48c2a |  | note | VERIFICATION ACTIVITY - Visual check
label | 12d4d47a-d324-5770-89f9-f487d9509569 |  | note | FREQ. - All installed measures
label | 2947ae77-f0af-532e-9d13-43831984bdd2 |  | note | ACCEPTANCE CRITERIA - Installed controls are removed
label | 93c67400-f5ab-5fad-9309-5a6fec76e3b3 |  | note | INSPECTORATE W/H - Type: - H
label | 9bfb2b88-8279-5034-885e-825e7c400ff0 |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Traffic Management Removed
label | 6d061af0-444c-515a-b349-1200e3366fb0 |  | note | VERIFICATION ACTIVITY - Visual check
label | aa0356e3-4398-5695-8339-420c1611cc92 |  | note | FREQ. - When safe, after all physical works completed
label | 3f14770d-3d06-55f5-b774-fb73fd33f2d7 |  | note | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | be6150cd-89db-5751-8f00-383cdff5655d |  | note | INSPECTORATE W/H - Type: - W
label | 4ab6ce45-d398-5608-8047-7cef792d4160 |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.6 - Site left clean & tidy
label | 0d09def8-6fee-5734-b54c-69ee6a2d47da |  | note | VERIFICATION ACTIVITY - Visual check
label | 8545c534-77cd-5531-a5ec-31cc163ce7a6 |  | note | FREQ. - After vacating site
label | 3faa1026-1f2d-5806-80e0-4d87291b23c8 |  | note | ACCEPTANCE CRITERIA - Stockpiles removed; Plant removed; Litter cleared from site
label | 16f22193-3737-5ddf-9192-700f69cb4c12 |  | note | INSPECTORATE W/H - Type: - W
label | f7ce9a6b-d186-526f-bcc1-a157ca5fadd4 |  | note | INSPECTORATE W/H - Description: - Invite NZTA to carry out joint site inspection to inspect site.
label | f0b9c081-5fd5-5f3b-a351-cc4cb06b60a8 |  | note | Responsible Person - Paving Supervisor
checkpoint-group |  |  | section | 5 - As Built Records
checkpoint-status |  |  | checkpoint | 5.1 - Collect asset data
label | e684d1cc-42ca-5756-bd0c-863abd343d07 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | e1eb71a2-168c-5f8f-a2ab-fb569c0d545f |  | note | FREQ. - During construction
label | 22b2fc6b-49f7-56d6-b4d7-76df875ead8b |  | note | ACCEPTANCE CRITERIA - All relevant as built information collected.
label | de22151f-2484-53fd-8ddf-fea4edf0fb63 |  | note | INSPECTORATE W/H - Type: - W
label | 4574cafb-674a-501e-b10a-171ac50a865a |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.2 - Enter asset data into RAMM and/or register(s)
label | 7288bcdb-7e70-55d9-99f5-9a5128c2d0bf |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | bcfc32f0-7b56-5bc0-8cdb-85459477b888 |  | note | METHODS OR REFERENCE - RAMM
label | 70599920-ffcc-595d-93bc-0dbfa8b1d8b6 |  | note | FREQ. - At completion of work.
label | 8e2e73a2-6ac6-5881-81e6-db7122591c72 |  | note | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.
label | 131c94db-11d5-530a-9df8-f0f19c45e83f |  | note | INSPECTORATE W/H - Type: - W
label | 878408fc-10d1-5f6e-92a5-5b4560372014 |  | note | INSPECTORATE W/H - Description: - Data entered by 20th of follow month after month of completion
label | 842b5e51-382f-565f-8171-3753bef02c10 |  | note | Responsible Person - Asset Information Manager
checkpoint-status |  |  | checkpoint | 5.3 - Construction Completion Report
label | b8ad3ce0-e788-54c7-8ab1-c6ddb2489a9e |  | note | VERIFICATION ACTIVITY - Confirmation
label | 422d909f-3cee-5d25-bbe9-dafa1c7bc35d |  | note | METHODS OR REFERENCE - Contract Specification
label | f156fa48-b24b-58b8-b34a-e81f5842210d |  | note | FREQ. - At completion of work.
label | 2de2e9bd-9c15-5e96-8e1c-26b743971a07 |  | note | ACCEPTANCE CRITERIA - Checked and approved
label | 15044203-fef3-5dd1-ba16-7aa463e0cd63 |  | note | INSPECTORATE W/H - Type: - W
label | 0a358287-5a96-5691-9366-9c83fd390f1d |  | note | INSPECTORATE W/H - Description: - Completed within two months after Paving Wearing Course
label | a5bba98e-5b86-5901-a0b4-8b82977f81eb |  | note | Responsible Person - Renewals Engineer/ Renewals Manager
checkpoint-no-status |  |  | checkpoint | Quality Assurance Close Out
text | 368ff1d7-0815-5fe1-aa63-1f3dbbecc579 |  | textbox | Quality Assurance Close Out by - Name:
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-sectioned |  |  | checklist | ITP - Milton - Thin Asphalt Paving |  |  |  |  | Yes | ITP - Milton - Thin Asphalt Paving | 68294a68-eba3-4f35-8b10-d7d94fcad37e
checkpoint-group |  |  | section | 1 - Preliminary and General
checkpoint-status |  |  | checkpoint | 1.1 - Construction Programme Completion
label | 0e8cde22-952b-5b97-83eb-e313d2f69525 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 2a7e8056-87b6-59eb-8dca-a5d04d14ac1c |  | note | METHODS OR REFERENCE - Best Practice Contract Specific MMP
label | 887c9d4a-e501-5f2c-b2dc-b32faf0df2f6 |  | note | FREQ. - Before work commences
label | e61bf4de-4c70-57af-9f6b-f761d4d3e526 |  | note | ACCEPTANCE CRITERIA - Construction Completion will be the lesser of the completion date according to the pavement classification risk profile (documented in the contract specific MMP) or the contract completion date.
label | 2d6b7f55-bc68-56c7-9dfc-5dfac7db2632 |  | note | INSPECTORATE W/H - Type: - W
label | ec13bb2f-ce65-58e7-83f8-48583370f83b |  | note | Responsible Person - Renewals Manager
checkpoint-status |  |  | checkpoint | 1.2 - Approved RQP
label | 344dd30b-2146-55cc-89f6-ba7d7351eff5 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 4c71af03-bbbf-5e20-a4b4-f0c75bc98ce9 |  | note | METHODS OR REFERENCE - Contract Specification
label | e4242651-9581-560e-bf0c-c048b873b6b8 |  | note | FREQ. - Before work commences
label | 25872c96-38a5-55e2-9d19-d93435762662 |  | note | ACCEPTANCE CRITERIA - Principal Acceptance according to guidelines in appendix 6.3
label | 285eba0d-4863-55cd-b7a5-d74987036241 |  | note | INSPECTORATE W/H - Type: - H
label | d739ac7d-11d7-5369-9dd7-5ad399dcf494 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. NZTA to approve
label | cca3b713-d4a1-5c53-8106-22142c0b97f3 |  | note | Responsible Person - Renewals Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Traffic Management- TMP
label | 31a602a6-c8d9-5901-957f-7090b0f5f36d |  | note | VERIFICATION ACTIVITY - Visual check
label | f8ce7b52-6619-5a23-ae97-6cc8bcdfe668 |  | note | METHODS OR REFERENCE - CoPTTM
label | 6768bbc7-5f49-5aee-a71e-30859f7665a8 |  | note | FREQ. - Before traffic management set up
label | 0955b64e-a6fb-506f-8dfb-a0eeec76e3ba |  | note | ACCEPTANCE CRITERIA - TMP checked and approved Plans approved Current EED (if applicable)
label | 23db9662-194f-5f70-9fb0-e8aac03a452c |  | note | INSPECTORATE W/H - Type: - H
label | 63801ea7-d7c4-5414-85f2-2e4971738040 |  | note | INSPECTORATE W/H - Description: - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | 51c5ff05-2cec-5126-b105-cfca0351baa1 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Mix Design Verification for all mixes Check Laydown Trials are complete and compliant
label | 98d0933e-a8d3-5a47-bf70-a4052b88dd54 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 436b502c-9183-5c7c-be17-4b680ee325db |  | note | METHODS OR REFERENCE - NZTA M/10, P/11, P23
label | e2fdf91b-5a37-5042-a17a-b8d109d39521 |  | note | FREQ. - Before planning commences
label | 701bdc74-ddf1-5175-b9a5-d9850d330140 |  | note | ACCEPTANCE CRITERIA - Mix Design compliant, current and relevant. Batching plant production capability is confirmed
label | 3acf4d1c-e640-53d7-bd7d-a68f5fbe1f63 |  | note | INSPECTORATE W/H - Type: - H
label | 91cfa423-2476-5f3b-a256-f18b49941e93 |  | note | INSPECTORATE W/H - Description: - Hold point - No planning of on-site works shall commenced until the mix design is verified.
label | 99699d29-6b85-591b-9edb-8963ceaba5ba |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Notification of intention to start work
label | a0bc3d99-97b7-581a-887d-2af90fa91b90 |  | note | VERIFICATION ACTIVITY - Notification
label | 2c3f94e6-27b1-5506-bbd4-abad622b81af |  | note | FREQ. - Before work commences
label | da5226ee-d9cf-58d5-955b-ebc7d1388095 |  | note | ACCEPTANCE CRITERIA - Letter drop to local residents. Greater consultation where required
label | 0b369e2c-2b06-5a3d-816f-8948180d5f86 |  | note | INSPECTORATE W/H - Type: - H
label | 219a9006-7928-5999-807b-5b98730abe25 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | 217efbc5-b9ca-57c1-9b96-6daf2bccac2e |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Works Extents
label | 92fb6be8-d703-53d7-82fd-dc9f4d0a1a25 |  | note | VERIFICATION ACTIVITY - Confirmation
label | c2294109-b203-50a1-b935-6fa1ee9395da |  | note | METHODS OR REFERENCE - Site Visit
label | 03eb1f0a-c66b-5f2e-8cc8-4b0808504ca1 |  | note | FREQ. - Before work commences
label | 7babde6c-4ef2-5c41-95c9-fd8d6fbd2956 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and/or Client to agree extents of project
label | ae46714c-f0e2-5841-981e-33d9ef8a3e37 |  | note | INSPECTORATE W/H - Type: - H
label | b37e6301-ccf7-5980-9851-737dff791f09 |  | note | INSPECTORATE W/H - Description: - Hold point - Walk over site with Renewals Engineer and/or Renewals Manager and/or NZTA
label | 4fe28e9e-fb6a-58ba-8f9b-f3f20f5dbf0c |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - Pavement Marking Records
label | 9ec426ff-f213-532d-a655-021966fa60f2 |  | note | VERIFICATION ACTIVITY - Measurement Data
label | 4cae7e91-e02d-56f6-afbf-8f09e71cd5bc |  | note | METHODS OR REFERENCE - Site Measure or Video Viewer
label | 2337dd00-46a9-5b78-b035-403bcd5121b8 |  | note | FREQ. - Before work commences
label | 88bc5f2c-53d1-50dd-b520-73c9a19c6d91 |  | note | ACCEPTANCE CRITERIA - Measure existing markings to aid reinstatement
label | 5e5cadf8-810e-56f2-8810-f024853263da |  | note | INSPECTORATE W/H - Type: - H
label | a127dfa1-99e4-569a-8c72-a30dd748e7b9 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | 4af6955c-d958-54b5-99f2-2d821a5333ee |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Milling and Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | 23f58907-7014-5691-b863-3395ff07ac22 |  | note | VERIFICATION ACTIVITY - Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth)
label | e82bf196-5f85-5ad9-9064-57b7dd56a292 |  | note | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | 50c2147d-2389-592c-811b-0b984a064640 |  | note | FREQ. - Before work commences
label | e96a6208-7b3d-57de-a1ab-995066985fca |  | note | ACCEPTANCE CRITERIA - Zero service strikes
label | 1454c77d-cbaf-531e-af68-842db7b1a61d |  | note | INSPECTORATE W/H - Type: - H
label | 009f3d16-38be-5ba8-bc20-60ac75626944 |  | note | INSPECTORATE W/H - Description: - Hold point - No excavation/milling is to be commenced until services are located and accounted for
label | 3c7a9418-6e85-548c-83a8-4ac06caa8c00 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Stormwater Management
label | 10137ba3-ac52-54fd-8a11-9168d4ddf892 |  | note | VERIFICATION ACTIVITY - Visual check
label | 00e9aa76-5254-5b4c-9491-c858767c4d7f |  | note | METHODS OR REFERENCE - On Site
label | f92f89f1-97a7-5aa1-83df-4fa5b482392a |  | note | FREQ. - Before work commences
label | b7df797c-a746-592b-84b7-b5c074abc0ac |  | note | ACCEPTANCE CRITERIA - Mudtanks bunded or filtered to prevent mix from dropping in or runoff entering
label | 5bd0f167-ec6c-52c9-b42a-ce83dff32f22 |  | note | INSPECTORATE W/H - Type: - H
label | 2a4e983d-3a2d-55e9-b424-a94d9a618022 |  | note | INSPECTORATE W/H - Description: - Hold point - No work to be commenced until protections in place
label | a7a873d4-0285-51fd-b151-6d94c60f50f8 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Traffic Management- Setup
label | 7a3e3312-697e-58a0-b7f1-c1bdfd78acb8 |  | note | VERIFICATION ACTIVITY - Visual check
label | c56b4bae-095c-5032-9e80-d720a83dd05c |  | note | METHODS OR REFERENCE - Traffic Management Plan
label | d0181651-2662-5fcd-9b1d-ed65479b626c |  | note | FREQ. - Before work commences each day
label | da9e628d-f484-5e59-b18c-ba05917c7eae |  | note | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | b0791cb3-f815-5185-b028-244720508604 |  | note | INSPECTORATE W/H - Type: - H
label | c702bbb8-5f47-577e-830d-230c51dde077 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | c643f7e1-17ca-5138-914b-e65be9926930 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Milling Depths
label | 009368a1-0f7e-5c6a-a790-ef0d4663606d |  | note | VERIFICATION ACTIVITY - Measurement
label | 454d6575-f92d-5129-a84f-a8ba5be1466a |  | note | METHODS OR REFERENCE - On Site
label | 6be50807-7e47-581e-9bf1-70d828187e82 |  | note | FREQ. - Measure each side of milling machine cut
label | 76f65dc1-b01b-5295-8425-0351aa55b736 |  | note | ACCEPTANCE CRITERIA - Every 10m. Depth matches target
label | ddd5cd3c-ee0d-5e38-879f-02872450a2b2 |  | note | INSPECTORATE W/H - Type: - H
label | 10ab18fc-52d2-55d3-bcef-8f494c037951 |  | note | Responsible Person - Site Foreperson / QA
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Service Covers Preparation
label | 1ec93aaa-50b0-5017-91eb-22a40c1aaf3f |  | note | VERIFICATION ACTIVITY - Visual
label | c112af15-0bef-574f-9f94-ecaeda4aeebb |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 24a0f2ad-abc8-5322-abaa-c53508409ee8 |  | note | FREQ. - All Covers
label | ba8b919f-7bac-5330-8d94-a41ab791608d |  | note | ACCEPTANCE CRITERIA - Hand excavation around ironwork and adjustment to desired level (if required)
label | d1c843a9-9e28-5b7b-af44-8ffb98cf0d8b |  | note | INSPECTORATE W/H - Type: - H
label | ca1b83fd-4492-5726-92f4-1ccfb53dfb67 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Additional Surfacing Preparation - Side Roads - Accesses - Driveways - Dish Channels - High Shoulders
label | 881d0356-5dd8-51ca-84ac-59637a637ebb |  | note | VERIFICATION ACTIVITY - Visual Check
label | 8437c889-22ea-5c1c-b90d-9fe2ec3049b8 |  | note | METHODS OR REFERENCE - Per Design
label | bbda70e1-5b9e-59f2-b037-94cd7c7e8c5b |  | note | FREQ. - Before Membraning and Paving
label | b6f468b3-3961-5a3b-a8c7-3fbee08454b5 |  | note | ACCEPTANCE CRITERIA - Have all areas of additional surfacing on the design been prepared, membraned and marked for paving?
label | 6d520f62-f2b0-5d8c-9b33-f965e81710cb |  | note | INSPECTORATE W/H - Type: - H
label | 2a8e0e2b-f903-599e-99c1-f5795f11f1bd |  | note | INSPECTORATE W/H - Description: - Hold Point – All areas planned for AC are prepared ready for surfacing layer
label | 8178d036-7564-5f63-972a-c67a0f2f1b2a |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Over-Milling
label | 4330cd3c-35d2-5c59-b8a7-343e0719df5a |  | note | VERIFICATION ACTIVITY - Measurement
label | cc929c72-0793-5b21-a204-f5ee4358f7af |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 5c237191-6e1d-5360-b66c-6b0b6c1f27a2 |  | note | FREQ. - Prior to pre-level
label | 054568d8-7bed-5773-adf5-f4ce91026b04 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree need and extent of over-milling and infill.
label | 931f784f-640d-59de-aad5-d4a53f74a561 |  | note | INSPECTORATE W/H - Type: - H
label | 2821ccd0-1b00-5e20-98f6-6e301aeb5dda |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Pre-Level
label | 895be3ba-f655-5907-810f-332843dc1909 |  | note | VERIFICATION ACTIVITY - Measurement
label | b0909e31-42e0-5fc5-b82c-c67886d44f44 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 331c99df-2eb2-5aef-aec2-ad3d9695d31f |  | note | FREQ. - Prior to surfacing
label | 3d4d1829-58ec-5433-85c5-6d252d39488e |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree pre-level extents
label | 94257c2b-94de-590f-b1dc-9362cb7a4709 |  | note | INSPECTORATE W/H - Type: - H
label | 9f42e186-d3f1-5c14-a919-fb44d9591196 |  | note | INSPECTORATE W/H - Description: - Hold point - Inspection and agreement by NZTA
label | 81485420-288b-57f0-b0f3-4bd1fb45212e |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.9 - Membrane Sealing
label | c1bc69b0-74d3-5802-887d-1ba10c6187e2 |  | note | VERIFICATION ACTIVITY - Visual
label | 17a72c3e-e793-5be6-85b7-330e888873af |  | note | METHODS OR REFERENCE - On Site
label | 81819539-d478-59bf-ae00-6a27b0751266 |  | note | FREQ. - Prior to surfacing
label | b38b269e-4078-5a95-a87b-089bbef154d3 |  | note | ACCEPTANCE CRITERIA - Membrane seal meets design and extent. Sealing Docket record kept
label | cf9a8268-0e63-58a3-800b-fcfdeda049cf |  | note | INSPECTORATE W/H - Type: - H
label | 50c04cb9-46d6-5b1d-9c84-49e49d2d9127 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Paving Structural
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | f1fc284f-5b44-59a2-8b6d-3e7644107c15 |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | 51430ba7-cb6a-5e7c-9825-9e96e798becb |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | 09a35ca7-b569-5814-9dfa-10eea3d12b94 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 0148111a-4832-56c6-bf83-8d90cc037ffe |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 678ce60c-8862-5227-b586-27c2aedbf54b |  | note | INSPECTORATE W/H - Type: - W
label | d9623a4c-0bb5-59c9-9dd8-9ef9cfd7b997 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-conformance
label | 7e8b07c4-72c6-5f1c-94e3-fed6a564f5d6 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | fc9a4cab-f3aa-5f53-869c-7dc9234b9514 |  | note | VERIFICATION ACTIVITY - Quantitative Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | 80a2a148-7de4-56ae-9ad7-0550cac09dc9 |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | 6bec9080-fbbb-509d-8ba6-f37596109336 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | ee7de2cf-d4e9-593f-b44d-10ade881a636 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | c34f31a3-2154-5d6b-b793-309572b18769 |  | note | INSPECTORATE W/H - Type: - W
label | a3496706-20f5-5958-a123-dc55817da72c |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-conformance
label | 9135d9eb-b3ef-5d63-b79a-7e840ec008cc |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | a92ae389-5673-5fea-94a9-c1b570526c9b |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | 3c497e5c-16fa-5b21-907d-44bba523ab9f |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | 6bc494b7-3299-53e0-9833-7b3f65c73e2a |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 00e0c6ba-309d-5bd7-b279-98d56585daec |  | note | INSPECTORATE W/H - Type: - W
label | 4e618ed7-7e7c-5248-8f5f-aca991af14e3 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-conformance
label | 61e6d6ab-9de8-5325-8d9e-92dadb321127 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | a483fb15-09e1-53f7-87d0-ce659685cd0d |  | note | VERIFICATION ACTIVITY - Visual
label | d099cd3e-8b44-5a41-a523-19ebc666c0d2 |  | note | METHODS OR REFERENCE - NZTA M/10
label | bc9dce34-4409-5331-ae51-6d7c68b815ef |  | note | FREQ. - Prior to Shift
label | f8a45f96-5bbe-5379-b3df-1bcde9f9a60f |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | 77560b43-5e3d-57bc-b203-72cec4c79c08 |  | note | INSPECTORATE W/H - Type: - W
label | 79aeed9d-8def-58d2-ad2b-3a327c42f369 |  | note | INSPECTORATE W/H - Description: - Paving Plan and Crew Briefing Plan completed prior
label | 9ccfd078-d070-577f-b9b7-c6fc79e9e135 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | 260b94f4-f554-58ae-8a8e-8a05ddf134bb |  | note | VERIFICATION ACTIVITY - Visual
label | 1474803a-d413-5c01-a5b3-ee776c70cd8a |  | note | METHODS OR REFERENCE - NZTA M/10
label | 5c2f695e-d241-5916-8b89-62ee2100a835 |  | note | FREQ. - Prior to Shift
label | 0d8c8fea-c48b-59ba-a8c1-cc973bcbd0fb |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | 361c44e8-3ef2-5cd0-88e4-ebd7d2d5fd10 |  | note | INSPECTORATE W/H - Type: - W
label | 928e0d0f-6a1d-5470-8b6d-9a02396a5123 |  | note | Responsible Person - Paving Supervisor / QA Engineer
checkpoint-status |  |  | checkpoint | 3.4 - Mix Inconsistency and Deficiency
label | bb513b0d-2208-5516-88fa-a1258952cff0 |  | note | VERIFICATION ACTIVITY - Visual
label | a3fa5cad-0a66-5b0a-9b68-be8bbd58cbd1 |  | note | METHODS OR REFERENCE - NZTA M/10
label | aaae5fad-b89a-5685-871b-16a767d713a2 |  | note | FREQ. - Continuous
label | a0781329-0a3b-5d04-a691-d97d36cc4733 |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | 8c739c38-bde0-5c78-a342-4f4673c299a6 |  | note | INSPECTORATE W/H - Type: - H
label | 043546c4-64eb-5f95-95ec-1e14cd119c51 |  | note | Responsible Person - Site Foreperson / QA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Load Locate
label | 3059fb6b-7a86-5aa7-9202-41910c26732c |  | note | VERIFICATION ACTIVITY - Measurement
label | 7950a248-ba00-5467-87b2-ade8d2652e72 |  | note | FREQ. - Every Load
label | 989b32fe-eef1-5386-be49-25ca63961e39 |  | note | ACCEPTANCE CRITERIA - Each load can be identified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
label | 572b1548-57c0-5aa6-851b-3208f6db17be |  | note | INSPECTORATE W/H - Type: - W
label | d830efa5-2b52-5193-95be-f5b7322a000c |  | note | INSPECTORATE W/H - Description: - Per standard practice
label | 23dcf1cf-6920-5601-bec8-79aef966e851 |  | note | Responsible Person - Quality Assurance Engineer
checkpoint-status |  |  | checkpoint | 3.6 - Laying Temperature
label | 1d328ebc-bb48-5493-b68d-3005517ca68c |  | note | VERIFICATION ACTIVITY - Confirmation
label | 284eddf6-15e0-5af7-9c54-fd6ec3b3cb7c |  | note | METHODS OR REFERENCE - NZTA M/10
label | 19c35402-806c-5bd5-aeee-826c40455939 |  | note | FREQ. - Every Load
label | e99ac7d2-c4c3-53c4-b5fb-1eac28cdfba1 |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | 52e165cd-bdb1-5599-b895-f0550c7a8cf6 |  | note | INSPECTORATE W/H - Type: - H
label | d89a194e-8546-51c4-92d8-e79bb22d4c37 |  | note | INSPECTORATE W/H - Description: - Hold point - Reject mix for non-compliant temperatures.
label | c9c9025b-3163-5d9f-9aef-de5ba060ffd6 |  | note | Responsible Person - Quality Assurance Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Compaction
label | 41fcce37-3541-5856-9b54-f9d3350b8c8e |  | note | VERIFICATION ACTIVITY - NDM Testing
label | fee64386-e722-5413-9a50-787a990be85e |  | note | METHODS OR REFERENCE - NZTA M/10
label | ce01691f-92e2-52c6-a658-9516c2f09084 |  | note | FREQ. - Minimum: 1 Test per 300m² within Mat. 1 Test per 100m of joint.
label | d000a4e4-572d-5c85-8ca1-fc8a5e45d82b |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | 328565f5-cf78-5545-8971-22afeb595072 |  | note | INSPECTORATE W/H - Type: - H
label | 747e14fa-3860-5863-992a-096d10402b68 |  | note | INSPECTORATE W/H - Description: - Hold Point - No Wearing course paved until any non-compliance is sorted
label | 457fe689-f171-55d3-b681-1399d9893438 |  | note | Responsible Person - Quality Assurance Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Roughness
label | ac01c1c5-f462-5554-8079-3c9fb03f6174 |  | note | VERIFICATION ACTIVITY - NASSRA Testing
label | 30bfb7f2-522b-57a8-ae56-e86cd3bc8762 |  | note | METHODS OR REFERENCE - Contract Specification
label | bd147245-96df-514e-b70e-8d570b65c679 |  | note | FREQ. - post construction
label | e2cf74dd-c48d-52a9-b454-786c5e2812f0 |  | note | ACCEPTANCE CRITERIA - NASSRA rolling meter average under 60, max of 70
label | 54615226-a0f6-58ef-aa6e-201ad30dd151 |  | note | INSPECTORATE W/H - Type: - H
label | 087d946f-5fc6-5f3b-9aaa-e9e4e71f98cb |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Paving Wearing Course
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | 51cd75d3-3f9c-587f-b880-155e28867c70 |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | c0c5835a-2984-579c-a403-59a219c27467 |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | 2a57b611-c628-538d-a7ed-daa91d0f5268 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | ba7204f6-cbbd-5984-865d-2cc34e17911d |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 411c631f-70ff-5d3a-9138-57faf6384d0a |  | note | INSPECTORATE W/H - Type: - W
label | c999c8cf-7a6a-503e-9bbb-c08298ba96dc |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-conformance
label | fa620bdf-ef2a-5faa-a7c6-1a524e48f55f |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | cc7242c3-5a5e-5890-bab0-d53732021391 |  | note | VERIFICATION ACTIVITY - Quantitative Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | da07efd4-9a9e-5d79-8b4b-a4e16676f27c |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | 7db164cd-1063-523b-b2cb-6f500c430293 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 50b3b41d-e8ac-5aa9-9c70-0722f67551d2 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | a9436c6b-32ad-5267-be50-c149eb63b139 |  | note | INSPECTORATE W/H - Type: - W
label | 4e077c7e-22a4-5d73-8022-de39ae0456c5 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-conformance
label | 1e1a5ced-ad59-518a-badb-bf0ac5a28518 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | e04011f1-a801-5638-bcf3-559ec44477a5 |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | cfbce524-30ef-5ccb-b8c3-2db450731ed2 |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | e00f6af5-8242-5c7d-b9a0-e71767553980 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 500f2dab-e689-5093-9728-75558cd52566 |  | note | ACCEPTANCE CRITERIA - Per Mix design
label | 29f22cae-0332-55aa-ba6f-a487a0b74dad |  | note | INSPECTORATE W/H - Type: - W
label | 714cda72-3b9c-5972-90e7-d558bfcd118c |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-conformance
label | 19c4bb5d-e767-51c2-93e2-bfab89204404 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | f182e0f6-3291-5d10-8943-d87a9944aaee |  | note | VERIFICATION ACTIVITY - Visual
label | 32c30323-cc39-5fda-a488-f760f8165051 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 505132f2-7c53-5359-81e9-32214f9d3bd6 |  | note | FREQ. - Prior to Shift
label | f5e3bc8c-adb4-53a7-afc4-5e239198edb3 |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | ab4c0943-21eb-5504-abcf-bc4b78ec558c |  | note | INSPECTORATE W/H - Type: - W
label | 64ae8f2f-89d1-5aa1-8c1e-5d17f440d05f |  | note | INSPECTORATE W/H - Description: - Paving Plan and Crew Briefing Plan completed prior
label | d4754540-9a24-5113-91e2-30002a2b24fe |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | 79ddc8d4-301e-52e6-befb-e11affc43925 |  | note | VERIFICATION ACTIVITY - Visual
label | 86131147-fc41-5047-a9c0-b3ab767081a5 |  | note | METHODS OR REFERENCE - NZTA M/10
label | cbef2abc-752e-5848-887c-a579cbabc45f |  | note | FREQ. - Prior to Shift
label | 463d06fb-5888-5b1a-9122-9a1e0beea1dd |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | 60223bfc-f887-5546-872a-d591e182df1a |  | note | INSPECTORATE W/H - Type: - W
label | 414f38c2-bdf0-59b3-822a-51303785009a |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.4 - Grade 3 Membrane Sealing
label | a9a5136f-eb27-5c82-a623-17883c88b7b7 |  | note | VERIFICATION ACTIVITY - Visual
label | 9ae0900d-aa6b-5862-ba13-c54b856d3b1c |  | note | METHODS OR REFERENCE - NZTA M/10
label | a1ccae40-9721-5bfe-9aa7-d81ac14f54ec |  | note | FREQ. - Prior to Paving
label | 532fa944-3d21-5cc5-9fc5-e2409912b86a |  | note | ACCEPTANCE CRITERIA - Applied 2.0l/m² residual
label | f5459a0e-fce5-59fe-aa67-b58e17be2c44 |  | note | INSPECTORATE W/H - Type: - H
label | 5c4f0dd4-7cea-557f-aa65-39094093092f |  | note | INSPECTORATE W/H - Description: - Hold Point - No paving until Membrane Done.
label | 1066ef11-7fa2-54e8-8621-c9765b61ee33 |  | note | Responsible Person - Paving Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Mix Inconsistency and Deficiency
label | efd7db0b-6571-57fa-af1d-1cd61382dd23 |  | note | VERIFICATION ACTIVITY - Visual
label | ffb19896-f2d1-530f-81f7-0973029dc218 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 35c3da9b-ec36-5a1c-ace4-164f15e427d4 |  | note | FREQ. - Continuous
label | a9659bed-88c6-5443-9013-05d037c75f2e |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | 893aa526-7e4f-5e01-a986-661053520cfc |  | note | INSPECTORATE W/H - Type: - H
label | 66af9a98-74d3-5be8-8eaf-8780369be0a8 |  | note | Responsible Person - Site Foreperson / QA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Load Locate
label | cfaffbdc-c634-5333-b02b-5b639bd404f9 |  | note | VERIFICATION ACTIVITY - Measurement
label | 0728850e-d070-5fea-9a24-78dc5be3fa9e |  | note | FREQ. - Every Load
label | 64798d36-157c-5d7d-9032-c1a3c4994601 |  | note | ACCEPTANCE CRITERIA - Each load can be identified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
label | 76f08ab3-ff0a-543f-94d2-760989d66ba8 |  | note | INSPECTORATE W/H - Type: - W
label | 490ae395-39ba-528c-9892-11cc1db969d9 |  | note | INSPECTORATE W/H - Description: - Per standard practice
label | dd0ccbb9-19e7-5c90-8a7e-95d5f2678087 |  | note | Responsible Person - Quality Assurance Technician.
checkpoint-status |  |  | checkpoint | 3.7 - Laying Temperature
label | 1a7167a7-df25-5a7d-9d8f-f9ae59188c50 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 415911c1-2554-55c2-b14c-0ea6c94ca38e |  | note | METHODS OR REFERENCE - NZTA M/10
label | ca7466c4-b159-5c3d-84b4-6a1daf6b7a15 |  | note | FREQ. - Every Load
label | e0f07cc6-5b55-56c7-a7fd-a452747f11dc |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | b07c9938-34c7-5028-a6b5-439a928a9733 |  | note | INSPECTORATE W/H - Type: - H
label | e4bfbafd-948e-5188-9593-b868b7b5e380 |  | note | INSPECTORATE W/H - Description: - Hold point - Reject mix for non-compliant temperatures.
label | f0ef56bf-707b-5b1e-a460-0449f296b855 |  | note | Responsible Person - Quality Assurance Technician
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Compaction
label | be11502e-013d-5f93-8aeb-4e6605b0bb0f |  | note | VERIFICATION ACTIVITY - PQI Non-Nuclear Gauge/Cores. Or Non Destructive Method Testing.
label | 88f16e75-fbc1-5618-8d3e-c0bf7f1cd07d |  | note | METHODS OR REFERENCE - NZTA M/10
label | 2bf91d95-0f25-53ec-a76f-a6fc58a45589 |  | note | FREQ. - Minimum: 1 Test per 300m² within Mat. 1 Test per 100m of joint. Minimum 8 cores on Mat and 3 on Joints as Per M10:2020.
label | e02df175-f706-5b90-ba66-60caf85d1226 |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | 70bfce03-d98b-5e4c-9568-915c63e2ae49 |  | note | INSPECTORATE W/H - Type: - W
label | 8daad528-6f3d-5c0b-8d18-c518a795e305 |  | note | Responsible Person - Quality Assurance Technician
checkpoint-group |  |  | section | 4 - Site Reinstatement / Clearance
checkpoint-status |  |  | checkpoint | 4.1 - Post-seal Area Check
label | 1b3dbb5e-f35b-5233-85ee-25f114dde541 |  | note | VERIFICATION ACTIVITY - Measurement
label | 903b7753-7bdf-5b60-a9e7-9d124a1ec8ba |  | note | METHODS OR REFERENCE - On Site tape-measure
label | c1f4562a-9b3b-51e1-b89b-f9964d5ee698 |  | note | FREQ. - After Surfacing
label | 767b6966-5993-55c4-83e0-23152d9b9af8 |  | note | ACCEPTANCE CRITERIA - Check sealed area meets design
label | 13c96914-9bd7-55db-a196-b0a26e8dcc0f |  | note | INSPECTORATE W/H - Type: - W
label | dc6e0e6e-b936-5af2-8ddb-4a93cda3166b |  | note | INSPECTORATE W/H - Description: - Notify Renewals Engineer or Renewals Manager
label | 23f89fad-fac2-55a5-82b0-8ba204fd676e |  | note | Responsible Person - QA Engineer
checkpoint-status |  |  | checkpoint | 5.3 - Service Covers
label | e0da3a3c-274c-5264-9966-cbac90d6b27f |  | note | VERIFICATION ACTIVITY - Measurement/Visual
label | cc393323-3cd3-5336-aece-384692a87c21 |  | note | METHODS OR REFERENCE - On Site
label | 249ed481-923d-546a-bd0e-6c6a4ec8e3b7 |  | note | FREQ. - After Surfacing
label | 8e8a38f2-c230-5f97-97bb-897225684705 |  | note | ACCEPTANCE CRITERIA - All service covers are checked and adjusted (if necessary) to finished level
label | a60ae2cf-c9cf-593d-a9f4-66f7d7025045 |  | note | INSPECTORATE W/H - Type: - W
label | 49a9a4a3-437f-5888-a4e2-476056798681 |  | note | Responsible Person - Paving Supervisor / Foreman
checkpoint-status |  |  | checkpoint | 5.4 - Joint Sealing
label | faa0df9d-584d-5260-b376-94921e94dba9 |  | note | VERIFICATION ACTIVITY - Visual
label | c163da74-0642-585d-a72f-826531b96178 |  | note | METHODS OR REFERENCE - On Site
label | 8c7779b3-a174-5908-9142-8d869a300763 |  | note | FREQ. - After Surfacing
label | 4e73f66b-e3f6-58ec-9414-6828fbbdc654 |  | note | ACCEPTANCE CRITERIA - Check cold joints are bandage sealed
label | e28386e5-aae4-5abd-a04a-089308d59a34 |  | note | INSPECTORATE W/H - Type: - W
label | d2372164-57f5-5e46-94a5-c85d9a972b3b |  | note | Responsible Person - Paving Supervisor / Foreman
checkpoint-status |  |  | checkpoint | 4.2 - Road Marking
label | 867043b4-8762-5507-9fb9-5c2b76efe324 |  | note | VERIFICATION ACTIVITY - MOTSAM
label | b08cc35b-b6c7-59e2-915a-6809c19fcf4a |  | note | METHODS OR REFERENCE - Visual inspection
label | 02b1f905-0905-5635-bc9f-9482f9d505a6 |  | note | FREQ. - All markings
label | 78db8094-5a1b-5087-81c0-6245cc873ddb |  | note | ACCEPTANCE CRITERIA - Replaced in same position, or per design
label | 6b877bbc-9204-55bb-ba59-e777aae9a5d8 |  | note | INSPECTORATE W/H - Type: - H
label | 7c15b654-e843-5d6c-ae5e-7d49e6f38e8e |  | note | INSPECTORATE W/H - Description: - Hold point – Site TTM cannot be removed until markings reinstated
label | 05ac7732-da81-5612-945d-985f5056e6ea |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 - Other Traffic Services - Marker pegs/ Signs/Markings/RRPMs Replaced
label | 3ee62f3a-b725-5f62-b260-0b7e049d55cd |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | 1d163c1a-73e4-55c3-b832-b20af38f1ac8 |  | note | METHODS OR REFERENCE - Visual inspection
label | 716abf9f-62d1-53b0-bad6-dea68761e44e |  | note | FREQ. - All signs/markers
label | a8d98810-9575-5e29-9ae5-2e46602a56f1 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | 0a0871d2-a3d5-5657-8dcc-448a437b6a32 |  | note | INSPECTORATE W/H - Type: - H
label | 85d93f5b-17dc-5e38-a1f2-845090ede558 |  | note | INSPECTORATE W/H - Description: - Hold point – Site TTM cannot be removed until marker pegs, signs, markings and RRPMs reinstated
label | 947bcec8-9219-53bb-9823-869be63a4604 |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Stormwater Management Controls removed
label | a9c5ba26-0978-5289-8747-bf9accfee52d |  | note | VERIFICATION ACTIVITY - Visual check
label | 085797f4-e6f4-592a-bccd-0e1bce62fe15 |  | note | FREQ. - All installed measures
label | 408c36d6-b4f6-59af-85a6-477e9910e9fe |  | note | ACCEPTANCE CRITERIA - Installed controls are removed
label | 12a7f71b-8351-556a-8872-18820d3063c0 |  | note | INSPECTORATE W/H - Type: - H
label | 21a18d7e-1c63-5dda-8b3d-64c61d3831bc |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Traffic Management Removed
label | 7cd97eb5-ad79-50d9-b037-0328b9232b62 |  | note | VERIFICATION ACTIVITY - Visual check
label | 9cfb72cd-a3ce-5e55-8efe-167a5391e717 |  | note | FREQ. - When safe, after all physical works completed
label | f68085f2-d342-54ab-89ae-f3e27faf98d9 |  | note | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | 0207db11-cff8-505a-b3b3-b56864cf22cb |  | note | INSPECTORATE W/H - Type: - W
label | 2142fa4f-2759-5dc4-97d2-511dce08372b |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.6 - Site left clean & tidy
label | 1db513da-9947-5c0d-8c38-f8094ad8eb07 |  | note | VERIFICATION ACTIVITY - Visual check
label | 101b2e6a-75d9-523d-bdb1-fd24e6b3b023 |  | note | FREQ. - After vacating site
label | 709d338b-48ae-5134-b909-e788df603a24 |  | note | ACCEPTANCE CRITERIA - Stockpiles removed; Plant removed; Litter cleared from site
label | 5ee2baa8-1286-569b-908c-9ae7af0ed6a0 |  | note | INSPECTORATE W/H - Type: - W
label | c2860fc0-4721-54bf-929c-c9286d538a46 |  | note | INSPECTORATE W/H - Description: - Invite NZTA to carry out joint site inspection to inspect site.
label | 0d37adbc-0443-523d-8e49-15d143cb43e2 |  | note | Responsible Person - Paving Supervisor
checkpoint-group |  |  | section | 5 - As Built Records
checkpoint-status |  |  | checkpoint | 5.1 - Collect asset data
label | 1f41f069-1dc5-5e83-81d6-01f1d39cdae6 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | 5c354756-5379-5e19-b03b-48f7fa415587 |  | note | FREQ. - During construction
label | c0acf849-c305-5cf7-90cf-a5671c73d0d0 |  | note | ACCEPTANCE CRITERIA - All relevant as built information collected.
label | f9951d6d-7a76-5b88-b2e9-de9e98bf8d27 |  | note | INSPECTORATE W/H - Type: - W
label | 8662ba8d-c1ef-53b7-a7c0-3c748e1896de |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.2 - Enter asset data into RAMM and/or register(s)
label | 57906b13-6a9a-515f-ae91-c7bf4655e7e9 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | 97645bfc-03d7-59dc-a5ba-61336240215f |  | note | METHODS OR REFERENCE - RAMM
label | 5a32b572-ef67-52ee-8629-40ff9c56d31d |  | note | FREQ. - At completion of work.
label | a18a75ca-034b-5b6f-bfc7-7dbcacd08e5b |  | note | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.
label | e1f86b01-8910-56b2-adb0-77d3e2d3c900 |  | note | INSPECTORATE W/H - Type: - W
label | e6d804b5-1637-5d52-967a-4b8fb6eba677 |  | note | INSPECTORATE W/H - Description: - Data entered by 20th of follow month after month of completion
label | 57c079cc-459d-5c8f-b4c4-9ac32f28c515 |  | note | Responsible Person - Asset Information Manager
checkpoint-status |  |  | checkpoint | 5.3 - Construction Completion Report
label | dc920976-af0e-56e9-8d92-ecec8f5151ef |  | note | VERIFICATION ACTIVITY - Confirmation
label | d16e496d-7ee6-5dcc-be15-bb4a1620450e |  | note | METHODS OR REFERENCE - Contract Specification
label | 6f4ce03a-8ac9-5310-acaf-3423039399ee |  | note | FREQ. - At completion of work.
label | 9963b8b1-9c2e-5375-a90d-d0ff6fbb8b20 |  | note | ACCEPTANCE CRITERIA - Checked and approved
label | 4757a42d-3139-51df-8b6b-58caa5a972fd |  | note | INSPECTORATE W/H - Type: - W
label | 9e96ebb5-5404-5f7d-b43e-1cc5799cf9aa |  | note | INSPECTORATE W/H - Description: - Completed within two months after Paving Wearing Course
label | 2df406c1-4467-5692-93bf-8e47e3e71c80 |  | note | Responsible Person - Renewals Engineer/ Renewals Manager
checkpoint-no-status |  |  | checkpoint | Quality Assurance Close Out
text | 86799ca2-b5b9-5c71-94fe-9245736f4da0 |  | textbox | Quality Assurance Close Out by - Name:
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | ITP - CONOC Operations - Install a Culvert Sock | itp |  |  |  | Yes | ITP - CONOC Operations (General) - Install a Culvert Sock | 710ad0b0-5b23-4781-9c89-60d98e3c18c9
checkpoint-status |  |  | checkpoint | 1 - Prepare Base
label | 2a0fda86-4439-517b-a5c2-8957e78c4f63 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | a4238823-c036-5e99-b296-90006bd813cd |  | note | Accept / Reject Criteria - As per Specification
label | d3425d97-8f9f-5f48-b8ee-3bfacf07b18b |  | note | Frequency Of Inspection Or Test - In-process
label | ac9a5eab-73c0-5913-9a45-ae289fff684b |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP085
label | cc9ec93d-847f-55f8-bd26-d1a99e1c5e4c |  | note | Records Required - NO
label | bf8361bc-c7a1-55d8-b1f3-46ccbd587091 |  | note | ENGINEER - R
label | 2f3f3f46-9a11-50c9-9190-b5575907ea41 |  | note | SUPERVISOR - R
label | 3eea7ae6-3c1d-5fff-8d5a-e3dcc37e8419 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Install Sock
label | 01604e4f-38d5-578a-ae3b-38cafbf21c7c |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 4247bdfe-2bd8-51ca-956d-4c3b027c8ace |  | note | Accept / Reject Criteria - As per Specification
label | e49c2b1a-b3d2-5dd3-b89c-e9255e3b67e6 |  | note | Frequency Of Inspection Or Test - In-process
label | 6320d5cf-66bb-5a11-a7f4-bb4b9a80dffc |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP085
label | 0186935e-edf0-5c38-bcde-8d8ec9e13c50 |  | note | Records Required - YES
label | 2adf0173-0677-5add-b24a-89c8825139ea |  | note | ENGINEER - W(10%)
label | a8ed8478-ebc0-51ac-95ab-edfb4000dc07 |  | note | SUPERVISOR - R
label | 50ad85a4-33ee-5579-b03f-a9e33b78602d |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Outlet Control
label | 0a111316-1ca8-5264-a3fb-3988f9a44d35 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 01f80a3d-d16b-5092-9aa6-c9df0b66ee0a |  | note | Accept / Reject Criteria - As per Specification
label | aacbf15c-7b32-5b87-9d9a-6d39b5cd4400 |  | note | Frequency Of Inspection Or Test - In-process
label | 7b73d473-7218-5025-bd30-d3b79439f7e5 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP085
label | a7f85b94-6f32-540d-b583-e0bc337964e4 |  | note | Records Required - NO
label | 9dd6c184-7d37-5a8f-b7ad-3d4cb237c345 |  | note | ENGINEER - W(10%)
label | 97690689-3843-5782-86f2-020a8bf9a214 |  | note | SUPERVISOR - R
label | 0ba0035f-da45-543c-8931-db5a9e78c045 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Test and Check
label | b347f396-8cfb-564e-8f7c-7f778901bae9 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | c10cd887-e019-5710-82d2-0956f6961984 |  | note | Accept / Reject Criteria - As per Specification
label | 8414f8b0-d295-54ac-afef-08263253b226 |  | note | Frequency Of Inspection Or Test - In-process
label | e766f985-9562-59a2-8b53-42924402f62c |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP085
label | 9e55f014-cad2-5268-9ae2-c5e17494cb26 |  | note | Records Required - YES
label | 2840f996-471c-536a-8e6a-fa87b795dd75 |  | note | ENGINEER - W(10%)
label | 173da373-db09-57b2-860a-3b1b2fbc43b0 |  | note | SUPERVISOR - R
label | dffa67d5-513d-51bd-8d59-5168126c998f |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations - Emergency Works: Clearance of a Small Tree | itp |  |  |  | Yes | ITP - CONOC Operations (General) - Emergency Works: Clearance of a Small Tree | 71d5856f-5f7d-48e3-abf9-c98c0824a9de
checkpoint-status |  |  | checkpoint | 1 - Prepare
label | cf3fe523-bfd9-5a6d-8b4e-a6790b18e811 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 7a33793f-4977-5fc9-afe4-f24f3abe1c87 |  | note | Accept / Reject Criteria - As per Specification
label | 4aeaa5d4-a985-5f19-9fdb-84091c3c0979 |  | note | Frequency Of Inspection Or Test - In-process
label | 83a953ba-b7b1-514e-99c2-70ee9c7a9678 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP103
label | d3da3198-66d2-58b4-82da-8e5995392b87 |  | note | Records Required - NO
label | fa2991eb-2ec8-5433-9cce-7a4aa09b4ec3 |  | note | ENGINEER - R
label | f2efadd5-f9e3-54a6-bfc6-a01b0da33283 |  | note | SUPERVISOR - R
label | 1b9069d0-109e-5dc3-b241-064aef003003 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Co-ordinated Incident Management (CIMMS)
label | 43a19113-d38f-5af2-8085-0b0b97791ce6 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | ca87aa32-038b-5eeb-b957-14a28c9c2650 |  | note | Accept / Reject Criteria - As per Specification
label | 59140bd3-d722-58ac-93b0-b148ba2b4359 |  | note | Frequency Of Inspection Or Test - In-process
label | 9478d4ca-89c0-587a-b9fe-5b37cb0afec6 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP103
label | 3b89e51d-c813-5703-984d-57c349a3c396 |  | note | Records Required - NO
label | a7759334-543d-5fc1-9bf3-51a2a8f2c4c2 |  | note | ENGINEER - R
label | 8731c302-f4e0-5a0d-9be8-81f19c5a4242 |  | note | SUPERVISOR - R
label | 157a8b97-db42-595c-8428-6f5243fa2387 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Planing
label | 9106c793-6ad6-506e-a4fb-32ea5143862d |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 7e6bc71d-c292-582f-89c4-b725954a76ee |  | note | Accept / Reject Criteria - As per Specification
label | 977f2e8b-ef03-5606-a90a-aa064b060d77 |  | note | Frequency Of Inspection Or Test - In-process
label | 416cbe55-706e-547a-b394-f2a1c77a462a |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP103
label | 0caa02b4-31d4-5abc-9942-a347cb428997 |  | note | Records Required - NO
label | 18a53021-5d0e-5f4f-926d-f6be294f64e9 |  | note | ENGINEER - W(10%)
label | e22adf1f-fe76-5e3e-8bf8-dc77006083c1 |  | note | SUPERVISOR - R
label | 92cea10a-5b4c-56ee-b205-bf06c0729cc3 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Removal Operations
label | 48a87d74-f1a1-5a0d-9d18-6ad8960d811e |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | e4abfe25-a72f-5438-9c5b-24de45fca2fa |  | note | Accept / Reject Criteria - As per Specification
label | b767d47f-053d-5007-8f1c-6ba60e53f503 |  | note | Frequency Of Inspection Or Test - In-process
label | 00d15af1-4cba-59e4-8020-8aeda9de9677 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP103
label | 63d8b01b-ea76-52fc-ba50-62ea1d817095 |  | note | Records Required - NO
label | 4461c67a-c0c7-56a6-ba9a-5f275eff1a95 |  | note | ENGINEER - W(10%)
label | f0768eb8-1e52-511c-9e00-42c887e77e5c |  | note | SUPERVISOR - R
label | b23434e9-37a0-5db9-8d39-e753f9e8268f |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Test and Check
label | cfc035b1-9d19-53a4-92bf-575ffb25c927 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 275b1e90-7172-59ed-8292-5e6c14343371 |  | note | Accept / Reject Criteria - As per Specification
label | 7e60fbae-8d4d-56d3-852e-825cc0b62141 |  | note | Frequency Of Inspection Or Test - In-process
label | fa2e4c46-08fc-5a66-b781-774de39a77ff |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP103
label | 8f30998c-e1fc-5310-86a4-56c577815a34 |  | note | Records Required - YES
label | 8b309d21-b1c6-5a02-b082-2a915e4501aa |  | note | ENGINEER - W(10%)
label | 9d5d6b16-19f8-5b0b-b0f9-718741b6d477 |  | note | SUPERVISOR - R
label | 5bd6f0eb-2d2c-524e-babb-eb405fdd215d |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations (Heavy and Light Maintenance) - Crack Seal Repairs (5-15mm) Reservoir and Overband Methods | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy and Light Maintenance) - Crack Seal Repairs (5-15mm) Reservoir and Overband Methods | 72243e6d-dddf-4308-8b15-0918218b2cb1
checkpoint-status |  |  | checkpoint | 1 - Materail
label | 84bb2882-7903-59d5-a4ee-577eb068d096 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 8a82cee7-b951-57d7-ab87-86a4e726261d |  | note | Accept / Reject Criteria - As per specification
label | 8c3965dd-17b0-5b43-962a-1c564da24808 |  | note | Frequency Of Inspection Or Test - In-process
label | 4231e0ad-2b5e-5b0b-8446-6de2d0215cd1 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP044
label | cb344bd5-5d34-5eee-ae0b-0d3fcd7e19e0 |  | note | Records Required - NO
label | 5bb66660-31da-5476-a0b6-ac4063121e27 |  | note | DOWNER ENGINEER - R
label | 250f3f6c-ec4b-5aa0-97e0-0b9905c0dcca |  | note | SUPERVISOR - R
label | db0bb1cb-9634-5a36-bd25-0345a8c9e617 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Weather
label | 17f766bf-8710-50fc-8a64-9bce656930f5 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | e55811ea-eef4-5d29-bd85-bdec3efdd376 |  | note | Accept / Reject Criteria - As per specification
label | cb50c860-294b-515d-9428-a77a42a722ab |  | note | Frequency Of Inspection Or Test - In-process
label | e97b6644-bca6-5399-b806-e8b9b85b346d |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP044
label | 99f520d8-f9e1-5b2d-a98d-c3502ac0bb57 |  | note | Records Required - NO
label | 6e0025eb-1878-5e18-a6c6-8c8e0e6bfad4 |  | note | DOWNER ENGINEER - R
label | 5ddff92e-5fbc-51ec-a882-f5b0aa83242a |  | note | SUPERVISOR - R
label | a0d747e8-573a-5768-aee1-bd5cea07ba97 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Preparation
label | ee3ee221-375a-5907-999b-17c9955d1b88 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | ec9748e7-6bb6-5b99-a331-f16bfcd094db |  | note | Accept / Reject Criteria - As per specification
label | 49ec7f64-9c8a-564b-a929-dcd77c5ea84e |  | note | Frequency Of Inspection Or Test - In-process
label | f85c349d-a8bf-5d0c-824d-83b11088f9dc |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP044
label | fc231c28-e5f6-53dc-af17-f4aad21b5e41 |  | note | Records Required - NO
label | 444c5f84-6883-585b-af41-4b8799e5aea7 |  | note | DOWNER ENGINEER - W(10%)
label | a62af881-387c-58e7-a7d9-b473f119f3b1 |  | note | SUPERVISOR - R
label | a200932d-3414-54ca-ae58-9cbb3f34c4d8 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Cleaning and Drying
label | 8e036764-eab4-5210-b48c-88e56f285735 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | bdc53d6c-a2bd-5ba6-8d09-73f5c0d72c71 |  | note | Accept / Reject Criteria - As per specification
label | a67ba811-b8ce-5a8c-b9da-baecf98495a4 |  | note | Frequency Of Inspection Or Test - In-process
label | 1eecb9d5-f9d2-5085-8355-46b5a8dd8c3a |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP044
label | f3f73848-8f27-53c3-a7e5-54aa41da8e8c |  | note | Records Required - NO
label | de32345b-3160-552e-b31f-79202633bf6e |  | note | DOWNER ENGINEER - W(10%)
label | 4e7612e1-26f5-5620-a2ba-aeca76a00b60 |  | note | SUPERVISOR - R
label | 01bead47-abbf-5ce9-850e-79d9ef8021a5 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Application of Sealer/Filler
label | 0830519d-e5a2-5bd9-b165-594509f6de47 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 18d42fb8-e1c7-58c6-a592-d94b41182274 |  | note | Accept / Reject Criteria - As per specification
label | 8f1c0459-d5e9-5819-b3bd-0d79e8b71ea0 |  | note | Frequency Of Inspection Or Test - In-process
label | 68242d11-7d1f-5071-8062-13e6b898b0fb |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP044
label | 71db2da0-de52-592e-b440-1e0df8911583 |  | note | Records Required - NO
label | 7619a155-8e15-53eb-b097-9cb9b2bbf535 |  | note | DOWNER ENGINEER - W(10%)
label | 50d5a526-cefa-54ec-aa10-f2bc5286d3f1 |  | note | SUPERVISOR - R
label | a14612cf-c1cf-597e-898b-809ef91365c0 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Finishing
label | e1799d37-ee67-574a-a2f1-d5df00390072 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 800ca242-2e9a-515a-a718-bd5c5e569061 |  | note | Accept / Reject Criteria - As per specification
label | b733e5e3-44ce-55a7-8e31-20f930857990 |  | note | Frequency Of Inspection Or Test - In-process
label | 9d5fb60e-1f78-565d-8266-9cd8cd99a00f |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP044
label | adc3a083-ead0-5a35-8888-7017755fa288 |  | note | Records Required - NO
label | ea920033-3258-55a6-8f18-f1a5e7faabf2 |  | note | DOWNER ENGINEER - W(10%)
label | b78cea14-3806-51f8-bf04-026b9d9e75eb |  | note | SUPERVISOR - R
label | e96caed3-e586-5426-ada9-5b27c3a9a858 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Test and Check
label | 2d9d6389-fa91-58fd-aab2-3c8f736129a9 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 240de039-f427-5e4d-ace2-042928dae9ff |  | note | Accept / Reject Criteria - As per specification
label | 5e53ee04-c7b7-5d6d-8eae-425acfe873fa |  | note | Frequency Of Inspection Or Test - In-process
label | 0bd052d9-3f60-5e98-9fcf-4175dadd5320 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP044
label | 2fdff1b1-5ab1-5cf4-b547-4741cb018f72 |  | note | Records Required - NO
label | 8a1f6c0b-66e3-5cac-83a5-a1ca988277c3 |  | note | DOWNER ENGINEER - W(10%)
label | 1c245174-9553-53ff-93f8-315f7c70fcfe |  | note | SUPERVISOR - R
label | b132533f-6044-5b0f-a606-ff7727abe7b1 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations - Line a Channel With Rock Riprap | itp |  |  |  | Yes | ITP - CONOC Operations (General) - Line a Channel With Rock Riprap | 72323a1f-096e-47ec-922d-112329e01aee
checkpoint-status |  |  | checkpoint | 1 - Prepare the Site
label | 56a67886-d9b8-57ff-bb4b-cfe619845ab2 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 0c8d2c07-4844-52a4-90df-2fb5d0341f51 |  | note | Accept / Reject Criteria - As per specification
label | 45d52f2f-30f5-55d6-83c8-38c2a2640596 |  | note | Frequency Of Inspection Or Test - In-process
label | 6c884259-4128-589c-b74e-36ef3665e4cb |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP090
label | 22b3d0da-377b-5034-b758-17a6d6c274a5 |  | note | Records Required - NO
label | ec7be43a-12bb-5155-8b35-968f11559016 |  | note | ENGINEER - R
label | 3eb66c94-0e15-5cbc-9d95-5171313095e2 |  | note | SUPERVISOR - R
label | d38d0e48-853c-5318-a046-e2733fcc614b |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Setting Out
label | 257c8fb4-99f0-5647-aa86-b22c2a054c0f |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | ab2d45d1-ab54-5aed-bbb5-d5281992510e |  | note | Accept / Reject Criteria - As per specification
label | 79f9c92d-7689-52ee-a7ba-469c386bc018 |  | note | Frequency Of Inspection Or Test - In-process
label | e34f22e4-f1f7-5419-ac6f-47361d4020a4 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP090
label | 477f68b3-fed1-5799-b978-7205969066c0 |  | note | Records Required - NO
label | c5fd7f89-e5f6-5e67-8371-d9aeba92929f |  | note | ENGINEER - W(10%)
label | c3a81389-7da5-5103-a450-629bbb68e720 |  | note | SUPERVISOR - R
label | 3e46dfc0-a6ee-5eee-b41f-950c62554170 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Prepare Base
label | 7f7b64dd-b7da-5c7a-9b0c-272f30d85fda |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | f2e13b4e-d2f9-5f8d-a05e-956b30d001be |  | note | Accept / Reject Criteria - As per specification
label | 49431e70-804c-5c7d-a7eb-319a09bfb2be |  | note | Frequency Of Inspection Or Test - In-process
label | ac4fb6de-b781-5589-941b-95aa35aa6c92 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP090
label | 41423d9b-ff32-52ec-8203-67ee064681e2 |  | note | Records Required - NO
label | 48892ebe-bb21-5ac3-af5a-8afb6841d32d |  | note | ENGINEER - W(10%)
label | 2b430726-8695-5ce6-bbf7-6dc04d540778 |  | note | SUPERVISOR - R
label | 80d04ec6-199e-57ad-83bb-7f0587216406 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Place Rock
label | b0258578-3847-51a7-8027-6d8059518010 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 61e35e09-ce32-52b2-97c9-f14e03a28ef7 |  | note | Accept / Reject Criteria - As per specification
label | d4d8b2b5-c939-5c0b-b734-30f6b85c54bd |  | note | Frequency Of Inspection Or Test - In-process
label | bcd8bd52-57be-55b3-8c74-d1f9d80d9cca |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP090
label | 724dacec-fc26-5bfc-bfcd-907a4a4a0b5d |  | note | Records Required - NO
label | 7cd27686-be28-5b0f-a2f6-c7a0aa835e74 |  | note | ENGINEER - W(10%)
label | 88234431-bbd9-5884-9419-b9b3b7e30461 |  | note | SUPERVISOR - R
label | f585687d-e726-58c1-8f37-7bc5c96a8f28 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Test and Check
label | 5895f796-3aae-57fc-a2b7-f76a489f4bc3 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 1fb96b63-e884-5ee7-bdd5-0ba586a308b5 |  | note | Accept / Reject Criteria - As per specification
label | fd24a23a-a1e5-5cea-8fd3-22527fae4fba |  | note | Frequency Of Inspection Or Test - In-process
label | f757f436-7b7f-5ea2-afec-88eb59539f1a |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP090
label | c212e093-4210-59ab-a6ee-0d49f7dede07 |  | note | Records Required - YES
label | 41f6f8d9-9807-50ed-832d-d15cc6e087f1 |  | note | ENGINEER - W(10%)
label | 94ca7ee3-782b-5270-bc5f-ab2b6dca5b1c |  | note | SUPERVISOR - R
label | e5675cb3-002c-56bf-81ba-80f2b98f217f |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - Industrial Park - Thin Asphalt Paving |  |  |  |  | Yes | ITP - Industrial Park - Thin Asphalt Paving | 732318a3-d1a9-48cc-89c8-3c9814fbb3b4
checkpoint-group |  |  | section | 1 - Preliminary and General
checkpoint-status |  |  | checkpoint | 1.1 - Construction Programme Completion
label | 46bf026b-98ca-58d5-a2a7-d16ebfa90a42 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 47286d4b-77cc-566d-ad10-ecdca5f8777e |  | note | METHODS OR REFERENCE - Best Practice Contract Specific MMP
label | 23ebf7a6-bcb7-583c-b980-f74002c32d8d |  | note | FREQ. - Before work commences
label | ccfdb82c-bb7f-551e-b796-a62e0ec271d6 |  | note | ACCEPTANCE CRITERIA - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date.
label | 739d8b3d-7eaa-56d2-801c-d7edef245ce1 |  | note | INSPECTORATE W/H - Type: - W
label | af451566-90ab-530a-bccb-9d4288a9a23f |  | note | Responsible Person - Renewals Manager
checkpoint-status |  |  | checkpoint | 1.2 - Approved RQP
label | c6ebeb86-d873-5dbc-982c-19164db5b1f7 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 67702548-91a2-545b-a223-516f45336d16 |  | note | METHODS OR REFERENCE - Contract Specification
label | c0509341-39e4-59a5-afe6-39c79150ab57 |  | note | FREQ. - Before work commences
label | fd4eff23-49e7-55ad-b07f-c8a5c63c7878 |  | note | ACCEPTANCE CRITERIA - Principal Acceptance according to guidelines in appendix 6.3
label | 42892ac4-3780-58e7-9c55-bb69ee8eeaeb |  | note | INSPECTORATE W/H - Type: - H
label | 5cdcf126-268d-5406-add0-e7b87d6073d6 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. NZTA to approve
label | 19a9ec76-c006-5728-a408-b9ec46b983b3 |  | note | Responsible Person - Renewals Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Traffic Management - TMP
label | c084d39f-b090-5dd6-b921-a22780c0fe2a |  | note | VERIFICATION ACTIVITY - Visual check
label | 644dfcb5-dc50-5217-b21b-87245163227c |  | note | METHODS OR REFERENCE - CoPTTM
label | e6a49322-48af-56d9-9bd6-e314ee511902 |  | note | FREQ. - Before traffic management set up
label | 18e1f8c6-66b4-5ea4-b43b-1957ab193996 |  | note | ACCEPTANCE CRITERIA - TMP checked and approved Plans approved Current EED (if applicable)
label | 7a462240-9ec4-50fa-bf0b-4b8528ffe7b2 |  | note | INSPECTORATE W/H - Type: - H
label | bf1b555d-8945-5d3d-bffe-20cfa2c8b139 |  | note | INSPECTORATE W/H - Description: - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | 2561fa79-f7dc-5610-a87b-f673ba7c2567 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Mix Design Verification for all mixes Check Laydown Trials are complete and compliant
label | 56b0e8f8-e866-5b70-afd1-261dddc434ce |  | note | VERIFICATION ACTIVITY - Confirmation
label | 8692479c-0377-5bfe-8814-7450ded9d43a |  | note | METHODS OR REFERENCE - NZTA M/10, P/11, P23
label | c8018e21-a1a3-53a0-83e6-85f65d1a221c |  | note | FREQ. - Before planning commences
label | 4e248259-6b9a-50ee-ba11-505fad62db47 |  | note | ACCEPTANCE CRITERIA - Mix Design compliant, current and relevant. Batching plant production capability is confirmed
label | 81cb5f33-20cd-5fee-a1cc-2cabf38ee28a |  | note | INSPECTORATE W/H - Type: - H
label | 260fc59a-a8d5-539d-9f60-dc5433c23082 |  | note | INSPECTORATE W/H - Description: - Hold point - No planning of on-site works shall commenced until the mix design is verified.
label | f23dd254-23db-51bf-80a8-af2050579b26 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Notification of intention to start work
label | 3be375d8-9609-5667-a5e6-03707499ffff |  | note | VERIFICATION ACTIVITY - Notification
label | 81faf092-157b-5149-8337-05a82b288c75 |  | note | FREQ. - Before work commences
label | 4ef8fa33-5505-5af9-867c-c451324a039e |  | note | ACCEPTANCE CRITERIA - Letter drop to local residents. Greater consultation where required
label | 0f544758-adb7-50cc-80da-fbfda092a364 |  | note | INSPECTORATE W/H - Type: - H
label | a640db81-bf24-5b0d-9db4-73ea61d6d3b0 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | 65cf6d21-e3ef-5aaf-98de-ee2d1fca2a2d |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Works Extents
label | 8f9cd899-cb97-585c-9d59-443da29e8ae3 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 51afb926-3da5-5c75-b023-7a13985500fa |  | note | METHODS OR REFERENCE - Site Visit
label | 04185f6d-584f-58d6-97f5-ba7a2818b8ec |  | note | FREQ. - Before work commences
label | 4d014f97-2d71-58fb-a2fe-3c38d096919b |  | note | ACCEPTANCE CRITERIA - Renewals Manager and/or Client to agree extents of project
label | 1b519865-1b11-5557-9a78-c42c22d643dc |  | note | INSPECTORATE W/H - Type: - H
label | 9387d9d7-ac6d-5c3f-a182-7f3a77d97ab9 |  | note | INSPECTORATE W/H - Description: - Hold point - Walk over site with Renewals Engineer and/or Renewals Manager and/or NZTA
label | fa11fc47-7317-5844-bfb0-490313b3c994 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - Pavement Marking Records
label | 216908c9-ff1a-53b1-9be6-276f3f978883 |  | note | VERIFICATION ACTIVITY - Measurment Data
label | 63035e46-8202-5926-b728-a058aa0b5868 |  | note | METHODS OR REFERENCE - Site Measure or Video Viewer
label | cadcaeb6-a1b2-56d3-84e2-ee21ca356a9c |  | note | FREQ. - Before work commences
label | 32d749a7-017d-5372-81d7-7b70759d32be |  | note | ACCEPTANCE CRITERIA - Measure existing markings to aid reinstatement
label | 0b6352cd-3b1d-5043-b969-e1f635d892ba |  | note | INSPECTORATE W/H - Type: - H
label | 26b14326-c8d9-5eda-953e-ec1dae9e0d21 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | 2021789e-1c86-5a1d-a6f4-95685e75b7de |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Milling and Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | 4e0ba5d0-a00b-5e4b-88ce-793814164de1 |  | note | VERIFICATION ACTIVITY - Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth)
label | 3d046e23-aa00-548a-ad83-6fa5c93febf4 |  | note | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | 1f9c4318-a8fc-5b38-8f36-7a4d8ec0896c |  | note | FREQ. - Before work commences
label | 9364f972-c2e2-5ce1-b32b-4cf4086d9234 |  | note | ACCEPTANCE CRITERIA - Zero service strikes
label | b9f80056-6fda-561c-bbfc-b4ef444786b5 |  | note | INSPECTORATE W/H - Type: - H
label | ed847386-c159-562a-9e13-ebab0f1155ed |  | note | INSPECTORATE W/H - Description: - Hold point - No excavation/milling is to be commenced until services are located and accounted for
label | 3cbae975-ffdc-58f4-b85d-46e99c9e5c31 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Stormwater Management
label | 9f6eb4ec-cb95-57e4-8581-4d3fa0a1e10b |  | note | VERIFICATION ACTIVITY - Visual check
label | 721df9ba-2358-5c77-8ec4-2db5cb57797c |  | note | METHODS OR REFERENCE - On Site
label | 99c46b27-1849-58a1-8c3c-45931306d3ad |  | note | FREQ. - Before work commences
label | dfa437be-a4b4-5fa3-9a29-e21b6e0494bf |  | note | ACCEPTANCE CRITERIA - Mudtanks bunded or filtered to prevent mix from dropping in or runoff entering
label | 59f84813-c92a-521a-9228-535ca8c87b1f |  | note | INSPECTORATE W/H - Type: - H
label | 87e20ed1-acb6-5a32-8696-67a295083c32 |  | note | INSPECTORATE W/H - Description: - Hold point - No work to be commenced until protections in place
label | 0d5a303e-ce98-58d6-b773-6002aba256be |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Traffic Management - Setup
label | 8e96cf0a-9e45-57b2-bf74-d8dbebf39821 |  | note | VERIFICATION ACTIVITY - Visual check
label | b4ad4e55-840c-5618-a661-a68d9201dad9 |  | note | METHODS OR REFERENCE - Traffic Management Plan
label | c25cc512-fd01-5b22-8dae-f027910ea7d6 |  | note | FREQ. - Before work commences each day
label | 117d06b1-68cf-5ce5-bedf-cbf868d9e49b |  | note | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | 1b91295b-cfff-591a-b185-14bffb9d58b9 |  | note | INSPECTORATE W/H - Type: - H
label | 30aa5f4f-4031-5e9a-bada-f4333b87bef0 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | f0b2cb61-5d73-58b2-baa0-196fad0604bb |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Milling Depths
label | 193661f1-3eb3-5f6c-b482-72adb9ea6fbe |  | note | VERIFICATION ACTIVITY - Measurement
label | 499fa67e-912f-571d-8f91-d7a3c6213a7d |  | note | METHODS OR REFERENCE - On Site
label | b79202ad-bd5e-5e55-beef-8dfdf27e571d |  | note | FREQ. - Measure each side of milling machine cut
label | b423000c-8cd4-5797-a664-19edc0e4e35b |  | note | ACCEPTANCE CRITERIA - Every 10m. Depth matches target
label | 94528d6f-de8f-5ffe-8d40-59ee2da6e614 |  | note | INSPECTORATE W/H - Type: - H
label | f413c023-1347-599f-8e01-f7af29df7cc8 |  | note | Responsible Person - Site Foreperson / QA
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Service Covers Preparation
label | eb463b17-5c6a-5ac4-a5e0-d340452b7b66 |  | note | VERIFICATION ACTIVITY - Visual
label | d61c2f69-ce35-58a3-a0b2-8dbd3ecae204 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 45ca89fc-2a39-5696-a71e-728831c08720 |  | note | FREQ. - All Covers
label | 50f7a781-5ff3-5879-92c4-d90bb927eb48 |  | note | ACCEPTANCE CRITERIA - Hand excavation around ironwork and adjustment to desired level (if required)
label | 839dfeb5-c765-5fab-be35-ac9637c493a3 |  | note | INSPECTORATE W/H - Type: - H
label | f6e3ac8e-58aa-5136-a94e-4099adaccf43 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Additional Surfacing Preparation
label | 3ceed80b-89b9-5d63-befe-22117bdcd093 |  | note | Side Roads; Accesses; Driveways; Dish Channels; High Shoulders
label | 5696aeea-c0d2-535b-9b08-53f86a3e4422 |  | note | VERIFICATION ACTIVITY - Visual Check
label | 7abb94ba-8fc3-50a1-8801-fe16e43f10b8 |  | note | METHODS OR REFERENCE - Per Design
label | e253b4c2-59f1-5ae3-891c-69d260399b34 |  | note | FREQ. - Before Membraning and Paving
label | 4ad598ca-724a-5b83-ada2-c42925eb586b |  | note | ACCEPTANCE CRITERIA - Have all areas of additional surfacing on the design been prepared, membraned and marked for paving?
label | ab424963-d0c7-58cd-ba11-5ca5637d0088 |  | note | INSPECTORATE W/H - Type: - H
label | 17e8fe72-57e5-5163-98d5-2815fa64e720 |  | note | INSPECTORATE W/H - Description: - Hold Point – All areas planned for AC are prepared ready for surfacing layer
label | 514781d0-ed01-5c8e-9091-bd2bdb412c75 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Over-Milling
label | 29e38bda-1a92-5194-9b31-c64daac33956 |  | note | VERIFICATION ACTIVITY - Measurement
label | 126517c4-d119-5c25-806e-2d78130d20f3 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 4600e851-d63f-5a60-aa57-0afedb935aa3 |  | note | FREQ. - Prior to pre-level
label | 22e6aadf-a647-538a-bfb4-96c0f9ec911d |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree need and extent of over-milling and infill.
label | fc2c395c-a92b-54b4-8a83-122696465255 |  | note | INSPECTORATE W/H - Type: - H
label | d829a8ba-6608-5759-8f45-799fa653da03 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Pre-Level
label | 2ed0ed92-8048-5a71-9e18-00b867e00cfc |  | note | VERIFICATION ACTIVITY - Measurement
label | be6101ee-81a4-55aa-912a-385ac9143640 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | e91ebb50-602b-5709-be10-6aa6069f6433 |  | note | FREQ. - Prior to surfacing
label | 1dcfc055-e790-538c-ac44-cc1fc48cbcf7 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree pre-level extents
label | cabdec27-4276-5d34-9c68-54967f895e29 |  | note | INSPECTORATE W/H - Type: - H
label | efc533dd-e2c5-5f32-a95b-131ba1f4abef |  | note | INSPECTORATE W/H - Description: - Hold point - Inspection and agreement by NZTA
label | 1f61723d-a8cc-527b-b37e-0dbcca153a04 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.9 - Membrane Sealing
label | 62772c88-be5a-561b-893a-93b371b34b86 |  | note | VERIFICATION ACTIVITY - Visual
label | 50356f70-fd0d-53af-947e-a51a0be3de73 |  | note | METHODS OR REFERENCE - On Site
label | 3350c130-07c8-5133-8900-a8dda7eb80ea |  | note | FREQ. - Prior to surfacing
label | 24dab181-9dd4-53d2-a4d9-afccd42cc3dd |  | note | ACCEPTANCE CRITERIA - Membrane seal meets design and extent. Sealing Docket record kept
label | 6088dab0-8920-561e-80c6-f34595c27c03 |  | note | INSPECTORATE W/H - Type: - H
label | 3248d0f5-8945-5293-a2d7-8ed6a9e26e2b |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Paving Structural
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | 515e2955-f69f-5a31-9a4c-a0351ddb7fa9 |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | ea97f23d-bfd7-58f5-ae37-4f428cfcc2b5 |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | 56deabb5-44df-50eb-97f1-bf6aa636efe3 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | e1600756-86b1-56b3-8dc0-e1bde63934a0 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 6dbde415-a3fe-5699-8efc-ad721faeaa49 |  | note | INSPECTORATE W/H - Type: - W
label | 9f02590d-76aa-5757-8b67-289ca40f63f5 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | c3555d34-557b-5b43-872e-de40138e9db2 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | 7a7d695b-00dc-511d-a952-9327280375d5 |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | e6253347-467b-51d0-b672-6d1d966fa30e |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | 2e62a5b7-fd7a-5f76-a825-f5bdc9d8cb64 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 75b7273b-68ff-572a-9d4a-a720202c9ac0 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | cdc31c98-ad2b-5e0a-b95b-c5a89da2342b |  | note | INSPECTORATE W/H - Type: - W
label | e7106bf6-4e9d-5520-87a8-648202219c86 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 7816f35e-2c57-526c-bf29-a6ebf8fc32e2 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | 152872c2-d4f4-5b45-b461-01522db36849 |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | 00ee7f74-163c-5fe6-ae78-2451341f3e42 |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | 48e44171-2abe-5465-bdb4-3561a18d4158 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 21dabeb0-8eeb-538e-9431-a10d2386740b |  | note | INSPECTORATE W/H - Type: - W
label | 380d2cfd-ebeb-5280-bf5a-169e69cb7108 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | e60d9398-b7c8-5b90-8701-bfed00217c93 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | 69aa7002-9e23-5955-9ff2-51e019eae626 |  | note | VERIFICATION ACTIVITY - Visual
label | 52b827bd-ab62-5ecd-9d0a-7a8c1068e93a |  | note | METHODS OR REFERENCE - NZTA M/10
label | 9b38c577-3f55-52de-83be-b6124bad31fc |  | note | FREQ. - Prior to Shift
label | 8fc0f443-54e3-5a1c-b12b-859627568a7a |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | ed76c8f7-84ba-5937-97bc-b9247194fc98 |  | note | INSPECTORATE W/H - Type: - W
label | a785e60c-8d32-5871-96da-a35d9357ce54 |  | note | INSPECTORATE W/H - Description: - Paving Plan and Crew Briefing Plan completed prior
label | 55fbe24a-5df4-5f83-891e-6c5affacac29 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | 3f23b1ae-a5c4-5842-a366-50e5a127b5a9 |  | note | VERIFICATION ACTIVITY - Visual
label | 4a966f9d-0b40-5b51-8074-858297a345b1 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 1a39fa07-38c4-5f85-b371-99d3f882a07f |  | note | FREQ. - Prior to Shift
label | 235aeb9a-67f5-5c48-b0fa-0a020fa93c82 |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | f2ae9bc1-eb8c-5228-9360-82917920be0d |  | note | INSPECTORATE W/H - Type: - W
label | 3f8263bd-008e-5975-bab5-ab61fb376160 |  | note | Responsible Person - Paving Supervisor / QA Engineer
checkpoint-status |  |  | checkpoint | 3.4 - Mix Inconsistency and Deficiency
label | fce25181-acc0-5d0a-8686-3f4dec2c4f8d |  | note | VERIFICATION ACTIVITY - Visual
label | 893f8615-2d96-5293-b76a-de6e38dd16dc |  | note | METHODS OR REFERENCE - NZTA M/10
label | 91829cac-c604-5f74-88b8-3b3ed9a3c02d |  | note | FREQ. - Continuous
label | 320fef1f-7520-57c5-a177-3015a793bdc7 |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | d58a6169-c66d-581c-a658-17b63b279dfc |  | note | INSPECTORATE W/H - Type: - H
label | 02f6cb05-558e-5262-9de5-29071e92d8ad |  | note | Responsible Person - Site Foreperson / QA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Load Locate
label | f0b13672-a749-5efb-bf5c-c9cb66e1de16 |  | note | VERIFICATION ACTIVITY - Measurement
label | 86d6d3d4-34ec-5ff1-a2e3-ee105fdc4ec0 |  | note | FREQ. - Every Load
label | 57800ba5-f75d-5798-8659-3d31940de16e |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
label | c0afb939-1a82-50f4-91c2-fafb2c6c0ea7 |  | note | INSPECTORATE W/H - Type: - W
label | c9237e15-7a61-5ec7-a049-5c4b5477bd8b |  | note | INSPECTORATE W/H - Description: - Per standard practice
label | 44de86c6-1145-5cce-b342-80dbc61c6204 |  | note | Responsible Person - Quality Assurance Engineer
checkpoint-status |  |  | checkpoint | 3.6 - Laying Temperature
label | 21d98bd2-400e-5b31-90a7-045469b8636e |  | note | VERIFICATION ACTIVITY - Confirmation
label | ea80fe5c-588e-5c25-aff8-1e2d867fb739 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 7a648eea-e913-549e-9185-a2a07700d433 |  | note | FREQ. - Every Load
label | 4c5d8722-13cb-5b50-903a-7225e360a5f5 |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | be65c351-e85f-5b31-a789-130db17c6a9e |  | note | INSPECTORATE W/H - Type: - H
label | 7ac71ff6-7093-5f86-bda7-a0b37a59f632 |  | note | INSPECTORATE W/H - Description: - Hold point - Reject mix for non-compliant temperatures.
label | 39410fc2-9146-501f-9b15-39e3c052d830 |  | note | Responsible Person - Quality Assurance Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Compaction
label | 1a4b9945-fc35-58a5-b46a-14ca333c3138 |  | note | VERIFICATION ACTIVITY - NDM Testing
label | 94766d0f-c881-512f-8535-e637452a7a24 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 866c9ee1-e710-5f96-9509-f044b169f2dc |  | note | FREQ. - Minimum: 1 Test per 300m² within Mat. 1 Test per 100m of joint.
label | 5bf10f42-cd80-5e7c-b7bb-c64e2b0eca28 |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | 411ce2ec-5536-51ff-a70c-65016c6d6b6d |  | note | INSPECTORATE W/H - Type: - H
label | 299f96e3-aa4e-5662-9574-292f84e27fab |  | note | INSPECTORATE W/H - Description: - Hold Point - No Wearing course paved until any non-compliance is sorted
label | 5222c364-b025-538b-8abf-1d3d268330fa |  | note | Responsible Person - Quality Assurance Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Roughness
label | ee16eb28-06e8-5b92-85b6-c366e9019e61 |  | note | VERIFICATION ACTIVITY - NASSRA Testing
label | ed28aa7b-efd4-5726-9b1d-ece263efb0da |  | note | METHODS OR REFERENCE - Contract Specification
label | 7dd6950e-4bd2-5109-9ab3-850fe081aa5e |  | note | FREQ. - post construction
label | a2a93251-5b57-5b7e-9852-d0568f0ae195 |  | note | ACCEPTANCE CRITERIA - NASSRA rolling meter average under 60, max of 70
label | 15de0975-f61a-56bf-9933-04fc1348643a |  | note | INSPECTORATE W/H - Type: - H
label | f6137182-a605-5c88-a04e-4af4ac42b772 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Paving Wearing Course
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | 97ba75cf-6006-5de1-8b85-f94427fd2dae |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | b5ed0a91-95e8-5e78-8454-6269f4ff1820 |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | 7c3884a5-3b67-595f-b592-0495a2501c1a |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | e3f41220-941b-518b-a6b1-4a2ef98fdd05 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | e35c4365-f914-53f9-a0ff-33ceb9b6f302 |  | note | INSPECTORATE W/H - Type: - W
label | 35dcba2b-198d-5765-8911-2021decb6ca4 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | eab54fd0-96bb-5f77-8f6e-089ad2f5a87b |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | 0c3a4134-3f1e-555d-8ba4-b6c49242d29d |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | ea135a17-dc6e-5915-b1e4-8d344bbf8d6f |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | 904c915e-8e3d-5bdd-a61e-68325c3d576c |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 9d964ba3-f129-52f6-adf7-ca66fac9a97b |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 777fdd35-1ad4-5ddb-88da-1abc45360e0d |  | note | INSPECTORATE W/H - Type: - W
label | c358d412-ce72-5c8e-9c2c-f20ad2b2fed5 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | a15ab862-022a-5f40-a3c9-0549d646be6e |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | 937630b6-0691-59e8-9f31-1478c5557e1a |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | 25aec74d-c493-5288-8334-047f8ce3b58d |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | 268f7c55-74ec-54a6-9308-9efe0f5bd9d7 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | f6d64d5a-a798-5f29-bc28-290b360da25a |  | note | ACCEPTANCE CRITERIA - Per Mix design
label | 858fa6d3-10ad-5e78-8306-376764be0db9 |  | note | INSPECTORATE W/H - Type: - W
label | 9a4a01eb-b37b-59c3-a561-a5df260d1c4a |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | bd64137b-0342-50eb-963d-0bdee1a8e4e9 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | ab674a87-ad0a-5f2e-8d9d-76858a164cf8 |  | note | VERIFICATION ACTIVITY - Visual
label | a2dbd90b-62fb-506a-ba17-1c86f35d1f8e |  | note | METHODS OR REFERENCE - NZTA M/10
label | ec69c758-779f-5f42-805f-47c2ec9d27d2 |  | note | FREQ. - Prior to Shift
label | 34e241bc-8d63-5890-a2b0-d2c0d95e4654 |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | 6419df0a-2e2b-5a71-92e3-01f8dd2c1edd |  | note | INSPECTORATE W/H - Type: - W
label | 4c573b79-f329-5d44-b6e9-81835b8be118 |  | note | INSPECTORATE W/H - Description: - Paving Plan and Crew Briefing Plan completed prior
label | 3a59acee-30bf-54d8-acc1-a8e560d43445 |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | 56025e30-06e3-5d83-bd65-5e26527bc57e |  | note | VERIFICATION ACTIVITY - Visual
label | 46181801-2d96-5610-bd57-def307e57115 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 03e360b0-4b57-5fd7-92fc-961c6edbfa0b |  | note | FREQ. - Prior to Shift
label | ba916408-1369-5225-9bbf-a946cc0b4791 |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | f27d6446-cc02-5b64-9b79-9e0aa86dcf17 |  | note | INSPECTORATE W/H - Type: - W
label | f07ca882-3dd6-5c69-9930-207735f48f5a |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.4 - Grade 3 Membrane Sealing
label | edda94e5-1039-5ceb-9fb3-8193fc970fd5 |  | note | VERIFICATION ACTIVITY - Visual
label | ffafadda-50c2-578e-b02a-925273d38873 |  | note | METHODS OR REFERENCE - NZTA M/10
label | d1eff4f5-0ec5-56b5-bdd3-f812b9e31d07 |  | note | FREQ. - Prior to Paving
label | 04ffb9ef-ce39-5ea6-99ad-d59748e912f6 |  | note | ACCEPTANCE CRITERIA - Applied 2.0l/m² residual
label | 191ec4ef-ef82-5599-9b8c-937ecab2233e |  | note | INSPECTORATE W/H - Type: - H
label | 53af323b-46ec-56af-8e22-f70c4ae2ed7a |  | note | INSPECTORATE W/H - Description: - Hold Point - No paving until Membrane Done.
label | e01d47de-c618-55c3-8312-af60c14da6fd |  | note | Responsible Person - Paving Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Mix Inconsistency and Deficiency
label | f886a86f-5dcd-56e8-a7ea-c2af2b90816b |  | note | VERIFICATION ACTIVITY - Visual
label | 0f595a31-4ec9-5a13-bca3-e1b77023707b |  | note | METHODS OR REFERENCE - NZTA M/10
label | 8275079b-fc06-54fb-a23b-c20d8e6960c9 |  | note | FREQ. - Continuous
label | a6c67e24-74fd-520c-8116-11fcf8c1e2b1 |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | 50f7d26d-f13a-5271-a50f-2014aa5ae234 |  | note | INSPECTORATE W/H - Type: - H
label | ac4a146e-6e7c-5c38-93ae-14c821e94136 |  | note | Responsible Person - Site Foreperson / QA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Load Locate
label | 3c9ce126-8039-5ee3-b848-c3a3f626dc03 |  | note | VERIFICATION ACTIVITY - Measurement
label | d48583bd-0688-5a13-a455-f1a40d5c0bf6 |  | note | FREQ. - Every Load
label | 426c2845-b4c1-5912-ba68-c7dfd34e9118 |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
label | b410f53d-9bbe-504f-a35f-8697ba2f13d9 |  | note | INSPECTORATE W/H - Type: - W
label | 6d7bf86e-629f-5128-aff8-01c58faf852d |  | note | INSPECTORATE W/H - Description: - Per standard practice
label | dc45d20e-aaab-5553-bf24-cc0abc63c4ab |  | note | Responsible Person - Quality Assurance Technician.
checkpoint-status |  |  | checkpoint | 3.7 - Laying Temperature
label | e9c22110-88d9-5e47-8ba0-44fec4f72d6f |  | note | VERIFICATION ACTIVITY - Confirmation
label | 89b4a6b5-4e63-5ed8-b9f2-3ac2ccf12219 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 12cf92b4-d152-59ac-bc30-d4fb617f3c63 |  | note | FREQ. - Every Load
label | 19b9dbf1-d520-55b1-8b1e-af27d1482183 |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | 28a941a4-028d-517b-840d-7bdd30ad77c2 |  | note | INSPECTORATE W/H - Type: - H
label | 168dab9d-ec41-5d58-9e6f-69c288e20f81 |  | note | INSPECTORATE W/H - Description: - Hold point - Reject mix for non-compliant temperatures.
label | d40637ff-13d2-5606-a586-354d57668fcc |  | note | Responsible Person - Quality Assurance Technician
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Compaction
label | 3cd0de81-368a-59a1-a3c3-d316eccfdeb0 |  | note | VERIFICATION ACTIVITY - PQI Non-Nuclear Gauge/Cores. Or Non Distrctive Method Testing.
label | aceaa957-07e9-5aba-b992-0a968df922a0 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 81550f81-e1c2-5f1b-97e2-36989f72a244 |  | note | FREQ. - Minimum: 1 Test per 300m² within Mat. 1 Test per 100m of joint. Minimum 8 cores on Mat and 3 on Joints as Per M10:2020.
label | 357cbc4b-4cc8-585f-b6d5-f75bc203d04b |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | c1a43495-e80c-5411-8c82-d29ae6bc85a1 |  | note | INSPECTORATE W/H - Type: - W
label | 59593521-b82c-57ce-a23d-e056d6a5189f |  | note | Responsible Person - Quality Assurance Technician
checkpoint-group |  |  | section | 4 - Site Reinstatement / Clearance
checkpoint-status |  |  | checkpoint | 4.1 - Post-seal Area Check
label | 14dc11a8-d122-5873-9142-0593598862ec |  | note | VERIFICATION ACTIVITY - Measurement
label | 6f1cedff-4484-53db-8dd3-e9c5777c0e54 |  | note | METHODS OR REFERENCE - On Site tape-measure
label | 5b68e1fb-803d-594f-b461-980406f40276 |  | note | FREQ. - After Surfacing
label | cb0e170e-fb5d-5212-a846-b3b74e9600bf |  | note | ACCEPTANCE CRITERIA - Check sealed area meets design
label | e8510024-3388-537b-bccb-6c4d4b53a500 |  | note | INSPECTORATE W/H - Type: - W
label | 4081fb22-240b-50be-9956-6dd12df6d1d4 |  | note | INSPECTORATE W/H - Description: - Notify Renewals Engineer or Renewals Manager
label | dc4232e0-5cbc-5ccc-b2d9-f32359cdc0d4 |  | note | Responsible Person - QA Engineer
checkpoint-status |  |  | checkpoint | 5.3 - Service Covers
label | 29981e3c-697a-58a7-899f-413c11af5c56 |  | note | VERIFICATION ACTIVITY - Measurement/Visual
label | 1d2bf8b8-8f43-5b6f-a341-f17c2c746ea3 |  | note | METHODS OR REFERENCE - On Site
label | 7f713176-0794-5e26-b9dc-1e6929db87bf |  | note | FREQ. - After Surfacing
label | 84bb9261-0a15-5abe-a29b-13952354982f |  | note | ACCEPTANCE CRITERIA - All service covers are checked and adjusted (if necessary) to finished level
label | 76d2c684-4cdd-5b92-9f09-bd2ed1449ef4 |  | note | INSPECTORATE W/H - Type: - W
label | cdd8300f-d8d0-5cbf-9275-097d552fd1cd |  | note | Responsible Person - Paving Supervisor / Foreman
checkpoint-status |  |  | checkpoint | 5.4 - Joint Sealing
label | e6099afa-c1b7-5eae-945a-5a9753e57c2a |  | note | VERIFICATION ACTIVITY - Visual
label | 41653238-27ef-525d-8561-e739957ce29d |  | note | METHODS OR REFERENCE - On Site
label | b200b992-bfee-540b-88da-b47d79b68bad |  | note | FREQ. - After Surfacing
label | 0940e3be-985f-56e6-9beb-7873d67ad991 |  | note | ACCEPTANCE CRITERIA - Check cold joints are bandage sealed
label | 2591e45f-c6d9-5a6a-be72-a2718ff8d7fa |  | note | INSPECTORATE W/H - Type: - W
label | d76bc997-e752-5c02-a8cb-b2ae41b505af |  | note | Responsible Person - Paving Supervisor / Foreman
checkpoint-status |  |  | checkpoint | 4.2 - Road Marking
label | e1ff10cb-39fb-5a2d-a715-1daf2a5504b3 |  | note | VERIFICATION ACTIVITY - MOTSAM
label | fcea9998-dfa8-54d1-84c5-b5a0ea6359ba |  | note | METHODS OR REFERENCE - Visual inspection
label | 1518eb8d-7acc-535b-9aee-3d6d629167a3 |  | note | FREQ. - All markings
label | 34c7c7e5-c40b-5351-840a-acb88e069f43 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, or per design
label | 1d13fae0-8868-56db-9ff7-7ac470f0ca53 |  | note | INSPECTORATE W/H - Type: - H
label | 19404944-aed5-5291-ad0b-3adb5a0eedc0 |  | note | INSPECTORATE W/H - Description: - Hold point – Site TTM cannot be removed until markings reinstated
label | 376899aa-ba73-5e7d-bec6-c218db3f18c5 |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 - Other Traffic Services - Marker pegs/ Signs/Markings/RRPMs Replaced
label | f142a529-becd-5665-ae0a-1f016976c0cc |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | cdb93334-b936-5c61-b8a6-341b76922e35 |  | note | METHODS OR REFERENCE - Visual inspection
label | 594feee7-01a9-5d7a-b1a9-323b6c56850e |  | note | FREQ. - All signs/markers
label | 2d0e37de-8592-5c57-80cb-3ad38e298ce2 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | 6fe47b47-ad89-5b23-8e83-18c50c5fbf98 |  | note | INSPECTORATE W/H - Type: - H
label | f53808fc-8080-52f6-bb0e-f7921469d48e |  | note | INSPECTORATE W/H - Description: - Hold point – Site TTM cannot be removed until marker pegs, signs, markings and RRPMs reinstated
label | c1fd4865-55e2-5b21-8d87-7d52aeff8080 |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Stormwater Management Controls removed
label | 6857b09f-364d-5ddf-8029-3e0da70429c6 |  | note | VERIFICATION ACTIVITY - Visual check
label | b6d953bb-43f9-5e11-a09c-ede9a3c3141d |  | note | FREQ. - All installed measures
label | 9c3e56e3-e93b-5e71-a7f9-65098b3c73c9 |  | note | ACCEPTANCE CRITERIA - Installed controls are removed
label | efa7bfae-0245-56b3-9226-5cb8e8142a6d |  | note | INSPECTORATE W/H - Type: - H
label | 0a9e0f06-25d1-573c-a0e2-84902152e4af |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Traffic Management Removed
label | 9e208ad5-189a-577d-b304-f2dfc02ea14e |  | note | VERIFICATION ACTIVITY - Visual check
label | 31189150-c040-58fa-a678-87f33bd98a1c |  | note | FREQ. - When safe, after all physical works completed
label | f06c402c-ace3-5128-b6da-7cdaf86520b2 |  | note | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | 8bc505c3-1969-5001-ae1c-2f0c9744f1ce |  | note | INSPECTORATE W/H - Type: - W
label | 566d4469-72bd-5be7-8aa7-0dde7210fe8d |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.6 - Site left clean & tidy
label | ec2c55cf-d059-5ce5-80ad-7a6cbbf3c726 |  | note | VERIFICATION ACTIVITY - Visual check
label | 57e6105c-c2f2-53da-91ee-91ffee58c244 |  | note | FREQ. - After vacating site
label | 7a4f1646-1307-5b00-8aa7-eca84ebb8852 |  | note | ACCEPTANCE CRITERIA - Stockpiles removed; Plant removed; Litter cleared from site
label | f608f43d-4d9d-5af2-a6ce-209990d78b0d |  | note | INSPECTORATE W/H - Type: - W
label | 21dd826c-400c-5500-bece-5a423673a007 |  | note | INSPECTORATE W/H - Description: - Invite NZTA to carry out joint site inspection to inspect site.
label | 085e9783-a7a2-5ee3-bdb7-47ee2bf4e229 |  | note | Responsible Person - Paving Supervisor
checkpoint-group |  |  | section | 5 - As Built Records
checkpoint-status |  |  | checkpoint | 5.1 - Collect asset data
label | 2a59273a-2d05-5013-bb60-528151375da9 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | 4b2423f5-403e-5300-a884-321383e2e13f |  | note | FREQ. - During construction
label | 26d171ae-cf35-55e1-935f-e8f62021d5ff |  | note | ACCEPTANCE CRITERIA - All relevant as built information collected.
label | a2652b4b-2ec6-50e9-b5e2-14cdd10a5fa9 |  | note | INSPECTORATE W/H - Type: - W
label | 6edf5d79-3358-5507-9c2e-ca80da08541d |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.2 - Enter asset data into RAMM and/or register(s)
label | 4894038e-50b3-5e9c-80b9-1d3e04d59533 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | 8f7c2071-080c-5f30-9643-bdfa5117a826 |  | note | METHODS OR REFERENCE - RAMM
label | d267cf9c-d8e6-5db9-a6da-ec3f47814b7c |  | note | FREQ. - At completion of work.
label | d59a3e2b-7353-5a82-8d02-481ad5222f42 |  | note | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.
label | be29263d-eca0-57bd-a42f-6ca21d2312f4 |  | note | INSPECTORATE W/H - Type: - W
label | 3e7d0a81-47ca-559a-88a6-f8c30cee43ea |  | note | INSPECTORATE W/H - Description: - Data entered by 20th of follow month after month of completion
label | 3976b881-a3b8-5711-b943-10038f90f05e |  | note | Responsible Person - Asset Information Manager
checkpoint-status |  |  | checkpoint | 5.3 - Construction Completion Report
label | caf463b6-d886-56c3-91e2-514ad02d0215 |  | note | VERIFICATION ACTIVITY - Confirmation
label | fa45ab61-2f9e-54c7-ac4e-a0db0fe013f0 |  | note | METHODS OR REFERENCE - Contract Specification
label | 95ef68e7-111c-51e8-8197-a7f55db5d97d |  | note | FREQ. - At completion of work.
label | 8293a0ad-f185-5e19-b979-4e4b9736cd0d |  | note | ACCEPTANCE CRITERIA - Checked and approved
label | 781bc712-3c6b-5b5c-b596-fceb4db607eb |  | note | INSPECTORATE W/H - Type: - W
label | abeac894-d266-5a5d-9493-21d75de9dd3d |  | note | INSPECTORATE W/H - Description: - Completed within two months after Paving Wearing Course
label | cd140a17-8125-5698-999e-9a63fc2b8061 |  | note | Responsible Person - Renewals Engineer/ Renewals Manager
checkpoint-no-status |  |  | checkpoint | Quality Assurance Close Out
text | 4a4e8184-9932-5871-85de-2e0676b66657 |  | textbox | Quality Assurance Close Out by - Name:
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | ITP - CONOC Operations - Repair Broken Kerb and Channel In Situ | itp |  |  |  | Yes | ITP - CONOC Operations (General) - Repair Broken Kerb and Channel In Situ | 79a82c45-3ee3-437a-8d38-6d50f8b4d3ff
checkpoint-status |  |  | checkpoint | 1 - Prepare
label | 55613c9d-59c1-5a73-9e45-73f0db7509e4 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | b04a0c7a-0b08-5e79-a737-3b857506e13c |  | note | Accept / Reject Criteria - As per specification
label | 1736fc7c-c79c-5d8d-98fc-03cabe43afc8 |  | note | Frequency Of Inspection Or Test - In-process
label | 8c0be56a-bde5-5834-9aee-2902a8e34974 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP092
label | 5caee6e2-ea7f-5465-be2d-195bf3a73ef9 |  | note | Records Required - NO
label | 411f3426-a2e2-5035-ac02-cea46dad7f78 |  | note | ENGINEER - R
label | beb6d4c7-ef17-5120-9910-036ef3e8a59e |  | note | SUPERVISOR - R
label | 6b58f831-5087-505d-bb9d-b358ad698bd2 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Excavation
label | effeb28a-f3bc-5642-91ec-1e83680f3451 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 1a024d3a-65e7-5c9f-b8c4-8898fed09029 |  | note | Accept / Reject Criteria - As per specification
label | b21b8071-b58c-5b1d-95d2-5053898985cf |  | note | Frequency Of Inspection Or Test - In-process
label | 4dfd03e1-8a0b-5122-a142-ee35dbe3bbee |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP092
label | 3d7b3a66-5109-5a0b-8812-b1a64f2449a3 |  | note | Records Required - NO
label | a2840a29-9e20-59fe-8ad0-328858fa4e5e |  | note | ENGINEER - W(10%)
label | 6e9fb782-43e7-532f-8a71-5c56c3bc7b62 |  | note | SUPERVISOR - R
label | bc02e5f2-2854-5f15-b563-16d98ff268be |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Bae Construction
label | 2d32ea10-1783-5e12-b2e9-04f9e8627385 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | a1f62166-6601-5d50-85c1-73a425b24358 |  | note | Accept / Reject Criteria - As per specification
label | da2fc334-21cd-5628-a8ee-16af38a68fc7 |  | note | Frequency Of Inspection Or Test - In-process
label | 1f5bfa2e-f4b8-5051-bba2-c8627ce923e6 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP092
label | d58c48b1-9344-59df-a8b3-015ff94a39bd |  | note | Records Required - YES
label | 17dfc9fc-3d21-5aa2-9bff-39f47bc1638f |  | note | ENGINEER - W(10%)
label | 1ad5154f-35e5-53d1-908d-9c5f597a4383 |  | note | SUPERVISOR - R
label | f1ccaa56-d9c1-58d7-b719-688796a35b6d |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Formwork/Boxing
label | bb082352-b975-5d4a-92a9-36458c771657 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | ffff0191-856e-54ed-8b0e-d02f4c8c0d61 |  | note | Accept / Reject Criteria - As per specification
label | dc1dd3ce-3f28-53d8-b341-b1fa502948ea |  | note | Frequency Of Inspection Or Test - In-process
label | a87d9706-061a-5cd2-8a3b-2af6e6e4e532 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP092
label | 3d4b4dac-3687-5dc8-9229-0c53309ca416 |  | note | Records Required - YES
label | 25c18b57-4059-54ee-951f-29f0480c17c7 |  | note | ENGINEER - W(10%)
label | e78bd400-662a-5a64-8ef1-0bc322324a5a |  | note | SUPERVISOR - R
label | 0b26cf33-4a63-545b-bec5-9fe4381c7c2d |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Concrete
label | 4f600091-d563-5c33-82fe-d32b142cf04f |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 4fcb524f-adf5-55fc-900b-84897af3e0b6 |  | note | Accept / Reject Criteria - As per specification
label | 215b0f9e-5359-5b7f-ac5b-0bcf7181995d |  | note | Frequency Of Inspection Or Test - In-process
label | 515b7d2a-731e-53cb-9912-3d92181fe8fd |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP092
label | bbf65144-0faf-5b39-92e0-862fad0757ff |  | note | Records Required - YES
label | d7c8642e-3b93-54a2-a336-06abd1747cb6 |  | note | ENGINEER - W(10%)
label | 02598685-1b21-55ff-bfb8-e91b7721e09d |  | note | SUPERVISOR - R
label | 6fb6b229-7ef0-5014-99ff-a0dc83a88071 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Concrete Finishing
label | 65884e05-60f6-5055-9908-335014b8bdf0 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 6f54a916-0ace-597b-9207-8f3ebceee6d0 |  | note | Accept / Reject Criteria - As per specification
label | 75a288a9-1ea6-5205-810a-4dfa36dd706f |  | note | Frequency Of Inspection Or Test - In-process
label | 52b6dc79-f922-5baa-ae54-774a107aff48 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP092
label | 6899c537-7c00-52b2-8e5f-4834a4012ef6 |  | note | Records Required - YES
label | b49e9a41-6076-5c96-b83e-e137691cd139 |  | note | ENGINEER - W(10%)
label | 1439da9a-d488-5517-9429-8cb2ceb42b92 |  | note | SUPERVISOR - R
label | 70610d13-76a8-5d84-ad34-081719cf72d1 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Restore Road Pavement
label | 889540a5-7a59-5a74-bf52-652080e14569 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | fd0c6542-de36-5258-a27b-13a37dd245a8 |  | note | Accept / Reject Criteria - As per specification
label | f6c0994d-f1ff-5ab8-935d-8c3a50e76974 |  | note | Frequency Of Inspection Or Test - In-process
label | e5865a55-b032-511b-8b2e-637f8edbbf74 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP092
label | d4a665ed-5c66-58a9-940d-f51ecfba0e2f |  | note | Records Required - YES
label | 86aa5163-d4dd-5d75-94a0-f54b0d672bc6 |  | note | ENGINEER - W(10%)
label | fead96b0-0770-5bbc-879f-b7f57d697f90 |  | note | SUPERVISOR - R
label | 16638da5-c6f0-589b-8f5d-0818fc655fb1 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Surfacing
label | 3a591439-d263-5547-a2de-e0d86512ac01 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 79005894-7d04-5fd8-b072-3a9459a8248e |  | note | Accept / Reject Criteria - As per specification
label | 536435f7-3e41-5b76-a348-3ef8a6ecbf04 |  | note | Frequency Of Inspection Or Test - In-process
label | 2aba69b5-be16-5402-a8c3-22bcfbebedac |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP092
label | d91ff102-e62b-5a6b-8996-72506bdb8727 |  | note | Records Required - YES
label | 39f452a8-9603-53e6-9e9a-1d7c7e9930f6 |  | note | ENGINEER - W(10%)
label | 02965e0d-40bf-538c-a544-90930d95e1d0 |  | note | SUPERVISOR - R
label | 0124c19b-2f00-5b6d-9a9f-9b9d9cc7c280 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Restore Grass Berm and/or Footpath
label | a5cbac64-94b5-5498-9a42-7c83b7050a51 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 59a993a6-f18c-588b-8e2d-67fc48c96f10 |  | note | Accept / Reject Criteria - As per specification
label | 9e62e791-9dcf-56b6-a1d0-894e013e90d8 |  | note | Frequency Of Inspection Or Test - In-process
label | 2a6cabb0-5456-53cd-b8aa-c05e90feea64 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP092
label | 620ae12f-ce35-58e7-b1b1-8f6aafa99f22 |  | note | Records Required - YES
label | e06bdb51-ae53-592d-b7dc-4a1602046876 |  | note | ENGINEER - W(10%)
label | b713ef3e-fe99-5ee7-8df4-6bf314373225 |  | note | SUPERVISOR - R
label | c18d5219-57b6-5fa0-8716-2f7ebbfd0a00 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Test and Check
label | 53730a88-51df-5a99-a289-c5d634434755 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 9a7227ea-0007-516e-a80a-393ce3bdc189 |  | note | Accept / Reject Criteria - As per specification
label | 109a8441-c108-5710-844c-187073b85753 |  | note | Frequency Of Inspection Or Test - In-process
label | b9fea7b4-a57d-5eca-a5e7-1490a468f900 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP092
label | 337da2e4-be98-54a9-b32c-f4f06f2c2ccf |  | note | Records Required - YES
label | a4383ef8-993d-5821-a77f-7e41986f65a9 |  | note | ENGINEER - W(10%)
label | 8bda02f8-59f8-5453-9107-a75bc35ed8e7 |  | note | SUPERVISOR - R
label | 433a9211-faa9-5ffc-8620-3a50c4ff3c14 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations (Heavy and Light Maintenance) - Pothole repair using a Broom Road Patch (BRP) | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy and Light Maintenance) - Pothole repair using a Broom Road Patch (BRP) | 7c4445c6-c5a6-4066-bbc7-b090794accbd
checkpoint-status |  |  | checkpoint | 1 - Prepare Hole
label | 5bf245bf-e5f4-503b-a2d0-991735bb423b |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 84ae6677-4583-5415-a2d2-304eaad648c5 |  | note | Accept / Reject Criteria - As per specification
label | 0f8ba06c-05e6-570b-b1f6-6aab6a94a453 |  | note | Frequency Of Inspection Or Test - In-process
label | 389df326-bd09-5af8-8cd5-42d390b9e82e |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP034
label | 496898ce-121f-5d00-a9e8-6aed7e0b29e3 |  | note | Records Required - NO
label | 10ffe44f-9a6b-5316-aaef-caead30d6264 |  | note | DOWNER ENGINEER - R
label | 16ca5858-2d2e-5b7c-b104-3bd99c48b25e |  | note | SUPERVISOR - R
label | aafd770c-29ce-5122-93d6-7044cbad6b43 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Apply RS1 Tack Coat Emulsion
label | db94dadf-83b9-5231-b8eb-e50e5b2c5c85 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 0b9346b1-a737-5981-9bbb-4135a435ed35 |  | note | Accept / Reject Criteria - As per specification
label | 86cdfb08-9b47-5563-8466-8c428eceb427 |  | note | Frequency Of Inspection Or Test - In-process
label | cd11d97b-a7bc-5de5-86fb-6e240a1aa0ce |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP034
label | f40cf953-7f7c-58d6-a92c-d5adb9abe938 |  | note | Records Required - NO
label | a1610317-1e6b-5ecb-a419-261b939cd5de |  | note | DOWNER ENGINEER - R
label | dc5c5858-950c-5c0c-8b6a-ba5dcbfe62d9 |  | note | SUPERVISOR - R
label | 710c96fb-b0fa-5238-9a2b-c80892fde119 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Attach BRP
label | 5f5b9e3f-15c0-5512-9bad-82199007dde5 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 7e7a6874-ec03-5244-9856-4c2942e27d86 |  | note | Accept / Reject Criteria - As per specification
label | ed7556ce-e157-5fff-9ab9-d3ee63f2650f |  | note | Frequency Of Inspection Or Test - In-process
label | 76f5cdf5-6e74-5566-81b1-5de4545abd86 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP034
label | 58b22ad9-beff-56f9-b7fd-45deff271be4 |  | note | Records Required - NO
label | 74f0d61f-30e2-510b-a7fa-f768253527e8 |  | note | DOWNER ENGINEER - R
label | 04c51dc0-c42c-5407-86cf-cf5166c2bccc |  | note | SUPERVISOR - R
label | f8f30343-8233-5527-94c2-71caa6cf2b5e |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Blinding
label | 27e488a5-6cfc-57a3-9b25-4732b9d6de7f |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 3383696f-3ed2-5b39-9a5b-03e5b079a1e9 |  | note | Accept / Reject Criteria - As per specification
label | f19a60d3-6a8b-5d50-8b84-7993f5d205e9 |  | note | Frequency Of Inspection Or Test - In-process
label | e2513797-81b8-5535-ba6c-afa8cb80ffd1 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP034
label | 419d6149-a84f-5809-81bc-dee7185b078e |  | note | Records Required - NO
label | f1d57977-f255-58fb-90d1-2afdec8c3bd5 |  | note | DOWNER ENGINEER - R
label | 21991015-7cca-5cc8-a991-dd42287c7680 |  | note | SUPERVISOR - R
label | eb6ea451-ca1e-502f-a0c6-53a963496496 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Test and Check
label | 1b3a420d-30c1-5904-8aef-4ffc6a7119ee |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 65219267-1f51-54f7-ba15-eca627998f8d |  | note | Accept / Reject Criteria - As per specification
label | 56042ad9-e95c-55c7-900e-bf8d31126de6 |  | note | Frequency Of Inspection Or Test - In-process
label | 2c757646-376e-5b0a-90fb-24b12b3ca96f |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP034
label | 4d78e349-fae0-5b54-ac4d-4df96844bb97 |  | note | Records Required - NO
label | e4f616f8-88c9-542b-aa29-d898ac5eaca0 |  | note | DOWNER ENGINEER - W(10%)
label | 93b5b1e0-d019-55b8-a153-c80c49248bce |  | note | SUPERVISOR - R
label | 64148f55-d1af-5d23-9acf-998943b91870 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations - Control of Spill | itp |  |  |  | Yes | ITP - CONOC Operations (General) - Control of Spill | 82ddf544-e813-454d-b67c-cf8da0308200
checkpoint-status |  |  | checkpoint | 1 - Preparation
label | f3131853-9646-57b4-88a3-c65227468c9c |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 2cc98dbd-1cd4-58c6-ab75-e9b6bf34de0b |  | note | Accept / Reject Criteria - As per Specification
label | 999e78bc-75ca-5905-b1a2-3b33b6e852d4 |  | note | Frequency Of Inspection Or Test - In-process
label | 600f0f6e-6e4d-5318-b28d-65bf70004e2c |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP101
label | 2513f43f-723c-572a-b09e-e640375b67fd |  | note | Records Required - NO
label | 3c637bf6-16f0-5ab0-ae74-dafe18a10eff |  | note | ENGINEER - R
label | 39a3978a-b0be-5b5a-8841-58300cfd87d1 |  | note | SUPERVISOR - R
label | bf12a3b7-003f-5087-bf41-60f38d4a70fa |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Establishment on Site
label | f04dfe3e-f83b-5b01-8aab-a72df54fd052 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | b0fe75e3-7ebb-5b3a-a39c-4fc8ffbbfb88 |  | note | Accept / Reject Criteria - As per Specification
label | fc7cd08d-da56-5fe3-bf29-b6649a990482 |  | note | Frequency Of Inspection Or Test - In-process
label | 94f7dcc7-acd7-53fa-b222-059772b43be1 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP101
label | 20243159-3e41-5de6-99b7-1a83a58a4fb0 |  | note | Records Required - NO
label | d632b167-d736-5908-9f16-e82342ec07f9 |  | note | ENGINEER - R
label | b3de2d5b-6d31-5bb2-9970-567d2ae13dd9 |  | note | SUPERVISOR - R
label | dfaafa2f-857c-57aa-8048-8c17fa48aa50 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Initial Action
label | a8ba2ec1-fa0d-5188-905d-c7250eea19fd |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 56955f3a-e73a-5f9e-b847-f5414b2f554c |  | note | Accept / Reject Criteria - As per Specification
label | 258a20df-c776-5ba2-a0a0-080cb7914503 |  | note | Frequency Of Inspection Or Test - In-process
label | 24756498-f24f-51b3-9a6e-ba2487459cf9 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP101
label | 2acad5c0-7e1d-507e-b70c-a442b388ca1c |  | note | Records Required - NO
label | a2a31678-bf8b-58df-995e-934034357dff |  | note | ENGINEER - R
label | 260ab69e-e7a6-5da0-ad5a-44572a34c9bd |  | note | SUPERVISOR - R
label | 0cf8ddd1-fcf6-5f3a-b56c-4d1d4d64b6fe |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Treatment
label | c9b798a2-ef8a-5205-851f-99d282bc8a25 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 63cfd947-aa5b-5a69-8da7-751db54671be |  | note | Accept / Reject Criteria - As per Specification
label | 329bd0e9-68d3-5893-8f69-d8dbb9aebae4 |  | note | Frequency Of Inspection Or Test - In-process
label | 4feb66d2-32b4-54f1-80d7-27a531e1590c |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP101
label | d2a9e4e0-530a-57ef-bc60-16bd9ffdb0df |  | note | Records Required - NO
label | acb0dda5-7d34-5b2e-ac46-6ce521a71f9d |  | note | ENGINEER - W(10%)
label | ca8c9660-818a-5b36-b6e1-d29081d86f87 |  | note | SUPERVISOR - R
label | c0a5800f-dacf-50d8-8fcb-c2318e8636eb |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Disposal of Uplift Material
label | 6b441d02-a600-564c-9669-2500dd31c485 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | f001bc3e-d87c-5ce0-a5a4-d28847a23cdc |  | note | Accept / Reject Criteria - As per Specification
label | 0633b3e0-1709-5244-ae06-f66c1f6de30a |  | note | Frequency Of Inspection Or Test - In-process
label | 6f76084d-633f-5d16-a1b2-b3e09b90a5e5 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP101
label | 507f076e-dcc6-5f1e-ba76-1b18442b06e6 |  | note | Records Required - NO
label | 2f986f68-8c5e-5ec7-8da1-0b1fde796f5e |  | note | ENGINEER - W(10%)
label | 9c626dd0-dd72-52e8-8022-302bdaaf808b |  | note | SUPERVISOR - R
label | 6266510a-f527-50ad-9494-db787b5d6ac2 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Test and Check
label | a3e0123e-b948-5d6b-84cd-caa858d64c50 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | a1a78369-aa26-5596-b8a2-101bbeef1f1a |  | note | Accept / Reject Criteria - As per Specification
label | 43932a01-adf3-5c5f-b054-f8adbea19672 |  | note | Frequency Of Inspection Or Test - In-process
label | e5e2635f-8373-5fdf-ad3a-e98a4f50aa57 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP101
label | aa79ff1c-1ca2-5c14-af91-a1ade6378095 |  | note | Records Required - YES
label | 2e0224eb-0b06-562a-88c1-8e5bcaf11513 |  | note | ENGINEER - W(10%)
label | 98b58ba0-b08d-553a-a204-8b78d8a70514 |  | note | SUPERVISOR - R
label | 23741ee9-55ef-5f6f-a502-77a9a70d826b |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC NETWORK - Repair Surface Depression - Mill and Fill Method | itp |  |  |  | Yes | ITP - CONOC NETWORK - Repair Surface Depression - Mill and Fill Method | 84dc7dc4-27fb-4402-bb46-3a9f516ad838
checkpoint-status |  |  | checkpoint | 1 - Preparation
label | 00be5ae7-ec46-5a7c-a131-eab48f646ba8 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | c9b436ed-ce69-56ee-ad53-2a45ff5dd0cd |  | note | Accept / Reject Criteria - As per specification
label | a437c2be-697e-523e-948c-cab355ca34ba |  | note | Frequency Of Inspection Or Test - In-process
label | 0287920c-1556-5e5b-b9c4-f928f04c6972 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041/Ground Distrubance Permit
label | ed7b1977-800f-58fa-aa58-716551b2cc3c |  | note | Records Required - YES
label | 1dbf41cf-7e67-5c18-ac31-a13641b199a2 |  | note | ENGINEER - W(10%)
label | ae84ad7d-c828-5480-838b-e8b0b788e6a7 |  | note | SUPERVISOR - R
label | 4d8b9c4a-c0e3-5a43-8b24-f6b3b1314196 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Milling
label | 00329cac-7266-553d-b815-4d858af2560c |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 6ef360a0-bf02-58cc-9f2d-fb9541f5a726 |  | note | Accept / Reject Criteria - Check depth with a straight edge or string line
label | 0c5cf5bb-34ff-538a-b239-9407316b9e05 |  | note | Frequency Of Inspection Or Test - Every 10m or based on the site length
label | 914dae96-6a41-554c-83ae-70732941ca27 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | 176ff1be-410b-59f5-8323-56f4bddc83cd |  | note | Records Required - YES
label | 8891946b-251c-5a72-a56e-96ba494aaa47 |  | note | ENGINEER - W(10%)
label | 02043791-4da7-5faf-ba1e-5a6e30085dbe |  | note | SUPERVISOR - R
label | 6d0c1d9a-da4a-5996-a435-1e80314009e0 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Base Layer Acceptance (Clegg Value)
label | 56af0c77-868c-5cfa-a6c6-315a8438364b |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 0db018fe-828b-568f-8940-4e2a95d1c792 |  | note | Accept / Reject Criteria - Value of 25-35 needed
label | d7851c5e-fc65-5326-baee-ff8859721de1 |  | note | Frequency Of Inspection Or Test - After every 1m
label | d83d9444-ee97-5b80-ac0c-c23119b34bf4 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041/Clegg Log
label | 98f4a345-0e23-5348-aabf-bd499d95904d |  | note | Records Required - YES
label | 17cf601d-89d2-5475-8f81-abb327d74e15 |  | note | ENGINEER - W(10%)
label | eaa7b96c-784a-5640-b921-e125d99d6487 |  | note | SUPERVISOR - R
label | 28ec378e-8e7a-5bd7-bf41-914e6599833a |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Application of Binder (Tack Coat)
label | a303531f-cc1e-5b8e-a140-c0a48d9049f2 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 95901ce2-66ec-5a29-8b1c-a335201ff521 |  | note | Accept / Reject Criteria - As per specification
label | 68e9bddf-33b5-5a3d-b2ac-e9f603e85268 |  | note | Frequency Of Inspection Or Test - In-process
label | 791487ff-2543-5f70-897c-b1578df5b1ac |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | 05fe5755-68b5-5eca-9c81-cbbd6acfe105 |  | note | Records Required - YES
label | 49407629-1144-536a-820e-b75f86215256 |  | note | ENGINEER - W(10%)
label | fd55100a-c07f-57da-84ce-e283531c78c6 |  | note | SUPERVISOR - R
label | 6c1b6d52-046a-5149-83ed-8d4e4787d178 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Premix Selection
label | 9064311a-f6ad-5820-ab7d-90ab02a711ef |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | e6387827-5239-5c79-a0d5-2f2b23cec151 |  | note | Accept / Reject Criteria - As per specification
label | 4d72f624-0800-5756-ac45-12105884ec2a |  | note | Frequency Of Inspection Or Test - In-process
label | 938f6d4b-223b-5170-922a-fca524f2fdaf |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | b8f679cc-806d-521b-a548-4fed7dfc79aa |  | note | Records Required - YES
label | df1bcff1-ada9-5891-9720-13abe16ed3d9 |  | note | ENGINEER - W(10%)
label | 2027cf09-a7d7-5f82-ae97-fe1622a33554 |  | note | SUPERVISOR - R
label | 51f985b3-811c-5e3f-9d2f-2474bbfd78cd |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Laying Premix Material
label | 5bcbf248-9e6c-5c09-81c5-43398357b130 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | c7400a23-75a6-577b-af8c-1656013cd521 |  | note | Accept / Reject Criteria - Lay Premix in even thickness layers
label | 37eba5ae-f751-564f-8b29-aac17457d5d9 |  | note | Frequency Of Inspection Or Test - In-process
label | a8d6b34a-bf6c-5e4a-85b2-f87173329414 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | be2f1719-c77e-5a57-a4a2-52372c5bf20d |  | note | Records Required - YES
label | 0c45fd00-dc5f-5432-b0a1-af5450dd05c5 |  | note | ENGINEER - W(10%)
label | 78a51d7c-7ba0-5699-9117-c2ce80f40fe6 |  | note | SUPERVISOR - R
label | 518b149e-eead-528d-b0dd-0807f006427e |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Final Compaction
label | 329a5bf8-43db-54f2-ac80-555996d028a7 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | eca8f5d9-e473-572a-85bc-909e43d55db4 |  | note | Accept / Reject Criteria - As per specification
label | b3d2d22d-e3cd-55ac-89dc-0ab159f84750 |  | note | Frequency Of Inspection Or Test - In-process
label | 68c3afb6-092d-518f-a4d6-2e65cedd1017 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | d4d07984-bf55-5168-8b18-635f636d8f2b |  | note | Records Required - NO
label | cd10d451-df93-597a-a88c-e7af6d577d7f |  | note | ENGINEER - W(10%)
label | 6f5e0984-3754-5e38-8520-10c55e9a7f16 |  | note | SUPERVISOR - R
label | d1637e97-dfae-501c-ac8e-e645a1955d9e |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Blinding
label | 2f63ac41-4aa0-5ac6-bf87-e048ac11ae78 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | a5aa1983-db93-5384-a4f5-8dfb08b22c49 |  | note | Accept / Reject Criteria - Blinding with sand and restore road marking
label | 584c1f0a-2553-5f95-9c28-58831b259cd7 |  | note | Frequency Of Inspection Or Test - In-process
label | 982097c9-869c-598a-bcb6-a061f542db92 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | 1cc29e5c-151c-588c-9c9f-70800bab8738 |  | note | Records Required - NO
label | 4b15bde7-9e06-5116-8ef8-65411cf074fe |  | note | ENGINEER - R
label | 46bbcec1-e0f7-5a14-9fe2-2570306a6dc0 |  | note | SUPERVISOR - R
label | 6a1f78fc-5678-5e6a-981f-edcacfcea468 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Test and Check
label | 4a646ba7-a3ca-56b5-a61f-75c2620b1033 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | a127ebcc-bdf2-502c-bec5-7cdb91d6560d |  | note | Accept / Reject Criteria - Any depression must be less than 5mm
label | 7ff5a838-b67b-56eb-b6c3-2b61928af23e |  | note | Frequency Of Inspection Or Test - In-process
label | 5ff4bfbf-1945-5252-8d18-2067431567ae |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | 476a33b7-0177-59ad-baeb-d9f7841e98ab |  | note | Records Required - YES
label | 70a9831d-ff89-5c32-b722-cc798cb84290 |  | note | ENGINEER - W(10%)
label | 9e6fd23b-c385-50bf-ac90-4c320485e63a |  | note | SUPERVISOR - R
label | 5fbd579b-04b4-5b43-9428-d3ebc52adb81 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - Wanaka to Athol - Thin Asphalt Paving |  |  |  |  | Yes | ITP - Wanaka to Athol - Thin Asphalt Paving | 8593b7f3-a18a-4483-9540-e882aaf876ae
checkpoint-group |  |  | section | 1 - Preliminary and General
checkpoint-status |  |  | checkpoint | 1.1 - Construction Programme Completion
label | 13fe8677-4283-5e57-b78d-4be8a49c7a75 |  | note | VERIFICATION ACTIVITY - Confirmation
label | f5d14940-46d2-5ba7-871d-d9e1cb047edd |  | note | METHODS OR REFERENCE - Best Practice Contract Specific MMP
label | b2eeeeae-fa78-52ba-af0a-51e8212db4de |  | note | FREQ. - Before work commences
label | a41fb442-a5e6-570a-b8de-4f40758ef594 |  | note | ACCEPTANCE CRITERIA - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date.
label | 2a723a21-ccd4-53bc-9b71-35b243c7a040 |  | note | INSPECTORATE W/H - Type: - W
label | de1fe50a-6744-5faa-b954-71ccf723dc80 |  | note | Responsible Person - Renewals Manager
checkpoint-status |  |  | checkpoint | 1.2 - Approved RQP
label | dd405f7d-7eaf-526c-951e-adcf751db837 |  | note | VERIFICATION ACTIVITY - Confirmation
label | fcbfca5f-cd1d-5006-8628-588ca7403c05 |  | note | METHODS OR REFERENCE - Contract Specification
label | 3053c8c6-e35d-598e-9119-8cdb86d6386f |  | note | FREQ. - Before work commences
label | 599bde3a-831c-59d0-8f5b-c532f7ab2922 |  | note | ACCEPTANCE CRITERIA - Principal Acceptance according to guidelines in appendix 6.3
label | cdc460bf-dbfd-5b6f-a05f-9ff972c0cb32 |  | note | INSPECTORATE W/H - Type: - H
label | 97f1d074-c588-560d-96f3-14686b9e5286 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. NZTA to approve
label | f9832709-6def-58b4-b72a-1e4654ff8f3b |  | note | Responsible Person - Renewals Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Traffic Management - TMP
label | ebbde381-4a54-5bbf-b5f5-1c69c1bc119c |  | note | VERIFICATION ACTIVITY - Visual check
label | e1ba86ed-60e4-5bef-8d6b-00fe2dafd32f |  | note | METHODS OR REFERENCE - CoPTTM
label | 0b19ad12-b153-5a73-900f-429a6fd1ab33 |  | note | FREQ. - Before traffic management set up
label | 72128c52-33d6-5e60-86b7-e45b97d1192b |  | note | ACCEPTANCE CRITERIA - TMP checked and approved Plans approved Current EED (if applicable)
label | f9b61bda-2214-5213-a377-82e56072164e |  | note | INSPECTORATE W/H - Type: - H
label | 6213ef7e-a429-5ccf-9085-0da38123bf71 |  | note | INSPECTORATE W/H - Description: - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | f5b81e7a-4caf-57d5-9eff-71681f62c6ef |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Mix Design Verification for all mixes Check Laydown Trials are complete and compliant
label | ceaae546-0989-5e5d-bc69-48af60e09bec |  | note | VERIFICATION ACTIVITY - Confirmation
label | 4b59633c-0ba9-5447-adcc-926bfd18562a |  | note | METHODS OR REFERENCE - NZTA M/10, P/11, P23
label | 724899d4-aed1-5c50-9742-8ca47fd2bd56 |  | note | FREQ. - Before planning commences
label | 33b4e2c8-1e7f-5c31-8ed8-5f9ca6905daa |  | note | ACCEPTANCE CRITERIA - Mix Design compliant, current and relevant. Batching plant production capability is confirmed
label | 5952d52d-4055-5e77-97d8-918d9353e017 |  | note | INSPECTORATE W/H - Type: - H
label | cfe97264-6ede-5b46-b17b-512f92d7e637 |  | note | INSPECTORATE W/H - Description: - Hold point - No planning of on-site works shall commenced until the mix design is verified.
label | e8a5dca9-fa9b-520c-9d9c-1ab165c4ff31 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Notification of intention to start work
label | 6961c775-0ed1-5978-ac72-1d2a37d85796 |  | note | VERIFICATION ACTIVITY - Notification
label | 5f050983-546c-5d05-8271-43a0013b3271 |  | note | FREQ. - Before work commences
label | 2b1afaa1-ba20-5c34-9444-ab50c48dd2ff |  | note | ACCEPTANCE CRITERIA - Letter drop to local residents. Greater consultation where required
label | 2bd85c5b-d3fb-5678-b5d7-2356e41a40e4 |  | note | INSPECTORATE W/H - Type: - H
label | b70b008a-f364-505b-ba8b-1e7baa22190e |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | 72a01221-2a21-5ad0-afdc-7e96ac06aa8a |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Works Extents
label | 4044a8c1-5f63-576e-80b7-a99d157ac330 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 0f547a9b-1e41-5298-afc3-18a75ac844b3 |  | note | METHODS OR REFERENCE - Site Visit
label | ac7613b3-1cef-5eb6-80d3-d93ca46c0d14 |  | note | FREQ. - Before work commences
label | 595d82db-63f3-57c9-9dd9-4c1b33f2f844 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and/or Client to agree extents of project
label | 0ba46e4a-14cd-52ed-ae55-61bffc2fe902 |  | note | INSPECTORATE W/H - Type: - H
label | 7c706598-5d37-5d78-b994-ecde0cb69aa1 |  | note | INSPECTORATE W/H - Description: - Hold point - Walk over site with Renewals Engineer and/or Renewals Manager and/or NZTA
label | 0db0a7eb-e4cc-510b-98bd-a8f5aa0f7436 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - Pavement Marking Records
label | 3b9524f9-0ba6-5086-8d47-f17a071fa1b6 |  | note | VERIFICATION ACTIVITY - Measurment Data
label | d9315d78-6543-5a06-abe5-c55d19ae6e3a |  | note | METHODS OR REFERENCE - Site Measure or Video Viewer
label | 9f3cb3b4-6ff7-515d-9189-72a1294f58db |  | note | FREQ. - Before work commences
label | d3e2485b-2787-53a5-9668-57489cae6874 |  | note | ACCEPTANCE CRITERIA - Measure existing markings to aid reinstatement
label | 92b3d41c-ea51-53df-911e-c114bf2621e8 |  | note | INSPECTORATE W/H - Type: - H
label | 321e5265-8979-51e5-bbe0-8fcc16425ea0 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | 31abcfe8-6ba2-5b93-8485-2d78e37a83ac |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Milling and Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | bd2870e4-85cb-55ad-a94c-45cccd8e3a52 |  | note | VERIFICATION ACTIVITY - Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth)
label | 19966c27-f082-5452-9dd3-09cdf551e678 |  | note | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | 22a3d752-c197-520f-8575-3242c15a0d7d |  | note | FREQ. - Before work commences
label | 8af73a7d-7668-5490-9912-9cd8976a610a |  | note | ACCEPTANCE CRITERIA - Zero service strikes
label | 2645f6e8-3f7f-5b18-968a-93e1086c4908 |  | note | INSPECTORATE W/H - Type: - H
label | f794e038-3a81-5b7d-a6e1-89af67b290dc |  | note | INSPECTORATE W/H - Description: - Hold point - No excavation/milling is to be commenced until services are located and accounted for
label | 28258b6b-d278-5505-8eb5-0030d29fdc3b |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Stormwater Management
label | 56a31308-6eac-5bed-8d82-d408d30a1ad6 |  | note | VERIFICATION ACTIVITY - Visual check
label | 72a603b4-7d4c-5230-9121-39e43a4c17c7 |  | note | METHODS OR REFERENCE - On Site
label | e200d391-792d-54c2-8235-620223fbaadc |  | note | FREQ. - Before work commences
label | 2dc1d510-8df7-59e3-b03d-f407de7e3fee |  | note | ACCEPTANCE CRITERIA - Mudtanks bunded or filtered to prevent mix from dropping in or runoff entering
label | 42af7f4b-f533-552a-bba4-57ed6b2d38b8 |  | note | INSPECTORATE W/H - Type: - H
label | dceb74e8-729d-53a3-ba5c-099cd7460e39 |  | note | INSPECTORATE W/H - Description: - Hold point - No work to be commenced until protections in place
label | eab6408b-d462-5f1f-9d58-bc6550dcc5e3 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Traffic Management - Setup
label | 3eaa593f-9c5d-5c10-9b7b-08ab0caee8da |  | note | VERIFICATION ACTIVITY - Visual check
label | a721055c-d2c8-58b2-85dd-194d85b92886 |  | note | METHODS OR REFERENCE - Traffic Management Plan
label | 85c2a58b-bdb5-5936-bba7-e6c27b47b66e |  | note | FREQ. - Before work commences each day
label | e51474ef-760a-5602-b8c8-2e337872cb49 |  | note | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | 741fa462-9fb6-572e-be4e-7a7760d0b1bc |  | note | INSPECTORATE W/H - Type: - H
label | f9e31ba6-ff68-5edf-b582-fab712ecad04 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | e89cd3cb-2910-5d17-97a5-f9013832bc3c |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Milling Depths
label | 03fb5222-28c4-523e-89c8-2c4ce4ddae57 |  | note | VERIFICATION ACTIVITY - Measurement
label | c01ff21b-45d7-5bf7-bd11-2120d07d3910 |  | note | METHODS OR REFERENCE - On Site
label | c0134629-3796-50ec-a0ec-cd82c006ffd2 |  | note | FREQ. - Measure each side of milling machine cut
label | 5065ee79-388d-50d4-8c9d-d2775c7e71af |  | note | ACCEPTANCE CRITERIA - Every 10m. Depth matches target
label | 55390b37-8cb4-5f1e-a388-b45ac3dd5280 |  | note | INSPECTORATE W/H - Type: - H
label | afeb0905-09b7-5c04-8e5a-8a9d307a9a77 |  | note | Responsible Person - Site Foreperson / QA
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Service Covers Preparation
label | 33bb5bc2-4fab-5882-b017-6194f0f2e2a6 |  | note | VERIFICATION ACTIVITY - Visual
label | e9561c38-cf6d-5cee-b58b-b940c0b268c9 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 32f582ba-b18b-5d54-89c2-82e6977bc7ae |  | note | FREQ. - All Covers
label | 3d8f374d-e5dc-56d3-8ea7-d8875c7ba85c |  | note | ACCEPTANCE CRITERIA - Hand excavation around ironwork and adjustment to desired level (if required)
label | 334b819d-3950-51d1-9546-1781feff213b |  | note | INSPECTORATE W/H - Type: - H
label | e1a80a8a-9480-57e9-bb29-18b2eeb1b748 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Additional Surfacing Preparation
label | aa2f195c-e96e-5b30-8e7a-4423ffb7a674 |  | note | Side Roads; Accesses; Driveways; Dish Channels; High Shoulders
label | ee988bf4-29a3-505b-b2f8-fdaed9eaa481 |  | note | VERIFICATION ACTIVITY - Visual Check
label | 8693f044-2292-5a11-8fef-2e51f534c03f |  | note | METHODS OR REFERENCE - Per Design
label | ddbe0ac1-51ac-59a6-8d4e-f270d5db23b6 |  | note | FREQ. - Before Membraning and Paving
label | edbb523e-2a17-5519-a6bb-9f25480c4216 |  | note | ACCEPTANCE CRITERIA - Have all areas of additional surfacing on the design been prepared, membraned and marked for paving?
label | 985d03d2-cb8d-5a82-bd86-1b55f00af08f |  | note | INSPECTORATE W/H - Type: - H
label | baf6ea8c-9bd6-5a29-92da-ea5355e72975 |  | note | INSPECTORATE W/H - Description: - Hold Point – All areas planned for AC are prepared ready for surfacing layer
label | e2a433a4-58e4-5509-8814-46591c6bd4b3 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Over-Milling
label | 698d8d4b-6a3e-57a6-9354-6bb31e3a3bc7 |  | note | VERIFICATION ACTIVITY - Measurement
label | dc31cbd2-f1f5-51a2-b7c3-9a1871c99bbc |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 252b27fb-05a3-5181-ab85-d994dcec2beb |  | note | FREQ. - Prior to pre-level
label | 106c45fe-4581-5004-a8d7-b1c878f98078 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree need and extent of over-milling and infill.
label | 9d239529-2d74-5a51-be32-ff0661ad7246 |  | note | INSPECTORATE W/H - Type: - H
label | 20d1a290-bd9c-5fa7-ae2e-b94d2627899c |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Pre-Level
label | 921daa76-e1de-5782-8e8d-b00e5ffff78d |  | note | VERIFICATION ACTIVITY - Measurement
label | 59999c6c-409a-5df6-9f13-1e64c306cba7 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | da5e1b96-d208-59e7-9482-4d608d3f14bc |  | note | FREQ. - Prior to surfacing
label | d9980bb5-de8e-52a5-ab0d-c477b4d95aed |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree pre-level extents
label | b95c770a-c902-5448-9936-57cdc1fbbf93 |  | note | INSPECTORATE W/H - Type: - H
label | c4c83eba-a57b-5ce9-ada0-8040ed44178f |  | note | INSPECTORATE W/H - Description: - Hold point - Inspection and agreement by NZTA
label | fc5e797c-eca1-5d0d-89af-d685299d9f4d |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.9 - Membrane Sealing
label | cee876fc-ca48-5d6a-b086-c8a09ed315ed |  | note | VERIFICATION ACTIVITY - Visual
label | 9691f28a-6110-5b22-b356-362ec73086d4 |  | note | METHODS OR REFERENCE - On Site
label | 1078ee7f-3239-5cae-889f-2fe7b8c02aef |  | note | FREQ. - Prior to surfacing
label | 55d661b2-afdf-5454-a423-e220196dc38b |  | note | ACCEPTANCE CRITERIA - Membrane seal meets design and extent. Sealing Docket record kept
label | d1721636-3478-59bb-8c0d-d19e4f6d5045 |  | note | INSPECTORATE W/H - Type: - H
label | 20e90d59-7f79-549d-ba45-79fb92eaf732 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Paving Structural
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | 0d33b5d2-46f1-5541-ab61-cc58598a794b |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | 0074b9a3-9b6e-5923-9ca7-3feec0fb73a5 |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | 1cfbbc63-6aec-5b0c-b67b-e8b7520600c6 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 788c2858-8b7b-54f4-b0e4-2fd8af47a096 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | c40b2527-71dc-501d-900f-f087b035e03a |  | note | INSPECTORATE W/H - Type: - W
label | e565315e-2317-59f7-850a-a42f20698ed5 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 3ca53aaa-3935-581f-b80a-a7b8fc603893 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | 7bc81702-f925-5e25-8543-8a9317e80444 |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | 1807e044-38e8-5390-9e12-e388be6488c5 |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | ab797b2b-448d-5fcd-9c00-fe422fee1c8b |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 0c2fcf17-9153-54b2-b8cb-711138bf49e4 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 8f1f61bf-c0e4-511c-88b2-f80ad1b65685 |  | note | INSPECTORATE W/H - Type: - W
label | 86e711f9-00f1-5cf6-a0bd-ef1bafe25e4c |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | fc0ff55c-cb34-5c95-b38f-c8351cb4e20d |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | 83f8b2dc-71c0-5f2f-b9e8-59ae28d42bb7 |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | 812556e3-02d6-5370-bde3-6a901e117c35 |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | a8b80c1d-6632-569c-b95a-b638655487b0 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | c182da33-3d42-511e-948c-ce4255b7e472 |  | note | INSPECTORATE W/H - Type: - W
label | 7eadd90f-aa73-56cd-a4b7-1ae71d89b144 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | fede0263-ec37-5550-9293-5d3a662d20d9 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | d2ae0269-6a35-5d38-9c55-428f60693426 |  | note | VERIFICATION ACTIVITY - Visual
label | 104ad2af-12e5-5b05-82fd-e29f9ff26849 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 2e40dd56-5a5e-5b0d-b571-3fb656926197 |  | note | FREQ. - Prior to Shift
label | 16d040ed-2805-553c-9a2a-08326a721faa |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | 39bef1f7-60c9-512b-8f80-4cc89edc9c87 |  | note | INSPECTORATE W/H - Type: - W
label | a9276e03-85a3-5c8d-b058-066bcd0c4d48 |  | note | INSPECTORATE W/H - Description: - Paving Plan and Crew Briefing Plan completed prior
label | f700cfcd-3de0-5c31-9076-570c65ef31ad |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | 180b25e2-6f2a-51f4-9ea1-de7c8c1bfb0a |  | note | VERIFICATION ACTIVITY - Visual
label | f4e4595f-458c-5cc3-afc3-36284049132c |  | note | METHODS OR REFERENCE - NZTA M/10
label | 79139cf6-fcf8-52d0-bc87-d8d30440737b |  | note | FREQ. - Prior to Shift
label | 58bbe0ef-b730-5600-bf18-de9f4632c8df |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | a637101f-8593-57a5-b4a3-f6839d25f3bd |  | note | INSPECTORATE W/H - Type: - W
label | 149a8e8c-6532-5d6b-af91-fc5548948b01 |  | note | Responsible Person - Paving Supervisor / QA Engineer
checkpoint-status |  |  | checkpoint | 3.4 - Mix Inconsistency and Deficiency
label | e9f6e512-4b11-574e-8faf-fb2e3d8445e9 |  | note | VERIFICATION ACTIVITY - Visual
label | 0df6d2d4-0c9b-5540-8d24-58dd08577288 |  | note | METHODS OR REFERENCE - NZTA M/10
label | d82a0982-5d7b-517f-ad8b-ec88f0a556a5 |  | note | FREQ. - Continuous
label | 1c3c34a6-83be-56b4-b049-b14cc08867e2 |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | 9cead324-32a9-5ceb-8384-bfa5dd2c531b |  | note | INSPECTORATE W/H - Type: - H
label | 50c2c8ad-94b9-5bfd-a197-a76f01b60006 |  | note | Responsible Person - Site Foreperson / QA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Load Locate
label | b760213f-0e58-5c6c-beb5-1850c8c250b2 |  | note | VERIFICATION ACTIVITY - Measurement
label | 442a26f9-a130-547b-a6e7-5b7c7c79b5d5 |  | note | FREQ. - Every Load
label | 71eb1531-af31-5579-8f72-53472791e1e7 |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
label | 9dc5a430-e4f6-50c4-99df-c50739b1d1ab |  | note | INSPECTORATE W/H - Type: - W
label | 50330be9-55f7-52c0-9160-122c10174d7c |  | note | INSPECTORATE W/H - Description: - Per standard practice
label | 3ff7fad1-cd72-5cb8-8cb8-d8a57506ae5b |  | note | Responsible Person - Quality Assurance Engineer
checkpoint-status |  |  | checkpoint | 3.6 - Laying Temperature
label | 7e013e67-a698-5441-8fe8-4670ebb2185c |  | note | VERIFICATION ACTIVITY - Confirmation
label | 50a1f8d5-b0fd-5e0a-8ea7-296a9c64ff5c |  | note | METHODS OR REFERENCE - NZTA M/10
label | 1c856092-b440-566a-bfbd-53fddff8a167 |  | note | FREQ. - Every Load
label | fffb6ab6-3023-5e1c-80fc-537d644f03d0 |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | aff2d63f-690f-5b26-a0e2-b00110f2c4ca |  | note | INSPECTORATE W/H - Type: - H
label | 8501f045-fd97-599c-9848-b35896753ddb |  | note | INSPECTORATE W/H - Description: - Hold point - Reject mix for non-compliant temperatures.
label | d2fb6823-8473-58db-b1eb-5e66da48eac5 |  | note | Responsible Person - Quality Assurance Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Compaction
label | 0df917fc-9c6c-5f65-a97c-2db26c8cf6c4 |  | note | VERIFICATION ACTIVITY - NDM Testing
label | e8318faf-f847-5bf1-bf1b-ea8359dabbe0 |  | note | METHODS OR REFERENCE - NZTA M/10
label | fc2ab79f-dc58-5613-bd01-a58395357512 |  | note | FREQ. - Minimum: 1 Test per 300m² within Mat. 1 Test per 100m of joint.
label | 2fd61e32-c32e-5882-8fbf-43a3c9b25132 |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | b8d2659c-c92c-54a5-9b55-217570cf6bcf |  | note | INSPECTORATE W/H - Type: - H
label | ee320ebb-68f8-5311-bf42-d3f15414b0b2 |  | note | INSPECTORATE W/H - Description: - Hold Point - No Wearing course paved until any non-compliance is sorted
label | 61801603-dfa9-5525-b25a-47389da22639 |  | note | Responsible Person - Quality Assurance Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Roughness
label | 82d5d9ee-6a0a-5ad5-b941-e873fd7c8bb2 |  | note | VERIFICATION ACTIVITY - NASSRA Testing
label | 7f7bfa9e-9142-5ff6-8b9f-2377c48595a1 |  | note | METHODS OR REFERENCE - Contract Specification
label | 754183a9-0333-5ef5-a386-6f1500afb457 |  | note | FREQ. - post construction
label | d864d4c7-74aa-5fb6-ae46-ba4895956358 |  | note | ACCEPTANCE CRITERIA - NASSRA rolling meter average under 60, max of 70
label | 6f0c227b-3fbf-50df-83ef-826bf0425094 |  | note | INSPECTORATE W/H - Type: - H
label | 92399d0e-b2b9-5258-baff-a5b506db319c |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Paving Wearing Course
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | 9984e08f-8751-5e39-b0e9-a23228448dcf |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | 53967002-356d-57e4-bf7e-6c894cfa221e |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | 03cf638c-26f6-540f-af03-cda280388aae |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | a733f059-4672-5fd0-8547-d72311acefa7 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | cb49c71e-07d1-502f-9292-1ccb50d36f38 |  | note | INSPECTORATE W/H - Type: - W
label | 9a2c4a99-8679-596a-a1d3-77596a111910 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 36a05717-03aa-5819-abce-1e2c5089f1ee |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | 030c0e81-89fa-5bcd-a84a-375203ee93e7 |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | 4666e009-a235-5278-b70f-dd3535c3c4b4 |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | 63d7ec68-c67e-5fe8-b218-a7b44889d342 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 163efeb9-6077-5e9b-9244-cd9f12812e81 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 822ee9f9-a35c-5782-95a2-8c79d5bd4804 |  | note | INSPECTORATE W/H - Type: - W
label | add7b209-6d74-50ac-9ff3-e5a9998af57d |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | cd36cc9a-f1b4-5611-a403-53c1eefd226d |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | 479e0070-fa5d-532c-a43b-2c23a91187c1 |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | bcc3d086-5f22-5d23-a38a-f5b161e93e58 |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | b53175fb-c402-5266-a8bb-53ec53b428cc |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 663067f9-2258-57ca-b29c-16c676a9fe51 |  | note | ACCEPTANCE CRITERIA - Per Mix design
label | 9e0f37e8-c854-5a6e-94f7-87b98eb68b4e |  | note | INSPECTORATE W/H - Type: - W
label | 34871abe-6bf9-57ac-9828-8ce6f8219313 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 0160f4c8-230e-59fa-8345-bda18e70ef38 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | 604326ca-a15e-5037-9eea-e1c9d4e7375e |  | note | VERIFICATION ACTIVITY - Visual
label | 088c034e-c310-5d78-8bad-67861dbef65d |  | note | METHODS OR REFERENCE - NZTA M/10
label | 2bef7bd8-02be-51e8-b550-b7847cbb5f66 |  | note | FREQ. - Prior to Shift
label | 17a46b4a-cdf4-5cc4-8cb1-fa8e927180f7 |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | faca3e76-df4e-5410-85dc-2d675fba6d1a |  | note | INSPECTORATE W/H - Type: - W
label | 36adfce6-04fe-5a3f-993a-48da8940a2e6 |  | note | INSPECTORATE W/H - Description: - Paving Plan and Crew Briefing Plan completed prior
label | 9206a349-dcd8-5c88-a433-a1daa17b4500 |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | c3517cee-3aa0-5572-b051-01d954ab68b3 |  | note | VERIFICATION ACTIVITY - Visual
label | 09780f55-6f6f-5809-8f4a-db54694b480f |  | note | METHODS OR REFERENCE - NZTA M/10
label | ff2c9832-59a7-561a-a22f-0d173abeea9f |  | note | FREQ. - Prior to Shift
label | cd041bb1-bc29-50c9-9a68-abacbeae8c61 |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | cd801336-4934-58be-b3ae-d9dcbafc98f4 |  | note | INSPECTORATE W/H - Type: - W
label | da75e251-1ceb-50f7-a864-44e85fdf2465 |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.4 - Grade 3 Membrane Sealing
label | 5f0e901e-4d0f-57b1-b59d-6bc7240c67e4 |  | note | VERIFICATION ACTIVITY - Visual
label | 3a797e40-5f81-554b-8363-dff559cbe966 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 9745ccad-363d-5d08-a5e7-bc0aeca9d014 |  | note | FREQ. - Prior to Paving
label | 93760374-bbd8-5d33-8330-c7219ef987f3 |  | note | ACCEPTANCE CRITERIA - Applied 2.0l/m² residual
label | edcf6820-49b0-50b6-8a08-6abc7c006713 |  | note | INSPECTORATE W/H - Type: - H
label | 12fdda8f-4ceb-5707-89cc-674a7a5c6fb0 |  | note | INSPECTORATE W/H - Description: - Hold Point - No paving until Membrane Done.
label | a216eff8-863c-5cf9-84c2-45e04adc35ad |  | note | Responsible Person - Paving Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Mix Inconsistency and Deficiency
label | aee90c85-4605-54b2-848a-8c251b029ca0 |  | note | VERIFICATION ACTIVITY - Visual
label | cbcdd6ee-23d7-5de2-95ee-242bc3425f8c |  | note | METHODS OR REFERENCE - NZTA M/10
label | 5d837383-136b-5f26-8b0e-f5932f3a1da1 |  | note | FREQ. - Continuous
label | 332fcc99-1e77-5c43-b3a3-48596ad699db |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | 0ad0908a-4e4c-5e03-bd3f-c6f17ec42395 |  | note | INSPECTORATE W/H - Type: - H
label | ef772999-5389-58a0-bbcc-bd84530470a0 |  | note | Responsible Person - Site Foreperson / QA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Load Locate
label | b6cd24fa-5ebe-5453-a07d-73ebbd0c9415 |  | note | VERIFICATION ACTIVITY - Measurement
label | 6fbbaf56-363a-5b78-b5f6-ea0b2d803eae |  | note | FREQ. - Every Load
label | 28f35f54-30e6-59e1-80f3-a73bf1c54b3a |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
label | 24758024-7200-5234-bde5-43b754511b1f |  | note | INSPECTORATE W/H - Type: - W
label | 2e8292e3-435d-5d78-94e4-bd4ce844f585 |  | note | INSPECTORATE W/H - Description: - Per standard practice
label | 4018e8ad-250c-5785-b27d-cbc15b233131 |  | note | Responsible Person - Quality Assurance Technician.
checkpoint-status |  |  | checkpoint | 3.7 - Laying Temperature
label | 24515203-13ab-5a4a-b692-675beafd47f8 |  | note | VERIFICATION ACTIVITY - Confirmation
label | ed41bc69-3df3-5ee4-8401-981d4fb5a5b6 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 8eb9cf22-b7d5-5fd6-944c-4f71615d68da |  | note | FREQ. - Every Load
label | 590d6158-2ab7-5b9c-855e-36f9a17a4cc1 |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | 241b2d8c-d614-57fa-8b74-c6d6d8896975 |  | note | INSPECTORATE W/H - Type: - H
label | e9321500-e588-5eef-afaa-4cd8eae6bcab |  | note | INSPECTORATE W/H - Description: - Hold point - Reject mix for non-compliant temperatures.
label | c07b0338-65c5-58b3-88cb-c225fda1fd27 |  | note | Responsible Person - Quality Assurance Technician
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Compaction
label | e5abe7f4-2319-5258-b19a-5197665e0e93 |  | note | VERIFICATION ACTIVITY - PQI Non-Nuclear Gauge/Cores. Or Non Distrctive Method Testing.
label | 83608efe-613d-50c9-a0f8-cd4c7b3e6686 |  | note | METHODS OR REFERENCE - NZTA M/10
label | e5dc7607-14bc-5bd8-bd65-dad57d1baa66 |  | note | FREQ. - Minimum: 1 Test per 300m² within Mat. 1 Test per 100m of joint. Minimum 8 cores on Mat and 3 on Joints as Per M10:2020.
label | 12ab339f-06c6-5469-aa94-de92a04eb1fc |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | d6b146ba-835e-587e-bdb3-e7a0330e774f |  | note | INSPECTORATE W/H - Type: - W
label | 3fdb4645-3305-5fa5-917b-882b42d3ddf9 |  | note | Responsible Person - Quality Assurance Technician
checkpoint-group |  |  | section | 4 - Site Reinstatement / Clearance
checkpoint-status |  |  | checkpoint | 4.1 - Post-seal Area Check
label | d167b29b-5b3d-5266-a649-ae31d0b57b07 |  | note | VERIFICATION ACTIVITY - Measurement
label | 9345cf41-c012-5a5f-b41b-e8f7e3626278 |  | note | METHODS OR REFERENCE - On Site tape-measure
label | e33a0127-ef59-5c9f-b233-2d1289711ae0 |  | note | FREQ. - After Surfacing
label | da901635-6bb9-568c-ab8c-c4adbf5daf3a |  | note | ACCEPTANCE CRITERIA - Check sealed area meets design
label | 69f41aae-09d9-5288-95e4-d2738d10a509 |  | note | INSPECTORATE W/H - Type: - W
label | bea0cb1c-73ab-5e34-bf62-6762f56410f0 |  | note | INSPECTORATE W/H - Description: - Notify Renewals Engineer or Renewals Manager
label | bc54e6c7-3b59-5140-bbb6-3503484a11be |  | note | Responsible Person - QA Engineer
checkpoint-status |  |  | checkpoint | 5.3 - Service Covers
label | 310f3dc8-f1f0-55a7-8a26-1e01544af96f |  | note | VERIFICATION ACTIVITY - Measurement/Visual
label | 0d62f444-07ac-5809-8a27-086f08ba2d3b |  | note | METHODS OR REFERENCE - On Site
label | 85fd1492-d7b1-511d-83e8-2a456ac318f8 |  | note | FREQ. - After Surfacing
label | 8facb651-bcde-5afa-adeb-f51114491b29 |  | note | ACCEPTANCE CRITERIA - All service covers are checked and adjusted (if necessary) to finished level
label | 397402bf-87a5-5833-96c9-e18610f2cfcc |  | note | INSPECTORATE W/H - Type: - W
label | 1ae45fa5-0ef5-5581-9f67-c0c8e49e4e4d |  | note | Responsible Person - Paving Supervisor / Foreman
checkpoint-status |  |  | checkpoint | 5.4 - Joint Sealing
label | 7e9cf6f4-13a7-56b5-880e-2034d6b180db |  | note | VERIFICATION ACTIVITY - Visual
label | 2ff83058-32d2-5e92-9d5c-5e328fc9215c |  | note | METHODS OR REFERENCE - On Site
label | 45341a42-e282-55cd-be87-97eec9b1ca6a |  | note | FREQ. - After Surfacing
label | 6800fd9d-ac74-5038-9b1b-9bab8f25cf52 |  | note | ACCEPTANCE CRITERIA - Check cold joints are bandage sealed
label | e7cc970d-914b-534f-9f1c-fe1394a2c860 |  | note | INSPECTORATE W/H - Type: - W
label | b48b3899-181b-52df-988c-27e4d505f8fc |  | note | Responsible Person - Paving Supervisor / Foreman
checkpoint-status |  |  | checkpoint | 4.2 - Road Marking
label | b3d1aee9-2b61-58bf-93e2-4b706631f0c3 |  | note | VERIFICATION ACTIVITY - MOTSAM
label | 5c41d4dc-f36f-5966-9727-840247b41686 |  | note | METHODS OR REFERENCE - Visual inspection
label | 834f944e-cd28-5878-a730-24a53235037f |  | note | FREQ. - All markings
label | cd98387e-aa62-5a0d-a893-cc63d683521c |  | note | ACCEPTANCE CRITERIA - Replaced in same position, or per design
label | 54a4f241-6b69-5a90-8cc5-fa99d37b430d |  | note | INSPECTORATE W/H - Type: - H
label | 207cb8fb-4a35-5e0f-8f60-d3fa7c5ef7a8 |  | note | INSPECTORATE W/H - Description: - Hold point – Site TTM cannot be removed until markings reinstated
label | 24872620-2e07-5437-b40d-64453e43071b |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 - Other Traffic Services - Marker pegs/ Signs/Markings/RRPMs Replaced
label | 818434ce-6712-526b-8737-5bc3acd4b88a |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | 3a2f0871-3a26-57a9-b014-56e2eabe941e |  | note | METHODS OR REFERENCE - Visual inspection
label | ea0003d7-69a4-55b4-8e65-1087b5498d40 |  | note | FREQ. - All signs/markers
label | 97ebab3f-5a16-51d8-802c-890acc355ca7 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | 77e4108b-5707-5c2c-9e27-1b40a5be9de7 |  | note | INSPECTORATE W/H - Type: - H
label | dc084808-4b91-572b-a12d-052115467be1 |  | note | INSPECTORATE W/H - Description: - Hold point – Site TTM cannot be removed until marker pegs, signs, markings and RRPMs reinstated
label | 8530a66a-97e2-5de8-a9d8-e0a3365d60d4 |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Stormwater Management Controls removed
label | d16740d5-2ccd-5b14-aa50-ade6b79784c7 |  | note | VERIFICATION ACTIVITY - Visual check
label | 0cde4629-5ef1-502c-9ed8-f23c6555d94a |  | note | FREQ. - All installed measures
label | d5a1594b-a693-5c76-a74d-f1ca3ecafd6e |  | note | ACCEPTANCE CRITERIA - Installed controls are removed
label | ad498bc9-dc35-5fb0-a017-de55ba054e0f |  | note | INSPECTORATE W/H - Type: - H
label | ae00ed1c-b499-5712-b5c5-d688390050a0 |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Traffic Management Removed
label | 7896475e-1c5b-539c-91ac-3d43c20fd7ee |  | note | VERIFICATION ACTIVITY - Visual check
label | 06ac27c8-b2c5-5b37-860e-3f7036af712a |  | note | FREQ. - When safe, after all physical works completed
label | b161d2d3-6472-5842-801d-e445e8196761 |  | note | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | 4bcefcdd-47de-51fe-85f0-5912ef9d4238 |  | note | INSPECTORATE W/H - Type: - W
label | 587f3b98-9747-5744-ab55-2c8a157d2d9a |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.6 - Site left clean & tidy
label | c4781646-0e4e-50d8-aa8c-793fe2ebbf50 |  | note | VERIFICATION ACTIVITY - Visual check
label | be3d40ea-4fe0-55f8-a730-f323c0c52fa5 |  | note | FREQ. - After vacating site
label | 8879af58-c4fc-5518-9032-2a43503ba377 |  | note | ACCEPTANCE CRITERIA - Stockpiles removed; Plant removed; Litter cleared from site
label | 7760157f-9fcd-590e-8d23-788da849d24e |  | note | INSPECTORATE W/H - Type: - W
label | 29307781-4876-575e-abc4-97e966ccb935 |  | note | INSPECTORATE W/H - Description: - Invite NZTA to carry out joint site inspection to inspect site.
label | cf2ab0f4-f8d0-515f-93a5-368bd9ce7e26 |  | note | Responsible Person - Paving Supervisor
checkpoint-group |  |  | section | 5 - As Built Records
checkpoint-status |  |  | checkpoint | 5.1 - Collect asset data
label | 7eedf179-ca0a-5180-9f1f-d67cb0ba0466 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | d0a48c94-b355-5ec3-be40-ac8e8000829f |  | note | FREQ. - During construction
label | 0b14cb2d-3eb1-5d8d-b480-e95c8c13c08e |  | note | ACCEPTANCE CRITERIA - All relevant as built information collected.
label | eb1b264e-212f-5eb5-8b84-e24f4074d0e7 |  | note | INSPECTORATE W/H - Type: - W
label | a3424b6a-c626-57f3-9fbb-443e9a5bdae8 |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.2 - Enter asset data into RAMM and/or register(s)
label | 5f7a0017-dbb2-559b-b8c8-7ec7f4eb43c2 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | 259e008a-51ba-559e-8fca-76139ba20148 |  | note | METHODS OR REFERENCE - RAMM
label | 03a347ab-b396-52a9-97c3-d2bc60338148 |  | note | FREQ. - At completion of work.
label | 822c143f-b545-59fb-a0de-8ff06eb31096 |  | note | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.
label | ade21c7a-e6d3-5b47-9565-4805662defb8 |  | note | INSPECTORATE W/H - Type: - W
label | 432750d1-b9bf-5672-9be7-798709da3c25 |  | note | INSPECTORATE W/H - Description: - Data entered by 20th of follow month after month of completion
label | 97f4f905-6992-5141-a505-987317fd59ed |  | note | Responsible Person - Asset Information Manager
checkpoint-status |  |  | checkpoint | 5.3 - Construction Completion Report
label | 1505c849-c952-5c5c-a7f2-b6395fee950a |  | note | VERIFICATION ACTIVITY - Confirmation
label | 0113994b-42ce-5de2-9def-98f18c7e86ae |  | note | METHODS OR REFERENCE - Contract Specification
label | ca13c4a1-ed81-5de6-b913-acd9b747d691 |  | note | FREQ. - At completion of work.
label | dd2ac220-140c-5564-a4fb-76e0140c9980 |  | note | ACCEPTANCE CRITERIA - Checked and approved
label | 3d16203c-6c8f-5637-b4f3-a309ea2cdbb4 |  | note | INSPECTORATE W/H - Type: - W
label | b44e8fa3-6afc-567b-9232-4d6723ddf9a3 |  | note | INSPECTORATE W/H - Description: - Completed within two months after Paving Wearing Course
label | 694502e4-1b07-584b-9ddf-2c4d86eb326f |  | note | Responsible Person - Renewals Engineer/ Renewals Manager
checkpoint-no-status |  |  | checkpoint | Quality Assurance Close Out
text | c71e230c-069f-5dbf-a29f-ebd5fe48f474 |  | textbox | Quality Assurance Close Out by - Name:
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | ITP - CONOC Operations (Heavy and Light Maintenance) - Unsealed Pavement - Digout Repair | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy and Light Maintenance) - Unsealed Pavement - Digout Repair | 9b5334ba-8063-4de6-a07b-cbd24e317b7a
checkpoint-status |  |  | checkpoint | 1 - Prepare
label | 10e755db-4e5b-524c-832e-778acf56b6f5 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | e12e5104-a971-5cd9-9402-38ee897ab3c8 |  | note | Accept / Reject Criteria - As per specification
label | c582c978-1e25-55b8-94f0-46315a81fed2 |  | note | Frequency Of Inspection Or Test - In-process
label | c16081bb-cafd-58f7-a6b6-2a5dd5b46773 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP064
label | c2a4c3b5-440d-5e37-a715-f023abd697f2 |  | note | Records Required - NO
label | 572c1055-530d-5e7f-b942-f2942b9df29b |  | note | DOWNER ENGINEER - R
label | 7d00eaa7-ff57-5f5c-a5d8-2407d6233a63 |  | note | SUPERVISOR - R
label | 4f8e87d7-bac7-5360-9ff2-3c620e9b50cb |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Drainage
label | b09209ae-dfa7-5625-9a95-6de8db9cc070 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 8ab464c9-1d9b-5c90-96ad-28f5de445a91 |  | note | Accept / Reject Criteria - As per specification
label | 85384694-636b-52a8-a734-e3791a53a068 |  | note | Frequency Of Inspection Or Test - In-process
label | 1f01b800-8816-5f21-ad3a-dbbe90f7fc0d |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP064
label | c06b2f79-8d43-5d23-abaa-23a7b75ce43a |  | note | Records Required - NO
label | 3c3c55b5-918e-559c-9998-10c8c1f74709 |  | note | DOWNER ENGINEER - R
label | ecbf3bd6-c291-506e-9dc3-3a62340c2b40 |  | note | SUPERVISOR - R
label | 40896bdb-f68a-5e5a-9f10-b79fbc7d3c11 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Excavation
label | d7e74c4a-e773-5b14-a7f0-a26be4afbccd |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 9463f82e-6646-58c6-b057-88c37b09f9e5 |  | note | Accept / Reject Criteria - As per specification
label | 54260d62-6a9e-593b-a14b-f884810fd981 |  | note | Frequency Of Inspection Or Test - In-process
label | 73a836b2-926a-564d-9a23-78ad2def06f4 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP064
label | 468c33b5-93ca-5ecc-b949-9fa8e0d2a760 |  | note | Records Required - YES
label | c900dc8c-0ac3-5634-a35d-ffe18492d78d |  | note | DOWNER ENGINEER - W(10%)
label | 724df68b-bab3-5f0c-999f-84ff9cbd3919 |  | note | SUPERVISOR - R
label | 75963e16-7611-54a4-912c-dbf79dcbc7fd |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Filter Fabric
label | ebc5abe9-a72b-5909-8d1e-acfbfbc2bdb7 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | aacaa831-045c-5e0a-8026-ad1c67fcdc9d |  | note | Accept / Reject Criteria - As per specification
label | e453f488-71c4-5948-b04d-b05d78308c07 |  | note | Frequency Of Inspection Or Test - In-process
label | b1f5be18-a79e-5219-8691-9de4ef1d0c00 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP064
label | 87b3de47-9407-577a-8785-25cf6b7c92e0 |  | note | Records Required - YES
label | 09d85d80-0410-5191-b8e2-09c250fd1f2a |  | note | DOWNER ENGINEER - W(10%)
label | 6fd1d20c-5771-57fd-b0d1-e34a8fbc4ffd |  | note | SUPERVISOR - R
label | 3ba7f7e1-9153-5130-a0f3-20714bc70f10 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Subsoil Drainage
label | 2dee1a9e-8a02-595c-8153-db50601aad5a |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | ab0d3667-aabb-5dc2-84be-e2204ad15196 |  | note | Accept / Reject Criteria - As per specification
label | 23765001-a195-580a-b4b7-416f778dc5dc |  | note | Frequency Of Inspection Or Test - In-process
label | d8ee59fb-7436-5316-a687-274203672d37 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP064
label | 12cf1b63-018f-55cd-bdc4-e2d4a8c75857 |  | note | Records Required - YES
label | 433c49c1-f4bb-5ad6-8b92-01d92d64b032 |  | note | DOWNER ENGINEER - W(10%)
label | 5419083b-d9c9-5382-bcbb-e49c3774942b |  | note | SUPERVISOR - R
label | bfb13bd8-ed1f-590d-9a91-b128d7c050c6 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Backfill and Compaction
label | 28e70c20-045c-55b2-9206-7e7a94d8ddc8 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 2f1daed5-dc0b-550a-b4bf-de399a500bbb |  | note | Accept / Reject Criteria - As per specification
label | 3db40c8c-c5ed-5b64-9c0f-070566e75b84 |  | note | Frequency Of Inspection Or Test - In-process
label | 0e4068ef-1061-5878-98a2-98ccb22625ff |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP064
label | 7251319e-a997-50d5-946c-6ddf5e9a2cf7 |  | note | Records Required - YES
label | 3715b39e-c575-5505-aaf4-4c58fdb37417 |  | note | DOWNER ENGINEER - W(10%)
label | 77599c69-ccc4-55ec-b826-5e41a12af2ba |  | note | SUPERVISOR - R
label | d7bbb780-9375-5926-8449-ab83dcbe3705 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Running Course
label | 3265d4f6-9995-5de7-a741-1849cc937839 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 9df6c9e9-b47b-53a6-8e97-d6583ff78384 |  | note | Accept / Reject Criteria - As per specification
label | ee13716a-15bc-5039-888b-f8c0e21c611d |  | note | Frequency Of Inspection Or Test - In-process
label | 4831c562-e7a1-5096-90e7-093d72a53a5c |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP064
label | 2a244ceb-cbf1-53c3-b256-2530e6ca4286 |  | note | Records Required - NO
label | 6b44aa42-1e05-5589-a704-08240318579e |  | note | DOWNER ENGINEER - W(10%)
label | 7fcaaa96-2d34-52e8-b6b2-d90dec9ccae9 |  | note | SUPERVISOR - R
label | af861d4a-0251-5510-90fa-789b9e388acc |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Test and Check
label | c89baf19-3035-506b-b6d9-1b13c1809c72 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | c79892f5-a9d9-5d3f-95ed-d1eca9618e9e |  | note | Accept / Reject Criteria - As per specification
label | 6a0a3002-9873-53ba-be99-f122a8bd7b5c |  | note | Frequency Of Inspection Or Test - In-process
label | 22872ae1-decf-535c-aacf-9a4aea06c4bb |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP064
label | 8fae7969-1090-5502-85bb-12eaf93b40e1 |  | note | Records Required - YES
label | 4daea935-e7ac-59d0-8240-ead6797932fa |  | note | DOWNER ENGINEER - W(10%)
label | 946b725e-3e16-51ce-b5bd-224320c6360b |  | note | SUPERVISOR - R
label | d01fc305-fc06-5ca9-b712-aab2f117260a |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations - Install Subsoil Drain Corrugated Plastic Type | itp |  |  |  | Yes | ITP - CONOC Operations (General) - Install Subsoil Drain Corrugated Plastic Type | 9b690545-f0a1-4310-bb84-336714b26813
checkpoint-status |  |  | checkpoint | 1 - Design Principles
label | 301d0c03-91c7-5c47-ba31-28c43f4ef166 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 731e7014-8bdf-53a5-87fa-31206fc16e94 |  | note | Accept / Reject Criteria - As per specification
label | 7b8394a0-bf41-5a5c-9e90-08aef1a9817e |  | note | Frequency Of Inspection Or Test - In-process
label | 3aa1f456-a3fd-5c2f-ac7b-99a1eed6e91a |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP089
label | 2c8bfaf0-f94f-503f-932b-8ebb4fa8ccaa |  | note | Records Required - NO
label | 78e6c06a-c4fd-57ea-912a-ef4174ffbe38 |  | note | ENGINEER - R
label | 6c969573-50e7-5d07-a15f-3be7ea651961 |  | note | SUPERVISOR - R
label | 6666808c-2956-52b2-829c-8eb8ed8ef447 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Prepare the Site
label | 088ec198-b662-547a-b7d6-adf0a0faa6a3 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 8a8e76dd-5984-5538-bf85-a3d968983935 |  | note | Accept / Reject Criteria - As per specification
label | 04e7bf1d-9b41-5eff-adc0-1f553b9fe7b2 |  | note | Frequency Of Inspection Or Test - In-process
label | 4a62a799-76db-5e73-b9e3-ddffb4d0261d |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP089
label | acebd671-8bb1-5eec-9253-25430ad240b7 |  | note | Records Required - NO
label | bc8f7e07-d467-5f4b-b309-962a9e229e95 |  | note | ENGINEER - W(10%)
label | 38840513-57f7-54e4-bb89-21fa03393740 |  | note | SUPERVISOR - R
label | 26daa293-c559-59c5-90ef-ba954de588be |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Prepare Base
label | d508896d-ce84-5cc4-9d9c-e1795420e8b6 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | b95aceef-88dc-5f82-8c2d-99f0f054f32e |  | note | Accept / Reject Criteria - As per specification
label | 93b70aee-ca65-55e3-b8a7-568e0553fb05 |  | note | Frequency Of Inspection Or Test - In-process
label | 7d0edd45-e100-5144-8464-abffe2402a18 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP089
label | 6cafb214-5101-5343-879d-ce4cc4294476 |  | note | Records Required - NO
label | 30afb163-c09d-5e18-aa6e-b269809a405b |  | note | ENGINEER - W(10%)
label | 74de3445-9363-5f68-8f1a-51ecd4aa70ce |  | note | SUPERVISOR - R
label | 633d175a-aaa2-54ad-ab5b-80ac596852b3 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Lay Filter Fabric Wrap (if required)
label | 23132c65-49c7-5124-a4f4-66f4d4a83f0d |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | d277a918-ebfc-596f-9545-ae0e748a6d2f |  | note | Accept / Reject Criteria - As per specification
label | df992e58-582d-5e1c-b412-4426a23573ca |  | note | Frequency Of Inspection Or Test - In-process
label | 39352464-6b18-5a26-b7de-7b0da345eefa |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP089
label | cf5a54ac-e373-51fd-bc10-3b75a7faa736 |  | note | Records Required - NO
label | 7bf4ec47-3b77-56f5-af3d-6285da26cf3d |  | note | ENGINEER - W(10%)
label | f096e043-5068-5ac0-b60b-6d16457e31ef |  | note | SUPERVISOR - R
label | 143b4bf7-2a2b-59fd-9259-de1d4d223b59 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Lay Bedding Material
label | b632ed15-5637-5de4-b445-2d93d99d23d1 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | d4a32fe2-2dbe-5fa9-945d-2ee79dc6d2cd |  | note | Accept / Reject Criteria - As per specification
label | d03aba06-460d-56c0-b7f7-b421d701336a |  | note | Frequency Of Inspection Or Test - In-process
label | 6ab2323a-f910-5191-86b6-c753bb14b2f7 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP089
label | 94613ae9-b53a-5a19-abe8-0cbb747295b0 |  | note | Records Required - YES
label | c7abf135-9293-5df6-9f7b-3768ccd8838e |  | note | ENGINEER - W(10%)
label | a21389dd-4c76-548c-b983-73826aba870c |  | note | SUPERVISOR - R
label | b27f2053-ff02-5acb-9478-62f5000c94c1 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Lay Pipe
label | c919b074-c18c-5bb8-955f-ece93541204c |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | b373a06d-5586-5e7a-847a-c89e83a9a046 |  | note | Accept / Reject Criteria - As per specification
label | d329e7cc-2c57-5626-b608-a351c729fead |  | note | Frequency Of Inspection Or Test - In-process
label | e7d04bcd-5f5b-5cea-8eaf-16bb77c92b4d |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP089
label | 64e72d9c-f313-522b-8281-fccfae41fcbd |  | note | Records Required - YES
label | acab9382-0221-5a57-b4be-32c7a28664f8 |  | note | ENGINEER - W(10%)
label | 8c5f8ea5-9748-586f-95ed-60273db9dbd8 |  | note | SUPERVISOR - R
label | d968ff26-76a5-5163-9f62-522fb146056b |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Outlet Control
label | 55bc982a-2c9d-5f89-983b-ef275156fc38 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 6d5c7ad8-cc47-5602-9d28-4f7e65f6906a |  | note | Accept / Reject Criteria - As per specification
label | 27884b82-f665-5be6-bccf-2916faed3268 |  | note | Frequency Of Inspection Or Test - In-process
label | 8ad897b2-f776-568e-b649-c09955899053 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP089
label | 39251c11-3851-5061-9bcc-21930164ab5c |  | note | Records Required - NO
label | ecbc96b1-9260-5fc6-8b4b-ee71dcaf0073 |  | note | ENGINEER - W(10%)
label | 4cefb4c7-cf11-5a60-96a7-cdeccbeba015 |  | note | SUPERVISOR - R
label | b2cf117d-b860-5d51-a9e3-e38c5cc1d56a |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Test and Check
label | 8088c5e3-30bd-5773-85aa-cd0f214f3330 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | d2fea2bb-224d-5c46-baa2-8b6b9bea1551 |  | note | Accept / Reject Criteria - As per specification
label | a654f299-7fc0-5389-a556-abe1f409ad07 |  | note | Frequency Of Inspection Or Test - In-process
label | 8bf878af-6aae-5d06-bdbc-1252218a763d |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP089
label | db631fee-7922-59d9-b039-9a286d0c2c3e |  | note | Records Required - NO
label | a81952c4-85f2-51da-8ed1-233b2ca34534 |  | note | ENGINEER - W(10%)
label | ca027c2f-50c9-5cf4-90db-c37f5fc93fe7 |  | note | SUPERVISOR - R
label | 38ab09f3-cdfb-577e-8eb8-70386b92f219 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC NETWORK - Guardrail Repair Thriebeam Type with Steel 'I' Posts | itp |  |  |  | Yes | ITP - CONOC NETWORK - Guardrail Repair Thriebeam Type with Steel 'I' Posts | 9eb5648f-01c0-438c-928a-80d429a45f04
checkpoint-status |  |  | checkpoint | 1 - Prepare the Site
label | 1d94ea76-2a33-592c-81d0-fe2975ba5215 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 09402173-4543-5291-b8e0-ff81aef0d3d8 |  | note | Accept / Reject Criteria - As per Specification
label | 403f10f3-f3f2-5497-8dc8-e9e27264c9a7 |  | note | Frequency Of Inspection Or Test - In-process
label | 2b57154a-ce8d-5adf-9e6d-91ce076cdb67 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP142
label | 816fb9f1-434a-571c-8931-33d862d83696 |  | note | Records Required - NO
label | 47fc2aef-da46-528e-9ae2-e517c5216633 |  | note | ENGINEER - R
label | 746e802e-4002-5dc9-b307-1cb3a51f92ed |  | note | SUPERVISOR - R
label | d72c3fc8-28a1-57e7-99ae-ab8b978f477d |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Restore Rail
label | 54947daf-fb3d-5b5a-801c-710252976352 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 30c69f29-4e28-54d7-8a4d-84220ca38dd9 |  | note | Accept / Reject Criteria - As per Specification
label | 20ba4c20-348e-562a-95ff-1c99fb3fcfbd |  | note | Frequency Of Inspection Or Test - In-process
label | 96eba19e-feb6-53fb-a6ee-81c76be9a98e |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP142
label | 1574227f-2da4-57a8-afc9-d3412ed763c6 |  | note | Records Required - NO
label | 81234a89-ce8b-5b08-a4a9-0b65c329ecbe |  | note | ENGINEER - W(10%)
label | 035dc029-d084-5039-92ea-50ff93385d9e |  | note | SUPERVISOR - R
label | a4b63e1d-6046-5e7a-bc7c-3bcbf3f28bfd |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Restore Posts
label | a236e38c-b150-58e5-bb13-1df2b877b2f9 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 8f21540f-dd9b-5a3b-9b21-aee598d9db46 |  | note | Accept / Reject Criteria - As per Specification
label | 47d694ce-a812-59d0-8722-259702c8a14d |  | note | Frequency Of Inspection Or Test - In-process
label | 8d577683-bd94-5556-ac0c-4d08152787f5 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP142
label | 0a787376-9e3a-53f4-bd17-37050f34042b |  | note | Records Required - NO
label | 59418047-247d-5993-81e8-3befbc8f027f |  | note | ENGINEER - W(10%)
label | caa9835f-5466-5993-b6ee-951ad001f7b5 |  | note | SUPERVISOR - R
label | 9404589f-be97-5321-8d92-fa0a096245f1 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Installation of "modified block-outs" and "back-up plates"
label | 7a58ffdb-e066-5744-8472-b819c6237082 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 39a2c134-80e4-50f4-9e56-868d8516d420 |  | note | Accept / Reject Criteria - As per Specification
label | 7aaf4292-3777-5bb5-a036-fa7e37dfa31b |  | note | Frequency Of Inspection Or Test - In-process
label | 3e23fe3f-2fe1-5cae-b1a1-3f4f330d5c4f |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP142
label | f2b93d30-ca7d-5dd0-966f-68594dbf15cd |  | note | Records Required - YES
label | 454a4dcb-7591-5408-9b23-df168c49b2e6 |  | note | ENGINEER - W(10%)
label | 8a33c7db-7e63-5f97-844f-53bd018710b9 |  | note | SUPERVISOR - R
label | a5e5ec56-438b-55e9-a793-05595156ce77 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Finishing
label | 04e76b25-7f9a-56a5-a8eb-2fd0c1c0bbda |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 7e746e76-e08d-50e1-964d-435511cc961a |  | note | Accept / Reject Criteria - As per Specification
label | 12d062d4-416f-5b8a-b45c-524795949b42 |  | note | Frequency Of Inspection Or Test - In-process
label | f04c148d-0658-5c02-939f-89e3e2d1a776 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP142
label | 81e2bd69-116c-5ccb-9564-ed98a712d5ea |  | note | Records Required - YES
label | 398aa4c0-6a0e-514d-9ecb-38e443380fec |  | note | ENGINEER - W(10%)
label | 2be5ee5a-9573-57b1-8d24-e33475b5af2b |  | note | SUPERVISOR - R
label | 1fcbb1dc-47a6-5329-806c-494f748d5d6f |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Test and Check
label | 7aae9042-1ba4-5e8a-9f25-880f69eabe13 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | d0cac6f1-d360-5e57-87b4-60db5900d4e7 |  | note | Accept / Reject Criteria - As per Specification
label | 39d58cba-a908-5c67-8caa-0a6b63930437 |  | note | Frequency Of Inspection Or Test - In-process
label | a272b62d-207e-5066-a049-0e5ee9f76cb7 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP142
label | 9b6920e8-d4e5-5508-8c6c-0c76dbc55894 |  | note | Records Required - YES
label | 0c70be64-6aee-5977-957a-3f0e8e3e2a57 |  | note | ENGINEER - W(10%)
label | bc00dff8-0555-59aa-b2bb-1616d6cccb24 |  | note | SUPERVISOR - R
label | 8fc0bc75-3fe2-51f6-8f5f-7db67134d756 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations - Clearing Snow - Snow Plough Method | itp |  |  |  | Yes | ITP - CONOC Operations (General) - Clearing Snow - Snow Plough Method | a7247193-43ab-46e7-9d8f-80b27eef6ac0
checkpoint-status |  |  | checkpoint | 1 - Prepare
label | 41ffce07-7da0-50ca-950d-e13321233f0a |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 9b1cb1e4-4500-517b-a25b-6ecdb5fac939 |  | note | Accept / Reject Criteria - As per Specification
label | 9c0c8ca8-f5b6-5c87-9672-f5c5d88a3c41 |  | note | Frequency Of Inspection Or Test - In-process
label | 11bea039-8b57-5bb2-9571-d436760c7227 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP106
label | 4638ca99-0fb2-5f67-9eaa-7379c727ecef |  | note | Records Required - NO
label | 589484b4-db69-5e55-a2a5-69d1b75d71a6 |  | note | ENGINEER - R
label | 02431e24-dd3b-577a-aebc-47e5480de19b |  | note | SUPERVISOR - R
label | 0b9db55f-b70d-57b0-a13d-c862f6e7d6ab |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Operation
label | 61f8c779-087f-5fab-94c9-1344d56195ae |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | b47b6d1c-8dbc-5583-a984-f55fa4c99755 |  | note | Accept / Reject Criteria - As per Specification
label | 78ac2e7e-3680-5a4a-a2a1-9ec596d07680 |  | note | Frequency Of Inspection Or Test - In-process
label | 98ba0fbc-45ae-5462-af3b-d09323a41407 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP106
label | 248cec3e-15a5-56f2-971e-0073313b8b94 |  | note | Records Required - NO
label | 445ceb81-8834-545c-803b-77b7437231df |  | note | ENGINEER - W(10%)
label | 28863cec-ec00-57bd-874a-2ab3ee151122 |  | note | SUPERVISOR - R
label | a9921ddc-d50f-5cae-9f0e-2f27d2226af7 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Maintenance
label | 87cf372c-03ea-51c1-af37-48a938e1dcb9 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | c1b072a5-fdc7-5864-b158-dc09756075d9 |  | note | Accept / Reject Criteria - As per Specification
label | 7be91249-21e9-5d05-9b9e-536c150f4ccd |  | note | Frequency Of Inspection Or Test - In-process
label | 6de5f1e3-75c7-5243-a4bf-6e322a2a9492 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP106
label | 897852f4-21eb-52ae-adaa-513edebdfd28 |  | note | Records Required - NO
label | bc9e01a0-3d7e-5c42-a140-19a27369fc5c |  | note | ENGINEER - W(10%)
label | 30c98601-dc92-5630-abe9-3d828dbf2706 |  | note | SUPERVISOR - R
label | 3bc7996c-80cb-55f7-84d8-04f4ce8cce17 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Communication and Report
label | 770dfab6-12ab-5ee4-a6e3-12be382b530e |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 225bde02-c373-50db-a0d5-29fcf8d2e2ce |  | note | Accept / Reject Criteria - As per Specification
label | 57919181-62eb-5269-b170-034f39b2be1b |  | note | Frequency Of Inspection Or Test - In-process
label | 47dc1d86-641e-571c-b6c2-8975a4e7a757 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP106
label | c8e88256-1175-5cf4-93e1-8c95c21455c9 |  | note | Records Required - NO
label | 1d77ea02-2a8b-57aa-84d1-17b15f93002f |  | note | ENGINEER - W(10%)
label | 56071948-ac0c-5d62-a0e3-96607283ed43 |  | note | SUPERVISOR - R
label | d56aac3b-c51e-503a-8b48-394513650ab4 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Lay Bedding Material
label | c6159f35-163d-5e01-8188-a5ffd154de51 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | c713346d-3e51-50cf-8275-01871cda15b0 |  | note | Accept / Reject Criteria - As per Specification
label | 020ba84d-9941-5b56-b3e6-8a2cb36d1e43 |  | note | Frequency Of Inspection Or Test - In-process
label | 26f333ad-9771-5f1d-ba06-530e469bf673 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP106
label | ef69a309-2b71-509d-b3c9-9fe0ac140d54 |  | note | Records Required - YES
label | a004376e-277f-5d52-82f3-77313ddbcf6b |  | note | ENGINEER - W(10%)
label | 38c4e219-cdd6-53b0-9c62-c8f9ad793856 |  | note | SUPERVISOR - R
label | 454a6a31-1b17-5c37-8f52-7283abec9e8e |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Incident Report
label | 75a3b5a5-f100-5ea4-a77b-a69f14079443 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | acc18d08-ebd2-5abc-ab87-2b85642eace8 |  | note | Accept / Reject Criteria - As per Specification
label | e8845c60-9a1a-5076-89d0-480154ab92c7 |  | note | Frequency Of Inspection Or Test - In-process
label | f2dff327-bc92-5a84-a69b-869fc9056b61 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP106
label | 51abb333-f99b-5a8f-8bed-7a1f1015b89c |  | note | Records Required - YES
label | 6839c050-0cfc-51c8-94cf-c3e77fb91a41 |  | note | ENGINEER - W(10%)
label | f4429381-3780-526d-93fd-2f3d3e3e2f84 |  | note | SUPERVISOR - R
label | 2dbbc500-8aee-5966-92c5-54fd2c3dc739 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Test and Check
label | f9a60c8d-a351-584c-8323-f3097f48eea2 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | d44da74e-9fbb-5111-a414-b938fd121a60 |  | note | Accept / Reject Criteria - As per Specification
label | 07d965f0-9c7d-53ad-926b-71d531207ee4 |  | note | Frequency Of Inspection Or Test - In-process
label | e59916af-cd93-5ae9-8aba-39781b7cf7de |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP106
label | 828e3e8d-b1d3-5aeb-ad8e-716bef5357f4 |  | note | Records Required - YES
label | 6ce8b4d0-46ab-57f8-a327-dd1bb32f1fbe |  | note | ENGINEER - W(10%)
label | 85ae0550-dbd2-56c5-9d7d-85f20a826a93 |  | note | SUPERVISOR - R
label | 095b325b-8fe9-5143-b2be-a18619833021 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations (Heavy and Light Maintenance) - Construct a Sandbag Weir | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy and Light Maintenance) - Construct a Sandbag Weir | a777c79b-6194-4e6c-9ea4-81da72013fa2
checkpoint-status |  |  | checkpoint | 1 - Prepare the Site
label | 04273ec6-8d24-5740-a42f-2bb0fde47766 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 8e4da6ee-2548-52ce-9594-34fec2246306 |  | note | Accept / Reject Criteria - As per specification
label | 7fad7041-e949-5913-a257-84e41774bb5b |  | note | Frequency Of Inspection Or Test - In-process
label | 70498e5e-e943-5922-a00e-8f61fcae797e |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP081
label | 59078f63-e5df-50cb-a5ef-4b3df6863dff |  | note | Records Required - NO
label | 34424c85-3f1f-54e2-ac23-b78d7f7e6988 |  | note | DOWNER ENGINEER - R
label | 4ec195e1-27fa-5da1-acf0-770b5e5e4b71 |  | note | SUPERVISOR - R
label | 6bd7e313-bf0c-51fd-89a5-1c305ebb05ee |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Setting Out
label | 6b1a1ddb-24c2-5ef9-8ae5-4a0f1bea3d08 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | dcdd9558-4a98-55f2-b005-4a90af97f5dd |  | note | Accept / Reject Criteria - As per specification
label | f5489a82-7419-5540-9f4c-d3f0ebfd3de2 |  | note | Frequency Of Inspection Or Test - In-process
label | 489d8354-18a2-53ff-a855-90869bed07d8 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP081
label | 9631a408-c0cc-5518-9cb7-58f7126a82c9 |  | note | Records Required - NO
label | c8e67d3d-6914-5c16-8660-3ffe0bc16c24 |  | note | DOWNER ENGINEER - R
label | c0afbc8e-f6de-5597-9546-278bb47d2a02 |  | note | SUPERVISOR - R
label | 82fed93e-d3f3-5edd-a8ae-1d7eddc26457 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Prepare Base
label | 1f2ceeba-c67a-542a-9a45-3d57d26ddd4e |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | a27b162d-d2b6-5b88-9d49-d4c355381f42 |  | note | Accept / Reject Criteria - As per specification
label | cb32f112-1ed9-519f-bc70-1aa034836e6b |  | note | Frequency Of Inspection Or Test - In-process
label | 80ad8379-73fc-56df-8b80-274e89914ce2 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP081
label | 245b4593-feaa-5f93-94df-aca09af5cf36 |  | note | Records Required - NO
label | 23ab38fb-7eab-5f81-bed5-72a8686af16a |  | note | DOWNER ENGINEER - W(10%)
label | 8a0af8f2-5996-579a-bf25-692c0f29f4e4 |  | note | SUPERVISOR - R
label | cddc7578-fb92-58ec-be12-1948ec6f085c |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Sandbag Filling
label | 9258277a-c530-5788-8032-262f8a67988a |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | ce23d734-7b30-5636-99ca-8e6be37d88d1 |  | note | Accept / Reject Criteria - As per specification
label | 1eaa7812-95e5-5b06-9c42-56d41eeca4e1 |  | note | Frequency Of Inspection Or Test - In-process
label | 353cf4f1-4290-55ca-b50c-56c4a6982fc4 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP081
label | d62055bf-bdad-5ff9-baaa-209a1bc76ea8 |  | note | Records Required - NO
label | 20937448-e883-57dc-a633-06e4e667cb4b |  | note | DOWNER ENGINEER - W(10%)
label | 5c9b48bd-a8e7-5cd3-81c9-da4f716b23d2 |  | note | SUPERVISOR - R
label | f347c128-8083-5201-bf29-b0e1ff35079a |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Sandbag Placing
label | b5fabd4d-3e3d-5182-bc59-0fb731c096b0 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 9dc03b46-a0e8-5f78-a7cb-8dbf724fcaae |  | note | Accept / Reject Criteria - As per specification
label | 467f5b17-0186-5345-8b5a-4a1adfff480e |  | note | Frequency Of Inspection Or Test - In-process
label | c1a616f4-4d4d-51dd-b800-6a971efebcb3 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP081
label | acdd7981-f329-51d0-aa60-e3e506da1433 |  | note | Records Required - NO
label | a55ca5f9-52d7-540a-b3ca-2e594215b0fc |  | note | DOWNER ENGINEER - W(10%)
label | 93e72707-3cce-5442-a9bc-9fe8f9cd327a |  | note | SUPERVISOR - R
label | 69efe774-d3db-5d50-b49c-84b572b033d4 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Test and Check
label | 93a1650e-ec7e-5871-8983-0ff1dc12c869 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 01f956ee-71d0-50ff-9282-adb5d14f60ae |  | note | Accept / Reject Criteria - As per specification
label | c7c07046-a8be-5064-a09b-510263284a8c |  | note | Frequency Of Inspection Or Test - In-process
label | 8dbad87e-c9c6-5bba-b812-b246172a1bfb |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP081
label | ff771c5c-2eec-5b0d-98ed-0b1d03e94dde |  | note | Records Required - NO
label | a4968bd0-e9a3-5a45-836a-1c984eb65cb8 |  | note | DOWNER ENGINEER - W(10%)
label | bce5a7b6-56dc-58d9-87d8-6616206041ea |  | note | SUPERVISOR - R
label | 2c7cffa6-48f2-56a1-af05-d10f8ed822b0 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC NETWORK - Guard Rail W Type Install Rail and NUCOR Steel Posts | itp |  |  |  | Yes | ITP - CONOC NETWORK - Guard Rail W Type Install Rail and NUCOR Steel Posts | ad9d0e1d-ac76-4a7e-9786-a3f71eca9717
checkpoint-status |  |  | checkpoint | 1 - Prepare the Site
label | 112e9ec8-052d-5073-affe-7e088d39fac1 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 17c9b4b8-7a4e-57e3-862f-9e321823af5b |  | note | Accept / Reject Criteria - As per Specification
label | 0825c7b5-7656-56b7-917d-f7111d0c0a3d |  | note | Frequency Of Inspection Or Test - In-process
label | 8494bd3e-a0c0-5c05-b651-ddb8c23b2aaf |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP137
label | 8e84fb7e-55bf-5e43-b43a-f01247d4e887 |  | note | Records Required - NO
label | 76674e40-a01e-54ef-82f3-24e17168f9c0 |  | note | ENGINEER - R
label | a507d154-9c01-5f15-965d-773cee74a91a |  | note | SUPERVISOR - R
label | 08cb8dc4-c820-5ae9-bb91-878d0403c232 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Place Post
label | 1a7c7942-3f2e-5623-9511-6c1c44025304 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | d9b2956b-e016-5096-a825-a3d40911cb35 |  | note | Accept / Reject Criteria - As per Specification
label | 12736c9c-6faf-546c-82ec-a5e5c603e837 |  | note | Frequency Of Inspection Or Test - In-process
label | 142a389a-d75c-5e3f-ba9e-9bcbc95a4b2e |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP137
label | 41fb283b-7822-51ef-b220-83c9b3ea2152 |  | note | Records Required - NO
label | 9d1c0956-f0ff-55cd-91ca-570e6663bfe2 |  | note | ENGINEER - R
label | 3f7b6fbd-ddee-5922-828d-e05f077d04f7 |  | note | SUPERVISOR - R
label | 3f710610-de9d-51e2-915c-39cc0982b57d |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Erect Guardrail
label | 63d1f88f-a292-5867-80dc-31b888183580 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | a05b7481-5a17-56b1-b1a8-40dfaf08a87e |  | note | Accept / Reject Criteria - As per Specification
label | 3cc8c770-1468-54b0-9704-52d65a045941 |  | note | Frequency Of Inspection Or Test - In-process
label | d680a26c-871d-5850-a260-9614cad4ef2b |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP137
label | f0e82fd5-c540-5d48-bd80-05b60b28c2e0 |  | note | Records Required - NO
label | 48f5a957-6cc9-5d3d-b5d9-a974a0060230 |  | note | ENGINEER - W(10%)
label | ec9425e3-07a2-5452-9094-2c7597ddf1ed |  | note | SUPERVISOR - R
label | 01723d08-8812-5eff-97d8-c6bf7d875c49 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Attach Terminal End
label | 02b08c5b-82bf-5c0c-86c9-44f80e1664cf |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | de88e5a7-79a2-5084-9e24-1b8cc9948ef9 |  | note | Accept / Reject Criteria - As per Specification
label | b081aa1c-4a8c-5e4d-9de6-43d15731cdbe |  | note | Frequency Of Inspection Or Test - In-process
label | f87df022-6c81-58b2-9698-87c5bc64ed67 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP137
label | ff6088db-2917-571f-9bbc-1eaf4d96c065 |  | note | Records Required - NO
label | ce1b796d-cb5b-5e54-aa52-12864798e02b |  | note | ENGINEER - W(10%)
label | 91562368-ab9f-5bf3-8ba6-df60400fc33f |  | note | SUPERVISOR - R
label | 19758c65-5ee8-5169-acd1-44cced72d166 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Finishing
label | 426951ea-583a-5ea7-8841-62a319d792d1 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 994bc81d-4a9e-5cb9-b8f3-79ff0ffaa419 |  | note | Accept / Reject Criteria - As per Specification
label | fc005bc7-38de-599e-a637-5dc6a994b71e |  | note | Frequency Of Inspection Or Test - In-process
label | fd4af815-0d06-5375-9040-6cb56565da91 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP137
label | 9cdab08e-a8d2-5005-bbbb-f98ade6e4578 |  | note | Records Required - NO
label | 21f6ebaa-c423-5132-bdb8-faf29be7dd1f |  | note | ENGINEER - W(10%)
label | 03584175-5ed4-5254-a840-885fc049a165 |  | note | SUPERVISOR - R
label | 33767c5b-5e30-55f5-ae10-2b14826afb22 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Test and Check
label | 036fb283-ea40-58f4-ae0c-c4c6fbccad7e |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 673d1b54-e475-550e-baee-913dddea5b4e |  | note | Accept / Reject Criteria - As per Specification
label | 930238c3-9fa9-54c2-9c0a-7a9a6af79e15 |  | note | Frequency Of Inspection Or Test - In-process
label | 0c80d9c6-8346-5d47-8d49-d5263653615b |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP137
label | cc95a711-dd0d-5d82-9168-e51a91c1aa93 |  | note | Records Required - YES
label | 2c3bd007-2517-5177-a36f-eb94e21e9705 |  | note | ENGINEER - W(10%)
label | 78f4f88b-bbfe-5ac3-928b-5cf09fbe230e |  | note | SUPERVISOR - R
label | f297a762-0ab0-5271-982e-d2d422562529 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations - Clearing Snow - Excavator Loader Method | itp |  |  |  | Yes | ITP - CONOC Operations (General) - Clearing Snow - Excavator Loader Method | ae0751f9-f227-4a3b-b2c7-0c19ea302b63
checkpoint-status |  |  | checkpoint | 1 - Snow Clearance
label | 8b37934f-147a-50de-a096-7daa42890f44 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | cb0e32dc-4656-5507-b7fa-0931fa61626f |  | note | Accept / Reject Criteria - As per Specification
label | 22b02711-b9c5-5b25-9b45-85e255a6d104 |  | note | Frequency Of Inspection Or Test - In-process
label | f3e1c64b-337f-5393-9862-7319303fd802 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP107
label | da914a3a-bc92-5b67-bab8-7ac981098e09 |  | note | Records Required - NO
label | 050f16ca-ea9c-5504-9b07-126afbc95020 |  | note | ENGINEER - R
label | cbefa109-246c-5bbe-ba32-5e2775035290 |  | note | SUPERVISOR - R
label | 6c654b5c-24bb-5b7f-8ac3-c404e99812f4 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Prepare
label | e5e7bdab-fb07-52f8-84d9-18e70878d60c |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 1476a1bb-ea6a-5355-8f5f-1e406b2213d4 |  | note | Accept / Reject Criteria - As per Specification
label | 2bf4697c-c64e-5967-a52d-3181d8dc671a |  | note | Frequency Of Inspection Or Test - In-process
label | a15c04c5-9378-590a-83b8-9adb22dcfd8f |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP107
label | 155d7d86-4f1c-5ed6-8996-224791000a2c |  | note | Records Required - NO
label | 339bfc0c-0156-5c0d-b8a7-b059a14e0afb |  | note | ENGINEER - R
label | eb6907dc-5947-5dd9-843d-5b31502e3886 |  | note | SUPERVISOR - R
label | 176d9c4e-c620-5d50-b6fe-11e09a392599 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Operation
label | 5a356a51-e04f-56d4-9b4b-fefe82c81f12 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | c75c3af9-b57b-5691-b827-c7077c9f66f0 |  | note | Accept / Reject Criteria - As per Specification
label | ac14b8a7-b77f-5733-a358-7778caaf61f0 |  | note | Frequency Of Inspection Or Test - In-process
label | 93ab82d6-63df-5cdb-bb4d-2adfb12c3a24 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP107
label | 4f74da6d-53db-513a-aa5d-cef5465bdf60 |  | note | Records Required - NO
label | 3adcfb54-ae14-5151-b80f-ff6aaa3730bf |  | note | ENGINEER - W(10%)
label | 92962a8a-65bc-56fe-8625-1f975a21bdff |  | note | SUPERVISOR - R
label | 8fad33d1-8134-5a73-a0fa-62ebe81b9a64 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Maintenance
label | bd8a7e44-ad88-5716-b073-cde91b434181 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 6c39f3ac-a52d-5e52-8fe5-52d153e3aa03 |  | note | Accept / Reject Criteria - As per Specification
label | 7cdffa07-b7c9-5820-bd16-860fc8cecc93 |  | note | Frequency Of Inspection Or Test - In-process
label | e3d87ff5-0826-5cd9-a322-a3a9dde2baf2 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP107
label | 0bae069d-5962-5c8d-ad12-729fb1b0ad8c |  | note | Records Required - NO
label | a6b4bb6e-fea2-519e-8d34-1726b5eadb68 |  | note | ENGINEER - W(10%)
label | 9af8d2ac-129b-5f86-97af-3625c9655042 |  | note | SUPERVISOR - R
label | 656ebd55-b86b-50f1-acdf-78084c9bc022 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Communicate and Report
label | 26609f43-cd49-5e6b-939e-0c18af75d2cf |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 35f5f764-58ce-5d42-b712-a861b9aa4289 |  | note | Accept / Reject Criteria - As per Specification
label | 8beb9cba-5401-5972-ba6b-8ba00b50a991 |  | note | Frequency Of Inspection Or Test - In-process
label | e4c95837-9a3c-5d9b-b1cd-b0e854766fa4 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP107
label | de04839b-d8f1-5616-846a-0dd13a25e598 |  | note | Records Required - YES
label | ce7c5534-5595-507c-8ade-14a18a356376 |  | note | ENGINEER - W(10%)
label | ad621051-1ff6-5e2c-9ed3-fc68584424d6 |  | note | SUPERVISOR - R
label | 3bfa7097-b83d-51e1-9c7b-01f6926641fa |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Incident Reporting
label | 0151b2fd-81f7-56b4-a985-3c697113e6cd |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | feb18eb7-c4f9-571f-840d-4f1a3782d99a |  | note | Accept / Reject Criteria - As per Specification
label | 8932d886-7924-5de3-b940-9bb1d7e44e11 |  | note | Frequency Of Inspection Or Test - In-process
label | dff7f73d-c974-596a-8927-8cac8c6f0b93 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP107
label | 1bd33a7d-8c57-57bc-8a09-c29f4c814d4b |  | note | Records Required - YES
label | 086b1ada-bedc-5ddd-8033-9344df8d1294 |  | note | ENGINEER - W(10%)
label | 2a043de7-b354-5c71-b4e9-0a995e34d514 |  | note | SUPERVISOR - R
label | e5d64951-3f92-5330-a98f-bca9188ce416 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Test and Check
label | 1af5cef0-566e-5640-8615-453838d4e20c |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 582746ab-40d9-5cba-b1d3-f5019c9d1f16 |  | note | Accept / Reject Criteria - As per Specification
label | ab85e305-6e5a-585e-aae8-c31e927bbfac |  | note | Frequency Of Inspection Or Test - In-process
label | 72dee4c7-519c-5f96-8204-bbb0cd38ac6a |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP107
label | 04e92946-4c71-5827-9baf-19b73c7a2768 |  | note | Records Required - NO
label | 5346dcfa-b00b-5c71-a750-05fc1e462e6c |  | note | ENGINEER - W(10%)
label | de6cd065-7993-573c-84af-8b343b4f67a1 |  | note | SUPERVISOR - R
label | faf0a7e9-d369-5a65-acb9-0dfacd96adb6 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations - Grit - Application by Spreader | itp |  |  |  | Yes | ITP - CONOC Operations (General) - Grit - Application by Spreader | afec7b66-9515-4386-ab1a-12a1493bc234
checkpoint-status |  |  | checkpoint | 1 - Complete Pre-Start Check on the Vehicle
label | c34eddab-68ab-5941-ab98-59b06fcdf4a5 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 56d6e99a-f72d-5991-a386-031e175c3de0 |  | note | Accept / Reject Criteria - As per Specification
label | f2057357-90d6-56e6-bd6c-04e33fa05a07 |  | note | Frequency Of Inspection Or Test - In-process
label | d58270b1-4b05-55c9-bed8-41e5bec633e8 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP111
label | d81760ef-084b-51d5-839b-cde5cded99ad |  | note | Records Required - NO
label | e0e3e2db-60a8-54f0-a2a4-e77a29ef5b10 |  | note | ENGINEER - R
label | 0d1e383a-0c5c-55f2-92fb-a1a8cb05f1a2 |  | note | SUPERVISOR - R
label | d49ac3ab-55d9-56fe-a87d-3b1bbc9773bc |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Find Out
label | 5f9b4f80-8a9a-5ad8-bcfe-03d1758ea87d |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 9e43e5b3-4b93-5faf-9946-12a3bf04cfdc |  | note | Accept / Reject Criteria - As per Specification
label | 3c2f8d19-3196-5a62-aa8e-82653c4a6135 |  | note | Frequency Of Inspection Or Test - In-process
label | d0ee484b-abd6-545d-93c1-dd7ed3c6210b |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP111
label | c518fd15-969e-55e9-bac0-68889bfe85a2 |  | note | Records Required - NO
label | c0a3e9df-406c-584a-b87f-310d118cdefa |  | note | ENGINEER - R
label | e53dbbc1-32b6-5653-a9a9-5e7878273662 |  | note | SUPERVISOR - R
label | 8b6c3cf7-b63d-5020-93c4-7d606d007d7e |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Spreading Grit
label | 9d6cf7e8-45b1-5c7a-ab3e-3f04509600ab |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | b52184de-aacc-5607-9db2-5bdb1d92f190 |  | note | Accept / Reject Criteria - As per Specification
label | c3a8af15-0e2d-502e-8790-d5eb0b0f1d90 |  | note | Frequency Of Inspection Or Test - In-process
label | 8d7af81e-7d91-5453-ad3d-a2353e3506d7 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP111
label | 4da7210d-5f36-54c3-a78d-bee3dca2c28d |  | note | Records Required - NO
label | f71ce0fd-a078-504f-aa04-c1166803ea8e |  | note | ENGINEER - W(10%)
label | 9fa156a6-3541-50ab-aa57-5ddd0a75bbdb |  | note | SUPERVISOR - R
label | b01e3e5e-65e4-5d1d-bf95-82591dfee72e |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Preparation
label | f4f60948-caf7-51f0-9bbc-6dcb95072049 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 2e37d501-c82e-5b0a-8124-1ef1fee71404 |  | note | Accept / Reject Criteria - As per Specification
label | a1798b6b-6ee6-5492-8305-25c2937bf189 |  | note | Frequency Of Inspection Or Test - In-process
label | c8da05da-011d-5e27-b5a9-5e010e6fdf11 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP111
label | 2d15b1f2-e61f-50f7-a3aa-da938c751a3c |  | note | Records Required - NO
label | f6581809-f387-587e-99a9-b4beece2169b |  | note | ENGINEER - W(10%)
label | c0141fe8-259d-5164-a9f7-3d6b6fd4f150 |  | note | SUPERVISOR - R
label | 3166e811-d860-5687-b81f-1e12a9844545 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Sign Management
label | 0392d65a-2bb4-5f3f-bd0a-61e1b86c4fb7 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | fd83c767-8aa7-5110-9f06-31eeaa4f2eb8 |  | note | Accept / Reject Criteria - As per Specification
label | b361079d-d71e-5c81-9114-49de4602b594 |  | note | Frequency Of Inspection Or Test - In-process
label | ab267bea-f940-5592-994b-3cc72cc279ee |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP111
label | a243ba03-d92f-5df9-a096-91420665768d |  | note | Records Required - NO
label | 191b7649-be46-5565-b2bf-665df7c4cd09 |  | note | ENGINEER - W(10%)
label | cc2d8e82-c527-5e3c-b0c8-7eb48cb7ace8 |  | note | SUPERVISOR - R
label | 3025e82c-ca78-5145-a5cb-590180f9827e |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Operation
label | de2aa42f-a5a8-5866-9d4b-48168c773f31 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 6cd2760a-a9c7-505a-a526-14c1e1565dc3 |  | note | Accept / Reject Criteria - As per Specification
label | 0803cfe4-a253-549c-b493-d4d5bd358f27 |  | note | Frequency Of Inspection Or Test - In-process
label | 7f718b2e-04e0-5343-b11f-447988efaf9c |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP111
label | f5e93f47-a0ac-595f-9270-cc632c1ad8c5 |  | note | Records Required - NO
label | dcc5a40c-39ca-5c25-aeb1-c8d94a539415 |  | note | ENGINEER - W(10%)
label | ff632a44-9995-577c-a207-ce05a61e337d |  | note | SUPERVISOR - R
label | d55e018d-7c53-5c33-9e78-885ddd366503 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Periodic Maintenance
label | 648ee419-0e20-5287-95eb-76898b8af761 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 4737d89d-c2d6-5e65-97b8-a2a7937df136 |  | note | Accept / Reject Criteria - As per Specification
label | 0a4b441f-fe4e-51bc-9067-37d716f0d3b5 |  | note | Frequency Of Inspection Or Test - In-process
label | 9ebdc07a-b98e-5a88-aa76-f9868cc70628 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP111
label | d09a1bc3-a2b9-5d76-99a0-adb2d6936876 |  | note | Records Required - YES
label | 672f6c15-125d-51fb-b46f-0f58f49a53ad |  | note | ENGINEER - W(10%)
label | 59b2be7b-ef91-54da-bec7-6b0279ffef6b |  | note | SUPERVISOR - R
label | 55b7cca7-872a-5945-8484-6c228efcdea1 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Communication and Reporting
label | 2d29f5ef-7917-5bbc-b6d8-2534a7fb9270 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 5c56dfb2-7054-5101-b1fb-38cf7fe6457f |  | note | Accept / Reject Criteria - As per Specification
label | 634ce953-9454-5edf-803c-fcbcc7dced7e |  | note | Frequency Of Inspection Or Test - In-process
label | 1c7f5c87-4f45-505f-bbf6-894edc1b0c20 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP111
label | 97acef56-0a38-5657-b471-220082396113 |  | note | Records Required - NO
label | 66d46e67-1595-5547-82ca-f525b3a7a36a |  | note | ENGINEER - W(10%)
label | 37ba9d33-21a8-54f5-a7b4-8e1f11bf3885 |  | note | SUPERVISOR - R
label | a57b3946-b1aa-5b08-9fe5-476ada6afc13 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Incident Reporting
label | 9fe30641-7821-5fa9-ae1e-d373c9c83eb1 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | fbd0f51d-26c3-574e-9b97-ab3c0289ee4d |  | note | Accept / Reject Criteria - As per Specification
label | 32b1ea89-8e5d-5256-a44c-885ebaf885bb |  | note | Frequency Of Inspection Or Test - In-process
label | c8f8f50d-45c4-5643-b9ea-e8d39dc1a36f |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP111
label | 79f70337-72fe-5f2d-a581-3ffb49735c26 |  | note | Records Required - YES
label | 30fb98df-f554-5b1e-a854-d0e94da74c15 |  | note | ENGINEER - W(10%)
label | 144b7e5a-a1b1-586d-b72c-aa82043855ff |  | note | SUPERVISOR - R
label | b6854285-ed27-5775-99be-7a0663e26e86 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Test and Check
label | 336720f4-d50f-56fa-b3d8-974e244675c9 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | edc8a0e0-de13-5904-ba7d-101ad3d509bd |  | note | Accept / Reject Criteria - As per Specification
label | abd57711-507e-51e0-b39d-f39820a83412 |  | note | Frequency Of Inspection Or Test - In-process
label | 170f07bd-aad0-5f1e-bc4a-c9e9c01b3e97 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP111
label | 838753bf-377d-502e-99f1-f47c18a37d60 |  | note | Records Required - YES
label | 0861a74f-0c01-52e5-9528-0573233159cb |  | note | ENGINEER - W(10%)
label | e60c27b8-df79-5968-8efb-9992c1403634 |  | note | SUPERVISOR - R
label | 5358c3ad-6ca1-5b31-b01d-ee115895d827 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations (Heavy and Light Maintenance) - Install a Culvert Headwall Constructed of Dry Concrete Sand Bags | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy and Light Maintenance) - Install a Culvert Headwall Constructed of Dry Concrete Sand Bags | b046f9f5-fc4a-4b5e-a1d9-b907c81cc8e3
checkpoint-status |  |  | checkpoint | 1 - Prepare the Site
label | aca8827c-7840-5ef7-a9f1-9fc8524b6a72 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 7ddd9e63-3caa-5146-ab84-485f9ed780db |  | note | Accept / Reject Criteria - As per specification
label | 7759f1d4-2fb1-547f-9575-7d07524ee2c8 |  | note | Frequency Of Inspection Or Test - In-process
label | 984dd712-1376-5703-8144-2c13a076da69 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP083
label | 0b2eeb41-a51a-5fe1-ad2c-e18745646dbd |  | note | Records Required - NO
label | 7c0dee07-2de4-5445-9823-8baa4de045a4 |  | note | DOWNER ENGINEER - R
label | db1e08a5-f496-5b96-9747-8ef7d041c59c |  | note | SUPERVISOR - R
label | 3328176f-527f-51ea-bed2-1628660dc214 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Setting Out
label | 44e80547-bf9b-5297-8008-e6e7bbe9222a |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | a23386bf-39e8-573f-b0e0-1b86d3666f31 |  | note | Accept / Reject Criteria - As per specification
label | 5f3dcfa9-c86f-5cac-99a4-197b462e0d14 |  | note | Frequency Of Inspection Or Test - In-process
label | 04ba976a-e0ca-55db-8584-3e4847ac7290 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP083
label | 1fe5508d-f064-5ada-9ea1-f00f7e20d271 |  | note | Records Required - NO
label | 83dad45f-c9e7-52fc-9529-9a9a83966907 |  | note | DOWNER ENGINEER - R
label | 300dba7c-16a8-539f-8268-619e0ece8843 |  | note | SUPERVISOR - R
label | b766a664-092f-5b7f-816d-a8741f210e36 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Prepare Base
label | 5b66c4fc-d68a-5f1f-9d1a-3ff914a80118 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | abb10e15-3b6a-5d60-b259-fde9da906b83 |  | note | Accept / Reject Criteria - As per specification
label | a24981cb-84d0-5420-a9fd-03848992c5bd |  | note | Frequency Of Inspection Or Test - In-process
label | 33b4f1b6-3a99-5d38-84f3-ab37c333286d |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP083
label | 2ee43ea6-129d-5334-975c-f3d5a55032ed |  | note | Records Required - NO
label | f509eb22-8fd4-54b4-b55f-d4531a1bc3b3 |  | note | DOWNER ENGINEER - W(10%)
label | f8e4bf2b-0790-5dd0-bf54-28baad695557 |  | note | SUPERVISOR - R
label | dca47c47-3975-5c06-84f9-c8ac13c34266 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Fill Sandbags
label | 9c8d2097-7b3f-5b83-8b91-73c54bdec470 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 826810ce-6471-5a67-a525-be70b7b37eab |  | note | Accept / Reject Criteria - As per specification
label | f46f2bfb-99b2-53ae-b5ac-744c8b9cc7ba |  | note | Frequency Of Inspection Or Test - In-process
label | 592bcc4c-573c-5c61-aff4-4d4f1cfddf13 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP083
label | c55af432-11af-5a1f-88ec-a5556266e31a |  | note | Records Required - NO
label | 77448662-e2f9-5e19-bb4f-ad2a5f919a93 |  | note | DOWNER ENGINEER - W(10%)
label | 922b73d3-8999-5164-8afb-5caf74a11250 |  | note | SUPERVISOR - R
label | 60ce7475-bc1a-599c-9c8a-7002f400de43 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Place Sandbags
label | 98515a2b-bfb7-50f4-93cd-47661fe0f575 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 32c072c7-1af5-5ee0-9802-99ec948ede57 |  | note | Accept / Reject Criteria - As per specification
label | d63f1017-8d38-54c8-a7cd-8b6ada1313e3 |  | note | Frequency Of Inspection Or Test - In-process
label | c5f5f59d-fd75-574b-9b15-365be7703a91 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP083
label | bb092046-1c38-5c4f-8f54-e87c8affff93 |  | note | Records Required - NO
label | c08fc3e9-85e6-5c62-b394-bd16f79b2c14 |  | note | DOWNER ENGINEER - W(10%)
label | 68a4a1f7-58c6-5d8f-8211-f73cc19b4e32 |  | note | SUPERVISOR - R
label | b260a6dc-0288-548f-b2ef-f590431d0a3f |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Sight Rail
label | aa638d55-22d3-5379-a6c8-494c776a603b |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 110a9505-663b-58a4-9091-b727cab7bb5b |  | note | Accept / Reject Criteria - As per specification
label | c4372cd0-4ee0-53a1-bbf4-0edbd2b80a4b |  | note | Frequency Of Inspection Or Test - In-process
label | 0075010a-37d0-5b95-b9f0-76f9fe8adb9d |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP083
label | bbc64576-1c67-500e-9166-b59c466aed29 |  | note | Records Required - NO
label | 9231d26f-806c-5113-8ac9-d713494621e7 |  | note | DOWNER ENGINEER - W(10%)
label | 0e8738b6-917d-5829-b731-858cdad89b20 |  | note | SUPERVISOR - R
label | 81369c31-8ae7-55c6-866b-4043d5fc253f |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Test and Check
label | de4a1fd7-1679-52e6-9e58-c2f4e5cc7b5b |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | d2f76c39-6d65-597b-bc85-498fd159360e |  | note | Accept / Reject Criteria - As per specification
label | b5e0e7df-ecfd-53cb-a43b-4b4ef6a2043d |  | note | Frequency Of Inspection Or Test - In-process
label | 5c88b1f0-cdd0-573f-a98e-3813a4808977 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP083
label | 14f64503-5007-59d3-b75e-6154df0f21f1 |  | note | Records Required - NO
label | 5944d205-e625-548e-99e3-6911b4fcda4e |  | note | DOWNER ENGINEER - W(10%)
label | 8505ad74-b960-55ee-8068-1e31cf7a9366 |  | note | SUPERVISOR - R
label | be02e597-9452-5d75-a9f2-f7d08969f065 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC NETWORK - Sealed Pavement Repair - Digout | itp |  |  |  | Yes | ITP - CONOC NETWORK - Sealed Pavement Repair - Digout | b4ec67c6-1063-4b41-b1cc-a67d904af9e2
checkpoint-status |  |  | checkpoint | 1 - Preparation
label | be2aff45-c317-5859-9b1d-67d8ab973a50 |  | note | Controlled By : (Position) - Sub Supervisor/Downer Engineer
label | d7f66db8-79be-54b5-9c5d-0b8623428c79 |  | note | Accept / Reject Criteria - GAP=DEPTH/1.5
label | 889797fa-f3f2-584e-9144-7f9fb4fcf67c |  | note | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | c269a037-49a8-547f-8700-a772f8074ef3 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP030/Ground Distrubance Permit
label | 95e7703d-13af-5587-bad4-68bb6624a93d |  | note | Records Required - NO
label | 6f98a75c-3a86-5ed9-81fa-de9b22feec26 |  | note | ENGINEER - W(10%)
label | ac456b20-e809-5f7d-9b18-233bfbf252dd |  | note | SUPERVISOR - R
label | b3298fa8-3b85-50e3-9a85-6f971f2455bd |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Excavation
label | a966246d-0263-50eb-ac2d-0a181fee57a6 |  | note | Controlled By : (Position) - Sub Supervisor/Downer Engineer
label | 047fc3c9-7fa2-5f9e-b92a-8ea22d746f98 |  | note | Accept / Reject Criteria - The bottom of the digout should match slope of the pavement surface
label | 491b039b-bd3a-5802-a3c8-ffa42f8351b6 |  | note | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | 92a56656-42c8-511a-a336-5e785092ff28 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP030
label | 55185dc7-9396-570e-951e-3fe59d7a5b88 |  | note | Records Required - YES
label | 835420f4-4639-50e2-a699-458f1b4cb962 |  | note | ENGINEER - YES
label | 53a0c613-7aeb-5495-ab85-c3ac15997a54 |  | note | SUPERVISOR - R
label | 60768ab3-996b-5ef8-9e90-6d74de7fed40 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Checking the base (Scala Test)
label | 7f3daa6d-4ede-5fff-9ac7-7886e2e924c6 |  | note | Controlled By : (Position) - Sub Supervisor/Downer Engineer
label | 52fe13da-b347-5b3f-ac80-2c446729425f |  | note | Accept / Reject Criteria - Base is strong enough to safely carry the load
label | 76ad6be6-db0c-5a30-82c2-cc67ebadf8d7 |  | note | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | 96c24f73-1537-5a72-93e3-30b8dea83aac |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP030/Scala Log
label | 9399daa5-dd63-5b3b-84b9-553186929672 |  | note | Records Required - YES
label | c9782896-cd3b-5b2b-b575-d6dece3e684d |  | note | ENGINEER - W
label | cb7423bd-b9ce-5b36-9516-8aad4ec776d1 |  | note | SUPERVISOR - W(10%)
label | f8ba5161-ccf8-5b3f-8b78-8f8839195db4 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Filter Fabric
label | 171ae7dc-f761-5c0c-a19a-2ce14e0f76b0 |  | note | Controlled By : (Position) - Sub Supervisor/Downer Engineer
label | 78c699e7-809e-56d2-903f-3bfe3e0f3a68 |  | note | Accept / Reject Criteria - Lay the fabric when Subgrade reached
label | 2f709c2c-e6e2-59f9-bc06-d4a900104392 |  | note | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | be113733-f8f5-5c67-a476-2c4ef210984a |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP030
label | bd1c7374-2fee-5658-bed6-5c49f223dedb |  | note | Records Required - YES
label | f898a451-bb4e-5995-ae5d-4ef44ee3db80 |  | note | ENGINEER - W(10%)
label | 3ebf00aa-f066-551d-8a84-13c7df6fbe1b |  | note | SUPERVISOR - R
label | d19bab99-5efd-5c97-b2f0-572b9b7cba7b |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Subsoil Drainage
label | e28c1cab-40e4-549b-b4a0-6ececfb7f2f1 |  | note | Controlled By : (Position) - Sub Supervisor/Downer Engineer
label | 017682ca-2f03-549c-a2db-f6e56df3cff3 |  | note | Accept / Reject Criteria - Refer GP089
label | 80d6ae8c-ff9e-5739-9d55-145a68ec1745 |  | note | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | e7f1adc1-9df2-51fa-a8d9-2371b9fcedb9 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP030
label | 5103160f-2a84-5913-96ea-84ead76d0e50 |  | note | Records Required - YES
label | c0bb12c1-f46f-5509-862f-9440d1695c3a |  | note | ENGINEER - W(10%)
label | c2c9f413-1e87-569a-8db2-ac9a9320a3d3 |  | note | SUPERVISOR - R
label | 8ecb087d-4dd9-5d52-ae89-f10420566f5f |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Backfill and Compact (Clegg Hammer Reading)
label | 07ce672e-c40d-5271-9572-330117c3442c |  | note | Controlled By : (Position) - Sub Supervisor/Downer Engineer
label | 0634f389-ce55-5ac6-a7f0-a39a43ea2c76 |  | note | Accept / Reject Criteria - Atleast 35 CIV
label | a81ffcdc-895e-565e-8e15-cae0154839c5 |  | note | Frequency Of Inspection Or Test - After every 1m
label | fa0c78d3-f4d3-5ed9-841a-713063de8e15 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP030/Clegg Log
label | fed45c31-2a47-5c2d-8fa0-d59f52d64301 |  | note | Records Required - YES
label | 6b63b977-9839-5b9f-a51c-404be4aacc6f |  | note | ENGINEER - W
label | 000b7ccc-aea0-599e-b33a-c4af7a790dc6 |  | note | SUPERVISOR - W(10%)
label | 8c8d1f80-d291-5495-a7fd-3ad0ae7dc5bc |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Final shape and Trim
label | 79b38781-a226-571a-8687-7055e478e139 |  | note | Controlled By : (Position) - Sub Supervisor/Downer Engineer
label | cc21462c-b42b-512f-a503-57ce3dfeba14 |  | note | Accept / Reject Criteria - Shape and trim the repair to prsent a tidy apperance
label | 731cd1d3-d573-5db6-8a7d-4221fee673bc |  | note | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | 84250400-d0f1-55e7-989e-f811cc698dd4 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP030
label | a702489c-776a-54e6-baa1-525b335c30cd |  | note | Records Required - NO
label | d18acc49-9281-5e37-a52b-4c65f00ed9eb |  | note | ENGINEER - W(10%)
label | e43ec166-a7d8-54b9-9a33-d0b3818cdd8a |  | note | SUPERVISOR - R
label | d763d9cd-0624-5a43-bd27-0171428cada8 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Surfacing
label | 048bc701-42ac-5430-bc38-e48474618fcb |  | note | Controlled By : (Position) - Sub Supervisor/Downer Engineer
label | 8ef48d4e-c127-584e-9ca5-032c5b367302 |  | note | Accept / Reject Criteria - Chip Seal refer GP047/Premix refer GP041
label | 77bd4088-08d5-5d25-b124-ccca67f23fc0 |  | note | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | 0e936517-1e1e-520a-89bb-93a9cc07dd4b |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP030
label | 6d8f0c73-ebf0-5b6a-9e76-bb02598e7ba1 |  | note | Records Required - YES
label | c95c9e6c-cbb5-588b-ae7b-1217489ee2d4 |  | note | ENGINEER - W(10%)
label | 638431dd-15f2-55d8-bbb3-84fbd9af7020 |  | note | SUPERVISOR - R
label | be61d4a4-54af-55d5-b266-6ff706c9f59d |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Test and Check
label | dde751ff-f723-5013-a3a5-ffb4955f6867 |  | note | Controlled By : (Position) - Sub Supervisor/Downer Engineer
label | 62e542d5-b50d-59d6-9246-42be33775c7e |  | note | Accept / Reject Criteria - No more than 6mm depression with 2 meter straight edge
label | 7be1b844-90fd-550d-9cbf-7f23ec0b93a7 |  | note | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | 7b2def57-da29-5a2a-a1ec-d56ba36a8a26 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP030
label | 6e3b126c-b4f3-551b-8142-7c868d9a6aa0 |  | note | Records Required - NO
label | a4aca7ab-618b-5e5c-948b-11225e24b8d3 |  | note | ENGINEER - W(10%)
label | 10db7044-3aef-5a74-8cb5-e327f68c69f1 |  | note | SUPERVISOR - R
label | 6d1bd1e0-fca0-5892-ac73-a8c14138542a |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC NETWORK - Fabric Seal | itp |  |  |  | Yes | ITP - CONOC NETWORK - Fabric Seal | b51592dc-17ea-4053-82c2-67d03cf135fb
checkpoint-status |  |  | checkpoint | 1 - Prepare the site
label | e2295d69-260a-5054-82d1-66f53e91c2fb |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 090d19a1-2b52-57db-9709-fc707216b023 |  | note | Accept / Reject Criteria - As per specification
label | cd186700-38d5-5e88-8e64-ca249c5a35cb |  | note | Frequency Of Inspection Or Test - In-process
label | 19e0d3fb-0f49-53cb-84ea-bc7ea65fef14 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP046/Ground Distrubance Permit
label | a0c6a4cd-2854-5257-ad14-ea764054ad47 |  | note | Records Required - YES
label | 0843f16b-e4c4-515d-af0e-ff4e499802de |  | note | ENGINEER - R
label | 9c6f3cdd-ace9-5fc7-b9c3-104fddfe8eaf |  | note | SUPERVISOR - R
label | 3627373f-00a2-54f7-98d9-7de4fcc99b7e |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Prepare the surface
label | 762d34c7-6234-5d12-ab12-10944dd1a81b |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | f44aa6b7-6c73-58f3-91e0-d0a10a599a0a |  | note | Accept / Reject Criteria - As per specification
label | 499b308c-6bbe-5c0f-abab-0ee15a177d86 |  | note | Frequency Of Inspection Or Test - In-process
label | 1d1eac96-4928-523e-9e43-dbcf36d987ee |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP046
label | 273e3118-fd05-5713-9af9-f21df4d4c540 |  | note | Records Required - YES
label | 0c3413c4-1030-538a-8d88-ebf908f00a91 |  | note | ENGINEER - W(10%)
label | d4969254-fd0f-580a-928a-d736153f0bf6 |  | note | SUPERVISOR - R
label | 366d36b3-9a40-5ceb-a41e-94e8ae24f12a |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Lay the Fabric
label | 2e1cac33-5888-5c85-be87-aad0d7246252 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 2364df98-7f23-5a62-bce2-b49cc4a3f38d |  | note | Accept / Reject Criteria - As per specification
label | faab7f89-4a43-5af8-ad0e-6e6a4e6ec327 |  | note | Frequency Of Inspection Or Test - In-process
label | ca92af52-afb5-5cb5-b1fd-34aa79f9d2eb |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP046
label | ddfcb064-21f2-5745-b665-fcfa1979e248 |  | note | Records Required - YES
label | b0567e00-615f-5e49-b919-89e1b35218e9 |  | note | ENGINEER - W(10%)
label | 85384df7-229f-518a-a77e-da4bb70b00da |  | note | SUPERVISOR - R
label | bfc03014-8608-5c05-8c1d-a3d507ca1b87 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Two Coat Seal
label | 6a34f977-0e64-5c4a-9e8e-294769f2d16b |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | eed534a6-6899-51a6-a27c-5921389a7592 |  | note | Accept / Reject Criteria - As per specification
label | 5cb5a226-797c-5062-a421-ea8702a581ca |  | note | Frequency Of Inspection Or Test - In-process
label | 276f68a2-850e-5795-b946-8bb84d79788a |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP046
label | b9120674-94e9-565f-aea3-074ee29af5b3 |  | note | Records Required - YES
label | 4b768c8c-6268-5b65-9ebd-9578aee12b45 |  | note | ENGINEER - W(10%)
label | 6be57268-71f7-514e-a7c8-1fdeb3c0ebb4 |  | note | SUPERVISOR - R
label | 8cfb5724-8b8f-5d16-925e-f4a8bcfc17f4 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Site Monitoring
label | 99f47c3d-82a8-528a-a432-113f83889467 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 98a4d71c-aabe-567a-9fe9-b7661febf248 |  | note | Accept / Reject Criteria - As per specification
label | ce64e048-6c62-529b-9539-31b1cb035656 |  | note | Frequency Of Inspection Or Test - In-process
label | 91034866-1f7e-53cd-83e4-c1acf2dde3af |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP046
label | 80b717ca-c9fe-548e-b874-7d6055d512b2 |  | note | Records Required - YES
label | 5103e8a8-f8c7-5578-b4c0-2f2ba3e84836 |  | note | ENGINEER - W(10%)
label | 29422a9b-6316-58f2-b7fb-53dedf02549d |  | note | SUPERVISOR - R
label | 78ebe880-5793-51a3-acc0-544b4497393c |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Sweeping and Marking
label | d689a95f-a9ff-5f21-ba23-c17db1673058 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 956af37b-b193-5bef-af21-d3c030bfac89 |  | note | Accept / Reject Criteria - As per specification
label | 1d338a8a-4001-5fe4-9459-c347e76c744d |  | note | Frequency Of Inspection Or Test - In-process
label | 7bd3fce2-bdf6-5bb1-982c-1cd6b5b22e06 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP046
label | 6a469a3d-b4f8-572b-9109-186fef186dba |  | note | Records Required - YES
label | 0daf8914-d390-5ed4-a509-518d4e9dd920 |  | note | ENGINEER - W(10%)
label | d620d802-eefa-5020-8f49-f2c1ecfc3515 |  | note | SUPERVISOR - R
label | 329841c5-d5bd-590d-8de9-604a526ccc43 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Test and Check
label | c510c652-0989-5d2f-8ea6-887de61dbdb8 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 4ecfc286-a54a-5e0a-85d5-795e5a418f93 |  | note | Accept / Reject Criteria - As per specification
label | 34df5e26-5abf-59e8-b28d-381f305c8d92 |  | note | Frequency Of Inspection Or Test - In-process
label | 058579b3-d288-5313-bf73-df9ce931db11 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP046
label | 9b0448f5-c16f-5571-9740-4382cf3e55ac |  | note | Records Required - NO
label | 6a792fbb-c2cc-5061-aa57-dffe3fbaac96 |  | note | ENGINEER - W(10%)
label | 09a687e4-e024-5e09-834e-651f15922a75 |  | note | SUPERVISOR - R
label | 1b6d986b-0d7a-5333-b1c0-014c617a20e0 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC NETWORK - Guard Rail W Type Repair Section of Rail and NUCOR Steel Posts | itp |  |  |  | Yes | ITP - CONOC NETWORK - Guard Rail W Type Repair Section of Rail and NUCOR Steel Posts | b70126a8-2760-470c-ab19-e242594a5953
checkpoint-status |  |  | checkpoint | 1 - Prepare the Site
label | 5a89eb9f-cada-5fa6-a46e-fb990911d148 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 33010247-7c9c-515f-ae83-b4030db0b3cc |  | note | Accept / Reject Criteria - As per Specification
label | 9915d0b4-51a9-5dc5-83f9-33d91df1f630 |  | note | Frequency Of Inspection Or Test - In-process
label | 1f11bdcb-499b-5f99-9c06-37125b5ee63b |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP139
label | 1862253d-20bd-56ec-9568-e3c5d00e39d8 |  | note | Records Required - NO
label | bf3ceabf-bfb8-571d-a6df-7d587fb18ab2 |  | note | ENGINEER - R
label | 8a5dbea3-c48c-5c64-b321-e3221a55f3fa |  | note | SUPERVISOR - R
label | 0bad320b-64e0-59d1-8fd3-07f1a601de7a |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Assemble Rails
label | bba6f4fe-4b52-54e8-a8e2-f3d1d322a8d8 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 2a358192-8af7-50e2-958f-75a97597b21e |  | note | Accept / Reject Criteria - As per Specification
label | 2e83fc18-f1b7-5221-b466-31f26a496d92 |  | note | Frequency Of Inspection Or Test - In-process
label | 2774a0a3-abe7-57e2-a152-b31bf87494be |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP139
label | 70c20ce2-6f94-592f-9b5f-b93ebd378d3d |  | note | Records Required - NO
label | 3cb39c8e-aa13-5eb4-9034-d82573c9088f |  | note | ENGINEER - W(10%)
label | f662390e-281b-51ef-8077-1cbac9f364c5 |  | note | SUPERVISOR - R
label | 9126170b-8b03-548c-b021-72e9d830d8ad |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Install Posts
label | 018ffe72-4f2e-54d5-b80b-93f672620a2b |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | b582c148-8587-5135-ba28-f3769fd6a3a2 |  | note | Accept / Reject Criteria - As per Specification
label | cf629c69-45fb-574c-8ec8-f237cd601fe7 |  | note | Frequency Of Inspection Or Test - In-process
label | 9efb5750-5479-5632-adea-41906b5c1795 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP139
label | d313fa82-ecbe-5d0f-a09a-4d54ca2cf776 |  | note | Records Required - NO
label | 0bbf14ad-66be-5c89-b85c-c34add280f20 |  | note | ENGINEER - W(10%)
label | 90a0e83e-b7f4-545f-8753-ba2b0e7bf1d3 |  | note | SUPERVISOR - R
label | d2319ea8-47f7-5ed2-b199-70b6bb58b50e |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Finishing
label | 46989862-d2aa-5362-8e30-ab02f652147a |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | a19afe44-9ffe-52af-9eaa-db81c152cc29 |  | note | Accept / Reject Criteria - As per Specification
label | b98139ae-1db4-5e27-8225-c1cc6acb274b |  | note | Frequency Of Inspection Or Test - In-process
label | 206ea7a0-caa0-5d8f-bc36-76f8fd565462 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP139
label | ce0b06ea-95ea-5b3b-969b-a3d641621471 |  | note | Records Required - NO
label | 9af08e51-0767-51f8-8f48-3318f67b03f7 |  | note | ENGINEER - W(10%)
label | 73f1428d-c7af-53ff-b100-4cf4a2057bb4 |  | note | SUPERVISOR - R
label | 53554a30-c938-5af6-9aaa-51dd0e2d7b9b |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Test and Check
label | 77e1b432-c005-558a-bc1f-98c4e957c6d6 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | a3d2588f-06cc-5fbb-b4cb-70a65551ef15 |  | note | Accept / Reject Criteria - As per Specification
label | 16700760-aa71-57b0-bdfd-973b211a067e |  | note | Frequency Of Inspection Or Test - In-process
label | e6cc8981-b8fc-59bb-8dc4-a66de09236ed |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP139
label | 5bc2e936-d735-592e-92c5-b6c3503ee424 |  | note | Records Required - YES
label | 7e2543a3-7162-5c8f-93e8-81e3e46d8144 |  | note | ENGINEER - W(10%)
label | 29ab7d35-e982-578b-928c-2811a3b34b73 |  | note | SUPERVISOR - R
label | 00d920d6-1187-554b-8fb3-92f590e07691 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations - Repair Broken Kerb and Channel – Pre-cast Block | itp |  |  |  | Yes | ITP - CONOC Operations (General) - Repair Broken Kerb and Channel – Pre-cast Block | b9797841-cdf3-4363-a59c-fb30c642e976
checkpoint-status |  |  | checkpoint | 1 - Prepare
label | b9cc3729-31b8-5ee7-9111-4ee605c658af |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 9761a9d9-f8b3-5a1a-9a45-f32a89e688af |  | note | Accept / Reject Criteria - As per specification
label | ea7f5482-51c0-51de-9637-65c1d0ac81a2 |  | note | Frequency Of Inspection Or Test - In-process
label | e087c3ab-5ef6-5333-9575-1d3e4cbc5d58 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP093
label | 09214c49-d812-55fd-bc69-d2d3611aa0f5 |  | note | Records Required - NO
label | 111e40a0-ea9b-53ab-ba17-11e69f8c9ddf |  | note | ENGINEER - R
label | f81f5007-0664-5f90-b99d-8adb5daececd |  | note | SUPERVISOR - R
label | 75c1c4dc-00d6-5775-b87c-e366f280adc1 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Excavation
label | 175a8a79-5d59-5383-93dc-d45363cdee35 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | bc8aa6e0-3144-5d58-af69-0fcaa0243aa2 |  | note | Accept / Reject Criteria - As per specification
label | 4508934e-63e1-5e55-893e-e680359bda7e |  | note | Frequency Of Inspection Or Test - In-process
label | 4ce39c47-4fe4-51b5-9c72-33190dc35ed8 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP093
label | 93268f4b-5bee-5823-8694-5229a88519d2 |  | note | Records Required - NO
label | 308e84c3-6df9-5268-b6ff-3f7a13a6dbf7 |  | note | ENGINEER - R
label | 021cfed5-15f1-521f-8f5c-83006934568d |  | note | SUPERVISOR - R
label | daabf9f4-65d4-57fb-977a-10d2f92be103 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Base Construction
label | 100c3122-2501-5bad-a3d1-bafcc7e61b5b |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 2cea0f5c-8a2b-5093-a62a-df520ae214d0 |  | note | Accept / Reject Criteria - As per specification
label | b0c3c5b3-ec5c-57e8-a70e-7bc8a0d18ee0 |  | note | Frequency Of Inspection Or Test - In-process
label | de4f0460-85e0-5e30-a658-05bef3666158 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP093
label | edc753cb-327d-5d2e-b476-b5eca3a67a13 |  | note | Records Required - YES
label | 7d929040-eb2e-5091-950f-deb13c96c971 |  | note | ENGINEER - W(10%)
label | f9b5d37c-222a-536a-8c70-6421ddc2b1e7 |  | note | SUPERVISOR - R
label | 0b9c343a-d6b4-52e2-9f30-b0e04c140a76 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Formwork/Boxing (if channel required)
label | cec88be1-def9-5d87-be5a-a1051ad18982 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | ddcbcd86-9094-56db-a12c-c14caa4baad2 |  | note | Accept / Reject Criteria - As per specification
label | 07af900f-3c81-5529-8d4b-964fc948eb13 |  | note | Frequency Of Inspection Or Test - In-process
label | 11dc2eeb-b9e8-509f-9b30-e45d43297778 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP093
label | 34c1b056-9d37-5525-a6bb-32faca6531c7 |  | note | Records Required - YES
label | fc633222-5b92-5657-a8ee-2a3135ff06cd |  | note | ENGINEER - W(10%)
label | d7e53a5e-393a-5db9-a70f-fbf53ca43497 |  | note | SUPERVISOR - R
label | 17c6c5d1-2709-50e2-ae49-c574813b1e42 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Kerb Laying
label | 0643ecaa-ac91-5abd-ae14-1825825bab94 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | a232acc2-ba37-54d4-a2fc-cc25a8026db1 |  | note | Accept / Reject Criteria - As per specification
label | 4e25ec9d-30f6-51d6-b00a-a3a0af706339 |  | note | Frequency Of Inspection Or Test - In-process
label | 0049b4de-ae03-5d37-b1fc-ba6d5ef8c53b |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP093
label | 374d3de2-85c2-552d-b2a1-58ac99d95dcb |  | note | Records Required - YES
label | 3a7bd0bc-4b98-5b46-9d0f-8fd1d3a5cd26 |  | note | ENGINEER - W(10%)
label | 7b090124-b912-5af4-86f4-e30a7003df6c |  | note | SUPERVISOR - R
label | 4875a5c5-06ee-5d66-a62d-ea276fa9c164 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Concrete Finishing
label | 914cb2a2-c38e-59a6-8e95-47292a4bce46 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 934efba7-839c-54e9-8555-bd54e7ea88a8 |  | note | Accept / Reject Criteria - As per specification
label | f10de055-769b-50f7-976a-8ef8d29e417a |  | note | Frequency Of Inspection Or Test - In-process
label | 89b3da40-97d9-5ba1-8e16-1706cd245af0 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP093
label | 64a51383-518b-599e-b348-80751fefd4b7 |  | note | Records Required - YES
label | 582f4bd6-e7d2-585f-a06e-6c05d1d17d64 |  | note | ENGINEER - W(10%)
label | eed73bb4-e5ba-5992-8d42-dbb9f67be7e9 |  | note | SUPERVISOR - R
label | fba3cf5a-30a6-576f-b55b-7fa6b1402296 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Restore Road Pavement
label | 4b91249d-0b4e-52c8-94e2-61863a77cd7b |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | be1d734a-40bf-5da3-b754-a83f05967f90 |  | note | Accept / Reject Criteria - As per specification
label | 3739b88b-5b25-51f9-b5a5-3d905881c505 |  | note | Frequency Of Inspection Or Test - In-process
label | d7d96bad-db43-5b9b-8572-7698ea4ebf3e |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP093
label | 759ec019-ab00-52cc-9166-a99375c19e18 |  | note | Records Required - YES
label | c95d8995-7512-527c-a13e-a2d1f66d5e89 |  | note | ENGINEER - W(10%)
label | f5660de8-731d-5994-a9d1-a2756756d1b3 |  | note | SUPERVISOR - R
label | 3eed3d79-1c89-5e41-95e6-397490abd5ec |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Surfacing
label | d3115d71-f4cd-54d2-95d6-8ed7eead89cb |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 32e83d06-bcaa-5edc-9e17-3f4d6b57b9de |  | note | Accept / Reject Criteria - As per specification
label | 0e68b81a-b0bb-58e2-933d-586f925abb1d |  | note | Frequency Of Inspection Or Test - In-process
label | 5a9266c7-6815-55f1-b89a-04cd6cc1e0f7 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP093
label | 64151421-7e59-5ff5-a69c-6b4bca3b189b |  | note | Records Required - YES
label | 3b0d516a-605f-572b-8d27-28096118aa4a |  | note | ENGINEER - W(10%)
label | 2a4491da-4917-539e-b3e9-a17468f0fc43 |  | note | SUPERVISOR - R
label | 875e0544-f6a5-5cb9-b4d1-5cbef8cbaa9a |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Restore Grass Berm and/or Footpath
label | e3becd66-2f92-530a-99ec-93f7838398ee |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | e78f41cf-47f5-5361-ad99-adfd4b27faa0 |  | note | Accept / Reject Criteria - As per specification
label | 4ea840c9-129d-58e6-8f16-58d42c33c33b |  | note | Frequency Of Inspection Or Test - In-process
label | 66ed91ce-c924-52f3-9873-073f7c61aa45 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP093
label | 8caf8902-7d4f-5b4a-95eb-cc09aca4f7f3 |  | note | Records Required - YES
label | 25a79435-1003-55be-a985-31e2a4a576b0 |  | note | ENGINEER - W(10%)
label | 3534c3f7-9ae2-5aaa-b374-0d74982fa84b |  | note | SUPERVISOR - R
label | 6b8cd439-012d-5208-8e4c-e44e1f5c55f3 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Test and Check
label | 35ac6d45-f9f4-547c-ab94-3851e6ef470e |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 6cda1540-7332-5431-ae73-77d3a470d856 |  | note | Accept / Reject Criteria - As per specification
label | dff771da-8e36-50d8-911c-26d93f858b40 |  | note | Frequency Of Inspection Or Test - In-process
label | 7c85f2e7-6ca0-5fc8-8165-679271b17bae |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP093
label | fb355959-d9d7-5dd7-9941-9e3bc7938da1 |  | note | Records Required - YES
label | e3a8180f-d11b-598f-89ad-aa335ef56ec4 |  | note | ENGINEER - W(10%)
label | c7f993c2-7a2a-573b-bfdd-842be4f52a6b |  | note | SUPERVISOR - R
label | 22fffa48-5bc4-5434-8f46-2a437a6da7aa |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations (Heavy and Light Maintenance) - Unsealed Pavement - Repair a Pothole | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy and Light Maintenance) - Unsealed Pavement - Repair a Pothole | ba6c1728-3ee3-44a0-a7fd-16b892dd2b88
checkpoint-status |  |  | checkpoint | 1 - Selecating Patching Material
label | 95be2b78-dd6e-5c03-b148-3cb1d541b758 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 8d44dc8f-1cf7-57a1-be70-c7b6d2d11d3f |  | note | Accept / Reject Criteria - As per specification
label | 19f0edda-ce0f-58b9-8c2c-031efaad9898 |  | note | Frequency Of Inspection Or Test - In-process
label | e096ddf6-9235-53ee-88f7-8c4416df436b |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP063
label | 59a90eea-7786-5e02-8458-ac76e916311c |  | note | Records Required - NO
label | dacd440c-1d75-525e-9625-c3f899a32e54 |  | note | DOWNER ENGINEER - R
label | 27255411-ddac-58a2-a79c-10250f0a27c4 |  | note | SUPERVISOR - R
label | 99ddebb1-6b5c-5941-b31f-481628f29949 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Short Term Repair
label | bf8b91eb-9c5b-5b6d-b013-eb3e8a3de025 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 45cb3a86-eda6-552c-8b38-b9d13f0d5403 |  | note | Accept / Reject Criteria - As per specification
label | f771bfbb-0da5-57a2-aa5e-643755c10962 |  | note | Frequency Of Inspection Or Test - In-process
label | c023227e-ff98-541a-babe-d5d2bf2ffc85 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP063
label | cb1381a7-744c-5c67-824a-9785a58e842e |  | note | Records Required - NO
label | ae1bab3c-84c6-5626-b7a0-02f65f62c819 |  | note | DOWNER ENGINEER - R
label | e172f849-f6d1-5e34-a1f6-032de9e767f7 |  | note | SUPERVISOR - R
label | 55158786-da55-5998-8869-c2ab7751a90b |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Long Term Repair
label | a0ae67e3-efe8-5c77-9190-26b358dbf37e |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 57487a37-b71a-5b61-b621-36bc9521304e |  | note | Accept / Reject Criteria - As per specification
label | f917e98f-7308-5995-9157-4a21fe3b2737 |  | note | Frequency Of Inspection Or Test - In-process
label | 72d6c8b0-86c7-534f-b061-60dd0bce0ce8 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP063
label | 16800644-e805-59f5-ac28-9e7db2066bed |  | note | Records Required - NO
label | eeeeba87-c020-5031-a9b4-261a37a04cda |  | note | DOWNER ENGINEER - R
label | 933e1ec6-e37f-5eec-bf35-39e25da7550a |  | note | SUPERVISOR - R
label | 138dfb87-af45-5ce1-a337-5244638c6fbb |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Test and Check
label | 9d223e66-1009-57ad-87b3-c90efc76a09c |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 509c05d3-43fc-540b-9d31-0971ef29e43c |  | note | Accept / Reject Criteria - As per specification
label | 86f9d0aa-7501-5f22-a921-49653c4a7fb8 |  | note | Frequency Of Inspection Or Test - In-process
label | 7ab98dc0-1464-5a3d-9c82-0e427c7a0515 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP063
label | 0c740b9d-f391-5df9-b85c-9161f2302def |  | note | Records Required - NO
label | e7724021-ea30-59a1-89af-98b47527478a |  | note | DOWNER ENGINEER - W(10%)
label | 4edb71cd-a7e5-5057-a943-331e2d8f6725 |  | note | SUPERVISOR - R
label | 19c02617-d9a0-5d81-8bb5-f840515e4063 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations (Heavy and Light Maintenance) - Unsealed Road: Laying Metal Using a Tip Truck (or Bottom Dumper) | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy and Light Maintenance) - Unsealed Road: Laying Metal Using a Tip Truck (or Bottom Dumper) | bb6d8c0e-c76d-439f-b005-119ae1ccd688
checkpoint-status |  |  | checkpoint | 1 - Prepare
label | c5ddd05d-6234-537a-9e25-94f554f5b035 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 3df47ab5-e576-5f58-ae60-293ed44f84ad |  | note | Accept / Reject Criteria - As per specification
label | 383b0721-2d57-5efd-b268-6b651dd0963f |  | note | Frequency Of Inspection Or Test - In-process
label | 30ce2304-350f-5ea1-8aee-a0d7d1e332e4 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP065
label | d3e25e79-af44-5fc5-a039-8fbb14ef5b21 |  | note | Records Required - NO
label | 78c51495-b2e0-5e67-89a1-e73e52278172 |  | note | DOWNER ENGINEER - R
label | fe67fde2-6c78-5a3b-8008-ed843515e86c |  | note | SUPERVISOR - R
label | 8382a93b-b8be-51b0-b0dd-67dfe1dcf5b9 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Base Preparation
label | 1cb1e8a9-e20d-5d64-b4f0-25d22b5b9357 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | d5e8c6bc-7313-526b-9a27-10a046f8f480 |  | note | Accept / Reject Criteria - As per specification
label | d974d2e2-7a8c-5da5-be66-2fe79ecc290f |  | note | Frequency Of Inspection Or Test - In-process
label | 5adf85d5-5d7d-5f6b-aac5-538dad32d08e |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP065
label | 9c1406c8-f141-53d6-bca9-0e220a2ce699 |  | note | Records Required - DN-GD-GP065
label | 39910e2f-a3cf-5b67-a858-4ca460c4c1f2 |  | note | DOWNER ENGINEER - R
label | 7606ebaf-5acb-5cb1-8533-47079059f56d |  | note | SUPERVISOR - R
label | 8d96ab69-d375-5e83-bbad-b5f95591771b |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Metal Spreading
label | ca92beb9-54b8-5059-b5a5-b6a15d3eb932 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | c782963d-7c5e-5b12-b7e5-9713f0779816 |  | note | Accept / Reject Criteria - As per specification
label | 88815233-9565-5024-8e2d-c06591340989 |  | note | Frequency Of Inspection Or Test - In-process
label | c615c2c4-9eb3-5b84-a066-51404401fba6 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP065
label | 4e33d3db-f727-5f19-a522-ff4a1c279f48 |  | note | Records Required - NO
label | 13279b75-6408-549e-b68a-57fb60c7019b |  | note | DOWNER ENGINEER - R
label | 15aae598-44ac-58b6-b67c-772592547113 |  | note | SUPERVISOR - R
label | 7d6ce219-7a17-5f8f-99c3-a980d190f6cd |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Test and Check
label | d9b527b7-d578-5601-bdfe-e5496b26a177 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 2622f33f-d2a6-559b-86b1-2c14683effa0 |  | note | Accept / Reject Criteria - As per specification
label | abdccb1e-741e-5556-ae01-e35a6ca6f866 |  | note | Frequency Of Inspection Or Test - In-process
label | 801aa359-52cf-514f-ac81-c11ad07cc3d8 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP065
label | f410fd5c-a875-58ce-9baf-b86892abb98b |  | note | Records Required - NO
label | 60840b43-90f0-5966-87d2-fd0c21b0b84e |  | note | DOWNER ENGINEER - W(10%)
label | bc5f378e-f774-576e-9d73-e617a828b006 |  | note | SUPERVISOR - R
label | d853b326-6cb0-56a3-aff6-9fc11e7e6eda |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC NETWORK - First Coat - Two Coat Chip Seal (Spraybar Method) | itp |  |  |  | Yes | ITP - CONOC NETWORK - First Coat - Two Coat Chip Seal (Spraybar Method) | bde659a7-7e52-4f0f-b3a4-90101d3ee01d
checkpoint-status |  |  | checkpoint | 1 - Weather
label | 0f10d2de-efd1-574f-a6fe-c4dcd24d062c |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 31f2cb49-10cc-5466-875c-aa64a025d28d |  | note | Accept / Reject Criteria - As per specification
label | 82de08c7-e231-5ce5-ba04-db14a926838c |  | note | Frequency Of Inspection Or Test - In-process
label | f8aeb0b0-2cea-5c7a-a0b5-545a3c132b9d |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP048
label | 596b05e5-8a97-599f-81fb-e44fd432b281 |  | note | Records Required - NO
label | 06b5b478-57ab-5c43-8262-8f55715f9b90 |  | note | ENGINEER - R
label | b94c3a7d-41d8-5a6a-a5d0-0e5c444a54fd |  | note | SUPERVISOR - R
label | d2e320bb-0608-569e-ae29-9c55aa8733e5 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Site Preparation
label | a03c697d-ca24-578d-bb84-dd94b1362c9d |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 618858a6-793c-56c7-b968-c334d6520d7d |  | note | Accept / Reject Criteria - As per specification
label | 9dfcad63-e1d6-5152-bef6-3748ba9757e6 |  | note | Frequency Of Inspection Or Test - In-process
label | 5661a481-c546-54e5-b513-d01be7768473 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP048
label | 11981aa2-eff7-5f07-9877-ef9652e7ae95 |  | note | Records Required - YES
label | 45833d1a-b029-5db8-9707-81d1896b4f9f |  | note | ENGINEER - W
label | 644a3af4-ce86-5da1-9760-e5370fa29e78 |  | note | SUPERVISOR - W(10%)
label | 4a5d37be-0dab-55b8-82c2-3fd79315e577 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Binder Spray - First Coat
label | 9037428b-59d3-5b5a-a2fc-4419331c9dde |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | ea95e891-9102-5fc5-9a14-32085cb846b8 |  | note | Accept / Reject Criteria - Maintain 100mm Overlap
label | 33a34daa-05b0-563b-9b8e-6baa65e38267 |  | note | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | 5f392824-7436-5e96-91ce-188dba7baea6 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP048
label | 54c6bce4-51c6-5fdf-abfc-7d57d792726b |  | note | Records Required - YES
label | 155e6e3a-77e8-5815-a0cc-da52cc7382cf |  | note | ENGINEER - W(10%)
label | 779febeb-fb10-5dfc-a506-59df19246833 |  | note | SUPERVISOR - R
label | fdb48137-e12f-54f6-9b86-238f44407340 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Spreading Chip - First Coat
label | bd0a1ce8-95ab-536d-89d6-0db19dc39fab |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | f3f4d242-cd67-50a4-b1fb-8803536c8827 |  | note | Accept / Reject Criteria - As per specification
label | c930259a-f1e8-563b-a327-57908ffac88d |  | note | Frequency Of Inspection Or Test - In-process
label | c974c904-ba75-5efe-b71a-8eedba397168 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP048
label | ac2bfdf7-80df-5607-adf8-e32976a18740 |  | note | Records Required - YES
label | 78835412-2f16-5e87-b41c-d5278d945b57 |  | note | ENGINEER - W(10%)
label | cc03ff19-b77f-5a32-bf82-bad5677e5c5c |  | note | SUPERVISOR - R
label | 928787eb-1185-53e8-a1c5-83dd458256b4 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Prepare for Second Coat
label | 5464ef64-6626-5bcd-9793-ff623ad891e5 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 8c2d4148-27a7-5110-9907-9563cafc1bd3 |  | note | Accept / Reject Criteria - As per specification
label | 71e174a7-c9b3-5793-bcb2-25b606de9e56 |  | note | Frequency Of Inspection Or Test - In-process
label | 3b88b90e-1dbe-5e37-b6ed-43b51c50b456 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP048
label | 739ec1be-709e-5596-a004-7b77a7c81428 |  | note | Records Required - NO
label | e358ae1d-191a-50c6-85fb-f20714246d1c |  | note | ENGINEER - W(10%)
label | c31e54df-3437-556b-9d75-49c66c011ef8 |  | note | SUPERVISOR - R
label | 968c43b7-0a1d-501e-aa05-ac5e0a91aa40 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Second Coat
label | 2f8b4fa9-eeed-5146-be6e-52f1552ee706 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 1886245a-50f4-5df0-9d59-75bcb18b8453 |  | note | Accept / Reject Criteria - As per specification
label | aef25b08-db57-58d8-b49e-989a206f6eaa |  | note | Frequency Of Inspection Or Test - In-process
label | 1976d93d-291f-53da-ae7f-6d2294d3a598 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP048
label | 039b7754-dbc6-595a-b93f-cef3cb15ced6 |  | note | Records Required - YES
label | f4cbdad2-4d5e-51e8-96c7-75d8d5f2da7a |  | note | ENGINEER - W(10%)
label | 55ae8740-5a3d-565d-bd61-bbb1c5ad257a |  | note | SUPERVISOR - R
label | c841be39-44dd-51a2-893e-f6c62d64dfc2 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Site Monitoring
label | 158b3896-6b42-5c59-a376-115e9d91807c |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 2c77da7c-6025-5d70-a51b-6059ab77211d |  | note | Accept / Reject Criteria - As per specification
label | 74bdffc8-5da0-5986-95b8-66e8dbe5ed97 |  | note | Frequency Of Inspection Or Test - In-process
label | f94b776b-c546-5fe2-a914-9b039066a86c |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP048
label | 63c5bf24-03bd-5016-aebb-5a628e609d94 |  | note | Records Required - NO
label | 1eacf034-1e83-51a6-8256-bb330e0b38fd |  | note | ENGINEER - W(10%)
label | fcd0178d-a1d7-5e70-a5fb-7478f0534bcc |  | note | SUPERVISOR - R
label | 1fa7f41f-0bd0-54a6-9172-668ed80a11b0 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Sweeping and Marking
label | c42cdf77-d904-5eec-b8d8-efcbe5d5d801 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 19f6f91b-e140-555d-aa8d-1a8fedd70433 |  | note | Accept / Reject Criteria - As per specification
label | 2c939a63-f78b-5ef0-8d27-0dd1c70166fc |  | note | Frequency Of Inspection Or Test - In-process
label | 1acd1c43-77bf-51c5-a215-776eedbc254e |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP048
label | 2b535970-e074-55a7-877f-e70aeb6d7a8d |  | note | Records Required - NO
label | 074d37eb-03a6-5681-88d9-1e6edc06ad78 |  | note | ENGINEER - R
label | d41e24e3-b918-5c4e-a6b8-a03412ea993a |  | note | SUPERVISOR - R
label | fe8b9cff-3b93-534a-968f-3b5204d155a8 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Test and Check
label | f236009d-882f-5e5a-920d-22e568feaa0d |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | c830e470-1378-5de9-b9bd-514cd8dee3a0 |  | note | Accept / Reject Criteria - Check there is 100mm overlap
label | 86dd4f25-53c8-5726-94ef-df5407c562a1 |  | note | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | 7719a40f-fffd-596e-bf3e-963768c7b49a |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP048
label | ba193094-e6f5-57ef-878a-1f6bf4f52a81 |  | note | Records Required - Nno
label | 4704cdf8-b6a8-5918-9021-7aef2a2619c8 |  | note | ENGINEER - W(10%)
label | 9ed96a7b-7ab4-5af5-aa2b-9b25c728959a |  | note | SUPERVISOR - R
label | 1e25ec62-d9ff-5677-8bc5-78bcd5a29820 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - Stadium RDB - Thin Asphalt Paving |  |  |  |  | Yes | ITP - Stadium RDB - Thin Asphalt Paving | c8034652-2ba3-4664-94dd-c64e3150fcb8
checkpoint-group |  |  | section | 1 - Preliminary and General
checkpoint-status |  |  | checkpoint | 1.1 - Construction Programme Completion
label | 2bd8cb39-fcbc-5010-af70-76cd8f4af936 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 82ce4d08-b24f-5b6d-84a6-ed354924801b |  | note | METHODS OR REFERENCE - Best Practice Contract Specific MMP
label | cfecbea0-dcbc-585e-a2a3-81e18bd219cf |  | note | FREQ. - Before work commences
label | 1f34e9da-8760-557c-9c88-5f29ab3f5d66 |  | note | ACCEPTANCE CRITERIA - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date.
label | 49d9c61d-0182-5d75-b5ea-949d6a26652f |  | note | INSPECTORATE W/H - Type: - W
label | 8bb17cfc-d8fe-5617-abc7-eae7c0e04927 |  | note | Responsible Person - Renewals Manager
checkpoint-status |  |  | checkpoint | 1.2 - Approved RQP
label | 77152fe9-fe45-5ab2-8722-834ee1ae462c |  | note | VERIFICATION ACTIVITY - Confirmation
label | 42e263af-36a3-5c65-9442-6484aac5ac6b |  | note | METHODS OR REFERENCE - Contract Specification
label | 94b13b9f-7acb-58dc-abd1-f22825f54337 |  | note | FREQ. - Before work commences
label | 187fb8c5-bd17-5476-a26d-244281065cbd |  | note | ACCEPTANCE CRITERIA - Principal Acceptance according to guidelines in appendix 6.3
label | f320d884-04a7-5b06-ae32-50f8c34a0eb4 |  | note | INSPECTORATE W/H - Type: - H
label | a5fcc3bf-acf7-5ed3-827d-257c516711a6 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. NZTA to approve
label | 1fce2961-0d33-5605-b68b-fcae51f3ae96 |  | note | Responsible Person - Renewals Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Traffic Management - TMP
label | b4689f16-e475-5f34-81ac-fe98ea7b3d28 |  | note | VERIFICATION ACTIVITY - Visual check
label | 5d6226cb-4bdd-5213-9ba0-203b42d70163 |  | note | METHODS OR REFERENCE - CoPTTM
label | b4511f94-c683-5e35-9cb8-b5f244c7396f |  | note | FREQ. - Before traffic management set up
label | c6ef3ed3-c2e4-5b89-a59b-e026f22507fa |  | note | ACCEPTANCE CRITERIA - TMP checked and approved Plans approved Current EED (if applicable)
label | bb227165-4641-512f-83c6-719f0aa94b0b |  | note | INSPECTORATE W/H - Type: - H
label | 9f2899d0-ecd7-5406-86f7-efcca0986020 |  | note | INSPECTORATE W/H - Description: - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | 311ba7b9-1ac2-5bdf-9b18-7c69b3b86a8d |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Mix Design Verification for all mixes Check Laydown Trials are complete and compliant
label | df23fdd0-d5c3-536d-97e5-83772bc6e035 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 7bfe6707-675c-57ff-b06a-7f807cf00158 |  | note | METHODS OR REFERENCE - NZTA M/10, P/11, P23
label | 079e7637-d68c-5356-9f44-4b6b92b061ee |  | note | FREQ. - Before planning commences
label | 40bc3022-4072-5e12-9e92-8af8831357f5 |  | note | ACCEPTANCE CRITERIA - Mix Design compliant, current and relevant. Batching plant production capability is confirmed
label | d691225f-904a-54f7-855e-3e10880db5e7 |  | note | INSPECTORATE W/H - Type: - H
label | c854e6f2-9833-5703-9b83-b25564f4895c |  | note | INSPECTORATE W/H - Description: - Hold point - No planning of on-site works shall commenced until the mix design is verified.
label | e0462a21-becf-5da4-a7e3-2550a8cc8f25 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Notification of intention to start work
label | ea5704ad-dab0-583f-83a3-9a9c29f03a8a |  | note | VERIFICATION ACTIVITY - Notification
label | af42d2b9-8d80-5714-bee8-cbc6f9322a87 |  | note | FREQ. - Before work commences
label | a2e20b24-80d9-5fd6-8d3d-ca809d9f075a |  | note | ACCEPTANCE CRITERIA - Letter drop to local residents. Greater consultation where required
label | ed746767-6850-52b9-8c93-3d5546d164e1 |  | note | INSPECTORATE W/H - Type: - H
label | 6bd254aa-6b58-5c6a-8ca3-83892128d701 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | 688d9df2-6420-5cc7-a784-839ddc65bdb6 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Works Extents
label | b3863ec8-308c-5b29-aef5-bff075cca35b |  | note | VERIFICATION ACTIVITY - Confirmation
label | 6337ff05-ad88-5809-b37c-a0b6a58415a2 |  | note | METHODS OR REFERENCE - Site Visit
label | 9eb5b4c4-de51-5182-bc62-a0138db0c57d |  | note | FREQ. - Before work commences
label | d12ab6de-f0d9-526d-8815-38b94b7a4c90 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and/or Client to agree extents of project
label | fc602aaf-7a60-58e0-94ab-0cabe61f74b4 |  | note | INSPECTORATE W/H - Type: - H
label | aa5e2497-f9d3-52f9-baf1-6f3663dc0e61 |  | note | INSPECTORATE W/H - Description: - Hold point - Walk over site with Renewals Engineer and/or Renewals Manager and/or NZTA
label | 4b96435f-b9e7-5018-b0b2-845b6b853229 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - Pavement Marking Records
label | e782fa1e-ee7c-56ee-96b6-29ff3c5c1e05 |  | note | VERIFICATION ACTIVITY - Measurment Data
label | 01c57d66-bce2-5dd9-87ac-f8b6ac304f3b |  | note | METHODS OR REFERENCE - Site Measure or Video Viewer
label | 3aef9ae1-498f-597e-b761-afd1555f04bc |  | note | FREQ. - Before work commences
label | ed4c9a31-fad1-5cc0-932b-f887f47c3580 |  | note | ACCEPTANCE CRITERIA - Measure existing markings to aid reinstatement
label | 84e3f45a-14ee-50b0-8f20-433fa8007741 |  | note | INSPECTORATE W/H - Type: - H
label | fb73f7b7-c8f9-5f5f-ae11-17b52e6c6add |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | 3e0d91ea-b31b-59dc-ba03-3a7627f2ef30 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Milling and Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | 87e647ef-31d7-5224-93b0-a02c3fc55c93 |  | note | VERIFICATION ACTIVITY - Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth)
label | eaea20f4-6891-5c4d-b447-d32436c21f76 |  | note | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | fa95c595-6e5c-5d64-9db9-56d35e5fd152 |  | note | FREQ. - Before work commences
label | ada4d660-3fbe-51a7-9126-c20adb9948a8 |  | note | ACCEPTANCE CRITERIA - Zero service strikes
label | 3e77aa8a-9fda-5f93-a4de-f228f5580583 |  | note | INSPECTORATE W/H - Type: - H
label | 6a9053cd-3466-5c75-b2da-fc6b2271c2e5 |  | note | INSPECTORATE W/H - Description: - Hold point - No excavation/milling is to be commenced until services are located and accounted for
label | 189b61c3-b174-515f-8f6c-2d1db234ce09 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Stormwater Management
label | 9991714d-1632-55cb-b7b5-105333882e14 |  | note | VERIFICATION ACTIVITY - Visual check
label | a5320048-8445-578b-a2ea-d956f56fe7b2 |  | note | METHODS OR REFERENCE - On Site
label | f5bc3349-7983-529a-b3d2-d36484601a32 |  | note | FREQ. - Before work commences
label | 9fb163fd-5d7f-5394-ac8e-bd56a03c6434 |  | note | ACCEPTANCE CRITERIA - Mudtanks bunded or filtered to prevent mix from dropping in or runoff entering
label | 2c9fe0c5-2537-5906-a343-a0ad0085080e |  | note | INSPECTORATE W/H - Type: - H
label | 52f52a88-2b8f-54df-beda-ae3e194db692 |  | note | INSPECTORATE W/H - Description: - Hold point - No work to be commenced until protections in place
label | 360ce8bb-11ac-5b56-bec6-7fb071e6bacb |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Traffic Management - Setup
label | 9b24c842-5dac-5b7b-8466-021737bc3770 |  | note | VERIFICATION ACTIVITY - Visual check
label | d273ab94-786e-5f85-8cab-36ba31f38def |  | note | METHODS OR REFERENCE - Traffic Management Plan
label | 4ca72ad1-e84b-5d1f-b18f-b6f8619f2205 |  | note | FREQ. - Before work commences each day
label | b7f63429-677b-5095-b429-52ac72938519 |  | note | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | 511140a7-72d0-5830-b2e4-a4e3d0acd737 |  | note | INSPECTORATE W/H - Type: - H
label | 1ed9e660-3ec6-5fb2-bb3e-569ed7082f68 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | c63905b3-fae7-56bf-b46c-6f08371e782f |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Milling Depths
label | 8fbdcce9-e4d5-594a-b84e-a7626f3a9ab7 |  | note | VERIFICATION ACTIVITY - Measurement
label | 8b822db8-a835-5876-8ede-9bb06bb78362 |  | note | METHODS OR REFERENCE - On Site
label | 9dc52bf7-2a26-556d-9c9b-2f9f3e7cebe4 |  | note | FREQ. - Measure each side of milling machine cut
label | 105fb83f-97a3-5f54-9e1f-71396bd8822e |  | note | ACCEPTANCE CRITERIA - Every 10m. Depth matches target
label | 0d0565d2-44cc-5a6e-b93b-3662fecef08e |  | note | INSPECTORATE W/H - Type: - H
label | 4590d554-1dc9-5d86-953d-cb469b0f7877 |  | note | Responsible Person - Site Foreperson / QA
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Service Covers Preparation
label | f534057b-65fc-5b8d-a927-6ccd28141055 |  | note | VERIFICATION ACTIVITY - Visual
label | c4129306-5d26-511f-9f06-43054bdcf9ac |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 81bec760-8a70-57a1-9ad1-9d0998302b27 |  | note | FREQ. - All Covers
label | 9c3e981c-4908-55dc-8e46-506083413d7c |  | note | ACCEPTANCE CRITERIA - Hand excavation around ironwork and adjustment to desired level (if required)
label | a0cf67a7-ccf9-5b1d-8c92-7768a8ddf387 |  | note | INSPECTORATE W/H - Type: - H
label | 602efe08-fc35-5ab3-acea-f005055d7e68 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Additional Surfacing Preparation
label | ac15b6ad-d75a-599c-8fc0-4c7bcf181da1 |  | note | Side Roads; Accesses; Driveways; Dish Channels; High Shoulders
label | 12045864-9437-5fe4-a90a-3d8120a4abe9 |  | note | VERIFICATION ACTIVITY - Visual Check
label | 16d246a2-4723-5333-8555-14183fd6a809 |  | note | METHODS OR REFERENCE - Per Design
label | ee8b158a-2c51-5bf0-9dbe-d7819c50e4fc |  | note | FREQ. - Before Membraning and Paving
label | 962db35e-7429-5132-bb90-ca3b1cfd7ed8 |  | note | ACCEPTANCE CRITERIA - Have all areas of additional surfacing on the design been prepared, membraned and marked for paving?
label | 9b53b6a0-6915-5a02-a13f-c3cca49ee39a |  | note | INSPECTORATE W/H - Type: - H
label | 42e1a9b7-e9d0-538f-a981-d233028b08ad |  | note | INSPECTORATE W/H - Description: - Hold Point – All areas planned for AC are prepared ready for surfacing layer
label | bbe819cd-f9a1-5b35-a5ad-f3aca96d8994 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Over-Milling
label | 8059443b-a6ec-5448-95c8-829d4e32450c |  | note | VERIFICATION ACTIVITY - Measurement
label | 52be08d2-69c6-5c1e-a644-e121e0d318dc |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 4b24e55c-d9b0-5d22-93ac-ba77ac0051bc |  | note | FREQ. - Prior to pre-level
label | 0bae7709-b0f6-5fdd-af67-692260c197a2 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree need and extent of over-milling and infill.
label | b9263de6-9308-5509-9a29-e8ac6250aaaf |  | note | INSPECTORATE W/H - Type: - H
label | f0c411cc-d97f-58e8-81ec-980f7f4540e5 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Pre-Level
label | 02d83cda-4594-56d4-974c-14524446a0a0 |  | note | VERIFICATION ACTIVITY - Measurement
label | 9da9ddcd-8dcb-5107-a7b0-d14b34c6fce5 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 7e04aa8e-a040-51cc-b7ef-1d852a229051 |  | note | FREQ. - Prior to surfacing
label | 51225694-5cc6-50b1-aa39-2d2c6208d40b |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree pre-level extents
label | a9c0898c-79f6-54e1-a696-133777920c6e |  | note | INSPECTORATE W/H - Type: - H
label | 50cd6a9b-e591-5b59-9664-46e66d8eede4 |  | note | INSPECTORATE W/H - Description: - Hold point - Inspection and agreement by NZTA
label | 102174ea-d9e0-563c-b331-593608922124 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.9 - Membrane Sealing
label | 24d8f429-941f-5a6e-935f-b4e8ed2253f7 |  | note | VERIFICATION ACTIVITY - Visual
label | 4d5e163e-d90c-5a52-8649-2c28e3ca7ddf |  | note | METHODS OR REFERENCE - On Site
label | 0b8beb6e-6e16-55f2-9805-e18d4cda63f3 |  | note | FREQ. - Prior to surfacing
label | f32f963f-062f-54c8-ab29-c909750d7a03 |  | note | ACCEPTANCE CRITERIA - Membrane seal meets design and extent. Sealing Docket record kept
label | 4bcc7aaf-d2ef-5475-a698-3a4b8f7f33c7 |  | note | INSPECTORATE W/H - Type: - H
label | c9ac5dcc-ebbc-591e-95c5-4f7f3ae71e9c |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Paving Structural
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | edef7e61-1a8b-5ecb-9af2-8ad1515ab098 |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | d472314a-419c-57ae-a659-2293ab7044fc |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | 2508464e-ee91-507b-8c20-c3a5e16cf4e3 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | d08ddd14-754f-5e02-aa93-33546d70755f |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | ef29f989-b519-5ff8-9b8c-12aac11cfe20 |  | note | INSPECTORATE W/H - Type: - W
label | 1778549c-af6c-5e80-9630-3a18005dfd03 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | c51c7caf-93ab-5f6e-ba21-336573a7a829 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | 0c584801-4e57-5b8e-8b06-a2e93223e0c6 |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | 297112e0-889d-570e-a63a-69776365a862 |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | 41173a8b-a887-5a42-9470-cfce12e7b676 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 4ad006c9-d16b-53cf-8bbc-b5d0d811581b |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | f6a9d72d-6f64-596a-acc5-607b6dc8c2ba |  | note | INSPECTORATE W/H - Type: - W
label | 55cc5929-3e79-534e-858b-0a44f580555f |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | f47fcad9-dbf4-5e44-895b-4858f08ed63c |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | 90a7315d-5996-5f00-ae5a-048537256076 |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | e0b67383-ae68-59a3-b75a-92b8117f49ad |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | 0cbcd764-34ab-585c-bc0f-80fde959e76e |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | a377720c-c4a8-5210-a5f8-00e3e09f4676 |  | note | INSPECTORATE W/H - Type: - W
label | e12b802a-25d5-5e77-8ace-d52c60e5b90b |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | ef4253af-b08d-5bfb-865d-4a88b916ef3a |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | 0ff20105-c69c-5f17-9278-45ca69339b51 |  | note | VERIFICATION ACTIVITY - Visual
label | b32983b9-f559-580a-870e-05379f2e1697 |  | note | METHODS OR REFERENCE - NZTA M/10
label | af7d7d5a-99f1-530f-b9b8-8b1fd1d6b8eb |  | note | FREQ. - Prior to Shift
label | 9c6a4f00-f641-50f8-bd64-cbb11c343534 |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | a9ac6342-0df8-53f9-8930-0cf6cb24d708 |  | note | INSPECTORATE W/H - Type: - W
label | 714ced5d-d72a-5642-9118-e773c20ae317 |  | note | INSPECTORATE W/H - Description: - Paving Plan and Crew Briefing Plan completed prior
label | ea0eb7a5-9adb-5fb1-883f-de572cb59d3d |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | 0bd433cf-0109-5194-b7b2-6bc50d49152f |  | note | VERIFICATION ACTIVITY - Visual
label | 14e34ec2-7ec0-5344-a455-ae4c39d9069d |  | note | METHODS OR REFERENCE - NZTA M/10
label | 7d4885f2-790f-5696-827b-5753a5fad515 |  | note | FREQ. - Prior to Shift
label | af4048d9-57a0-57cc-9d24-de35a96bf960 |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | acf5a6a7-8a15-5538-93f7-6e4389bbcefb |  | note | INSPECTORATE W/H - Type: - W
label | a7f7b3dc-14a5-5d04-bee9-9af30a48ec78 |  | note | Responsible Person - Paving Supervisor / QA Engineer
checkpoint-status |  |  | checkpoint | 3.4 - Mix Inconsistency and Deficiency
label | 71374109-ca29-5733-b97d-fd6463d3058d |  | note | VERIFICATION ACTIVITY - Visual
label | dec12232-8a63-5242-aa26-ea9ece06a1c9 |  | note | METHODS OR REFERENCE - NZTA M/10
label | fc47e39f-6b1e-56c1-9b98-b8e25e43df2b |  | note | FREQ. - Continuous
label | 59ba0674-bea8-5076-8f92-4bc7d36dab33 |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | 37e9d267-e9cb-5ee9-ba77-c74b340c7a1c |  | note | INSPECTORATE W/H - Type: - H
label | 73fd8d4f-2a94-52fb-a4d7-d9a340e7d076 |  | note | Responsible Person - Site Foreperson / QA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Load Locate
label | be88c238-6343-5db7-aa0d-e977f31c357e |  | note | VERIFICATION ACTIVITY - Measurement
label | 4d53f4fe-4b09-58a8-b28e-56ff3749ca9f |  | note | FREQ. - Every Load
label | 38a12f05-bb61-59f1-a855-2e389370e64c |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
label | 3575c852-16da-544f-b94f-bb3915e95c12 |  | note | INSPECTORATE W/H - Type: - W
label | d89e0b52-5ca7-536c-8c94-864cf5e5d48b |  | note | INSPECTORATE W/H - Description: - Per standard practice
label | 895da98e-41d8-511a-bddb-500cf7db71f8 |  | note | Responsible Person - Quality Assurance Engineer
checkpoint-status |  |  | checkpoint | 3.6 - Laying Temperature
label | bdbb94c6-7da3-593b-b5b8-4eb134ee5fac |  | note | VERIFICATION ACTIVITY - Confirmation
label | 26d96f49-c68c-50b1-acfa-5b8df3eb9db9 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 9fba526a-136a-5ff4-89c9-8281e0f0b81f |  | note | FREQ. - Every Load
label | 7d811bce-b3c8-5999-852e-88629c369b5a |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | 12e74255-70f3-515b-b7c1-2bfe07b3a05b |  | note | INSPECTORATE W/H - Type: - H
label | 5d9d3048-c684-51d7-b10b-14575e8bce0b |  | note | INSPECTORATE W/H - Description: - Hold point - Reject mix for non-compliant temperatures.
label | 887c9d53-53b1-59cc-8d39-e4977901999e |  | note | Responsible Person - Quality Assurance Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Compaction
label | 33c20833-3861-53f9-982c-a77df8255002 |  | note | VERIFICATION ACTIVITY - NDM Testing
label | e9013a8d-9d3a-5c13-b89f-c18ef53bd108 |  | note | METHODS OR REFERENCE - NZTA M/10
label | b4aedc52-aea1-5549-8f48-2ce9a7bfc46e |  | note | FREQ. - Minimum: 1 Test per 300m² within Mat. 1 Test per 100m of joint.
label | 5fab681e-2de1-5a8c-8e08-6e0a07bf022c |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | e2ff3962-46bc-5dd8-a8c3-56fcac49f42a |  | note | INSPECTORATE W/H - Type: - H
label | 78721649-03b4-5651-bb71-abfbe46f644b |  | note | INSPECTORATE W/H - Description: - Hold Point - No Wearing course paved until any non-compliance is sorted
label | cec578f8-8f9d-5d2a-9d2e-6a9765653475 |  | note | Responsible Person - Quality Assurance Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Roughness
label | 4888ed7d-e1da-5ef0-b536-c98b7837a426 |  | note | VERIFICATION ACTIVITY - NASSRA Testing
label | 2bebfefa-6f8c-51d2-a15d-98b8dcec0be4 |  | note | METHODS OR REFERENCE - Contract Specification
label | 87b4d9c8-45b5-5fb7-8e47-587776d455a1 |  | note | FREQ. - post construction
label | 418381f1-017b-5c67-89ac-0025ee60bfda |  | note | ACCEPTANCE CRITERIA - NASSRA rolling meter average under 60, max of 70
label | 1270c208-0449-51e1-a004-926e00b18023 |  | note | INSPECTORATE W/H - Type: - H
label | f77070d4-1a85-5797-a162-a6e97fe82834 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Paving Wearing Course
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | 951ff810-0069-5447-baaa-e5f76d007e39 |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | ba1024b2-286b-5a03-85c6-5a5050c1fbda |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | 0c4bef47-d46b-57df-aa1f-ee50e6d78dbf |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 782b13df-1a0b-5f03-ac6d-91e826da5324 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 15ca92b1-7147-5c76-aee7-a93cef1276b3 |  | note | INSPECTORATE W/H - Type: - W
label | 4616c754-127a-5101-bc52-d1a66a67fc79 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 3aa99cc1-368b-582d-83dd-2ec55d0828bb |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | 65263cbd-e6ca-54f9-9ffb-5c152a3736e2 |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | d2aa7845-2aae-5529-92ff-aa19cc1bb138 |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | 92235bcb-9c7c-5bae-a959-8b347d59c7d1 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 3ea5e740-a797-5722-bc8a-0662dda78073 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 9e62e4f5-ed77-5be5-9bc9-8d3192b84ec2 |  | note | INSPECTORATE W/H - Type: - W
label | b8c673b5-c900-5e1b-8570-246122b04fc3 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 2d4930c5-529a-5bd8-b502-84279ac094bb |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | 5a7dac2e-6acc-55b7-b89e-20f531deae2c |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | cae0a1f3-4dd7-5537-b393-c1dc88560983 |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | aedd951b-8fc1-5d54-bca4-dca6c4bd5f71 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 88d9b152-6d9e-5ec2-9c2b-2838907156fa |  | note | ACCEPTANCE CRITERIA - Per Mix design
label | a2aea0e7-f998-52d7-9b26-2f9f98d61f10 |  | note | INSPECTORATE W/H - Type: - W
label | 7f180b31-ee7f-57d2-b3ee-970f16d713f8 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | c1f1f089-4cc8-5b31-936f-2da92cff3fdf |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | a09f66fa-58b8-589b-b455-7483e776d975 |  | note | VERIFICATION ACTIVITY - Visual
label | f4ac0232-d2b8-518b-bc0d-7b6762f61205 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 66c609d8-c4b6-5f68-b2da-c24aa090638a |  | note | FREQ. - Prior to Shift
label | 6017060c-68c6-5433-ad42-2d1bf93e7dbe |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | 6e978b8f-ba3f-5001-944f-873c842e0bf4 |  | note | INSPECTORATE W/H - Type: - W
label | 4d0d471f-72d1-5ca9-8fc2-09a1763a2d9b |  | note | INSPECTORATE W/H - Description: - Paving Plan and Crew Briefing Plan completed prior
label | 83c966b3-2801-5d41-a145-bc537488fc8c |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | a7a70403-c972-57b0-8870-1455f10ef11d |  | note | VERIFICATION ACTIVITY - Visual
label | 96ccd524-4007-52a3-a3a7-d9413d8a26ad |  | note | METHODS OR REFERENCE - NZTA M/10
label | 8e3c2e79-78e3-589c-8c6e-d1b471716d01 |  | note | FREQ. - Prior to Shift
label | 3da46a4f-fcc3-5207-9f17-dade4705c553 |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | 122265e9-6afa-5349-ae65-4883aceec827 |  | note | INSPECTORATE W/H - Type: - W
label | 6fbd7205-2cfc-5750-a1a3-013e62845b59 |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.4 - Grade 3 Membrane Sealing
label | b6306db5-b538-5368-a806-7115439bc1b0 |  | note | VERIFICATION ACTIVITY - Visual
label | 9370826f-c84c-54fe-b985-7c47b80b2dae |  | note | METHODS OR REFERENCE - NZTA M/10
label | 3efe4d7e-6baf-5f12-89e1-4184091135f8 |  | note | FREQ. - Prior to Paving
label | 094768f4-cc9e-5b6c-8225-9df9ff5d72cb |  | note | ACCEPTANCE CRITERIA - Applied 2.0l/m² residual
label | 988ec36a-ab7f-5f82-9ddd-12d05cbbd905 |  | note | INSPECTORATE W/H - Type: - H
label | 4f7a551e-3896-52ea-bea7-df36506fb0e6 |  | note | INSPECTORATE W/H - Description: - Hold Point - No paving until Membrane Done.
label | 5b6bdfdf-9834-5150-a627-0fc9ec73c562 |  | note | Responsible Person - Paving Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Mix Inconsistency and Deficiency
label | ae619a04-1093-554c-931a-9522f202805e |  | note | VERIFICATION ACTIVITY - Visual
label | 85405f21-f5a9-581c-bd51-5732a24a52df |  | note | METHODS OR REFERENCE - NZTA M/10
label | 171f5f4c-8bca-57af-8b62-a89ac05d741b |  | note | FREQ. - Continuous
label | 0f795661-0b31-52c2-8f89-4c277cb2ca6b |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | bc520c31-38b9-5282-b568-9b73acb29ef8 |  | note | INSPECTORATE W/H - Type: - H
label | 3a78cad9-9137-5aa6-9b45-3463785f8ba7 |  | note | Responsible Person - Site Foreperson / QA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Load Locate
label | 6a3624cf-122a-57c1-9bfe-2a14c0c5b56f |  | note | VERIFICATION ACTIVITY - Measurement
label | 7bc338fb-d37b-5cd1-8630-b829470aa42d |  | note | FREQ. - Every Load
label | 59635119-07bf-597b-a3ec-2f3710b1b1c8 |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
label | eb786b3d-c28b-5a41-95b9-dfedc26c0c95 |  | note | INSPECTORATE W/H - Type: - W
label | a70a5cdd-aa62-52c7-ab84-836ea0facd42 |  | note | INSPECTORATE W/H - Description: - Per standard practice
label | b1875caa-b2c3-50bb-81d7-85227dac71c0 |  | note | Responsible Person - Quality Assurance Technician.
checkpoint-status |  |  | checkpoint | 3.7 - Laying Temperature
label | e75de33f-fd0b-5623-a4fe-3c9edf90fff3 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 4f3e63e5-d8cb-5f64-b96d-6679027c0f98 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 25f0c50d-9a6b-58fc-a3b4-3a28924b7aad |  | note | FREQ. - Every Load
label | 70b42231-fbab-5457-b396-7fd92455f2b4 |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | 0256e0f3-e4ab-5532-9955-0d166b70d344 |  | note | INSPECTORATE W/H - Type: - H
label | d2fbb617-f81a-557c-8059-32b81902d0ab |  | note | INSPECTORATE W/H - Description: - Hold point - Reject mix for non-compliant temperatures.
label | b99a63e6-f07b-5528-b37a-d1761626594d |  | note | Responsible Person - Quality Assurance Technician
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Compaction
label | 04a6c577-3a82-55b4-96f2-c7be6f66443b |  | note | VERIFICATION ACTIVITY - PQI Non-Nuclear Gauge/Cores. Or Non Distrctive Method Testing.
label | c5d78b06-afea-5012-a4d4-76442d9dcebd |  | note | METHODS OR REFERENCE - NZTA M/10
label | abc51374-dd7b-5b62-9d4b-08301c9bc7bd |  | note | FREQ. - Minimum: 1 Test per 300m² within Mat. 1 Test per 100m of joint. Minimum 8 cores on Mat and 3 on Joints as Per M10:2020.
label | 1dc12786-18be-5ab6-a16a-4b3591e9e57b |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | 152acab1-658d-5dcd-93ef-6e2d253c0433 |  | note | INSPECTORATE W/H - Type: - W
label | 6091f529-e131-5828-b288-ff0ef421023e |  | note | Responsible Person - Quality Assurance Technician
checkpoint-group |  |  | section | 4 - Site Reinstatement / Clearance
checkpoint-status |  |  | checkpoint | 4.1 - Post-seal Area Check
label | e091694b-0ab5-5903-b0f0-574aae41d35c |  | note | VERIFICATION ACTIVITY - Measurement
label | 003acca9-9407-5146-ad4e-553bebd16299 |  | note | METHODS OR REFERENCE - On Site tape-measure
label | dab422b7-1023-56f6-afc5-144d06aee5de |  | note | FREQ. - After Surfacing
label | 7482cd12-6fcc-55df-aa0c-328da4051c66 |  | note | ACCEPTANCE CRITERIA - Check sealed area meets design
label | 6ca12d14-3117-5e1c-ba00-c8aafe5c7dfa |  | note | INSPECTORATE W/H - Type: - W
label | 071ee053-9b72-538c-b876-638841d15109 |  | note | INSPECTORATE W/H - Description: - Notify Renewals Engineer or Renewals Manager
label | 1186c8e8-afc9-53ab-8e7b-dea422ccef6b |  | note | Responsible Person - QA Engineer
checkpoint-status |  |  | checkpoint | 5.3 - Service Covers
label | c7309fab-3bf7-5b84-a94f-8bf0499dc8b9 |  | note | VERIFICATION ACTIVITY - Measurement/Visual
label | 43154b14-ac16-53c8-b0e1-acb0521bf4bb |  | note | METHODS OR REFERENCE - On Site
label | 316e110d-d00e-5987-8a8b-3d21679faf8a |  | note | FREQ. - After Surfacing
label | f2edf676-bc5a-55ab-9cb6-bd2830d077f8 |  | note | ACCEPTANCE CRITERIA - All service covers are checked and adjusted (if necessary) to finished level
label | 4937574f-222e-5589-ba34-a80da61c6b51 |  | note | INSPECTORATE W/H - Type: - W
label | a63fb8c2-5701-5ec1-a975-0280c882eea1 |  | note | Responsible Person - Paving Supervisor / Foreman
checkpoint-status |  |  | checkpoint | 5.4 - Joint Sealing
label | b138515d-89a1-5804-ab20-8824dbe77b59 |  | note | VERIFICATION ACTIVITY - Visual
label | 4dadd254-c092-5a3c-b24a-a5c365e236f5 |  | note | METHODS OR REFERENCE - On Site
label | a1549456-ad23-57da-89dd-ef71f5e55473 |  | note | FREQ. - After Surfacing
label | caa73d56-faeb-5f0c-aeeb-3a64e4750337 |  | note | ACCEPTANCE CRITERIA - Check cold joints are bandage sealed
label | 5c02a693-35a1-5809-9a3b-62aff5d608f3 |  | note | INSPECTORATE W/H - Type: - W
label | 5a09ff12-b28d-5821-942e-8d6f75d70486 |  | note | Responsible Person - Paving Supervisor / Foreman
checkpoint-status |  |  | checkpoint | 4.2 - Road Marking
label | d10548df-638b-5190-8af2-ba5895e43907 |  | note | VERIFICATION ACTIVITY - MOTSAM
label | 6a2d6e72-5028-5908-95c9-c5e117f99abd |  | note | METHODS OR REFERENCE - Visual inspection
label | a076c4ec-629b-52f0-a766-8af9b022fd48 |  | note | FREQ. - All markings
label | cc916e79-72d7-5538-8c96-8fcc973145c9 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, or per design
label | 7a1cc299-049d-53e8-8dc3-4d05c24ceac8 |  | note | INSPECTORATE W/H - Type: - H
label | fb976e75-b6f1-52df-9335-a7b74c7a178c |  | note | INSPECTORATE W/H - Description: - Hold point – Site TTM cannot be removed until markings reinstated
label | 74f18730-52d4-5688-9bcd-38c2710f1323 |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 - Other Traffic Services - Marker pegs/ Signs/Markings/RRPMs Replaced
label | 8c77509e-1812-5727-bb1e-fce555d50b32 |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | 06548fbb-1356-5ded-891f-99a55383d4e9 |  | note | METHODS OR REFERENCE - Visual inspection
label | ced55480-2bb2-5f51-8a86-df86ef1bf903 |  | note | FREQ. - All signs/markers
label | 232f4717-8147-5751-9c2d-16224f3e8350 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | 8e6d22a2-083d-5cfd-b9a7-2118cf8971c3 |  | note | INSPECTORATE W/H - Type: - H
label | 45b5b4ab-b4af-5467-93d3-c7a2dc635e02 |  | note | INSPECTORATE W/H - Description: - Hold point – Site TTM cannot be removed until marker pegs, signs, markings and RRPMs reinstated
label | e329277f-847b-5af3-ae41-46cfee77421a |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Stormwater Management Controls removed
label | 09d58985-0e00-54b2-a9fc-a1451c25f439 |  | note | VERIFICATION ACTIVITY - Visual check
label | c27bcf33-2578-5db0-99bd-74fff086913a |  | note | FREQ. - All installed measures
label | d9174e9d-fefc-5778-8901-60e437e8abf4 |  | note | ACCEPTANCE CRITERIA - Installed controls are removed
label | 2fcf0c7e-9e79-503e-bb0f-e7936bbea2d3 |  | note | INSPECTORATE W/H - Type: - H
label | ab8c7a46-82d7-5559-a630-868492a52f2c |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Traffic Management Removed
label | 0151b010-e224-5afd-95ef-c9a7e0c31e81 |  | note | VERIFICATION ACTIVITY - Visual check
label | fd28546d-61f3-5e5b-a3b7-8195b2b3d113 |  | note | FREQ. - When safe, after all physical works completed
label | 24225ca6-a28f-5119-a28e-4597bf570ee8 |  | note | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | 2c546a1a-5131-51c9-9940-af38dc77f423 |  | note | INSPECTORATE W/H - Type: - W
label | e79ddcc0-21e0-5d15-8b1a-a1adfa6df43c |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.6 - Site left clean & tidy
label | bbd4d42b-07ca-5bfc-a578-99d48be0295c |  | note | VERIFICATION ACTIVITY - Visual check
label | db8e9fa3-2cbc-5cf0-a0ba-b658dcfacf5e |  | note | FREQ. - After vacating site
label | 5606a2ae-27d7-5d1c-9c54-9892e13d85ef |  | note | ACCEPTANCE CRITERIA - Stockpiles removed; Plant removed; Litter cleared from site
label | 32d25510-aca0-5b10-89ca-c15a493641f3 |  | note | INSPECTORATE W/H - Type: - W
label | d3626be0-69f2-55a3-9e06-89e934f3cd7c |  | note | INSPECTORATE W/H - Description: - Invite NZTA to carry out joint site inspection to inspect site.
label | d52cd988-1efd-5342-99f8-9ea489e564ed |  | note | Responsible Person - Paving Supervisor
checkpoint-group |  |  | section | 5 - As Built Records
checkpoint-status |  |  | checkpoint | 5.1 - Collect asset data
label | d0b5ed13-ef0a-50ff-b7c8-fb92b3ab9ea1 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | 8ab82e8e-b157-5f41-8bfb-2a154d698b15 |  | note | FREQ. - During construction
label | 3e89af30-d04f-5028-939b-544932a42257 |  | note | ACCEPTANCE CRITERIA - All relevant as built information collected.
label | c741be7a-2a4d-5d6c-b25a-a8b01037028f |  | note | INSPECTORATE W/H - Type: - W
label | 0e989f00-679c-5ffd-8aed-6bf41de43647 |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.2 - Enter asset data into RAMM and/or register(s)
label | 88c46a70-ee7b-5f91-b34f-283dc6931227 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | 72528147-80a7-55a2-b7ec-58d1fe101b56 |  | note | METHODS OR REFERENCE - RAMM
label | 923a5116-e83e-5039-a053-707319681dbe |  | note | FREQ. - At completion of work.
label | 96bf7b13-6665-58f9-b8b4-048dfe193ee9 |  | note | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.
label | 586fdc41-dfd0-5702-96fc-9dce285a5db9 |  | note | INSPECTORATE W/H - Type: - W
label | 2eaff862-2abd-517f-a4a9-b1df04085466 |  | note | INSPECTORATE W/H - Description: - Data entered by 20th of follow month after month of completion
label | 3ff11ccd-dc71-52a1-8452-d7704fc71cfa |  | note | Responsible Person - Asset Information Manager
checkpoint-status |  |  | checkpoint | 5.3 - Construction Completion Report
label | c9f576e9-ca54-5a92-b8fe-c3df15acec00 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 45ef9106-6c13-55f3-a6c6-963828f219e1 |  | note | METHODS OR REFERENCE - Contract Specification
label | 13b05d54-86ab-5c28-b0f1-87bd957130d9 |  | note | FREQ. - At completion of work.
label | dfaeb028-d3ef-5acc-be88-a23c6d5e2bfa |  | note | ACCEPTANCE CRITERIA - Checked and approved
label | 041bf9ae-f459-54ea-a254-9a5521dd7a3e |  | note | INSPECTORATE W/H - Type: - W
label | 69ed4caf-c454-508f-b9f8-dc96f568c749 |  | note | INSPECTORATE W/H - Description: - Completed within two months after Paving Wearing Course
label | 550d5ec2-f961-5e20-a7b2-fda6e3a251b9 |  | note | Responsible Person - Renewals Engineer/ Renewals Manager
checkpoint-no-status |  |  | checkpoint | Quality Assurance Close Out
text | 0e0055b9-f15d-58bc-b911-81d050bfdb67 |  | textbox | Quality Assurance Close Out by - Name:
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | ITP - CONOC Operations - Emergency Works: Make the Site of an Underslip Safe | itp |  |  |  | Yes | ITP - CONOC Operations (General) - Emergency Works: Make the Site of an Underslip Safe | cb4aabd0-dd11-412f-9e5e-27b2414c6f40
checkpoint-status |  |  | checkpoint | 1 - Planing
label | 02f5fc1f-3a71-5b04-a9f4-6c7fbe6377ea |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 55838e12-710b-5200-ba7a-d0a2c77303c3 |  | note | Accept / Reject Criteria - As per Specification
label | cdf868c1-5eb1-514a-9685-b9c0c2a24bbf |  | note | Frequency Of Inspection Or Test - In-process
label | c2779e55-5f14-5d38-b637-95f6b7adfc6e |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP104
label | 3c616c2b-baa7-5204-93d4-4b84cf70db97 |  | note | Records Required - NO
label | 3657ded7-d46c-5a37-a302-e2e1ebaa32d0 |  | note | ENGINEER - R
label | f8d613ec-68c5-585f-9b5b-99ed5b61e0e6 |  | note | SUPERVISOR - R
label | 65eb125e-83b6-5edc-a73a-94c649bdaa50 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Preparation
label | 90f6abbf-8ae1-5394-b1b9-d00d931b1ffb |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 57f604f5-84c5-5f1c-8bea-e8a15a5f64ef |  | note | Accept / Reject Criteria - As per Specification
label | a72373c9-3c3c-5eae-92f4-cc7499df649c |  | note | Frequency Of Inspection Or Test - In-process
label | 8dfc76ec-e465-547f-b87b-b2bb347cd013 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP104
label | f1b7718a-ffd8-5f9f-80d6-f5958832f60d |  | note | Records Required - NO
label | dbb373a7-67ba-5e23-aab6-34658d889caa |  | note | ENGINEER - R
label | ef63ca54-f334-5a61-90ae-89aed50ad3bd |  | note | SUPERVISOR - R
label | 9cd6c477-9068-5907-abdf-9877f2e40bd2 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Order of Work
label | 56489cfa-d573-581d-a47f-2621cf52b3bc |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 8aebef3c-9318-5fd6-90fa-f31c46ee3076 |  | note | Accept / Reject Criteria - As per Specification
label | 42406316-a9c2-5048-8da0-89b1fe9acb9b |  | note | Frequency Of Inspection Or Test - In-process
label | 8a1d756c-7881-55d8-9d3c-b31d370d3b08 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP104
label | dfcede1d-dcbb-5252-bebb-1ea43afee834 |  | note | Records Required - NO
label | 25d58a03-ef64-5e1b-96ef-8537ce63c7fb |  | note | ENGINEER - R
label | 1d0f9a2f-cc80-5190-ab1c-5b8c1273d4cd |  | note | SUPERVISOR - R
label | 75c01d23-32fa-5fb9-b6ca-a6b6785dd902 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Remove Overhang
label | 033e8434-dc6f-5912-b7ad-fdeb6bb1f170 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 8beca3c9-ebda-5091-a33f-21eb00e84703 |  | note | Accept / Reject Criteria - As per Specification
label | 362a014b-c794-54cd-9178-c0505dcdfdba |  | note | Frequency Of Inspection Or Test - In-process
label | 517c725f-faa0-561b-b04d-e001c2cf16b8 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP104
label | 1c31d95e-64cb-550d-ae64-44cf9dd9e16a |  | note | Records Required - NO
label | 6f9ff38b-fd42-538f-be54-75d8a36234d6 |  | note | ENGINEER - W(10%)
label | b14b3fe1-56fa-5acb-87c5-655f27ae5267 |  | note | SUPERVISOR - R
label | ae79ba64-0213-5c96-87f8-980a8da0f3d6 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Install Temporary Bund
label | ba223685-1912-5a95-b4e8-3bd4cb5f01ec |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | a8bf0819-ea86-51a5-bd3d-15c03d059980 |  | note | Accept / Reject Criteria - As per Specification
label | d1d21811-f73a-5fed-bab1-fc7fa016489b |  | note | Frequency Of Inspection Or Test - In-process
label | 1f9aa6a8-71b2-5d28-92bf-72692b73ec83 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP104
label | 2d4db20b-ae8c-52df-ad1a-eb5ddee1b7c1 |  | note | Records Required - NO
label | 48cdeb84-3319-5e24-86e1-6673dc317103 |  | note | ENGINEER - W(10%)
label | 472e1c9f-4c04-5691-a132-e562c4627127 |  | note | SUPERVISOR - R
label | 94eb3d09-a6da-581a-b616-fed9d9fe04d6 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Temporary Fence
label | bef47f12-edcb-5be9-b7f2-77d707f829cd |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | ff6c37ab-c6a8-5b42-b90e-5d3c449cce42 |  | note | Accept / Reject Criteria - As per Specification
label | 2042e244-9545-57c8-b09e-8cccaa57271d |  | note | Frequency Of Inspection Or Test - In-process
label | 39c69ed5-e8d1-51a9-8946-beb0a4c153a9 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP104
label | 4ebc7cc0-8bd1-56da-a45e-22fff03d159c |  | note | Records Required - NO
label | 883a24a9-9756-5104-8a47-0830637f67eb |  | note | ENGINEER - W(10%)
label | 928a8e74-b578-57e2-a990-c9a0a7da04fb |  | note | SUPERVISOR - R
label | bd0585a2-2047-539e-a57f-cdb3f7a20af2 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Test and Check
label | d5db6260-bdfb-55d7-a186-a48f6cec5dac |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | deca2282-2a12-5fb4-9115-7f4b137e5a1d |  | note | Accept / Reject Criteria - As per Specification
label | 9a141e1f-af23-5ed5-a97c-87f8634cc721 |  | note | Frequency Of Inspection Or Test - In-process
label | 8ab1823b-25fe-5a76-9968-f4ca1856e5f9 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP104
label | 26da788f-988c-57eb-9996-ea0b7004e761 |  | note | Records Required - YES
label | 94d2b12b-a191-56e5-8885-c936073a9efa |  | note | ENGINEER - W(10%)
label | fbb26c79-02df-570f-a543-69d49aba6754 |  | note | SUPERVISOR - R
label | 5f572b68-45a5-54e5-91ab-dc2f0ffabe0c |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations (Heavy and Light Maintenance) - Grading Unsealed Road - Medium | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy and Light Maintenance) - Grading Unsealed Road - Medium | cd489642-7289-406e-b0f7-d7c1d07990a6
checkpoint-status |  |  | checkpoint | 1 - Prepare
label | cfca0946-f2ec-5a59-99e2-22502271cb58 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | e041d997-d6da-5587-a30c-e04c9d46643f |  | note | Accept / Reject Criteria - As per specification
label | 453bb3dc-5bfd-5161-b0d3-035ea1c87d7b |  | note | Frequency Of Inspection Or Test - In-process
label | 5adffa9a-4fd2-5bd8-9265-a894f1421227 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | 88f01b32-68ef-5509-89cf-613c16be0154 |  | note | Records Required - NO
label | b1be2344-0e31-5259-87c1-cab78aed3bbb |  | note | DOWNER ENGINEER - R
label | a85bd739-210b-56b9-9e18-3c871f093aa1 |  | note | SUPERVISOR - R
label | 57f8b12b-7965-5073-a7db-3ade5500ad45 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Grader Operation
label | ca4513bf-f081-520d-804e-456aa07c5c95 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 0754a5e6-8fc4-5b99-bafe-f9e474e75266 |  | note | Accept / Reject Criteria - As per specification
label | e0088e6b-a32b-5b3e-b701-85b3c6ccea0b |  | note | Frequency Of Inspection Or Test - In-process
label | 9db1e10a-9e99-50fa-9cd9-7d88401df89a |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | fed50ddc-91b6-580d-81f4-e2a386982ff3 |  | note | Records Required - NO
label | 50986ff3-32bf-56f4-be1b-29336085977a |  | note | DOWNER ENGINEER - R
label | cbf308df-9be9-588b-bc97-c5a246ed3c09 |  | note | SUPERVISOR - R
label | 53798e16-c5d8-5850-b69f-bfa2cee76960 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Grader Set-up
label | 31fae5c1-0edf-55bc-be41-1310935c435c |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 22a68e31-0249-592e-9dd3-a243f43e8d97 |  | note | Accept / Reject Criteria - As per specification
label | c2d997e6-2310-532e-a15e-9b131beca808 |  | note | Frequency Of Inspection Or Test - In-process
label | dfa21548-e14b-59bf-ab60-130431057ac3 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | 23cf8acd-150b-5dd3-97fb-46de24e5b9a4 |  | note | Records Required - NO
label | 5e6f0486-a4d6-5676-91ed-66e00b4fbefb |  | note | DOWNER ENGINEER - R
label | e978320e-a134-5a31-9db0-07b2e400cdda |  | note | SUPERVISOR - R
label | 601e252e-0990-5f41-b79e-908933318cd5 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Super Elevation on Corners
label | e36e5d58-84f6-5f3a-adb2-04c2f0932226 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 65853eb2-02f2-57c6-b1f4-76b2efc39266 |  | note | Accept / Reject Criteria - As per specification
label | 0b6f9a4e-5e80-540d-a48d-fecd4ff4d32a |  | note | Frequency Of Inspection Or Test - In-process
label | 397cece9-646e-5562-991d-1609268e8599 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | 982ca2a5-0a5a-54fa-aacb-5d954f92f966 |  | note | Records Required - YES
label | a2f130ad-94e8-535b-ad50-d4810a20c9d7 |  | note | DOWNER ENGINEER - W(10%)
label | 8fc2d3d8-cd81-59c3-a387-f3bff2f44adc |  | note | SUPERVISOR - R
label | f3e4d7c3-ffc3-544f-8720-561977234885 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - First Pass
label | 7ee43f8d-60b6-5f9c-9cf8-cf1fb6856619 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 0daade0c-edf9-52f9-a07b-777e22ee5c7c |  | note | Accept / Reject Criteria - As per specification
label | 9478d9e3-6bdb-5aae-b087-690532982a34 |  | note | Frequency Of Inspection Or Test - In-process
label | 399b20ad-3519-57e0-a2d5-53f64ca20696 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | ee626a16-89df-58ee-aeb7-c9f83576d7f7 |  | note | Records Required - NO
label | b7687d87-9e77-5cbc-85a3-6d2ab6053e41 |  | note | DOWNER ENGINEER - W(10%)
label | c13ee057-17b9-5569-8a6c-c61610f068e2 |  | note | SUPERVISOR - R
label | ff38b46e-e9a5-580c-b3c5-397f8f35ed09 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Second Pass
label | 7d5e812d-e754-5456-8ce0-d16e5b46ebb3 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 1e03a89a-0397-5472-9da2-53660d4d0fb7 |  | note | Accept / Reject Criteria - As per specification
label | f31a12c8-5e9a-5338-af6c-9ca82f759d26 |  | note | Frequency Of Inspection Or Test - In-process
label | dd7d6112-0cba-5c32-850b-2d0401181328 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | 80a2c2e4-b73c-5f5b-89b9-ea7f448411bc |  | note | Records Required - NO
label | 48ccba44-f345-5483-a727-674aef68d59a |  | note | DOWNER ENGINEER - W(10%)
label | be64dc91-6507-5194-ad7b-0339796f0f9a |  | note | SUPERVISOR - R
label | 7c939c8a-bce5-5f40-9f23-cc592acf5693 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Cut outs
label | 53b799dd-65e5-5133-a6c1-3400f1632572 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | f75b5472-1328-53da-9524-fc4a40de67d4 |  | note | Accept / Reject Criteria - As per specification
label | 0b6e4814-be1c-55ad-8862-b56dbac06a6e |  | note | Frequency Of Inspection Or Test - In-process
label | 44d64c18-b523-505d-91ed-df44c3f82c91 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | a105bdef-9e9c-54e0-8ca1-da74ea44c10d |  | note | Records Required - NO
label | d6175a99-82f0-5a41-a7da-49e35538c023 |  | note | DOWNER ENGINEER - W(10%)
label | dd375a4b-5ad2-50a3-b5d6-006110469741 |  | note | SUPERVISOR - R
label | 621070e7-d3e3-5ed7-a13c-06a4537e017e |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Third Pass
label | 5c35eead-22f9-56dd-a411-55de75655336 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 7c265090-f3c4-5205-ab32-6677d7ff1ba0 |  | note | Accept / Reject Criteria - As per specification
label | ae2f3f45-677e-56c2-95df-0f39b50c6913 |  | note | Frequency Of Inspection Or Test - In-process
label | 931293bd-c3d2-5ce6-81c1-757ebf92df56 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | fd645f73-87b7-5dba-bffd-70d9676fb153 |  | note | Records Required - NO
label | 474ec345-8a67-5372-bd31-ab9051f25f7b |  | note | DOWNER ENGINEER - W(10%)
label | 3268e8f4-0095-556d-a5b7-38dca4e7a11d |  | note | SUPERVISOR - R
label | 45d913cd-6d64-52ca-ab7d-fd43cf35231b |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Fourth Pass
label | edfbd8b1-b9f9-5698-8918-f92e51b5fd1f |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | fde86fc1-818b-549a-82ac-9fa3a5265e9f |  | note | Accept / Reject Criteria - As per specification
label | 2820a048-4703-5128-9b94-1775b320d6dd |  | note | Frequency Of Inspection Or Test - In-process
label | 4b10d583-ee62-5e23-8b67-560443b37e06 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | ecea586a-5b92-52d0-b6ec-095c7afea126 |  | note | Records Required - NO
label | 7c540c90-1772-593b-a8a6-62136e27b992 |  | note | DOWNER ENGINEER - W(10%)
label | d090e4ac-98d9-58a3-8e61-105625fcf0f6 |  | note | SUPERVISOR - R
label | e9d664d2-94b9-5a96-ae7d-7ff8b03a15be |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Extra Pass
label | 106841f9-5912-554e-b690-efc7d97a76e9 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 46af1b62-8934-5cef-a2ac-a38bbf41e417 |  | note | Accept / Reject Criteria - As per specification
label | 06bc2856-4f3a-5191-90be-6fa2971616dd |  | note | Frequency Of Inspection Or Test - In-process
label | 3dd20eab-2645-500b-b5c3-cfb6111b3b22 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | fd72c693-34d5-58ff-b736-c03468895fa6 |  | note | Records Required - NO
label | 76fe5165-daae-5d5c-95bf-07a511289ee9 |  | note | DOWNER ENGINEER - W(10%)
label | ab6f8df5-1ac0-5903-847e-c38c7670dd03 |  | note | SUPERVISOR - R
label | 30bc54ee-8212-54e9-a5c4-963ed7ea9887 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Spreading Passes 1-2
label | 5dab9c32-144f-5d70-94b2-0815a23294da |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 51cf715f-1bef-51e5-811e-c1b2c258f429 |  | note | Accept / Reject Criteria - As per specification
label | c3e07eb8-b0ac-5a88-bd99-6205724b1b3d |  | note | Frequency Of Inspection Or Test - In-process
label | 20913d49-0306-549a-bcbd-960f2a51dfa3 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | bf09baba-a2f6-5af5-9c29-e8063fb9da5e |  | note | Records Required - NO
label | 5b64209a-70a8-5950-abe6-ebacf0863fa8 |  | note | DOWNER ENGINEER - W(10%)
label | 2bce8610-c479-574a-99eb-787924289398 |  | note | SUPERVISOR -
label | 47ec8358-c436-52b2-9d09-c7d331a0b698 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 - Issues
label | 0431d081-70bd-5328-84e9-eafa6e1571be |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | b348594c-aa92-5824-aa1d-9100e407fcbb |  | note | Accept / Reject Criteria - As per specification
label | 21026f61-319f-51cc-8df5-c4263ee22729 |  | note | Frequency Of Inspection Or Test - In-process
label | 03f0a24a-ff3a-52ce-ba95-a30a16e8e5e1 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | 00be1059-c2a3-511b-bd89-c8f214277c8a |  | note | Records Required - NO
label | 9d53ff50-02a2-5e0c-8dd9-d2caffb1408f |  | note | DOWNER ENGINEER - W(10%)
label | 862440a7-ea01-5b68-9d19-2c7a755422d7 |  | note | SUPERVISOR - R
label | 86ce3157-0055-5411-be01-7a4ca4fa4612 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13 - Test and Check
label | be8cbf5c-8813-58af-b2a7-fbc15262e1a4 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | f4fdccd9-44f5-5b20-9968-d1cb68b3c2d5 |  | note | Accept / Reject Criteria - As per specification
label | 4a9fb2b0-d758-514e-bcbf-87ca9ea444f4 |  | note | Frequency Of Inspection Or Test - In-process
label | ca743131-4c75-59bc-a044-755e9fc036e1 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | 36d0625c-4265-500b-a23f-700ff3a2e10f |  | note | Records Required - YES
label | bdd6ef7b-ace7-5db7-9bac-0bae7115ff86 |  | note | DOWNER ENGINEER - W(10%)
label | 0d3001ee-8e6d-58c2-937b-43f4bb12e14e |  | note | SUPERVISOR - R
label | 2d3a038b-ae8a-5d59-9d37-ace65885905f |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations - Saddle Hill - Repair Surface Depression - Mill and Fill Method | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy Maintenance) - Saddle Hill - Repair Surface Depression - Mill and Fill Method | ce22070a-8edc-41b6-a14d-df3a45b92a1a
checkpoint-status |  |  | checkpoint | 1 - Preparation
label | 43653344-f1ed-5329-9016-9fd9e11332af |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 3aac4eb2-a51f-5239-97b7-fbd65470ba46 |  | note | Accept / Reject Criteria - As per specification
label | 8c1b001f-d1ac-5b08-b5fa-f5b29fb4f4b6 |  | note | Frequency Of Inspection Or Test - In-process
label | 6d6d8206-8ef4-5c0f-9d14-21ca066b0784 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041/Ground Distrubance Permit
label | 659dbd92-58dd-5f65-97fe-21444ded4808 |  | note | Records Required - YES
label | 2e372fb0-81f8-5c89-b8d0-f38a011d1c45 |  | note | ENGINEER - W(10%)
label | 9e75798b-9448-51da-b1db-b5491075112f |  | note | SUPERVISOR - R
label | 27cb4354-9c09-5925-9fa2-cbebc1e9b3e5 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Milling
label | a8ce589e-b564-5fdf-b375-9c98d3680f09 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | c3ac6c24-4cc2-5316-ad12-b6eec9f3e47b |  | note | Accept / Reject Criteria - Check depth with a straight edge or string line
label | 5c1073b6-290d-502e-b06a-033e95391798 |  | note | Frequency Of Inspection Or Test - Every 10m or based on the site length
label | f90290a6-3bc2-5298-b2b4-52f05fb89a4c |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | 7bd0a083-8a52-5487-921f-9a4fdde551f4 |  | note | Records Required - YES
label | f1d2bc73-cb59-59e5-bc08-c4215d69aa08 |  | note | ENGINEER - W(10%)
label | 4cb09840-4e8b-55c8-a144-bbad696a7781 |  | note | SUPERVISOR - R
label | 20bb7f28-adc1-50b2-aaaa-1fd8ddb013fc |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Base Layer Acceptance (Clegg Value)
label | 771391fe-a08f-5c42-adb1-56657554ff5f |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | f33899d6-b800-5175-918d-cc2a83699132 |  | note | Accept / Reject Criteria - Value of 25-35 needed
label | a786d06a-82fc-5862-b786-04eaa935a596 |  | note | Frequency Of Inspection Or Test - After every 1m
label | a8d63335-0d0b-5fb8-a2e2-82d65b24a7da |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041/Clegg Log
label | d3d1e57c-21f6-5758-9465-335795041be9 |  | note | Records Required - YES
label | d5d20f26-0067-5bda-89d8-09fe59be015b |  | note | ENGINEER - W(10%)
label | b92b7736-c967-509a-b880-958c33719bc7 |  | note | SUPERVISOR - R
label | 5c51a53f-e24d-565d-958c-f3908326581d |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Application of Binder (Tack Coat)
label | feb7887a-e27a-5efd-af65-38a36f751da4 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 53b1a88f-911a-5a8d-8da2-61da369cfa45 |  | note | Accept / Reject Criteria - As per specification
label | aeb3a686-3d44-5a3b-a144-d4954783ba7f |  | note | Frequency Of Inspection Or Test - In-process
label | 3f039a9a-3ed7-56d0-ab29-0d2948a5023e |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | 04096c9c-28db-530f-b31c-24df4cd77975 |  | note | Records Required - YES
label | 0d03056a-3778-5177-adda-eefe01c25a2e |  | note | ENGINEER - W(10%)
label | 7c300793-af30-5c7e-b23c-ec3bc5c3784d |  | note | SUPERVISOR - R
label | f3ed3564-ec51-5145-9afe-397045556251 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Premix Selection
label | d4111622-9884-516e-9ca0-80f0aec9f436 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 34c455fb-fb64-58fb-aef5-de6770e0c03a |  | note | Accept / Reject Criteria - As per specification
label | 5bba6028-b43c-5dd2-880f-03d7bf736c22 |  | note | Frequency Of Inspection Or Test - In-process
label | 2c95f3ff-e21c-5241-9def-bd015956cbc0 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | a7185cd7-508d-5abc-a2ed-8ce165c4b7fd |  | note | Records Required - YES
label | e166693d-7d87-505e-8ca3-59ca49207f9b |  | note | ENGINEER - W(10%)
label | 7d60180a-a822-5011-b2ae-a55482703202 |  | note | SUPERVISOR - R
label | 3314027a-eff3-52e0-8d10-b00240e69399 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Laying Premix Material
label | 9be4f0d8-4ac0-5c89-93ec-fa611cf5e9a7 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | b76c85b7-b418-5b4a-8479-64d4872968ba |  | note | Accept / Reject Criteria - Lay Premix in even thickness layers
label | e07c2653-3455-5a64-b0b8-314240955902 |  | note | Frequency Of Inspection Or Test - In-process
label | 02e18263-6a32-5bf4-8927-50a4627cf72b |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | ce954eec-857d-5bed-bcca-59efb317595f |  | note | Records Required - YES
label | b1fc3b1d-b470-5914-9459-3b7d4a9604d0 |  | note | ENGINEER - W(10%)
label | c0c183e0-787e-51f7-8202-b7bf1de76341 |  | note | SUPERVISOR - R
label | bbfe42c7-37bd-5592-8d72-13b24a7a3038 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Final Compaction
label | 3fd7db46-6622-51b4-85ea-7ca7dfc5b1ad |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 155d57ae-17c4-5bd1-93d4-c677f7fdecdf |  | note | Accept / Reject Criteria - As per specification
label | bf64d56f-d612-5ef4-9e26-c887c2925197 |  | note | Frequency Of Inspection Or Test - In-process
label | 9ba9da06-1e27-5dfb-b930-d1b6bed8699d |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | ea002927-a02e-5209-a515-09dd0c6887fa |  | note | Records Required - NO
label | 6bce4cba-1516-5b14-b99c-7233f96d8b92 |  | note | ENGINEER - W(10%)
label | 4bb5359e-2d38-5fc6-8e55-d5458892d931 |  | note | SUPERVISOR - R
label | 20b80291-18bf-5a5f-b60b-cbbde4f3823c |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Blinding
label | fcac3917-cde9-5441-8faf-ecfc47c6db3e |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 8349dd66-23f4-541b-a710-23cc03e58d98 |  | note | Accept / Reject Criteria - Blinding with sand and restore road marking
label | c2bb5b95-5027-553c-8492-8c133af04d49 |  | note | Frequency Of Inspection Or Test - In-process
label | e3a8e7e3-ec1c-5b18-8721-ddb0112cd152 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | c9da0f8d-eae3-5eb4-88d1-5bbc3586fd3b |  | note | Records Required - NO
label | 6f5bd7b6-bcad-541d-93fe-23a6b8c7e832 |  | note | ENGINEER - R
label | 6b2a2aac-8070-52ff-aa62-bdbbfa7464d4 |  | note | SUPERVISOR - R
label | 3389a76a-7dd8-51e1-b3a5-ecfdf43676e0 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Test and Check
label | 92c5f078-7d89-595a-a6a2-7c72c70f6a8c |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | c91c256d-50ff-5af7-aa18-94005f036ebb |  | note | Accept / Reject Criteria - Any depression must be less than 5mm
label | 3b66ce24-8a22-5337-acb3-3e47dee709da |  | note | Frequency Of Inspection Or Test - In-process
label | 25ecbedb-7303-55a0-8ce8-5307c39e2b30 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | 2fd35c5e-171b-5152-b430-6d8fc5d58d07 |  | note | Records Required - YES
label | 454a2947-5916-5feb-a814-30bfe2bf1f11 |  | note | ENGINEER - W(10%)
label | 8f6fef1d-b76d-569e-8c38-99510e4a816f |  | note | SUPERVISOR - R
label | e29b460b-95f6-52fd-b1e7-b9414db318c1 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - Carisbrook - Thin Asphalt Paving |  |  |  |  | Yes | ITP - Carisbrook - Thin Asphalt Paving | d43b0a28-fc79-4cd7-be10-179dec4e510f
checkpoint-group |  |  | section | 1 - Preliminary and General
checkpoint-status |  |  | checkpoint | 1.1 - Construction Programme Completion
label | eb3a62e9-53e2-5a0d-a289-27424cc4050b |  | note | VERIFICATION ACTIVITY - Confirmation
label | 9801ccc6-293d-5598-8e58-414923da028b |  | note | METHODS OR REFERENCE - Best Practice Contract Specific MMP
label | 95c2f78f-04a7-5ba0-9716-922ccd4941c3 |  | note | FREQ. - Before work commences
label | 8d74ef7f-d2dd-5cea-9163-1c237a2c3c41 |  | note | ACCEPTANCE CRITERIA - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date.
label | 6e048d03-31b7-55c7-af0a-5cc726a0cadf |  | note | INSPECTORATE W/H - Type: - W
label | 806b1651-b0f5-5c93-9591-15b48d9d7017 |  | note | Responsible Person - Renewals Manager
checkpoint-status |  |  | checkpoint | 1.2 - Approved RQP
label | 038d44cb-a397-50d5-842d-42e751c5bf08 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 52876848-378a-5af0-b20c-4af8283e7f7e |  | note | METHODS OR REFERENCE - Contract Specification
label | c788e535-d748-5361-b8d9-270088aa416f |  | note | FREQ. - Before work commences
label | 94dcd661-eeb2-53b3-ac25-4cb7cd12ace8 |  | note | ACCEPTANCE CRITERIA - Principal Acceptance according to guidelines in appendix 6.3
label | 36d10ea3-89fb-5261-ab01-10e9917c645c |  | note | INSPECTORATE W/H - Type: - H
label | 126c157a-b373-5efd-bf80-e176d2c91041 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. NZTA to approve
label | 472f9022-633b-57a6-a520-79d439609cd7 |  | note | Responsible Person - Renewals Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Traffic Management - TMP
label | 7985e11d-6248-55fe-bb9e-1a64249f1400 |  | note | VERIFICATION ACTIVITY - Visual check
label | 5f9605ae-f1e5-504a-b9a3-a3563d738c53 |  | note | METHODS OR REFERENCE - CoPTTM
label | 17d070db-5b68-5f83-b06f-daf1894f41df |  | note | FREQ. - Before traffic management set up
label | 235daaf6-8902-57ca-bbd9-f7e28617f024 |  | note | ACCEPTANCE CRITERIA - TMP checked and approved Plans approved Current EED (if applicable)
label | 4eb737c5-192b-5e48-927b-4cc1a0293f81 |  | note | INSPECTORATE W/H - Type: - H
label | cbe5d728-689b-5c96-9ea1-e066524d99ce |  | note | INSPECTORATE W/H - Description: - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | 8e79fd28-1dcb-5a80-9662-ee850dd82fa9 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Mix Design Verification for all mixes Check Laydown Trials are complete and compliant
label | 975ed882-70d1-5d4e-8ab7-aa881aa0de20 |  | note | VERIFICATION ACTIVITY - Confirmation
label | 8947402e-7f88-5ed4-9dda-f38dfe04de88 |  | note | METHODS OR REFERENCE - NZTA M/10, P/11, P23
label | 69e25a8d-34d4-5823-b1fa-ac038589950b |  | note | FREQ. - Before planning commences
label | d5ba513f-d5f0-5dc5-a8e5-1c80f26e299e |  | note | ACCEPTANCE CRITERIA - Mix Design compliant, current and relevant. Batching plant production capability is confirmed
label | 043f3da6-dfaf-5fe0-9f1c-e8a11855eea8 |  | note | INSPECTORATE W/H - Type: - H
label | 6d9e6da1-2116-5892-927d-bf15978c3108 |  | note | INSPECTORATE W/H - Description: - Hold point - No planning of on-site works shall commenced until the mix design is verified.
label | 38fa7c45-86f9-52f3-a0f4-236dd98be2e2 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Notification of intention to start work
label | 25a20f3e-4cee-58f9-b3c9-f6bd3cf60fda |  | note | VERIFICATION ACTIVITY - Notification
label | cad7f916-e9a1-59aa-be4d-d1e8dd3477ff |  | note | FREQ. - Before work commences
label | 5b6b88a3-c49f-5eb4-8b9a-c9dd17a9c7e0 |  | note | ACCEPTANCE CRITERIA - Letter drop to local residents. Greater consultation where required
label | 2de26881-f1d1-5cd4-af2e-dce85479bf3d |  | note | INSPECTORATE W/H - Type: - H
label | 5e3ca3f8-685c-55c8-978c-9de2a812c998 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | fbb61539-5b86-5893-bb97-8c581d2c6136 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Works Extents
label | 9670d0c8-8432-56ec-8328-1f82f043ba8c |  | note | VERIFICATION ACTIVITY - Confirmation
label | a4facf2b-9cc3-53f2-9b9b-7e0b7ffde62c |  | note | METHODS OR REFERENCE - Site Visit
label | 50f6d360-4081-556d-a55c-18cb66ffdc38 |  | note | FREQ. - Before work commences
label | 49f12f2a-9e76-5624-a4fb-e61e806449ad |  | note | ACCEPTANCE CRITERIA - Renewals Manager and/or Client to agree extents of project
label | 7575798e-c8f3-572a-9556-709956f2df20 |  | note | INSPECTORATE W/H - Type: - H
label | f5cbd29f-ae09-5063-b68b-01fa7aa0a67a |  | note | INSPECTORATE W/H - Description: - Hold point - Walk over site with Renewals Engineer and/or Renewals Manager and/or NZTA
label | 0ebbad10-b4ce-5d90-acfd-74c7bf328fdc |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - Pavement Marking Records
label | 98d080fc-a21b-55e4-aec3-c669d77c5262 |  | note | VERIFICATION ACTIVITY - Measurment Data
label | a57a3274-2b19-5010-9e92-0f7c41be613e |  | note | METHODS OR REFERENCE - Site Measure or Video Viewer
label | 175f5752-d28f-53cc-8849-2036d6f105b9 |  | note | FREQ. - Before work commences
label | cc9831e9-5cba-5f20-ae77-05f74e090d61 |  | note | ACCEPTANCE CRITERIA - Measure existing markings to aid reinstatement
label | 222cfd07-4107-5c32-b118-cf16e611baa5 |  | note | INSPECTORATE W/H - Type: - H
label | 06f4315c-1231-59fc-b1f0-4a9e0405fa9c |  | note | INSPECTORATE W/H - Description: - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | b228f3f9-f65e-55f2-aad3-03ff94f617b8 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Milling and Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | 795bd4e2-a037-5609-8e52-7570c2230897 |  | note | VERIFICATION ACTIVITY - Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth)
label | aac8fdd0-50f6-5089-9eb8-ed12fe1a90b1 |  | note | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | 3b816b9b-c016-52e7-916f-c22b20060b77 |  | note | FREQ. - Before work commences
label | 9d8eccc9-6972-5874-a41b-5760bab63291 |  | note | ACCEPTANCE CRITERIA - Zero service strikes
label | ea52b492-3a9d-5828-879a-82aaa0717aae |  | note | INSPECTORATE W/H - Type: - H
label | 72eb5be7-b0c6-542b-a943-fe35602b1e3b |  | note | INSPECTORATE W/H - Description: - Hold point - No excavation/milling is to be commenced until services are located and accounted for
label | 95e8ab35-3d76-5940-997f-596de2d154e1 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Stormwater Management
label | 169a1bc6-ebac-57d4-bef0-27191960f34a |  | note | VERIFICATION ACTIVITY - Visual check
label | f6705ed6-314f-5a29-89c5-f997d72fa3c4 |  | note | METHODS OR REFERENCE - On Site
label | 5bb96037-578e-5c53-8563-7322aba79b4e |  | note | FREQ. - Before work commences
label | d7be9f05-304d-5af6-8f49-76cf943f2ef2 |  | note | ACCEPTANCE CRITERIA - Mudtanks bunded or filtered to prevent mix from dropping in or runoff entering
label | 86e67da7-0ea5-594d-a9a1-4b7e819e0580 |  | note | INSPECTORATE W/H - Type: - H
label | bfe45a88-7d0d-5bf7-a0b9-522284447c49 |  | note | INSPECTORATE W/H - Description: - Hold point - No work to be commenced until protections in place
label | d89372a3-5877-5d99-a48b-218e30a01887 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Traffic Management - Setup
label | f46f5a49-55d5-50a7-8543-2ad7809f60f0 |  | note | VERIFICATION ACTIVITY - Visual check
label | 6b62eb4f-fe18-5b5e-8f3a-74f42aa26d2d |  | note | METHODS OR REFERENCE - Traffic Management Plan
label | 1fcf2506-45e1-5eda-8b4b-ffbebd4340e8 |  | note | FREQ. - Before work commences each day
label | 3c14eaf9-b5db-5e03-bd78-b4208906ca6b |  | note | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | 1f63b808-f5fc-5c08-b0b5-b63cb8c3e68c |  | note | INSPECTORATE W/H - Type: - H
label | 5d577568-3deb-5762-81fa-5a00785e3075 |  | note | INSPECTORATE W/H - Description: - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | 9edc1e82-0372-5674-9f70-920518e48ab3 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Milling Depths
label | 26aa447f-fb29-59ca-9d80-9b22affe8058 |  | note | VERIFICATION ACTIVITY - Measurement
label | 5fec89ac-c178-5117-b826-6e535d9ea901 |  | note | METHODS OR REFERENCE - On Site
label | 0bf74525-11e6-5017-baf4-ed5aae327137 |  | note | FREQ. - Measure each side of milling machine cut
label | 1ca41c7a-3b17-5c45-b27b-a7f9f390cf59 |  | note | ACCEPTANCE CRITERIA - Every 10m. Depth matches target
label | b584cb3c-4397-5f57-9c21-9504a91023ff |  | note | INSPECTORATE W/H - Type: - H
label | cd977b22-4292-5dce-9ec4-d09fd8683441 |  | note | Responsible Person - Site Foreperson / QA
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Service Covers Preparation
label | f37fe564-a480-53e4-8c02-a0504d8a647a |  | note | VERIFICATION ACTIVITY - Visual
label | d101cabe-a4df-501f-ab81-c19746fa9354 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 9517bef8-2907-57ea-81df-1af8d35db1ec |  | note | FREQ. - All Covers
label | 23214f20-fe9b-5c70-84f2-4e6061c1bd3f |  | note | ACCEPTANCE CRITERIA - Hand excavation around ironwork and adjustment to desired level (if required)
label | eb449897-f97a-5a97-9416-4a50d02f2a27 |  | note | INSPECTORATE W/H - Type: - H
label | 4c3de857-1337-509b-99d4-795da2d28366 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Additional Surfacing Preparation
label | fa383b0c-1c67-5588-b856-4f7f9c600945 |  | note | Side Roads; Accesses; Driveways; Dish Channels; High Shoulders
label | 6c55e476-8588-58ba-b4d2-03ac213b6b99 |  | note | VERIFICATION ACTIVITY - Visual Check
label | cfc00af6-cd69-5652-b7c3-975e9d964bb2 |  | note | METHODS OR REFERENCE - Per Design
label | 1b9f6a71-dd06-5a8a-90aa-5523baf6d84b |  | note | FREQ. - Before Membraning and Paving
label | 55dcd2e3-266f-593c-9eae-a0266c2fc576 |  | note | ACCEPTANCE CRITERIA - Have all areas of additional surfacing on the design been prepared, membraned and marked for paving?
label | 201efdc1-fef5-51f7-b15e-c5bede445dda |  | note | INSPECTORATE W/H - Type: - H
label | 34210244-5f41-5c3f-bc98-46b2cae8720e |  | note | INSPECTORATE W/H - Description: - Hold Point – All areas planned for AC are prepared ready for surfacing layer
label | ea9a47f4-1b85-5ed8-b522-c94ca445871b |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Over-Milling
label | fb0448d2-e835-5372-8f26-e9b6820004e0 |  | note | VERIFICATION ACTIVITY - Measurement
label | e55d9409-e333-5d68-b2fc-349ee1b92cdd |  | note | METHODS OR REFERENCE - On site measurements & photos
label | 07c36a94-a0b8-513e-8571-63e8f726cb45 |  | note | FREQ. - Prior to pre-level
label | d5175815-5cd5-5614-b46f-7879435195ce |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree need and extent of over-milling and infill.
label | 8c4a1aba-ba85-5535-98df-6744d63a13ce |  | note | INSPECTORATE W/H - Type: - H
label | ec8f052e-f356-5c34-86fb-0807e2cb7ab2 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Pre-Level
label | f4a83f8c-2d7c-5b5a-88c9-d1897a99aedd |  | note | VERIFICATION ACTIVITY - Measurement
label | dbf0a056-c524-5514-9fea-d5309161b509 |  | note | METHODS OR REFERENCE - On site measurements & photos
label | df910f6c-bf39-512b-aae2-400c17662ac4 |  | note | FREQ. - Prior to surfacing
label | 67e01e60-b14c-58e3-804e-9099ac7f6866 |  | note | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree pre-level extents
label | 5863f5dc-2760-5e41-abe2-d682da15828b |  | note | INSPECTORATE W/H - Type: - H
label | e19266d2-4ecb-5532-a38e-17aff0e7a2a4 |  | note | INSPECTORATE W/H - Description: - Hold point - Inspection and agreement by NZTA
label | bf74d6f2-920d-5199-b80a-640b2f2f0b99 |  | note | Responsible Person - Paving Manager
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.9 - Membrane Sealing
label | 4a31a67b-4da5-5a6e-81be-968a95fc4661 |  | note | VERIFICATION ACTIVITY - Visual
label | d803abb7-977b-5fa3-b776-1074c705d900 |  | note | METHODS OR REFERENCE - On Site
label | a306a5fe-7e5a-5547-8e7a-96c7ca5d7323 |  | note | FREQ. - Prior to surfacing
label | d8f267fb-cb4f-572d-8170-ce2f12f1c1a3 |  | note | ACCEPTANCE CRITERIA - Membrane seal meets design and extent. Sealing Docket record kept
label | c420df97-30d9-5078-8ed7-f56f77cb250f |  | note | INSPECTORATE W/H - Type: - H
label | aede5387-f7c2-5d59-8e9a-1ea2557ed0c7 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Paving Structural
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | 19318d72-d612-5aa9-8e63-307814439238 |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | 70d709e5-890a-5474-bf7d-0b082d3d8033 |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | 86334b43-c900-5db0-8238-f78fc0d9fbe2 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 1ea9917d-5a21-51a2-93ad-9d0bab115447 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | a333b271-47de-517f-82fa-31256f8d4b74 |  | note | INSPECTORATE W/H - Type: - W
label | 621b27f1-939c-5c93-a344-50bd0d36ad43 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 3b8dfdbb-8997-5112-a91a-10d7f30356af |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | f0706be0-efb9-524e-9e21-3cb398a16765 |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | 78358874-b4b8-5a00-a3e6-1574d6318165 |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | f5dca5ff-19d7-5cd4-aae8-725391ee73e5 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 3ea711e9-ece9-5c10-8f00-7fdb80db7544 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 4018e59e-87c3-5584-a9e8-e4cb7a2043b5 |  | note | INSPECTORATE W/H - Type: - W
label | 73c4e05e-55be-52bb-a575-2ca83bb0f4f3 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 03aacff5-0ae1-5472-807a-e7a27c11360e |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | cf2bdb85-8cb0-58f7-94b0-d22f48bfa1be |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | 99d05001-3d9f-5bb2-9d65-93080da6f335 |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | 0d564243-383a-58a8-b2db-91068c1b5328 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | eeabad15-5f98-5b3d-8274-06d1f3f004ef |  | note | INSPECTORATE W/H - Type: - W
label | bf82582f-b1e1-551a-84ea-6cd0e14ebfb7 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | e9717ec7-4b4c-5076-9176-f256284991c7 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | dc7a6c42-fc7e-5044-83e8-c0847449ec4a |  | note | VERIFICATION ACTIVITY - Visual
label | 85117449-548d-5a1a-9b3a-8a800b934029 |  | note | METHODS OR REFERENCE - NZTA M/10
label | fbb379c9-bcd8-531f-a1e1-c34a96ba8f9e |  | note | FREQ. - Prior to Shift
label | 46a43a39-e9ca-568e-9790-0b42455ed0bc |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | 8d97b057-8834-593f-ab9b-07567d50b531 |  | note | INSPECTORATE W/H - Type: - W
label | 4044b2c5-44db-54c8-b507-b64a4e060891 |  | note | INSPECTORATE W/H - Description: - Paving Plan and Crew Briefing Plan completed prior
label | 86d727d7-9d8c-5fdd-8fc0-1b51b6d59825 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | 3febf8ee-224d-5485-b146-1726cafe874b |  | note | VERIFICATION ACTIVITY - Visual
label | b8d9375b-d848-5f4f-a419-f18cb87e9635 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 4ccea2fa-5934-558f-810b-25626efc7de4 |  | note | FREQ. - Prior to Shift
label | ef89382b-e822-5e48-89bb-41fffcfd4a27 |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | d5cb92d1-2800-52af-8ab3-6e3d4bb737e3 |  | note | INSPECTORATE W/H - Type: - W
label | 73e6c997-08a0-5997-aa15-3b755c87368c |  | note | Responsible Person - Paving Supervisor / QA Engineer
checkpoint-status |  |  | checkpoint | 3.4 - Mix Inconsistency and Deficiency
label | ce15b099-e259-52a7-bf77-cba23e7300b9 |  | note | VERIFICATION ACTIVITY - Visual
label | a473edc4-55a2-536f-8a6d-bbf93078e8b3 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 06d780d6-bf82-5ed3-80b3-6222639dd9bc |  | note | FREQ. - Continuous
label | 2d20002d-0737-53aa-b945-df35a643cf46 |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | 394e3409-192c-5ec8-8ff4-d048e905c195 |  | note | INSPECTORATE W/H - Type: - H
label | 2596a48f-bd1d-5b7f-b049-dd462c1ee62d |  | note | Responsible Person - Site Foreperson / QA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Load Locate
label | 4e8606b6-ae06-5330-bcc7-bb349365cc9a |  | note | VERIFICATION ACTIVITY - Measurement
label | 8f9796f5-e347-5b59-9bc4-c9cde091b7b2 |  | note | FREQ. - Every Load
label | b88df59f-91a1-54be-8ffb-5f73d2225e9e |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
label | c2ca31f8-fbed-5df2-9300-a7df0877bb7a |  | note | INSPECTORATE W/H - Type: - W
label | 6a47d543-283c-5a39-b75b-4e9bc049923c |  | note | INSPECTORATE W/H - Description: - Per standard practice
label | ea8648a2-6449-56c0-8e3c-3c7b87a14dff |  | note | Responsible Person - Quality Assurance Engineer
checkpoint-status |  |  | checkpoint | 3.6 - Laying Temperature
label | 1b69c51f-a402-594a-985c-c1bc6350085f |  | note | VERIFICATION ACTIVITY - Confirmation
label | 1f1155d8-e9cd-5335-8305-472328598520 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 6015b56f-7cde-5bb5-be14-bd87af47fa71 |  | note | FREQ. - Every Load
label | a2d0e77e-d6f0-5b14-825a-2771d01147be |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | eb41a777-ba56-5bb9-88aa-ca571805a40a |  | note | INSPECTORATE W/H - Type: - H
label | bd27d3d8-87a4-5759-97b5-0ee8303dc919 |  | note | INSPECTORATE W/H - Description: - Hold point - Reject mix for non-compliant temperatures.
label | f9ed0cac-7fc2-58d6-87d1-53e32492b690 |  | note | Responsible Person - Quality Assurance Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Compaction
label | d6d33621-2e66-52ff-82fa-4f871e1bc027 |  | note | VERIFICATION ACTIVITY - NDM Testing
label | fead0994-0421-5b03-952f-945a1c2e6f1d |  | note | METHODS OR REFERENCE - NZTA M/10
label | bf78b0d7-eac2-5283-b31f-10a2cfe9b293 |  | note | FREQ. - Minimum: 1 Test per 300m² within Mat. 1 Test per 100m of joint.
label | 8dc24e8d-8ca9-5656-9d10-7386cef48a30 |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | f8955585-35c0-5c4f-847c-2eefb9c945d0 |  | note | INSPECTORATE W/H - Type: - H
label | c1caa508-de76-53f9-b11b-c23fcdea2a63 |  | note | INSPECTORATE W/H - Description: - Hold Point - No Wearing course paved until any non-compliance is sorted
label | 34621f08-e548-55b1-8da6-6adb228239c4 |  | note | Responsible Person - Quality Assurance Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Roughness
label | 036cc144-5038-59eb-a741-b36d12c05d6e |  | note | VERIFICATION ACTIVITY - NASSRA Testing
label | 4986953c-a25e-558e-b54a-0c77dfe2898e |  | note | METHODS OR REFERENCE - Contract Specification
label | 8ca719a0-008d-5bab-8420-0717155e1713 |  | note | FREQ. - post construction
label | 0192859d-0990-57f3-8e97-0b953ba59050 |  | note | ACCEPTANCE CRITERIA - NASSRA rolling meter average under 60, max of 70
label | f5eb84b7-80d4-5c9f-a152-4674f7fa6fdc |  | note | INSPECTORATE W/H - Type: - H
label | 50d5c8fa-4816-52d2-b63f-e61942aa5ce2 |  | note | Responsible Person - Site Foreperson
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Paving Wearing Course
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | 815c77b3-d967-5599-90ab-535f5761726c |  | note | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | 6605c05b-833b-522f-966d-fea9e20fdf37 |  | note | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | ed1da50b-7de1-5be4-846e-872c439314df |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 545d0a14-f6de-5f70-8614-7fd4aa305122 |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 4a7e6433-3893-58e5-8fe3-c476770f782c |  | note | INSPECTORATE W/H - Type: - W
label | bf71fa80-cab1-5d2e-9602-9e17d82d2a3f |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 6f04d92a-601b-5f81-979b-549347e2b474 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Binder Content
label | 246ccdc0-2430-54ea-b29f-22e559b38cdb |  | note | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | 5a40c0a3-7aa0-5c83-a67e-feab47b26c8f |  | note | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | 097e8bad-9269-5ee9-b25d-98fb517eb6a1 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | 5e1682e9-9f9d-5d38-afb2-d62abffc6bad |  | note | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | 54569e60-cb4f-5ad5-9fec-f21f87f33359 |  | note | INSPECTORATE W/H - Type: - W
label | b0bef69e-f182-5d8c-8859-46917669aa5c |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | 32fd8ae5-f2ab-5a88-9bad-fe40f2284222 |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | 6809db27-1a53-589e-9799-5c92a7f73ceb |  | note | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | 96f0b24c-b5dc-5cb3-ae7b-c7755c86220e |  | note | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | d682a2c7-586e-5911-b3d8-526e267f8251 |  | note | FREQ. - 1 per 200t or maximum of 3 per production lot
label | ed91d0f2-72ef-526f-b6d7-2d223cf7787e |  | note | ACCEPTANCE CRITERIA - Per Mix design
label | 9a5b5b0b-ac06-5456-b032-2664e956f890 |  | note | INSPECTORATE W/H - Type: - W
label | d7056436-3f03-5dbe-8b3a-1c2c87d9c4a6 |  | note | INSPECTORATE W/H - Description: - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non-comformance
label | b7406fae-57da-5310-b6aa-351e4834a04b |  | note | Responsible Person - Paving Manager
checkpoint-status |  |  | checkpoint | 3.2 - Preparation
label | 35682603-e458-507a-bc58-a4d40a1dd5a1 |  | note | VERIFICATION ACTIVITY - Visual
label | afc0d8ab-bdcc-5441-abfa-8b2f255120ec |  | note | METHODS OR REFERENCE - NZTA M/10
label | 892011cb-1670-5440-9d4e-653a3a85edc6 |  | note | FREQ. - Prior to Shift
label | 9bb0c048-8aff-5085-b9e1-10861f5f5dbd |  | note | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | 9140c0d3-5af6-502d-938e-c0bf8487c4ab |  | note | INSPECTORATE W/H - Type: - W
label | 0aeeb7bd-9e79-5fbd-a142-372afa7a5cf0 |  | note | INSPECTORATE W/H - Description: - Paving Plan and Crew Briefing Plan completed prior
label | ed09afe7-1889-557d-b646-9161f020d49b |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.3 - Joins
label | 5d0334ba-7836-5993-b81b-e5d00cbc273d |  | note | VERIFICATION ACTIVITY - Visual
label | 5728c3da-440f-54db-aba0-cba7b123e85c |  | note | METHODS OR REFERENCE - NZTA M/10
label | 102515d9-db73-5fc4-9397-cba639e29fc2 |  | note | FREQ. - Prior to Shift
label | f9d7c756-5924-5cf8-99c3-7571a9614fcb |  | note | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | 62dabf7c-fe91-589c-80ee-0fa37ee0b7e3 |  | note | INSPECTORATE W/H - Type: - W
label | 80ee51bc-995b-5657-a77a-a78018661b3b |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 3.4 - Grade 3 Membrane Sealing
label | d24c96a5-0b98-5082-99b8-59f05c04d001 |  | note | VERIFICATION ACTIVITY - Visual
label | 3d60f410-daa3-5c28-88b6-58e7ebab532b |  | note | METHODS OR REFERENCE - NZTA M/10
label | d6dce558-b268-5da5-a49b-50e03ef68ca2 |  | note | FREQ. - Prior to Paving
label | 0e3e6052-b973-509a-8503-95a29c825b67 |  | note | ACCEPTANCE CRITERIA - Applied 2.0l/m² residual
label | deda0ce7-fdaa-5c54-9d97-b8442f477d5d |  | note | INSPECTORATE W/H - Type: - H
label | fc288bf3-0a36-51e3-a9af-ac7b11e7c136 |  | note | INSPECTORATE W/H - Description: - Hold Point - No paving until Membrane Done.
label | 657459a8-59fe-50e4-893c-cb0e4a8d2467 |  | note | Responsible Person - Paving Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Mix Inconsistency and Deficiency
label | 4806eaf8-1dac-5627-a50f-2958b674d955 |  | note | VERIFICATION ACTIVITY - Visual
label | 77a5e756-e6a1-57e3-a108-abaac7149364 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 9cd7d44f-b76c-535c-9fd0-ae69a5325356 |  | note | FREQ. - Continuous
label | 1005d690-77f2-5023-8b24-191a094d9c0d |  | note | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | ff10dfd0-f767-5f11-9bbb-b29ce2fba6db |  | note | INSPECTORATE W/H - Type: - H
label | aa2153ce-725f-5647-89ad-01f469ecdf1d |  | note | Responsible Person - Site Foreperson / QA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Load Locate
label | 67e42b7c-0e36-5574-ba81-43f033a266ef |  | note | VERIFICATION ACTIVITY - Measurement
label | c27958db-af0f-54d7-9f49-270c47800825 |  | note | FREQ. - Every Load
label | 1ef32d3b-834b-5e3e-8b74-40c057678731 |  | note | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
label | 25c70d37-6e90-5282-8cd4-0997ef3ddacb |  | note | INSPECTORATE W/H - Type: - W
label | a8baf50f-b586-5c9f-8df1-7fd5f888782e |  | note | INSPECTORATE W/H - Description: - Per standard practice
label | f51b7ab7-927a-55f3-8142-92e703427172 |  | note | Responsible Person - Quality Assurance Technician.
checkpoint-status |  |  | checkpoint | 3.7 - Laying Temperature
label | b2a9b212-2047-5f4b-bb82-21f81268c000 |  | note | VERIFICATION ACTIVITY - Confirmation
label | ce8b219c-0a81-5032-bca2-0efc201ab070 |  | note | METHODS OR REFERENCE - NZTA M/10
label | a802d3bc-ba3d-5a42-8e7b-0727df427215 |  | note | FREQ. - Every Load
label | 9be68aba-807a-567b-b322-6949cc1a1e96 |  | note | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | 318b8922-4364-50d4-b11a-8cd6ae5a0547 |  | note | INSPECTORATE W/H - Type: - H
label | 06ffa92a-afcb-5a0e-925a-a9ad26e0434d |  | note | INSPECTORATE W/H - Description: - Hold point - Reject mix for non-compliant temperatures.
label | 7b93cba1-77cb-5515-8db7-b035d96fb8ea |  | note | Responsible Person - Quality Assurance Technician
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Compaction
label | 56d1dead-7f93-5fe0-9cff-122c12c48ac7 |  | note | VERIFICATION ACTIVITY - PQI Non-Nuclear Gauge/Cores. Or Non Distrctive Method Testing.
label | de0939a2-dc74-5c2d-a9ae-a80cb78e9a30 |  | note | METHODS OR REFERENCE - NZTA M/10
label | 51778c0a-f608-59cc-a614-5bad07e5fac5 |  | note | FREQ. - Minimum: 1 Test per 300m² within Mat. 1 Test per 100m of joint. Minimum 8 cores on Mat and 3 on Joints as Per M10:2020.
label | 80eca107-413d-5e1f-96ce-24c69e2ce9d7 |  | note | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | 6afb68f2-2693-515b-a491-9e415c8f0609 |  | note | INSPECTORATE W/H - Type: - W
label | 7ed506bc-37e5-55da-9f7b-9805e1fc7093 |  | note | Responsible Person - Quality Assurance Technician
checkpoint-group |  |  | section | 4 - Site Reinstatement / Clearance
checkpoint-status |  |  | checkpoint | 4.1 - Post-seal Area Check
label | 1355a9ce-8a52-5570-8e0b-9f5566004364 |  | note | VERIFICATION ACTIVITY - Measurement
label | dce6ffc9-a1ff-578e-8a33-48dcec8d5415 |  | note | METHODS OR REFERENCE - On Site tape-measure
label | 9a04a368-4b26-5632-a5c9-1471aff915fc |  | note | FREQ. - After Surfacing
label | c115e866-9418-5c93-b0d7-da1161744a57 |  | note | ACCEPTANCE CRITERIA - Check sealed area meets design
label | 7dae44ec-4d41-5539-834d-916e7de08855 |  | note | INSPECTORATE W/H - Type: - W
label | 7dcad571-aa09-51ac-b4bd-bb4df00d44f4 |  | note | INSPECTORATE W/H - Description: - Notify Renewals Engineer or Renewals Manager
label | 18143a56-fe2b-5f32-8cb5-5378ec420373 |  | note | Responsible Person - QA Engineer
checkpoint-status |  |  | checkpoint | 5.3 - Service Covers
label | 4b45e7e7-328b-524b-b27b-e2183f4d03f2 |  | note | VERIFICATION ACTIVITY - Measurement/Visual
label | cf5e0e24-5d95-53f6-bf4d-23cee4f5d15f |  | note | METHODS OR REFERENCE - On Site
label | 20f08455-249a-5f52-8a7b-f61c32de384d |  | note | FREQ. - After Surfacing
label | 7fc42072-fda4-5d68-a6ad-0e0ea69c9c7f |  | note | ACCEPTANCE CRITERIA - All service covers are checked and adjusted (if necessary) to finished level
label | e5c2f721-f95c-52ba-9a3b-f95b76450c22 |  | note | INSPECTORATE W/H - Type: - W
label | 0fa538ea-a37b-5faa-8eb3-c76280f761b4 |  | note | Responsible Person - Paving Supervisor / Foreman
checkpoint-status |  |  | checkpoint | 5.4 - Joint Sealing
label | e1550d38-876e-5277-bfa6-e5f61b84dc0e |  | note | VERIFICATION ACTIVITY - Visual
label | b15b2baf-34eb-524d-9437-367728fd0a5f |  | note | METHODS OR REFERENCE - On Site
label | 48e17d2f-24de-5a08-a1f0-0beb93cc0714 |  | note | FREQ. - After Surfacing
label | 5dd386ae-bfdd-5018-88e7-63b286fef81a |  | note | ACCEPTANCE CRITERIA - Check cold joints are bandage sealed
label | 3a66c19a-ac28-5009-a732-8db45b8cdb64 |  | note | INSPECTORATE W/H - Type: - W
label | 2c584be9-d9b7-525f-b71b-82e1c5b859ad |  | note | Responsible Person - Paving Supervisor / Foreman
checkpoint-status |  |  | checkpoint | 4.2 - Road Marking
label | 603f451d-5134-529d-881d-218d8d303149 |  | note | VERIFICATION ACTIVITY - MOTSAM
label | e8d3a6b7-cb3e-5a0e-af86-ce5ff866fa09 |  | note | METHODS OR REFERENCE - Visual inspection
label | 375430ca-f3c1-5692-8873-1a2a004a5332 |  | note | FREQ. - All markings
label | 07d353e3-237a-5e2a-96ce-8b9178d1b5f3 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, or per design
label | a7e721fd-f1ec-5df9-a365-6953b01a29fc |  | note | INSPECTORATE W/H - Type: - H
label | d1c593fc-b1bd-59bf-b3d5-51b53914cd1e |  | note | INSPECTORATE W/H - Description: - Hold point – Site TTM cannot be removed until markings reinstated
label | 5fe36e84-212b-5d15-ba28-abc55a646dec |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 - Other Traffic Services - Marker pegs/ Signs/Markings/RRPMs Replaced
label | e9817f6d-68b5-5b43-a66d-aaafcdaedaf6 |  | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | 43e73c05-af93-5ed6-989f-e26b5a4cebcd |  | note | METHODS OR REFERENCE - Visual inspection
label | afe55108-caa3-5c3b-ad0f-37d98ea469ca |  | note | FREQ. - All signs/markers
label | 0a03f09d-7bde-5b2a-bf3d-8538330f2285 |  | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | 1112c033-b204-5671-86f1-76fc3a11ea3e |  | note | INSPECTORATE W/H - Type: - H
label | c4bad8c7-f2e7-5d7c-93c9-d9733c588656 |  | note | INSPECTORATE W/H - Description: - Hold point – Site TTM cannot be removed until marker pegs, signs, markings and RRPMs reinstated
label | 4b6fcbc4-1c98-571e-bb19-abac3598d86c |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Stormwater Management Controls removed
label | 6938830c-72db-5933-9ba1-95564911a6b4 |  | note | VERIFICATION ACTIVITY - Visual check
label | ae3cd345-16a9-5158-9858-098bed077df0 |  | note | FREQ. - All installed measures
label | 3ed18d67-d686-5f38-a92c-5c0f162b7d51 |  | note | ACCEPTANCE CRITERIA - Installed controls are removed
label | 36a904dc-af1b-51b0-b435-2bb28755e6df |  | note | INSPECTORATE W/H - Type: - H
label | 147c70ce-aba0-55ba-a129-10de1245c115 |  | note | Responsible Person - Paving Supervisor / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Traffic Management Removed
label | 77a3867b-a8dc-5501-985d-f59331ed8fe9 |  | note | VERIFICATION ACTIVITY - Visual check
label | 2434663e-593d-5c7c-85cb-9a75195e9370 |  | note | FREQ. - When safe, after all physical works completed
label | 681e4454-faa6-5d46-8c9e-8bc658f6513b |  | note | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | 9553d2b4-8aa4-5753-af8f-02bc253392cc |  | note | INSPECTORATE W/H - Type: - W
label | dc280ada-a690-52c7-9476-a165295c7e8c |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 4.6 - Site left clean & tidy
label | ccc4240d-8a60-5ebf-960d-1317037d0e06 |  | note | VERIFICATION ACTIVITY - Visual check
label | dccb88cb-08a3-57f3-affb-0787727189fe |  | note | FREQ. - After vacating site
label | 64fd11ce-02ea-56f7-b216-9325de2a31fa |  | note | ACCEPTANCE CRITERIA - Stockpiles removed; Plant removed; Litter cleared from site
label | 4ba885c6-1031-5a92-a18d-d235cd35fa78 |  | note | INSPECTORATE W/H - Type: - W
label | 8e17e3d5-13e8-57ac-b20e-07639be98eed |  | note | INSPECTORATE W/H - Description: - Invite NZTA to carry out joint site inspection to inspect site.
label | 9dd6b020-5c43-5436-a19b-43db158c52f8 |  | note | Responsible Person - Paving Supervisor
checkpoint-group |  |  | section | 5 - As Built Records
checkpoint-status |  |  | checkpoint | 5.1 - Collect asset data
label | 62ed0fcd-ec24-5619-9754-0f046ee9f4e2 |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | e14c390a-fd29-50b9-8955-47668f9784ec |  | note | FREQ. - During construction
label | 09d31ff2-c5b3-5240-a780-ae1125a22b47 |  | note | ACCEPTANCE CRITERIA - All relevant as built information collected.
label | 8ddf9008-570f-5b2c-88ae-f32880429fc9 |  | note | INSPECTORATE W/H - Type: - W
label | f3542804-41c2-5ab3-90d2-abbd0e9cff96 |  | note | Responsible Person - Paving Supervisor
checkpoint-status |  |  | checkpoint | 5.2 - Enter asset data into RAMM and/or register(s)
label | 31c370a6-f860-5d88-8388-9fd2d2d4206f |  | note | VERIFICATION ACTIVITY - SHDOM (SM050)
label | da3ee97f-bd9f-53b0-b51a-63ec03f37bfd |  | note | METHODS OR REFERENCE - RAMM
label | 4a50ac7f-e605-522a-ac4d-7d90cf5a8761 |  | note | FREQ. - At completion of work.
label | 09019591-e091-5c51-a820-21db905cd293 |  | note | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.
label | 3c817d63-e791-5bcb-9147-ed61029dc6e2 |  | note | INSPECTORATE W/H - Type: - W
label | 6050741c-e6d8-56ae-9028-f09923a564c5 |  | note | INSPECTORATE W/H - Description: - Data entered by 20th of follow month after month of completion
label | 212af931-a92c-5459-ab0b-5344ac6dd7a7 |  | note | Responsible Person - Asset Information Manager
checkpoint-status |  |  | checkpoint | 5.3 - Construction Completion Report
label | ac63f842-f390-53ca-b421-9932af5636a6 |  | note | VERIFICATION ACTIVITY - Confirmation
label | aad4a43c-87c3-50fd-9167-00395d9e945c |  | note | METHODS OR REFERENCE - Contract Specification
label | b9807523-f1e1-5272-ac05-9d40f9feac58 |  | note | FREQ. - At completion of work.
label | 04e8a83e-954a-57d5-b5e1-c2acc8bf608c |  | note | ACCEPTANCE CRITERIA - Checked and approved
label | a3a6c695-5403-5bcd-bcc5-546c984e7d0d |  | note | INSPECTORATE W/H - Type: - W
label | 7ed355d5-b818-5c65-bacb-37e01832bdce |  | note | INSPECTORATE W/H - Description: - Completed within two months after Paving Wearing Course
label | 0089c83f-e5d9-5993-9d5b-d5bb0aa19d8e |  | note | Responsible Person - Renewals Engineer/ Renewals Manager
checkpoint-no-status |  |  | checkpoint | Quality Assurance Close Out
text | ae6444a6-7692-51b4-b296-74ceb255261a |  | textbox | Quality Assurance Close Out by - Name:
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | ITP - CONOC Operations - Milton - Repair Surface Depression - Mill and Fill Method | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy Maintenance) - Milton - Repair Surface Depression - Mill and Fill Method | d72d31b1-f386-437d-84ce-2021842c11a3
checkpoint-status |  |  | checkpoint | 1 - Preparation
label | cb3644e4-c353-5dbd-a2b1-ab74289e4f41 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | ae360f53-4c2a-5745-ba6d-d6377f727d62 |  | note | Accept / Reject Criteria - As per specification
label | d078d0b9-4852-5755-9338-4b9b33f61de1 |  | note | Frequency Of Inspection Or Test - In-process
label | bda67843-1f97-5484-b2c8-0c48bd2dfe57 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041/Ground Distrubance Permit
label | 03139df1-5f3c-5ade-aa53-052f0f3d1104 |  | note | Records Required - YES
label | a4c0b21a-2070-5f72-8952-dd4bf3997a4a |  | note | ENGINEER - W(10%)
label | add3860f-9ead-5ddd-8a06-8d5d42c23d93 |  | note | SUPERVISOR - R
label | 879ab706-0d6d-5821-9ece-df6b9bc9abc7 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Milling
label | a8617756-5d52-597b-ac5b-194c5834d12e |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | b3686ade-a5e0-55f3-8e82-edc9a881d684 |  | note | Accept / Reject Criteria - Check depth with a straight edge or string line
label | c754a63e-2581-5133-b45e-f178397199dc |  | note | Frequency Of Inspection Or Test - Every 10m or based on the site length
label | c97495a3-c828-5d8f-aa4a-4aa0d9640ef0 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | da4f192d-9350-59ef-9cb5-5876e01cf578 |  | note | Records Required - YES
label | bab6387a-bbd5-5d96-8884-66f7b1f075d8 |  | note | ENGINEER - W(10%)
label | 0820df52-ef44-5184-9e24-e4b58039ce51 |  | note | SUPERVISOR - R
label | f6d354d6-243d-5f0e-9f34-6ebd2649ef3f |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Base Layer Acceptance (Clegg Value)
label | f3773bc5-5115-5eef-9ac7-5acfe5545477 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 5a63df8f-a0dd-5aa8-a88f-9f38ac64f8d0 |  | note | Accept / Reject Criteria - Value of 25-35 needed
label | 92fdc297-bb9c-5de3-bab7-3dae58031de0 |  | note | Frequency Of Inspection Or Test - After every 1m
label | 49083900-c99d-5dad-bdb5-16556dc0b98d |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041/Clegg Log
label | d11a2532-ee0a-5522-8de5-fbcf54b423bc |  | note | Records Required - YES
label | 7a083698-d660-539b-bfbc-1c06dc28e03c |  | note | ENGINEER - W(10%)
label | 09510467-2979-5905-8568-bae12427d7f1 |  | note | SUPERVISOR - R
label | e82f82b6-1b15-5c3e-a3df-20067b4ebeb7 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Application of Binder (Tack Coat)
label | ea6cc74b-a89d-51ef-956f-652914fd79cc |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | af90ce0f-b651-525b-9803-8bf95c8d1c89 |  | note | Accept / Reject Criteria - As per specification
label | da154616-e0a8-5c89-bad0-6fcb93bcc95f |  | note | Frequency Of Inspection Or Test - In-process
label | 713e4d70-e4ba-56de-9589-8fe46dfc4919 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | 6046431c-f7e8-583c-8544-6f048bb9856d |  | note | Records Required - YES
label | 4ce75996-8dda-5780-9eaa-ad3d188b90fe |  | note | ENGINEER - W(10%)
label | d7b37600-2d72-5259-b91c-374e1e600713 |  | note | SUPERVISOR - R
label | a663d452-a519-51d1-825e-93250af0c288 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Premix Selection
label | bb48169d-9110-518a-8f9e-e578e88ce4c1 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 9e7465e8-6fcd-5a79-9c19-cdf5090807ca |  | note | Accept / Reject Criteria - As per specification
label | 4a9c818c-4fb2-5bb5-80ba-2560fda6afae |  | note | Frequency Of Inspection Or Test - In-process
label | adbf59f8-e8ff-5908-b579-5d7eda9a6148 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | d088f230-dc54-57be-a9f9-017e483128c6 |  | note | Records Required - YES
label | 6b03f61a-5298-5043-98b3-9698c92b12c7 |  | note | ENGINEER - W(10%)
label | 701adff6-a3f0-58e8-bb73-4a6e0cef3914 |  | note | SUPERVISOR - R
label | 6f11ff57-6ac2-5af4-9075-d4f7001903c6 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Laying Premix Material
label | 9dab60ea-faa2-54c0-9cba-a51dc9495b78 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 7d70b781-b11a-5909-ae89-03353087e4d8 |  | note | Accept / Reject Criteria - Lay Premix in even thickness layers
label | 5cacaa24-422c-5551-913d-ce774c6f887f |  | note | Frequency Of Inspection Or Test - In-process
label | 7cf05f35-a6d7-59b8-b4e6-28ccfaafb8c4 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | ec487a6b-d9ea-5fc9-8e83-fe39462f1cf3 |  | note | Records Required - YES
label | c17d9f57-984e-52bc-bbc7-8275957ddcef |  | note | ENGINEER - W(10%)
label | e0d84ab9-fa79-5091-b8eb-d6a3da9174aa |  | note | SUPERVISOR - R
label | a7129618-82ac-562e-b081-661a01fecadb |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Final Compaction
label | 1b6f7da6-bfa2-5148-80e9-e2faa4b31140 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 124e7f18-1c60-5346-8078-0a893bb9b3ef |  | note | Accept / Reject Criteria - As per specification
label | aa408ec5-87bd-51df-9820-b346ffe04560 |  | note | Frequency Of Inspection Or Test - In-process
label | 3833ac8d-ade1-5768-8301-055030680a81 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | f321421e-cbc0-5f13-a325-91c19d58e207 |  | note | Records Required - NO
label | e1f907d6-0525-5e6f-9431-4ab5b9df9965 |  | note | ENGINEER - W(10%)
label | 2c5e42be-841b-51d3-8e96-6e1decd40840 |  | note | SUPERVISOR - R
label | 6a66b467-ebd6-5456-ad5e-82996cdfc1ae |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Blinding
label | e7a5f781-8852-5b0c-88e4-f16d2e8f5ab4 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 8b7e94bf-0f14-5ac0-9909-11b5a80c59c9 |  | note | Accept / Reject Criteria - Blinding with sand and restore road marking
label | a5218372-d67f-583e-bb59-689495936ea7 |  | note | Frequency Of Inspection Or Test - In-process
label | 14b01eaf-54a1-5633-95d6-488ff6be34ff |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | 78da1b18-4bd1-5355-9002-1e36daeaaeff |  | note | Records Required - NO
label | 5720c707-224c-5a75-9037-54e113ee49df |  | note | ENGINEER - R
label | 03d2374e-fa55-5f76-9425-690dab207db4 |  | note | SUPERVISOR - R
label | 12e9c280-50bd-57a0-8c54-fffe18eeb0f5 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Test and Check
label | ce11e525-0145-591b-bc9e-cc4ea7f4b451 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | bd0e87bb-1c23-5667-a6c9-b976058f9b9f |  | note | Accept / Reject Criteria - Any depression must be less than 5mm
label | 6453e902-6f6e-52e6-b74f-030724fc7824 |  | note | Frequency Of Inspection Or Test - In-process
label | 40d316b8-d33e-5387-b431-7d9f74d85795 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | 6979cf2d-3a24-5d80-a87b-a523d10d61e3 |  | note | Records Required - YES
label | eec38913-30e1-5d0d-85fd-84c0ee5e518a |  | note | ENGINEER - W(10%)
label | dce7e368-8ccd-5431-98f9-63b7484ea3ea |  | note | SUPERVISOR - R
label | 5fec0437-02c0-5e4e-96da-6fa450f61446 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations (Heavy and Light Maintenance) - Shallow Pothole Repair in a sealed Pavement - Premixe Method - QPR | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy and Light Maintenance) - Shallow Pothole Repair in a sealed Pavement - Premixe Method - QPR | de0a2f6c-b265-4d4c-bb39-86c835056482
checkpoint-status |  |  | checkpoint | 1 - Prepare Hole
label | d0528ae8-9f08-5cbf-ba40-3764940f53bc |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | eb5b36d4-93af-5653-828d-c796f9273016 |  | note | Accept / Reject Criteria - As per Specification
label | 6c219321-04b1-5bfa-9c8b-49851093b60a |  | note | Frequency Of Inspection Or Test - In-process
label | 3f914d87-73ca-5c27-9584-111f1a1ae907 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP032
label | 1b5e9e10-69de-5e28-9ec4-06bf614b13bd |  | note | Records Required - NO
label | 7d83d05e-49e1-5759-bf82-cb5dde3600d9 |  | note | DOWNER ENGINEER - R
label | 8a9d380e-de44-53f8-ac03-f033f6b7653c |  | note | SUPERVISOR - R
label | 6195334f-211f-54f8-b462-b8e22ab96853 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Filling Hole
label | 093347dd-e814-56d5-9c5f-64d30bf5a8e3 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 8b17843d-cee0-5a0c-9871-0d20decafa4f |  | note | Accept / Reject Criteria - As per Specification
label | 8a6eb695-c06e-598a-90ff-dc5324a0bb9f |  | note | Frequency Of Inspection Or Test - In-process
label | 20553708-bde8-5816-9a7f-e0b966994317 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP032
label | 950de8df-e73a-581e-a252-473718782645 |  | note | Records Required - NO
label | 3f9b18bd-1725-58f2-8d3a-e534995fd91d |  | note | DOWNER ENGINEER - R
label | e34b4777-314c-55d4-b37d-a5ab3b914ccd |  | note | SUPERVISOR - R
label | 0cc6ec32-21e4-57b6-9182-9adb572daf06 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Blinding
label | 1234cc73-7286-54ed-bfb2-bf6435470d75 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 05b42191-745c-5b0e-845c-7790617eedc6 |  | note | Accept / Reject Criteria - As per Specification
label | 8ff49c79-c7c2-5c7b-900c-c769f024a6ab |  | note | Frequency Of Inspection Or Test - In-process
label | e1e7eea4-309f-5750-ac90-6b000241f026 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP032
label | eaa0e1e9-6d0b-56f2-8698-e7556bbdc5c9 |  | note | Records Required - NO
label | a47ec134-4252-5176-beb9-b0b9bbe922c2 |  | note | DOWNER ENGINEER - R
label | c1047ef4-71ca-5541-95a6-e0a634d1740c |  | note | SUPERVISOR - R
label | 8fdf8a98-5cd2-5dd6-992f-ceb0058badb6 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Test and Check
label | 4e37456b-9d70-5052-9653-93d5d87db655 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 675e5fae-3910-5e37-816b-21f8778222fd |  | note | Accept / Reject Criteria - As per Specification
label | c549ebba-827b-5e0d-9413-75f9e9bfa3e0 |  | note | Frequency Of Inspection Or Test - In-process
label | f2da2b51-ebf9-5d85-b535-97a3f26b8865 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP032
label | 5e6dda3f-93cc-53d5-849c-05cc05c03165 |  | note | Records Required - NO
label | 361269ef-4a39-51c1-a17d-67cc5fd9f614 |  | note | DOWNER ENGINEER - W(10%)
label | adad75a5-87eb-5b5d-983b-9e209bd9c315 |  | note | SUPERVISOR - R
label | 7140d20c-1076-54d2-90d6-ccd8b069b0c2 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - CONOC NETWORK - AWT - Unbound Granular | itp |  |  |  | Yes | ITP - CONOC NETWORK - AWT - Unbound Granular | e03e9fa5-08bc-428c-8641-bd1ef2f398a7
checkpoint-group |  |  | section | 1 - Preliminary and General
checkpoint-status |  |  | checkpoint | 1.1 - Construction Program Completion
label | 3ad413e3-75bf-5cf9-a68f-f0f23ccff2d8 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | c449795f-e019-5330-9853-2d1bbe73401d |  | note | Accept / Reject Criteria - Best Practice Contract Specific MMP
label | 051e00b1-7169-5edc-a4e6-67a4c5ee362a |  | note | Frequency Of Inspection Or Test - Before work Commence
label | e911ea76-50a3-5638-8be7-b065c8b996d6 |  | note | Spec. Ref, Procedure Or Method Statement - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date.
label | 300b374a-d39c-58f4-9495-2752e4e664d7 |  | note | Records Required - NO
label | b17759dd-642b-5f50-9afe-8935f010c5fe |  | note | ENGINEER - W(10%)
label | 1f23b939-b53a-5fe3-ab72-5b4138d4e87f |  | note | SUPERVISOR - R
label | f57345d8-efb1-575e-b036-37827fb0932d |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 - Approved RQP
label | 4f172432-4660-5825-af46-15f80d2403ed |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 0fc75837-2ee8-5ee2-88ef-bf4be43f6c55 |  | note | Accept / Reject Criteria - Contract Specification
label | 01359cb4-f010-5879-a833-d6c5f03639f9 |  | note | Frequency Of Inspection Or Test - Before work Commence
label | 5f7175f2-33f1-5dfb-b59f-79a0d6ec2185 |  | note | Spec. Ref, Procedure Or Method Statement - Principal Acceptance according to guidelines in appendix 6.3
label | 96197674-7903-5ace-859a-58d5d6d7f93c |  | note | Records Required - YES
label | 7262626d-8851-5e7b-bdb2-739af9637c70 |  | note | ENGINEER - W(10%)
label | 6df6b795-c0e1-52f5-bde5-160d4768a0e9 |  | note | SUPERVISOR - R
label | beaa28e7-0cc6-5c89-94c7-f8df3dc0e946 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Traffic Management/TMP
label | 43e58f37-716a-5f92-9b0f-e95d13a7a934 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 8a731b38-0783-5c35-9892-b666a7ee567d |  | note | Accept / Reject Criteria - CoPTTM
label | d84c26d8-d787-53b2-a0cd-a9798e964323 |  | note | Frequency Of Inspection Or Test - Before Traffic Management Setup
label | 74741ecd-eae8-5830-9399-55c277deec74 |  | note | Spec. Ref, Procedure Or Method Statement - TMP checked and approved, Plans approved, Current EED (if applicable)
label | 011c74fa-c2be-5e4e-8629-e02f8b9578ae |  | note | Records Required - YES
label | b3549fab-8d54-51ed-b795-4539b08b115a |  | note | ENGINEER - R
label | 3f4a0300-1673-5992-9972-0486d3f45c68 |  | note | SUPERVISOR - R
label | 717610e8-6b0e-51ba-9920-b026680504dd |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Notification of intention to start work
label | fd271a08-1a5c-582e-a991-ef69749de414 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | fdbeb311-5be5-5674-82da-1c5ae35a507b |  | note | Accept / Reject Criteria - Notification
label | cd230465-fc6c-5d92-8512-1449b467371c |  | note | Frequency Of Inspection Or Test - Before work commences
label | 1357a6b0-2792-5c51-9eb9-41c407a4ed5a |  | note | Spec. Ref, Procedure Or Method Statement - Letter drop to local residents. Where required and defined by SWAMP, VMS, social media/media advertising
label | 42606b72-fe52-51de-a915-ea0ec7470c9d |  | note | Records Required - YES
label | cd70905a-7cb2-57e3-b461-51d421d21b0e |  | note | ENGINEER - R
label | f72f0fb5-d68e-5722-8577-db4b25c666b0 |  | note | SUPERVISOR - R
label | fefde325-ff93-5236-ad69-f3f03403fa4a |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Setout/Site Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Setout/Survey
label | 42abb599-1373-59f4-b8de-7eeacac028d5 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 7ae047ca-e3b8-551f-8dff-2fb249c5ff5a |  | note | Accept / Reject Criteria - Best Practice
label | 1b59e9e7-5714-5a0d-86ef-10e1cfcc3330 |  | note | Frequency Of Inspection Or Test - Per installation
label | ff76c6b3-f5c9-5f7a-ae24-b5fd82e60f4f |  | note | Spec. Ref, Procedure Or Method Statement - Survey Records
label | f6e985a5-eaf6-5db9-b4f2-2e8ba73a44ba |  | note | Records Required - YES
label | ea60dcf2-de36-573d-bc2e-67ee03a6ede4 |  | note | ENGINEER - W(10%)
label | 69fa7503-039d-5146-b881-b9aed485ca65 |  | note | SUPERVISOR - R
label | df207d68-1ba8-576b-a5f9-70f1ea8e8b14 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | 2feef3f4-0ee7-5097-b550-7408a006e8ed |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 3d04bc66-29a8-5098-9a8d-7747a2e1b7e5 |  | note | Accept / Reject Criteria - NZAUAG Guide to Working on the Road
label | e8afb371-2da6-51fa-b43b-07cb6e339fac |  | note | Frequency Of Inspection Or Test - Before work commences
label | bd35a582-55ff-5db4-8ddc-87fdea5dee45 |  | note | Spec. Ref, Procedure Or Method Statement - Zero service strikes
label | d2db75b7-86fd-5b62-80fb-911d8f171d83 |  | note | Records Required - YES
label | e096900b-ffb8-53f8-8a69-f962229720ee |  | note | ENGINEER - R
label | 52ed00d3-591f-5048-ad59-7b932abd31c4 |  | note | SUPERVISOR - R
label | 32979ba6-6625-5765-943d-9b04206dfc87 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Permit to dig/Authority to Work/close approach permits
label | 30e161fe-12a7-5fa7-9f59-d0c4399fc5b1 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 0ec82ded-3601-55fe-848c-adba758b197f |  | note | Accept / Reject Criteria - Downer Permit to work or Equvilent
label | 3a7ef8e4-e3c5-583e-bc64-6dbaf182bc0b |  | note | Frequency Of Inspection Or Test - Before work commences
label | 4bc0e938-9641-5d34-9dbe-b97ed6fdf1d7 |  | note | Spec. Ref, Procedure Or Method Statement - Organisational approval
label | b73e1ba2-1cfd-54d7-a8f7-f39dfec8787e |  | note | Records Required - YES
label | fedf4482-bff7-50ef-8467-ce6aa307d118 |  | note | ENGINEER - R
label | cbc5001b-e3b9-549e-bb22-3a990c52d254 |  | note | SUPERVISOR - R
label | 21a6e1d9-0a41-53a7-8483-99990134c8a3 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - CONOC Construction (Dunedin Airport) - Pavement Construction Area 1, 2, 3, 3A, 4 & 5 | itp |  |  |  | Yes | ITP - CONOC Construction (Dunedin Airport) - Pavement Construction Area 1, 2, 3, 3A, 4 & 5 | e706e055-686b-46b8-9f9e-9466cfce8e91
checkpoint-group |  |  | section | 1.1 - General
checkpoint-status |  |  | checkpoint | 1.1.1 - Contract Management plans, (including ITP)
label | 85fe9d2b-9230-5681-856b-158706e470d6 |  | note | Controlled By : (Position) - Project Manager
label | 73b6608c-9c7d-5521-a33d-58da4ce693e5 |  | note | Accept / Reject Criteria - The Contractor to provide contract management plans as defined in the project specification prior to commencement of works. ITP to be reviewed and updated upon receipt of construction issue drawings/Specification.
label | 9e957352-0b3b-57d0-8222-211386dc0b91 |  | note | Frequency Of Inspection Or Test - Prior to physical works
label | e669f645-e6a3-5a5a-99fc-ba80432c9c0d |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification NTC / Email verification approving Contract Management Plans
label | bf71e523-4340-5772-a4a4-42cd31cd90c6 |  | note | Records Required - YES
label | 9040a344-e1fe-57fd-929c-2b7e2f5be678 |  | note | DOWNER ENGINEER - H
label | 4684d7b6-ea73-545d-9aff-23e30d6ade0b |  | note | SUPERVISOR - H
label | 2db87322-c314-5df8-8bff-dd9f36d11941 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.1 - Site Specific Requirements
checkpoint-status |  |  | checkpoint | 2.1 - Construction Pack (SSSP/CBP)
label | a05770f1-cb35-584b-a2f8-0db4482f008a |  | note | Controlled By : (Position) - SE, FM
label | 97294e62-1d1d-52c4-aff9-0564315a6651 |  | note | Accept / Reject Criteria - Construction Pack including Site Specific Safety Plan developed for work area and issued to Engineer in advance of works.
label | 02c955e3-bab6-57b4-a1d1-0d3c8cac3cd5 |  | note | Frequency Of Inspection Or Test - Prior to physical works 1 per site
label | 45e751c4-0473-5c70-94ef-c9a56d9d4e22 |  | note | Spec. Ref, Procedure Or Method Statement - Downer/Construction Pack
label | 7cdb664f-61a0-5494-b79f-ba5224ec0f6f |  | note | Records Required - YES
label | 3b9c98b8-6e0a-51df-9c2a-0ae4aa4c9831 |  | note | DOWNER ENGINEER - H
label | 1876056b-6624-5283-8dd4-64cea453ab31 |  | note | SUPERVISOR - R
label | d644aa8b-7af0-5ef8-bebb-50835501e60f |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Service Location
label | 0ff829b1-9b1a-5e0f-963d-7636a4bbef71 |  | note | Controlled By : (Position) - SE, FM
label | fc38d396-8676-57ed-9a1c-87641fbcbe00 |  | note | Accept / Reject Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | f2ac2773-9803-5af3-b2c9-0c205dad4544 |  | note | Frequency Of Inspection Or Test - Prior to Excavation 1 per site/work area
label | b1a9d985-b95f-5efc-9628-dcdb2e4cb374 |  | note | Spec. Ref, Procedure Or Method Statement - Downer/Excavation Permit
label | 5e397df2-3607-5414-99a2-de29211c664c |  | note | Records Required - YES
label | 71e60e74-adc6-53b3-acad-4678b4ae7b85 |  | note | DOWNER ENGINEER - H
label | edd62023-0f44-54da-8b17-3b5c331b4e48 |  | note | SUPERVISOR - R
label | ed64136c-ff85-51ef-a2f6-aff2c49d2652 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Internal Permits
label | 1ebbc836-180d-5aec-b9f7-e401b11a2cc2 |  | note | Controlled By : (Position) - SE
label | 9a34a71f-2ada-5c3a-b839-20661220fab3 |  | note | Accept / Reject Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | 6abddeba-927c-5e77-80db-55575c2a509b |  | note | Frequency Of Inspection Or Test - Prior to Excavation as needed
label | 54fff108-3f60-5053-bd43-2b30f43d0f29 |  | note | Spec. Ref, Procedure Or Method Statement - Downer/Internal Permits
label | bb412049-11ec-5fd8-8139-ed52f397ed3a |  | note | Records Required - YES
label | 777f4262-feb3-5e39-8276-a38e80fc5c65 |  | note | DOWNER ENGINEER - H
label | 84b8d7af-bd39-52a8-b0a6-a1bcd1b14658 |  | note | SUPERVISOR - R
label | 6691e3b9-2636-57a5-912a-eb9ff5bc3e01 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - External Permits
label | 4eb927ae-5c9e-56b2-a84c-23d3411e7672 |  | note | Controlled By : (Position) - SE
label | 2083627f-3880-53cb-82af-9e806902033c |  | note | Accept / Reject Criteria - Obtain External Permits as required to complete works including but not limited to: Airport Inductions, Close approach, Worksafe Notice etc.
label | 5b38bf2d-0869-5a56-9215-67f5f56db01d |  | note | Frequency Of Inspection Or Test - Prior to Excavation as needed
label | 3dba9e1d-f95f-575d-a0e8-d2f097b0c1b1 |  | note | Spec. Ref, Procedure Or Method Statement - Downer/External Permits
label | f907d38e-e373-5e89-b65a-b013de852005 |  | note | Records Required - YES
label | 53e89a8c-0dc7-51f1-aaa2-6772b0af2858 |  | note | DOWNER ENGINEER - H
label | f5f45a0c-1911-59fe-ab97-b7f831186898 |  | note | SUPERVISOR - R
label | b057de9e-e5d2-5109-b464-94c340971c4e |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.1 - Construction
checkpoint-status |  |  | checkpoint | 3.1.1 - Insitu Subgrade Fill Material
label | 94fd3a83-7fb8-5b3d-bfc8-469729fcdea8 |  | note | Controlled By : (Position) - SE
label | df80a42a-fd2f-5b1d-9a47-4a01b8dc00bb |  | note | Accept / Reject Criteria - AP150 - Duncans Quarry (Abbotsford)
label | 5a9827e0-c174-5ea9-baee-7f7db361c7a5 |  | note | Frequency Of Inspection Or Test - Annually/Project
label | 956ac8b4-7e93-56dd-8a46-fddac9cb20e2 |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification/As per NZTA Specifications
label | d149d774-7d0d-5382-91c5-7494e1bb948c |  | note | Records Required - YES
label | 99a0b185-1886-5d04-a8ea-06d40d4e57d7 |  | note | DOWNER ENGINEER - H
label | 2a28e974-fc8c-5238-b271-fa6cd7ff2ceb |  | note | SUPERVISOR - R
label | 041e65ea-bdbe-5ae7-8f29-64502a9677d2 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.2 - Insitu Subgrade Fill Material
label | f15e5703-ad5d-53bc-8ab3-8ac720891d65 |  | note | Controlled By : (Position) - SE
label | 399e3e58-1dc2-5e37-8fbc-04416bace6b4 |  | note | Accept / Reject Criteria - AP65 - Duncans Quarry (Abbotsford)
label | a6c915ff-59ef-5715-966e-c73d5a28913d |  | note | Frequency Of Inspection Or Test - Annually/Project
label | 923494c3-0a98-50a9-b41a-b55d1d20a239 |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification/As per NZTA Specifications
label | e8b13fb6-432d-59f2-9ac4-96e909e1fc67 |  | note | Records Required - YES
label | 169d444c-d69e-545d-bdf6-b490fa0cd4c4 |  | note | DOWNER ENGINEER - H
label | 81ff9a9c-e763-575b-921a-da845c88c9f4 |  | note | SUPERVISOR - R
label | 2c2b714f-673f-56a3-87da-4ba7692ef428 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.3 - Basecourse Aggregates
label | b46467c6-e1cf-5038-918b-e88266b462ef |  | note | Controlled By : (Position) - SE
label | 6104a083-78da-5b25-aab8-6e797c1df8b3 |  | note | Accept / Reject Criteria - M4-AP40 - Blackhead Quarries
label | e7e1b73d-98c0-5234-a98d-3dfc403e0c18 |  | note | Frequency Of Inspection Or Test - Annually/Project
label | 2bda46db-19eb-5237-9938-007b7d2f0a2e |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification/As per NZTA Specifications
label | f9e807d6-b1db-511a-a89d-2b1c713b6030 |  | note | Records Required - YES
label | 7d904449-0f41-584f-8c47-895ecfb3bb66 |  | note | DOWNER ENGINEER - H
label | 08eac4cf-3741-529d-800f-c852f0df2965 |  | note | SUPERVISOR - R
label | d3bdee0c-15cd-54ce-b449-0071d6607d15 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.4 - Basecourse Aggregates
label | c4811d50-e597-5e3f-8460-a6ffd26b752f |  | note | Controlled By : (Position) - SE
label | f5e34c07-d2fa-53d5-836b-12a084ffefc3 |  | note | Accept / Reject Criteria - M4-AP20 - Duncans Quarry (Abbotsford)
label | bab63d56-9d9b-5840-b484-1e7b6ddec708 |  | note | Frequency Of Inspection Or Test - Annually/Project
label | 16fb56d3-d84b-5464-ba5f-9337b32ac494 |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification/As per NZTA Specifications
checkpoint-status |  |  | checkpoint | 3.1.5 - Geofabric
label | b16e9c46-cc57-5acb-bbce-8487f05fa10f |  | note | Controlled By : (Position) - SE
label | 09aca168-6569-5e30-a65e-3fe9dcd5342e |  | note | Accept / Reject Criteria - Installation of geogrid/geocloth (A29/TX160) when instructed by Engineer. AP65 Compacted in layers not exceeding 200mm.
label | c6fefe4e-4d6a-5b76-8f7c-4c4132bb62e9 |  | note | Frequency Of Inspection Or Test - Annually/Project
label | ee1b7780-86c7-56bf-a512-c5bd1e912323 |  | note | Spec. Ref, Procedure Or Method Statement - NZTA F/1, TNZ M/3 Notes/As per NZTA Specifications
label | 0e7ad21a-e82c-5b51-8b8f-c2789f51e33e |  | note | Records Required - YES
label | d17db4be-0543-5171-b194-1333ffe1f441 |  | note | DOWNER ENGINEER - H
label | 9bef47f8-923d-5820-adb8-a7014cbf8112 |  | note | SUPERVISOR - R
label | a56cf4bc-54f2-59f3-8d51-f0cf69a316bd |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.2 - Paving
checkpoint-status |  |  | checkpoint | 3.2.1 - Road Asphalt
label | e69ac9d4-c1b4-5ffa-a58a-820148eebb99 |  | note | Controlled By : (Position) - SE
label | 4fdca27e-e06c-5640-8a86-13bd226c9de8 |  | note | Accept / Reject Criteria - 50mm AC14
label | 16d7cf9b-fbcc-5bbe-8b8e-b213e5f20b81 |  | note | Frequency Of Inspection Or Test - Supplied/approved annually by Engineer to Contract/Prior to AC
label | 35f92cd0-89ee-55cb-8a0c-eb2498ec3a87 |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification TNZ M/10:2020/Approved Mix Design
label | fefa8362-2201-5a4c-a2ee-4166865b4fcc |  | note | Records Required - YES
label | 4e4567d7-95cd-5816-9cff-c0d446fec7db |  | note | DOWNER ENGINEER - H
label | 2d7b8f01-8dbf-5b5c-bca0-3bfd3f1b3104 |  | note | SUPERVISOR - R
label | bbf098e3-1a61-5452-90f8-ec043c04b8ce |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2.2 - Road Asphalt
label | 377eb864-c95b-55c9-a6b4-6eb6be8491dd |  | note | Controlled By : (Position) - SE
label | e095af54-ab47-51b4-831c-f4b53b652619 |  | note | Accept / Reject Criteria - 90mm EME2 (Trial Mix)
label | e8bf21b9-da4f-5b72-ba42-a04333075b8f |  | note | Frequency Of Inspection Or Test - Supplied/approved annually by ETC/Prior to AC
label | d4817ae8-5baf-5dd8-972f-177b132c8c90 |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification NZTA M32: 2021/Approved Mix Design
label | 27a9f213-61d2-5b84-a737-ffe14b225fd6 |  | note | Records Required - YES
label | 328f2e58-c731-57c1-ba8b-b7d34ba4d69d |  | note | DOWNER ENGINEER - H
label | 11ae92eb-2532-5d38-9621-2dec477e8764 |  | note | SUPERVISOR - R
label | 77003535-0501-5963-a830-2217f60ee046 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.3 - Pavement Marking
checkpoint-status |  |  | checkpoint | 3.3.1 - Standard Marking
label | b77e41b3-d339-5f6a-99dc-7f4d4fb16945 |  | note | Controlled By : (Position) - SE
label | 9cb95bfd-bb06-5071-ab3f-8aac31025f21 |  | note | Accept / Reject Criteria - Standards pavement marking. Paint shall comply with TNZ M7 and shall be on the current Transit New Zealand list of approved paints.
label | 1808ba08-fc05-51b3-8551-64d6adcc5256 |  | note | Frequency Of Inspection Or Test - Approved once by ETC/Prior to Line Marking
label | c2c154bb-66bf-5134-875d-d0e67deee493 |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification TNZ/LTSA (MOTSAM)/Approved pavement marking quality system
label | 21767e63-26e7-5646-9e21-22c01323f625 |  | note | Records Required - YES
label | ed82a06f-fd24-546b-8b7f-2e6948e66449 |  | note | DOWNER ENGINEER - H
label | c5696b27-8d67-5dcb-a030-d86dc73de946 |  | note | SUPERVISOR - R
label | 59d31ebb-f4de-5ce9-8df1-48da5900d526 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4.1 - Excavation
checkpoint-status |  |  | checkpoint | 4.1.1 - Site Clearance
label | 885fde1e-e87c-5d38-be90-d5dcd42c1a49 |  | note | Controlled By : (Position) - SE, ENG
label | 8369116d-a3ba-554f-a944-bd7735b782f2 |  | note | Accept / Reject Criteria - Unless shown otherwise on the drawings or directed by the Engineer, all vegetation, shrubs, trees under 3m in height, fences and foundations, retaining timbers, abandoned pipes and services, etc over the contract length and within the extent of the earthworks shall be removed off site.
label | dbbca75e-5183-5244-bbf2-605132d8042a |  | note | ○ All waste will be disposed at DIAL approved location.
label | 89a7f2c2-17bd-5188-a881-912807d31278 |  | note | Frequency Of Inspection Or Test - Prior to Excavation/clearance works/per site
label | e5c3336a-c4a9-5995-bd69-5ce51665e30c |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification/Pre construction walkover inspection DNZ Field Inspection Record
label | 8c3d426c-74e3-50a1-ba41-4cfe3981dd39 |  | note | Records Required - YES
label | 44f24b3a-2b25-5bf4-84b3-caf894cfe320 |  | note | DOWNER ENGINEER - H
label | e724fccf-2b8d-52c0-bf97-80455bac4f02 |  | note | SUPERVISOR - R
label | 42a03072-437c-51d7-81bc-16b924ec3aa9 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.1.2 - Excavation
label | b2047466-1eff-527a-9962-6c73c707496e |  | note | Controlled By : (Position) - SE
label | 818cdfc0-65b9-586f-a91f-9d6c5bb36e38 |  | note | Accept / Reject Criteria - Excavation carried out as per project extents detailed on construction issue drawings.
label | 50786fb0-d2f5-55d5-9eb7-2754d839543c |  | note | ○ Level as per subgrade requirements below.
label | 0eba280a-a10a-57ec-8e66-9ba7496746b9 |  | note | Frequency Of Inspection Or Test - Per site specific requirements/as required
label | 3836169a-8f1e-5a62-b0cf-e0e811143eb6 |  | note | Spec. Ref, Procedure Or Method Statement - NZTA F1 DNZ Field Inspection Record
label | fec1e17d-c4d3-56f1-9c94-f488b6d56983 |  | note | Records Required - YES
label | 151f2ada-d55b-578b-9ff7-fd23ce87ace6 |  | note | DOWNER ENGINEER - H
label | fedcd1e2-1f9c-56f1-a604-d153d4196b06 |  | note | SUPERVISOR - R
label | 991bb7ed-b691-5a55-bc94-0cd860e0af76 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5 - Subgrade
checkpoint-status |  |  | checkpoint | 5.1.1 - Subgrade Suitability Inspection
label | 51546b46-7208-5224-b575-e32e891e2d61 |  | note | Controlled By : (Position) - SE, ENG
label | 99fee813-3059-5d0d-8d16-ffa152e57e2e |  | note | Accept / Reject Criteria - The Subgrade must be inspected by the Engineer following clearing and prior to the placement of any filling to confirm the strength of the underlying soils is sufficient.
label | 2fa78aab-a9af-5c1d-8b0e-4821d6507787 |  | note | ○ Where Scala testing is deemed unsuitable by Contractor (hardfill or Service Strike Risk etc). Visual inspection by Engineer supersedes foundation testing requirements - Site instruction required.
label | 2af4241e-7d8b-5c3d-b84d-d285e949b825 |  | note | ○ Should material be determined as unsuitable (highly organic, saturated clay pug etc) Contractor to elevate to Engineer who will determine whether the material is unsuitable or not and agree the extent of the unsuitable material with the Contractor.
label | 56ec29c5-3988-5a0f-bbf7-1ee3e3ec0621 |  | note | Frequency Of Inspection Or Test - 20m where practical
label | 9266c673-5202-5598-b4d6-2e15016c3739 |  | note | ○ Not required for failed visual inspection areas (ie wet pug, highly organic material)/per site
label | 72152f46-545c-57a2-83d2-6bb207173b83 |  | note | Spec. Ref, Procedure Or Method Statement - NZTA F/1 Scala Report (CBR 5)
label | 8aeb1867-ff04-5b08-851d-e628767d2b84 |  | note | ○ 3blows per 100mm
label | c3eb06a0-2e5b-5416-ad3a-c420ea12b317 |  | note | ○ Visual Inspection
label | 278993e2-bc9d-559e-9b87-3307b5fefe73 |  | note | ○ DNZ Field Inspection Record
label | 52733fbe-12fd-5aec-8651-729c7ab4eaef |  | note | Records Required - YES
label | 427d8ab3-d478-5270-879f-f21ade650438 |  | note | DOWNER ENGINEER - H
label | cdf3ba0d-df09-58bf-b47d-dc163b7c2faa |  | note | SUPERVISOR - R
label | c7a20c05-49c5-51ba-a352-88e97a317682 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.1.2 - Geofabric installation
label | 1bf32b07-2854-5466-ac90-27809205cfdf |  | note | Controlled By : (Position) - SE
label | d11d7539-f899-57c2-bdf4-b764db428294 |  | note | Accept / Reject Criteria - Installation of geogrid/geocloth (A29/TX160) as per design.
label | e3a27f58-107b-5b0c-8124-e3e9e6452f51 |  | note | ○ AP40 compacted in layer not exceeding 100mm, AP65 not exceeding 200mm and AP150 not exceeding 300mm.
label | 76c6eca0-dd8e-5a51-975f-7ccaa2eee032 |  | note | Frequency Of Inspection Or Test - 10,000m3/Project
label | 54a18b80-ebc6-5c45-a735-bccc01e27f25 |  | note | Spec. Ref, Procedure Or Method Statement - NZTA F/1 TNZ M/3 Notes IANZ Lab Reports (on request)
label | 4132a0be-0cb7-553c-bcf3-ef18f9e5bf0a |  | note | Records Required - YES
label | 9cbda00c-8ed5-57bb-bf4b-dc029401dce8 |  | note | DOWNER ENGINEER - H
label | d35ddb43-e313-5ee8-aada-1e7e26c11140 |  | note | SUPERVISOR - R
label | 86e7274d-33c2-5716-a336-5bbf207f8147 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.1.3 - Subgrade formation level - Kerbs
label | 4bee3fc2-d037-54f3-830f-6c73892306ff |  | note | Controlled By : (Position) - SE
label | 9897faf8-e886-5bb0-ab50-25116aa85188 |  | note | Accept / Reject Criteria - Excavation Min 300mm from design lip level (road tie in) allowing for minimum 120mm M440 foundation for kerbs.
label | 820a721c-5335-50b9-bac1-5c62032b575b |  | note | Frequency Of Inspection Or Test - Per site specific requirements/Project
label | b1990294-e3f0-5303-9374-f9b76f490597 |  | note | Spec. Ref, Procedure Or Method Statement - Downer NZTA B/2:2005 DNZ Field Inspection Record
label | 4829577d-3387-5ae2-8f23-f0f00ef900d8 |  | note | Records Required - YES
label | ff06c9b7-10c1-58ee-b085-4f40e7ecffa4 |  | note | DOWNER ENGINEER - H
label | 9128c608-2a73-5dd8-887d-1a2f4fd25a24 |  | note | SUPERVISOR - R
label | d8cd31c3-26bb-50e2-aaa5-35770bf73044 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6.1 - Area 1
checkpoint-status |  |  | checkpoint | 6.1.1 - Remove top 100mm
label | 87ad8636-a6f6-545d-bda6-56efbd12bbae |  | note | Controlled By : (Position) - SE
label | 540fbe10-edc4-5ff6-8d73-01c43cf5394e |  | note | Accept / Reject Criteria - Rip surface and lime treat subbase
label | 99b1ebef-247a-5ca0-a546-e3fb57c4e199 |  | note | Frequency Of Inspection Or Test - 1 per pavement area
label | 71f0bf83-a624-571d-be28-a852b9c9b9e4 |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records with measuring tape
label | 39c56fc5-52c6-51ac-9aaf-72f327473e9c |  | note | Records Required - Yes
label | 9300a91f-054f-58c1-96ca-3b0722a3b421 |  | note | DOWNER ENGINEER - H
label | ed342b27-d8a9-58cf-872b-3401361cd3f3 |  | note | SUPERVISOR - R
label | 28c9d51c-f126-58dc-9a65-033cea5911cd |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.1.2 - Subject to Beams Test
label | 64b464bf-8522-57fe-9308-c94d5c9d5e09 |  | note | Controlled By : (Position) - SE
label | 1ba4f407-47da-5441-ac94-72297f9121ea |  | note | Accept / Reject Criteria - Backfill or Seal
label | 33b55504-26eb-51bf-81b5-317d30975d51 |  | note | Frequency Of Inspection Or Test - 1 per pavement area
label | 254e2ffe-6ddc-585c-83ff-f8f0d694d050 |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records and Results
label | 5a70af80-c87e-5615-ba26-75854c3413cc |  | note | Records Required - Yes
label | c38f768e-f852-586e-957c-43f210f2bc21 |  | note | DOWNER ENGINEER - H
label | b61d19a9-82b4-55f3-84a9-1e135069a943 |  | note | SUPERVISOR - R
label | 58c8054b-19a1-52c4-9ae7-c8374ac81100 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.1.3 - Backfill
label | 9bbde7c5-e728-59b6-9d52-232ff3121219 |  | note | Controlled By : (Position) - SE
label | 290263eb-2b30-57ba-b44f-911423c90537 |  | note | Accept / Reject Criteria - AP40 and stabilise top 200mm
label | fb55f63a-730b-599a-a675-97d6512304b4 |  | note | Frequency Of Inspection Or Test - 1 per pavement area
label | 16c42675-7c44-5136-b9f6-250d3115c81b |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records with measuring tape
label | 6a27ff39-07c3-5736-bae9-b4d1f48e2f95 |  | note | Records Required - Yes
label | 54037482-28fb-5d68-a8dc-f6299b31b435 |  | note | DOWNER ENGINEER - H
label | 77af0f84-fd73-54c0-96c4-a28938b4547e |  | note | SUPERVISOR - R
label | e6596f0d-58f1-53af-a42a-ad37e4a6f0b8 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.1.4 - Surfacing
label | 7e28676d-20a4-504c-bfc3-e1b60592b79e |  | note | Controlled By : (Position) - SE
label | 1d8a3b37-31c8-5f23-8181-7c145f28c9d4 |  | note | Accept / Reject Criteria - 90mm EME2 (Trial Mix)
label | b07878ba-eaad-5059-bd40-bb92d308e72a |  | note | Frequency Of Inspection Or Test - Prior to AC/1 per pavement area
label | e614efff-136e-517d-bbdb-4e2f13336860 |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Approved Mix Design
label | e277c57d-c576-5d9a-9080-7547864d473b |  | note | Records Required - Yes
label | ae88c138-b3f5-5b07-8c11-b3b842f9c704 |  | note | DOWNER ENGINEER - H
label | 0aaa97ad-43ec-5b8a-94d3-106af41bdd07 |  | note | SUPERVISOR - R
label | dab91af8-9931-5fdf-be2b-4baa9181e437 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6.2 - Area 2
checkpoint-status |  |  | checkpoint | 6.2.1 - Remove top 600mm
label | 68c74c2a-4c59-5967-866e-5cc68de42285 |  | note | Controlled By : (Position) - SE
label | dd3deb89-a839-5c35-b20b-17f1e6e13d63 |  | note | Frequency Of Inspection Or Test - 1 per pavement area
label | 27b911f9-252b-5ff3-aa55-6293c49ad020 |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records with measuring tape
label | 32158fae-b3b2-55b5-aca8-8d714e89472b |  | note | Records Required - Yes
label | 31855597-8e12-5eb5-ae10-9286ff19a7bc |  | note | DOWNER ENGINEER - H
label | 2394de9f-8253-5f81-8cc7-03921ad1330a |  | note | SUPERVISOR - R
label | df34e3d3-f8e3-5212-ba28-17fe61c96b82 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2.2 - Geofabric
label | e2c34893-5773-5eb7-a3aa-c6b88bf64b5c |  | note | Controlled By : (Position) - SE
label | 5e777592-824e-5ad9-8dd6-668ed11de55b |  | note | Accept / Reject Criteria - A29 Fabric
label | b88aa67a-cf23-5f9f-9412-f0844dea8cb2 |  | note | Frequency Of Inspection Or Test - 1 per pavement area
label | da44e202-ff0c-5c6c-900c-c40911b45c8c |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records
label | 02db4714-50dc-5e81-bc35-f7ebd367333f |  | note | Records Required - Yes
label | 11d4e5d1-950d-5a3a-b105-173d28b1b60c |  | note | DOWNER ENGINEER - H
label | a1fff2be-5e9c-51ad-b7a4-a28fe6c50823 |  | note | SUPERVISOR - R
label | c141125e-3b7e-57fc-a480-cc9f17eb6728 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2.3 - AP150
label | ec63ce93-7c81-5a23-a157-0faeab47420b |  | note | Controlled By : (Position) - SE
label | 9dd5e9be-3af2-5699-b1d0-410b5b91a921 |  | note | Accept / Reject Criteria - 300mm
label | 235c4d55-937c-5fb9-a367-5f053130c2cc |  | note | Frequency Of Inspection Or Test - 1 per pavement area
label | 54e5a4d4-8f52-5c68-b4f3-83dca82e4e6a |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records with measuring tape
label | e2b52631-d520-530a-8627-691268c28480 |  | note | Records Required - Yes
label | 2bff5755-592f-5fc7-80aa-cb333441e05e |  | note | DOWNER ENGINEER - H
label | 785835ee-0919-504e-a0a1-7324db6b7506 |  | note | SUPERVISOR - R
label | 81e573ec-9c83-538f-bdb3-0d5104f1f0e5 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2.4 - Geofabric
label | 181f0801-c9fd-5166-812c-22ed3e30b6f6 |  | note | Controlled By : (Position) - SE
label | c4973940-ec5a-50b9-8e25-d9871da94424 |  | note | Accept / Reject Criteria - TX160
label | b0fbd0a0-9c67-5434-98e2-c7331c3207e0 |  | note | Frequency Of Inspection Or Test - 1 per pavement area
label | 11407b05-a52f-53d3-8f14-796fd4a5afaf |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records
label | b95285f4-c910-5569-8fba-0ea59a89fada |  | note | Records Required - Yes
label | 50232381-3166-56d0-a4d0-c9f3d73729e3 |  | note | DOWNER ENGINEER - H
label | 13555b66-ad86-5dfd-bdef-2f321ffde7db |  | note | SUPERVISOR - R
label | 6646211c-9d23-5fda-9848-27996ed433f7 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2.5 - AP65
label | 0e679959-950d-51ee-99d3-b7706a1549a5 |  | note | Controlled By : (Position) - SE
label | 008a0214-29f4-55c2-9b3e-9d536a434c6e |  | note | Accept / Reject Criteria - 200mm
label | c30e5c3c-1012-5d0f-8bad-583fcc63fa0d |  | note | Frequency Of Inspection Or Test - 1 per pavement area
label | c1a47cf6-1aab-50b7-967a-43961135aab6 |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records with measuring tape
label | b9c20cf5-122f-50cf-85e4-ae4591c36280 |  | note | Records Required - Yes
label | c491b3a2-5cd4-5bf1-91b3-07524eb13f7f |  | note | DOWNER ENGINEER - H
label | 8cdcfaa0-7461-5be8-b297-8333927ae714 |  | note | SUPERVISOR - R
label | d3084b2d-6a37-5f1f-baa0-d7dee97df6f0 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2.6 - AP40
label | 0c60b5fb-ca71-5b82-aaa8-064805fca02c |  | note | Controlled By : (Position) - SE
label | b34f7dd6-3607-5595-b638-bbd1e51f9b88 |  | note | Accept / Reject Criteria - 100mm
label | aaff5837-55fb-5124-99c9-953a1b98017b |  | note | Frequency Of Inspection Or Test - 1 per pavement area
label | f3f588b5-b248-520c-94ce-1871fc719556 |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records
label | c745630e-0abc-568d-a40e-f207a6509b08 |  | note | Records Required - Yes
label | 5b5eaaf8-cbd5-5e2a-bb8c-068f2a7069a5 |  | note | DOWNER ENGINEER - H
label | ba6f0c5c-814e-5ee5-880c-0478673187c2 |  | note | SUPERVISOR - R
label | 24928c38-875f-574d-a298-fe8495647a1b |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2.7 - Surfacing
label | ec4bba5f-d3b8-553d-af93-07f77c3847c3 |  | note | Controlled By : (Position) - SE
label | 9bc62b92-4e51-5353-b448-5011db3e9182 |  | note | Accept / Reject Criteria - 90mm EME2 (Trial Mix)
label | 466bcc8f-2e47-5b20-ac5c-3621d03a785a |  | note | Frequency Of Inspection Or Test - 1 per pavement area
label | 6c12a291-06b5-59e5-a479-cabb4bb29e7c |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Approved Mix Design
label | 69a563d1-ce54-516a-8e27-4166f8571e5f |  | note | Records Required - Yes
label | 569f4928-656e-5561-b5d8-29fa72cfbd8f |  | note | DOWNER ENGINEER - H
label | e6ec2681-6f8a-58e1-aa15-e0c026e99788 |  | note | SUPERVISOR - R
label | 9758eda1-f19f-5e42-bb79-4bc5eabaa77e |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6.3 - Area 3 & 3A
checkpoint-status |  |  | checkpoint | 6.3.1 - Remove existing surface
label | 0be3a67d-1696-5ef1-bcdb-46e79eb4b0bf |  | note | Controlled By : (Position) - SE
label | ab57a416-8e8d-586f-916a-c5670369e409 |  | note | Frequency Of Inspection Or Test - 1 per pavement area
label | cd2e3742-4194-5cc1-b343-fee14291b5fa |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records
label | 8f48455e-75ec-5635-b1b7-4928de9febb2 |  | note | Records Required - YES
label | 075c447b-2039-538f-b6f3-e2441c0f8c05 |  | note | DOWNER ENGINEER - H
label | 235e1d95-aa27-5ffe-8802-26c600fa4017 |  | note | SUPERVISOR - R
label | befed7c6-1746-5cc4-aaf4-67a66ef1e5bf |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.3.2 - Prep to suit existing kerb and drianage
label | 361c8d4e-58d4-56ec-b2ab-6c41d0a2f1e2 |  | note | Controlled By : (Position) - SE
label | aa54945b-1ae5-5cb6-a7f1-8a1ee357274e |  | note | Accept / Reject Criteria - AP150
label | e43f5cfa-b2ea-530c-8e3e-9860fdec2939 |  | note | Frequency Of Inspection Or Test - 1 per pavement area
label | e481ff4e-487f-5090-b710-28baa9f62475 |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records with measuring tape and falls
label | d47432c7-1432-5569-917f-84cf729b6538 |  | note | Records Required - YES
label | d1b2d86a-317c-5f31-9850-4b47a36cbfad |  | note | DOWNER ENGINEER - H
label | 3c304ce5-d7c4-5bcb-9198-e9ab362e86a6 |  | note | SUPERVISOR - R
label | dc598809-d844-52a5-ae37-64bb76e02098 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.3.3 - Surfacing
label | 55ed37f1-e38c-5de0-9438-dc8ac1f0c53c |  | note | Controlled By : (Position) - SE
label | c8aad964-5c12-5817-8a8b-479b1192fef4 |  | note | Accept / Reject Criteria - 50mm AC14
label | 50256470-22fa-56c5-b612-aae8adf900d4 |  | note | Frequency Of Inspection Or Test - 1 per pavement area
label | cc2cb022-0b16-5165-a81b-c132124b8f4a |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Approved Mix Design
label | 1fc4f742-9dc8-5310-8113-e655e99677ea |  | note | Records Required - YES
label | 4b0c99aa-4a37-5575-84c8-59803bde0767 |  | note | DOWNER ENGINEER - H
label | 77e5b817-b3be-5349-912a-6e4e65e8cce5 |  | note | SUPERVISOR - R
label | 7b509cc5-b2e6-59f4-889d-beee9b301080 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6.4 - Area 4
checkpoint-status |  |  | checkpoint | 6.4.1 - Remove top 650mm
label | dc00c981-895c-5fe3-ade8-094921f27c99 |  | note | Controlled By : (Position) - SE
label | 84dae2b9-9f26-5ef0-9c64-b112b8fe465e |  | note | Frequency Of Inspection Or Test - 1 per pavement area
label | 2166781c-a252-5327-a174-a5650c609f71 |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records with measuring tape
label | 1c86e33f-0644-58af-bbdf-6aa7bf1c9a8c |  | note | Records Required - YES
label | 851f12df-d60f-5ded-aed8-e47289319b81 |  | note | DOWNER ENGINEER - H
label | 78a663ae-9d74-5928-a61a-730696864a90 |  | note | SUPERVISOR - R
label | 1eb85238-9f28-53dc-8186-0853157676ce |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.4.2 - Geofabric
label | f7476367-de01-5078-a8c9-841f7c1baa21 |  | note | Controlled By : (Position) - SE
label | 20eff683-3dca-503d-b7ba-7acf072c5859 |  | note | Accept / Reject Criteria - A29 Fabric
label | 4bb1f356-9885-5f7c-ba29-38ffa99ad1ce |  | note | Frequency Of Inspection Or Test - 1 per pavement area
label | e183b73f-c770-5240-b9c6-dfd4852185ed |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records
label | 1fd20fd4-ff02-5485-aabf-0a33da5b5872 |  | note | Records Required - YES
label | 06be3af0-2a0b-5645-94bb-b800aeffb380 |  | note | DOWNER ENGINEER - H
label | e14742d6-f8f2-5a67-a832-d177eb431f01 |  | note | SUPERVISOR - R
label | 427feaaa-1a5a-5f74-9948-d2501af8aff6 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.4.3 - AP150
label | 8404b74e-1ce1-5d4a-82a0-dfbb7d3d9192 |  | note | Controlled By : (Position) - SE
label | d33151d4-e770-523f-a879-fba78db1c9c8 |  | note | Accept / Reject Criteria - 300mm
label | 891f867c-2de6-5f05-8333-9aab012e2839 |  | note | Frequency Of Inspection Or Test - 1 per pavement area
label | 864148e7-7640-56cf-ba63-5bce7da6d3cc |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records with measuring tape
label | dd33e2bc-fd03-5258-9b2b-757c20757517 |  | note | Records Required - YES
label | 3cb3847f-267e-5885-8c3d-9fffe69e9049 |  | note | DOWNER ENGINEER - H
label | cb5e970f-616e-547a-8979-3f8532913018 |  | note | SUPERVISOR - R
label | 2a84494f-8a0e-505e-ad89-ff6a09ee16bd |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.4.4 - Geofabric
label | e3cc058f-6214-55c1-8992-47c80237fd8a |  | note | Controlled By : (Position) - SE
label | e0e1dcbc-dbb8-555a-9419-dcc8bb7b5fa0 |  | note | Accept / Reject Criteria - TX160
label | 51113734-fa8d-5ede-afe1-811415ca84ba |  | note | Frequency Of Inspection Or Test - 1 per pavement area
label | cbdf330e-d47b-5506-8263-cc7d6dbef292 |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records
label | 8ed90fa4-1c23-54cc-ae4f-2af2037bd730 |  | note | Records Required - YES
label | 36e04cc7-8a11-5068-9ba2-b2c134569ca4 |  | note | DOWNER ENGINEER - H
label | 50195ecc-ffb7-5672-b7ba-3f81ac8aa140 |  | note | SUPERVISOR - R
label | 0e626203-87a5-5cf9-bccf-13c083c22382 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.4.5 - AP65
label | 4b709676-a358-53ed-8a6d-365171da0dd7 |  | note | Controlled By : (Position) - SE
label | 14c1d7d7-d3c3-5aee-9f34-7116f3330728 |  | note | Accept / Reject Criteria - 200mm
label | 0ece815f-d9b5-578e-b5fe-32576cdb7a35 |  | note | Frequency Of Inspection Or Test - 1 per pavement area
label | 187cf602-cabe-5197-bb0b-ec77b04e4c1d |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records with measuring tape
label | fee2b51c-c2d2-58ed-a1f4-c094eafdce04 |  | note | Records Required - YES
label | 21150062-feab-5cdc-b76a-c22da7b20db9 |  | note | DOWNER ENGINEER - H
label | 1b5c5d70-7417-579a-b639-424a9d631886 |  | note | SUPERVISOR - R
label | ff7d31b9-4551-5a4a-ba48-377dda94780f |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.4.6 - AP40
label | 45e3b37e-7b78-5a7d-b535-4d648a4a8d41 |  | note | Controlled By : (Position) - SE
label | 455d9a06-a7ac-571d-af6f-f7920e1e2b2e |  | note | Accept / Reject Criteria - 100mm
label | 065a4c5c-6b16-550e-beb4-0ff975b5cf12 |  | note | Frequency Of Inspection Or Test - 1 per pavement area
label | 38225b3d-4046-5dc3-9532-885cd2bf2ba6 |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records
label | e7a72b6b-92ec-50b3-bb9b-a1d90faa2515 |  | note | Records Required - YES
label | 22d36658-17f9-55da-b9e5-e82d6e0be59e |  | note | DOWNER ENGINEER - H
label | 07ff9fc2-4a28-502d-a2b2-ef62ef3fca59 |  | note | SUPERVISOR - R
label | 12643083-98e6-5850-969e-5a4491992a65 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.4.7 - Surfacing
label | dbf87a11-e126-5352-a7e7-dca35f14db0b |  | note | Controlled By : (Position) - SE
label | dd1ab350-eb17-51ad-a672-99acb9ed3f9d |  | note | Accept / Reject Criteria - 50mm AC14
label | 15197057-547f-5c29-8685-dcaf095aa40a |  | note | Frequency Of Inspection Or Test - 1 per pavement area
label | 6c06547d-d0a9-5785-8611-199e25e1ff01 |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records
label | 63d40ef1-a84b-5757-88b7-0f6bd16bc6b0 |  | note | Records Required - YES
label | 797a3592-105d-54ef-9400-9e15931e980b |  | note | DOWNER ENGINEER - H
label | 923e0e62-6dcc-56c1-a217-937c9f5c19e5 |  | note | SUPERVISOR - R
label | a679c7a4-538c-5989-a17f-eca92752b55b |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6.5 - Area 5 - Optional
checkpoint-status |  |  | checkpoint | 6.5.1 - Mill top 90mm
label | 877e3ed2-cccf-530b-bb97-6cbf5ac6b8e5 |  | note | Controlled By : (Position) - SE
label | 25b51e5f-f39c-5540-8f64-cd0e74d59051 |  | note | Frequency Of Inspection Or Test - 1 per pavement area
label | c4e8a8ac-d2e3-5d6f-9289-6fbdfb548700 |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records
label | 58881641-54f9-541e-86ca-a761f1711598 |  | note | Records Required - YES
label | cb16d921-3ba4-521b-8df2-db77bfad7069 |  | note | DOWNER ENGINEER - H
label | eb75877a-6fda-5199-bd5e-489f769f02b5 |  | note | SUPERVISOR - R
label | d769487c-1aeb-55dd-89cc-185dbc84df67 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.5.2 - Subject to Beams Test
label | f931384f-f35b-5819-bced-62c9ac4ce44e |  | note | Controlled By : (Position) - SE
label | 1e32eba8-2865-5de0-a428-b693b607de47 |  | note | Accept / Reject Criteria - Backfill or Seal
label | 5d84e2b2-5b46-5ee2-91bc-f02842fa6372 |  | note | Frequency Of Inspection Or Test - 1 per pavement area
label | 6618f482-8c73-5240-9368-4649480d59c9 |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records and Results
label | 16fb917e-6c18-5b0d-b5be-47394f1b32a3 |  | note | Records Required - YES
label | ee9fded0-da39-5dc8-a739-b8418c858717 |  | note | DOWNER ENGINEER - H
label | 258fed5f-d956-503d-a196-4cf0d105a0f2 |  | note | SUPERVISOR - R
label | 39991afa-3e19-5c01-b4fb-f606f8fe4ba5 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.5.3 - Backfill
label | 1f8ad8af-f900-5eb4-922e-b29045a38a80 |  | note | Controlled By : (Position) - SE
label | 844c758a-ad16-56d5-b5a6-4be35e3bc9f4 |  | note | Accept / Reject Criteria - AP40 and stabilise top 200mm
label | 3fee6a6e-7076-5b66-a58c-121c2d1bf206 |  | note | Frequency Of Inspection Or Test - 1 per pavement area
label | d868468e-623a-5745-923b-16fc219550c4 |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records
label | eaf7aa04-e8d0-5f30-b282-12f3f7f5bf48 |  | note | Records Required - YES
label | 6ea60a30-a7a2-51b7-a23d-7d1af102bd8d |  | note | DOWNER ENGINEER - H
label | 70dc3e8e-d28e-516c-b675-45069827cb70 |  | note | SUPERVISOR - R
label | 5c3c2170-15a6-5613-bc08-4da0165097da |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.5.4 - Surfacing
label | 781ba1a2-31b7-55bc-bb47-25dbffd1f6fd |  | note | Controlled By : (Position) - SE
label | e64b8ff6-5183-533c-ad39-03340fdebe3c |  | note | Accept / Reject Criteria - 90mm EME2 (Trial Mix)
label | c52adcc6-6a4b-5656-aa80-04c0b76a6132 |  | note | Frequency Of Inspection Or Test - 1 per pavement area
label | 4baddcb5-f158-59fd-a79a-3b0841677947 |  | note | Spec. Ref, Procedure Or Method Statement - Project Specification Approved Mix Design
label | c5820989-4d13-5e39-b218-5972dc1b57a6 |  | note | Records Required - YES
label | cb679146-2268-5ce5-9cd7-9145d43b7c48 |  | note | DOWNER ENGINEER - H
label | b23ec619-7be2-545a-a490-335fc1485982 |  | note | SUPERVISOR - R
label | fea9e67e-e09b-5192-8c90-20408dd67f48 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7 - Post Construction (Final Inspection and Handover)
checkpoint-status |  |  | checkpoint | 7.1 - Final Completion inspection
label | 731301ad-a0fd-55e9-9433-b4282a3f7072 |  | note | Controlled By : (Position) - PM, ENG
label | 74f70189-b902-5655-867c-7a523791bfcf |  | note | Accept / Reject Criteria - Walk over completed with the Engineer/Engineers Representative to review completed works.
label | a4fa9a09-0a95-563b-a8d0-b0c33f638357 |  | note | ○ Noting any minor omissions, transfer to snag list (NCR if deemed necessary)
label | 043aad40-22ac-5bc8-8a53-43737afbf2de |  | note | Frequency Of Inspection Or Test - Each Site (School Zone etc)/Per package of works
label | 2cd8b04e-278d-5dbe-90f0-3353c7fc193f |  | note | Spec. Ref, Procedure Or Method Statement - DNZ Field Inspection Record
label | 1aa22705-5a9e-50fb-9cf6-2a8f0ffe0f17 |  | note | ○ Practical Completion Certificate (Per package of works, ie SP1/SP2)
label | d7ab4005-b441-510d-9e5d-e2739161381f |  | note | Records Required - YES
label | 6284c782-dd32-56fd-94a1-f06621cd546d |  | note | DOWNER ENGINEER - H
label | 9f43e416-4555-56a6-929c-f7e0885036c8 |  | note | SUPERVISOR - R
label | 4e616074-e033-517c-a4a4-8822eff5579c |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.2 - Construction Record Compilation
label | cb3850d9-25f1-58bd-81c6-bf56e372d705 |  | note | Controlled By : (Position) - SE
label | d88b0bf5-0cae-566a-8531-379ebb41be6c |  | note | Accept / Reject Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | d84d4a09-790c-5512-a31e-93dafed024c4 |  | note | Frequency Of Inspection Or Test - Post construction/Per package of works
label | b6ff5090-7bf9-570a-aae8-19b501d698bf |  | note | Spec. Ref, Procedure Or Method Statement - Records
label | e4d659c3-80fc-5779-83c0-dad576cc1cef |  | note | Records Required - YES
label | 99e0be8f-0571-591c-a035-97955c9b1bcd |  | note | DOWNER ENGINEER - H
label | 5dc3acda-e548-5fa2-945c-933401a75299 |  | note | SUPERVISOR - R
label | 42a31152-ee62-5b8c-a9d9-43c905160c6b |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.3 - Survey Records
label | f8dcd475-de5b-5374-89ef-3f8780adba54 |  | note | Controlled By : (Position) - SV
label | 2fe6a036-86d0-5a0e-b6c3-dd9c46e85189 |  | note | Accept / Reject Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | e2b270dc-f6d6-5868-abaf-c96aeee3ccf6 |  | note | Frequency Of Inspection Or Test - Post construction/Per package of works
label | dd968856-09fe-5784-9f56-ad4bf6360c8f |  | note | Spec. Ref, Procedure Or Method Statement - Records
label | 12fb0b58-baf2-553e-a0a9-129f991fab31 |  | note | Records Required - Yes
label | 2e9d903f-4de9-5df4-9720-dec0208aa5d2 |  | note | DOWNER ENGINEER - H
label | 1500daff-0845-53c5-9a48-23a93cb4db68 |  | note | SUPERVISOR - R
label | 69912234-8577-512d-a7ca-2b218244d1b7 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.4 - Asbuilt Drawings
label | 9133ed18-7c58-5778-a6c6-6132a37873ff |  | note | Controlled By : (Position) - SE
label | dc04bcd9-08af-593b-8dd6-a427f3f42457 |  | note | Accept / Reject Criteria - Supplied in accordance with Project specification
label | 20d85caf-d7b8-5fab-a417-2c2a83653065 |  | note | Frequency Of Inspection Or Test - Post construction/Per package of works
label | 2af5dfca-bc30-507b-8178-b666efdfe15b |  | note | Spec. Ref, Procedure Or Method Statement - Records
label | cfbed348-5db7-5e09-9724-e8993e2855cb |  | note | Records Required - YES
label | f817ae9c-267d-535c-b320-c6ad1e3e863b |  | note | DOWNER ENGINEER - H
label | b509e6fa-39e2-5f5d-9e64-3e3fbaea778c |  | note | SUPERVISOR - R
label | bb716d4e-659d-55f1-98d9-b0ba4b418df8 |  | note | SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations - Manning of a Checkpoint | itp |  |  |  | Yes | ITP - CONOC Operations (General) - Manning of a Checkpoint | f07fa236-6338-4cef-9419-d04a5648ad8e
checkpoint-status |  |  | checkpoint | 1 - Co-ordinating Incident Management (CIMMS)
label | aa67b987-e0a9-5eb0-ac7d-d5772bf9691f |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 63c878a1-6c22-5ac6-b9b3-2f4a4dc27b11 |  | note | Accept / Reject Criteria - As per specification
label | 6b2e4142-52a6-54e9-a269-ec1f9ec8f78b |  | note | Frequency Of Inspection Or Test - In-process
label | dc47f4ca-be84-5075-8f70-3e6dca34f418 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP100
label | 26d1b5f3-e577-5dc7-8ebe-83eaabe55d8f |  | note | Records Required - NO
label | 9cb4e2dc-ae65-5639-8d1f-a5e9da69ec04 |  | note | ENGINEER - R
label | 502cd41d-0824-538a-bb75-c44ce6395238 |  | note | SUPERVISOR - R
label | e125d38f-cb73-5abe-91c4-cf1a3d1ca287 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Preparation
label | 9afc364a-4219-5d30-984a-8ff59006ee51 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 2df699ab-9a79-5ac1-b0da-923b30f4cb01 |  | note | Accept / Reject Criteria - As per specification
label | b2742bfd-7f84-554c-8ed5-37cf9c5122a3 |  | note | Frequency Of Inspection Or Test - In-process
label | ae03d925-84c1-517d-b04b-01ad925389ca |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP100
label | 88206a82-e4c5-5cb3-94fa-ae334b0c235c |  | note | Records Required - NO
label | 44b4e96c-5bda-5065-9bd8-e06aa4ef4a4a |  | note | ENGINEER - R
label | 8372ab8c-d545-5f3b-b4dd-c6c3da9bb371 |  | note | SUPERVISOR - R
label | abf5cbdd-d64c-587b-b596-975ce0a4857a |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Manual Traffic Controller
label | 6a9ee792-b309-5eb9-a156-999496ed1f12 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | fcac6d75-e5dd-5968-83ec-f6ac87fb23af |  | note | Accept / Reject Criteria - As per specification
label | 97e600a3-5746-5057-a04c-fa0811452437 |  | note | Frequency Of Inspection Or Test - In-process
label | bd18a887-a999-5b7b-b435-cc90b0eef498 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP100
label | 51194d48-a298-5fe8-a490-b39e39b99543 |  | note | Records Required - YES
label | d4392984-d219-5e43-9914-5839eb37d576 |  | note | ENGINEER - W(10%)
label | 03a7eac2-7a92-5dda-ae6a-dbc3b6da5797 |  | note | SUPERVISOR - R
label | aa8926d4-7715-521c-9d7f-547f31ff537d |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Manual Traffic Controller Operation
label | f1d55602-d7af-5e99-a9a2-75570f50edd2 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 2275ce03-3287-530d-9cd3-768c588eaeac |  | note | Accept / Reject Criteria - As per specification
label | fa5cfc7f-aa33-5b39-bc4e-ac232c54203b |  | note | Frequency Of Inspection Or Test - In-process
label | 9f2aafa9-c906-5792-866f-b4136af460dc |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP100
label | a08e1304-a7ba-54a0-9814-88e48b87835a |  | note | Records Required - YES
label | 1a6a3dde-5f7c-575c-b982-9e0dd84b3fc7 |  | note | ENGINEER - W(10%)
label | bed0e9c2-e0a6-5587-8fa0-dceab0588ce2 |  | note | SUPERVISOR - R
label | b8ee2b53-eb2f-5bdd-80ce-1b2aa0c35209 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Establishment on Site
label | 13e8b3c5-133e-592e-922f-3727e920c41b |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 0f5ceba0-4caa-5950-b3a0-8dbbc5aa86cc |  | note | Accept / Reject Criteria - As per specification
label | bacc18f7-03f5-5e39-a673-a110493ee657 |  | note | Frequency Of Inspection Or Test - In-process
label | 055590c7-5a75-5154-a37a-c2f09192ec1b |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP100
label | 972f5ab9-e666-56c6-a1ac-ccfac6464518 |  | note | Records Required - NO
label | 34ab4f2d-b844-581b-8247-bb5b745e4a72 |  | note | ENGINEER - W(10%)
label | 84d69413-2806-5a68-84f3-bac1e7cadcf2 |  | note | SUPERVISOR - R
label | 707d86c5-0ba2-55d9-bb6b-2104071b03d4 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Inform the Public about Work Procedure and Progress
label | 0c291e07-bea1-5f79-99a5-6b7188742191 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 9714d6cc-9828-59dc-836a-57a3e628e489 |  | note | Accept / Reject Criteria - As per specification
label | c13b9cf3-00fb-519c-8175-a0c507dc534d |  | note | Frequency Of Inspection Or Test - In-process
label | 84e6f766-d969-50ec-8871-7afe66986af8 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP100
label | 26ba312d-0dc6-5ca5-b758-720184890484 |  | note | Records Required - NO
label | 17dcb395-ee54-5d6a-a369-f70b20e07ee6 |  | note | ENGINEER - W(10%)
label | ab06ab8e-4dbd-554f-b89e-59edb2935a83 |  | note | SUPERVISOR - R
label | 46b5c5cf-fa23-5082-8640-3bb4f21f48f0 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Media
label | a7664d08-6033-533c-af1f-ed9fac1ab672 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 00e15b71-5a86-5547-8b33-6e2ddaff9a55 |  | note | Accept / Reject Criteria - As per specification
label | 07690cf6-2385-5d60-817e-c0ae49fae626 |  | note | Frequency Of Inspection Or Test - In-process
label | 8affc2bc-c356-5f17-a73b-763069414049 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP100
label | d0993192-fb49-5585-b69f-f6044de5e5a1 |  | note | Records Required - NO
label | d1bfeecb-e422-54e8-9e5e-f6c90c97130c |  | note | ENGINEER - W(10%)
label | 8da9d252-6c09-5c1d-9ced-7b5e25dde11c |  | note | SUPERVISOR - R
label | 46084dd0-1b3a-53c7-98b9-33193e961445 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Incident Reporting
label | 72eeb82b-ad40-5207-861b-a0a22ab8fb30 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 7d910b9a-9b70-5fe9-a139-3948d0274525 |  | note | Accept / Reject Criteria - As per specification
label | d529b30e-b36a-5c73-8a43-e3da3dc74e0b |  | note | Frequency Of Inspection Or Test - In-process
label | 785be618-18e8-51ec-8e70-61cd91007017 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP100
label | 5cf79380-ad94-5af7-b2dc-f7766af50450 |  | note | Records Required - YES
label | 9eb4f45c-0007-59dd-98a6-44d7e626ac6c |  | note | ENGINEER - W(10%)
label | 4ddc7683-ae24-5607-81f0-55f8072531e6 |  | note | SUPERVISOR - R
label | 95896a91-364d-53c4-948e-d0b0e837c08d |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Test and Check
label | fcec4a02-4323-58da-a636-2471f7a8c3b0 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 1116551e-70c7-555c-b4a2-4299082712bf |  | note | Accept / Reject Criteria - As per specification
label | d2465c6c-8655-5fe9-bf96-14d17f938255 |  | note | Frequency Of Inspection Or Test - In-process
label | 83fa3faa-84ac-56ff-9ddc-7c9a242bbf8e |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP100
label | b11cd5fa-1456-5d10-93b5-91a560ac0597 |  | note | Records Required - NO
label | ccf045f9-32e1-5159-80be-e707cf26d08f |  | note | ENGINEER - W(10%)
label | b95e1494-3d61-54bd-a3d0-c0e3a7384cb4 |  | note | SUPERVISOR - R
label | 41cc4425-7d58-504d-a97e-e47e0aea0df5 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC NETWORK - Install a Concrete Culvert Less Than 900mm in Diameter | itp |  |  |  | Yes | ITP - CONOC NETWORK - Install a Concrete Culvert Less Than 900mm in Diameter | f514a50e-8f5b-421e-89e0-936c764f8878
checkpoint-status |  |  | checkpoint | 1 - Prepare the Site
label | ab95cb15-40b4-551a-a1bf-4964bd1c2641 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 36dbfee3-9293-5b9e-8dc2-b92c3038988a |  | note | Accept / Reject Criteria - As per specification
label | 1ff1cf12-668e-5a55-81cf-2f8b17fd32a5 |  | note | Frequency Of Inspection Or Test - In-process
label | fef74b64-1e01-554c-811e-927d4bdd2461 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP082/Ground Distrubance Permit
label | d4e6ffab-18a6-5c13-b532-c51f15e797fc |  | note | Records Required - YES
label | 3bc26f35-5eb1-55c3-bb65-dc6423bfb458 |  | note | ENGINEER - R
label | f2909cb6-6bea-5be3-b8ce-103693d2c6c3 |  | note | SUPERVISOR - R
label | 900ca07f-5290-5efa-b575-efad51de259d |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Setting Out
label | a37e5e06-21fa-50ab-9d28-8a050f862890 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 8631b75f-17f4-5ce9-84e8-70564548b90a |  | note | Accept / Reject Criteria - Check the Start, end and invert level is set out
label | 01cba47d-6617-5e5a-b4ab-786445d4466f |  | note | Frequency Of Inspection Or Test - In-process
label | 4585947b-ec07-5600-b501-b96d4f725c86 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP082
label | 6f5c1552-f25d-5bbf-8001-0c3bb0eeafbd |  | note | Records Required - YES
label | e01f35f0-65cb-5049-86ff-d6c71ec95fa0 |  | note | ENGINEER - W
label | a5a73299-40a5-5ea3-a3ee-39829f7f100a |  | note | SUPERVISOR - W(10%)
label | 91b94636-aff8-5ac9-85a5-1ea1ad972a31 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Excavation
label | ff75faa3-658b-54e2-bdd8-797dd1927004 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 4d9e5496-2037-51d1-a5a4-4bdf42803504 |  | note | Accept / Reject Criteria - Lay Bedding 100mm deep
label | 869694e0-5b9c-53af-9126-57d1f0a8659c |  | note | Frequency Of Inspection Or Test - Regular Interval
label | 12cbdc8c-e429-508a-9a92-9f48e181b38c |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP082
label | a62ef34d-1e96-518b-8e4a-08ceffd31f9f |  | note | Records Required - YES
label | 2c981801-32e5-510b-b429-9d1fefb52417 |  | note | ENGINEER - W(10%)
label | 9a42dade-7e6e-5fe5-aaf1-b301edce5865 |  | note | SUPERVISOR - R
label | def53221-9bfe-559b-988e-086ff3084161 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Prepare the Base
label | da7f5b18-3427-5c8b-8d09-d10d0fe3c67b |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 8b6497a0-5367-5271-b57c-883c4339dd42 |  | note | Accept / Reject Criteria - Meaasure pipe collar location
label | ed3c3cad-e610-5403-b431-c9e8454bb17b |  | note | Frequency Of Inspection Or Test - Atleast 1 check/Culvert
label | e7b2c997-4fdf-5467-acea-1dd4988d4c96 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP082
label | 3bc3ee60-8e14-51ff-a5e2-995f6ea8d462 |  | note | Records Required - YES
label | 65893569-c156-50dd-aea8-2972dba174af |  | note | ENGINEER - W
label | 9c00385c-78aa-5b7f-9045-5abe5f71557a |  | note | SUPERVISOR - W(10%)
label | 1d3cbb84-1a86-5f68-96a2-866444632b5a |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Prepare Pipes
label | 8ce39993-252c-56c6-a388-8408eaf8e485 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 7d822b54-6b4a-5c23-a13e-b06cfe005edd |  | note | Accept / Reject Criteria - As per specification
label | b11188bf-5de5-5327-9d60-159a73291c8a |  | note | Frequency Of Inspection Or Test - In-process
label | c747d33a-2699-5c01-a0e7-d2b7e9ce0e5a |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP082
label | 99965f75-a086-50f5-814d-fb90051b4036 |  | note | Records Required - NO
label | 692936b9-f57f-55a6-9899-95dd3f9132c5 |  | note | ENGINEER - W(10%)
label | 9ecd7e72-a6cd-5790-8201-e04a5a0f0662 |  | note | SUPERVISOR - R
label | 85cd02c5-10ef-54ae-8f8e-9d6e077a678a |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Lay Pipes
label | 5709768e-d09b-5f40-9630-4a36dc73b66c |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 9f7754c0-907c-549c-9986-93e65556483c |  | note | Accept / Reject Criteria - 300mm bedding material both side
label | 63788ea1-3e30-5fb7-96c1-53ba13915866 |  | note | Frequency Of Inspection Or Test - Regular Interval
label | c2cb9ab5-acab-588c-bd94-ddc2f10c4925 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP082
label | a55f5d17-a59c-51bb-adf9-03bca814be1e |  | note | Records Required - YES
label | a85032f6-a498-5ec3-b21b-b24f8918a863 |  | note | ENGINEER - W(10%)
label | 15946244-0dec-5c2d-851a-f12e3bc0a8f9 |  | note | SUPERVISOR - R
label | c80c85dd-0bca-5442-a1e6-fc916d07138c |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Backfilling
label | f102d7ee-6277-5771-9a9f-fc46e4a825b6 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 108d5fb3-b224-5b43-ba36-e00b7890c6a5 |  | note | Accept / Reject Criteria - As per specification
label | ba983632-8659-5c36-8ee0-0777d12e9a78 |  | note | Frequency Of Inspection Or Test - In-process
label | 80aaf244-d03e-5bde-854c-f5ca1ad1b75e |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP082
label | 2d8e9aec-db3a-50a0-8ba8-af5f8211115c |  | note | Records Required - YES
label | 34fd3dc4-5e61-5699-86b3-d4c7c8c26aa1 |  | note | ENGINEER - W(10%)
label | 517943a9-9f3f-5dbf-82b8-6c5705dbd5ad |  | note | SUPERVISOR - R
label | 6eb12711-a61e-5e68-91d3-ae6019488909 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Restore Pavement
label | 9757eadf-56db-5873-8a70-66837ccd3514 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 2b4f0b6e-769b-5338-895e-11379cc83f67 |  | note | Accept / Reject Criteria - Refer GP030
label | 84891cf4-6999-5cda-ba3e-9bbfc4a39759 |  | note | Frequency Of Inspection Or Test - In-process
label | 6cf935e0-1428-5598-8ebe-fea38c15ecfc |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP082
label | b19de981-a310-5aff-a299-c862e9ffe643 |  | note | Records Required - YES
label | b826ce83-d3fa-5dfc-a082-a219c24e7bd9 |  | note | ENGINEER - W(10%)
label | 62cab126-8e15-59a9-ae62-852230b40f83 |  | note | SUPERVISOR - R
label | 00faa17b-877e-5fc4-a947-023aec5240b4 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Test and Check
label | e788acb6-47fd-5db1-8810-81aa311d6868 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 268f9c5e-c5fc-50f0-bcd4-34cfceac62d3 |  | note | Accept / Reject Criteria - Inlet and Outlet should be within ±25mm for level
label | a3965f6f-23ec-5d7d-9ee0-dbde1dc58e1e |  | note | Frequency Of Inspection Or Test - Atleast 1 check/Culvert
label | 124704c0-90cf-5c24-93b7-81dd815b02d3 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP082
label | b1e4be5b-bbcc-596c-a84d-7bd9210422f3 |  | note | Records Required - YES
label | 2c1e4e79-5c41-55e5-9474-d848598cb07f |  | note | ENGINEER - W
label | a52b3a71-b855-5d07-9f80-2fbb12f40dca |  | note | SUPERVISOR - W(10%)
label | 746b9f70-5f66-5d4e-8030-42965d469763 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC Operations (Heavy and Light Maintenance) - Edgebreak Repair - Formed Shoulder (Manual Premix Method) | itp |  |  |  | Yes | ITP - CONOC Operations (Heavy and Light Maintenance) - Edgebreak Repair - Formed Shoulder (Manual Premix Method) | fafce593-df7a-4d27-bddd-aede53bf49be
checkpoint-status |  |  | checkpoint | 1 - Prepare Site
label | 2052e0cd-720c-54dc-a0b7-0962d945fff1 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 63c6dbd3-7b67-5498-b3d8-87e45db8727d |  | note | Accept / Reject Criteria - As per Specification
label | 3fb5e8af-577d-589d-b31e-2ecafcf22a86 |  | note | Frequency Of Inspection Or Test - In- process
label | 4beabdf2-bb09-5ff3-9d7a-267f15ae6eef |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP036
label | 7bd31070-686e-5fef-a451-aad19fad8796 |  | note | Records Required - NO
label | ef70e9be-29a9-5f39-b81c-0c80f3a21805 |  | note | DOWNER ENGINEER - R
label | cebeb1e1-1fa7-5032-b290-a66da1f9c76e |  | note | SUPERVISOR - R
label | dabb330d-4efe-56f5-98a9-6d8dd7b93497 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Prepare Shoulder
label | 303b896d-4c70-555b-81c8-2146452923b6 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 0161e9bf-1299-53f4-b710-1b645aee1cac |  | note | Accept / Reject Criteria - As per Specification
label | 49e0dbf3-e75c-5e7b-9c4c-57810730b12b |  | note | Frequency Of Inspection Or Test - In- process
label | 913d2dc2-d4d7-5c01-a738-ec6cca4281a6 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP036
label | 48095cd8-bca9-5d9b-ad0f-7f78af8669d9 |  | note | Records Required - NO
label | e641704d-d2b3-5041-8e87-c7514445f93b |  | note | DOWNER ENGINEER - W(10%)
label | c46f9238-1c6a-5edd-bd7d-e80f33bdf9ab |  | note | SUPERVISOR - R
label | f5ae155b-9afa-5905-82ec-e55eb13db0dc |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Filling the Edge Break
label | 89869efb-9b1f-5c78-97c6-597e7cb6ad8c |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | f951f2d2-0aa5-5457-8963-965770f109f6 |  | note | Accept / Reject Criteria - As per Specification
label | 1e11e00b-a0c1-5436-8a94-73d110b4fa82 |  | note | Frequency Of Inspection Or Test - In- process
label | 4a2aea4f-15bb-5c49-86ea-4decd65f34ee |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP036
label | 5355953e-2363-5d87-9596-4d939ab56a0e |  | note | Records Required - NO
label | dd00e07c-ce6e-56c1-9253-ba4704abc749 |  | note | DOWNER ENGINEER - W(10%)
label | ebaf59cb-2fb2-5e7c-ba51-70f4047739c3 |  | note | SUPERVISOR - R
label | e8587c80-ec7b-559a-aa13-03783a9f87fe |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Reconstruction Supporting Shoulder
label | a1cf904f-c0c5-545b-8fad-f91b867dc6a2 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 36ea003f-74a2-5f97-b599-56eab585fba5 |  | note | Accept / Reject Criteria - As per Specification
label | 7ba82b42-350e-568c-9150-43519607c342 |  | note | Frequency Of Inspection Or Test - In- process
label | 9d0a3e4b-bd70-5bb2-9adc-b987854fe685 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP036
label | 43be069f-6adf-5c32-a5e9-26defb46f43e |  | note | Records Required - YES
label | 068fd7ba-296a-5a15-920e-dd6e9f272c55 |  | note | DOWNER ENGINEER - W(10%)
label | 2b8b8208-a03a-5910-b117-624d48bb69a4 |  | note | SUPERVISOR - R
label | be46b6a2-50f0-5886-836b-d42c15c7f5e8 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Blinding
label | b7c8ef31-71cb-5f80-bdcd-7e9631b8867f |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 5526d81c-7b4e-5c81-b727-1d7a82ec0f67 |  | note | Accept / Reject Criteria - As per Specification
label | 6264bb2a-1675-55b9-9b4b-c0388162bbd9 |  | note | Frequency Of Inspection Or Test - In- process
label | e6234fe1-4171-5565-b5b6-b1e94fb71d9c |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP036
label | a8846ce5-5952-5694-88a6-51bcaff1c3eb |  | note | Records Required - NO
label | 0d0580db-a235-5262-9076-a79c61dd5885 |  | note | DOWNER ENGINEER - W(10%)
label | 2c925492-5121-5024-8740-26b3c0100f07 |  | note | SUPERVISOR - R
label | dbd77cf9-4f31-58fd-ba01-9668615e7b24 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Test and Check
label | 78dd703a-db90-589a-9cd4-ce52265eca23 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | b323d326-438f-5b1d-83ab-3c3e84432b10 |  | note | Accept / Reject Criteria - As per Specification
label | 49d12d55-bd2c-5e3d-8b0d-706eb921d58a |  | note | Frequency Of Inspection Or Test - In- process
label | 1ccf99c9-4281-56c8-b6ec-4832402d3698 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP036
label | 14758bbc-5456-57f8-9f96-133f2be601cc |  | note | Records Required - NO
label | 0c40f709-9fbd-5340-9dfe-cce8c69e6e5d |  | note | DOWNER ENGINEER - W(10%)
label | 74b9800a-7a01-50e4-bc8d-5adfe68cbf8b |  | note | SUPERVISOR - R
label | 250dbea3-5985-54bd-9b83-f619b22dbdf3 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - CONOC NETWORK - Guardrail Construct Thriebeam Type with Steel 'I' Posts | itp |  |  |  | Yes | ITP - CONOC NETWORK - Guardrail Construct Thriebeam Type with Steel 'I' Posts | ffa8254c-2813-42b0-a514-38a6e0ab5b70
checkpoint-status |  |  | checkpoint | 1 - Prepare the Site
label | 90eac569-fc50-535a-ad92-3c536e0aba61 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | f496ed31-8d95-5b57-9e77-5e8ce3d578d4 |  | note | Accept / Reject Criteria - As per Specification
label | 0af12d78-f91d-5a0b-81eb-4a8c32d8af18 |  | note | Frequency Of Inspection Or Test - In-process
label | 630b1cf0-8f40-5c50-ae1f-59b74aa21194 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP141
label | 7e7bd1f4-6a01-59b0-8ae3-ce1cd8ab4ca9 |  | note | Records Required - NO
label | eb6f8c66-e1af-5127-b1ce-612841c3570a |  | note | ENGINEER - R
label | a7452052-798f-5d5e-b6e4-f70d9a26f820 |  | note | SUPERVISOR - R
label | 7316fa76-838a-5b12-85ee-d4d887195438 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Place Posts
label | 93ed6c48-b0b6-566e-8aa8-c40ade3267cb |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 96474ba0-d7f4-5eb8-920b-17272ef1908b |  | note | Accept / Reject Criteria - As per Specification
label | 33582888-02a3-5161-b5a4-ea58cace7485 |  | note | Frequency Of Inspection Or Test - In-process
label | 0de4df0c-38f0-5ae9-bff9-1a756a254d31 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP141
label | 98ab36ba-55c8-5c0e-b805-b9a34cd18c49 |  | note | Records Required - NO
label | de6ec044-1ab6-5af5-bb74-4c987f40508e |  | note | ENGINEER - R
label | 6dc6b69f-95c5-5e88-baef-42a4bc70a915 |  | note | SUPERVISOR - R
label | c938f944-6262-5213-b392-d7e550a1b7c9 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Installation of 'modified block-outs' and 'back-up plates'
label | 43a025af-2cef-5100-9a4d-b7ad6c92c728 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 8b224af7-88bb-5c2f-a69e-836fca5c538a |  | note | Accept / Reject Criteria - As per Specification
label | 6bcf559f-cf67-5279-b21c-bdcee8e41123 |  | note | Frequency Of Inspection Or Test - In-process
label | a86dc605-9ffe-5eaa-9135-fb2c28d4bc11 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP141
label | 6e39e2e7-143e-5120-93a6-a78eaac535af |  | note | Records Required - NO
label | 86fbb630-f4b2-5332-a8ba-912367a214a2 |  | note | ENGINEER - W(10%)
label | be2853c0-6938-5161-b646-227ec21d0357 |  | note | SUPERVISOR - R
label | bc088824-766e-5d11-878c-22dc2144ca50 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Erect Guardrail
label | 36029f17-bb81-580d-be79-8811afada466 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | df3cb92b-abe8-5936-8929-06f097f78e18 |  | note | Accept / Reject Criteria - As per Specification
label | 3ca1d710-3cdb-58bb-bf5a-9430e16c7d37 |  | note | Frequency Of Inspection Or Test - In-process
label | b7d620a9-5185-5d79-a2ff-41c0159595b7 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP141
label | bab1cfeb-3945-500b-a02c-2dbd97791da1 |  | note | Records Required - NO
label | ceb7430c-9cad-5918-8047-73486d794407 |  | note | ENGINEER - W(10%)
label | f1ae2149-4bb2-5d92-8e12-b43093d15dca |  | note | SUPERVISOR - R
label | d9ede0ff-607c-5305-8674-ab092a8b0de7 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Attach Terminal End
label | ed4b8013-49a2-53e9-8836-1f7c1e8f9198 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | f8d099ce-cfe7-5fa5-9f16-348c3b8f32ee |  | note | Accept / Reject Criteria - As per Specification
label | f898d65e-9d62-5283-a6ff-4e1948f4c033 |  | note | Frequency Of Inspection Or Test - In-process
label | 0911da12-7759-5756-9e07-8de61187b446 |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP141
label | 29cc3c7a-a5a6-563b-9dd9-7d2648e0f1b7 |  | note | Records Required - NO
label | 2cd0b39e-6809-5528-910f-32a9e2d81191 |  | note | ENGINEER - W(10%)
label | cd1a90f5-51d6-54c7-aced-fef6bd606b03 |  | note | SUPERVISOR - R
label | 835de83c-a60b-556c-b5df-46f04417170e |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Finishing
label | 37d93baa-4c82-563b-9962-46a4f570023c |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | 40f27f37-304d-505d-8e9e-2c0b9bf3dbe9 |  | note | Accept / Reject Criteria - As per Specification
label | 753dd139-ae0f-5cc0-b430-fcdc9928ab7d |  | note | Frequency Of Inspection Or Test - In-process
label | ddc63a61-d3bd-5160-a824-b2958ac4d0de |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP141
label | 447af819-a1c0-58b4-9ee7-d0123385819e |  | note | Records Required - NO
label | 21644ec7-b050-5736-a94b-7113f1c6b4e4 |  | note | ENGINEER - W(10%)
label | ce98697f-8425-5a1c-9553-f4afd64247a5 |  | note | SUPERVISOR - R
label | 48fb98c6-4af2-550e-aa88-fd8f129ee4a1 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Test and Check
label | ab64e152-fac3-5666-bc8f-f9c847f4a899 |  | note | Controlled By : (Position) - Sub Sup/Downer Eng
label | f140f0e2-e859-5016-8e77-fc99d0f59c9e |  | note | Accept / Reject Criteria - As per Specification
label | f794e362-118d-503c-9769-dc6cd1b63f82 |  | note | Frequency Of Inspection Or Test - In-process
label | 170e3910-4adc-54ef-b817-115185093c0e |  | note | Spec. Ref, Procedure Or Method Statement - DN-GD-GP141
label | 9a05e5eb-c5c5-5e45-b0a1-e32b208ac682 |  | note | Records Required - YES
label | 08d9d098-c1f7-5e28-b0d7-aef3af98c281 |  | note | ENGINEER - W(10%)
label | e176e14b-c885-5bb1-80ef-d551881c8664 |  | note | SUPERVISOR - R
label | 612979ff-8421-554c-9c35-8f17e2f71912 |  | note | Downer/ SUB-CON - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT