## Braeside Culvert Replacement
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH01 Braeside Culvert Replacement (SH01 Braeside RS 0720 RB/1.020) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
SH01 Braeside Culvert Replacement |  |  | As per Specification Ref, Procedure Or Method Statement |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER | Description |  |  |  | W(5%) | Sub Supervisor
1.1 | Preliminary and General
1.1 | Construction Programme Completion |  | Project Manager | Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date. | Confirmation/Before work commences | Best Practice Contract Specific MMP | YES | W
1.2 | Approved RQP |  | NZTA Maintenance Contact Manager | Principal Acceptance according to guidelines in appendix 6.3 | Confirmation/Before work commences | Contract Specification | YES | H | Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
1.3 | Traffic Management (TMP) |  | Project Manager | TMP checked and approved Plans approved Current EED (if applicable) | Visual Check/Before traffic management set up | CoPTTM | YES | H | Hold point - No traffic management is to be set up until TMP has been checked and approved
1.4 | Notification of intention to start work |  | Project Manager | Letter drop to local residents. Where required and defined by SWAMP, VMS, social media/media advertising | Notification/Before work commences |  | YES | H | Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
2 | Set-Out/Site Preparation
2.1 | Setout |  | Project Manager |  | Survey/Pre-Installation | Best Practice | YES | W
2.2 | Permit to dig/Authority to Work/close approach permits |  | Construction Foreman | Organisational approval | Permit Approved/Before work commences | Downer Permit to work or Equvilent | YES | H | Hold point - No excavation is to be commenced until approvals are gained
2.3 | Cultural/Heritage Risk Assessment |  | Project Manager | Local iwi has been notified of intent to start work | Notification/Before work commences | WK Cultural & Heritage Risk Model | YES | H
2.4 | Archaeological Risk |  | Project Manager | Toolbox meeting held covering accidental discovery protocol | Toolbox meeting/Before work commences | WK Cultural & Heritage Risk Model | YES | H | Hold point - No excavation is to be commenced until toolbox meeting is held
2.5 | Traffic Management Setup |  | Construction Foreman / STMS | Traffic management complies with TMP | Visual Check/Before work commences each day | Traffic Management Plan | YES | H | Hold point - No physical works are to be commenced until necessary traffic management is in place
2.6 | Site Setout |  | Construction Foreman | Verification of survey control points and setup | Measurement/Before Excavation | On Site | YES | H | Hold point - Survey set-up accuracy to be verified with aid of surveyor or specialist
2.7 | Prepare String Sheet (Digital) |  | Project Manager | Digital design set-out data is consistent with existing formation | Measurement/Before using machine control | On Site | YES | H | Hold point - Design accuracy to be verified prior to undertaking work
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 17/05/2024 |  |  | DATE: 17/05/2024 |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH01 Braeside Culvert Replacement (SH01 Braeside RS 0720 RB/1.020) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
SH01 Braeside Culvert Replacement |  |  | As per Specification Ref, Procedure Or Method Statement |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | Discription |  |  |  | W(5%) | Sub Supervisor
3 | Drainage | [11 empty] | W & I | Supplier
3.1 | Earthwork and Stripping
3.1.1 | Cut/Excavation |  | Project Manager | Meets design drawings of cross-sectional extent | Measurement/Tape measure from set-out or existing CL, as per design | On Site | YES | H | Hold point - Excavation width needs to be checked against the design cross-sections to ensure correctness
3.2 | Drainage Structures
3.2.1 | HW B-01 |  | Project Manager | Survey setout location, measure invert depth, As per design drawings and/or NZTA F/2 Specification (if required or specified) | Meaasurement/During construction | NZS2566.2 & TNZ F2 | YES | H | Hold point - Design accuracy to be verified prior to undertaking work
3.2.2 | HW B-02 |  | Project Manager | Survey setout location, measure invert depth, As per design drawings and/or NZTA F/2 Specification (if required or specified) | Meaasurement/During construction | NZS2566.2 & TNZ F2 | YES | H | Hold point - Design accuracy to be verified prior to undertaking work
3.2.3 | HW B-03 |  | Project Manager | Survey setout location, measure invert depth, As per design drawings and/or NZTA F/2 Specification (if required or specified) | Meaasurement/During construction | NZS2566.2 & TNZ F2 | YES | H | Hold point - Design accuracy to be verified prior to undertaking work
3.2.4 | HW B-07 |  | Project Manager | Survey setout location, measure invert depth, As per design drawings and/or NZTA F/2 Specification (if required or specified) | Meaasurement/During construction | NZS2566.2 & TNZ F2 | YES | H | Hold point - Design accuracy to be verified prior to undertaking work
3.2.5 | MH B-04 |  | Project Manager | Survey setout location, measure invert depth, As per design drawings and/or NZTA F/2 Specification (if required or specified) Cobel/starters set and constructed as per regional/NZTA standards | Meaasurement/During construction | NZS2566.2 & TNZ F2 | YES | H | Hold point - Design accuracy to be verified prior to undertaking work
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 17/05/2024 |  |  | DATE: 17/05/2024 |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH01 Braeside Culvert Replacement (SH01 Braeside RS 0720 RB/1.020) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
SH01 Braeside Culvert Replacement |  |  | As per Specification Ref, Procedure Or Method Statement |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | Discription |  |  |  | W(5%) | Sub Supervisor
3.2.6 | MH B-05 |  | Project Manager | Survey setout location, measure invert depth, As per design drawings and/or NZTA F/2 Specification (if required or specified) Cobel/starters set and constructed as per regional/NZTA standards | Meaasurement/During construction | NZS2566.2 & TNZ F2 | YES | H | Hold point - Design accuracy to be verified prior to undertaking work |  |  |  | W & I | Supplier
3.2.7 | MH B-06 |  | Project Manager | Survey setout location, measure invert depth, As per design drawings and/or NZTA F/2 Specification (if required or specified) Cobel/starters set and constructed as per regional/NZTA standards | Meaasurement/During construction | NZS2566.2 & TNZ F2 | YES | H | Hold point - Design accuracy to be verified prior to undertaking work
3.2.8 | Other Structures |  | Project Manager | Constructed to design drawings and relevant standards | Visual Check/Continuous |  | YES | H | Hold Point – Visual check prior to pavement construction
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 17/05/2024 |  |  | DATE: 17/05/2024 |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH01 Braeside Culvert Replacement (SH01 Braeside RS 0720 RB/1.020) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
SH01 Braeside Culvert Replacement |  |  | As per Specification Ref, Procedure Or Method Statement |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | Discription |  |  |  | W(5%) | Sub Supervisor
3.3 | Ancillary Works | [11 empty] | W & I | Supplier
3.3.1 | Ancillary Items as per design Example: - Rock Benching - Signage - Vegetation/Trees - Kerb and Channel - Underground Services - Service Covers |  | Project Manager | Constructed to design drawings and relevant standards | Visual Check/Once |  | Yes | H | Hold Point – Visual check prior to pavement construction
3.3.2 | Rock aprons |  | Project Manager | As per drawing details or as directed by the Engineer | Visual Check/During Construction |  | Yes | W
3.4 | Subsoil Drainge
3.4.1 | Subsoil Drain Construction |  | Construction Foreman | As per design drawings and/or NZTA F/2 Specification (if required or specified) | Visual/Each Site |  | Yes | W | Hold Point – Visual check prior to pipe placement
3.4.2 | Inlets/Outlets |  | Construction Foreman | Connect to sump/catchpit, Concrete Apron, Open Channel, Inspection Eyes. | Visual |  | Yes | W | Hold Point – Visual check prior to reinstatement
3.5 | Pipe Installation B-01
3.5.1 | Trench Excavation |  | Construction Foreman | - excavate to achieve required depth to invert as per drawings - Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe - Floor of trench to be even across width and length | Visual/Ongoing | NZS2566.2 & TNZ F2 | Yes | W
3.5.2 | Subgrade |  | Construction Foreman | minimum 5 blows per 100mm | measurement/every 2m inline with trench | Scala Penetrometer | Yes | H | Hold Point - Record scala measurement and adivse PM if criteria not met
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 17/05/2024 |  |  | DATE: 17/05/2024 |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH01 Braeside Culvert Replacement (SH01 Braeside RS 0720 RB/1.020) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
SH01 Braeside Culvert Replacement |  |  | As per Specification Ref, Procedure Or Method Statement |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | Discription |  |  |  | W(5%) | Sub Supervisor
3.5.3 | Install Pipe |  | Construction Foreman | As per design drawings and/or NZTA F/2 Specification (if required or specified) | Visual/Each Pipe | NZS2566.2 & TNZ F2 | Yes | W | Record invert |  |  |  | W & I | Supplier
3.5.4 | Embedment Zone |  | Construction Foreman | Embedment material shall be AP20 or approved by the Engineer in writing | Visual/every 5m inline with trench | NZS2566.2 & TNZ F2 | Yes | W | Compacted material recorded via clegg test
3.5.5 | Backfill and Compact |  | Construction Foreman | - Backfill in 200mm layers of compacted material - Compaction testing one test every two layers as required - conductive signal strip to be laid at …mm cover | Visual/Every layer, every 5m inline with trench | NZS2566.2 & TNZ F2 | Yes | H | Hold Point - Compacted materiial recorded via clegg testing - tests must pass to continue with backfill
3.6 | Pipe Installation B-02
3.6.1 | Trench Excavation |  | Construction Foreman | - excavate to achieve required depth to invert as per drawings - Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe - Floor of trench to be even across width and length | Visual/Ongoing | NZS2566.2 & TNZ F2 | Yes | W
3.6.2 | Subgrade |  | Construction Foreman | minimum 5 blows per 100mm | Measurement/Every 2m inline with trench | Scala Penetrometer | Yes | H | Hold Point - Record scala measurement and advise PM if criteria not met
3.6.3 | Install Pipe |  | Construction Foreman | As per design drawings and/or NZTA F/2 Specification (if required or specified) | Visual/Each Pipe | NZS2566.2 & TNZ F2 | Yes | W | Record invert
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 17/05/2024 |  |  | DATE: 17/05/2024 |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH01 Braeside Culvert Replacement (SH01 Braeside RS 0720 RB/1.020) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
SH01 Braeside Culvert Replacement |  |  | As per Specification Ref, Procedure Or Method Statement |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | Discription |  |  |  | W(5%) | Sub Supervisor
3.6.4 | Embedment zone |  | Construction Foreman | Embedment material shall be AP20 or approved by the Engineer in writing | Visual/Every 5m inline with trench | NZS2566.2 & TNZ F2 | Yes | W | Compacted material recorded via clegg test
3.6.5 | Backfill and Compact |  | Site Engineer | - Backfill in 200mm layers of compacted material - Compaction testing one test every two layers as required - conductive signal strip to be laid at …mm cover | Visual/Every layer, every 5m inline with trench | NZS2566.2 & TNZ F2 | Yes | H | Hold Point - Compacted materiial recorded via clegg testing - tests must pass to continue with backfill
3.7 | Pipe Installation B-03 North Lane
3.7.1 | Trench Excavation |  | Construction Foreman | - excavate to achieve required depth to invert as per drawings - Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe - Floor of trench to be even across width and length | Visual/Ongoing | NZS2566.2 & TNZ F2 | Yes | W
3.7.2 | Subgrade |  | Construction Foreman | minimum 5 blows per 100mm | Measurement/Every 2m inline with trench | Scala Penetrometer | Yes | H | Hold Point - Record scala measurement and advise PM if criteria not met
3.7.3 | Install Pipe |  | Construction Foreman | As per design drawings and/or NZTA F/2 Specification (if required or specified) | Visual/Each Pipe | NZS2566.2 & TNZ F2 | Yes | W | Record invert
3.7.4 | Embedment zone |  | Construction Foreman | Embedment material shall be AP20 or approved by the Engineer in writing | Visual/Every 5m inline with trench | NZS2566.2 & TNZ F2 | Yes | W | Compacted material recorded via clegg test
3.7.5 | Backfill and Compact |  | Site Engineer | - Backfill in 200mm layers of compacted material - Compaction testing one test every two layers as required - conductive signal strip to be laid at …mm cover | Visual/Every layer, every 5m inline with trench | NZS2566.2 & TNZ F2 | Yes | H | Hold Point - Compacted materiial recorded via clegg testing - tests must pass to continue with backfill
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 17/05/2024 |  |  | DATE: 17/05/2024 |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH01 Braeside Culvert Replacement (SH01 Braeside RS 0720 RB/1.020) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
SH01 Braeside Culvert Replacement |  |  | As per Specification Ref, Procedure Or Method Statement |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | Discription |  |  |  | W(5%) | Sub Supervisor
3.8 | Pipe Installation B-03 South Lane
3.8.1 | Trench Excavation |  | Construction Foreman | - excavate to achieve required depth to invert as per drawings - Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe - Floor of trench to be even across width and length | Visual/Ongoing | NZS2566.2 & TNZ F2 | Yes | W
3.8.2 | Subgrade |  | Construction Foreman | minimum 5 blows per 100mm | Measurement/Every 2m inline with trench | Scala Penetrometer | Yes | H | Hold Point - Record scala measurement and advise PM if criteria not met
3.8.3 | Install Pipe |  | Construction Foreman | As per design drawings and/or NZTA F/2 Specification (if required or specified) | Visual/Each Pipe | NZS2566.2 & TNZ F2 | Yes | W | Record invert
3.8.4 | Embedment zone |  | Construction Foreman | Embedment material shall be AP20 or approved by the Engineer in writing | Visual/Every 5m inline with trench | NZS2566.2 & TNZ F2 | Yes | W | Compacted material recorded via clegg test
3.8.5 | Backfill and Compact |  | Site Engineer | - Backfill in 200mm layers of compacted material - Compaction testing one test every two layers as required - conductive signal strip to be laid at …mm cover | Visual/Every layer, every 5m inline with trench | NZS2566.2 & TNZ F2 | Yes | H | Hold Point - Compacted materiial recorded via clegg testing - tests must pass to continue with backfill
3.9 | Pipe Installation B-04
3.8.1 | Trench Excavation |  | Construction Foreman | - excavate to achieve required depth to invert as per drawings - Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe - Floor of trench to be even across width and length | Visual/Ongoing | NZS2566.2 & TNZ F2 | Yes | W
3.9.1 | Trench Excavation |  | Construction Foreman | - excavate to achieve required depth to invert as per drawings - Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe - Floor of trench to be even across width and length | Visual/Ongoing | NZS2566.2 & TNZ F2 | Yes | W
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 17/05/2024 |  |  | DATE: 17/05/2024 |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH01 Braeside Culvert Replacement (SH01 Braeside RS 0720 RB/1.020) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
SH01 Braeside Culvert Replacement |  |  | As per Specification Ref, Procedure Or Method Statement |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | Discription |  |  |  | W(5%) | Sub Supervisor
3.9.2 | Subgrade |  | Construction Foreman | minimum 5 blows per 100mm | Measurement/Every 2m inline with trench | Scala Penetrometer | Yes | H | Hold Point - Record scala measurement and advise PM if criteria not met
| Subgrade |  | Construction Foreman | minimum 5 blows per 100mm | Measurement/Every 2m inline with trench | Scala Penetrometer | Yes | H | Hold Point - Record scala measurement and advise PM if criteria not met
3.9.3 | Install Pipe |  | Construction Foreman | As per design drawings and/or NZTA F/2 Specification (if required or specified) | Visual/Each Pipe | NZS2566.2 & TNZ F2 | Yes | W | Record invert
3.9.4 | Embedment zone |  | Construction Foreman | Embedment material shall be AP20 or approved by the Engineer in writing | Visual/Every 5m inline with trench | NZS2566.2 & TNZ F2 | Yes | W | Compacted material recorded via clegg test
3.9.5 | Backfill and Compact |  | Site Engineer | - Backfill in 200mm layers of compacted material - Compaction testing one test every two layers as required - conductive signal strip to be laid at …mm cover | Visual/Every layer, every 5m inline with trench | NZS2566.2 & TNZ F2 | Yes | H | Hold Point - Compacted materiial recorded via clegg testing - tests must pass to continue with backfill
3.1 | Pipe Installation B-05
3.10.1 | Trench Excavation |  | Construction Foreman | - excavate to achieve required depth to invert as per drawings - Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe - Floor of trench to be even across width and length | Visual/Ongoing | NZS2566.2 & TNZ F2 | Yes | W
3.10.2 | Subgrade |  | Construction Foreman | minimum 5 blows per 100mm | Measurement/Every 2m inline with trench | Scala Penetrometer | Yes | H | Hold Point - Record scala measurement and advise PM if criteria not met
3.10.3 | Install Pipe |  | Construction Foreman | As per design drawings and/or NZTA F/2 Specification (if required or specified) | Visual/Each Pipe | NZS2566.2 & TNZ F2 | Yes | W | Record invert
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 17/05/2024 |  |  | DATE: 17/05/2024 |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH01 Braeside Culvert Replacement (SH01 Braeside RS 0720 RB/1.020) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
SH01 Braeside Culvert Replacement |  |  | As per Specification Ref, Procedure Or Method Statement |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | Discription |  |  |  | W(5%) | Sub Supervisor
3.10.4 | Embedment zone |  | Construction Foreman | Embedment material shall be AP20 or approved by the Engineer in writing | Visual/Every 5m inline with trench | NZS2566.2 & TNZ F2 | Yes | W | Compacted material recorded via clegg test
3.10.5 | Backfill and Compact |  | Site Engineer | - Backfill in 200mm layers of compacted material - Compaction testing one test every two layers as required - conductive signal strip to be laid at …mm cover | Visual/Every layer, every 5m inline with trench | NZS2566.2 & TNZ F2 | Yes | H | Hold Point - Compacted materiial recorded via clegg testing - tests must pass to continue with backfill
4 | Pavement (including sealed shoulder)
4.1 | Pavement Preliminary
4.1.1 | Production Properties Note: Running course to be produced from the same type and source of material as the basecourse. |  | Project Manager | TNZ M/4: Cl.4.2.3 | PSD Wet Sieving Test 1 - 400m3 – 2 tests 400 - 1500m3 - 3 tests 1500 - 4000m3 – 4 tests >4000m3 – 1 test per 1000m3 | TNZ M/4:2006 NZS 4407 :1991 Test 3.8.1 | Yes | H | Hold Point – All production and source testing results to be provided prior to placement of material on road
|  |  |  | Aggregate broken face content in each of the three aggregate fractions between 37.5mm and 4.75mm ≥ 70% by weight and has 2 or more broken faces | Broken Face Test 1 - 400m3 – 2 tests 400 - 1500m3 - 3 tests 1500 - 4000m3 – 4 tests >4000m3 – 1 test per 1000m3 | TNZ M/4: 2006 NZS 4407 :1991 Test 3.14
|  |  |  | Sand equivalent > 40 NB Downer Policy that only SE compliant basecourse allowed unless stabilised | Sand equivalent test 1 - 400m3 – 2 tests 400 - 1500m3 - 3 tests 1500 - 4000m3 – 4 tests >4000m3 – 1 test per 1000m3 | TNZ M/4: 2006 NZS 4407 :1991 Test 3.6
|  |  |  | PI ≤ 5 | Plasticity Index Test 1 - 400m3 – 2 tests 400 - 1500m3 - 3 tests 1500 - 4000m3 – 4 tests >4000m3 – 1 test per 1000m3 | TNZ M/4: 2006 NZS 4407:1991 Test 3.4
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 17/05/2024 |  |  | DATE: 17/05/2024 |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH01 Braeside Culvert Replacement (SH01 Braeside RS 0720 RB/1.020) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
SH01 Braeside Culvert Replacement |  |  | As per Specification Ref, Procedure Or Method Statement |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | Discription |  |  |  | W(5%) | Sub Supervisor
4.1.2 | B/02 Lab Testing |  | Project Manager | OWC as determined in the lab. | NZ vibrating hammer compaction test at OWC The lesser of: a) 1 test per stockpile or new seam b) 1 test every 5000m2 (in place) | NZS 4407:1991 Solid Density Test 3.7 TNZ B/2: 2005 | Yes | H | Hold Point – All lab testing results to be provided prior to placement of material on road
|  |  |  | When sampling stockpile for lab, take NDM for W/C offset. Record moisture content and take sample from beneath NDM to dry in the oven. (Two W/C readings and samples) | Solid density The lesser of: a) 1 test per stockpile or new seam b) 1 test every 5000m2 (in place) | NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005
|  |  |  | MDD as the higher of the two results from lab and field Ensure plateau test is done at OWC from Lab Value and with NDM moisture offset | MDD at OWC – in lab The lesser of: a) 1 test per stockpile or new seam b) 1 test every 5000m2 (in place) | NZS 4402: 1986 MDD and W/C Test 4.1.3 TNZ B/2: 2005
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 17/05/2024 |  |  | DATE: 17/05/2024 |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH01 Braeside Culvert Replacement (SH01 Braeside RS 0720 RB/1.020) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
SH01 Braeside Culvert Replacement |  |  | As per Specification Ref, Procedure Or Method Statement |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | Discription |  |  |  | W(5%) | Sub Supervisor
4.1.3 | Source Properties Note: Running course to be produced from the same type and source of material as the basecourse |  | Project Manager | Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve | TNZ M/4 Crushing Resistance Test 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | TNZ M/4: 2006 NZS 4407 :1991 Test 3.10 | Yes | H | Hold Point – All production and source testing results to be provided prior to placement of material on road for a source <2 years old
[5 empty] | TNZ M/4/NZ vibrating hammer compaction test at OMC/Determination of CBR. 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | NZS 4402: 1986 Test 4.13/NZS 4407: 1991 Test CBR 3.15/TNZ M/4: 2006
|  |  |  | Soaked CBR ≥ 80% when compacted/tested in accordance with both tests | Weathering quality index test 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | NZS 4407:1991 Test 3.11/TNZ M/4:2006
NZTA T15
|  |  |  | Must have quality index of AA, AB, AC, BA, BB or CA | NZTA T15 RLT strain test for rutting performance 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
T15 Specification
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 17/05/2024 |  |  | DATE: 17/05/2024 |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH01 Braeside Culvert Replacement (SH01 Braeside RS 0720 RB/1.020) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
SH01 Braeside Culvert Replacement |  |  | As per Specification Ref, Procedure Or Method Statement |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | Discription |  |  |  | W(5%) | Sub Supervisor
4.2 | Reinstatment
4.2.2 | Compaction |  | Project Manager | Basecourse : Average ≥ 98% MDD Minimum ≥ 95% MDD Subbase: Average ≥ 95% MDD Minimum ≥ 92% MDD Subgrade >1.5m depth Average Average ≥ 92% MDD Minimum ≥ 90% MDD | NDM – maximum dry density - Backscatter method 5 tests per homogeneous lot of up to 1000m2 of laid pavement | NZS 4407: 1991 Test 4.2.2. TNZ B/2: 2005 | Yes | H | Hold Point – no surfacing layer is to be applied until passing results are achieved (ie average & minimum MDD)
| Degree of Saturation (DOS) |  | Project Manager | DOS ≤ 80% from Solid Density and %W | DOS/5 tests per homogeneous lot of up to 1000m2 of laid pavement | NZS 4407: 1991 Test 4.2.2. TNZ B/2: 2005 | Yes | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 17/05/2024 |  |  | DATE: 17/05/2024 |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH01 Braeside Culvert Replacement (SH01 Braeside RS 0720 RB/1.020) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
SH01 Braeside Culvert Replacement |  |  | As per Specification Ref, Procedure Or Method Statement |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | Discription |  |  |  | W(5%) | Sub Supervisor
5 | Shoulders and Additional Surfacing Prep
5.1 | Slope |  | Project Manager | Slopes consistent with pavement surface | Visual check | Visual inspection with smart level | Yes | H | Hold Point – no surfacing layer is to be applied until all necessary results are achieved
5.2 | Compaction |  | Project Manager | Vehicles can drive on shoulders without significant indentation/soft surface | Visual check/All shoulders | Drive over 4T, check wheeltracks | Yes | H | Hold Point – no surfacing layer is to be applied until all necessary results are achieved
5.3 | Additional Surfacing Preparation - Side Roads - Accesses - Driveways - Dish Channels - High Shoulders |  | Project Manager | Have all areas of additional surfacing on the design been prepared and marked for sealing? | Visual check/Before/During Sealing | Per Design | Yes | H | Hold Point – All areas planned for sealing are prepared ready for surfacing layer
5.4 | Soiling |  | Construction Foreman | Soiling has been done where required | Visual check/All areas requiring grassing |  | Yes | W
5.5 | Grassing |  | Construction Foreman | Grassing has been done where required | Visual check/All areas requiring grassing |  | Yes | W
12 |  |  | XXX | [5 empty] | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 17/05/2024 |  |  | DATE: 17/05/2024 |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH01 Braeside Culvert Replacement (SH01 Braeside RS 0720 RB/1.020) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
SH01 Braeside Culvert Replacement |  |  | As per Specification Ref, Procedure Or Method Statement |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | Discription |  |  |  | W(5%) | Sub Supervisor
6 | Pavement Finishing and Surfacing
6.1 | Completed construction pavement surface, Pre-sealing walkover and checks |  | NZTA Engineers Rep | The large aggregate is held in place by a matrix of smaller aggregates The smaller aggregate is held firmly in place by fine material The matrix does not displace under normal trafficking or sweeping | Visual inspection/Overview of site for tight mosaic surface |  | Yes | H | Hold Point – no surfacing layer is to be applied until passing results are achieved
|  |  |  | All other necessary checks have been done & accepted | Visual check/Before sealing
|  |  |  | See Sealing ITP |  |  |  |  | Hold Point – All hold points and checks in ITP to be completed before physical works continue
6.2 | Pre-seal Area Check |  | NZTA Maintenance Contact Manager | Check prepared and marked area for sealing against design to check whether full area of design ready for surfacing | Measurement/Before Sealing | On Site tape-measure | Yes | H | Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
6.3 | Sealing TMP and aftercare process |  | Sealing Manager | See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site |  |  | Yes | W | Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
6.4 | Sweeping of Sealing works and handover to Roadmarkers |  | Sealing Manager | Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor. |  |  | Yes | H | 24 hour trafficking and aftercare of sealing works are described and confirmed in TMP for sealing works before physical sealing works proceed.
6.5 | Post-seal Area Check |  | NZTA Maintenance Contact Manager | Check sealed area meets design | Measurement/After Surfacing | On Site tape-measure | Yes | W | Raise non-conformance with Renewals Enginner or Renewals Manager
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 17/05/2024 |  |  | DATE: 17/05/2024 |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH01 Braeside Culvert Replacement (SH01 Braeside RS 0720 RB/1.020) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
SH01 Braeside Culvert Replacement |  |  | As per Specification Ref, Procedure Or Method Statement |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | Discription |  |  |  | W(5%) | Sub Supervisor
7 | Improvements
7.1 | Improvements - Guardrail - Signage - Footpath |  | Project Manager | Replaced in same position, height etc | Visual inspection/All Signs & Markers | TNZ C/20: 2003 | Yes | H | Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
8 | Site Reinstatement / Clearance
8.1 | Road Marking |  | Project Manager | Replaced in same position, or per design | Visual inspection/All Markings | MOTSAM | Yes | H | Hold point – Site TTM cannot be removed until markings reinstated
8.2 | Traffic Services | Marker pegs/ Signs/Markings/RRPMs Replaced | Construction Foreman | Replaced in same position, height etc | Visual inspection/All Signs & Markers | TNZ C/20: 2003 | Yes | H | Hold point – Site TTM cannot be removed until marker pegs, signs, markings and RRPMs reinstated
8.3 | Drains cleared |  | Construction Foreman | Drains are cleared and culvert ends and side (accessway) culverts installed or reinstated |  | Visual check | Yes | W
8.4 | Envirnomental Controls Removed |  | Construction Foreman | Any silt fences or other controls are removed |  | Visual check | Yes | W
8.5 | Traffic Management Removed |  | Construction Foreman | All traffic management removed from site safely |  | Visual check | Yes | W
8.6 | Site left clean & tidy |  | Construction Foreman | Stockpiles removed Plant removed Litter cleared from site |  | Visual check | Yes | W
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 17/05/2024 |  |  | DATE: 17/05/2024 |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH01 Braeside Culvert Replacement (SH01 Braeside RS 0720 RB/1.020) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
SH01 Braeside Culvert Replacement |  |  | As per Specification Ref, Procedure Or Method Statement |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | Discription |  |  |  | W(5%) | Sub Supervisor
9 | As Built Records
9.1 | Collect asset data |  | Renewals Engineer | All relevant as built information collected. | During construction | SHDOM (SM050) | Yes | W
9.2 | Enter asset data into RAMM and/or register(s) |  | Asset Information Manager | All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file. | RAMM/At completion of work. | SHDOM (SM050) | Yes | W | Data entered by 20th of follow month after month of completion
9.3 | CCTV |  | Project Manager | Video survelance recorded into database. Audit completed and scoring preformed on video | Recorded Video/Upon Completion | CCTV Audit | Yes | W
9.4 | Construction Completion Report |  | Project Manager/ Renewals Manager | Checked and approved | Confirmation/At completion of work. | Contract Specification | Yes | W | Completed within two months after first coat surfacing
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 17/05/2024 |  |  | DATE: 17/05/2024 |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client