## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - CONOC Construction (SH01 Braeside Culvert Replacement) - SH01 Braeside RS 0720 RB/1.020 | itp |  |  |  |  | ITP - CONOC Construction (SH01 Braeside Culvert Replacement) - SH01 Braeside RS 0720 RB/1.020
section | 1 - Preliminary and General
checkpoint | 1.1 - Construction Programme Completion
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date.
label | Frequency Of Inspection Or Test - Confirmation/Before work commences
label | Spec. Ref, Procedure Or Method Statement - Best Practice Contract Specific MMP
label | Records Required - YES
label | DOWNER ENGINEER - W
checkpoint | 1.2 - Approved RQP
label | Controlled By : (Position) - NZTA Maintenance Contact Manager
label | Accept / Reject Criteria - Principal Acceptance according to guidelines in appendix 6.3
label | Frequency Of Inspection Or Test - Confirmation/Before work commences
label | Spec. Ref, Procedure Or Method Statement - Contract Specification
label | Records Required - YES
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Traffic Management (TMP)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - TMP checked and approved, Plans approved, Current EED (if applicable)
label | Frequency Of Inspection Or Test - Visual Check/Before traffic management set up
label | Spec. Ref, Procedure Or Method Statement - CoPTTM
label | Records Required - YES
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold point - No traffic management is to be set up until TMP has been checked and approved
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Notification of intention to start work
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Letter drop to local residents. Where required and defined by SWAMP, VMS, social media/media advertising
label | Frequency Of Inspection Or Test - Notification/Before work commences
label | Records Required - YES
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Set-Out/Site Preparation
checkpoint | 2.1 - Setout
label | Controlled By : (Position) - Project Manager
label | Frequency Of Inspection Or Test - Survey/Pre-Installation
label | Spec. Ref, Procedure Or Method Statement - Best Practice
label | Records Required - YES
label | DOWNER ENGINEER - W
checkpoint | 2.2 - Permit to dig/Authority to Work/close approach permits
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Organisational approval
label | Frequency Of Inspection Or Test - Permit Approved/Before work commences
label | Spec. Ref, Procedure Or Method Statement - Downer Permit to work or Equvilent
label | Records Required - YES
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold point - No excavation is to be commenced until approvals are gained
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Cultural/Heritage Risk Assessment
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Local iwi has been notified of intent to start work
label | Frequency Of Inspection Or Test - Notification/Before work commences
label | Spec. Ref, Procedure Or Method Statement - WK Cultural & Heritage Risk Model
label | Records Required - YES
label | DOWNER ENGINEER - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Archaeological Risk
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Toolbox meeting held covering accidental discovery protocol
label | Frequency Of Inspection Or Test - Toolbox meeting/Before work commences
label | Spec. Ref, Procedure Or Method Statement - WK Cultural & Heritage Risk Model
label | Records Required - YES
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold point - No excavation is to be commenced until toolbox meeting is held
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Traffic Management Setup
label | Controlled By : (Position) - Construction Foreman / STMS
label | Accept / Reject Criteria - Traffic management complies with TMP
label | Frequency Of Inspection Or Test - Visual Check/Before work commences each day
label | Spec. Ref, Procedure Or Method Statement - Traffic Management Plan
label | Records Required - YES
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold point - No physical works are to be commenced until necessary traffic management is in place
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Site Setout
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Verification of survey control points and setup
label | Frequency Of Inspection Or Test - Measurement/Before Excavation
label | Spec. Ref, Procedure Or Method Statement - On Site
label | Records Required - YES
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold point - Survey set-up accuracy to be verified with aid of surveyor or specialist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Prepare String Sheet (Digital)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Digital design set-out data is consistent with existing formation
label | Frequency Of Inspection Or Test - Measurement/Before using machine control
label | Spec. Ref, Procedure Or Method Statement - On Site
label | Records Required - YES
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold point - Design accuracy to be verified prior to undertaking work
holdpoint | AUTHORITY HOLDPOINT
section | 3.1 - Earthwork and Stripping
checkpoint | 3.1.1 - Cut/Excavation
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Meets design drawings of cross-sectional extent
label | Frequency Of Inspection Or Test - Measurement/Tape measure from set-out or existing CL, as per design
label | Spec. Ref, Procedure Or Method Statement - On Site
label | Records Required - YES
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold point - Excavation width needs to be checked against the design cross-sections to ensure correctness
holdpoint | AUTHORITY HOLDPOINT
section | 3.2 - Drainage Structures
checkpoint | 3.2.1 - HW B-01
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Survey setout location, measure invert depth, As per design drawings and/or NZTA F/2 Specification (if required or specified)
label | Frequency Of Inspection Or Test - Meaasurement/During construction
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - YES
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold point - Design accuracy to be verified prior to undertaking work
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.2 - HW B-02
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Survey setout location, measure invert depth, As per design drawings and/or NZTA F/2 Specification (if required or specified)
label | Frequency Of Inspection Or Test - Meaasurement/During construction
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - YES
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold point - Design accuracy to be verified prior to undertaking work
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.3 - HW B-03
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Survey setout location, measure invert depth, As per design drawings and/or NZTA F/2 Specification (if required or specified)
label | Frequency Of Inspection Or Test - Meaasurement/During construction
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - YES
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold point - Design accuracy to be verified prior to undertaking work
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.4 - HW B-07
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Survey setout location, measure invert depth, As per design drawings and/or NZTA F/2 Specification (if required or specified)
label | Frequency Of Inspection Or Test - Meaasurement/During construction
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - YES
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold point - Design accuracy to be verified prior to undertaking work
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.5 - MH B-04
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Survey setout location, measure invert depth, As per design drawings and/or NZTA F/2 Specification (if required or specified) Cobel/starters set and constructed as per regional/NZTA standards
label | Frequency Of Inspection Or Test - Meaasurement/During construction
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - YES
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold point - Design accuracy to be verified prior to undertaking work
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.6 - MH B-05
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Survey setout location, measure invert depth, As per design drawings and/or NZTA F/2 Specification (if required or specified) Cobel/starters set and constructed as per regional/NZTA standards
label | Frequency Of Inspection Or Test - Meaasurement/During construction
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - YES
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold point - Design accuracy to be verified prior to undertaking work
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.7 - MH B-06
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Survey setout location, measure invert depth, As per design drawings and/or NZTA F/2 Specification (if required or specified) Cobel/starters set and constructed as per regional/NZTA standards
label | Frequency Of Inspection Or Test - Meaasurement/During construction
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - YES
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold point - Design accuracy to be verified prior to undertaking work
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.8 - Other Structures
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Constructed to design drawings and relevant standards
label | Frequency Of Inspection Or Test - Visual Check/Continuous
label | Records Required - YES
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point – Visual check prior to pavement construction
holdpoint | AUTHORITY HOLDPOINT
section | 3.3 - Ancillary Works
checkpoint | 3.3.1 - Ancillary Items as per design
label | Example:
label | – Rock Benching
label | – Signage
label | – Vegetation/Trees
label | – Kerb and Channel
label | – Underground Services
label | – Service Covers
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Constructed to design drawings and relevant standards
label | Frequency Of Inspection Or Test - Visual Check/Once
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point – Visual check prior to pavement construction
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.2 - Rock aprons
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - As per drawing details or as directed by the Engineer
label | Frequency Of Inspection Or Test - Visual Check/During Construction
label | Records Required - Yes
label | DOWNER ENGINEER - W
section | 3.4 - Subsoil Drainge
checkpoint | 3.4.1 - Subsoil Drain Construction
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - As per design drawings and/or NZTA F/2 Specification (if required or specified)
label | Frequency Of Inspection Or Test - Visual/Each Site
label | Records Required - Yes
label | DOWNER ENGINEER - W
label | DESCRIPTION - Hold Point – Visual check prior to pipe placement
checkpoint | 3.4.2 - Inlets/Outlets
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Connect to sump/catchpit, Concrete Apron, Open Channel, Inspection Eyes.
label | Frequency Of Inspection Or Test - Visual
label | Records Required - Yes
label | DOWNER ENGINEER - W
label | DESCRIPTION - Hold Point – Visual check prior to reinstatement
section | 3.5 - Pipe Installation B-01
checkpoint | 3.5.1 - Trench Excavation
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Excavate to achieve required depth to invert as per drawings
label | ○ Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe
label | ○ Floor of trench to be even across width and length
label | Frequency Of Inspection Or Test - Visual/Ongoing
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - Yes
label | DOWNER ENGINEER - W
checkpoint | 3.5.2 - Subgrade
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - minimum 5 blows per 100mm
label | Frequency Of Inspection Or Test - measurement/every 2m inline with trench
label | Spec. Ref, Procedure Or Method Statement - Scala Penetrometer
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point - Record scala measurement and adivse PM if criteria not met
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5.3 - Install Pipe
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - As per design drawings and/or NZTA F/2 Specification (if required or specified)
label | Frequency Of Inspection Or Test - Visual/Each Pipe
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - Yes
label | DOWNER ENGINEER - W
label | DESCRIPTION - Record invert
checkpoint | 3.5.4 - Embedment Zone
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Embedment material shall be AP20 or approved by the Engineer in writing
label | Frequency Of Inspection Or Test - Visual/every 5m inline with trench
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - Yes
label | DOWNER ENGINEER - W
label | DESCRIPTION - Compacted material recorded via clegg test
checkpoint | 3.5.5 - Backfill and Compact
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Backfill in 200mm layers of compacted material
label | ○ Compaction testing one test every two layers as required
textbox | ○ Conductive signal strip to be laid at |  |  | mm cover
label | Frequency Of Inspection Or Test - Visual/Every layer, every 5m inline with trench
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point - Compacted material recorded via clegg testing - tests must pass to continue with backfill
holdpoint | AUTHORITY HOLDPOINT
section | 3.6 - Pipe Installation B-02
checkpoint | 3.6.1 - Trench Excavation
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Excavate to achieve required depth to invert as per drawings
label | ○ Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe
label | ○ Floor of trench to be even across width and length
label | Frequency Of Inspection Or Test - Visual/Ongoing
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - Yes
label | DOWNER ENGINEER - W
checkpoint | 3.6.2 - Subgrade
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - minimum 5 blows per 100mm
label | Frequency Of Inspection Or Test - Measurement/Every 2m inline with trench
label | Spec. Ref, Procedure Or Method Statement - Scala Penetrometer
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point - Record scala measurement and advise PM if criteria not met
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6.3 - Install Pipe
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - As per design drawings and/or NZTA F/2 Specification (if required or specified)
label | Frequency Of Inspection Or Test - Visual/Each Pipe
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - Yes
label | DOWNER ENGINEER - W
label | DESCRIPTION - Record invert
checkpoint | 3.6.4 - Embedment zone
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Embedment material shall be AP20 or approved by the Engineer in writing
label | Frequency Of Inspection Or Test - Visual/Every 5m inline with trench
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - Yes
label | DOWNER ENGINEER - W
label | DESCRIPTION - Compacted material recorded via clegg test
checkpoint | 3.6.5 - Backfill and Compact
label | Controlled By : (Position) - Site Engineer
label | Accept / Reject Criteria - Backfill in 200mm layers of compacted material
label | ○ Compaction testing one test every two layers as required
textbox | ○ Conductive signal strip to be laid at |  |  | mm cover
label | Frequency Of Inspection Or Test - Visual/Every layer, every 5m inline with trench
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point - Compacted material recorded via clegg testing - tests must pass to continue with backfill
holdpoint | AUTHORITY HOLDPOINT
section | 3.7 - Pipe Installation B-03 North Lane
checkpoint | 3.7.1 - Trench Excavation
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Excavate to achieve required depth to invert as per drawings
label | ○ Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe
label | ○ Floor of trench to be even across width and length
label | Frequency Of Inspection Or Test - Visual/Ongoing
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - Yes
label | DOWNER ENGINEER - W
checkpoint | 3.7.2 - Subgrade
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - minimum 5 blows per 100mm
label | Frequency Of Inspection Or Test - Measurement/Every 2m inline with trench
label | Spec. Ref, Procedure Or Method Statement - Scala Penetrometer
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point - Record scala measurement and advise PM if criteria not met
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7.3 - Install Pipe
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - As per design drawings and/or NZTA F/2 Specification (if required or specified)
label | Frequency Of Inspection Or Test - Visual/Each Pipe
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - Yes
label | DOWNER ENGINEER - W
label | DESCRIPTION - Record invert
checkpoint | 3.7.4 - Embedment zone
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Embedment material shall be AP20 or approved by the Engineer in writing
label | Frequency Of Inspection Or Test - Visual/Every 5m inline with trench
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - Yes
label | DOWNER ENGINEER - W
label | DESCRIPTION - Compacted material recorded via clegg test
checkpoint | 3.7.5 - Backfill and Compact
label | Controlled By : (Position) - Site Engineer
label | Accept / Reject Criteria - Backfill in 200mm layers of compacted material
label | ○ Compaction testing one test every two layers as required
textbox | ○ Conductive signal strip to be laid at |  |  | mm cover
label | Frequency Of Inspection Or Test - Visual/Every layer, every 5m inline with trench
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point - Compacted material recorded via clegg testing - tests must pass to continue with backfill
holdpoint | AUTHORITY HOLDPOINT
section | 3.8 - Pipe Installation B-03 South Lane
checkpoint | 3.8.1 - Trench Excavation
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Excavate to achieve required depth to invert as per drawings
label | ○ Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe
label | ○ Floor of trench to be even across width and length
label | Frequency Of Inspection Or Test - Visual/Ongoing
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - Yes
label | DOWNER ENGINEER - W
checkpoint | 3.8.2 - Subgrade
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - minimum 5 blows per 100mm
label | Frequency Of Inspection Or Test - Measurement/Every 2m inline with trench
label | Spec. Ref, Procedure Or Method Statement - Scala Penetrometer
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point - Record scala measurement and advise PM if criteria not met
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8.3 - Install Pipe
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - As per design drawings and/or NZTA F/2 Specification (if required or specified)
label | Frequency Of Inspection Or Test - Visual/Each Pipe
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - Yes
label | DOWNER ENGINEER - W
label | DESCRIPTION - Record invert
checkpoint | 3.8.4 - Embedment zone
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Embedment material shall be AP20 or approved by the Engineer in writing
label | Frequency Of Inspection Or Test - Visual/Every 5m inline with trench
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - Yes
label | DOWNER ENGINEER - W
label | DESCRIPTION - Compacted material recorded via clegg test
checkpoint | 3.8.5 - Backfill and Compact
label | Controlled By : (Position) - Site Engineer
label | Accept / Reject Criteria - Backfill in 200mm layers of compacted material
label | ○ Compaction testing one test every two layers as required
textbox | ○ Conductive signal strip to be laid at |  |  | mm cover
label | Frequency Of Inspection Or Test - Visual/Every layer, every 5m inline with trench
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point - Compacted material recorded via clegg testing - tests must pass to continue with backfill
holdpoint | AUTHORITY HOLDPOINT
section | 3.9 - Pipe Installation B-04
checkpoint | 3.9.1 - Trench Excavation
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Excavate to achieve required depth to invert as per drawings
label | ○ Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe
label | ○ Floor of trench to be even across width and length
label | Frequency Of Inspection Or Test - Visual/Ongoing
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - Yes
label | DOWNER ENGINEER - W
checkpoint | 3.9.2 - Subgrade
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - minimum 5 blows per 100mm
label | Frequency Of Inspection Or Test - Measurement/Every 2m inline with trench
label | Spec. Ref, Procedure Or Method Statement - Scala Penetrometer
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point - Record scala measurement and advise PM if criteria not met
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9.2 - Subgrade
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - minimum 5 blows per 100mm
label | Frequency Of Inspection Or Test - Measurement/Every 2m inline with trench
label | Spec. Ref, Procedure Or Method Statement - Scala Penetrometer
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point - Record scala measurement and advise PM if criteria not met
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9.3 - Install Pipe
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - As per design drawings and/or NZTA F/2 Specification (if required or specified)
label | Frequency Of Inspection Or Test - Visual/Each Pipe
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - Yes
label | DOWNER ENGINEER - W
label | DESCRIPTION - Record invert
checkpoint | 3.9.4 - Embedment zone
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Embedment material shall be AP20 or approved by the Engineer in writing
label | Frequency Of Inspection Or Test - Visual/Every 5m inline with trench
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - Yes
label | DOWNER ENGINEER - W
label | DESCRIPTION - Compacted material recorded via clegg test
checkpoint | 3.9.5 - Backfill and Compact
label | Controlled By : (Position) - Site Engineer
label | Accept / Reject Criteria - Backfill in 200mm layers of compacted material
label | ○ Compaction testing one test every two layers as required
textbox | ○ Conductive signal strip to be laid at |  |  | mm cover
label | Frequency Of Inspection Or Test - Visual/Every layer, every 5m inline with trench
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point - Compacted material recorded via clegg testing - tests must pass to continue with backfill
holdpoint | AUTHORITY HOLDPOINT
section | 3.10 - Pipe Installation B-05
checkpoint | 3.10.1 - Trench Excavation
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Excavate to achieve required depth to invert as per drawings
label | ○ Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe
label | ○ Floor of trench to be even across width and length
label | Frequency Of Inspection Or Test - Visual/Ongoing
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - Yes
label | DOWNER ENGINEER - W
checkpoint | 3.10.2 - Subgrade
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - minimum 5 blows per 100mm
label | Frequency Of Inspection Or Test - Measurement/Every 2m inline with trench
label | Spec. Ref, Procedure Or Method Statement - Scala Penetrometer
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point - Record scala measurement and advise PM if criteria not met
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.10.3 - Install Pipe
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - As per design drawings and/or NZTA F/2 Specification (if required or specified)
label | Frequency Of Inspection Or Test - Visual/Each Pipe
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - Yes
label | DOWNER ENGINEER - W
label | DESCRIPTION - Record invert
checkpoint | 3.10.4 - Embedment zone
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Embedment material shall be AP20 or approved by the Engineer in writing
label | Frequency Of Inspection Or Test - Visual/Every 5m inline with trench
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - Yes
label | DOWNER ENGINEER - W
label | DESCRIPTION - Compacted material recorded via clegg test
checkpoint | 3.10.5 - Backfill and Compact
label | Controlled By : (Position) - Site Engineer
label | Accept / Reject Criteria - Backfill in 200mm layers of compacted material
label | ○ Compaction testing one test every two layers as required
textbox | ○ Conductive signal strip to be laid at |  |  | mm cover
label | Frequency Of Inspection Or Test - Visual/Every layer, every 5m inline with trench
label | Spec. Ref, Procedure Or Method Statement - NZS2566.2 & TNZ F2
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point - Compacted material recorded via clegg testing - tests must pass to continue with backfill
holdpoint | AUTHORITY HOLDPOINT
section | 4.1 - Pavement Preliminary
checkpoint | 4.1.1 - Production Properties - Note: Running course to be produced from the same type and source of material as the basecourse. (1)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - TNZ M/4: Cl.4.2.3
label | Frequency Of Inspection Or Test - PSD Wet Sieving Test
label | ○ 1 - 400m3 – 2 tests
label | ○ 400 - 1500m3 - 3 tests
label | ○ 1500 - 4000m3 – 4 tests
label | ○ >4000m3 – 1 test per 1000m3
label | Spec. Ref, Procedure Or Method Statement - TNZ M/4:2006, NZS 4407 :1991 Test 3.8.1
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point – All production and source testing results to be provided prior to placement of material on road
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.1 - Production Properties - Note: Running course to be produced from the same type and source of material as the basecourse. (2)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Aggregate broken face content in each of the three aggregate fractions between 37.5mm and 4.75mm ≥ 70% by weight and has 2 or more broken faces
label | Frequency Of Inspection Or Test - Broken Face Test
label | ○ 1 - 400m3 – 2 tests
label | ○ 400 - 1500m3 - 3 tests
label | ○ 1500 - 4000m3 – 4 tests
label | ○ >4000m3 – 1 test per 1000m3
label | Spec. Ref, Procedure Or Method Statement - TNZ M/4: 2006, NZS 4407 :1991 Test 3.14
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point – All production and source testing results to be provided prior to placement of material on road
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.1 - Production Properties - Note: Running course to be produced from the same type and source of material as the basecourse. (3)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Sand equivalent > 40, NB Downer Policy that only SE compliant basecourse allowed unless stabilised
label | Frequency Of Inspection Or Test - Sand equivalent test 1
label | ○ 400m3 – 2 tests
label | ○ 400 - 1500m3 - 3 tests
label | ○ 1500 - 4000m3 – 4 tests
label | ○ >4000m3 – 1 test per 1000m3
label | Spec. Ref, Procedure Or Method Statement - TNZ M/4: 2006, NZS 4407 :1991 Test 3.6
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point – All production and source testing results to be provided prior to placement of material on road
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.1 - Production Properties - Note: Running course to be produced from the same type and source of material as the basecourse. (4)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - PI ≤ 5
label | Frequency Of Inspection Or Test - Plasticity Index Test
label | ○ 1 - 400m3 – 2 tests
label | ○ 400 - 1500m3 - 3 tests
label | ○ 1500 - 4000m3 – 4 tests
label | ○ >4000m3 – 1 test per 1000m3
label | Spec. Ref, Procedure Or Method Statement - TNZ M/4: 2006, NZS 4407:1991 Test 3.4
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point – All production and source testing results to be provided prior to placement of material on road
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.2 - B/02 Lab Testing (1)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - OWC as determined in the lab.
label | Frequency Of Inspection Or Test - NZ vibrating hammer compaction test at OWC The lesser of:
label | a) 1 test per stockpile or new seam
label | b) 1 test every 5000m2 (in place)
label | Spec. Ref, Procedure Or Method Statement - NZS 4407:1991 Solid Density Test 3.7 TNZ B/2: 2005
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point – All lab testing results to be provided prior to placement of material on road
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.2 - B/02 Lab Testing (2)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - When sampling stockpile for lab, take NDM for W/C offset. Record moisture content and take sample from beneath NDM to dry in the oven. (Two W/C readings and samples)
label | Frequency Of Inspection Or Test - Solid density
label | The lesser of:
label | a) 1 test per stockpile or new seam
label | b) 1 test every 5000m2 (in place)
label | Spec. Ref, Procedure Or Method Statement - NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point – All lab testing results to be provided prior to placement of material on road
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.2 - B/02 Lab Testing (3)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - MDD as the higher of the two results from lab and field
label | ○ Ensure plateau test is done at OWC from Lab Value and with NDM moisture offset
label | Frequency Of Inspection Or Test - MDD at OWC – in lab
label | The lesser of:
label | a) 1 test per stockpile or new seam
label | b) 1 test every 5000m2 (in place)
label | Spec. Ref, Procedure Or Method Statement - NZS 4402: 1986 MDD and W/C Test 4.1.3 TNZ B/2: 2005
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point – All lab testing results to be provided prior to placement of material on road
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.3 - Source Properties - Note: Running course to be produced from the same type and source of material as the basecourse (1)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve
label | Frequency Of Inspection Or Test - TNZ M/4 Crushing Resistance Test
label | ○ 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | Spec. Ref, Procedure Or Method Statement - TNZ M/4: 2006, NZS 4407 :1991 Test 3.10
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source CHAR(LESS)2 years old
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.3 - Source Properties - Note: Running course to be produced from the same type and source of material as the basecourse (2)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve
label | Frequency Of Inspection Or Test - TNZ M/4/NZ vibrating hammer compaction test at OMC/Determination of CBR. 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | Spec. Ref, Procedure Or Method Statement - NZS 4402: 1986 Test 4.13/NZS 4407: 1991 Test CBR 3.15/TNZ M/4: 2006
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source CHAR(LESS)2 years old
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.3 - Source Properties - Note: Running course to be produced from the same type and source of material as the basecourse (3)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Soaked CBR ≥ 80% when compacted/tested in accordance with both tests
label | Frequency Of Inspection Or Test - Weathering quality index test
label | ○ 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | Spec. Ref, Procedure Or Method Statement - NZS 4407:1991, Test 3.11/TNZ M/4:2006
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source CHAR(LESS)2 years old
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.3 - Source Properties - Note: Running course to be produced from the same type and source of material as the basecourse (4)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Must have quality index of AA, AB, AC, BA, BB or CA
label | Frequency Of Inspection Or Test - NZTA T15 RLT strain test for rutting performance
label | ○ 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | Spec. Ref, Procedure Or Method Statement - NZTA T15
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source CHAR(LESS)2 years old
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.3 - Source Properties - Note: Running course to be produced from the same type and source of material as the basecourse (5)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - T15 Specification
label | Frequency Of Inspection Or Test - NZTA T15 RLT strain test for rutting performance
label | ○ 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | Spec. Ref, Procedure Or Method Statement - NZTA T15
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source CHAR(LESS)2 years old
holdpoint | AUTHORITY HOLDPOINT
section | 4.2 - Reinstatement
checkpoint | 4.2.2 - Compaction
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Basecourse:
label | ○ Average ≥ 98% MDD
label | ○ Minimum ≥ 95% MDD
label | Subbase:
label | ○ Average ≥ 95% MDD
label | ○ Minimum ≥ 92% MDD Subgrade >1.5m depth Average
label | ○ Average ≥ 92% MDD
label | ○ Minimum ≥ 90% MDD
label | Frequency Of Inspection Or Test - NDM – maximum dry density - Backscatter method, 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | Spec. Ref, Procedure Or Method Statement - NZS 4407: 1991 Test 4.2.2. TNZ B/2: 2005
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved (ie average & minimum MDD)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.2 - Degree of Saturation (DOS)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - DOS ≤ 80% from Solid Density and %W
label | Frequency Of Inspection Or Test - DOS/5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | Spec. Ref, Procedure Or Method Statement - NZS 4407: 1991 Test 4.2.2. TNZ B/2: 2005
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved (ie average & minimum MDD)
holdpoint | AUTHORITY HOLDPOINT
section | 5 - Shoulders and Additional Surfacing Prep
checkpoint | 5.1 - Slope
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Slopes consistent with pavement surface
label | Frequency Of Inspection Or Test - Visual check
label | Spec. Ref, Procedure Or Method Statement - Visual inspection with smart level
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point – no surfacing layer is to be applied until all necessary results are achieved
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Compaction
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Vehicles can drive on shoulders without significant indentation/soft surface
label | Frequency Of Inspection Or Test - Visual check/All shoulders
label | Spec. Ref, Procedure Or Method Statement - Drive over 4T, check wheeltracks
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point – no surfacing layer is to be applied until all necessary results are achieved
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Additional Surfacing Preparation (Side Roads, Accesses, Driveways, Dish Channels, High Shoulders)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Have all areas of additional surfacing on the design been prepared and marked for sealing?
label | Frequency Of Inspection Or Test - Visual check/Before/During Sealing
label | Spec. Ref, Procedure Or Method Statement - Per Design
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point – All areas planned for sealing are prepared ready for surfacing layer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 - Soiling
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Soiling has been done where required
label | Frequency Of Inspection Or Test - Visual check/All areas requiring grassing
label | Records Required - Yes
label | DOWNER ENGINEER - W
checkpoint | 5.5 - Grassing
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Grassing has been done where required
label | Frequency Of Inspection Or Test - Visual check/All areas requiring grassing
label | Records Required - Yes
label | DOWNER ENGINEER - W
section | 6 - Pavement Finishing and Surfacing
checkpoint | 6.1 - Completed construction pavement surface, Pre-sealing walkover and checks
label | Controlled By : (Position) - NZTA Engineers Rep
label | Accept / Reject Criteria - The large aggregate is held in place by a matrix of smaller aggregates
label | ○ The smaller aggregate is held firmly in place by fine material
label | ○ The matrix does not displace under normal trafficking or sweeping
label | Frequency Of Inspection Or Test - Visual inspection/Overview of site for tight mosaic surface
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.1 - Completed construction pavement surface, Pre-sealing walkover and checks
label | Controlled By : (Position) - NZTA Engineers Rep
label | Accept / Reject Criteria - All other necessary checks have been done & accepted
label | Frequency Of Inspection Or Test - Visual check/Before sealing
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.1 - Completed construction pavement surface, Pre-sealing walkover and checks
label | Controlled By : (Position) - NZTA Engineers Rep
label | Accept / Reject Criteria - See Sealing ITP
label | Frequency Of Inspection Or Test - See Sealing ITP
label | Spec. Ref, Procedure Or Method Statement - See Sealing ITP
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold Point – All hold points and checks in ITP to be completed before physical works continue
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2 - Pre-seal Area Check
label | Controlled By : (Position) - NZTA Maintenance Contact Manager
label | Accept / Reject Criteria - Check prepared and marked area for sealing against design to check whether full area of design ready for surfacing
label | Frequency Of Inspection Or Test - Measurement/Before Sealing
label | Spec. Ref, Procedure Or Method Statement - On Site tape-measure
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.3 - Sealing TMP and aftercare process
label | Controlled By : (Position) - Sealing Manager
label | Accept / Reject Criteria - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | Frequency Of Inspection Or Test - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | Spec. Ref, Procedure Or Method Statement - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | Records Required - Yes
label | DOWNER ENGINEER - W
label | DESCRIPTION - Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
checkpoint | 6.4 - Sweeping of Sealing works and handover to Roadmarkers
label | Controlled By : (Position) - Sealing Manager
label | Accept / Reject Criteria - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | Frequency Of Inspection Or Test - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | Spec. Ref, Procedure Or Method Statement - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - 24 hour trafficking and aftercare of sealing works are described and confirmed in TMP for sealing works before physical sealing works proceed.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.5 - Post-seal Area Check
label | Controlled By : (Position) - NZTA Maintenance Contact Manager
label | Accept / Reject Criteria - Check sealed area meets design
label | Frequency Of Inspection Or Test - Measurement/After Surfacing
label | Spec. Ref, Procedure Or Method Statement - On Site tape-measure
label | Records Required - Yes
label | DOWNER ENGINEER - W
label | DESCRIPTION - Raise non-conformance with Renewals Enginner or Renewals Manager
section | 7 - Improvements
checkpoint | 7.1 - Improvements (Guardrail, Signage, Footpath)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Replaced in same position, height etc
label | Frequency Of Inspection Or Test - Visual inspection/All Signs & Markers
label | Spec. Ref, Procedure Or Method Statement - TNZ C/20: 2003
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
holdpoint | AUTHORITY HOLDPOINT
section | 8 - Site Reinstatement / Clearance
checkpoint | 8.1 - Road Marking
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Replaced in same position, or per design
label | Frequency Of Inspection Or Test - Visual inspection/All Markings
label | Spec. Ref, Procedure Or Method Statement - MOTSAM
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold point – Site TTM cannot be removed until markings reinstated
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.2 - Traffic Services Marker pegs/ Signs/Markings/RRPMs Replaced
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Replaced in same position, height etc
label | Frequency Of Inspection Or Test - Visual inspection/All Signs & Markers
label | Spec. Ref, Procedure Or Method Statement - TNZ C/20: 2003
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | DESCRIPTION - Hold point – Site TTM cannot be removed until marker pegs, signs, markings and RRPMs reinstated
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.3 - Drains cleared
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Drains are cleared and culvert ends and side (accessway) culverts installed or reinstated
label | Spec. Ref, Procedure Or Method Statement - Visual check
label | Records Required - Yes
label | DOWNER ENGINEER - W
checkpoint | 8.4 - Envirnomental Controls Removed
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Any silt fences or other controls are removed
label | Spec. Ref, Procedure Or Method Statement - Visual check
label | Records Required - Yes
label | DOWNER ENGINEER - W
checkpoint | 8.5 - Traffic Management Removed
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - All traffic management removed from site safely
label | Spec. Ref, Procedure Or Method Statement - Visual check
label | Records Required - Yes
label | DOWNER ENGINEER - W
checkpoint | 8.6 - Site left clean & tidy
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Stockpiles removed, Plant removed, Litter cleared from site
label | Spec. Ref, Procedure Or Method Statement - Visual check
label | Records Required - Yes
label | DOWNER ENGINEER - W
section | 9 - As Built Records
checkpoint | 9.1 - Collect asset data
label | Controlled By : (Position) - Renewals Engineer
label | Accept / Reject Criteria - All relevant as built information collected.
label | Frequency Of Inspection Or Test - During construction
label | Spec. Ref, Procedure Or Method Statement - SHDOM (SM050)
label | Records Required - Yes
label | DOWNER ENGINEER - W
checkpoint | 9.2 - Enter asset data into RAMM and/or register(s)
label | Controlled By : (Position) - Asset Information Manager
label | Accept / Reject Criteria - All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.
label | Frequency Of Inspection Or Test - RAMM/At completion of work.
label | Spec. Ref, Procedure Or Method Statement - SHDOM (SM050)
label | Records Required - Yes
label | DOWNER ENGINEER - W
label | DESCRIPTION - Data entered by 20th of follow month after month of completion
checkpoint | 9.3 - CCTV
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Video survelance recorded into database. Audit completed and scoring preformed on video
label | Frequency Of Inspection Or Test - Recorded Video/Upon Completion
label | Spec. Ref, Procedure Or Method Statement - CCTV Audit
label | Records Required - Yes
label | DOWNER ENGINEER - W
checkpoint | 9.4 - Construction Completion Report
label | Controlled By : (Position) - Project Manager/ Renewals Manager
label | Accept / Reject Criteria - Checked and approved
label | Frequency Of Inspection Or Test - Confirmation/At completion of work.
label | Spec. Ref, Procedure Or Method Statement - Contract Specification
label | Records Required - Yes
label | DOWNER ENGINEER - W
label | DESCRIPTION - Completed within two months after first coat surfacing