## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 3d74aca7-9982-41b5-af05-64628c0c022f |  | checklist | GIB Lining |  |  |  |  | Yes | GIB Lining | 09c5b30a-1d41-40ec-8951-c6cf4888d147
checkpoint-status | 2b82be1e-a147-4847-b765-c7c3763943cb |  | checkpoint | Installer details entered
text | 60e19cfd-c818-5ba6-9681-96548b8a7ceb |  | textbox | Installer:
checkpoint-status | 6d5e1cf1-2418-40a0-8b29-f2adf8cf7e3d |  | checkpoint | All relevant drawings and revision numbers checked and attached/commented
checkpoint-status | 73f33e0c-369c-4284-9f54-16005ef29c4a |  | checkpoint | Area ready for GIB install
checkpoint-status | 5476ccc3-a922-445e-b269-8916cc64f868 |  | checkpoint | Insulation installed
checkpoint-status | 6724bf1a-4c59-419f-b701-194e7672ba84 |  | checkpoint | General photos, comments and observations during install
checkpoint-status | 48a8002c-4618-499b-a8f5-40c79e3bc5d0 |  | checkpoint | Correct lining checked and approved and area specifics checked
checkpoint-status | 62dae2f3-24e9-4e75-9059-e804301194dd |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status | d0cc8a9f-b39c-478c-9c61-97604e8ba568 |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status | 3f794aa9-9f60-40df-aa8f-1e77dd88c208 |  | checkpoint | In long unbroken partitions or wall runs, control joints are required at 12 metres centres in either direction
checkpoint-status | 4f1d5afc-4f66-4bb4-a353-766563d460f9 |  | checkpoint | GIB Lining completed correctly within specified tolerance, checked and approved
checkpoint-status | 89e42923-042f-476e-931f-a0920b93538c |  | checkpoint | GIB Lining report sent through to client
checklist-flat |  |  | checklist | External Wall Framing Checklist |  |  |  |  | Yes | External Wall Framing Checklist | 18a0bc1e-1e65-4a3c-9cb2-59f228401eb3
checkpoint-status |  |  | checkpoint | Installer details entered
text | 685431b5-7d44-59f1-b02c-2a6e1d10ce18 |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | 1) All relevant drawings and revision numbers checked and attached.
checkpoint-status |  |  | checkpoint | 2) Timber delivery dockets checked and correct on arrival.
boolean | 845a1d29-be41-596c-b76c-4d05477bc422 |  | tickbox | All timber dockets attached
checkpoint-status |  |  | checkpoint | 3) Timber delivered are well stored and protected.
checkpoint-status |  |  | checkpoint | 4) DPC installed, checked, and correct as per specifications.
checkpoint-status |  |  | checkpoint | 5) Wall locations checked, correct, and approved as per latest revised drawing.
checkpoint-status |  |  | checkpoint | 6) Fixings and hold down bolts checked and correct.
checkpoint-status |  |  | checkpoint | 7) All openings (doors/windows, etc) checked, correct and approved.
checkpoint-status |  |  | checkpoint | 8) Wall type checked (straight and plumb) and within tolerance.
checkpoint-status |  |  | checkpoint | 9) 20mm clearance zone required between the threaded rod and structure above
checkpoint-status |  |  | checkpoint | 10) All relevant nogs (service, and special fixtures) installed, checked and correct.
checkpoint-status |  |  | checkpoint | 11) Moisture reading checked, recorded and acceptable.
checkpoint-status |  |  | checkpoint | 12) All wall framing checks completed and inspections carried out.
checkpoint-status |  |  | checkpoint | 13) Report sent to client.
checklist-sectioned |  |  | checklist | Prefab Module Fabrication |  |  |  |  | Yes | Prefab Module Fabrication | 2b34b135-5d64-4738-884c-40c7228726a0
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Panel Numbers
checkpoint-status |  |  | checkpoint | Date Check
checkpoint-status |  |  | checkpoint | Installers Details
checkpoint-status |  |  | checkpoint | Fixing used checked and correct
checkpoint-status |  |  | checkpoint | Panel constructed checked (straight, plumb and square)
checkpoint-status |  |  | checkpoint | All window openings checked and correct
checkpoint-status |  |  | checkpoint | Gib Weatherline – correct fixings used and installed at correct centres
checkpoint-status |  |  | checkpoint | WrapShield – all installation as per manufacturer’s specs; overlaps must be a minimum of 80mm on horizontal and vertical seams, VaproLiqui-Flash applied evenly at least 50mm onto the face and at least 25mm out along all sides of the penetration and all air bubbles must be smooth out to ensure full adhesion.
label | f1830bff-e028-5d3e-b117-001f178e3e3a |  | note | All panel checks completed and inspections carried out.
holdpoint |  |  | signoff | ANT Steel Frame Check/Signoff
checkpoint-status |  |  | checkpoint | Livefirm Signoff
checkpoint-status |  |  | checkpoint | Report sent through to Hawkins
checklist-sectioned | fc5fc549-6091-488e-9513-c0c8922d44dc |  | checklist | Precast Erection Checklist |  |  |  |  | Yes | QA - Precast Erection Checklist | 35a129f3-bdb7-43fe-a0ba-8a328fb21eb9
checkpoint-group |  |  | section | Installer Details
checkpoint-status |  |  | checkpoint | Installer details entered
text | 65db7f28-ba53-5d38-8021-a5bd8f4f34b4 |  | textbox | Installer:
checkpoint-group | 61886a01-a1fb-4516-9e93-eaa1baf2f363 |  | section | Component
checkpoint-status | c993d19e-f34e-4a1d-8623-242e08451678 |  | checkpoint | Component Specified
select | 65db7f28-ba53-5d38-8021-a5bd8f4f34b4 |  | dropdown | Select | Beam,Double T,Dycore,Rib,Slab,Staircase,Wall
text | 8f6d7f14-c88a-5b12-ab5b-ccc19b88a6df |  | textbox | If other please specify
checkpoint-group | ef0fa217-8b42-4623-9a28-54d83ac4b033 |  | section | Drawing & Instruction
checkpoint-status | e139ce8f-eeb8-43d3-bb0e-85971fd406dd |  | checkpoint | Drawing References
text | dab72bfe-ea2c-5673-a2eb-12af9827fb1a |  | textbox | 1
text | adb306a7-e1fa-561c-8fe5-e0b1a4314a7d |  | textbox | 2
text | 4431912b-436d-557d-a09f-d7a25e5a9bdc |  | textbox | 3
text | df3bdf06-5ab1-53e8-8b52-db988cc2c4d5 |  | textbox | 4
checkpoint-group | 560312a8-b755-4eb4-9b9b-c584c6342a45 |  | section | Setting Out/Starter bar/Shore loading/Fixing
checkpoint-status | 962413fd-dc82-4309-8ac4-34eeed2b50d9 |  | checkpoint | Survey mark
checkpoint-status | a60f0d7c-d2f8-42bd-aec1-ea676fdc4140 |  | checkpoint | Grids & Offsets
checkpoint-status | 14148c21-a1b3-4a84-8b75-d5c2ca36bb6d |  | checkpoint | Datums
checkpoint-status | 188a59ad-9ced-4a34-bb61-7b99239e3663 |  | checkpoint | Starter bar
checkpoint-status | 560d74cd-4d99-462f-9e20-60a46b34fe75 |  | checkpoint | Shore Loading
checkpoint-status | d672f8f0-3c75-494e-9e4c-5ad433fe38b1 |  | checkpoint | Propping
checkpoint-status | 4e4bcab7-70fa-4e73-84c0-79c815560f8e |  | checkpoint | Safety bolt
text | c9a58ac6-251f-5d6e-baf3-8804464ffd95 |  | textbox | Bolt size :
text | 301048ac-5785-574a-9755-826c7fa1256c |  | textbox | Bolt type :
checkpoint-group | ac6d9b46-fc1c-46bb-b461-34589f3ad70b |  | section | Precast Items
checkpoint-status | 8908b511-6888-4f4d-a952-d0da16170005 |  | checkpoint | Dimensions
checkpoint-group | 4676117c-01d4-4210-9710-a4512112821d |  | section | Pre-Erection Meeting
checkpoint-status | d8d78ecd-2631-42ba-ad29-9f49bb964061 |  | checkpoint | Complete
text | 6e5ad12d-53b5-5100-ae55-b6adb99000be |  | textbox | List all who are present
checkpoint-group | 68bea212-be1a-4475-aa39-acf208686abf |  | section | Signoffs
checkpoint-status | c018d182-3ec9-4a45-a374-8d5b275db3a9 |  | checkpoint | Work to Proceed
checklist-sectioned |  |  | checklist | QA - Concrete Pour Checklist |  |  |  |  | Yes | QA - Concrete Pour Checklist | 49933a36-eed0-4c74-9bc0-0a99e2f8a614
checkpoint-group |  |  | section | Installer Details
checkpoint-status |  |  | checkpoint | Installer details entered
text | a9da33ce-75dd-5c2a-b115-ab772fbb2eac |  | textbox | Installer:
checkpoint-group |  |  | section | Pre-Formwork and Embedded Items
checkpoint-status |  |  | checkpoint | Drawing numbers and revisions
checkpoint-status |  |  | checkpoint | Pre Formwork Inspection
button | 20e0d790-fe28-5745-a64f-dbdab164e6e2 |  | button | Cover to reinforcement | Pass,Fail,N/A
button | 77f9f72e-fde0-5d54-893e-072dd14b63b4 |  | button | Dimension/Thickness according to design | Pass,Fail,N/A
holdpoint |  |  | signoff | Request for signoff
checkpoint-group |  |  | section | Post-Formwork and Embedded Items
checkpoint-status |  |  | checkpoint | Grids and RLs clearly marked for reference
checkpoint-status |  |  | checkpoint | Reinforcing approved by contractor
checkpoint-status |  |  | checkpoint | Formwork - location, heights, falls, and dimensions checked and accurate
checkpoint-status |  |  | checkpoint | Formwork sufficiently fixed and braced
checkpoint-status |  |  | checkpoint | Any rebates/nibs/cast in items are correctly positioned, sized and appropriately fixed in place
boolean | 8ad88f85-ba18-5a78-8315-48094e284c19 |  | tickbox | Hold down bolts checked and correct
boolean | de638392-fe4b-52b6-82f3-f62db2d821fa |  | tickbox | Precast panel starters checked and correct
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork, etc)
checkpoint-status |  |  | checkpoint | Any control joints/stop ends installed accurately and correctly braced
checkpoint-status |  |  | checkpoint | Waterproofing approved by contractor
checkpoint-status |  |  | checkpoint | DPM & connection to other waterproofing completed
checkpoint-status |  |  | checkpoint | Any additional formwork photos and observations
checkpoint-status |  |  | checkpoint | All formwork elements completed and ready for concrete pour (Livefirm’s own excess debris removed)
checkpoint-status |  |  | checkpoint | Slump test / Spread test (only applicable to special mix)
checkpoint-status |  |  | checkpoint | Signoff Request sent to Livefirm senior site manager
holdpoint |  |  | signoff | Signoff Request sent to Livefirm senior site manager
checkpoint-status |  |  | checkpoint | Signoff Request sent to Hawkins from Livefirm senior site manager
holdpoint |  |  | signoff | Signoff Request sent to Hawkins from Livefirm senior site manager
checkpoint-group |  |  | section | Placement Method
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
text | d486df44-034a-529d-8902-3317a89a21ce |  | textbox | Date of pour
text | 9870f572-e54b-5272-adc5-689e94fbb34f |  | textbox | Who is placing the concrete
checkpoint-status |  |  | checkpoint | Concrete ordered – correct mix and strength
text | cd2e3c1e-1665-540d-9690-8418d857c98c |  | textbox | Mix
text | 955aa592-22ea-5067-9420-87c7ff99bb31 |  | textbox | Strength
text | 620ef230-e4e0-580d-a373-18b04303d3ad |  | textbox | Summary of proposed cement mix date and revision checked
text | a32e7f09-374d-5f95-91b5-de97629cb7e6 |  | textbox | Structural services specifications number and revision checked
checkpoint-status |  |  | checkpoint | Height and falls checked / confirmed before placement
checkpoint-status |  |  | checkpoint | Cover correct to specification
checkpoint-status |  |  | checkpoint | Concrete pump priming grout slurry is pumped to waste
checkpoint-status |  |  | checkpoint | All concrete checked and correct on arrival (mix and strength)
text | 5d47a110-5184-5157-b37f-967cf41a1dfd |  | textbox | All concrete dockets attached
checkpoint-status |  |  | checkpoint | General photos and observations of concrete placement attached
checkpoint-status |  |  | checkpoint | Heights and falls checked / confirmed after placement
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | Report sent to client
holdpoint |  |  | signoff | Request for signoff
checkpoint-group |  |  | section | Post-Pour Checks
checkpoint-status |  |  | checkpoint | Any remedial work completed
checkpoint-status |  |  | checkpoint | Concrete Pour completed - all final checks and documentation completed and attached
checkpoint-status |  |  | checkpoint | Report sent to client
checklist-flat |  |  | checklist | GIB Weatherline |  |  |  |  | Yes | GIB Weatherline | 82bb4d25-8e87-4d58-a5d7-26eb510d4f58
checkpoint-status |  |  | checkpoint | All relevant KCL drawings and revision numbers checked and attached
checkpoint-status |  |  | checkpoint | Installation location
boolean | 06d42236-35d0-5a47-bb38-1c82482586e0 |  | tickbox | Timber Frame 800mm x 300mm
boolean | aef1f987-cc4f-5db1-b90d-e1bc56c32125 |  | tickbox | Steel Studs 300mm x 300mm
checkpoint-status |  |  | checkpoint | Correct fasteners used and installed at correct centres
checkpoint-status |  |  | checkpoint | Fasteners – 12mm from the edges and 18mm from ends
checkpoint-status |  |  | checkpoint | Fasteners – 200mm centres along sheet end butt joints
checkpoint-status |  |  | checkpoint | Are screws over driven? If YES, install a new screw fixing 25mm away and adjacent to the over driven screw.
checkpoint-status |  |  | checkpoint | Is the GIB installed hard up against the floor.
checkpoint-status |  |  | checkpoint | Installer details
text | 5132182e-2717-5353-8c19-51fb8318db5d |  | textbox | Installer:
checklist-sectioned |  |  | checklist | Soffit |  |  |  |  | Yes | Soffit | 8350c61f-2098-4335-8000-8201307b0886
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked.
checkpoint-status |  |  | checkpoint | Timber frame specifications.
checkpoint-status |  |  | checkpoint | All joists are installed at correct centres.
checkpoint-status |  |  | checkpoint | Correct fixing used and installed at correct centres
checkpoint-status |  |  | checkpoint | Soffit lined with GIB weatherline completed correctly according to manufacturer’s specifications.
checkpoint-status |  |  | checkpoint | Installer’s details.
text | c9667501-ac7a-57ab-99cc-4dff6da01a07 |  | textbox | Installer:
checklist-sectioned |  |  | checklist | Prefab Module Installation / Post Installation |  |  |  |  | Yes | Prefab Module Installation / Post Installation | b7c62ddf-458d-4bc5-8791-5fdbab72e897
checkpoint-group |  |  | section | Prefab Module Installation
checkpoint-status |  |  | checkpoint | Prefab module received and damaged free
checkpoint-status |  |  | checkpoint | Setup completed and clearly marked and ready for installation
checkpoint-status |  |  | checkpoint | Installed in correct centres location with adequate seating (each stud with packers)
checkpoint-status |  |  | checkpoint | Correct centres and fixing used on steel structure and floor
checkpoint-status |  |  | checkpoint | Prefab module installation completed (check location, height and level)
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Prefab Module Post Installation
checkpoint-status |  |  | checkpoint | Window opening location checked and correct
checkpoint-status |  |  | checkpoint | Drossbach fully grouted
checkpoint-status |  |  | checkpoint | Correct type of grout used
checkpoint-status |  |  | checkpoint | Simpson tie bolt checked and tighten
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | WrapShield |  |  |  |  | Yes | WrapShield | c18de092-4fd7-4a83-94e5-3b064d708527
checkpoint-status |  |  | checkpoint | Installer details entered
text | 249aea3a-4077-5d94-9725-c3c277f15604 |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | Substrate must be dry, clean and free of any contaminants.
checkpoint-status |  |  | checkpoint | All overlaps must be a minimum of 80mm on horizontal and vertical seams.
checkpoint-status |  |  | checkpoint | Inside and outside vertical corners should be at minimum 150mm of overlap.
checkpoint-status |  |  | checkpoint | All installation must be with the lower courses lapped under the upper courses.
checkpoint-status |  |  | checkpoint | All air bubbles must be smooth out to ensure full adhesion.
checkpoint-status |  |  | checkpoint | Apply VaproLiqui-Flash evenly at least 50mm onto the face and at least 25mm out along all sides of the penetration.
checklist-flat | 66ef80ee-c709-4d8a-b27c-5e41afe69dac |  | checklist | Wall Framing Checks |  |  |  |  | Yes | Wall Framing Checks | d075bc65-860f-4fc9-ba17-d7c7d52695b5
checkpoint-status | 242b4a2d-b6ea-4b9f-9b82-44c97e7664cb |  | checkpoint | Installer details entered
text | 71f8d068-5761-57e6-b5c5-9d03600b65d5 |  | textbox | Installer:
checkpoint-status | edb252a7-e90b-466f-bce4-a1e4f5291978 |  | checkpoint | All relevant drawings and revision numbers checked and attached
checkpoint-status | 0a7a108a-19ad-451b-934b-f7b12947377b |  | checkpoint | Drawing no. and revision
checkpoint-status | ad916d8f-5cd2-4f09-a24f-c45390255cdb |  | checkpoint | DPC installed, checked and correct as per specification
checkpoint-status | ed5387dd-2423-4123-b7f7-46304e373532 |  | checkpoint | Wall locations checked, correct and approved as per latest revised drawing
checkpoint-status | af766c46-1afc-47c9-a5d5-8cd6ce68795d |  | checkpoint | Fixings and hold down bolts checked and correct
checkpoint-status | 729bd163-422e-47d5-9ef0-a1597a81c079 |  | checkpoint | All openings (doors / windows etc) checked, correct and approved
checkpoint-status | ca10f7e4-86da-4169-b4eb-c904171e4a53 |  | checkpoint | Deflection heads type installed and correct
checkpoint-status | 02bbad7e-8c32-494e-b8df-b2648d8c6846 |  | checkpoint | Wall type checked (straight and plumb) and within tolerance
checkpoint-status | f7f65abf-1434-4bd1-a7fc-1ca3ed03938c |  | checkpoint | All relevant nogs (service and special/fixtures) installed, checked and correct
checkpoint-status | cfbb253e-1152-4b43-92d7-8be62659867f |  | checkpoint | All other nogs checked and approved
checkpoint-status | d7335047-3825-4433-b754-b2936fa3f825 |  | checkpoint | Moisture reading checked, recorded and acceptable
checkpoint-status | 5444ef0f-94a8-4e52-85d3-3dc006644d70 |  | checkpoint | A control joint is required where there is a split between the underlying structure with a break in the top and bottom plate
checkpoint-status | ec2c3681-ddd7-4d45-84c1-4ac865741a38 |  | checkpoint | All wall framing checks completed & Inspections carried out
checkpoint-status | bc4bec8e-9ade-4506-8897-668fde1d1a4f |  | checkpoint | Relevant inspections completed and attached
checkpoint-status | cb7f00af-8484-47d0-a0a4-b30e6faa2703 |  | checkpoint | Report sent to client
checklist-sectioned |  |  | checklist | Fire Door Pre-Installation Check |  |  |  |  | Yes | Fire Door Pre-Installation Check | e97d47e9-2eb5-463d-b47b-dca34fd121a1
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Installation can be carried out in accordance with finish floor product thickness.
checkpoint-status |  |  | checkpoint | Door opening area (slab) is level with door jamb area.
checkpoint-status |  |  | checkpoint | Wall framing opening size checked and correct.
checkpoint-status |  |  | checkpoint | The dimensions of the door frame and panel are in accordance to Hawkins’ order.
checkpoint-status |  |  | checkpoint | Door frame and panel are free from any defects and damages upon receiving from Hawkins.
checkpoint-status |  |  | checkpoint | Pre-Installation checked completed
holdpoint |  |  | signoff | Add signature
checklist-sectioned |  |  | checklist | Fire Door Post-Installation Check |  |  |  |  | Yes | Fire Door Post-Installation Check | f377388d-3ae1-4103-a40f-5f6873798483
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached.
checkpoint-status |  |  | checkpoint | Door is fully operational.
checkpoint-status |  |  | checkpoint | Door jambs are level and direction of door correct.
checkpoint-status |  |  | checkpoint | Correct fixings used and installed at correct centres.
checkpoint-status |  |  | checkpoint | Door gap around door leaf within tolerance as per manufacturer’s specifications.
checkpoint-status |  |  | checkpoint | Fireseal around door installed correctly.
checkpoint-status |  |  | checkpoint | Floor clearance is correct.
checkpoint-status |  |  | checkpoint | Installer details.
checkpoint-status |  |  | checkpoint | Post-Installation checked completed.
holdpoint |  |  | signoff | Add signature
checklist-flat | a841648e-e155-4245-ae76-575fcac4ad1f |  | checklist | QA - Base Set Out Checklist |  |  |  |  | Yes | QA - Base Set Out Checklist | f676fe1a-e1b3-4bb2-aff5-fe04a1de5678
checkpoint-status |  |  | checkpoint | Installer details entered
text | 79fee405-71e1-592b-b400-7252f4b7d727 |  | textbox | Installer:
checkpoint-status | 2a789262-deb8-4ee6-ab14-acb3f2173991 |  | checkpoint | All relevant drawings and revision numbers checked and attached/commented
checkpoint-status | 144d20c0-ec31-4140-a31d-56a99473f698 |  | checkpoint | Set out points and Datum to be established by surveyor
checkpoint-status | b41edaf8-208b-4878-bb5e-c5f9fd1d5781 |  | checkpoint | Obtain written confirmation from surveyor
checkpoint-status | fd0bb3a2-9a83-4ee5-a8e9-7eba95fbc3ab |  | checkpoint | Send Report to client