## ITC - Type C Earthworks
LOT DETAILS
| Internal Lot Number | Autogenerated
| External Lot Number (optional) | Open text
| Lot Description | Open text
| Lot Status | Drop List
|  | OPEN | [6 empty] | Lot Created but Work Has Not Been Commenced
|  | WORK IN PROGRESS | [6 empty] | Work Commenced and Continuing
|  | AWAITING HOLDPOINT | [6 empty] | Awaiting Hold Point Release
|  | AWAITING NCR | [6 empty] | Awaiting NCR Closure
|  | AWAITING TEST RESULT | [6 empty] | Awaiting Test Results Received
|  | OUTSTANDING | [6 empty] | Outstanding
|  | AWAITING VERIFICATION | [6 empty] | Awaiting Verification for Test Reports/QA Docs To Verified
|  | Submitted TO THE CLIENT | [6 empty] | Internally Closed
|  | CLOSED-OUT | [6 empty] | Externally Closed-out
|  | CANCELLED | [6 empty] | Cancelled
LOT INFORMATION
| Open date | Autogenerated
| Inspection Test Plan | Drop List
| Area | Drop List
| Zone | Drop List
| Discipline | Drop List
| Responsible Engineer | Drop List
| Work commenced on | Open Date
| Number of Underlier or Predecessor Lots | Open Number (0,1,2,#) | Lot 1 | Drop List --> Current Lots
|  |  | Lot 2 | Drop List --> Current Lots
|  |  | Lot # | Drop List --> Current Lots
INSPECTION TEST CHECKLITS | Type C Earthworks
PRELIMINARIES | Design Issued for Construction | Yes / No / NA
| Drawings Issue for Construction | Yes / No / NA
| Material Hold Points Released | Yes / No / NA
| Survey Request | Yes / No / NA
| Traffic Management Plan Approved | Yes / No / NA
| Subcontractor/Provider approved? | Yes / No / NA
| Kick-off meeting (Subcontractor) | Yes / No / NA
CONSTRUCTION
HP (Hold Point): Work shall only proceed past the Hold Point once it is released by the organisation imposing it. WP (Witness Point): An inspection point that may be witnessed by the organisation imposing the Witness Point. I (Inspection): Formal inspection activity to be undertaken and recorded. S (Surveillance): An activity that is subject to ongoing monitoring. R (Review): Review reports/records or other evidence of compliance. | Activity or Description | Applicable Standard / Reference | Acceptance Criteria | Frequency | Verification Records | Action Respon. | Sign & Date WINSLOW | Sign & Date Superintendent
| Safety; SWMS | HSMP | SMWS to be written for each activity on Project and shall be reviewed by a competent person. Submitted to the client …………..days prior to commencement of Activity. | Each Activity | Records | PE/SE
| Environmental Controls | EMP | No work shall commence unless all erosion/ Sediment controls are implemented in accordance with EMP. | Each Activity | ECP | PE/SE
| Excavation Permit | OHS | DBYD information available on site, Excavation permit issued and spotter at location before commencement of excavation works | Each Lot | Records | PE/SE
| Survey Control | VR204.03 (a), (b, c) | • All Earthworks shall be finished to conform to the levels, lines, grades and cross sections showed in the plans. | Each Lot | Setout | Surveyor
HP | Material - Type C | VR204.04 (b) | Material classified as silt, either before or after compaction, is not acceptable as Type C material unless otherwise approved by the Superintendent. | Each Lot | Visual | FM
HP | Site excavation - material category | VR204.06 (b) | Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04. | Each Lot | Visual | FM
HP | Earthworks - Groundwater Seepage | VR204.06 (h) | Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater. | Each Lot | Visual | PE/SE
HP | Earthworks - treatment of Unsuitable Material | VR204.07 (d) | Where unsuitable material is encountered the Contractor shall submit the proposed in situ treatment or extent of excavation to the Superintendent for review. | Each Lot | Visual | FM
HP | Earthworks - Fill construction | VR204.10 (b) | The Contractor shall not commence placing of any fill on the prepared surface until the area has been reviewed by the Superintendent. | Each Lot | Visual | FM
HP | Earthworks - Fill at Structures (wing walls, culverts >1200mm) | VR204.11 (b) | No fill shall be placed against or within 3m of a structure until the foundation for the fill has been reviewed by the Superintendent. | Each Lot | Visual | FM
| Test Rolling | VR173.03, VR204.12 | Undertake test roll prior to placement of fill/or proceeding layer. | Each Lot | Visual | FM
| Compaction - Lot size | VR204.13 | Type C: 10,000m2 or one day's production, whichever is the lesser | Each Lot | Records | PE/SE
| Compaction | VR204.13 (b), VR204.14 | • Compaction All Type C material should conform to 95% of a standard density Max. particle size<100mm (visual inspection) | 1 test per each 6 lots | Records/Visual | FM
**Other Contract Specific Requirements ……..
LOT CONFORMANCE
| Works completed on: | Date
All Hold Points released?
Yes
No
N/A
All Test Reports conforming?
Yes
No
N/A
NCR raised?
| Yes | NCR Number: | Drop List (From NCRs) | NCR Status: | Autogenerated from NCR Register
No
Lot Verified by:
List of Users
| Lot Verified on: | Date
| Comments: | Open text
| Date Submitted to Client: | Date

## ITC - Type B Earthworks
LOT DETAILS
| Internal Lot Number | Autogenerated
| External Lot Number (optional) | Open text
| Lot Description | Open text
| Lot Status | Drop List
|  | OPEN | [6 empty] | Lot Created but Work Has Not Been Commenced
|  | WORK IN PROGRESS | [6 empty] | Work Commenced and Continuing
|  | AWAITING HOLDPOINT | [6 empty] | Awaiting Hold Point Release
|  | AWAITING NCR | [6 empty] | Awaiting NCR Closure
|  | AWAITING TEST RESULT | [6 empty] | Awaiting Test Results Received
|  | OUTSTANDING | [6 empty] | Outstanding
|  | AWAITING VERIFICATION | [6 empty] | Awaiting Verification for Test Reports/QA Docs To Verified
|  | Submitted TO THE CLIENT | [6 empty] | Internally Closed
|  | CLOSED-OUT | [6 empty] | Externally Closed-out
|  | CANCELLED | [6 empty] | Cancelled
LOT INFORMATION
| Open date | Autogenerated
| Inspection Test Plan | Drop List
| Area | Drop List
| Zone | Drop List
| Discipline | Drop List
| Responsible Engineer | Drop List
| Work commenced on | Open Date
| Number of Underlier or Predecessor Lots | Open Number (0,1,2,#) | Lot 1 | Drop List --> Current Lots
|  |  | Lot 2 | Drop List --> Current Lots
|  |  | Lot # | Drop List --> Current Lots
INSPECTION TEST CHECKLITS | Type B Earthworks
PRELIMINARIES | Design Issued for Construction | Yes / No / NA
| Drawings Issue for Construction | Yes / No / NA
| Material Hold Points Released | Yes / No / NA
| Survey Request | Yes / No / NA
| Traffic Management Plan Approved | Yes / No / NA
| Subcontractor/Provider approved? | Yes / No / NA
| Kick-off meeting (Subcontractor) | Yes / No / NA
CONSTRUCTION
HP (Hold Point): Work shall only proceed past the Hold Point once it is released by the organisation imposing it. WP (Witness Point): An inspection point that may be witnessed by the organisation imposing the Witness Point. I (Inspection): Formal inspection activity to be undertaken and recorded. S (Surveillance): An activity that is subject to ongoing monitoring. R (Review): Review reports/records or other evidence of compliance. | Activity or Description | Applicable Standard / Reference | Acceptance Criteria | Frequency | Verification Records | Action Respon. | Sign & Date WINSLOW | Sign & Date Superintendent
| Safety; SWMS | HSMP | SMWS to be written for each activity on Project and shall be reviewed by a competent person. Submitted to the client …………..days prior to commencement of Activity. | Each Activity | Records | PE/SE
| Environmental Controls | EMP | No work shall commence unless all erosion/ Sediment controls are implemented in accordance with EMP. | Each Activity | ECP | PE/SE
| Excavation Permit | OHS | DBYD information available on site, Excavation permit issued and spotter at location before commencement of excavation works | Each Lot | Records | PE/SE
| Survey Control | VR204.03 (a), (b, c) | • All Earthworks shall be finished to conform to the levels, lines, grades and cross sections showed in the plans. | Each Lot | Setout | Surveyor
HP | Material - Type B | VR204.04 (b) | Material classified as silt, either before or after compaction, is not acceptable as Type B material unless otherwise approved by the Superintendent. | Each Lot | Visual | FM
| Site excavation - cutting floor | VR204.03 (f) | • The level at any point on the surface of the Cut Floor Level immediately below capping and/or selected material shall not differ by more than 15 mm above or 30 mm below the specified level. | Each Lot | Visual | FM
HP | Site excavation - material category | VR204.06 (b) | Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04. | Each Lot | Visual | FM
HP | Earthworks - Groundwater Seepage | VR204.06 (h) | Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater. | Each Lot | Visual | PE/SE
HP | Earthworks - treatment of Unsuitable Material | VR204.07 (d) | Where unsuitable material is encountered the Contractor shall submit the proposed in situ treatment or extent of excavation to the Superintendent for review. | Each Lot | Visual | FM
HP | Earthworks - Fill construction | VR204.10 (b) | The Contractor shall not commence placing of any fill on the prepared surface until the area has been reviewed by the Superintendent. | Each Lot | Visual | FM
HP | Earthworks - Fill at Structures (wing walls, culverts >1200mm) | VR204.11 (b) | No fill shall be placed against or within 3m of a structure until the foundation for the fill has been reviewed by the Superintendent. | Each Lot | Visual | FM
| Test Rolling | VR173.03, VR204.12 | Undertake test roll prior to placement of fill/or proceeding layer. | Each Lot | Visual | FM
| Compaction - Lot size | VR204.13 | Type B: max 10,000m2 or one day's production, whichever is the lesser | Each Lot | Records | PE/SE
| Compaction | VR204.13 (b), VR204.14 | • Compaction Type B material placed within 400mm of top of Type B level: min. 99% Type B material placed more than 400mm of top of Type B level: min. 97% • Grading Max. particle size<100mm (visual inspection) | 1 test for each lot then reduced to 1 test for every second lot | Records/Visual | FM
| Compaction - CBR & Swell | Table 204.141 | Type B: initial 1 lot test to determine assigned CBR and swell | Single CBR test to confirm assigned CBR and swell per every 8 lots | Records | PE/SE
| Compaction - LL | Table 204.141 | Type B: liquid limit and comparison of PI against LL | 1 test per 2 lots then reduced to 1 test per 4 lots | Records | PE/SE
**Other Contract Specific Requirements ……..
LOT CONFORMANCE
| Works completed on: | Date
All Hold Points released?
Yes
No
N/A
All Test Reports conforming?
Yes
No
N/A
NCR raised?
| Yes | NCR Number: | Drop List (From NCRs) | NCR Status: | Autogenerated from NCR Register
No
Lot Verified by:
List of Users
| Lot Verified on: | Date
| Comments: | Open text
| Date Submitted to Client: | Date

## ITC - Type A Earthworks
LOT DETAILS
| Internal Lot Number | Autogenerated
| External Lot Number (optional) | Open text
| Lot Description | Open text
| Lot Status | Drop List
|  | OPEN | [6 empty] | Lot Created but Work Has Not Been Commenced
|  | WORK IN PROGRESS | [6 empty] | Work Commenced and Continuing
|  | AWAITING HOLDPOINT | [6 empty] | Awaiting Hold Point Release
|  | AWAITING NCR | [6 empty] | Awaiting NCR Closure
|  | AWAITING TEST RESULT | [6 empty] | Awaiting Test Results Received
|  | OUTSTANDING | [6 empty] | Outstanding
|  | AWAITING VERIFICATION | [6 empty] | Awaiting Verification for Test Reports/QA Docs To Verified
|  | Submitted TO THE CLIENT | [6 empty] | Internally Closed
|  | CLOSED-OUT | [6 empty] | Externally Closed-out
|  | CANCELLED | [6 empty] | Cancelled
LOT INFORMATION
| Open date | Autogenerated
| Inspection Test Plan | Drop List
| Area | Drop List
| Zone | Drop List
| Discipline | Drop List
| Responsible Engineer | Drop List
| Work commenced on | Open Date
| Number of Underlier or Predecessor Lots | Open Number (0,1,2,#) | Lot 1 | Drop List --> Current Lots
|  |  | Lot 2 | Drop List --> Current Lots
|  |  | Lot # | Drop List --> Current Lots
INSPECTION TEST CHECKLITS | Type A Earthworks
PRELIMINARIES | Design Issued for Construction | Yes / No / NA
| Drawings Issue for Construction | Yes / No / NA
| Material Hold Points Released | Yes / No / NA
| Survey Request | Yes / No / NA
| Traffic Management Plan Approved | Yes / No / NA
| Subcontractor/Provider approved? | Yes / No / NA
| Kick-off meeting (Subcontractor) | Yes / No / NA
CONSTRUCTION
HP (Hold Point): Work shall only proceed past the Hold Point once it is released by the organisation imposing it. WP (Witness Point): An inspection point that may be witnessed by the organisation imposing the Witness Point. I (Inspection): Formal inspection activity to be undertaken and recorded. S (Surveillance): An activity that is subject to ongoing monitoring. R (Review): Review reports/records or other evidence of compliance. | Activity or Description | Applicable Standard / Reference | Acceptance Criteria | Frequency | Verification Records | Action Respon. | Sign & Date WINSLOW | Sign & Date Superintendent
| Safety; SWMS | HSMP | SMWS to be written for each activity on Project and shall be reviewed by a competent person. Submitted to the client …………..days prior to commencement of Activity. | Each Activity | Records | PE/SE
| Environmental Controls | EMP | No work shall commence unless all erosion/ Sediment controls are implemented in accordance with EMP. | Each Activity | ECP | PE/SE
| Excavation Permit | OHS | DBYD information available on site, Excavation permit issued and spotter at location befotre commencement of excavation works | Each Lot | Records | PE/SE
| Survey Control | VR204.03 (a), (b, c) | • All Earthworks shall be finished to conform to the levels, lines, grades and cross sections showed in the plans. Machine GPS File Date………….. | Each Lot | Setout | Surveyor
HP | Material - Type A | VR204.04 (b) | Material classified as silt, either before or after compaction, is not acceptable as Type A material unless otherwise approved by the Superintendent. | Each Lot | Visual | FM
| Site excavation - Cut Floor Level | VR204.03 (f) | • The level at any point on the surface of the Cut Floor Level immediately below capping and/or selected material shall not differ by more than 15 mm above or 30 mm below the specified level. | Each Lot | Visual | FM
HP | Site excavation - material category | VR204.06 © | Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04. | Each Lot | Visual | FM
| Earthworks - treatment of cutting at cut floor level | VR204.06 (e) (i) | In situ material below cut floor level having an assigned CBR less than 6, or a swell of 2.5% or greater, shall be removed to a depth of 400mm below cut floor level and replaced with conforming type B material to the underside of the capping or selected material layer | Each Lot | Visual | FM
HP | Earthworks - Groundwater Seepage | VR204.06 (h) | Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater. | Each Lot | Visual | FM
HP | Earthworks - treatment of Unsuitable Material | VR204.07 (d) | Where unsuitable material is encountered the Contractor shall submit the proposed in situ treatment or extent of excavation to the Superintendent for review. | Each Lot | Visual | FM
HP | Earthworks - Fill construction | VR204.10 (b) | The Contractor shall not commence placing of any fill on the prepared surface until the area has been reviewed by the Superintendent. | Each Lot | Visual | FM
HP | Earthworks - Fill at Structures (wing walls, culverts >1200mm) | VR204.11 (b) | No fill shall be placed against or within 3m of a structure until the foundation for the fill has been reviewed by the Superintendent. | Each Lot | Visual | FM
HP | Test Rolling | VR173.03, VR204.12 | Undertake test roll prior to placement of fill/or proceeding layer. Contractor shall provide for the Superintendant to be present during all test rolling. | Each Lot | Visual | FM
| Lot size | VR204.13, Table204.142 | Type A: max 5000m2 or one day's production, whichever is the lesser Actual……………….m2 | Each Lot | Records | PE/SE
| Compaction & Grading | VR204.13 (b), Tables 204.042, 204.14 1 | • Compaction All Type A Material, and Type B material placed within 400mm of top of cut floor level: min. 100% Actual……………..% / Minimum Frequency Testing • Grading as per Table 204.041 Pass/ Fail/ Minimum Frequency testing | 1 test for each lot then reduced to 1 test for every second lot | Records/Visual | FM
| Compaction - CBR & Swell | Table 204.141 & Table 204.041 | Type A: initial 1 lot test to determine assigned CBR >6% and swell <1.5% Assigned CBR…………………% Actual ………………….% Assigned Swell…………………% Actual ………………….% | Single CBR test to confrim assigned CBR and swell - first lot only | Records | PE/SE
| Compaction - PI | Table 204.141 & Table 204.041 | Type A: plasticity index (PI) calculation x % Passing 0.425mm Max. 1000 | 1 test per 2 lots then 1 test per 4 lots | Records | PE/SE
| Compaction - LL & Permeability | Table 204.141 & Table 204.041 | Type A: liquid limit and comparison of PI against LL, Permeability <5 x 10-9m/sec | 1 test per 2 lots then 1 test per 4 lots | Records | PE/SE
**Other Contract Specific Requirements ……..
LOT CONFORMANCE
| Works completed on: | Date
All Hold Points released?
Yes
No
N/A
All Test Reports conforming?
Yes
No
N/A
NCR raised?
| Yes | NCR Number: | Drop List (From NCRs) | NCR Status: | Autogenerated from NCR Register
No
Lot Verified by:
List of Users
| Lot Verified on: | Date
| Comments: | Open text
| Date Submitted to Client: | Date

## ITC - Capping Layer
LOT DETAILS
| Internal Lot Number | Autogenerated
| External Lot Number (optional) | Open text
| Lot Description | Open text
| Lot Status | Drop List
|  | OPEN | [6 empty] | Lot Created but Work Has Not Been Commenced
|  | WORK IN PROGRESS | [6 empty] | Work Commenced and Continuing
|  | AWAITING HOLDPOINT | [6 empty] | Awaiting Hold Point Release
|  | AWAITING NCR | [6 empty] | Awaiting NCR Closure
|  | AWAITING TEST RESULT | [6 empty] | Awaiting Test Results Received
|  | OUTSTANDING | [6 empty] | Outstanding
|  | AWAITING VERIFICATION | [6 empty] | Awaiting Verification for Test Reports/QA Docs To Verified
|  | Submitted TO THE CLIENT | [6 empty] | Internally Closed
|  | CLOSED-OUT | [6 empty] | Externally Closed-out
|  | CANCELLED | [6 empty] | Cancelled
LOT INFORMATION
| Open date | Autogenerated
| Inspection Test Plan | Drop List
| Area | Drop List
| Zone | Drop List
| Discipline | Drop List
| Responsible Engineer | Drop List
| Work commenced on | Open Date
| Number of Underlier or Predecessor Lots | Open Number (0,1,2,#) | Lot 1 | Drop List --> Current Lots
|  |  | Lot 2 | Drop List --> Current Lots
|  |  | Lot # | Drop List --> Current Lots
INSPECTION TEST CHECKLITS | Capping Layer
PRELIMINARIES | Design Issued for Construction | Yes / No / NA
| Drawings Issue for Construction | Yes / No / NA
| Material Hold Points Released | Yes / No / NA
| Survey Request | Yes / No / NA
| Traffic Management Plan Approved | Yes / No / NA
| Subcontractor/Provider approved? | Yes / No / NA
| Kick-off meeting (Subcontractor) | Yes / No / NA
CONSTRUCTION
HP (Hold Point): Work shall only proceed past the Hold Point once it is released by the organisation imposing it. WP (Witness Point): An inspection point that may be witnessed by the organisation imposing the Witness Point. I (Inspection): Formal inspection activity to be undertaken and recorded. S (Surveillance): An activity that is subject to ongoing monitoring. R (Review): Review reports/records or other evidence of compliance. | Activity or Description | Applicable Standard / Reference | Acceptance Criteria | Frequency | Verification Records | Action Respon. | Sign & Date WINSLOW | Sign & Date Superintendent
| Safety; SWMS | HSMP | SMWS to be written for each activity on Project and shall be reviewed by a competent person. Submitted to the client …………..days prior to commencement of Activity. | Each Activity | Records | PE/SE
| Environmental Controls | EMP | No work shall commence unless all erosion/ Sediment controls are implemented in accordance with EMP. | Each Activity | ECP | PE/SE
| Excavation Permit | OHS | DBYD information available on site, Excavation permit issued and spotter at location befotre commencement of excavation works | Each Lot | Records | PE/SE
| Survey Control | VR204.03 (a), (b, c) | • All Earthworks shall be finished to conform to the levels, lines, grades and cross sections showed in the plans. Machine GPS File Date………….. | Each Lot | Setout | Surveyor
HP | Material - Type A | VR204.04 (b) | Material classified as silt, either before or after compaction, is not acceptable as Type A material unless otherwise approved by the Superintendent. | Each Lot | Visual | SE
| Site excavation - Cut Floor Level | VR204.03 (f) | • The level at any point on the surface of the Cut Floor Level immediately below capping and/or selected material shall not differ by more than 15 mm above or 30 mm below the specified level. | Each Lot | Visual | SE
HP | Site excavation - material category | VR204.06 © | Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04. | Each Lot | Visual | SE
| Earthworks - treatment of cutting at cut floor level | VR204.06 (e) (i) | In situ material below cut floor level having an assigned CBR less than 6, or a swell of 2.5% or greater, shall be removed to a depth of 400mm below cut floor level and replaced with conforming type B material to the underside of the capping or selected material layer | Each Lot | Visual | SE
HP | Earthworks - Groundwater Seepage | VR204.06 (h) | Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater. | Each Lot | Visual | SE
HP | Earthworks - treatment of Unsuitable Material | VR204.07 (d) | Where unsuitable material is encountered the Contractor shall submit the proposed in situ treatment or extent of excavation to the Superintendent for review. | Each Lot | Visual | SE
HP | Earthworks - Fill construction | VR204.10 (b) | The Contractor shall not commence placing of any fill on the prepared surface until the area has been reviewed by the Superintendent. | Each Lot | Visual | SE
HP | Earthworks - Fill at Structures (wing walls, culverts >1200mm) | VR204.11 (b) | No fill shall be placed against or within 3m of a structure until the foundation for the fill has been reviewed by the Superintendent. | Each Lot | Visual | SE
HP | Test Rolling | VR173.03, VR204.12 | Undertake test roll prior to placement of fill/or proceeding layer. Contractor shall provide for the Superintendant to be present during all test rolling. | Each Lot | Visual | SE
| Lot size | VR204.13, Table204.142 | Type A: max 5000m2 or one day's production, whichever is the lesser Actual……………….m2 | Each Lot | Records | PE/SE
| Compaction & Grading | VR204.13 (b), Tables 204.042, 204.14 1 | • Compaction All Type A Material, and Type B material placed within 400mm of top of cut floor level: min. 100% Actual……………..% / Minimum Frequency Testing • Grading as per Table 204.041 Pass/ Fail/ Minimum Frequency testing | 1 test for each lot then reduced to 1 test for every second lot | Records/Visual | SE
| Compaction - CBR & Swell | Table 204.141 & Table 204.041 | Type A: initial 1 lot test to determine assigned CBR >6% and swell <1.5% Assigned CBR…………………% Actual ………………….% Assigned Swell…………………% Actual ………………….% | Single CBR test to confrim assigned CBR and swell - first lot only | Records | PE/SE
| Compaction - PI | Table 204.141 & Table 204.041 | Type A: plasticity index (PI) calculation x % Passing 0.425mm Max. 1000 | 1 test per 2 lots then 1 test per 4 lots | Records | PE/SE
| Compaction - LL & Permeability | Table 204.141 & Table 204.041 | Type A: liquid limit and comparison of PI against LL, Permeability <5 x 10-9m/sec | 1 test per 2 lots then 1 test per 4 lots | Records | PE/SE
S | **Other Contract Specific Requirements ……..
LOT CONFORMANCE
| Works completed on: | Date
All Hold Points released?
Yes
No
N/A
All Test Reports conforming?
Yes
No
N/A
NCR raised?
| Yes | NCR Number: | Drop List (From NCRs) | NCR Status: | Autogenerated from NCR Register
No
Lot Verified by:
List of Users
| Lot Verified on: | Date
| Comments: | Open text
| Date Submitted to Client: | Date

## ITC - Drainage Pit
LOT DETAILS
| Internal Lot Number | Autogenerated
| External Lot Number (optional) | Open text
| Lot Description | Open text
| Lot Status | Drop List
|  | OPEN | [6 empty] | Lot Created but Work Has Not Been Commenced
|  | WORK IN PROGRESS | [6 empty] | Work Commenced and Continuing
|  | AWAITING HOLDPOINT | [6 empty] | Awaiting Hold Point Release
|  | AWAITING NCR | [6 empty] | Awaiting NCR Closure
|  | AWAITING TEST RESULT | [6 empty] | Awaiting Test Results Received
|  | OUTSTANDING | [6 empty] | Outstanding
|  | AWAITING VERIFICATION | [6 empty] | Awaiting Verification for Test Reports/QA Docs To Verified
|  | Submitted TO THE CLIENT | [6 empty] | Internally Closed
|  | CLOSED-OUT | [6 empty] | Externally Closed-out
|  | CANCELLED | [6 empty] | Cancelled
LOT INFORMATION
| Open date | Autogenerated
| Inspection Test Plan | Drop List
| Area | Drop List
| Zone | Drop List
| Discipline | Drop List
| Responsible Engineer | Drop List
| Work commenced on | Open Date
| Number of Underlier or Predecessor Lots | Open Number (0,1,2,#) | Lot 1 | Drop List --> Current Lots
|  |  | Lot 2 | Drop List --> Current Lots
|  |  | Lot # | Drop List --> Current Lots
INSPECTION TEST CHECKLITS | Drainage Pits
PRELIMINARIES | Design Issued for Construction | Yes / No / NA
| Drawings Issue for Construction | Yes / No / NA
| Material Hold Points Released | Yes / No / NA
| Survey Request | Yes / No / NA
| Traffic Management Plan Approved | Yes / No / NA
| Subcontractor/Provider approved? | Yes / No / NA
| Kick-off meeting (Subcontractor) | Yes / No / NA
CONSTRUCTION
HP (Hold Point): Work shall only proceed past the Hold Point once it is released by the organisation imposing it. WP (Witness Point): An inspection point that may be witnessed by the organisation imposing the Witness Point. I (Inspection): Formal inspection activity to be undertaken and recorded. S (Surveillance): An activity that is subject to ongoing monitoring. R (Review): Review reports/records or other evidence of compliance. | Activity or Description | Applicable Standard / Reference | Acceptance Criteria | Frequency | Verification Records | Action Respon. | Sign & Date WINSLOW | Sign & Date Superintendent
W | Safety; SWMS | HSMP | SMWS to be written for each activity on Project and shall be reviewed by a competent person. Submitted to the client …………..days prior to commencement of Activity. | Each Activity | Records | PE/SE |  | NA
W | Environmental Controls | EMP | No work shall commence unless all erosion/ Sediment controls are implemented in accordance with EMP. | Each Activity | ECP | PE/SE |  | NA
H | Excavation Permit | OHS | DBYD information available on site, Excavation permit issued and spotter at location before commencement of excavation works | Each Lot | Records | PE/SE |  | NA
W | Manufacture Precast Documentation (QMP, ITPs,ITCs, Shop Drawings, Reports) | ITP |  | For Each Manufacture | Records | PE/SE |  | NA
R | Delivery Dockets | ITP | Delivery Docket for each Pit must be clearly identified and uploaded to the lot | Each Pit | Delivery Docket | PE/SE |  | NA
S | Unit Identification (Pit number, other) | ITP | Pit Unit Identification must be visible after installation for further identification | Each Pit | Picture | PE/SE |  | NA
W | Materials | VR705.04 (c) & (d) | Concrete - Shall be N32 standard strength grade ? Covers, Lids, Grates, Lintels as shown on drawings Step Irons - Those manufactured from 13mm steel bar covered with polypropylene plastic must be approved by superintendent | Once | Records | PE/SE |  | NA
I | Excavation - Precast Pits | VR705.05 (b) | • Clearance from all external faces of the pit to each face of the excavation shall be not less than 400mm. • Bedding shall be supplied, placed and compacted to a thickness not less than 80mm on a clay foundation or 150mm on a rock foundation. | Each Lot | Visual / Pictures | SE/FM |  | NA
I | Precast Pits | VR705.09 | • Holes for subsurface drains should be 150mm unless specified otherwise. • Weepholes of 50mm shall be provided in all precast pits (see spec for location) • Segmented pits require a minimum 15mm rebate. | Each Lot | Visual / Pictures | SE/FM |  | NA
I | Stormwater drainage connections | VR705.1 | All stormwater drainage connections to pits shall be neatly made, and where necessary the ends of all drains shall be trimmed off and finished with cement mortar. | Each Lot | Visual / Pictures | SE/FM |  | NA
S | Step Irons | VR705.11 | • Pits greater than 1.0m deep shall be fitted with step irons. Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions. | Each Lot | Visual / Pictures | SE/FM |  | NA
S | Shape of floor | VR705.12 | Pit floors shall be smoothly shaped from the inlet to the outlet for a height of 1/3 of the diameter of the outlet pipe. | Each Lot | Visual / Pictures | SE/FM |  | NA
W | Fitting of Covers | VR705.16 | • Frames for pit covers shall be cast into the top of the pit or bedded on fresh mortar, 5mm thick, consisting of 2 parts sand : 1 part cement and sufficient water. • Level at every point of the perimeter shall be within 10mm of the design level for that point, and the line of the cover shall be within 10mm of the design kerb line. | Each Lot | Visual / Pictures | SE/FM |  | NA
W | Backfilling | VR705.17 | • Backfilling around pits shall be placed in layers not exceeding 300mm loose thickness and compacted to refusal using hand held mechanical equipment. | Each Lot | Visual / Pictures Report | SE/FM |  | NA
S | **Other Contract Specific Requirements …….. | ITP
LOT CONFORMANCE
| Works completed on: | Date
All Hold Points released?
Yes
No
N/A
All Test Reports conforming?
Yes
No
N/A
NCR raised?
| Yes | NCR Number: | Drop List (From NCRs) | NCR Status: | Autogenerated from NCR Register
No
Lot Verified by:
List of Users
| Lot Verified on: | Date
| Comments: | Open text
| Date Submitted to Client: | Date

## ITC - Stormwater...
LOT DETAILS
| Internal Lot Number | Autogenerated
| External Lot Number (optional) | Open text
| Lot Description | Open text
| Lot Status | Drop List
|  | OPEN | [6 empty] | Lot Created but Work Has Not Been Commenced
|  | WORK IN PROGRESS | [6 empty] | Work Commenced and Continuing
|  | AWAITING HOLDPOINT | [6 empty] | Awaiting Hold Point Release
|  | AWAITING NCR | [6 empty] | Awaiting NCR Closure
|  | AWAITING TEST RESULT | [6 empty] | Awaiting Test Results Received
|  | OUTSTANDING | [6 empty] | Outstanding
|  | AWAITING VERIFICATION | [6 empty] | Awaiting Verification for Test Reports/QA Docs To Verified
|  | Submitted TO THE CLIENT | [6 empty] | Internally Closed
|  | CLOSED-OUT | [6 empty] | Externally Closed-out
|  | CANCELLED | [6 empty] | Cancelled
LOT INFORMATION
| Open date | Autogenerated
| Inspection Test Plan | Drop List
| Area | Drop List
| Zone | Drop List
| Discipline | Drop List
| Responsible Engineer | Drop List
| Work commenced on | Open Date
| Number of Underlier or Predecessor Lots | Open Number (0,1,2,#) | Lot 1 | Drop List --> Current Lots
|  |  | Lot 2 | Drop List --> Current Lots
|  |  | Lot # | Drop List --> Current Lots
INSPECTION TEST CHECKLITS | Drainage Pits
PRELIMINARIES | Design Issued for Construction | Yes / No / NA
| Drawings Issue for Construction | Yes / No / NA
| Material Hold Points Released | Yes / No / NA
| Survey Request | Yes / No / NA
| Traffic Management Plan Approved | Yes / No / NA
| Subcontractor/Provider approved? | Yes / No / NA
| Kick-off meeting (Subcontractor) | Yes / No / NA
CONSTRUCTION
HP (Hold Point): Work shall only proceed past the Hold Point once it is released by the organisation imposing it. WP (Witness Point): An inspection point that may be witnessed by the organisation imposing the Witness Point. I (Inspection): Formal inspection activity to be undertaken and recorded. S (Surveillance): An activity that is subject to ongoing monitoring. R (Review): Review reports/records or other evidence of compliance. | Activity or Description | Applicable Standard / Reference | Acceptance Criteria | Frequency | Verification Records | Action Respon. | Sign & Date WINSLOW | Sign & Date Superintendent
W | Safety; SWMS | HSMP | SMWS to be written for each activity on Project and shall be reviewed by a competent person. Submitted to the client …………..days prior to commencement of Activity. | Each Activity | Records | PE/SE |  | NA
W | Excavation Permit | OHS | DBYD information available on site, Permit to work- Services issued with assest protection Plan. All services identified located proved and protected. Spotter at location before commencement of excavation works (If required) | Each Lot | Records | PE/SE |  | NA
H | Environmental Controls | EMP | No work shall commence unless all erosion/ Sediment controls are implemented in accordance with EMP. | Each Activity | ECP | SE/FM |  | NA
W | Set out | 701.05 | Prior to commencement of excavation for the pipes the Contractor shall confirm the position of all pipes with the Superintendent after survey pegs have been installed | Each Lot | Visual / Pictures | FM & SR |  | NA
R | Excavation | VR701.10 | • Pipe culverts – the width of the trench at and below the level of the top of the pipe shall have a horizontal clearance of 300 – 600mm • The base of the trench shall be compacted • Soft, wet or unusable material at the base of the pipes should be treated or replaced | Each Lot | Visual / Pictures | SE/FM |  | NA
S | Culvert Bedding | VR701.11 | Depth of the layer of Compacted bedding material shall be: 100mm where pipe diameter is less than 1500mm 200mm where pipe diameter is greater than 1500mm Class of Bedding material……………………….. | Each Lot | Visual / Pictures | SE/FM |  | NA
W | Laying pipes. | VR701.12 | Class of Pipe……………. • Pipes – Rebate and socket ends of pipe shall be placed facing upstream. The lower portion of the pipe shall be in contact with the bedding for the full length of the section. (Pipes are free of cracks/ damage ) | Each Lot | Visual / Pictures | SE/FM |  | NA
I | Jointing | VR701.13 | Interlocking (Flash) Joint Pipes: Joint shall be mortar jointed, or wrapped with a 200mm wide external joint rubber band.Rubber band thickness shall not be less than 2mm. In case of internally jointed pipes 600 mm diameter and larger, the mortar shall be struck off flush with the bore of the pipe. Rubber ring Joint Points: Rubber ring joint pipes shall be jointed with rubber rings. Rubber rings shall be undisturbed clean and free from dirt. | Each Lot | Visual / Pictures | SE/FM |  | NA
I | Backfilling | VR701.12, & VR701.14 | Class of backfill material........................... Compaction Requirements......................... Depth of Layers..................... • Selected backfill material shall be placed for the full width of the bedding material to a height of 0.3m above the top of the culvert or subgrade level (whichever is lower) | Each Lot | Visual / Pictures | SE/FM |  | NA
I | Geotechnical Testing | VR701.15 | Minimum Testing Requirements ( per lot)…………... (1) Compaction Requirements……………... (2) Moisture Requirements………………. | Each Lot | Visual | SE/FM |  | NA
S | Grading & PI testing Frequency | VR701.23 Table 701.231 | Grading ………………. per tonnes or part thereof PI……………………….per tonnes or part thereof | Each Lot | Records | PE/SE |  | NA
NA
NA
NA
S | **Other Contract Specific Requirements …….. | ITP
LOT CONFORMANCE
| Works completed on: | Date
All Hold Points released?
Yes
No
N/A
All Test Reports conforming?
Yes
No
N/A
NCR raised?
| Yes | NCR Number: | Drop List (From NCRs) | NCR Status: | Autogenerated from NCR Register
No
Lot Verified by:
List of Users
| Lot Verified on: | Date
| Comments: | Open text
| Date Submitted to Client: | Date

## Discipline
Discipline | Discipline Title
ACC | Accounts
ADM | Administration
ARC | Architectural | ARC | Architectural
ASM | Asset Management
CIV | Civil - Other | CIV | Civil - Other
CMS | Commissioning
CMY | Community
CNS | Communications Systems
COM | Commercial
CON | Construction | CON | Construction
CSE | Comms and Stakeholder Engagement
CVD | Civil - Drainage | CVD | Civil - Drainage
CVE | Civil - Earthworks | CVE | Civil - Earthworks
CVP | Civil - Pavement | CVP | Civil - Pavement
CVR | Civil - Roads | CVR | Civil - Roads
DCC | Document Control
DES | Design
ELE | Electrical | ELE | Electrical
ENV | Environmental | ENV | Environmental
EST | Estimating
FIN | Finance
GEO | Geotechnical | GEO | Geotechnical
GOV | Governance
HER | Heritage
HRS | Human Resources
HSE | Health and Safety
HYD | Hydrology | HYD | Hydrology
IDR | Industrial Relations
IFM | Interface Management
LDE | Landscape | LDE | Landscape
LDP | Land Planning | LDP | Land Planning
LEG | Legal
MEC | Mechanical | MEC | Mechanical
MTC | Maintenance | MTC | Maintenance
PLN | Planning
PRM | Project Management
PRO | Procurement
QAC | Quality Assurance and Control
RAL | Rail
RSA | Road Safety Audit | RSA | Road Safety Audit
RSM | Risk Management
SBA | Structural - Barriers | SBA | Structural - Barriers
SBR | Structural - Bridges | SBR | Structural - Bridges
SCC | Structural - Concrete | SCC | Structural - Concrete
SNW | Structural - Noise Walls | SNW | Structural - Noise Walls
SRW | Structural - Retaining Wall | SRW | Structural - Retaining Wall
SST | Structural - Steel | SST | Structural - Steel
STR | Structural - Other | STR | Structural - Other
SUR | Survey | SUR | Survey
SUS | Sustainability
SUV | Surveillance | SUV | Surveillance
TFM | Traffic Management | TFM | Traffic Management
TML | Traffic Modelling | TML | Traffic Modelling
TPW | Temporary Works | TPW | Temporary Works
TSI | Traffic Signalling | TSI | Traffic Signalling
UBD | Urban Design | UBD | Urban Design
UTG | Utlities - Gas | UTG | Utlities - Gas
UTL | Utilities - Other | UTL | Utilities - Other
UTP | Utilities - Power | UTP | Utilities - Power
UTS | Utilities - Sewer | UTS | Utilities - Sewer
UTT | Utilities - Telecoms | UTT | Utilities - Telecoms
UTW | Utilities - Water | UTW | Utilities - Water

## Construction Element
Construction Element | Construction Element Title | Activity
EART | Earthwork | CLGR,CUFI,INSTA,PEFI,SEFI,TACAP,TACAPCEM,TACAPLIM,TAVER,TAVCEM,TAVLIM,TYPB,TBCEM,TBLIM,TYPC,UNMA
EMBA | Embankment | EBRW,GABW,NOIW,RETW,RSST,SOIN,SSCO
FOUN | Foundation | BORP,CAPB,CFAP,DRIP,PILC,SHEP
ITS | ITS | BEDD,BLUE,CONCF,COND,DATA,DETE,DIGI,ELECDC,ELUMS,FDS,FRS,ITS,LANE,OVER,RAMP,SIDE,STRE,TRAF,TRAV,VARI
LAND | Lanscaping | CULT,HARD,HYDR,MAIN,PLAN,RIPP,TOPS,WEED,WSRD
PAVE | Pavement | BASA,BAC1,BAC2,SUC3,SUC4,SCTCR,SCTCC
PAVI | Paving | COHS,COII,CONB,DDAT,FOOT,SHUP
ROAD | Road Furniture | BOLL,FENC,GUID,HAND,MARK,ROAD
SAFE | Safety Barrier | BOLL,CONCB,FENC,FWBE,FWPF,GRMS,GUAR,HAND,PCCO,RUBR,WRSB,WRSBAB,WRSBPF
SIGN | Sign & Pavement Marking | AUDI,LINE,RRPM,SIGN,SPF
SITE | Site General | DEMO,OTH,ROUT,SITE
STEE | Steel Structure | GANT,INST,PROC,SFWE
STOR | Stormwater | BADC,BEAC,BBSS,BCBS,BCPU,CATD,DRAB,DRAP,KERC,PIPC,RETB,SPIB,SPOD,SUSD,SWAD,TABD
SUBS | Substructure | ABUT,PIER,PIERH,PIPB,WINW
SUPE | Superstructure | ANCH,APPS,BEAP,BEAR,COBG,CONA,CONP,CONR,CROH,DECS,DIAPH,EXPJ,FENW,HAUN,OFSB,ONSB,PCCO,PCST,STBG,STEP,STER,SUTB,TOWE
SURF | Surfacing | ASWC,PRIS,SPRS
UTIL | Utility | FUEL,GAS,POWE,SEWA,TELE,WATE

## Activity
Activity | Activity Title
ABUT | Abutment
ANCH | Anchor
APPS | Approach Slab
ASWC | Asphalt Wearing Course
AUDI | Audio Tactile Lines
BAC1 | Base - Class 1
BAC2 | Base - Class 2
BADC | Batter Drain / Chute
BASA | Base - Asphalt
BBSS | BedBackfill STWATR Struct
BCBS | Box Culvert - Base Slab
BCPU | Box Culvert-Precast Units
BEAC | Beaching
BEAP | Bearing Pedestal
BEAR | Bearing
BEDD | Bedding and Backfill
BLUE | Bluetooth Data Stations
BOLL | Bollard
BORP | Bored Pile
CAPB | Capping Beam
CATD | Catch Drain
CFAP | CFA Pile
CLGR | Clearing and Grubbing
COBG | Concrete Beam / Girder
COHS | Concrete Hard Stand
COII | Concrete Infill/Island
CONA | Concrete Arch
CONB | Concrete Bay
CONCB | Concrete Barrier
CONCF | Concrete foundation
COND | Conduits / Pits
CONP | Concrete Post
CONR | Concrete Rail
CROH | Cross Head
CUFI | Cut and Fill
CULT | Cultivation
DATA | Data Communication Boxes
DDAT | DDA Tactile
DECS | Deck Slab
DEMO | Demob/House Keeping
DETE | Detection loop
DIAPH | Diaphragm
DIGI | Digital CCTV
DRAB | Drainage Blanket
DRAP | Drainage Pit
DRIP | Driven Pile
EBRW | Earthbackfill retainworks
ELECDC | Elec Distribution Cabinet
ELUMS | Elec Speed Limit Sign
EXPJ | Expansion Joint
FDS | Freeway Data Station
FENC | Fencing
FENW | Fender Wall
FOOT | Footpath
FRS | Freeway Ramp Signals
FUEL | Fuel/Oil
FWBE | Flexible W-Beam
FWPF | Flexible W-Beam PostFound
GABW | Gabion wall
GANT | Gantry
GAS | Gas
GRMS | Guardrail - Median Strip
GUAR | Guardrail
GUID | Guidepost
HAND | Handrails
HARD | Hardscaping
HAUN | Haunches
HYDR | Hydroseeding
INCL | Inclinometer Installation
INST | Installation
INSTA | Insitu Stabilisation
ITS | ITS Field Cabinets
KERC | Kerb and Channel
LANE | Lane Use Signs
LINE | Line Marking
MAIN | Maintenance
MARK | Marker Post
NOIW | Noise wall
OFSB | Off-structure Barrier
ONSB | On-structure Barrier
OTH | Other
OVER | OverHeight Detect Syst
PCCO | Protect coating concrete
PCST | Protective coating steel
PEFI | Permeable Fill
PIEH | Pier Head
PIER | Pier
PILC | Pile Cap
PIPB | Pier Protection Barrier
PIPC | Pipe Culvert
PLAN | Planting
POWE | Power
PRIS | Primer Seal
PROC | Protective coating
RAMP | Ramp ControlMeteringSigns
RETB | Retention Basins
RETW | Retaining wall
RIPP | Ripping
ROAD | Road Marking
ROUT | Routine Maintenance
RRPM | RRPM
RSST | Reinforced Soil Structure
RUBR | Rub-Rail/Bike Barrier
SCTCC | SubBase CTCC
SCTCR | SubBase CTCR
SEFI | Select Fill
SEWA | Sewage
SFWE | Steel fabrication/welding
SHEP | Sheet Pile
SHUP | Shared User Path
SIDE | Side Rd Activtd Speed Sys
SIGN | Sign
SITE | Site Establishment
SOIN | Soil Nail
SPF | Sign - Post foundation
SPIB | Spill Basin
SPOD | Spoon Drain
SPRS | Spray Seal
SSCO | Shotcrete/Sprayed Concret
STBG | Steel Beam / Girder
STEP | Steel Post
STER | Steel Rail
STRE | Street Lighting
SUC3 | SubBase - Class 3
SUC4 | SubBase - Class 4
SUSD | SubSurface Drainage
SUTB | Super T-beam
SWAD | Swale Drain
TABD | Table Drain
TACAP | TypeA Capping
TACAPCEM | TypeA Capping Cement Stab
TACAPLIM | TypeA Capping Lime Stab
TAVCEM | TypeA Verge Cement Stab
TAVER | TypeA Verge
TAVLIM | TypeA Verge Lime Stab
TBCEM | TypeB Cement Stabiliz
TBLIM | TypeB Lime Stabilization
TELE | Telecommunication
TOPS | Topsoil
TOWE | Tower
TRAF | Traffic Signals
TRAV | Travel Time Signs
TYPB | Type B
TYPC | Type C
UNMA | Unsuitable Material
VARI | VariableMessageSigns(VMS)
WATE | Water
WEED | Weed/Grass Management
WINW | Wing Wall
WRSB | WRSB
WRSBAB | WRSB - Anchor Block
WRSBPF | WRSB - Post Foundation
WSRD | WSRD

## Lot Type
LOT TYPE | DESCRIPTION | TARGET AFTER PWC (DAYS)
CIL | CIVIL LOT | 10
DRL | DRAINAGE LOT | 10
EAL | EARTHWORKS LOT | 10
ELL | ELECTRICAL LOT | 10
STL | STRUCTURAL LOT | 35
UTL | UTILITY LOT | 10

## Users
Responsible
Caelum Italia
Ifiyenia Papadopoulos
Keerthivasan Rathnasabapathy
Mohammad Zia
Pablo velasquez
Raman Kaur
Richardson Huynh
Sayyam Bindra
Sindhusri Nimmala
Zane El Mohamed
TBA