## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITC - Drainage Pit | itp |  |  |  | Yes | ITC - Drainage Pit | 4f94952e-2787-426f-a0fb-e44ba97fe38c
checkpoint-group |  |  | section | PRELIMINARIES
checkpoint-status |  |  | checkpoint | Design Issued for Construction
checkpoint-status |  |  | checkpoint | Drawings Issue for Construction
checkpoint-status |  |  | checkpoint | Material Hold Points Released
checkpoint-status |  |  | checkpoint | Survey Request
checkpoint-status |  |  | checkpoint | Traffic Management Plan Approved
checkpoint-status |  |  | checkpoint | Subcontractor/Provider approved?
checkpoint-status |  |  | checkpoint | Kick-off meeting (Subcontractor)
checkpoint-group |  |  | section | CONSTRUCTION
checkpoint-status |  |  | checkpoint | Safety; SWMS
label | 2c069adf-4821-5a45-943c-91bd3f3da84c |  | note | W
label | e0152f14-13b9-5112-a471-0cac2614eedd |  | note | Applicable Standard / Reference - HSMP
label | 5ce42bba-c891-52b7-889b-4bb0a50dd758 |  | note | Acceptance Criteria - SMWS to be written for each activity on Project and shall be reviewed by a competent person.
number | 27d4ed61-748a-504a-aa6f-d9b072f43468 |  | number | Submitted to the client |  |  | days prior to commencement of Activity.
label | 61580692-5546-539e-9d23-81328021af21 |  | note | Frequency - Each Activity
label | 8642d739-1db3-5f8f-b9a9-9caba849ecf3 |  | note | Verification Records - Records
label | 11ea7f75-7cde-5983-982c-45d38574fde9 |  | note | Action Respon. - PE/SE
date | 51cd4805-d0f1-553e-8827-cf07aeaff7a1 |  | date | Date:
checkpoint-status |  |  | checkpoint | Environmental Controls
label | 80551931-0635-541a-922f-4b51490b28c8 |  | note | W
label | 29202470-c8e1-579d-902a-55ba8ef651dc |  | note | Applicable Standard / Reference - EMP
label | 2e1ae175-4480-5694-876f-88555b7dd770 |  | note | Acceptance Criteria - No work shall commence unless all erosion/ Sediment controls are implemented in accordance with EMP.
label | 7550f321-aed3-5ddb-aeee-25a7b7e4ec49 |  | note | Frequency - Each Activity
label | 17168461-2183-5fb1-b418-588f523ec57b |  | note | Verification Records - ECP
label | 902e4ae2-ba5c-5e72-bc29-8149076bbc6a |  | note | Action Respon. - PE/SE
date | bd762d6a-fb97-5b0a-85c8-291d16ff6381 |  | date | Date:
checkpoint-status |  |  | checkpoint | Excavation Permit
label | 307a07ee-5883-5b62-ba3a-70b1f70993bc |  | note | H
label | b5dfd2d3-aad4-5e4f-9339-09a0a67ba802 |  | note | Applicable Standard / Reference - OHS
label | fbcb6396-9607-5a63-a05e-ad7923cd9fde |  | note | Acceptance Criteria - DBYD information available on site, Excavation permit issued and spotter at location before commencement of excavation works
label | e74b651e-7685-52e7-a2ee-a9ca13725078 |  | note | Frequency - Each Lot
label | acc9f7c8-4e27-5ac5-8904-0550424a717a |  | note | Verification Records - Records
label | 4173bb78-72a2-5e85-ba3c-24d152c74f48 |  | note | Action Respon. - PE/SE
date | f0a4b56e-dc66-5486-acf9-db65953fd434 |  | date | Date:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Manufacture Precast Documentation (QMP, ITPs,ITCs, Shop Drawings, Reports)
label | d127e527-1d31-50af-a192-83a6d58880d7 |  | note | W
label | e4eee257-3704-5f5e-a337-be4b0f2349e0 |  | note | Applicable Standard / Reference - ITP
label | aead8a78-6fc1-5124-974a-5e3c0f030d71 |  | note | Acceptance Criteria -
label | 36d8b662-5774-57dc-9b8d-2d825c655a3c |  | note | Frequency - For Each Manufacture
label | 7ba32e22-64df-525b-86fe-f6216f6c6b61 |  | note | Verification Records - Records
label | 87095faa-ad8b-5fdb-8aa9-56e9a0f2f3f4 |  | note | Action Respon. - PE/SE
date | c4316d42-694c-5d57-8925-58d2503b32dd |  | date | Date:
checkpoint-status |  |  | checkpoint | Delivery Dockets
label | 2ab792f9-a90a-5c7d-bc19-31dca2a22245 |  | note | R
label | b2d3e8a2-edc9-5bfd-ad41-859c26b3ab94 |  | note | Applicable Standard / Reference - ITP
label | d6f13cd5-e466-58c1-bf61-74ae3778495c |  | note | Acceptance Criteria - Delivery Docket for each Pit must be clearly identified and uploaded to the lot
label | 5aff589b-0bba-5a0e-8d66-c4b3514424a2 |  | note | Frequency - Each Pit
label | 5a98f8fc-e48b-55dc-a3cd-fea25ab101ff |  | note | Verification Records - Delivery Docket
label | d4415b4f-58ca-5207-aa71-97584e3710fe |  | note | Action Respon. - PE/SE
date | 60a7f091-073e-509b-a6d3-319913121f34 |  | date | Date:
checkpoint-status |  |  | checkpoint | Unit Identification (Pit number, other)
label | 7dab31a0-58bd-5563-bf2e-969013d3797f |  | note | S
label | 3d718021-2b1a-51c3-9096-3092ef6151bf |  | note | Applicable Standard / Reference - ITP
label | bd81b91b-0d9a-5eee-b305-227f379b6b73 |  | note | Acceptance Criteria - Pit Unit Identification must be visible after installation for further identification
label | 66d611e9-1a5c-535b-9ae2-071508226db4 |  | note | Frequency - Each Pit
label | fef79108-3e9b-55a2-9552-b1a334842d31 |  | note | Verification Records - Picture
label | a0951f6e-e868-55f6-9d64-d60f848f3b8d |  | note | Action Respon. - PE/SE
date | ce3e3bcc-c3b5-536c-8f06-1c00e75c0e31 |  | date | Date:
checkpoint-status |  |  | checkpoint | Materials
label | da962fd8-e879-50fc-b0f0-664c061e3c47 |  | note | W
label | 9ce49f24-cf2a-5a82-9b81-d89dd16cc432 |  | note | Applicable Standard / Reference - VR705.04 (c) & (d)
label | 24dfc8b2-8ab9-5aff-9248-16e84d34a552 |  | note | Acceptance Criteria - Concrete - Shall be N32 standard strength grade?
label | 52dc7ff4-71a0-53b1-8873-a19fe3a96da8 |  | note | ○ Covers, Lids, Grates, Lintels as shown on drawings
label | 56a9ffe2-d274-58ae-995d-cc07d7123853 |  | note | ○ Step Irons - Those manufactured from 13mm steel bar covered with polypropylene plastic must be approved by superintendent
label | f1aae10d-9079-5023-8aef-784b4084c34e |  | note | Frequency - Once
label | c3274c1e-a0b3-5386-83c9-a89aa3da0b40 |  | note | Verification Records - Records
label | 13d4a3ea-ce5d-5b2c-bfaa-5389f1adf6d7 |  | note | Action Respon. - PE/SE
date | 4a1c36dd-07eb-5167-a8e5-7c563d1c4eac |  | date | Date:
checkpoint-status |  |  | checkpoint | Excavation - Precast Pits
label | c17fcd2a-b755-52f8-809d-28d30fe57a7f |  | note | I
label | 123bd835-70ac-5fa0-811e-a7940011611e |  | note | Applicable Standard / Reference - VR705.05 (b)
label | 3c4c7a69-63f7-5f61-b312-e3ad1774efd3 |  | note | Acceptance Criteria - Clearance from all external faces of the pit to each face of the excavation shall be not less than 400mm.
label | 014dce96-92f5-5fe5-bf62-f9f926b24429 |  | note | ○ Bedding shall be supplied, placed and compacted to a thickness not less than 80mm on a clay foundation or 150mm on a rock foundation.
label | d3fc06b1-e29d-56d7-be20-7d6a96f9ddb3 |  | note | Frequency - Each Lot
label | d4c8f312-9a21-5134-870b-0e87d31fe43e |  | note | Verification Records - Visual / Pictures
label | 7d82ca6f-a303-5d35-9bae-92baa3490494 |  | note | Action Respon. - SE/FM
date | ebaa179e-e15b-5546-b5f5-fd816a0f9708 |  | date | Date:
checkpoint-status |  |  | checkpoint | Precast Pits
label | d9641a04-4e01-5bc3-918f-7ab7e3e56a41 |  | note | I
label | 960fc058-f56e-59cd-897c-cf800f40cba3 |  | note | Applicable Standard / Reference - VR705.09
label | bdb71d8b-78cc-55b2-8e79-a01c84a162b2 |  | note | Acceptance Criteria - Holes for subsurface drains should be 150mm unless specified otherwise.
label | ce817e3f-59e6-5762-90f1-141afaf82c0d |  | note | ○ Weepholes of 50mm shall be provided in all precast pits (see spec for location)
label | 94ecf57a-277e-5331-8552-ebcc41360472 |  | note | ○ Segmented pits require a minimum 15mm rebate.
label | 943a07ff-7cb5-5028-b6b4-9c2e4ccd61bd |  | note | Frequency - Each Lot
label | 0d0b1935-7237-5dfa-b7cc-f9ac6f93a447 |  | note | Verification Records - Visual / Pictures
label | 209bb861-d467-51b6-bb0a-a62b1b867c82 |  | note | Action Respon. - SE/FM
date | 08b97539-f4a6-527f-a629-6a483c0db007 |  | date | Date:
checkpoint-status |  |  | checkpoint | Stormwater drainage connections
label | b56a471f-b01f-5e80-843c-155cb762d2b4 |  | note | I
label | 97adef71-02a2-58ff-ab2a-14763ed1db7e |  | note | Applicable Standard / Reference - VR705.1
label | 672dd232-0204-5e6b-a302-74db46a09d9d |  | note | Acceptance Criteria - All stormwater drainage connections to pits shall be neatly made, and where necessary the ends of all drains shall be trimmed off and finished with cement mortar.
label | d9cb8af3-e6b2-581a-be72-d03c673a2bca |  | note | Frequency - Each Lot
label | 16545276-d7cc-5ed8-b814-d2c797d0a18d |  | note | Verification Records - Visual / Pictures
label | 78bab2cb-9565-539c-b6f9-68aa7b809c2e |  | note | Action Respon. - SE/FM
date | d1b7e5c1-2383-57d0-9c3e-18fcd1e90b61 |  | date | Date:
checkpoint-status |  |  | checkpoint | Step Irons
label | a9c8323b-9999-56db-a8cd-1aeb5b744d06 |  | note | S
label | 2f905ae1-ab2f-5579-82ca-ce3b465407e6 |  | note | Applicable Standard / Reference - VR705.11
label | c0c07bd6-7465-5445-b784-5ba519a5d70d |  | note | Acceptance Criteria - Pits greater than 1.0m deep shall be fitted with step irons. Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
label | 5c06b7c4-6346-5616-9ee8-7f52e7a4672e |  | note | Frequency - Each Lot
label | 3afef1fe-8453-5222-a173-90f12afbf1a7 |  | note | Verification Records - Visual / Pictures
label | 5067be92-5a16-56f8-90c9-4fe255220a92 |  | note | Action Respon. - SE/FM
date | 40a4ae72-dda1-563a-85f3-138414c25b80 |  | date | Date:
checkpoint-status |  |  | checkpoint | Shape of floor
label | ba6dac60-267a-5043-8496-7e4b2511624b |  | note | S
label | ec8e364a-9acb-52f1-9165-0d19deb778d0 |  | note | Applicable Standard / Reference - VR705.12
label | 54ac72cd-b7b3-5f4e-bd0a-de78f09111be |  | note | Acceptance Criteria - Pit floors shall be smoothly shaped from the inlet to the outlet for a height of 1/3 of the diameter of the outlet pipe.
label | a41a6b4a-2f64-55ec-a559-65c0a8d365c0 |  | note | Frequency - Each Lot
label | 7fc3780e-94e9-5cd3-9a2c-6791b56e2177 |  | note | Verification Records - Visual / Pictures
label | 8e03bee5-ee11-56f0-8c51-b701bc7206a0 |  | note | Action Respon. - SE/FM
date | 8f6c4360-bebb-537b-891e-8266b10f968e |  | date | Date:
checkpoint-status |  |  | checkpoint | Fitting of Covers
label | 98191ba8-4110-5056-9857-a3a91c5d2174 |  | note | W
label | 8fedd045-5a26-5c09-be4a-94efd7015b48 |  | note | Applicable Standard / Reference - VR705.16
label | 31d8660f-fae1-5568-aee1-1678a3f997d0 |  | note | Acceptance Criteria - Frames for pit covers shall be cast into the top of the pit or bedded on fresh mortar, 5mm thick, consisting of 2 parts sand : 1 part cement and sufficient water.
label | a2aefe78-ca18-5c43-bd1c-595dabcb5b17 |  | note | ○ Level at every point of the perimeter shall be within 10mm of the design level for that point, and the line of the cover shall be within 10mm of the design kerb line.
label | b149d308-f6d1-5950-90e2-c112ba29fed9 |  | note | Frequency - Each Lot
label | 9b78c086-28f3-5cff-b891-85657a78ec59 |  | note | Verification Records - Visual / Pictures
label | da898b63-004a-5b05-a224-c6a5e692844c |  | note | Action Respon. - SE/FM
date | 7b25ce15-2272-56e7-aebe-2a35703bde25 |  | date | Date:
checkpoint-status |  |  | checkpoint | Backfilling
label | b61f7017-6266-5550-8d6b-a9440f979ac6 |  | note | W
label | 6b54ad02-c68b-537b-b571-dcdc5aa7254b |  | note | Applicable Standard / Reference - VR705.17
label | 55be80bf-2fce-53f9-8595-4d8be631db14 |  | note | Acceptance Criteria - Backfilling around pits shall be placed in layers not exceeding 300mm loose thickness and compacted to refusal using hand held mechanical equipment.
label | 28709efc-0325-5aab-a0c5-319a5b65ac34 |  | note | Frequency - Each Lot
label | 2187e4ed-cdd7-5095-9504-e3b7f5765b37 |  | note | Verification Records - Visual / Pictures, Report
label | 0cd24154-ca2d-59bb-b6a4-878da10573fe |  | note | Action Respon. - SE/FM
date | 8bce5a67-6f71-5c4a-9a4f-f7f4f3bc38ab |  | date | Date:
checkpoint-status |  |  | checkpoint | Other Contract Specific Requirements
text | fa20320f-8e26-5628-951e-44f6255c376e |  | textbox | Requirement(s):
label | cbff3bf2-7fdb-522f-955b-e735bf3cf1c8 |  | note | S
label | 818d4b31-fdf6-5270-af41-caab567066c1 |  | note | Applicable Standard / Reference - ITP
date | 7ff5d18d-fc55-583b-83e3-b3544ca74a6b |  | date | Date:
checklist-sectioned |  |  | checklist | ITC - Stormwater | itp |  |  |  | Yes | ITC - Stormwater | e391f158-d34a-4f46-a49a-61bd4e44d5bf
checkpoint-group |  |  | section | PRELIMINARIES
checkpoint-status |  |  | checkpoint | Design Issued for Construction
checkpoint-status |  |  | checkpoint | Drawings Issue for Construction
checkpoint-status |  |  | checkpoint | Material Hold Points Released
checkpoint-status |  |  | checkpoint | Survey Request
checkpoint-status |  |  | checkpoint | Traffic Management Plan Approved
checkpoint-status |  |  | checkpoint | Subcontractor/Provider approved?
checkpoint-status |  |  | checkpoint | Kick-off meeting (Subcontractor)
checkpoint-group |  |  | section | CONSTRUCTION
checkpoint-status |  |  | checkpoint | Safety; SWMS
label | 78a9b5e6-63bc-59d5-b832-7883d2567945 |  | note | W
label | 422fc738-68c2-5998-b9ef-78031387c615 |  | note | Applicable Standard / Reference - HSMP
label | 72705fe4-9038-5d29-a861-9626004173db |  | note | Acceptance Criteria - SMWS to be written for each activity on Project and shall be reviewed by a competent person.
number | 168f2033-652f-5f13-85a7-b16daccb8c3f |  | number | Submitted to the client |  |  | days prior to commencement of Activity.
label | 2871f53d-9a07-57e8-b2e5-30e198d6274e |  | note | Frequency - Each Activity
label | fd28c72d-2a94-5aab-be49-ee17fdccc319 |  | note | Verification Records - Records
label | 08c72f95-8694-55b3-bc59-ff9d667b687c |  | note | Action Respon. - PE/SE
date | 32835a4d-358b-5793-8603-7c74e5eea4b3 |  | date | Date:
checkpoint-status |  |  | checkpoint | Excavation Permit
label | 33d157a5-b65a-576a-a3cc-4736bf3be132 |  | note | W
label | 8146097f-8c23-54ba-afa8-821ffc7bfb09 |  | note | Applicable Standard / Reference - OHS
label | d3f530ed-b80c-5cf8-9b5e-23184b4ac02d |  | note | Acceptance Criteria - DBYD information available on site, Permit to work- Services issued with assest protection Plan. All services identified located proved and protected. Spotter at location before commencement of excavation works (If required)
label | 525d0c92-3b73-5946-a075-472db6279d9b |  | note | Frequency - Each Lot
label | 77b818d5-acf7-5cec-ba53-d138228ff788 |  | note | Verification Records - Records
label | 47927645-65d4-5fa5-97a0-9506a39da422 |  | note | Action Respon. - PE/SE
date | 79e32103-c76d-532c-ba66-3909bad67b29 |  | date | Date:
checkpoint-status |  |  | checkpoint | Environmental Controls
label | 75eda769-b0c0-54d9-8435-c19d3dc607a6 |  | note | H
label | 7a6eb439-fb57-5ba3-9868-ea96ffe1a4f6 |  | note | Applicable Standard / Reference - EMP
label | 31ef4e80-7f29-5f1d-ad8d-ea7c34b2b9ad |  | note | Acceptance Criteria - No work shall commence unless all erosion/ Sediment controls are implemented in accordance with EMP.
label | cceab05f-0931-5813-9eea-1d45e8129055 |  | note | Frequency - Each Activity
label | b8d5e4c3-629f-5180-9409-0fe9a3b048b3 |  | note | Verification Records - ECP
label | 1e1b0a23-ce71-51ad-98a1-385842568358 |  | note | Action Respon. - SE/FM
date | 2a42719f-e1cc-59c0-9e9c-e470f293628a |  | date | Date:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Set out
label | 6ea064a2-ad0f-52a2-bb74-4c333c1bd825 |  | note | W
label | 716a24b4-17e5-5eca-9552-4e44de7d9d22 |  | note | Applicable Standard / Reference - 701.05
label | 00257bb2-a2d4-5e5b-aaeb-99db92d4db37 |  | note | Acceptance Criteria - Prior to commencement of excavation for the pipes the Contractor shall confirm the position of all pipes with the Superintendent after survey pegs have been installed
label | 8633ab63-2d97-5386-acb2-31fc93d25fd7 |  | note | Frequency - Each Lot
label | 040f35e7-5f57-5bad-a29e-74e21b30912f |  | note | Verification Records - Visual / Pictures
label | 4e7893ed-94a9-5223-8752-cb694ab4f84f |  | note | Action Respon. - FM & SR
date | d6f26f34-b60e-531a-87c5-52f471e978e6 |  | date | Date:
checkpoint-status |  |  | checkpoint | Excavation
label | 2504d5ed-1b77-54c1-91c0-f57377c7fcbe |  | note | R
label | be93cf52-8c18-5498-944f-c3bc2fa5795d |  | note | Applicable Standard / Reference - VR701.10
label | 75528324-a40b-5dae-9e93-3fbead017781 |  | note | Acceptance Criteria - Pipe culverts – the width of the trench at and below the level of the top of the pipe shall have a horizontal clearance of 300 – 600mm
label | 6e2431fc-0ab2-557b-a329-2117c40367e7 |  | note | ○ The base of the trench shall be compacted
label | dd0bb5fe-c692-5f98-8722-b845737c55b5 |  | note | ○ Soft, wet or unusable material at the base of the pipes should be treated or replaced
label | dfaf06bf-b723-52cd-b4ee-fd8ef28e3990 |  | note | Frequency - Each Lot
label | 607c93f7-d8a5-50ec-a6e9-a5b16fb9d9c7 |  | note | Verification Records - Visual / Pictures
label | f9348d77-e372-5fb4-9f91-21004a722a1d |  | note | Action Respon. - SE/FM
date | bb966822-616a-5856-a3c4-6c607a96233a |  | date | Date:
checkpoint-status |  |  | checkpoint | Culvert Bedding
label | 656dc617-d38e-510d-b1fd-14e101084fc7 |  | note | S
label | 0a6cccb5-dfb5-5ff9-8e47-45e128322c64 |  | note | Applicable Standard / Reference - VR701.11
label | 2a95be13-9aea-5576-ac37-337e64ba7968 |  | note | Acceptance Criteria - Depth of the layer of Compacted bedding material shall be:
label | f726877c-d691-5280-bb7e-8cf824ab67e6 |  | note | ○ 100mm where pipe diameter is less than 1500mm
label | 2772fca0-9ddb-541e-8211-3f44d7751991 |  | note | ○ 200mm where pipe diameter is greater than 1500mm
text | 7138ca48-50a5-54d1-be95-488ad4deefd5 |  | textbox | ○ Class of Bedding material
label | 675ff2c8-13b9-5187-840c-3da3131206a4 |  | note | Frequency - Each Lot
label | b6fb5af2-7ba2-577e-a884-612378da4e54 |  | note | Verification Records - Visual / Pictures
label | 9dc22adb-8932-55e6-84a2-a14a9dde51f8 |  | note | Action Respon. - SE/FM
date | 0bdc5fba-f3c1-5ba1-a95b-f41df34849f3 |  | date | Date:
checkpoint-status |  |  | checkpoint | Laying pipes.
label | cc8067ce-c969-5209-9de2-6395ba6b9d80 |  | note | W
label | b38582bb-11e9-5eaf-b0af-d335f7e820c4 |  | note | Applicable Standard / Reference - VR701.12
label | a664ceea-4b04-5e9e-bfac-a9811fa05ebc |  | note | Acceptance Criteria -
text | e42e39f6-d7e0-5fbb-a9ba-1d25e8c8bdf4 |  | textbox | ○ Class of Pipe
label | 1d08a40f-9d01-52a0-b340-d79118830d1e |  | note | ○ Pipes – Rebate and socket ends of pipe shall be placed facing upstream. The lower portion of the pipe shall be in contact with the bedding for the full length of the section. (Pipes are free of cracks/ damage )
label | f179473c-7033-53f4-bf2a-8a686a7b1124 |  | note | Frequency - Each Lot
label | 7ad8db78-0a4e-5f70-9849-0e56e42d60b8 |  | note | Verification Records - Visual / Pictures
label | 66695aba-743d-53d6-a3c3-cd3b8e1ea63a |  | note | Action Respon. - SE/FM
date | a51dacad-6a9f-5312-92d3-36fb2420475f |  | date | Date:
checkpoint-status |  |  | checkpoint | Jointing
label | 28d7c87f-3e15-5387-aeb6-ef81065ec725 |  | note | I
label | 1e3c3521-1f91-59c1-a276-ce31bee5e5fe |  | note | Applicable Standard / Reference - VR701.13
label | 6a547411-852b-5521-9a1d-c39822045bad |  | note | Acceptance Criteria - Interlocking (Flash) Joint Pipes:
label | 755299c4-6771-5234-9eba-77bcaf3f973e |  | note | ○ Joint shall be mortar jointed, or wrapped with a 200mm wide external joint rubber band.Rubber band thickness shall not be less than 2mm. In case of internally jointed pipes 600 mm diameter and larger, the mortar shall be struck off flush with the bore of the pipe.
label | 107459fb-ef62-5747-a1e0-5aea78ea465e |  | note | Rubber ring Joint Points:
label | d5502773-9662-58de-bed4-5b11d26cd970 |  | note | ○ Rubber ring joint pipes shall be jointed with rubber rings. Rubber rings shall be undisturbed clean and free from dirt.
label | b3efe0e5-17ba-5002-949f-959092318e0b |  | note | Frequency - Each Lot
label | b89b6734-ed78-5287-b44c-31550f2e700e |  | note | Verification Records - Visual / Pictures
label | 1e0022f8-7ae8-5426-9525-66e971985cce |  | note | Action Respon. - SE/FM
date | cd7d9f7e-cbbe-51a9-b99f-a88e04428a30 |  | date | Date:
checkpoint-status |  |  | checkpoint | Backfilling
label | bd9de219-be7a-560d-b5fa-7ddd3d66aecf |  | note | I
label | 2e4c77f2-6aa5-5d24-bad6-f537125ff72c |  | note | Applicable Standard / Reference - VR701.12, & VR701.14
label | 411621d1-eb99-5b5d-97a1-6c8bc2ae7dc9 |  | note | Acceptance Criteria -
text | 2ec305dd-0c7e-5d6f-af38-26ef4a731439 |  | textbox | ○ Class of backfill material
text | 6be0dbe1-a1ca-5752-840a-9091eb0073a1 |  | textbox | ○ Compaction Requirements
text | e06ff60d-d297-5d0b-90d7-6d3ba05d5660 |  | textbox | ○ Depth of Layers
label | ad161e71-1654-5100-9069-7a161ec3f7b1 |  | note | ○ Selected backfill material shall be placed for the full width of the bedding material to a height of 0.3m above the top of the culvert or subgrade level (whichever is lower)
label | e8db5b9b-e0e3-5b1f-919c-8ed9c0b0e892 |  | note | Frequency - Each Lot
label | 2493e2de-4a47-52f2-8d30-9dead65a01b1 |  | note | Verification Records - Visual / Pictures
label | f09e4260-484e-536d-9ab1-cd7ecaf196c9 |  | note | Action Respon. - SE/FM
date | 0fa6ffd0-a4a2-51d5-9231-4b6bce7e163f |  | date | Date:
checkpoint-status |  |  | checkpoint | Geotechnical Testing
label | da9fd1fc-befc-52aa-a636-3fdd4321fbbf |  | note | I
label | 2043ac61-9bcc-504d-84a2-e46f3d4e69ad |  | note | Applicable Standard / Reference - VR701.15
label | 56cf0eed-cc07-5748-8a4d-d39c55f4f2e2 |  | note | Acceptance Criteria -
text | d2526c1b-078f-5493-ba55-cfb04440a71d |  | textbox | Minimum Testing Requirements (per lot)
text | 314632e8-6163-5a87-ae90-bae8a087fcd4 |  | textbox | (1) Compaction Requirements
text | 32818d97-faad-59e2-8cd8-21d42cc6d9fb |  | textbox | (2) Moisture Requirements
label | 0d3d9fae-4329-5edb-b023-b55cf8237c89 |  | note | Frequency - Each Lot
label | 3eb2e335-0b86-51f2-837b-29b2ec22b948 |  | note | Verification Records - Visual
label | febbbf63-0cee-5804-b7e5-29daf288854e |  | note | Action Respon. - SE/FM
date | 47c8fc8c-1560-50f5-bb51-62423ff10848 |  | date | Date:
checkpoint-status |  |  | checkpoint | Grading & PI testing Frequency
label | 42d67e0a-1e5b-53ee-9a82-b6ec5e377ea8 |  | note | S
label | e5817e3b-0e71-565a-942e-14502174413e |  | note | Applicable Standard / Reference - VR701.23 Table 701.231
label | 993af202-e58d-5a85-a62c-2fa3e2b7092c |  | note | Acceptance Criteria -
text | 1b250045-57d2-56f3-ae23-0cbe945ef570 |  | textbox | Grading |  |  | per tonnes or part thereof
text | 9fe21bf9-7c07-51b9-8807-757b2930b3c9 |  | textbox | PI |  |  | per tonnes or part thereof
label | c2f0781b-60e3-5b71-99ad-474a2ea3f99c |  | note | Frequency - Each Lot
label | e16ff615-c009-52bb-8af9-77bb42fa906e |  | note | Verification Records - Records
label | 0c212114-7e14-5eea-a8a7-c25c26c5363a |  | note | Action Respon. - PE/SE
date | 48a5d5f2-6cc3-5f7e-b725-6a199bdc17d5 |  | date | Date:
checkpoint-status |  |  | checkpoint | Other Contract Specific Requirements
text | 535aa0d1-7c74-580f-ae3f-a9478fc339a5 |  | textbox | Requirement(s):
label | 25094c70-5c7c-5748-9dd6-9312726698e6 |  | note | S
label | 08d9bfe8-7df2-5714-b977-70548ca9c4f9 |  | note | Applicable Standard / Reference - ITP
date | 8f926f83-cfb2-5a40-b079-4f624fc595c6 |  | date | Date:
checklist-flat |  |  | checklist | NCR No: |  |  |  |  | Yes | NCR Checklist | f0704521-0eed-41a3-894d-64c7a2cc0f72
checkpoint-status |  |  | checkpoint | Non Conformance Report
text | a6579d74-50f0-5b0c-9053-4fa6c346ad52 |  | textbox | Lot Number
boolean | 491a55cf-aa1d-567c-ac68-0b1fd615a30f |  | tickbox | Operational
boolean | 7e5ad9d5-1c1f-59b4-bab3-a4fdf1d7018a |  | tickbox | Procedural
boolean | df55adf1-8c91-5618-905e-739290148913 |  | tickbox | Material
select | 093c16e5-b914-5ef9-b030-cdaa1528b656 |  | dropdown | NCR raised as result of: | Inspection & Testing, Co's NC Product, Suppliers NC Product, Customer Complaint, Audit
text | 52bd8673-a599-5f8e-b28c-0a410c7959c9 |  | textbox | Non Conformance Details
date | f87d50dd-b43c-5db7-8e41-56fac938515a |  | date | Approval Date
select | 68eb3b08-fec9-59fc-8cf0-6efcdf1ff742 |  | dropdown | Proposed Method of Disposition to Non - Conformance | Accept as it is, Accept with Concession, Rework or Repair, Reject & Replace, Return to Supplier, Regrade for other use
text | 01a4c3ef-b34a-52f3-bbd8-dc7f32049651 |  | textbox | Details of Disposition
select | 277c0a6a-c8df-5653-8636-38d45cc52b75 |  | dropdown | Customer/Client Approval | Required, Not Required
date | e4001a7c-3fff-5fd3-918f-4cf9357ffab3 |  | date | Disposition Completed On
text | 52da77a7-217f-5967-b0af-55d41801a0c3 |  | textbox | Completed By
date | 91814999-c2b3-5c43-95af-7dd99597d677 |  | date | Dispoition Approved On
date | 1d14c73a-6eed-5f37-8410-698abd8220fd |  | date | Date NCR Closed
text | 848847e6-8ba9-541c-adc5-5428edb2ac46 |  | textbox | Closed By
select | 2b538ff0-4ea6-5fb2-b8dd-9febf4e9a288 |  | dropdown | Corrective Action | Required, Not Required
select | c00fff82-5a25-58fb-a246-e693a8ddfc6b |  | dropdown | Preventative Action | Required, Not Required
text | a93dfa0b-ed20-5fd4-87af-2bd8b8c99db7 |  | textbox | Details of CA/PA taken if required:
date | 468f9164-522a-5c4b-b939-c33b71432c24 |  | date | CA/PA Closed
text | fba489c0-7318-54f1-a4cc-6d2253d09f6a |  | textbox | Closed By
holdpoint |  |  | signoff | NCR Sign Off