## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITC - Type C Earthworks | itp |  |  |  |  | ITC - Type C Earthworks
section | PRELIMINARIES
checkpoint | Design Issued for Construction
checkpoint | Drawings Issue for Construction
checkpoint | Material Hold Points Released
checkpoint | Survey Request
checkpoint | Traffic Management Plan Approved
checkpoint | Subcontractor/Provider approved?
checkpoint | Kick-off meeting (Subcontractor)
section | CONSTRUCTION
checkpoint | Safety; SWMS
label | Applicable Standard / Reference - HSMP
label | Acceptance Criteria - SMWS to be written for each activity on Project and shall be reviewed by a competent person.
number | Submitted to the client |  |  | days prior to commencement of Activity.
label | Frequency - Each Activity
label | Verification Records - Records
label | Action Respon. - PE/SE
date | Date:
checkpoint | Environmental Controls
label | Applicable Standard / Reference - EMP
label | Acceptance Criteria - No work shall commence unless all erosion/ Sediment controls are implemented in accordance with EMP.
label | Frequency - Each Activity
label | Verification Records - ECP
label | Action Respon. - PE/SE
date | Date:
checkpoint | Excavation Permit
label | Applicable Standard / Reference - OHS
label | Acceptance Criteria - DBYD information available on site, Excavation permit issued and spotter at location before commencement of excavation works
label | Frequency - Each Lot
label | Verification Records - Records
label | Action Respon. - PE/SE
date | Date:
checkpoint | Survey Control
label | Applicable Standard / Reference - VR204.03 (a), (b, c)
label | Acceptance Criteria - All Earthworks shall be finished to conform to the levels, lines, grades and cross sections showed in the plans.
label | Frequency - Each Lot
label | Verification Records - Setout
label | Action Respon. - Surveyor
date | Date:
checkpoint | Material - Type C
label | HP
label | Applicable Standard / Reference - VR204.04 (b)
label | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type C material unless otherwise approved by the Superintendent.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - FM
date | Date:
holdpoint | HOLD POINT
checkpoint | Site excavation - material category
label | HP
label | Applicable Standard / Reference - VR204.06 (b)
label | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - FM
date | Date:
holdpoint | HOLD POINT
checkpoint | Earthworks - Groundwater Seepage
label | HP
label | Applicable Standard / Reference - VR204.06 (h)
label | Acceptance Criteria - Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - PE/SE
date | Date:
holdpoint | HOLD POINT
checkpoint | Earthworks - treatment of Unsuitable Material
label | HP
label | Applicable Standard / Reference - VR204.07 (d)
label | Acceptance Criteria - Where unsuitable material is encountered the Contractor shall submit the proposed in situ treatment or extent of excavation to the Superintendent for review.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - FM
date | Date:
holdpoint | HOLD POINT
checkpoint | Earthworks - Fill construction
label | HP
label | Applicable Standard / Reference - VR204.10 (b)
label | Acceptance Criteria - The Contractor shall not commence placing of any fill on the prepared surface until the area has been reviewed by the Superintendent.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - FM
date | Date:
holdpoint | HOLD POINT
checkpoint | Earthworks - Fill at Structures (wing walls, culverts >1200mm)
label | HP
label | Applicable Standard / Reference - VR204.11 (b)
label | Acceptance Criteria - No fill shall be placed against or within 3m of a structure until the foundation for the fill has been reviewed by the Superintendent.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - FM
date | Date:
holdpoint | HOLD POINT
checkpoint | Test Rolling
label | Applicable Standard / Reference - VR173.03, VR204.12
label | Acceptance Criteria - Undertake test roll prior to placement of fill/or proceeding layer.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - FM
date | Date:
checkpoint | Compaction - Lot size
label | Applicable Standard / Reference - VR204.13
label | Acceptance Criteria - Type C: 10,000m2 or one day's production, whichever is the lesser
label | Frequency - Each Lot
label | Verification Records - Records
label | Action Respon. - PE/SE
date | Date:
checkpoint | Compaction
label | Applicable Standard / Reference - VR204.13 (b), VR204.14
label | Acceptance Criteria - Compaction
label | ○ All Type C material should conform to 95% of a standard density
label | ○ Max. particle size <100mm (visual inspection)
label | Frequency - 1 test per each 6 lots
label | Verification Records - Records/Visual
label | Action Respon. - FM
date | Date:
checkpoint | Other Contract Specific Requirements
textbox | Requirement(s):
date | Date:
checklist | ITC - Type B Earthworks | itp |  |  |  |  | ITC - Type B Earthworks
section | PRELIMINARIES
checkpoint | Design Issued for Construction
checkpoint | Drawings Issue for Construction
checkpoint | Material Hold Points Released
checkpoint | Survey Request
checkpoint | Traffic Management Plan Approved
checkpoint | Subcontractor/Provider approved?
checkpoint | Kick-off meeting (Subcontractor)
section | CONSTRUCTION
checkpoint | Safety; SWMS
label | Applicable Standard / Reference - HSMP
label | Acceptance Criteria - SMWS to be written for each activity on Project and shall be reviewed by a competent person.
number | Submitted to the client |  |  | days prior to commencement of Activity.
label | Frequency - Each Activity
label | Verification Records - Records
label | Action Respon. - PE/SE
date | Date:
checkpoint | Environmental Controls
label | Applicable Standard / Reference - EMP
label | Acceptance Criteria - No work shall commence unless all erosion/ Sediment controls are implemented in accordance with EMP.
label | Frequency - Each Activity
label | Verification Records - ECP
label | Action Respon. - PE/SE
date | Date:
checkpoint | Excavation Permit
label | Applicable Standard / Reference - OHS
label | Acceptance Criteria - DBYD information available on site, Excavation permit issued and spotter at location before commencement of excavation works
label | Frequency - Each Lot
label | Verification Records - Records
label | Action Respon. - PE/SE
date | Date:
checkpoint | Survey Control
label | Applicable Standard / Reference - VR204.03 (a), (b, c)
label | Acceptance Criteria - All Earthworks shall be finished to conform to the levels, lines, grades and cross sections showed in the plans.
label | Frequency - Each Lot
label | Verification Records - Setout
label | Action Respon. - Surveyor
date | Date:
checkpoint | Material - Type B
label | HP
label | Applicable Standard / Reference - VR204.04 (b)
label | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type B material unless otherwise approved by the Superintendent.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - FM
date | Date:
holdpoint | HOLD POINT
checkpoint | Site excavation - cutting floor
label | Applicable Standard / Reference - VR204.03 (f)
label | Acceptance Criteria - The level at any point on the surface of the Cut Floor Level immediately below capping and/or selected material shall not differ by more than 15 mm above or 30 mm below the specified level.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - FM
date | Date:
checkpoint | Site excavation - material category
label | HP
label | Applicable Standard / Reference - VR204.06 (b)
label | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - FM
date | Date:
holdpoint | HOLD POINT
checkpoint | Earthworks - Groundwater Seepage
label | HP
label | Applicable Standard / Reference - VR204.06 (h)
label | Acceptance Criteria - Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - PE/SE
date | Date:
holdpoint | HOLD POINT
checkpoint | Earthworks - treatment of Unsuitable Material
label | HP
label | Applicable Standard / Reference - VR204.07 (d)
label | Acceptance Criteria - Where unsuitable material is encountered the Contractor shall submit the proposed in situ treatment or extent of excavation to the Superintendent for review.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - FM
date | Date:
holdpoint | HOLD POINT
checkpoint | Earthworks - Fill construction
label | HP
label | Applicable Standard / Reference - VR204.10 (b)
label | Acceptance Criteria - The Contractor shall not commence placing of any fill on the prepared surface until the area has been reviewed by the Superintendent.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - FM
date | Date:
holdpoint | HOLD POINT
checkpoint | Earthworks - Fill at Structures (wing walls, culverts >1200mm)
label | HP
label | Applicable Standard / Reference - VR204.11 (b)
label | Acceptance Criteria - No fill shall be placed against or within 3m of a structure until the foundation for the fill has been reviewed by the Superintendent.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - FM
date | Date:
holdpoint | HOLD POINT
checkpoint | Test Rolling
label | Applicable Standard / Reference - VR173.03, VR204.12
label | Acceptance Criteria - Undertake test roll prior to placement of fill/or proceeding layer.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - FM
date | Date:
checkpoint | Compaction - Lot size
label | Applicable Standard / Reference - VR204.13
label | Acceptance Criteria - Type B: max 10,000m2 or one day's production, whichever is the lesser
label | Frequency - Each Lot
label | Verification Records - Records
label | Action Respon. - PE/SE
date | Date:
checkpoint | Compaction
label | Applicable Standard / Reference - VR204.13 (b), VR204.14
label | Acceptance Criteria - Compaction:
label | ○ Type B material placed within 400mm of top of Type B level: min. 99%
label | ○ Type B material placed more than 400mm of top of Type B level: min. 97%
label | Grading:
label | ○ Max. particle size <100mm (visual inspection)
label | Frequency - 1 test for each lot then reduced to 1 test for every second lot
label | Verification Records - Records/Visual
label | Action Respon. - FM
date | Date:
checkpoint | Compaction - CBR & Swell
label | Applicable Standard / Reference - Table 204.141
label | Acceptance Criteria - Type B: initial 1 lot test to determine assigned CBR and swell
label | Frequency - Single CBR test to confirm assigned CBR and swell per every 8 lots
label | Verification Records - Records
label | Action Respon. - PE/SE
date | Date:
checkpoint | Compaction - LL
label | Applicable Standard / Reference - Table 204.141
label | Acceptance Criteria - Type B: liquid limit and comparison of PI against LL
label | Frequency - 1 test per 2 lots then reduced to 1 test per 4 lots
label | Verification Records - Records
label | Action Respon. - PE/SE
date | Date:
checkpoint | Other Contract Specific Requirements
textbox | Requirement(s):
date | Date:
checklist | ITC - Type A Earthworks | itp |  |  |  |  | ITC - Type A Earthworks
section | PRELIMINARIES
checkpoint | Design Issued for Construction
checkpoint | Drawings Issue for Construction
checkpoint | Material Hold Points Released
checkpoint | Survey Request
checkpoint | Traffic Management Plan Approved
checkpoint | Subcontractor/Provider approved?
checkpoint | Kick-off meeting (Subcontractor)
section | CONSTRUCTION
checkpoint | Safety; SWMS
label | Applicable Standard / Reference - HSMP
label | Acceptance Criteria - SMWS to be written for each activity on Project and shall be reviewed by a competent person.
number | Submitted to the client |  |  | days prior to commencement of Activity.
label | Frequency - Each Activity
label | Verification Records - Records
label | Action Respon. - PE/SE
date | Date:
checkpoint | Environmental Controls
label | Applicable Standard / Reference - EMP
label | Acceptance Criteria - No work shall commence unless all erosion/ Sediment controls are implemented in accordance with EMP.
label | Frequency - Each Activity
label | Verification Records - ECP
label | Action Respon. - PE/SE
date | Date:
checkpoint | Excavation Permit
label | Applicable Standard / Reference - OHS
label | Acceptance Criteria - DBYD information available on site, Excavation permit issued and spotter at location befotre commencement of excavation works
label | Frequency - Each Lot
label | Verification Records - Records
label | Action Respon. - PE/SE
date | Date:
checkpoint | Survey Control
label | Applicable Standard / Reference - VR204.03 (a), (b, c)
label | Acceptance Criteria - All Earthworks shall be finished to conform to the levels, lines, grades and cross sections showed in the plans.
date | Machine GPS File Date
label | Frequency - Each Lot
label | Verification Records - Setout
label | Action Respon. - Surveyor
date | Date:
checkpoint | Material - Type A
label | HP
label | Applicable Standard / Reference - VR204.04 (b)
label | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material unless otherwise approved by the Superintendent.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - FM
date | Date:
holdpoint | HOLD POINT
checkpoint | Site excavation - Cut Floor Level
label | Applicable Standard / Reference - VR204.03 (f)
label | Acceptance Criteria - The level at any point on the surface of the Cut Floor Level immediately below capping and/or selected material shall not differ by more than 15 mm above or 30 mm below the specified level.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - FM
date | Date:
checkpoint | Site excavation - material category
label | HP
label | Applicable Standard / Reference - VR204.06 (c)
label | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - FM
date | Date:
holdpoint | HOLD POINT
checkpoint | Earthworks - treatment of cutting at cut floor level
label | Applicable Standard / Reference - VR204.06 (e) (i)
label | Acceptance Criteria - In situ material below cut floor level having an assigned CBR less than 6, or a swell of 2.5% or greater, shall be removed to a depth of 400mm below cut floor level and replaced with conforming type B material to the underside of the capping or selected material layer
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - FM
date | Date:
checkpoint | Earthworks - Groundwater Seepage
label | HP
label | Applicable Standard / Reference - VR204.06 (h)
label | Acceptance Criteria - Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - FM
date | Date:
holdpoint | HOLD POINT
checkpoint | Earthworks - treatment of Unsuitable Material
label | HP
label | Applicable Standard / Reference - VR204.07 (d)
label | Acceptance Criteria - Where unsuitable material is encountered the Contractor shall submit the proposed in situ treatment or extent of excavation to the Superintendent for review.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - FM
date | Date:
holdpoint | HOLD POINT
checkpoint | Earthworks - Fill construction
label | HP
label | Applicable Standard / Reference - VR204.10 (b)
label | Acceptance Criteria - The Contractor shall not commence placing of any fill on the prepared surface until the area has been reviewed by the Superintendent.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - FM
date | Date:
holdpoint | HOLD POINT
checkpoint | Earthworks - Fill at Structures (wing walls, culverts >1200mm)
label | HP
label | Applicable Standard / Reference - VR204.11 (b)
label | Acceptance Criteria - No fill shall be placed against or within 3m of a structure until the foundation for the fill has been reviewed by the Superintendent.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - FM
date | Date:
holdpoint | HOLD POINT
checkpoint | Test Rolling
label | HP
label | Applicable Standard / Reference - VR173.03, VR204.12
label | Acceptance Criteria - Undertake test roll prior to placement of fill/or proceeding layer. Contractor shall provide for the Superintendant to be present during all test rolling.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - FM
date | Date:
holdpoint | HOLD POINT
checkpoint | Lot size
label | Applicable Standard / Reference - VR204.13, Table 204.142
label | Acceptance Criteria - Type A: max 5000m2 or one day's production, whichever is the lesser
textbox | Actual |  |  | m2
label | Frequency - Each Lot
label | Verification Records - Records
label | Action Respon. - PE/SE
date | Date:
checkpoint | Compaction & Grading
label | Applicable Standard / Reference - VR204.13 (b), Tables 204.042, 204.14 1
label | Acceptance Criteria - Compaction:
label | ○ All Type A Material, and Type B material placed within 400mm of top of cut floor level: min. 100%
textbox | Actual % / Minimum Frequency Testing
label | Grading:
label | ○ as per Table 204.041
label | ○ Pass/ Fail/ Minimum Frequency testing
label | Frequency - 1 test for each lot then reduced to 1 test for every second lot
label | Verification Records - Records/Visual
label | Action Respon. - FM
date | Date:
checkpoint | Compaction - CBR & Swell
label | Applicable Standard / Reference - Table 204.141 & Table 204.041
label | Acceptance Criteria - Type A: initial 1 lot test to determine assigned CBR >6% and swell <1.5%
textbox | Assigned CBR |  |  | %
textbox | Actual |  |  | %
textbox | Assigned Swell |  |  | %
textbox | Actual |  |  | %
label | Frequency - Single CBR test to confrim assigned CBR and swell - first lot only
label | Verification Records - Records
label | Action Respon. - PE/SE
date | Date:
checkpoint | Compaction - PI
label | Applicable Standard / Reference - Table 204.141 & Table 204.041
label | Acceptance Criteria - Type A: plasticity index (PI) calculation x % Passing 0.425mm, Max. 1000
label | Frequency - 1 test per 2 lots then 1 test per 4 lots
label | Verification Records - Records
label | Action Respon. - PE/SE
date | Date:
checkpoint | Compaction - LL & Permeability
label | Applicable Standard / Reference - Table 204.141 & Table 204.041
label | Acceptance Criteria - Type A: liquid limit and comparison of PI against LL, Permeability <5 x 10-9m/sec
label | Frequency - 1 test per 2 lots then 1 test per 4 lots
label | Verification Records - Records
label | Action Respon. - PE/SE
date | Date:
checkpoint | Other Contract Specific Requirements
textbox | Requirement(s):
date | Date:
checklist | ITC - Capping Layer | itp |  |  |  |  | ITC - Capping Layer
section | PRELIMINARIES
checkpoint | Design Issued for Construction
checkpoint | Drawings Issue for Construction
checkpoint | Material Hold Points Released
checkpoint | Survey Request
checkpoint | Traffic Management Plan Approved
checkpoint | Subcontractor/Provider approved?
checkpoint | Kick-off meeting (Subcontractor)
section | CONSTRUCTION
checkpoint | Safety; SWMS
label | Applicable Standard / Reference - HSMP
label | Acceptance Criteria - SMWS to be written for each activity on Project and shall be reviewed by a competent person.
number | Submitted to the client |  |  | days prior to commencement of Activity.
label | Frequency - Each Activity
label | Verification Records - Records
label | Action Respon. - PE/SE
date | Date:
checkpoint | Environmental Controls
label | Applicable Standard / Reference - EMP
label | Acceptance Criteria - No work shall commence unless all erosion/ Sediment controls are implemented in accordance with EMP.
label | Frequency - Each Activity
label | Verification Records - ECP
label | Action Respon. - PE/SE
date | Date:
checkpoint | Excavation Permit
label | Applicable Standard / Reference - OHS
label | Acceptance Criteria - DBYD information available on site, Excavation permit issued and spotter at location befotre commencement of excavation works
label | Frequency - Each Lot
label | Verification Records - Records
label | Action Respon. - PE/SE
date | Date:
checkpoint | Survey Control
label | Applicable Standard / Reference - VR204.03 (a), (b, c)
label | Acceptance Criteria - All Earthworks shall be finished to conform to the levels, lines, grades and cross sections showed in the plans.
date | Machine GPS File Date
label | Frequency - Each Lot
label | Verification Records - Setout
label | Action Respon. - Surveyor
date | Date:
checkpoint | Material - Type A
label | HP
label | Applicable Standard / Reference - VR204.04 (b)
label | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material unless otherwise approved by the Superintendent.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - SE
date | Date:
holdpoint | HOLD POINT
checkpoint | Site excavation - Cut Floor Level
label | Applicable Standard / Reference - VR204.03 (f)
label | Acceptance Criteria - The level at any point on the surface of the Cut Floor Level immediately below capping and/or selected material shall not differ by more than 15 mm above or 30 mm below the specified level.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - SE
date | Date:
checkpoint | Site excavation - material category
label | HP
label | Applicable Standard / Reference - VR204.06 (c)
label | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - SE
date | Date:
holdpoint | HOLD POINT
checkpoint | Earthworks - treatment of cutting at cut floor level
label | Applicable Standard / Reference - VR204.06 (e) (i)
label | Acceptance Criteria - In situ material below cut floor level having an assigned CBR less than 6, or a swell of 2.5% or greater, shall be removed to a depth of 400mm below cut floor level and replaced with conforming type B material to the underside of the capping or selected material layer
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - SE
date | Date:
checkpoint | Earthworks - Groundwater Seepage
label | HP
label | Applicable Standard / Reference - VR204.06 (h)
label | Acceptance Criteria - Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - SE
date | Date:
holdpoint | HOLD POINT
checkpoint | Earthworks - treatment of Unsuitable Material
label | HP
label | Applicable Standard / Reference - VR204.07 (d)
label | Acceptance Criteria - Where unsuitable material is encountered the Contractor shall submit the proposed in situ treatment or extent of excavation to the Superintendent for review.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - SE
date | Date:
holdpoint | HOLD POINT
checkpoint | Earthworks - Fill construction
label | HP
label | Applicable Standard / Reference - VR204.10 (b)
label | Acceptance Criteria - The Contractor shall not commence placing of any fill on the prepared surface until the area has been reviewed by the Superintendent.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - SE
date | Date:
holdpoint | HOLD POINT
checkpoint | Earthworks - Fill at Structures (wing walls, culverts >1200mm)
label | HP
label | Applicable Standard / Reference - VR204.11 (b)
label | Acceptance Criteria - No fill shall be placed against or within 3m of a structure until the foundation for the fill has been reviewed by the Superintendent.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - SE
date | Date:
holdpoint | HOLD POINT
checkpoint | Test Rolling
label | HP
label | Applicable Standard / Reference - VR173.03, VR204.12
label | Acceptance Criteria - Undertake test roll prior to placement of fill/or proceeding layer. Contractor shall provide for the Superintendant to be present during all test rolling.
label | Frequency - Each Lot
label | Verification Records - Visual
label | Action Respon. - SE
date | Date:
holdpoint | HOLD POINT
checkpoint | Lot size
label | Applicable Standard / Reference - VR204.13, Table 204.142
label | Acceptance Criteria - Type A: max 5000m2 or one day's production, whichever is the lesser
textbox | Actual |  |  | m2
label | Frequency - Each Lot
label | Verification Records - Records
label | Action Respon. - PE/SE
date | Date:
checkpoint | Compaction & Grading
label | Applicable Standard / Reference - VR204.13 (b), Tables 204.042, 204.14 1
label | Acceptance Criteria - Compaction:
label | ○ All Type A Material, and Type B material placed within 400mm of top of cut floor level: min. 100%
textbox | Actual % / Minimum Frequency Testing
label | Grading:
label | ○ as per Table 204.041
label | ○ Pass/ Fail/ Minimum Frequency testing
label | Frequency - 1 test for each lot then reduced to 1 test for every second lot
label | Verification Records - Records/Visual
label | Action Respon. - SE
date | Date:
checkpoint | Compaction - CBR & Swell
label | Applicable Standard / Reference - Table 204.141 & Table 204.041
label | Acceptance Criteria - Type A: initial 1 lot test to determine assigned CBR >6% and swell <1.5%
textbox | Assigned CBR |  |  | %
textbox | Actual |  |  | %
textbox | Assigned Swell |  |  | %
textbox | Actual |  |  | %
label | Frequency - Single CBR test to confrim assigned CBR and swell - first lot only
label | Verification Records - Records
label | Action Respon. - PE/SE
date | Date:
checkpoint | Compaction - PI
label | Applicable Standard / Reference - Table 204.141 & Table 204.041
label | Acceptance Criteria - Type A: plasticity index (PI) calculation x % Passing 0.425mm, Max. 1000
label | Frequency - 1 test per 2 lots then 1 test per 4 lots
label | Verification Records - Records
label | Action Respon. - PE/SE
date | Date:
checkpoint | Compaction - LL & Permeability
label | Applicable Standard / Reference - Table 204.141 & Table 204.041
label | Acceptance Criteria - Type A: liquid limit and comparison of PI against LL, Permeability <5 x 10-9m/sec
label | Frequency - 1 test per 2 lots then 1 test per 4 lots
label | Verification Records - Records
label | Action Respon. - PE/SE
date | Date:
checkpoint | Other Contract Specific Requirements
textbox | Requirement(s):
label | S
date | Date: