## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Farmers Tauranga QA |  |  |  |  | Yes | Farmers Tauranga QA | c5e5d64a-9fd5-4e43-9c4e-4403f02597b8
checkpoint-group |  |  | section | Pre-Tiling Works Check
checkpoint-status |  |  | checkpoint | Door Frames installed
checkpoint-status |  |  | checkpoint | Shower tray installed
checkpoint-status |  |  | checkpoint | GIB level & straight
checkpoint-status |  |  | checkpoint | GIB fixing spaces
checkpoint-status |  |  | checkpoint | Tile layout as per specified drawings
checkpoint-status |  |  | checkpoint | Gaps around floor drains closed
checkpoint-status |  |  | checkpoint | Work area cleaned and ready
checkpoint-group |  |  | section | Levelling
checkpoint-status |  |  | checkpoint | Floor grinding and primer
checkpoint-status |  |  | checkpoint | QA floor levels
checkpoint-status |  |  | checkpoint | Apply levelling as per QA
checkpoint-group |  |  | section | Acoustic
checkpoint-status |  |  | checkpoint | Floor light grinded & primed
checkpoint-status |  |  | checkpoint | Joints are tight
checkpoint-status |  |  | checkpoint | Foam border installed
checkpoint-status |  |  | checkpoint | Specified level of finish achieved and area left clean and tidy
checkpoint-group |  |  | section | Waterproofing
checkpoint-status |  |  | checkpoint | All relevant substrates primed
checkpoint-status |  |  | checkpoint | Silicone Screw heads
checkpoint-status |  |  | checkpoint | Bond breaker & Tape applied to internal corners
checkpoint-status |  |  | checkpoint | 1st coat applied
checkpoint-status |  |  | checkpoint | 2nd coat applied
checkpoint-status |  |  | checkpoint | Flood test has been completed and passed (photo taken)
checkpoint-group |  |  | section | Tiling
checkpoint-status |  |  | checkpoint | Glass channel holder installed
checkpoint-status |  |  | checkpoint | Floor and channel wastes correctly installed and siliconed
checkpoint-status |  |  | checkpoint | Tiles and grout free from dust
checkpoint-status |  |  | checkpoint | Tiling completed, checked and Supervisor sign off
checkpoint-status |  |  | checkpoint | Area left clean & tidy