## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | FHC-ITP-032 - Bus Bay Concrete Slab Rev1 | itp |  |  |  |  | FHC-ITP-032 - Bus Bay Concrete Slab Rev1
section | 1 - Design and Submissions
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 1.3 Approval of mix design
label | FREQUENCY: Prior to the first concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 503.04
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 1.4 Reinforcement schedule
label | FREQUENCY: Prior to concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 503.09
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
section | 2 - Construction/Erection of Formwork
checkpoint | 2.1 Excavation
label | FREQUENCY: Prior to concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Contract Drawings
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Inspect
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.2 Construction Methodology
label | FREQUENCY: Prior to erection
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
label | ○ Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Contract Drawings
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
section | 3 - Pre-Pour Planning and Inspection
checkpoint | 3.1 Excavation/Foundation – Blinding, sealing or foundation concrete
label | FREQUENCY: Prior to concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Blinding, sealing or foundation concrete shall not be placed until the bottom of the excavation has been reviewed by the Superintendent. Inspected and approved by the Superintendent.
label | ○ Hold Point released by the Superintendent.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Contract Drawings
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | HP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan / VicRoads
label | – – – – – – – – –
text | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 Formwork levels and position
label | FREQUENCY: Prior to concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: A pre-pour survey carried out to confirm erected formwork within the tolerance. Any errors in the level or positioning of formwork is to be corrected prior to placing concrete
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Contract Drawings
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | SCP, HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 3.3 Location of splices
label | FREQUENCY: Schedule Review
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: In lapped splices, the bars shall be placed in contact and the specified cover shall be maintained.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Contract Drawings
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Inspect
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 3.4 Cleaning formwork
label | FREQUENCY: Each concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 503.13
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments
label | FREQUENCY: Prior to concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications. Pre-pour checklist completed and signed.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 503.07
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed & Pre-Pour checklist completed
label | – – – – – – – – –
label | HP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan / VicRoads
label | – – – – – – – – –
text | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 Reinforcement assembly of piles
label | FREQUENCY: Prior to concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 503.07
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | HP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 Monitoring weather
label | FREQUENCY: Prior to concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Concrete shall not be place when temperature is <5°C or > 35°C
label | ○ All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 503.07
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 3.8 Assessment of Base Thickness
label | FREQUENCY: Prior to lot closure
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Within the lots defined for assessment of compressive strength the surface levels of the subbase shall be measured as specified in Section 173. Levels of the base surface shall be taken at the same locations as taken on the subbase.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 503.05
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | TP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 3.9 Concrete Sampling and Testing
label | FREQUENCY: Prior to placement
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Concrete sampled and tested for slump test.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 503.05
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | TP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 3.10 Sampling and Testing of Cylinder Specimens
label | FREQUENCY: During concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: The Contractor shall record 3 sample, prepare, cure and compression test of 12 cylinders cast on site in accordance with AS 1012.
label | ○ The concrete shall be sampled at the point of discharge to the roadbed. Each sample shall consist of two cylinder specimens for testing at age 28 days.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 503.05
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | TP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
section | 4 - Placing and Finishing Concrete
checkpoint | 4.1 Carry out sampling of concrete
label | FREQUENCY: Each concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Sampling in accordance with 503.05
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 503.05
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Checklist
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 4.2 Discharge time
label | FREQUENCY: Each concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 503.05
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed. Accurate Site Notes & Load Mapping
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 4.3 Concrete Placement
label | FREQUENCY: Each concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Concrete shall not be placed until the proposed method of placement, spacing of planned transverse construction joints and the provision of dowels, constructed formwork, reinforcement and embedments conforming to the requirements of this specification and the drawings, has been reviewed by the Superintendent.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 503.05
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed. Accurate Site Notes & Load Mapping
label | – – – – – – – – –
label | HP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 Methodology of Placement
label | FREQUENCY: Each concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
label | ○ Concrete shall not be moved horizontally by vibrators
label | ○ In continuous pours the max. time lag between truckloads on site is 25 minutes
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 503.07
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 4.5 Compaction
label | FREQUENCY: During concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Base and subbase concrete shall be compacted to meet the requirements of clause 503.05.
label | ○ Concrete placed around dowel bars shall be carefully vibrated without the vibrators touching the dowels.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 503.07
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 4.6 Screeding and Finishing
label | FREQUENCY: Post concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: The concrete shall be finished to provide a dense and homogeneous concrete surface satisfying the requirements of clause 503.03.
label | ○ The subbase concrete shall be finished to a uniform non-textured surface. The base concrete shall be finished to a textured surface as specified.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 503.07
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 4.7 Joint Sealants
label | FREQUENCY: Post concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Permanent seals shall be either a neoprene compression seal or an in situ cast silicone sealant. A full technical description of the proposed sealant and method of installation recommended by its manufacturer shall be submitted for approval by the Superintendent at least four weeks prior to installation.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Contract Drawings
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 4.8 Joint Sealants for Base
label | FREQUENCY: Post concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Joints shall be constructed as specified and shown on the drawings.
label | ○ Joints shall be straight and vertical. Transverse joints shall be continuous from edge to edge of the pavement.
label | ○ Tie bars shall be installed such that anchorage strength of at least 85% of the yield strength of the bar is developed upon hardening of the base.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 503.13
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 4.9 Texturing of Surface
label | FREQUENCY: Post concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Texturing of the concrete surface shall be carried out to the standard of surface specified in clause 503.21. The textured surface shall extend across the full width of the base and shall be uniform in appearance.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 503.17
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
section | 5 - Post-Pour Details and Inspection
checkpoint | 5.1 Curing and Protection
label | FREQUENCY: Post concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Curing of the base and subbase concrete shall be undertaken by the use of a curing compound sprayed onto the freshly laid concrete at the application rates specified in this clause. Curing compound shall not be sprayed when bleed water is present.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 503.18
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 5.2 Curing Compounds
label | FREQUENCY: Post concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Prior to the use of curing compounds, the Contractor shall submit to the Superintendent for review not less than four weeks prior to placement of concrete
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 503.18
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | HP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 Formwork removal
label | FREQUENCY: Post concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Contract Drawings
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 5.4 Concrete Base Course
label | FREQUENCY: Post concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: With the exception of concrete saws, personnel the concrete base course shall not be trafficked until the in situ compressive strength has reached at least 20 MPa based on concrete cylinder testing.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 503.19
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | HP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5 Positional tolerance and dimensions of concrete members and piles
label | FREQUENCY: Each concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Dimensions within the tolerances given in Cl 17.5 of AS3600 (-10,+40)
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: AS3600 Cl 17.5
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed, Post Pour Checklist completed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 5.6 Concrete Sampling and Testing
label | FREQUENCY: Prior to lot closure
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Concrete sampled and tested for compressive strength. The required strength of concrete must be in accordance with the drawings
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 503.05
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | TP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 5.7 Curing and Protection
label | FREQUENCY: Post concrete pour
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Saw cutting and joint sealing shall be allowed on the finished base concrete until the in situ strength of the concrete is at least 60% of the target 28 day compressive strength.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 503.18
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | 5.8 As Built Drawings
label | FREQUENCY: Prior to lot closure
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Recorded of as-built drawings
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Fulton Hogan Procedure
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed
label | – – – – – – – – –
label | IP
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan
label | – – – – – – – – –
text | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: