## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP005 – Crack Sealing | itp |  |  |  | Yes | ITP005 – Crack Sealing
section | 1. Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Current revision drawing is being used including the Subcontractor’s copy. Current revision to be obtained via Aconex.
label | Reference Documents - Drawings and drawing registers on Aconex
label | Inspection/ Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project Engineer
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | Reference Documents - PSP, EMP, TMP, SWMS, WP
label | Inspection/ Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project Engineer
checkpoint | 1.3 - Definition of the work area
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Work area has been cleared and surveyed (marked on site). Limits of work clearly defined.
label | Reference Documents - Drawings
label | Inspection/ Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project Engineer
checkpoint | 1.4 - Material Sources – Conformance Test Certificates/Reports
label | Frequency - At least 2 weeks prior to application on site
label | Acceptance Criteria - Details of proposed Rubberised Bituminous Bandage (RBB) sealant product including manufacturer’s data sheet and recommendations for application to be submitted for approval.
label | Reference Documents - Cl 15.3
label | Inspection/ Test Method - Verify
label | Record of conformity - Aconex Correspondence
label | HP
label | Responsibility - Project Engineer Principal’s Representative
holdpoint | AUTHORITY HOLDPOINT
section | 2. Materials
checkpoint | 2.1 - Rubberised Bituminous Sealant
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - RBB must be a proprietary polymer modified bitumen (PMB) crack and joint bandage product and be suitable for climate conditions of the site. RBB to have following properties:
label | – Minimum softening point to be 95°C
label | – Penetration at 25°C between 20 and 50
label | – Flow at 60°C at 5 hours to be maximum 5mm
label | – Viscosity at 180°C to be maximum 3Pa.s
label | Reference Documents - Cl 15.3
label | Inspection/ Test Method - Verify
label | Record of conformity - Manufacturer Datasheet
label | HP
label | Responsibility - Project Engineer Principal’s Representative
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preparation
checkpoint | 3.1 - Preparation of cracks
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Cracks, joints and all other locations to be sealed must be sufficiently cleaned and dried out prior to sealing. All wide (greater than 8mm) and/or deep cracks in all types of pavement must be choked with dry sand to not less than 10mm below the surface of the pavement.
label | Reference Documents - Cl 15.4.1
label | Inspection/ Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Site Engineer
section | 4. Sealing
checkpoint | 4.1 - Trial Application
label | Frequency - Prior to continuing with crack sealing works
label | Acceptance Criteria - A 50m length of RBB to be applied at location agreed with Principal’s Design Consultant for inspection and approval.
label | Reference Documents - Cl 15.4.2.2
label | Inspection/ Test Method - Verify
label | Record of conformity - Aconex Correspondence
label | HP
label | Responsibility - Project Engineer Principal’s Representative
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Applying Sealant
label | Frequency - During crack sealing works
label | Acceptance Criteria - Sealant bandage must be within 50 to 75mm wide with the thickness not exceeding 1.5mm unless otherwise noted on drawings.
label | Reference Documents - Cl 15.4.2.3, Cl 15.4.2.4, Cl 15.4.2.5
label | Inspection/ Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Site Engineer
checkpoint | 4.3 - Protection of Applied Sealant
label | Frequency - During crack sealing works
label | Acceptance Criteria - Installed sealant must be protected from damage by traffic (and possible pick up on construction vehicles and aircraft tyres) until it has cooled to ambient temperature.
label | Reference Documents - Cl 15.4.2.1
label | Inspection/ Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Site Engineer
checkpoint | 4.4 - Cleaning up
label | Frequency - After sealing works
label | Acceptance Criteria - Any sealant split on surface of pavements must be cleaned off immediately.
label | Reference Documents - Cl 15.5
label | Inspection/ Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Site Engineer
section | 5. Post Construction
checkpoint | 5.1 - Conformance
label | Frequency - At completion of each work
label | Acceptance Criteria - Each lot package must include the following:
label | – Equipment used
label | – Product used including the batch number
label | – Date and start and finish times
label | – Weather conditions including range of air temperature
label | – Hourly sealant temperature
label | Reference Documents - Cl 15.6
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Site Engineer
checkpoint | Final Inspection
note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP