## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Fit-Off Checklist Food Waste |  |  |  |  | Yes | Fit-Off Checklist Food Waste | 003416d2-a04f-45fb-96ec-8eab724e9318
checkpoint-status |  |  | checkpoint | Food Waste
text | cfacc79c-85f7-500d-87b4-a0d8c6d69692 |  | textbox | Floor waste
checklist-flat |  |  | checklist | Hot Water |  |  |  |  | Yes | Hot Water Checklist | 0218f41c-17b2-400e-8057-5873bf1385a2
checkpoint-status |  |  | checkpoint | Quality control pressure test report uploaded below
text | 86deb85f-9151-5ab6-8671-50441ea907ae |  | textbox | Ambient temp
text | fddd2302-b92d-5c3e-af9f-ba503ef756d3 |  | textbox | First test
text | fd0fb33a-8efb-5942-aa4b-e2eb626b597c |  | textbox | Second test
checkpoint-status |  |  | checkpoint | Approved material
checkpoint-status |  |  | checkpoint | Approved Jointing methods
checkpoint-status |  |  | checkpoint | Appropriate protection
checkpoint-status |  |  | checkpoint | Pipe support
checkpoint-status |  |  | checkpoint | Appropriate cross connection controls
checkpoint-status |  |  | checkpoint | Appropriate valves and devices
checkpoint-status |  |  | checkpoint | Tested to required pressures and times under test.
checklist-flat |  |  | checklist | Commissioning Basement 1 |  |  |  |  | Yes | Commissioning Basement 1 | 1029ad17-d569-44d7-9aeb-5ea30887f402
checkpoint-status |  |  | checkpoint | Bin Room & Food waste
text | 11baed50-3340-55f5-ae1c-d8780d183ea3 |  | textbox | Sink Mixer
text | 16464be3-aaf4-5594-99c7-dd9f263d6617 |  | textbox | Sink Waste
text | d556520a-96eb-5bb5-a018-edcb806bfe44 |  | textbox | HWU
text | d9ab3fd5-9893-5e45-9da5-3f8e4d719254 |  | textbox | Floor wastes clear
checklist-flat |  |  | checklist | Rough-In |  |  |  |  | Yes | Rough-In Checklist | 309db9a2-cbe8-46e2-b379-0cc35413b673
checkpoint-status |  |  | checkpoint | Lagging Complete
checkpoint-status |  |  | checkpoint | Un used Peno's sealed
checkpoint-status |  |  | checkpoint | ROUGH IN COMPLETE
checkpoint-status |  |  | checkpoint | HEADER PIPES FIRE CAULKED
checkpoint-status |  |  | checkpoint | TMV ACCESSIBLE TO A/P
checkpoint-status |  |  | checkpoint | CROSS CONNECTIONS
checkpoint-status |  |  | checkpoint | MIXER STRAIGHT, SET BACK CORRECT
checkpoint-status |  |  | checkpoint | FW CLEANED, COVERED AND CLEAR OF DEBRIS
checkpoint-status |  |  | checkpoint | AAV REQUIRED?
checkpoint-status |  |  | checkpoint | FIXTURE SET OUT CORRECT
checklist-flat |  |  | checklist | DCW |  |  |  |  | Yes | DCW Checklist | 4f63fc4d-5f1d-4c50-b0f2-f222b75d3a83
checkpoint-status |  |  | checkpoint | Quality control pressure test report uploaded below
text | cff745de-7e3d-5e59-8152-be7309e863ff |  | textbox | Ambient temp
text | 5810cac3-c7bc-5200-93cf-31f7c6b463b5 |  | textbox | First test
text | 05ac3eb7-28da-5652-9de3-0fe919634d9b |  | textbox | Second test
checkpoint-status |  |  | checkpoint | Approved material
checkpoint-status |  |  | checkpoint | Approved Jointing methods
checkpoint-status |  |  | checkpoint | Appropriate protection/seperation between other services
checkpoint-status |  |  | checkpoint | Pipe support
checkpoint-status |  |  | checkpoint | Appropriate cross connection controls
checkpoint-status |  |  | checkpoint | Appropriate valves and devices
checkpoint-status |  |  | checkpoint | Tested to required pressures and times under test
checklist-flat |  |  | checklist | Fit-Off Checklist Bin Room |  |  |  |  | Yes | Fit-Off Checklist Bin Room | 55b8562d-57be-44e0-a02c-b6b522a17950
checkpoint-status |  |  | checkpoint | Food Waste
text | 8f9fb97d-dfb2-50b6-8606-256cd4c1dccc |  | textbox | Sink Mixer
text | ec368ac3-2ad2-5d7f-831b-149caed8cec1 |  | textbox | Sink Waste
text | d77e6a79-373c-557f-8335-1911014dc212 |  | textbox | HWU
text | 03ac1985-8ac0-5f3d-9f9e-ca4d024773ca |  | textbox | Floor waste
checklist-flat |  |  | checklist | Commissioning Checklist Level Roof |  |  |  |  | Yes | Commissioning Checklist Level Roof | 5996852e-5022-4c11-b487-08a8e21886a8
checkpoint-status |  |  | checkpoint | Floor waste cleaned and Clear
checkpoint-status |  |  | checkpoint | HWU
checklist-flat |  |  | checklist | Commissioning Checklist Level 1-7 |  |  |  |  | Yes | Commissioning Checklist Level 1-7 | 7b609e5f-83d0-4629-814e-90d01cdb61ff
checkpoint-status |  |  | checkpoint | Male WC
text | b306c6ad-3c42-59d0-929f-b560b1ebc089 |  | textbox | Basin
text | 7107c3af-b694-5a95-ad30-6ce65326924b |  | textbox | WC
text | af72c994-a3d7-5999-9d37-a42d3c758123 |  | textbox | Floor waste cleaned and Clear
checkpoint-status |  |  | checkpoint | Female WC
text | ef82e4e8-9bcf-5e70-9870-8f435238125f |  | textbox | Basin
text | 968a7ece-ca85-5e75-83b0-b2b2b81e3457 |  | textbox | WC
text | 9fd0d4fc-a3ba-560f-8046-5e3d3cd87754 |  | textbox | Floor waste cleaned and Clear
checkpoint-status |  |  | checkpoint | DDA WC
text | 6e86f77e-a03b-5e74-b5d0-f0ca57277bfc |  | textbox | Basin
text | e7dc3326-8308-56c7-95ce-c1b906eca2b2 |  | textbox | WC
text | 0b5d754e-2239-53d2-8894-b2f4ef3a8721 |  | textbox | Floor waste cleaned and Clear
checklist-flat |  |  | checklist | Rain Water |  |  |  |  | Yes | Rain Water Checklist | 8263c1f4-858e-441b-854a-5eba2e695c0e
checkpoint-status |  |  | checkpoint | Quality control pressure test report uploaded below
text | 05db102c-d7dd-551a-9954-46ae25cd314e |  | textbox | Ambient temp
text | 34412690-3bf0-56e8-a0a2-f417a379696b |  | textbox | First test
text | f7d2e31a-6a3f-5020-8bb1-660c8468e8e1 |  | textbox | Second test
checkpoint-status |  |  | checkpoint | Approved material
checkpoint-status |  |  | checkpoint | Approved Jointing methods
checkpoint-status |  |  | checkpoint | Appropriate protection
checkpoint-status |  |  | checkpoint | Pipe support
checkpoint-status |  |  | checkpoint | Appropriate cross connection controls
checkpoint-status |  |  | checkpoint | Appropriate valves and devices
checkpoint-status |  |  | checkpoint | Tested to required pressures and times under test.
checklist-flat |  |  | checklist | Fit-Off Checklist Level 1-7 |  |  |  |  | Yes | Fit-Off Checklist Level 1-7 | a0598a7b-358f-416b-a200-b66f14a4642f
checkpoint-status |  |  | checkpoint | Male WC
text | 31c6efd5-d7f7-5e43-b58e-ba895a499f33 |  | textbox | Basin
text | 399a913f-5350-55e6-ac48-96b490763554 |  | textbox | Mixer
text | 1506a972-e83d-56e3-99fc-f88a046bb1ea |  | textbox | Waste
text | 35f3c137-4398-5b45-b5fd-bc1a54cb2641 |  | textbox | WC Installed
checkpoint-status |  |  | checkpoint | Female WC
text | bf317a8e-29ca-5324-b837-416f4f4f9dff |  | textbox | Basin
text | 59914953-ac16-51c3-8cdf-45b818ad4d08 |  | textbox | Mixer
text | 496e7356-4c18-5b4a-bf6e-91b6c0976cff |  | textbox | Waste
text | 4785c2d1-4a5f-554c-9fc2-b10cb506fcfb |  | textbox | WC Installed
checkpoint-status |  |  | checkpoint | DDA WC
text | 2d0f5621-3179-5692-ad06-762f7f03412b |  | textbox | Basin
text | 5bc0f29e-59dd-5e14-a036-3af5fae9a164 |  | textbox | Mixer
text | 922624e2-5591-5e2f-a51b-7aadad149551 |  | textbox | Waste
text | a1700264-cbe6-5bd3-a251-bec9f291d482 |  | textbox | WC Installed
checkpoint-status |  |  | checkpoint | Water Meter
checklist-flat |  |  | checklist | Fit-Off Checklist Ground |  |  |  |  | Yes | Fit-Off Checklist Ground | b6e195b8-5ce0-4308-a1d3-382c640d3699
checkpoint-status |  |  | checkpoint | Male Change
text | 222edbe5-f2ae-5d92-bebb-e1079c6cb282 |  | textbox | Basin
text | 80f7cdc4-5003-5d0d-beb1-866fcb47c356 |  | textbox | Mixer
text | 87d723f3-39c6-5f40-b770-cba96d8b26d2 |  | textbox | Waste
text | d49bc028-aaef-53c1-a87f-b36b25a18d87 |  | textbox | Shower
text | 7293ad1f-c027-559d-93ab-d95da45c5068 |  | textbox | WC Installed
checkpoint-status |  |  | checkpoint | Female Change
text | 38440a0a-6059-5229-857a-430f54645d57 |  | textbox | Basin
text | 27deeb28-b099-52ad-bc7a-3c4be4313f39 |  | textbox | Mixer
text | 02d6895d-ed08-5abe-8cc3-9ed79f3d6a8d |  | textbox | Waste
text | c9122442-74bd-5db4-a826-fd4f8301c199 |  | textbox | Shower
text | 0af75296-13db-5153-8405-4f7692debf39 |  | textbox | WC Installed
checkpoint-status |  |  | checkpoint | Gender Nuetral Change
text | 2a7e358a-a6f6-5c4d-9536-b1bb8c8d125f |  | textbox | Basin
text | c1abc171-7aa0-5196-a852-5a2eda868853 |  | textbox | Mixer
text | 46179db2-3785-5736-819c-7d56090ebdd8 |  | textbox | Waste
text | df11a3ac-f819-51ca-8da9-e50158efa260 |  | textbox | WC Installed
text | d06e0088-eb89-5f47-8700-c04fa0e1a289 |  | textbox | Shower
checkpoint-status |  |  | checkpoint | Male WC
text | 9b06009f-8d19-554b-929d-e349c2f1eca7 |  | textbox | Basin
text | e8d7bb3a-e85d-5cee-8414-33860d973479 |  | textbox | Mixer
text | e31fea92-23ef-5262-a372-b467c144bf4a |  | textbox | Waste
text | 54f6ab38-b0ab-5fb8-82bb-841d5d38833d |  | textbox | WC Installed
checkpoint-status |  |  | checkpoint | Female WC
text | da8bf8a8-f5dd-5172-91c5-223e9405ff5a |  | textbox | Basin
text | 0445680a-5771-5340-b57e-f830c8e3705b |  | textbox | Mixer
text | fd985202-6ed7-515f-9c22-7619227982a2 |  | textbox | Waste
text | c5abe49d-8a62-50ee-b762-19b3b69ee9f9 |  | textbox | WC Installed
checkpoint-status |  |  | checkpoint | DDA WC
text | cadc8728-ca03-5299-8872-5b814ab5f740 |  | textbox | Basin
text | 3f854e35-401a-5dd6-8da8-e709151601e7 |  | textbox | Mixer
text | 1387aba8-7982-5c6f-9d07-9f5a7da680e8 |  | textbox | Waste
text | 5758ffc3-13ed-50ea-86a4-8d25305e5080 |  | textbox | WC Installed
checkpoint-status |  |  | checkpoint | Water Meter
checklist-flat |  |  | checklist | Commissioning Checklist Ground Floor |  |  |  |  | Yes | Commissioning Checklist Ground Floor | be0ea7a4-c6d8-4f88-9349-dbb91ec574bb
checkpoint-status |  |  | checkpoint | Male Change
text | 1ab83ede-4c3c-5850-9bf8-4efe2276293c |  | textbox | Basins
text | b377a134-052e-5606-8100-8d0fc09daa23 |  | textbox | Showers
text | fc21f58f-e698-595a-b4aa-4f30b18075a2 |  | textbox | WC
text | 9efec438-8c1a-599f-a349-ef78c89e7751 |  | textbox | Floor waste cleaned and Clear
checkpoint-status |  |  | checkpoint | Female Change
text | 6ebf7eda-a59a-5a87-8827-afe8b098b3b3 |  | textbox | Basins
text | a000d332-4460-5fa4-9f3e-4ed8828428f6 |  | textbox | Showers
text | f44ee07a-5f40-57c4-b6d9-ca88638c9246 |  | textbox | WC
text | 5c6a9905-16e0-5b00-8834-b2906e743182 |  | textbox | Floor waste cleaned and Clear
checkpoint-status |  |  | checkpoint | Gender Nuetral Change
text | f4c5ae6a-371e-50ed-9532-2d99e98ce799 |  | textbox | Basins
text | b24d7e65-771c-5882-ae66-fa20eea4824e |  | textbox | Showers
text | 87f8e945-b53d-5a57-a00c-ef5460e60d19 |  | textbox | WC
text | f2715ecb-a11e-5534-84af-b8d5c542eb46 |  | textbox | Floor waste cleaned and Clear
checkpoint-status |  |  | checkpoint | Male WC
text | 7ff0bf04-d35c-54d0-9b2b-0395b2e197ea |  | textbox | Basin
text | 173cdcd8-89d6-5f27-9afd-8df09097c59a |  | textbox | WC
text | 9038f32a-605e-5d97-af7b-76ab38d47c10 |  | textbox | Floor waste cleaned and Clear
checkpoint-status |  |  | checkpoint | Female WC
text | 68151de4-f0c5-535c-8d61-33c28cce4ef1 |  | textbox | Basin
text | 96904617-0e28-5a3b-b0ce-59cb01851581 |  | textbox | WC
text | 289fa0e1-13c6-5e9d-8c3e-2bbcca74d368 |  | textbox | Floor waste cleaned and Clear
checkpoint-status |  |  | checkpoint | DDA WC
text | 5c6a9087-86ad-5f16-84b4-6c9b5b2c1c71 |  | textbox | Basin
text | ac1f04f8-8e1a-5bb6-9565-4c41933952c8 |  | textbox | WC
text | 6da72417-aff5-571b-bf19-699cfef2633f |  | textbox | Floor waste cleaned and Clear
checkpoint-status |  |  | checkpoint | Cleaners Room
text | 97d1040e-3563-571d-87c8-e4267f81ca14 |  | textbox | Sink Mixer
text | 775cdd42-c0ed-5253-b03e-8ca8e35f221f |  | textbox | Sink Waste
text | eb590144-55ef-5369-80a0-7f37613041f4 |  | textbox | HWU
text | 56f6e3a1-f443-5368-be03-6fb75dffda23 |  | textbox | Floor waste
checkpoint-status |  |  | checkpoint | Bin Room
text | 064fe2e0-e127-5441-a68c-fe52e2e71d06 |  | textbox | Sink Mixer
text | ef991a78-275e-59ca-b80a-ac1a77c23a9e |  | textbox | Sink Waste
text | 1fdf3fff-24f9-5776-a9ce-cbf2ec474eec |  | textbox | HWU
text | f9fa6370-92b8-5398-9321-1307d50194f0 |  | textbox | Floor waste
checklist-flat |  |  | checklist | Sanitary drainage |  |  |  |  | Yes | Sanitary drainage Checklist | bfc4cad6-4a27-4e4e-a69b-b7f391be6c84
checkpoint-status |  |  | checkpoint | Drainage
boolean | e5642f6a-77a6-5087-8967-03fe09fc583e |  | tickbox | Pipework has approved gradient
boolean | 83c63db6-ac39-50d1-bcff-24359edd1c39 |  | tickbox | Provision for expansion provided
boolean | 462c7195-46d5-548b-a9e7-2420d4fbad20 |  | tickbox | Appropriate fitting used in appropriate manner
boolean | cd673ad1-77ec-50e8-9844-1af0624ee103 |  | tickbox | Venting requirements met
checkpoint-status |  |  | checkpoint | Pipe clip hanger - Pipe work has appropriate supports and spacings
checkpoint-status |  |  | checkpoint | Material approved and pipe installed to correct size
checkpoint-status |  |  | checkpoint | Alignment - restricted zone has been met
checkpoint-status |  |  | checkpoint | Approved labelling and identification applied
checkpoint-status |  |  | checkpoint | Approved jointing methods used
checkpoint-status |  |  | checkpoint | Penetrations correctly sealed
checkpoint-status |  |  | checkpoint | Fire stop retro collars sealed using approved sealant
checkpoint-status |  |  | checkpoint | Seismic bracing installed to comply with seismic certification
checkpoint-status |  |  | checkpoint | Water Test complete