## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
ee1f27ac-a386-46f1-ada0-988b4c8a659b | checklist | Clearing and Grubbing | itp | Clearing and Grubbing
4c6802ba-6f2c-4e3f-9b5b-cedb3650249a | section | Details
cea0d170-f8a2-4a1e-8cfa-35a1d0530d7b | checkpoint | 1 - Areas to Clear and Grub
570ec2ff-fc67-5d4c-a682-15fd7d7d6dff | note | Acceptance Criteria: Clearing and grubbing operations shall be limited to those areas required to construct the Works and/or meet specified visibility requirements. As a minimum, the following clearing and grubbing shall be carried out: a) where earthworks are to be constructed, the minimum width required to construct the Works, plus an additional width of not more than the distance stated in Clause 1.1 of Annexure MRTS04.1 to this Technical Specification or 3 m where not so stated, or the property boundaries, whichever is the lesser, and b )other areas specified in Clause 1.2 of Annexure MRTS04.1 to this Technical Specification.
5ddeff41-0e1e-5788-a916-a7e321b43cc9 | note | Reference - MRTS04 Cl. 7.2.1
8beb50c3-2741-5c47-a996-4d0717f43cbb | note | Item Check - Check and Verify
537a4b23-a952-49bb-9948-1329e942c7d3 | checkpoint | 2 - Limitations
f2fcc416-4126-5d14-9c2a-e61d5f467ea8 | note | Acceptance Criteria: Any trees, shrubs and overhanging branches to be left undisturbed shall be clearly marked by the Contractor. This marking shall be carried out prior to clearing operations reaching the areas concerned. HOLD POINT
b59d225c-1c90-5c20-b8f1-e1e47bd33c8f | note | Clearing operations within streams and waterways shall not include removal of stumps and roots below ground surface. Beyond the areas to be cleared, only those trees, shrubs and overhanging branches which are shown on the drawings shall be removed or pruned, as necessary. Such removal or pruning shall only be carried out after consultation with the Administrator
6c2c1b32-0942-53f1-af25-5154e46c57c7 | note | Reference - MRTS04 Cl. 7.2.2
026ddcc3-dfbc-5cf1-87e5-d71ba6c3ea3e | note | Item Check - HOLDPOINT
4607248b-7ca8-4f10-8a0d-48963b13b491 | signoff | Hold Point
bf8c9b6b-6bad-4327-99e0-b5df946a95b6 | checkpoint | 3 - Trees required by Administrator
86bc7902-1ef4-56ac-965d-cae588acc137 | note | Item Check - HOLDPOINT
2b90815b-c54e-45c8-a9a0-48529b4f1831 | signoff | Hold Point
68f2fa5e-4e11-41f0-b3aa-c6b1bf401cb2 | checkpoint | 4 - Material for Organic Mulch MRTS04 Clause
c45d87be-767f-5e33-8495-5e1b17c875ba | note | Acceptance Criteria: Where site manufactured mulch is required in accordance with MRTS16 Landscape and Revegetation Works or MRTS52 Erosion and Sediment Control, processing of such material shall also be carried out in accordance with the Material and Construction requirements of MRTS16 Landscape and Revegetation Works.
a64c228e-0ff0-538e-8919-4865001d1aa2 | note | Reference - MRTS04 Cl. 7.2.4
45fb18c7-d68f-50d9-84c7-28f1290da0ef | note | Item Check - Check and Verify
157bcdbe-cc12-47c4-9fd5-32506c684894 | checkpoint | 5 - Fauna Habitat Logs
1e66f058-09d0-5c20-86ad-96e1a12581b1 | note | Acceptance Criteria: Hollow timber which is identified as being suitable for fauna habitat logs shall be relocated to areas clear of construction activities as follows:
1515f294-eb71-5fd2-89db-84f82b525616 | note | a) behind batters
7f26777c-2705-5af4-9e05-701e9c6380ba | note | b) behind proposed safety barriers but not within any hazard free zone, and
a0dfcb27-3620-5955-8721-ce0cc85c0c06 | note | c) areas at least 9 m clear of carriageways.
f733615b-d531-5895-88a7-40670c209f26 | note | Fauna habitat log density shall not exceed 20 m length per 100 m² area. Logs shall not be placed in waterways or in any area where they are likely to be struck by errant vehicles.
979ccb52-c959-5776-84fa-0fd111046f1c | note | Reference - MRTS04 Cl. 7.2.5
9efccf4c-6f7f-5613-a07e-aa7fd13c705a | note | Item Check - Check and Verify
09506ffe-cb2b-4aa6-8b1c-4890cb5b0e71 | checkpoint | 6 - Sugar Cane and Banana Plants
96715588-4136-5359-be34-513a45b0acf1 | note | Acceptance Criteria: Particular attention shall be taken to ensure that sugar cane and banana plant root systems are completely removed and disposed of. Any regrowth of sugar cane and/or banana plants occurring during the Contract, including the Defects Liability Period, shall be removed.
f340df70-b9b1-5132-8a23-79f9d3034d17 | note | Reference - MRTS04 Cl. 7.2.6
0f148595-fb69-5a76-8094-e2dbbb07ffdf | note | Item Check - Check and Verify
d5c327c7-71e9-43eb-bde4-b26afabc0af1 | checkpoint | 7- Disposal of Clear and Grub
283f1f23-1842-5232-ad6f-5fb943d2055e | note | Acceptance Criteria: Cleared and grubbed material other than that mulched under Clause 7.2.4 shall be disposed of in any areas stated in Clause 6 of Annexure MRTS04.1. If no such disposal instructions are stated, the cleared and grubbed material shall be removed from the Site and disposed of in accordance with all relevant Statutory Requirements including the requirements in MRTS51 Environmental Management.Any burning of cleared and grubbed materials shall be carried out strictly in accordance with the requirements of the Contract.
bced38b8-4f46-5c4f-895a-be23180d0d15 | note | Reference - MRTS04 Clause 7.2.8
4efd8280-0fbf-59e1-a771-6af772fdae9a | note | Item Check - Check and Verify
d0946237-c90c-4b1c-934b-a402847a9a42 | checkpoint | 8 - Additional Requirements:
e1419ce1-d35e-5ea4-8e4d-148d1b3e9fd5 | note | Acceptance Criteria: Within the limits of the clearing and grubbing, but clear of earthworks operations, any existing local irregularities of the natural surface are trimmed so as not to cause a hazard to errant vehicles. The surface is lightly compacted when necessary to provide a surface consistent with that existing prior to the Works
da166361-4837-57ab-bc8c-9ebced42818c | note | Reference - MRTS04 Clause 7.2.8
e149b3d2-0ced-5507-9188-b860d9e87587 | note | Item Check - Check and Verify
1d808446-ed19-469d-9fd8-29f6cf6b12ae | checkpoint | 9 - Vegetation Management
87c19001-8dc9-5df5-a6fc-8c4fa5a1f217 | note | Acceptance Criteria: The contractor shall identify all vegetation which is at risk of being destroyed or damaged as part of the works. Following the hierarchy, avoid, mitigate, offset, the contractor shall provide a vegetation management plan which provides detailed description of trees within the work zone, providing the details of:
07a44b1c-52cb-5387-b081-ccd10bb68366 | note | -Species
83fbcae5-8ed5-56a7-91d7-71745e1456ea | note | -Size (diameter of trunk at 1.3m above ground level)
f998d47b-a474-5f9f-a7d7-609031a3652a | note | -Proposal for removal or retention based on arborist advice (AQF level 5 or above).
e6c16f10-8d23-5c1d-96b6-9d8a4b2aa793 | note | For native vegetation removal, justification must be provided for Council’s project management deliberation.
29169abc-1f56-5f18-a62b-f709da868023 | note | Reference - Project Specification
39e97b0f-be4e-52b7-8b87-5df2d5c3a571 | note | Item Check - Check and Verify
2a21c8c1-a238-45d2-8bdc-def966569654 | checkpoint | 10 - Fauna Spotter
2c0a861b-ebca-5dd7-b92b-c9b14e2e6a44 | note | Acceptance Criteria: Fauna Spotter to be present when undertaking Tree Removals.
897a199d-bf32-53d2-8d5b-22789c2b0fe5 | note | Reference - Contract Specification
e9e892af-e1c7-55d6-85d4-a5bf90a15d0b | note | Item Check - Check and Verify
df6b3ac8-23a3-4c68-ba69-2c872907b5e4 | checkpoint | Final Verification
3ca333fb-0f5e-5926-9826-82280ae83ce1 | note | Name of Cient's Representative
7cb5bfc5-e41f-5cd2-9b58-c7c0b8db959e | textbox | Print Name:
cc75e62b-45d8-56a4-96cc-ea69f6dde480 | date | Date:
759b4152-9cc5-5f6b-a506-ae41402b37e1 | note | Name of Contractor's Representative
7a596745-c651-5ec0-831b-c2a12e4d3644 | textbox | Print Name:
6d04b1b9-5867-56cb-90f3-70a8e8bb3f39 | date | Date:
fc372490-8c47-4ab5-8697-4d4f871ccad7 | signoff | Signature
a6ab5777-7be4-4d82-a6ab-184392409213 | section | Final Sign Offs (to be completed at closure of Lot)
0333be49-ee06-41f0-92df-fa5f6515d094 | checkpoint | Agreed Quantities
73fa9fe2-478a-4c14-99f7-1da4a2eeb1ac | signoff | Agreed Quantities Sign Off
404953bf-0a3c-4d35-a264-beb26a290831 | checkpoint | Closure of Lot
deca9a3e-30b3-4f5b-a7aa-267b27808561 | signoff | Closure of Lot Sign Off