## Project
Project | Magate - Cox Street (DIA 6) - Drainage Upgrade Stage 2 | Lot Number | Date | Start | Finish
Project No | 25 006 | Location
Client | Moreton Bay Regional Council |  | Chainage | From | To
Contract No | VP437279 | Description

## Stormwater Pipe Installation
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Magate - Cox Street (DIA 6) - Drainage Upgrade Stage 2 |  | Lot Number |  |  |  |  | Date | Start | Finish
Project No |  | 25 006 |  | Location
Client |  | Moreton Bay Regional Council | [6 empty] | Chainage | From | To
Contract No |  | VP437279 |  | Description
Specification |  | NAT-SPEC / MRTS03 /04 |  | Activity | Stormwater Pipe Installation
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Lot Boundaries | [5 empty] | Check and Verify |  | N/A
Lot Number established with the Lot boundaries of the works clearly defined for traceability within Check and Verify N/A the works
2 | Materials |  |  |  |  | Note 2 IPEA STD DRW DS-030 | Check and Verify |  | N/A
Bed Zone Material: 5mm or 10mm screenings. Embedment Zone Material: 5mm or 10mm screenings Backfill Material: Granular fill comprising rock (75mm maximum size, non plastic open graded material) or crusher run recycled concrete.
3 | Geometric Tolerances |  |  |  |  | MRTS03 Cl 8 | Survey |  | N/A
Vertical: +- 10mm Horizontal +- 100mm
4 | Excavation |  |  |  |  | MRTS04 Cl13.3.3.1 | Check and Verify |  | N/A
Excavations shall be constructed to the shapes, lines, dimensions, and other requirements shown on the drawings
5 | Unsuitable Trench Foundation |  |  |  |  | MRTS04 Cl13.3.2 | Hold Point
Where Unsuitable Material or potentially Unsuitable Material is encountered on the Site, the Contractor shall, before proceeding to remove or cover such material, Hold Point notify the Administrator,
6 | Bandage Cover Materials |  |  |  |  | MRTS03 Cl 11.2 | Hold Point
Where Bandage covers are used for culverts, Bandages shall have properties appropriate to the sealing requirements and shall be made available for inspection and acceptance by the Administrator prior to commencement of installation.
7 | Trench Foundation |  |  |  |  | MRTS04 CL13.3.7 | Check and Verify |  | N/A
Testing: Bottom of Excavation Minimum Compaction 95%. 1 test per 20LM / Per Drainage
8 | Drainage of Bedding Materials |  |  |  |  | Note 1 IPEA STD DRW DS-030 | Check & Verify |  | N/A
Upstream of each headwall, manhole, or gully (other than an end of line gully), a 3.0 metre length of 100mm diameter sub-soil drainage pipe has been laid in the bedding material
Inspection and Test Plan
9 | Pipe Laying |  |  |  |  | MRTS03 CL11.3.5 | Check and Verify |  | N/A
Where spigot and socket joints are used, the thickness of bedding material under each socket shall not be less than 50 mm. Pipes shall be placed with their external grooved ends or spigot ends facing the culvert outlet. Where the word ‘TOP’ is marked on pipes or where lifting holes are provided, the pipes shall be laid with the word / hole uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed. Spigot and socket joints shall be made using the appropriate rubber rings
10 | Survey |  |  |  |  | MRTS03 CL11.3.10 | Hold Point
Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met and notice of such works provided to the Administrator
11 | Pipe Backfill - Road Reserve |  |  |  |  | MRTS03 CL11.3.10 | Check and Verify |  | N/A
Pipe backfill (bedding, haunch and overlay zones) shall be uniformly graded 5 or 10mm screenings and shall be backfilled up to subgrade level
12 | Pipe Backfill - Outside Road Reserve |  |  |  |  | Note 5 IPEA STD DRW DS-030 | Testing |  | N/A
Where stormwater pipe is laid in a drainage easement or property other than the road reserve, backfill material backfill material shall be excavated material provided adequate compaction can be provided. Compaction Testing: 1 test per 20LM / Per Drainage
14 | CCTV |  |  |  |  | MRTS03 CL11.3.5 | Hold Point
The contractor shall conduct inspections of the pipe culvert using CCTV in accordance with WSA 05-2013 Conduit inspection Report Code of Australia Reports shall be submitted to the Administrator, and any rectification works completed, prior to acceptance of the culvert
Comments
Final Sign off and Approval - Conformance with the Specification
Name of Client's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## RCBC Installation
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Magate - Cox Street (DIA 6) - Drainage Upgrade Stage 2 |  | Lot Number |  |  |  |  | Date | Start | Finish
Project No |  | 25 006 |  | Location
Client |  | Moreton Bay Regional Council | [6 empty] | Chainage | From | To
Contract No |  | VP437279 |  | Description
Specification |  | NAT-SPEC / MRTS03 / 04 |  | Activity | RCBC Installation
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Lot Boundaries | [5 empty] | Check and Verify |  | N/A
Lot Number established with the Lot boundaries of the works clearly defined for traceability within Check and Verify N/A the works
2 | Materials |  |  |  |  | Note 2 IPEA STD DRW DS-031 | Check and Verify |  | N/A
Below Slab: Concrete Blinder or Gravel Base Backfill Material: Approved Fill / Approved CBR15 Gravel
3 | Geometric Tolerances |  |  |  |  | MRTS03 Cl 8 | Survey |  | N/A
Vertical: +- 10mm Horizontal +- 100mm
4 | Excavation |  |  |  |  | MRTS04 Cl13.3.3.1 | Check and Verify |  | N/A
Excavations shall be constructed to the shapes, lines, dimensions, and other requirements shown on the drawings
5 | Unsuitable Trench Foundation |  |  |  |  | MRTS04 Cl13.3.2 | Hold Point
Where Unsuitable Material or potentially Unsuitable Material is encountered on the Site, the Contractor shall, before proceeding to remove or cover such material, Hold Point notify the Administrator,
6 | Bandage Cover Materials |  |  |  |  | MRTS03 Cl 11.2 | Hold Point
Where Bandage covers are used for culverts, Bandages shall have properties appropriate to the sealing requirements and shall be made available for inspection and acceptance by the Administrator prior to commencement of installation. Denso 600 - Min 75mm Wide
7 | Trench Foundation |  |  |  |  | MRTS04 CL13.3.7 | Check and Verify |  | N/A
Testing: Bottom of Excavation Minimum Compaction 95%. 1 test per 20LM / Per Drainage
8 | Drainage of Bedding Materials |  |  |  |  | Note 1 IPEA STD DRW DS-031 | Check & Verify |  | N/A
Upstream of each headwall, manhole, or gully (other than an end of line gully), a 3.0 metre length of 100mm diameter sub-soil drainage pipe has been laid in the bedding material
Inspection and Test Plan
9 | RCBC Special Requirements |  |  |  |  | MRTS03 MRTS 11.3.6 | Check and Verify |  | N/A
Box Culvert components shall generally be installed in accordance with the details shown on Standard Drawings 1250 , DS-031 and Project Drawings.
10 | Survey |  |  |  |  | MRTS03 CL11.3.10 | Hold Point
Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met and notice of such works provided to the Administrator
11 | RCBC Special Requirements |  |  |  |  | MRTS03 MRTS 11.3.6 | Check and Verify |  | N/A
Where specified, holding down anchors shall also be installed to retain the units in position in accordance with the details shown on Standard Drawings 1250,DS-031 and Project Drawings
14 | Material Requirements |  |  |  |  | MRTS03 CL. 10.2 | Check and Verify |  | N/A
Precast box culvert components and spanning slabs shall comply with MRTS24 Manufacture of Precast Concrete Culverts.
Comments
Final Sign off and Approval - Conformance with the Specification
Name of Client's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## CAG (hidden)
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Magate - Cox Street (DIA 6) - Drainage Upgrade Stage 2 |  | Lot Number |  |  |  |  | Date | Start | Finish
Project No |  | 25 006 |  | Location
Client |  | Moreton Bay Regional Council | [6 empty] | Chainage | From | To
Contract No |  | VP437279 |  | Description | Clearing and Grubbing
Specification |  | NAT-SPEC / MRTS04 |  | Activity | Clearing and Grubbing
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Areas to Clear and Grub |  |  |  |  | MRTS04 Clause 7.2.1 | Check and Verify |  | N/A
Clearing and grubbing operations shall be limited to those areas required to construct the Works and/or meet specified visibility requirements. As a minimum, the following clearing and grubbing shall be carried out: a) where earthworks are to be constructed, the minimum width required to construct the Works, plus an additional width of not more than the distance stated in Clause 1.1 of Annexure MRTS04.1 to this Technical Specification or 3 m where not so stated, or the property boundaries, whichever is the lesser, and b )other areas specified in Clause 1.2 of Annexure MRTS04.1 to this Technical Specification.
2 | Limitations |  |  |  |  | MRTS04 Clause 7.2.2 | HOLD POINT
Any trees, shrubs and overhanging branches to be left undisturbed shall be clearly marked by the Contractor. This marking shall be carried out prior to clearing operations reaching the areas concerned. HOLD POINT Clearing operations within streams and waterways shall not include removal of stumps and roots below ground surface. Beyond the areas to be cleared, only those trees, shrubs and overhanging branches which are shown on the drawings shall be removed or pruned, as necessary. Such removal or pruning shall only be carried out after consultation with the Administrator.
3 | Trees required by Administrator |  |  |  |  | MRTS04 Clause 7.2.3 | HOLD POINT
Any trees required by the Administrator for use as marketable timber shall be as nominated in Clause 2.3 of Annexure MRTS04.1. Such trees shall be clearly marked by the Contractor prior to clearing operations reaching the areas concerned. Marked trees shall be felled and handled in a manner which avoids damaging the trunks. The trunks of these trees shall be trimmed of branches and the trunks stacked in neat manageable stockpiles at locations approved by the Administrator at spacings of not more than 500 m.
4 | Material for Organic Mulch |  |  |  |  | MRTS04 Clause 7.2.4 | Check and Verify |  | N/A
Where site manufactured mulch is required in accordance with MRTS16 Landscape and Revegetation Works or MRTS52 Erosion and Sediment Control, processing of such material shall also be carried out in accordance with the Material and Construction requirements of MRTS16 Landscape and Revegetation Works.
5 | Fauna Habitat Logs |  |  |  |  | MRTS04 Clause 7.2.5 | Check and Verify |  | N/A
Hollow timber which is identified as being suitable for fauna habitat logs shall be relocated to areas clear of construction activities as follows: a) behind batters b) behind proposed safety barriers but not within any hazard free zone, and c) areas at least 9 m clear of carriageways. Fauna habitat log density shall not exceed 20 m length per 100 m² area. Logs shall not be placed in waterways or in any area where they are likely to be struck by errant vehicles.
Inspection and Test Plan
6 | Sugar Cane and Banana Plants |  |  |  |  | MRTS04 Clause 7.2.6 | Check and Verify |  | N/A
Particular attention shall be taken to ensure that sugar cane and banana plant root systems are completely removed and disposed of. Any regrowth of sugar cane and/or banana plants occurring during the Contract, including the Defects Liability Period, shall be removed.
7 | Disposal of Clear and Grub |  |  |  |  | MRTS04 Clause 7.2.8 | Check and Verify |  | N/A
Cleared and grubbed material other than that mulched under Clause 7.2.4 shall be disposed of in any areas stated in Clause 6 of Annexure MRTS04.1. If no such disposal instructions are stated, the cleared and grubbed material shall be removed from the Site and disposed of in accordance with all relevant Statutory Requirements including the requirements in MRTS51 Environmental Management.Any burning of cleared and grubbed materials shall be carried out strictly in accordance with the requirements of the Contract.
8 | Additional Requirements: |  |  |  |  | MRTS04 Clause 7.2.8 | Check and Verify |  | N/A
Within the limits of the clearing and grubbing, but clear of earthworks operations, any existing local irregularities of the natural surface are trimmed so as not to cause a hazard to errant vehicles. The surface is lightly compacted when necessary to provide a surface consistent with that existing prior to the Works
8 | Vegetation Management |  |  |  |  | Project Specification | Check and Verify |  | N/A
The contractor shall identify all vegetation which is at risk of being destroyed or damaged as part of the works. Following the hierarchy, avoid, mitigate, offset, the contractor shall provide a vegetation management plan which provides detailed description of trees within the work zone, providing the details of: - Species - Size (diameter of trunk at 1.3m above ground level) - Proposal for removal or retention based on arborist advice (AQF level 5 or above). For native vegetation removal, justification must be provided for Council’s project management deliberation.
8 | Fauna Spotter |  |  |  |  | Contract Specification | Check and Verify |  | N/A
Fauna Spotter to be present when undertaking Tree Removals.
Final Sign off and Approval - Conformance with the Specification
Name of Cient's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## CON (N)
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Magate - Cox Street (DIA 6) - Drainage Upgrade Stage 2 |  | Lot Number | CW | W2 | 001 |  | Date | Start | Finish
Project No |  | 25 006 |  | Location | Retaining Wall 2 |  |  |  |  | 2024-10-30 | 2024-11-29
Client |  | Moreton Bay Regional Council |  | Description | Retaining Wall 2 Installation |  |  |  | Chainage | From | To
Contract No |  | VP437279 | [7 empty] | 0 | 48.098
Specification |  | NAT-SPEC / MRTS70 |  | Activity | Concrete (Normal Class)
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Concrete Class |  |  |  |  | MRTS70 Clause 17.1 | Check and Verify |  | N/A
The strength grade of concrete and maximum nominal aggregate size used shall be as specified on the Drawings.
2 | Batching, mixing and transport |  |  |  |  | MRTS70 Clause 17.6 | Check and Verify |  | N/A
Batching, supply and delivery of concrete shall comply with AS 1379.
3 | Long distance travel and extended placement times |  |  |  |  | MRTS70 Clause 17.6.1 | MILESTONE
Where travel times are, by necessity, longer than 90 min as listed in AS 1379, a procedure for longdistance travel or extended placement times shall be submitted to the Administrator for approval six weeks before concreting begins.
4 | Acceptance and rejection of plastic concrete |  |  |  |  | MRTS70 Clause 17.7 | Check and Verify |  | N/A
The consistency and workability of concrete shall be such that it can be handled and transported without segregation and can be placed, worked and compacted into all corners, angles and narrow sections of forms, and around all reinforcement. Consistency testing shall be undertaken in accordance with AS 1379 (Note that AS 1379 requires a consistence test every time a sample is taken for strength testing)
5 | Acceptance and rejection of hardened concrete |  |  |  |  | MRTS70 Clause 17.8 | Check and Verify |  | N/A
Acceptance and rejection of hardened concrete shall be on a production assessment basis in accordance with AS 1379 except as noted below. Concrete for the following applications shall be tested on a project assessment basis, where more than 25 m³ of concrete is used: a) signpost footings and plinths with dimension greater than 150 mm b) spill through or rock grouting, and c) manually placed kerb and channel on or alongside concrete base. Project assessment (Clause 6.5 of AS 1379) requires sampling on the project site and testing 1 sample per 50 m³ of concrete
6 | Placing Concrete |  |  |  |  | MRTS70 Clause 17.12.1 | HOLD/ WITNESS POINT
No concrete shall be placed in the Works until: a) the formwork and reinforcement have been inspected, and b) all foreign material has been completely removed from the forms The Administrator may revert this Hold Point to a Witness Point. The placing operation shall be conducted in the presence of the Administrator and the Contractor shall give at least 24 hours notice to the Administrator of the time that placing shall start.
7 | Compaction of Concrete |  |  |  |  | MRTS70 Clause 17.12.2 | Check and Verify |  | N/A
Concrete shall be compacted to achieve dense and durable concrete, to the levels and tolerances specified.
Inspection and Test Plan
8 | Finishing |  |  |  |  | MRTS70 Clause 17.14.1 | Check and Verify |  | N/A
All unformed surfaces shall be finished true to line and level within the tolerances specified.
9 | Early Loading |  |  |  |  | MRTS70 Clause 15.9 | Check and Verify |  | N/A
Concrete shall not be loaded until three days has elapsed from the placement of a concrete slab on ground, and 70% of the specified characteristic strength has been obtained. Loads placed on or against any concrete shall be subject to approval by the Administrator.
10 | Curing |  |  |  |  | MRTS70 Clause 15.11.1 | Check and Verify |  | N/A
The curing of unformed surfaces of concrete shall commence as soon as the concrete surface has hardened. Curing shall continue for a minimum period of seven days. If forms are removed in less than seven days, curing of the formed surface shall commence within one hour of stripping, unless otherwise specified in Clause 15.12
Comments
Final Sign off and Approval - Conformance with the Specification
Name of Cient's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## CON (S)
Inspection and Test Plan
Project Information | [5 empty] | Inspection and Test Plan Information
Project |  | Magate - Cox Street (DIA 6) - Drainage Upgrade Stage 2 |  |  |  | Lot Number |  |  |  |  | Date | Start | Finish
Project No |  | 25 006 |  |  |  | Location
Client |  | Moreton Bay Regional Council | [8 empty] | Chainage | From | To
Contract No |  | VP437279 |  |  |  | Description
Specification |  | NAT-SPEC / MRTS70 |  |  |  | Activity | In-situ Concrete
Acceptance of Activity
# | Acceptance Criteria | [6 empty] | Reference | Item Check | QA | Client | Date | NCR
1 | Mix Designs | [6 empty] | MRTS70 Clause 15.1 | HOLD POINT
No concrete shall be placed in the Works until approval of the mix design has been obtained from the Administrator.
2 | Trial Mix | [6 empty] | MRTS70 Clause 15.1.1 | WITNESS POINT
When requested by the Administrator, and where extensive performance data is not available, mix design acceptance will be on the basis of trial mixes.
3 | Transport and Delivery | [6 empty] | MRTS70 Clause 10.4 | Check and Verify |  | N/A
Concrete shall be placed and compacted within the times from the discharging of the batch plant as per the below: < 32 °C = 60 minutes 32 – 35 °C = 45 minutes > 35 °C = Reject load These times may be extended at the Administrator's discretion.
4 | Long Distance Procedure | [6 empty] | MRTS70 Clause 10.4 | MILESTONE
Where travel or placement times are, by necessity, longer than those listed in Clause 10.4, a procedure for long-distance travel or extended placement times shall be submitted to the Administrator for approval 6 weeks before concreting begins.
5 | Slump Test | [6 empty] | MRTS70 Clause 11 | Check and Verify |  | N/A
The plastic material properties (slump) shall lie within the range established using the approved nominated value and the tolerances specified below: ≥ 60, ≤ 80 = ± 15 > 80, ≤ 110 = ± 20
6 | Testing Samples | [6 empty] | MRTS70 Clause 15.2.1 | Check and Verify |  | N/A
Samples for compression strength testing, shall be taken from separate batches of concrete during the placing operation. 1 - 3 Batches = Every Batch 4 - 10 Batches = 4 Samples 11-23 Batches = 5 Samples >23 Batches = n⁄4
7 | Temperature | [6 empty] | MRTS70 Clause 13.1 | Check and Verify |  | N/A
No concrete shall be placed in the works if the temperature of the concrete is less than 10 °C or exceeds 35 °C
8 | Hot Weather Procedure | [6 empty] | MRTS70 Clause 13.1 | MILESTONE
If the ambient air temperature measured at the point of placement is likely to exceed 35 °C, the Contractor shall take practical precautions, approved by the Administrator, to ensure that the temperature of the concrete does not exceed the permitted maximum. These precautions shall be submitted as a procedure for hot weather concreting at least two weeks prior to the first concrete pour.
Inspection and Test Plan
# | Acceptance Criteria | [6 empty] | Reference | Item Check | QA | Client | Date | NCR
9 | Rain Event | [6 empty] | MRTS70 Clause 13.3 | Check and Verify
Concrete shall not be poured in the rain or if rain is imminent unless adequate measures are taken to protect the plastic concrete from the falling rain.
10 | Early Stripping/Loading | [6 empty] | MRTS70 Clause 15.2.3 | Check and Verify |  | N/A
Any proposal by the Contractor for early removal of forms or for early application of significant loads to the structure shall be submitted in writing to the Administrator prior to placing concrete.
11 | Formwork | [6 empty] | MRTS70 Clause 15.4.1 | HOLD POINT
All formwork shall be subject to inspection and approval by the Administrator.
12 | Construction Joints | [6 empty] | MRTS70 Clause 15.13 | HOLD POINT
Construction joints shown in the Drawings are mandatory. The use of construction joints elsewhere in the concrete work shall require the prior approval of the Designer.
13 | Supports | [6 empty] | MRTS70 Clause 15.4.2 | Check and Verify |  | N/A
Bar chairs and/or spacers shall be placed sufficiently close together to ensure that the specified cover is maintained before and during concrete placement and to prevent any potential crushing of the spacers or penetration into the formwork.
14 | Foundations | [6 empty] | MRTS70 Clause 15.6.1 | Check and Verify |  | N/A
Where reinforced concrete is placed on earth, sand or rock foundations, the earth or sand shall be compacted to 95% Relative Compaction as determined by Test Method Q140A and the rock freed of loose material.
15 | Separator | [6 empty] | MRTS70 Clause 15.6.1 | Check and Verify |  | N/A
Where concrete work is constructed on ground surfaces or on a foundation bedding, a polythene sheet separator of thickness not less than 100 μm shall be employed between the ground/bedding and the concrete. The separator shall extend not less than 300 mm beyond the concrete work.
16 | Monitoring Procedure | [6 empty] | MRTS70 Clause 15.5 | MILESTONE
The Contractor shall submit a procedure and plan for monitoring and procedures for ensuring compliance to the Administrator for approval at least four weeks prior to the concrete pour.
17 | Curing Procedure | [6 empty] | MRTS70 Clause 15.11.1 | MILESTONE
The Contractor shall submit a procedure for curing, including methods and materials, to the Administrator for approval at least two weeks prior to the first concrete pour.
18 | Procedures | [6 empty] | MRTS70 Clause 15.6 | HOLD POINT
Concrete operations shall not commence until all relevant procedures have been approved by the Administrator.
19 | Placing and Compaction | [6 empty] | MRTS70 Clause 15.6.1 | HOLD POINT
No concrete shall be placed in the Works until: a) the formwork and reinforcement have been inspected b) all foreign material has been completely removed from the forms c) the mixing, batching, and compaction equipment have been approved by the Administrator.
20 | Placing Operation | [6 empty] | MRTS70 Clause 15.6.1 | WITNESS POINT
The placing operation shall be conducted in the presence of the Administrator and the Contractor shall give at least 24 hours notice to the Administrator of the time that placing shall start.
Inspection and Test Plan
# | Acceptance Criteria | [6 empty] | Reference | Item Check | QA | Client | Date | NCR
21 | Compaction | [6 empty] | MRTS70 Clause 15.6.2 | Check and Verify |  | N/A
Unless otherwise approved by the Administrator, or for concrete to be placed under water and for no-fines concrete, concrete shall be deposited in horizontal layers not more than 400 mm thick. Compaction of concrete shall commence immediately after deposition using high frequency vibrators.
22 | Removal of Formwork | [6 empty] | MRTS70 Clause 15.8 | HOLD POINT
Forms, falsework and centring shall remain in position until the times stated below have elapsed after completion of concreting: Class A = 48 Hours Class B1, B2 = 72 Hours Class C1, C2 = 120 Hours
23 | Removal of Formwork | [6 empty] | MRTS70 Clause 15.8 | WITNESSS POINT
Forms shall be removed with care, without hammering and wedging, and in a manner which shall not injure the concrete or disturb the remaining supports.
24 | Early Loading | [6 empty] | MRTS70 Clause 15.9 | Check and Verify |  | N/A
Concrete shall not be loaded until three days has elapsed from the placement of a concrete slab on ground, and 70% of the specified characteristic strength has been obtained. Loads placed on or against any concrete shall be subject to approval by the Administrator.
25 | Curing | [6 empty] | MRTS70 Clause 15.11.1 | Check and Verify |  | N/A
The curing of unformed surfaces of concrete shall commence as soon as the concrete surface has hardened. Curing shall continue for a minimum period of seven days. If forms are removed in less than seven days, curing of the formed surface shall commence within one hour of stripping, unless otherwise specified in Clause 15.12
Final Sign off and Approval - Conformance with the Specification
Name of Cient's Representative |  |  |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  |  |  | Signature |  |  |  |  | Date
No | Time In | Time out | Slump | Temp
1
2
3
4
5
6
7

## Pits
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Magate - Cox Street (DIA 6) - Drainage Upgrade Stage 2 |  | Lot Number |  |  |  |  | Date | Start | Finish
Project No |  | 25 006 |  | Location
Client |  | Moreton Bay Regional Council | [6 empty] | Chainage | From | To
Contract No |  | VP437279 |  | Description
Specification |  | NAT-SPEC / MRTS03/70 |  | Activity | Concrete Gullies and Access Chambers
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Location |  |  |  |  | MRTS03 Clause 21.3 | Check and Verify |  | N/A
Concrete gullies and chambers shall be provided in the locations specified by, and in accordance with, the drawings.
2 | Bottom of excavation |  |  |  |  | MRTS03 Clause 21.3 | Check and Verify |  | N/A
Where insitu material on or against which gullies are to be constructed is other than rock, the material shall be compacted as for material at the bottom of excavations in accordance with MRTS04 General Earthworks. Compaction Standard: >= 95%
4 | Foundation Bedding |  |  |  |  | MRTS03 Clause 21.3 | Check and Verify |  | N/A
Foundation bedding material shall be placed to provide continuous even support for the chambers and gullies.
3 | Backforms |  |  |  |  | MRTS03 Clause 21.3 | Check and Verify |  | N/A
Where the sides of excavations are in firm ground, the access chamber shafts may be constructed without the use of backforms. Where concrete is placed against the ground without the use of backforms, the specified wall thicknesses shall be increased by 20 mm
5 | Cast-Insitu Concrete |  |  |  |  | Concrete (Normal Class) - ITP | Check and Verify |  | N/A
Concrete Cast-insitu works shall be completed in accordance with requirements of Concrete (Normal Class) - ITP and attached.
5 | Joints |  |  |  |  | MRTS03 Clause 21.3 | Check and Verify |  | N/A
The joints between gullies and culverts shall be made watertight using cement mortar. The mortar shall be used within one hour of mixing and shall not be re-tempered. The joints shall be finished to provide smooth surfaces, uniform with the inner surfaces of the gullie
6 | Concrete Top Slab |  |  |  |  | MRTS03 Clause 21.3 | HOLD POINT
Concrete top slabs, inlet units or converter slabs as applicable on access chambers and gullies shall not be placed until all the surveying requirements have been met. Hold Point Concrete top slabs shall be joined to the shafts using cement mortar or epoxy mortar
Inspection and Test Plan
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
7 | Horizontal Tolerances |  |  |  |  | MRTS03 Clause 21.3 | Survey |  | N/A
The locations of gullies shall not vary from those specified in the drawings by more than ± 100 mm in the direction of the construction centre line and ± 50 mm in the direction at right angles to the construction centre line
8 | Vertical tolerances |  |  |  |  | MRTS03 Clause 21.3 | Survey |  | N/A
The invert heights of gullies shall not vary from those specified by the drawings by more than ± 50 mm, provided always that the gullies join neatly to existing drainage structures, do not pond water unnecessarily and are at heights compatible with other adjacent structures. The heights of the tops of back-units, grates and frames shall not vary from those described in the drawings by more than ± 10 mm.
9 | Removal of Formwork |  |  |  |  | MRTS70 Clause 15.8 (TMR Structures) | HOLD POINT
Forms, falsework and centring shall remain in position until the times stated below have elapsed after completion of concreting: Class A = 48 Hours Class B1, B2 = 72 Hours Class C1, C2 = 120 Hours
10 | Removal of Formwork |  |  |  |  | AS3610 Table B1 (Non - TMR Structures) |  |  | N/A
Comments
Final Sign off and Approval - Conformance with the Specification
Name of Cient's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## Unbound Pavements
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Magate - Cox Street (DIA 6) - Drainage Upgrade Stage 2 |  | Lot Number |  |  |  |  | Date | Start | Finish
Project No |  | 25 006 |  | Location
Client |  | Moreton Bay Regional Council | [6 empty] | Chainage | From | To
Contract No |  | VP437279 |  | Description
Specification |  | NAT-SPEC / MRTS05 |  | Activity | Asphalt
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Lot Size |  |  |  |  | MRTS05 App. A Table A1 | MILESTONE
Define lot size. Maximum lot size for unbound pavements is 5000 tonnes for supply and the lesser of "A single continuous layer completed in one day's production" and 500m for construction
2 | Submission of Registration Certificate per quarry |  |  |  |  | MRTS05 Cl.6.2 | MILESTONE
Copies of current Quarry Registration Certificate (Type 1, 2 or 3) or quarry assessment (Type 4) forwarded to the Administrator at least 7 working days before material deliveries to the stockpile / pavement are to commence.
3 | Approval of procedure by from the Administrator |  |  |  |  | MRTS05 Cl 5.2.1 | HOLD POINT
No unbound pavement works shall commence until all relevant construction procedure have been accepted by the Administrator
4 | Submission of production procedure |  |  |  |  | MRTS05 CL 5.2.2 | MILESTONE
The Material Production Procedures shall be submitted to the Administrator at least seven days prior to the commencement of material production for the Works
5 | Written Permission from Administrator |  |  |  |  | MRTS05 Cl.6.1 | HOLD POINT
The written permission from the Administrator to use the quarry or source is required prior to material being supplied to or used in the works
6 | Layer Thickness between 75mm and 250mm in accordance with table 8.3.3 |  |  |  |  | MRTS05 Table 8.3.3 | Check & Verify |  | N/A
Layer Thickness between 75mm and 250mm in accordance with table 8.3.3
7 | Relative Dry Density |  |  |  |  | MRTS05 Table 8.4.3 | Check & Verify |  | N/A
Relative Dry Density Requirements C.V of RDD >= 100% MDD for Type 1 Materials = 100% SDD for type 2.3, 2.4 and 2.5
Inspection and Test Plan
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
8 | Trial Placement |  |  |  |  | MRTS05 Cl. 8.2 | HOLD POINT
Unless agreed otherwise, a trial placement of materials of a minimum size of 1000m2 is required.
9 | Moisture Content |  |  |  |  | MRTS05 Table 8.3.4.1 | HOLD POINT
Moisture content such that the degree of saturation is less than 60%(modified). The administrator may accept a higher level of moisture up to a maximum of 70%. S < 60% (1 test / 500m2, min 4 / lot)
10 | Segregation of Material |  |  |  |  | MRTS05 Table A3 | Check & Verify |  | N/A
No visible segregation of material. Partical Size Distribution Q103A. Min 1 per lot Additional tests as directed by the Administrator
11 | Geometric Tolerances in accordance with MRTS05.1 Cl.8.4.4.3 ±10mm when covered by AC ±15 mm in all other cases (1 test / 20m) |  |  |  |  | MRTS05 Cl.8.4.4.2 Table A4 | Check & Verify |  | N/A
Geometric Tolerances in accordance with MRTS05.1 Cl.8.4.4.3 ±10mm when covered by AC ±15 mm in all other cases (1 test / 20m)
12 | Straight Edge |  |  |  |  | MRTS05 Cl. 8.4.5 | Check & Verify |  | N/A
Deviation from a 3m straight edge shall be less than 5mm. Straight Edge Test Less than 5mm 1 test per 20m
13 | Proof Roll |  |  |  |  | MRTS05 Cl.9.4.7 | WITNESS POINT
Each unbound pavement layer shall be tested for perceptable surface deformation by 'proof rolling' the pavement, in the presence of the Administrator. Visual Continuous testing
14 | Geometrics |  |  |  |  | MRTS05 Cl.8.4.4.4 | Check & Verify |  | N/A
Additional Geometrics (final layer only) The crossfall shall not depart from the corresponding crossfall shown in the Contract by more than 0.5% absolute. 0.5% deviation from crossfall (1 test / 25m)
15 | Visual Inspection |  |  |  |  | MRTS05 Cl.8.3.5.1 | Check & Verify |  | N/A
The finished surface of any unbound pavement layer shall: - be hard and homogenous in apperance - not have any loose, segregated or contaminated areas - have the coarse particles slightly exposed - not be affected by delamination, and - not visibly deflect under load when proof rolled in accordance with Cl 9.4.6
16 | Material Incorporation into Works |  |  |  |  | MRTS05 Cl.9.1 | HOLD POINT
The Contractor shall not incorporate materials into the work unless it has demonstrated that the material complies fully with the requirements of this Technical Specification before delivery of the material to site
17 | Survey |  |  |  |  | MRTS05 Cl.9.5.1 | HOLD POINT
Unless otherwise approved by the Administrator, no unbound pavement layer shall be covered by a subsequent layer of pavement or by a surfacing until Hold Point 6: a) all testing has been completed b) the surface finish of the layer complies with the requirements of Clause 8.3.5 c) all test results comply with the requirements of this Technical Specification, or any nonconformances have been submitted, with corrective actions proposed by the Contractor, and accepted by the Administrator d) the layer has been presented to the Administrator for inspection, and e) the As Constructed Survey requirements of the lot have been met as specified in MRTS56 Construction Surveying and notice of such works has been provided to the Administrator.
Final Sign off and Approval - Conformance with the Specification
Name of Cient's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## Demolition
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Magate - Cox Street (DIA 6) - Drainage Upgrade Stage 2 |  | Lot Number |  |  |  |  | Date | Start | Finish
Project No |  | 25 006 |  | Location
Client |  | Moreton Bay Regional Council | [6 empty] | Chainage | From | To
Contract No |  | VP437279 |  | Description
Specification |  | MRTS03 |  | Activity | Demolition of Drainage Structures/Concrete
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Establising Lot Number /Boundaries |  |  |  |  | MRTS 50 | Check and Verify |  | N/A
Lot Number established with the Lot boundaries of the works clearly defined for traceability within the works
2 | Safety Check |  |  |  |  | Induction | Check and Verify |  | N/A
All site personnel inducted (includes environment and cultural) - Required Safe Work Method Statements, Task Hazard Review Cards and Traffic Control Plans completed, signed and implemented. - Traffic Control devices installed as per the approved traffic control plan and traffic management plan.
3 | Services |  |  |  |  | DBYD | Check and Verify |  | N/A
All services identified – shall be marked, potholed and/or protected as required - Permit to excavate issued by Project Engineer
4 | Environmental Checks |  |  |  |  | CEMP, MRTS51 Cl 10.3, MRTS51.1 Cl4.1 | Check and Verify |  | N/A
Erosion and sediment controls in place - Vibration and Air quality to be monitored as a direct result of construction activities
5 | Removal/Demolition of Culverts and End Structures |  |  |  |  | MRTS03 Clause 9.2 | Check and Verify |  | N/A
Culverts and culvert end structures shall be removed or demolished where specified in the drawings. If existing culvert components are to be removed and re-used, they shall be removed and stacked in a manner which avoids damaging the components. Removed components which are not to be salvaged, nor reused, shall be removed from the Site and disposed. Excavations carried out and the void left by the removed culvert or end structure shall be backfilled to reinstate the area to a safe and free draining state.
6 | Removal/Demolition of Kerbs and Channels and Concrete Slabs |  |  |  |  | MRTS03 Clause 9.4 | Check and Verify |  | N/A
Existing kerbs, channels, kerbs and channels, kerb crossings and concrete slabs shall be removed or demolished where specified in the drawings. No damage shall result to adjacent works. Where part only and new kerbs, kerb and channels, kerb crossings and concrete slabs are to be joined to the remaining part, removing or demolition shall terminate at a joint. Alternatively, existing shall be sawn to provide a clean joint. Any resulting excavations shall be backfilled and the surface finished level with the surrounding area.
7 | Removal/Demolition of Gullies and Access Chambers |  |  |  |  | MRTS03 Clause 9.4 | Check and Verify |  | N/A
Gullies and access chambers shall be removed or demolished where specified in the drawings. Gullies and access chambers shall be removed or demolished in a manner which avoids damaging any adjacent work. Resulting excavations and voids shall be backfilled and the surface finished level with the surrounding area.
8 | Lot Closure |  |  |  |  | MRTS 50 | Check and Verify |  | N/A
Lot closure requires all relevant information to be attached to the Conformance Report this includes a Lot Plan, Survey Report, Hold Points/Approvals & any supporting documentation
Inspection and Test Plan
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
Comments
Final Sign off and Approval - Conformance with the Specification
Name of Cient's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## Subgrade
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Magate - Cox Street (DIA 6) - Drainage Upgrade Stage 2 |  | Lot Number |  |  |  |  | Date | Start | Finish
Project No |  | 25 006 |  | Location
Client |  | Moreton Bay Regional Council | [6 empty] | Chainage | From | To
Contract No |  | VP437279 |  | Description
Specification |  | MRTS04 |  | Activity | Subgrade Treatment
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Lot Boundries |  |  |  |  | MRTS 04 Cl 5.6 | Check and Verify |  | N/A
Lot Number established with the Lot boundaries of the works clearly defined for traceability within the works
2 | Subgrade Level |  |  |  |  | MRTS 04 Cl 13.3.2.1 | HOLD POINT
When the level of excavation has reached Subgrade Level plus a nominal allowance determined by the Contractor, the Contractor shall carry out the requirements of the relevant provisions of Clause 18.3.3 and cease excavation until the Subgrade treatment type has been determined in accordance with Clause 18.3.3.
3 | Proof Roll |  |  |  |  | MRTS 04 Cl 18.3.2 | Witness Point
At the completion of earthworks to Subgrade Level, the Contractor shall test for perceptible surface deformation by undertaking proof rolling. Witness Point 8
5 | Subgrade Treament |  |  |  |  | MRTS 04 Cl 18.3.3 | HOLD POINT
Subgrade Treatment Ordered: ____________________
6 | Subgrade Treament Type A |  |  |  |  | MRTS 04 Cl 18.3.3 | Check and Verify |  | N/A
For Subgrade treatment Type A, excavation shall be completed to Subgrade Level in accordance with Clause 13.3.1. The material below Subgrade Level shall be compacted as specified in Clause 15.3 to a characteristic value of compaction as specified in Table 15.3(b). The depth of compaction shall be as specified in Clause 12.3 of Annexure MRTS04.1 to this Technical Specification or, where no such depth is specified, to a depth of 150 mm.
7 | Subgrade Treatment Type C |  |  |  |  | MRTS 04 Cl 18.3.3 | Check and Verify |  | N/A
For Subgrade treatment Type C, excavation shall be continued to a depth below Subgrade Level as specified in Clause 12.3 of Annexure MRTS04.1 to this Technical Specification or, where no such depth is specified, to a depth of 150 mm. Excavation shall comply with the requirements of Clause 13.3.1. The excavation shall be backfilled to Subgrade Level with unbound granular material, in accordance with Clause 18.2.2, and shall be constructed as specified in MRTS05 Unbound Pavements to a characteristic value of compaction of not less than that specified in Table 15.3(b).
8 | Testing - Compaction |  |  |  |  | MRTS 04 Table A.2 - 2.1 | Test Reports 1 per 500m2 4 per Lot |  | N/A
Compaction - depth as per Clause 13.5 of Annexure MRTS04.1
8 | Geometrics - Straight Edge |  |  |  |  | MRTS 04 Table A.2 - 2.1 | Test Reports 1 Per 20m |  | N/A
The gap beneath a three metre-long straight-edge placed anywhere on the surface at Subgrade Level shall not exceed 25 mm, due allowance being made for design shape where relevant.
8 | Geometrics - Survey |  |  |  |  | MRTS 04 Table A.2 - 2.1 | Survey 20m Iintervals |  | N/A
The heights of earthworks measured anywhere on a layer surface shall not vary from those shown on the drawings, or calculated in accordance with Clause 6.1, by more than the tolerance stated in Table 6.3.1 unless specified otherwise. Subgrade Level (Individual Results): ± 25mm Subrade Level (Average): ± 10
Final Sign off and Approval - Conformance with the Specification
Name of Cient's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date