## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Stormwater Pipe Installation | itp
section | Details
checkpoint | 1 - Lot Boundaries
label | Acceptance Criteria - Lot Number established with the Lot boundaries of the works clearly defined for traceability within Check and Verify N/A the works
label | Item Check - Check and Verify
checkpoint | 2 - Materials
label | Acceptance Criteria - Bed Zone Material: 5mm or 10mm screenings.
label | ○ Embedment Zone Material: 5mm or 10mm screenings
label | ○ Backfill Material: Granular fill comprising rock (75mm maximum size, non plastic open graded material) or crusher run recycled concrete.
label | Reference - Note 2 IPEA STD DRW DS-030
label | Item Check - Check and Verify
checkpoint | 3 - Geometric Tolerances
label | Acceptance Criteria - Vertical: +- 10mm
label | ○ Horizontal +- 100mm
label | Reference - MRTS03 Cl 8
label | Item Check - Survey
checkpoint | 4 - Excavation
label | Acceptance Criteria - Excavations shall be constructed to the shapes, lines, dimensions, and other requirements shown on the drawings
label | Reference - MRTS04 Cl13.3.3.1
label | Item Check - Check and Verify
checkpoint | 5 - Unsuitable Trench Foundation
label | Acceptance Criteria - Where Unsuitable Material or potentially Unsuitable Material is encountered on the Site, the Contractor shall, before proceeding to remove or cover such material, Hold Point notify the Administrator,
label | Reference - MRTS04 Cl13.3.2
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | 6 - Bandage Cover Materials
label | Acceptance Criteria - Where Bandage covers are used for culverts, Bandages shall have properties appropriate to the sealing requirements and shall be made available for inspection and acceptance by the Administrator prior to commencement of installation.
label | Reference - MRTS03 Cl 11.2
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | 7 - Trench Foundation
label | Acceptance Criteria - Testing: Bottom of Excavation
label | ○ Minimum Compaction 95%.
label | ○ 1 test per 20LM / Per Drainage
label | Reference - MRTS04 CL13.3.7
label | Item Check - Check and Verify
checkpoint | 8 - Drainage of Bedding Materials
label | Acceptance Criteria - Upstream of each headwall, manhole, or gully (other than an end of line gully), a 3.0 metre length of 100mm diameter sub-soil drainage pipe has been laid in the bedding material
label | Reference - Note 1 IPEA STD DRW DS-030
label | Item Check - Check & Verify
checkpoint | 9 - Pipe Laying
label | Acceptance Criteria - Where spigot and socket joints are used, the thickness of bedding material under each socket shall not be less than 50 mm.
label | ○ Pipes shall be placed with their external grooved ends or spigot ends facing the culvert outlet.
label | ○ Where the word ‘TOP’ is marked on pipes or where lifting holes are provided, the pipes shall be laid with the word / hole uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed.
label | ○ Spigot and socket joints shall be made using the appropriate rubber rings
label | Reference - MRTS03 CL11.3.5
label | Item Check - Check and Verify
checkpoint | 10 - Survey
label | Acceptance Criteria - Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met and notice of such works provided to the Administrator
label | Reference - MRTS03 CL11.3.10
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | 11 - Pipe Backfill - Road Reserve
label | Acceptance Criteria - Pipe backfill (bedding, haunch and overlay zones) shall be uniformly graded 5 or 10mm screenings and shall be backfilled up to subgrade level
label | Reference - MRTS03 CL11.3.10
label | Item Check - Check and Verify
checkpoint | 12 - Pipe Backfill - Outside Road Reserve
label | Acceptance Criteria - Where stormwater pipe is laid in a drainage easement or property other than the road reserve, backfill material backfill material shall be excavated material provided adequate compaction can be provided.
label | ○ Compaction Testing: 1 test per 20LM / Per Drainage
label | Reference - Note 5 IPEA STD DRW DS-030
label | Item Check - Testing
checkpoint | 14 - CCTV
label | Acceptance Criteria - The contractor shall conduct inspections of the pipe culvert using CCTV in accordance with WSA 05-2013 Conduit inspection Report Code of Australia
label | ○ Reports shall be submitted to the Administrator, and any rectification works completed, prior to acceptance of the culvert
label | Reference - MRTS03 CL11.3.5
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | Final Verification
note | Name of Client's Representative
textbox | Print Name:
date | Date:
note | Name of Contractor's Representative
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | RCBC Installation | itp
section | Details
checkpoint | 1 - Lot Boundaries
label | Acceptance Criteria - Lot Number established with the Lot boundaries of the works clearly defined for traceability within Check and Verify N/A the works
label | Item Check - Check and Verify
checkpoint | 2 - Materials
label | Acceptance Criteria - Below Slab: Concrete Blinder or Gravel Base
label | ○ Backfill Material: Approved Fill / Approved CBR15 Gravel
label | Reference - Note 2 IPEA STD DRW DS-031
label | Item Check - Check and Verify
checkpoint | 3 - Geometric Tolerances
label | Acceptance Criteria - Vertical: +- 10mm
label | ○ Horizontal +- 100mm
label | Reference - MRTS03 Cl 8
label | Item Check - Survey
checkpoint | 4 - Excavation
label | Acceptance Criteria - Excavations shall be constructed to the shapes, lines, dimensions, and other requirements shown on the drawings
label | Reference - MRTS04 Cl13.3.3.1
label | Item Check - Check and Verify
checkpoint | 5 - Unsuitable Trench Foundation
label | Acceptance Criteria - Where Unsuitable Material or potentially Unsuitable Material is encountered on the Site, the Contractor shall, before proceeding to remove or cover such material, Hold Point notify the Administrator,
label | Reference - MRTS04 Cl13.3.2
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | 6 - Bandage Cover Materials
label | Acceptance Criteria - Where Bandage covers are used for culverts, Bandages shall have properties appropriate to the sealing requirements and shall be made available for inspection and acceptance by the Administrator prior to commencement of installation.
label | ○ Denso 600 - Min 75mm Wide
label | Reference - MRTS03 Cl 11.2
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | 7 - Trench Foundation
label | Acceptance Criteria - Testing: Bottom of Excavation
label | ○ Minimum Compaction 95%.
label | ○ 1 test per 20LM / Per Drainage
label | Reference - MRTS04 CL13.3.7
label | Item Check - Check and Verify
checkpoint | 8 - Drainage of Bedding Materials
label | Acceptance Criteria - Upstream of each headwall, manhole, or gully (other than an end of line gully), a 3.0 metre length of 100mm diameter sub-soil drainage pipe has been laid in the bedding material
label | Reference - Note 1 IPEA STD DRW DS-031
label | Item Check - Check & Verify
checkpoint | 9 - RCBC Special Requirements
label | Acceptance Criteria - Box Culvert components shall generally be installed in accordance with the details shown on Standard Drawings 1250 , DS-031 and Project Drawings.
label | Reference - MRTS03, MRTS 11.3.6
label | Item Check - Check and Verify
checkpoint | 10 - Survey
label | Acceptance Criteria - Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met and notice of such works provided to the Administrator
label | Reference - MRTS03 CL11.3.10
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | 11 - RCBC Special Requirements
label | Acceptance Criteria - Where specified, holding down anchors shall also be installed to retain the units in position in accordance with the details shown on Standard Drawings 1250,DS-031 and Project Drawings
label | Reference - MRTS03, MRTS 11.3.6
label | Item Check - Check and Verify
checkpoint | 14 - Material Requirements
label | Acceptance Criteria - Precast box culvert components and spanning slabs shall comply with MRTS24 Manufacture of Precast Concrete Culverts.
label | Reference - MRTS03 CL. 10.2
label | Item Check - Check and Verify
checkpoint | Final Verification
note | Name of Client's Representative
textbox | Print Name:
date | Date:
note | Name of Contractor's Representative
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | Concrete (Normal Class) | itp
section | Details
checkpoint | 1 - Concrete Class
label | Acceptance Criteria - The strength grade of concrete and maximum nominal aggregate size used shall be as specified on the Drawings.
label | Reference - MRTS70 Clause 17.1
label | Item Check - Check and Verify
checkpoint | 2 - Batching, mixing and transport
label | Acceptance Criteria - Batching, supply and delivery of concrete shall comply with AS 1379.
label | Reference - MRTS70 Clause 17.6
label | Item Check - Check and Verify
checkpoint | 3 - Long distance travel and extended placement times
label | Acceptance Criteria - Where travel times are, by necessity, longer than 90 min as listed in AS 1379, a procedure for longdistance travel or extended placement times shall be submitted to the Administrator for approval six weeks before concreting begins.
label | Reference - MRTS70 Clause 17.6.1
label | Item Check - MILESTONE
checkpoint | 4 - Acceptance and rejection of plastic concrete
label | Acceptance Criteria - The consistency and workability of concrete shall be such that it can be handled and transported without segregation and can be placed, worked and compacted into all corners, angles and narrow sections of forms, and around all reinforcement.
label | ○ Consistency testing shall be undertaken in accordance with AS 1379 (Note that AS 1379 requires a consistence test every time a sample is taken for strength testing)
label | Reference - MRTS70 Clause 17.7
label | Item Check - Check and Verify
checkpoint | 5 - Acceptance and rejection of hardened concrete
label | Acceptance Criteria - Acceptance and rejection of hardened concrete shall be on a production assessment basis in accordance with AS 1379 except as noted below. Concrete for the following applications shall be tested on a project assessment basis, where more than 25 m³ of concrete is used:
label | a) signpost footings and plinths with dimension greater than 150 mm
label | b) spill through or rock grouting, and
label | c) manually placed kerb and channel on or alongside concrete base.
label | ○ Project assessment (Clause 6.5 of AS 1379) requires sampling on the project site and testing 1 sample per 50 m³ of concrete
label | Reference - MRTS70 Clause 17.8
label | Item Check - Check and Verify
checkpoint | 6 - Placing Concrete
label | Acceptance Criteria - No concrete shall be placed in the Works until:
label | a) the formwork and reinforcement have been inspected, and
label | b) all foreign material has been completely removed from the forms
label | ○ The Administrator may revert this Hold Point to a Witness Point.
label | ○ The placing operation shall be conducted in the presence of the Administrator and the Contractor shall give at least 24 hours notice to the Administrator of the time that placing shall start.
label | Reference - MRTS70 Clause 17.12.1
label | Item Check - HOLD/ WITNESS POINT
holdpoint | HOLD POINT
checkpoint | 7 - Compaction of Concrete
label | Acceptance Criteria - Concrete shall be compacted to achieve dense and durable concrete, to the levels and tolerances specified.
label | Reference - MRTS70 Clause 17.12.2
label | Item Check - Check and Verify
checkpoint | 8 - Finishing
label | Acceptance Criteria - All unformed surfaces shall be finished true to line and level within the tolerances specified.
label | Reference - MRTS70 Clause 17.14.1
label | Item Check - Check and Verify
checkpoint | 9 - Early Loading
label | Acceptance Criteria - Concrete shall not be loaded until three days has elapsed from the placement of a concrete slab on ground, and 70% of the specified characteristic strength has been obtained. Loads placed on or against any concrete shall be subject to approval by the Administrator.
label | Reference - MRTS70 Clause 15.9
label | Item Check - Check and Verify
checkpoint | 10 - Curing
label | Acceptance Criteria - The curing of unformed surfaces of concrete shall commence as soon as the concrete surface has hardened. Curing shall continue for a minimum period of seven days. If forms are removed in less than seven days, curing of the formed surface shall commence within one hour of stripping, unless otherwise specified in Clause 15.12
label | Reference - MRTS70 Clause 15.11.1
label | Item Check - Check and Verify
checkpoint | Final Verification
note | Name of Client's Representative
textbox | Print Name:
date | Date:
note | Name of Contractor's Representative
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | In-situ Concrete | itp
section | Details
checkpoint | 1 - Mix Designs
label | Acceptance Criteria - No concrete shall be placed in the Works until approval of the mix design has been obtained from the Administrator.
label | Reference - MRTS70 Clause 15.1
label | Item Check - HOLD POINT
holdpoint | HOLD POINT
checkpoint | 2 - Trial Mix
label | Acceptance Criteria - When requested by the Administrator, and where extensive performance data is not available, mix design acceptance will be on the basis of trial mixes.
label | Reference - MRTS70 Clause 15.1.1
label | Item Check - WITNESS POINT
checkpoint | 3 - Transport and Delivery
label | Acceptance Criteria - Concrete shall be placed and compacted within the times from the discharging of the batch plant as per the below:
label | < 32 °C = 60 minutes
label | 32 – 35 °C = 45 minutes
label | > 35 °C = Reject load
label | ○ These times may be extended at the Administrator's discretion.
label | Reference - MRTS70 Clause 10.4
label | Item Check - Check and Verify
checkpoint | 4 - Long Distance Procedure
label | Acceptance Criteria - Where travel or placement times are, by necessity, longer than those listed in Clause 10.4, a procedure for long-distance travel or extended placement times shall be submitted to the Administrator for approval 6 weeks before concreting begins.
label | Reference - MRTS70 Clause 10.4
label | Item Check - MILESTONE
checkpoint | 5 - Slump Test
label | Acceptance Criteria - The plastic material properties (slump) shall lie within the range established using the approved nominated value and the tolerances specified below:
label | ≥ 60, ≤ 80 = ± 15
label | > 80, ≤ 110 = ± 20
label | Reference - MRTS70 Clause 11
label | Item Check - Check and Verify
checkpoint | 6 - Testing Samples
label | Acceptance Criteria - Samples for compression strength testing, shall be taken from separate batches of concrete during the placing operation.
label | ○ 1 - 3 Batches = Every Batch
label | ○ 4 - 10 Batches = 4 Samples
label | ○ 11-23 Batches = 5 Samples
label | ○ >23 Batches = n⁄4
label | Reference - MRTS70 Clause 15.2.1
label | Item Check - Check and Verify
checkpoint | 7 - Temperature
label | Acceptance Criteria - No concrete shall be placed in the works if the temperature of the concrete is less than 10 °C or exceeds 35 °C
label | Reference - MRTS70 Clause 13.1
label | Item Check - Check and Verify
checkpoint | 8 - Hot Weather Procedure
label | Acceptance Criteria - If the ambient air temperature measured at the point of placement is likely to exceed 35 °C, the Contractor shall take practical precautions, approved by the Administrator, to ensure that the temperature of the concrete does not exceed the permitted maximum. These precautions shall be submitted as a procedure for hot weather concreting at least two weeks prior to the first concrete pour.
label | Reference - MRTS70 Clause 13.1
label | Item Check - MILESTONE
checkpoint | 9 - Rain Event
label | Acceptance Criteria - Concrete shall not be poured in the rain or if rain is imminent unless adequate measures are taken to protect the plastic concrete from the falling rain.
label | Reference - MRTS70 Clause 13.3
label | Item Check - Check and Verify
checkpoint | 10 - Early Stripping/Loading
label | Acceptance Criteria - Any proposal by the Contractor for early removal of forms or for early application of significant loads to the structure shall be submitted in writing to the Administrator prior to placing concrete.
label | Reference - MRTS70 Clause 15.2.3
label | Item Check - Check and Verify
checkpoint | 11 - Formwork
label | Acceptance Criteria - All formwork shall be subject to inspection and approval by the Administrator.
label | Reference - MRTS70 Clause 15.4.1
label | Item Check - HOLD POINT
holdpoint | HOLD POINT
checkpoint | 12 - Construction Joints
label | Acceptance Criteria - Construction joints shown in the Drawings are mandatory. The use of construction joints elsewhere in the concrete work shall require the prior approval of the Designer.
label | Reference - MRTS70 Clause 15.13
label | Item Check - HOLD POINT
holdpoint | HOLD POINT
checkpoint | 13 - Supports
label | Acceptance Criteria - Bar chairs and/or spacers shall be placed sufficiently close together to ensure that the specified cover is maintained before and during concrete placement and to prevent any potential crushing of the spacers or penetration into the formwork.
label | Reference - MRTS70 Clause 15.4.2
label | Item Check - Check and Verify
checkpoint | 14 - Foundations
label | Acceptance Criteria - Where reinforced concrete is placed on earth, sand or rock foundations, the earth or sand shall be compacted to 95% Relative Compaction as determined by Test Method Q140A and the rock freed of loose material.
label | Reference - MRTS70 Clause 15.6.1
label | Item Check - Check and Verify
checkpoint | 15 - Separator
label | Acceptance Criteria - Where concrete work is constructed on ground surfaces or on a foundation bedding, a polythene sheet separator of thickness not less than 100 μm shall be employed between the ground/bedding and the concrete. The separator shall extend not less than 300 mm beyond the concrete work.
label | Reference - MRTS70 Clause 15.6.1
label | Item Check - Check and Verify
checkpoint | 16 - Monitoring Procedure
label | Acceptance Criteria - The Contractor shall submit a procedure and plan for monitoring and procedures for ensuring compliance to the Administrator for approval at least four weeks prior to the concrete pour.
label | Reference - MRTS70 Clause 15.5
label | Item Check - MILESTONE
checkpoint | 17 - Curing Procedure
label | Acceptance Criteria - The Contractor shall submit a procedure for curing, including methods and materials, to the Administrator for approval at least two weeks prior to the first concrete pour.
label | Reference - MRTS70 Clause 15.11.1
label | Item Check - MILESTONE
checkpoint | 18 - Procedures
label | Acceptance Criteria - Concrete operations shall not commence until all relevant procedures have been approved by the Administrator.
label | Reference - MRTS70 Clause 15.6
label | Item Check - HOLD POINT
holdpoint | HOLD POINT
checkpoint | 19 - Placing and Compaction
label | Acceptance Criteria - No concrete shall be placed in the Works until:
label | a) the formwork and reinforcement have been inspected
label | b) all foreign material has been completely removed from the forms
label | c) the mixing, batching, and compaction equipment have been approved by the Administrator.
label | Reference - MRTS70 Clause 15.6.1
label | Item Check - HOLD POINT
holdpoint | HOLD POINT
checkpoint | 20 - Placing Operation
label | Acceptance Criteria - The placing operation shall be conducted in the presence of the Administrator and the Contractor shall give at least 24 hours notice to the Administrator of the time that placing shall start.
label | Reference - MRTS70 Clause 15.6.1
label | Item Check - WITNESS POINT
checkpoint | 21 - Compaction
label | Acceptance Criteria - Unless otherwise approved by the Administrator, or for concrete to be placed under water and for no-fines concrete, concrete shall be deposited in horizontal layers not more than 400 mm thick. Compaction of concrete shall commence immediately after deposition using high frequency vibrators.
label | Reference - MRTS70 Clause 15.6.2
label | Item Check - Check and Verify
checkpoint | 22 - Removal of Formwork
label | Acceptance Criteria - Forms, falsework and centring shall remain in position until the times stated below have elapsed after completion of concreting:
label | ○ Class A = 48 Hours
label | ○ Class B1, B2 = 72 Hours
label | ○ Class C1, C2 = 120 Hours
label | Reference - MRTS70 Clause 15.8
label | Item Check - HOLD POINT
holdpoint | HOLD POINT
checkpoint | 23 - Removal of Formwork
label | Acceptance Criteria - Forms shall be removed with care, without hammering and wedging, and in a manner which shall not injure the concrete or disturb the remaining supports.
label | Reference - MRTS70 Clause 15.8
label | Item Check - WITNESSS POINT
checkpoint | 24 - Early Loading
label | Acceptance Criteria - Concrete shall not be loaded until three days has elapsed from the placement of a concrete slab on ground, and 70% of the specified characteristic strength has been obtained. Loads placed on or against any concrete shall be subject to approval by the Administrator.
label | Reference - MRTS70 Clause 15.9
label | Item Check - Check and Verify
checkpoint | 25 - Curing
label | Acceptance Criteria - The curing of unformed surfaces of concrete shall commence as soon as the concrete surface has hardened. Curing shall continue for a minimum period of seven days. If forms are removed in less than seven days, curing of the formed surface shall commence within one hour of stripping, unless otherwise specified in Clause 15.12
label | Reference - MRTS70 Clause 15.11.1
label | Item Check - Check and Verify
checkpoint | Final Verification
note | Name of Client's Representative
textbox | Print Name:
date | Date:
note | Name of Contractor's Representative
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | Concrete Gullies and Access Chambers | itp
section | Details
checkpoint | 1 - Location
label | Acceptance Criteria - Concrete gullies and chambers shall be provided in the locations specified by, and in accordance with, the drawings.
label | Reference - MRTS03 Clause 21.3
label | Item Check - Check and Verify
checkpoint | 2 - Bottom of excavation
label | Acceptance Criteria - Where insitu material on or against which gullies are to be constructed is other than rock, the material shall be compacted as for material at the bottom of excavations in accordance with MRTS04 General Earthworks.
label | ○ Compaction Standard: >= 95%
label | Reference - MRTS03 Clause 21.3
label | Item Check - Check and Verify
checkpoint | 4 - Foundation Bedding
label | Acceptance Criteria - Foundation bedding material shall be placed to provide continuous even support for the chambers and gullies.
label | Reference - MRTS03 Clause 21.3
label | Item Check - Check and Verify
checkpoint | 3 - Backforms
label | Acceptance Criteria - Where the sides of excavations are in firm ground, the access chamber shafts may be constructed without the use of backforms. Where concrete is placed against the ground without the use of backforms, the specified wall thicknesses shall be increased by 20 mm
label | Reference - MRTS03 Clause 21.3
label | Item Check - Check and Verify
checkpoint | 5 - Cast-Insitu Concrete
label | Acceptance Criteria - Concrete Cast-insitu works shall be completed in accordance with requirements of Concrete (Normal Class) - ITP and attached.
label | Reference - Concrete (Normal Class) - ITP
label | Item Check - Check and Verify
checkpoint | 5 - Joints
label | Acceptance Criteria - The joints between gullies and culverts shall be made watertight using cement mortar. The mortar shall be used within one hour of mixing and shall not be re-tempered. The joints shall be finished to provide smooth surfaces, uniform with the inner surfaces of the gullie
label | Reference - MRTS03 Clause 21.3
label | Item Check - Check and Verify
checkpoint | 6 - Concrete Top Slab
label | Acceptance Criteria - Concrete top slabs, inlet units or converter slabs as applicable on access chambers and gullies shall not be placed until all the surveying requirements have been met. Hold Point
label | ○ Concrete top slabs shall be joined to the shafts using cement mortar or epoxy mortar
label | Reference - MRTS03 Clause 21.3
label | Item Check - HOLD POINT
holdpoint | HOLD POINT
checkpoint | 7 - Horizontal Tolerances
label | Acceptance Criteria - The locations of gullies shall not vary from those specified in the drawings by more than ± 100 mm in the direction of the construction centre line and ± 50 mm in the direction at right angles to the construction centre line
label | Reference - MRTS03 Clause 21.3
label | Item Check - Survey
checkpoint | 8 - Vertical tolerances
label | Acceptance Criteria - The invert heights of gullies shall not vary from those specified by the drawings by more than ± 50 mm, provided always that the gullies join neatly to existing drainage structures, do not pond water unnecessarily and are at heights compatible with other adjacent structures. The heights of the tops of back-units, grates and frames shall not vary from those described in the drawings by more than ± 10 mm.
label | Reference - MRTS03 Clause 21.3
label | Item Check - Survey
checkpoint | 9 - Removal of Formwork
label | Acceptance Criteria - Forms, falsework and centring shall remain in position until the times stated below have elapsed after completion of concreting:
label | ○ Class A = 48 Hours
label | ○ Class B1, B2 = 72 Hours
label | ○ Class C1, C2 = 120 Hours
label | Reference - MRTS70 Clause 15.8 (TMR Structures)
label | Item Check - HOLD POINT
holdpoint | HOLD POINT
checkpoint | 10 - Removal of Formwork
label | Acceptance Criteria - TABLE B1
label | VERTICAL FACE FORMWORK STRIPPING TIMES
label | — — — — — — — — — —
label | Classification ¦¦ Average Temperature (Greater than 20°C ¦ Between 12°C and 20°C ¦ Between 5°C and 12°C)
label | Class 1, Class 2 or Class 3 (see note 1) ¦¦ 1 d ¦ 2d ¦ 3d
label | Class 4 or Class 5 ¦¦ 9 h ¦ 12 h ¦ 18 h
label | — — — — — — — — — —
label | Reference - AS3610 Table B1 (Non - TMR Structures)
checkpoint | Final Verification
note | Name of Client's Representative
textbox | Print Name:
date | Date:
note | Name of Contractor's Representative
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | Unbound Pavements | itp
section | Details
checkpoint | 1 - Lot Size
label | Acceptance Criteria - Define lot size. Maximum lot size for unbound pavements is 5000 tonnes for supply and the lesser of "A single continuous layer completed in one day's production" and 500m for construction
label | Reference - MRTS05 App. A Table A1
label | Item Check - MILESTONE
checkpoint | 2 - Submission of Registration Certificate per quarry
label | Acceptance Criteria - Copies of current Quarry Registration Certificate (Type 1, 2 or 3) or quarry assessment (Type 4) forwarded to the Administrator at least 7 working days before material deliveries to the stockpile / pavement are to commence.
label | Reference - MRTS05 Cl.6.2
label | Item Check - MILESTONE
checkpoint | 3 - Approval of procedure by from the Administrator
label | Acceptance Criteria - No unbound pavement works shall commence until all relevant construction procedure have been accepted by the Administrator
label | Reference - MRTS05 Cl 5.2.1
label | Item Check - HOLD POINT
holdpoint | HOLD POINT
checkpoint | 4 - Submission of production procedure
label | Acceptance Criteria - The Material Production Procedures shall be submitted to the Administrator at least seven days prior to the commencement of material production for the Works
label | Reference - MRTS05 CL 5.2.2
label | Item Check - MILESTONE
checkpoint | 5 - Written Permission from Administrator
label | Acceptance Criteria - The written permission from the Administrator to use the quarry or source is required prior to material being supplied to or used in the works
label | Reference - MRTS05 Cl.6.1
label | Item Check - HOLD POINT
holdpoint | HOLD POINT
checkpoint | 6 - Layer Thickness between 75mm and 250mm in accordance with table 8.3.3
label | Acceptance Criteria - Layer Thickness between 75mm and 250mm in accordance with table 8.3.3
label | Reference - MRTS05 Table 8.3.3
label | Item Check - Check & Verify
checkpoint | 7 - Relative Dry Density
label | Acceptance Criteria - Relative Dry Density Requirements
label | C.V of RDD >
label | = 100% MDD for Type 1 Materials
label | = 100% SDD for type 2.3, 2.4 and 2.5
label | Reference - MRTS05 Table 8.4.3
label | Item Check - Check & Verify
checkpoint | 8 - Trial Placement
label | Acceptance Criteria - Unless agreed otherwise, a trial placement of materials of a minimum size of 1000m2 is required.
label | Reference - MRTS05 Cl. 8.2
label | Item Check - HOLD POINT
holdpoint | HOLD POINT
checkpoint | 9 - Moisture Content
label | Acceptance Criteria - Moisture content such that the degree of saturation is less than 60%(modified). The administrator may accept a higher level of moisture up to a maximum of 70%.
label | S < 60%
label | (1 test / 500m2, min 4 / lot)
label | Reference - MRTS05 Table 8.3.4.1
label | Item Check - HOLD POINT
holdpoint | HOLD POINT
checkpoint | 10 - Segregation of Material
label | Acceptance Criteria - No visible segregation of material. Partical Size Distribution Q103A.
label | ○ Min 1 per lot
label | ○ Additional tests as directed by the Administrator
label | Reference - MRTS05 Table A3
label | Item Check - Check & Verify
checkpoint | 11 - Geometric Tolerances in accordance with MRTS05.1 Cl.8.4.4.3
label | ±10mm when covered by AC
label | ±15 mm in all other cases
label | (1 test / 20m)
label | Acceptance Criteria - Geometric Tolerances in accordance with MRTS05.1 Cl.8.4.4.3
label | ○ ±10mm when covered by AC
label | ○ ±15 mm in all other cases
label | ○ (1 test / 20m)
label | Reference - MRTS05 Cl.8.4.4.2 Table A4
label | Item Check - Check & Verify
checkpoint | 12 - Straight Edge
label | Acceptance Criteria - Deviation from a 3m straight edge shall be less than 5mm.
label | Straight Edge Test
label | ○ Less than 5mm
label | ○ 1 test per 20m
label | Reference - MRTS05 Cl. 8.4.5
label | Item Check - Check & Verify
checkpoint | 13 - Proof Roll
label | Acceptance Criteria - Each unbound pavement layer shall be tested for perceptable surface deformation by 'proof rolling' the pavement, in the presence of the Administrator.
label | ○ Visual
label | ○ Continuous testing
label | Reference - MRTS05 Cl.9.4.7
label | Item Check - WITNESS POINT
checkpoint | 14 - Geometrics
label | Acceptance Criteria - Additional Geometrics (final layer only)
label | ○ The crossfall shall not depart from the corresponding crossfall shown in the Contract by more than 0.5% absolute.
label | ○ 0.5% deviation from crossfall (1 test / 25m)
label | Reference - MRTS05 Cl.8.4.4.4
label | Item Check - Check & Verify
checkpoint | 15 - Visual Inspection
label | Acceptance Criteria - The finished surface of any unbound pavement layer shall:
label | — be hard and homogenous in apperance
label | — not have any loose, segregated or contaminated areas
label | — have the coarse particles slightly exposed
label | — not be affected by delamination, and
label | — not visibly deflect under load when proof rolled in accordance with Cl 9.4.6
label | Reference - MRTS05 Cl.8.3.5.1
label | Item Check - Check & Verify
checkpoint | 16 - Material Incorporation into Works
label | Acceptance Criteria - The Contractor shall not incorporate materials into the work unless it has demonstrated that the material complies fully with the requirements of this Technical Specification before delivery of the material to site
label | Reference - MRTS05 Cl.9.1
label | Item Check - HOLD POINT
holdpoint | HOLD POINT
checkpoint | 17 - Survey
label | Acceptance Criteria - Unless otherwise approved by the Administrator, no unbound pavement layer shall be covered by a subsequent layer of pavement or by a surfacing until Hold Point 6:
label | a) all testing has been completed
label | b) the surface finish of the layer complies with the requirements of Clause 8.3.5
label | c) all test results comply with the requirements of this Technical Specification, or any nonconformances have been submitted, with corrective actions proposed by the Contractor, and accepted by the Administrator
label | d) the layer has been presented to the Administrator for inspection, and
label | e) the As Constructed Survey requirements of the lot have been met as specified in MRTS56 Construction Surveying and notice of such works has been provided to the Administrator.
label | Reference - MRTS05 Cl.9.5.1
label | Item Check - HOLD POINT
holdpoint | HOLD POINT
checkpoint | Final Verification
note | Name of Client's Representative
textbox | Print Name:
date | Date:
note | Name of Contractor's Representative
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | Demolition of Drainage Structures/Concrete | itp
section | Details
checkpoint | 1 - Establising Lot Number /Boundaries
label | Acceptance Criteria - Lot Number established with the Lot boundaries of the works clearly defined for traceability within the works
label | Reference - MRTS 50
label | Item Check - Check and Verify
checkpoint | 2 - Safety Check
label | Acceptance Criteria - All site personnel inducted (includes environment and cultural)
label | — Required Safe Work Method Statements, Task Hazard Review Cards and Traffic Control Plans completed, signed and implemented.
label | — Traffic Control devices installed as per the approved traffic control plan and traffic management plan.
label | Reference - Induction
label | Item Check - Check and Verify
checkpoint | 3 - Services
label | Acceptance Criteria - All services identified – shall be marked, potholed and/or protected as required
label | — Permit to excavate issued by Project Engineer
label | Reference - DBYD
label | Item Check - Check and Verify
checkpoint | 4 - Environmental Checks
label | Acceptance Criteria - Erosion and sediment controls in place
label | — Vibration and Air quality to be monitored as a direct result of construction activities
label | Reference - CEMP, MRTS51 Cl 10.3, MRTS51.1 Cl4.1
label | Item Check - Check and Verify
checkpoint | 5 - Removal/Demolition of Culverts and End Structures
label | Acceptance Criteria - Culverts and culvert end structures shall be removed or demolished where specified in the drawings. If existing culvert components are to be removed and re-used, they shall be removed and stacked in a manner which avoids damaging the components. Removed components which are not to be salvaged, nor reused, shall be removed from the Site and disposed.
label | ○ Excavations carried out and the void left by the removed culvert or end structure shall be backfilled to reinstate the area to a safe and free draining state.
label | Reference - MRTS03 Clause 9.2
label | Item Check - Check and Verify
checkpoint | 6 - Removal/Demolition of Kerbs and Channels and Concrete Slabs
label | Acceptance Criteria - Existing kerbs, channels, kerbs and channels, kerb crossings and concrete slabs shall be removed or demolished where specified in the drawings.
label | ○ No damage shall result to adjacent works. Where part only and new kerbs, kerb and channels, kerb crossings and concrete slabs are to be joined to the remaining part, removing or demolition shall terminate at a joint. Alternatively, existing shall be sawn to provide a clean joint.
label | ○ Any resulting excavations shall be backfilled and the surface finished level with the surrounding area.
label | Reference - MRTS03 Clause 9.4
label | Item Check - Check and Verify
checkpoint | 7 - Removal/Demolition of Gullies and Access Chambers
label | Acceptance Criteria - Gullies and access chambers shall be removed or demolished where specified in the drawings.
label | ○ Gullies and access chambers shall be removed or demolished in a manner which avoids damaging any adjacent work.
label | ○ Resulting excavations and voids shall be backfilled and the surface finished level with the surrounding area.
label | Reference - MRTS03 Clause 9.4
label | Item Check - Check and Verify
checkpoint | 8 - Lot Closure
label | Acceptance Criteria - Lot closure requires all relevant information to be attached to the Conformance Report this includes a Lot Plan, Survey Report, Hold Points/Approvals & any supporting documentation
label | Reference - MRTS 50
label | Item Check - Check and Verify
checkpoint | Final Verification
note | Name of Client's Representative
textbox | Print Name:
date | Date:
note | Name of Contractor's Representative
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | Subgrade Treatment | itp
section | Details
checkpoint | 1 - Lot Boundries
label | Acceptance Criteria - Lot Number established with the Lot boundaries of the works clearly defined for traceability within the works
label | Reference - MRTS 04 Cl 5.6
label | Item Check - Check and Verify
checkpoint | 2 - Subgrade Level
label | Acceptance Criteria - When the level of excavation has reached Subgrade Level plus a nominal allowance determined by the Contractor, the Contractor shall carry out the requirements of the relevant provisions of Clause 18.3.3 and cease excavation until the Subgrade treatment type has been determined in accordance with Clause 18.3.3.
label | Reference - MRTS 04 Cl 13.3.2.1
label | Item Check - HOLD POINT
holdpoint | HOLD POINT
checkpoint | 3 - Proof Roll
label | Acceptance Criteria - At the completion of earthworks to Subgrade Level, the Contractor shall test for perceptible surface deformation by undertaking proof rolling. Witness Point 8
label | Reference - MRTS 04 Cl 18.3.2
label | Item Check - Witness Point
checkpoint | 5 - Subgrade Treament
textbox | Acceptance Criteria - Subgrade Treatment Ordered:
label | Reference - MRTS 04 Cl 18.3.3
label | Item Check - HOLD POINT
holdpoint | HOLD POINT
checkpoint | 6 - Subgrade Treament Type A
label | Acceptance Criteria - For Subgrade treatment Type A, excavation shall be completed to Subgrade Level in accordance with Clause 13.3.1.
label | ○ The material below Subgrade Level shall be compacted as specified in Clause 15.3 to a characteristic value of compaction as specified in Table 15.3(b). The depth of compaction shall be as specified in Clause 12.3 of Annexure MRTS04.1 to this Technical Specification or, where no such depth is specified, to a depth of 150 mm.
label | Reference - MRTS 04 Cl 18.3.3
label | Item Check - Check and Verify
checkpoint | 7 - Subgrade Treatment Type C
label | Acceptance Criteria - For Subgrade treatment Type C, excavation shall be continued to a depth below Subgrade Level as specified in Clause 12.3 of Annexure MRTS04.1 to this Technical Specification or, where no such depth is specified, to a depth of 150 mm. Excavation shall comply with the requirements of Clause 13.3.1.
label | ○ The excavation shall be backfilled to Subgrade Level with unbound granular material, in accordance with Clause 18.2.2, and shall be constructed as specified in MRTS05 Unbound Pavements to a characteristic value of compaction of not less than that specified in Table 15.3(b).
label | Reference - MRTS 04 Cl 18.3.3
label | Item Check - Check and Verify
checkpoint | 8 - Testing - Compaction
label | Acceptance Criteria - Compaction - depth as per Clause 13.5 of Annexure MRTS04.1
label | Reference - MRTS 04 Table A.2 - 2.1
label | Item Check - Test Reports
label | ○ 1 per 500m2
label | ○ 4 per Lot
checkpoint | 8 - Geometrics - Straight Edge
label | Acceptance Criteria - The gap beneath a three metre-long straight-edge placed anywhere on the surface at Subgrade Level shall not exceed 25 mm, due allowance being made for design shape where relevant.
label | Reference - MRTS 04 Table A.2 - 2.1
label | Item Check - Test Reports
label | ○ 1 Per 20m
checkpoint | 8 - Geometrics - Survey
label | Acceptance Criteria - The heights of earthworks measured anywhere on a layer surface shall not vary from those shown on the drawings, or calculated in accordance with Clause 6.1, by more than the tolerance stated in Table 6.3.1 unless specified otherwise.
label | ○ Subgrade Level (Individual Results): ± 25mm
label | ○ Subgrade Level (Average): ± 10
label | Reference - MRTS 04 Table A.2 - 2.1
label | Item Check - Survey 20m Iintervals
checkpoint | Final Verification
note | Name of Client's Representative
textbox | Print Name:
date | Date:
note | Name of Contractor's Representative
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off