## ITP Cover Page
Line Marking Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - ITP 024 - Rev 0
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project |  |  |  |  | ITP Number: |  |  | ITP 024
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status: |  |  | IFC
ITP Description: |  |  | Line Marking |  |  |  |  | Revision: | 1000 |  | 0
Contract Number: |  |  | 8287 |  |  |  |  | Drawing Sets: |  |  | 232735.02-WSP-DR-RSA (309,333,334)
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | Project SpecificationSection 26.1 to Section 26.5
Quality Specified: |  |  | ISO9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | 15/04/2025 |  | Cordelia Girdler-Brown | [5 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection (Formal inspection activity to be undertaken and recorded) |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point (Review of text reports/records or other evidence of compliance) |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | CHRIS BENSON | [5 empty] | Downer PM |  | CHRIS BENSON
Downer QM |  | CORDELIA GIRDLER-BROWN |  |  |  |  | 18/05/25 | Downer QM |  | CORDELIA GIRDLER-BROWN
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Line Marking Inspection and Test Plan
Tauriko Enabling Works
DN1210 - ITP024 - REV 0
Item No. | Inspection and Test Point | Detail / Activity | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | ConQA Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
3.1 | MATERIAL COMPLIANCE AND TESTING
3.1.1 | Paint | comply to TNZ M/7, TNZ M/20 and TNZ M/24 requirements as applicable. It also must be the brand and type currently approved for use on State Highways. | Engineer approval | PS-26.4.4 | Data Sheet | Prior to Procurement | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
3.1.2 | Glass Beads | As per NZTA P/12:the Glass Beads must comply with the AS2009:1991 | As Per Specification Requirements and NZTA P/12 | PS-26.4.4 | Data Sheet | Prior to Procurement | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
3.1.4 | Paint Applicator Testing | All applicator plant/equipment shall comply to requirements of the NZTA specification T/8 and must have a certificate of Compliance as per TNZ P/12 Specification | As Per Project Specification | PS-26.4.4 | Test Certificate | Once per paint applicator | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
SECTION 4 – CONSTRUCTION ACTIVITY
4.1.1 | Survey Set Outs | Survey to set out edge,centre line at 20m interval on straight sections and 10m intervals on curves. Ensure setout is from the latest CAD file. | Prior to commencement of line marking. | IFC Drawings | Visual Inspection | For each shift | W Review of text reports/records or other evidence of compliance | ENG
4.1.2 | Paint Marking tolerances | Paint marking tolerances shall be accordence with the section 10 of P12 requirements. and as per PS26.4.6 for transverse location +-20mm, Longitudinal location +-50mm | #VALUE! | NZTA P12 | Visual Inspection | For each shift | V Visual Verification | SE
4.1.3 | Features, Arrows and Letters | Painting of Features, Arrows, Symbols, Letters etc shall be in accordance with industry best practice. Works shall conform with the requirement of TNZ P/12 specification. | Paint Marking meeting the project specification and NZTA P/12 | Detail as per IFC Drawing following PS 24.4.3 | Visual Inspection | For each shift | V Visual Verification | SE
4.1.4 | Application Rates | For paint the finished dry film thickness shall be 150microns or greater. Film thickness is measured on steel plates | Paint Marking meeting the project specification and NZTA P/12 | PS-26.4.4 | Visual Inspection / Test Plate Certificate | Min of 2 per day after pressure or speed settings are changed. | V Visual Verification | SE
4.1.5 | Thinners | Thinners, when used in conjunction with paint application, shall be added according to the manufacturer's instruction. | As Per Specification Requirements and NZTA P/12 | PS-26.4.4 | sub-contractor's QA Record | As required | M Monitor | SE
4.1.6 | Road Reflectorised Pavement Markings (RRPM) | RRPM's for lane lines and edge lines shall be monodirectional, while RRPM's for centerlines and flush median border lines shall be bidirectional, as per MOTSAM requirements | Paint Marking meeting the project specification and NZTA P/22 | PS-26.4.4 (I) | Visual Inspection | As per DWG, RSA-0333,0334 | V Visual Verification | SE
4.1.6 | Dry Reflectivity | The reflectivity is measured using a suitable photometer or reflectometer. 5 readings are taken and the results are avereged. | Paint Marking meeting the project specification and NZTA P/22 | PS-26.4.4 | Visual Inspection / Test Certificate | 1 test per 1km to a maximum of 5 tests | I Inspection (Formal inspection activity to be undertaken and recorded) | SE
SECTION 5 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
5.1.1 | Post Line Marking Inspection | Complete visual inspection of linemarking | Accepted by the engineers representative that it is visually appealing | Project Specifications | Site Instruction | Post works completion of a lot | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
5.1.2 | Survey As-Builts | As built records of the finished line marking | Meets spec as per drawings and capture any NCR or change to design. | Project Specifications | Red pen markup | Post works completion of a lot | R Review Redpen markup | SE