## ITP Cover Page
Landscaping & Urban Design Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 010 - Rev 2
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project |  |  |  |  | ITP Number: |  |  | 010
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status: |  |  | IFC
ITP Description: |  |  | Landscaping and Urban Design |  |  |  |  | Revision: | 1000 |  | 2
Contract Number: |  |  | NZTA 8287 |  |  |  |  | Drawing Sets: |  |  | 232735.02-WSP-DR-UDL
Customer: |  |  | NZTA |  |  |  |  | Specification: |  |  | Project Specification, NZTA P39:2013 Section F, Section 3.9
Quality Specified: |  |  | Project Specification
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | 2024-11-19 |  | Joshua Fraser |  | For approval |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
1 | Issued for construction | 2024-12-05 |  | Rex Humpherson |  | NTC-0352 - (Added in Table 21.13: testing requirements for Rip rap) |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
2 | Issued for construction | 2025-07-17 |  | Cordelia |  | Added section no. 2.2.1 Pre planting site walkove,2.2.2 Confirm Planting layout and 2.2.3 Planting Density |  |  |  | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | CHRIS BENSON | [5 empty] | Downer PM
Downer QM |  | Cordelia Girdler-Brown |  |  |  |  | 31/01/2025 | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Landscaping & Urban Design Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 010 - Rev 2
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
3.1 | MATERIAL TESTING PRE APPROVALS
3.1.1 | Wetland & Landscaping Methodology | The Contractor shall submit the construction and QA methodology, for each element of Wetland & Landscaping including, testing, inspection and hold points for review and approval prior to works. | Engineers Approval | Appendix V | Approved Methodology | Prior to Earthworks | HP | ENG
3.1.2 | Bentosure geosynthetic Clay liner | Permeability value of bentosure liner Liner Approved for use | permeability value of 1 × 10⁻⁹ m/s | Refer to installation guide | Delivery dockets | Once per source - prior to commencement of works | HP | ENG
3.1.3 | Geotextile Fabric | Geotextile fabric approval | Class D geotextile fabric | PS 21.5.15 | Engineers Approval | Once prior to commencement of works | HP | ENG
3.1.4 | Topsoil Analysis | Testing of on-site and imported topsoil for quality. | Topsoil must meet the criteria specified in the project standards. | NZTA P39: 2013, Section F | Soil Testing Report | Once per source | HP | SE
3.1.5 | Mulch Material Verification | Verify that the mulch used meets the specified criteria (e.g., pallet mulch, arborist mulch). | Mulch material should be free of contaminants, sufficiently aged, and appropriate to site and slope conditions | NZTA P39: 2013 Section 3.9 | Mulch Material Certification | 100% of mulch used | HP | ENG
3.1.6 | Biodegradeable Weed Mat | Biodegradeable weed mat approval | 450 GSM, 7mm thick, biodegradeable weed mat | PS 27.3.8 | Weed Mat Approval | Once prior to commencement of works | HP | ENG
3.1.7 | Rock Rip Rap Approval - Grading | D50=150mm Grading Approval D50=250mm Grading Approval | #VALUE! | PS 21.5.14 | Engineers Approval | Once prior to commencement of works | HP | ENG
3.1.8 | Rock Rip Rap Approval-Weathering | Weathering Index of Coarse Aggregate | AA to CA | PS 21.7.4 | Engineers Approval | 1 per 1000m3 | HP | ENG
3.1.9 | Rock Rip Rap Approval-Crushing resistance | Crushing Resistance of Course Aggregate | >150kN | PS 21.7.4 | Engineers Approval | 1 per 1000m3 | HP | ENG
3.1.10 | Rock Rip Rap Approval-Solid density | Solid Density of Aggregate | >2.65 tonnes per m3 | PS 21.7.4 | Engineers Approval | 1 per 1000m3 | HP | ENG
3.1.11 | Rock Rip Rap Approval - UCS | 1 per 1000m3 AS4133.4.2.1 >30 MPa | >30 MPa | PS 21.7.4 | Engineers Approval | 1 per 1000m3 | HP | ENG
3.1.12 | Rock Rip Rap Approval-Point load | Point Load Strength | > 1.5 Mpa | PS 21.7.4 | Engineers Approval | 1 per 1000m3 | HP | ENG
3.1.13 | Hydro-seeding | Grass mix approved | Send seed mix to engineer for approval | NZTA P39: 2013, Section F | Seed Mix | Once prior to commencement of works | HP | ENG
SECTION 4 – CONSTRUCTION ACTIVITY
4.1 | LANSCAPING
4.1.1 | Setting out Notice | Confirm that the site has been marked out according to the project plans and specifications before planting of trees begins. | The Contractor shall provide written notice to the Engineer, at least two days prior to Setting out. | PS 27.3.2 | Setting Out Notice Report | Before each stage | HP | ENG
4.1.2 | Site Grading | Grading for planting areas to ensure drainage. | Smooth, flowing contours with proper drainage. | NZTA P39: 2013, Section G PS 16.6.3 | Visual Inspection | 100% of areas | I | SE
4.2 | PLANTING
4.2.1 | Pre Planting site walk over | Confirm setout and ensure site is free from debris and is ready for Planting | 1. Confirm planting set out is acceptable as per design drawings 2. Confirm herbicide has been applied before planting 3. Confirm delivery of Plants and Trees is correct 4. Site mostly clear from vegetation and debris or rubbish | NZTA P39:2013 Section C and PS 27.3.2 | Visual Inspection | Once Per Establishment | HP | ENG
4.2.2 | Confirm planting layout / pattern | Layout a sample section of plants in the pattern and density as shown on the design as per WSP-DR-UDL set and confirm this is acceptable before planting. | For planting areas less than 2000m2: the sample area should a minimuim of 5% of entire area For planting areas more than 2000m2: sample area should be a minimum of 2% of the entire area. | PS 27.3.8 section b and NZTA P39:2013 Section B | Visual Inspection | Once per planting type mix | HP | ENG
4.2.3 | Planting Density | Plants shall be spaces as specified in the drawings. Either 500mm c/c or 1000mm c/c. | Plants designed to be 500mm c/c should be between 350mm-750mm apart. Plants designed to be 1000mm c/c should be between 750mm-1250mm apart. This allows for a slightly varied pattern to look natural. Avoid a grid pattern if possible. | UDL 250 - UDL 253 | Visual Inspection | Once Per Establishment | M | SE
4.2.4 | Tree Pit Excavation | Excavation of tree pits according to specified dimensions. | #VALUE! | 2-32735.02-WSP-DR-UDL 0402 Rev 1 | Visual Inspection | Per tree pit | I | SE
4.2.5 | Timber Stakes | Timber stakes used for landscaping must be of specified type, treated to prevent decay, and meet size and quality requirements. 50mmx50mmx1500mm H4 Treated Pine Stakes | #VALUE! | NZTA P39: 2013, Section I | Material Dockets | Per order | I | SE
4.2.6 | Fertilising | All plantings shall have two-year slow-release fertilizer tablets installed at the time of planting. | Fertiliser tablet placed in bottom of hole before planting. Fertiliser composition: 6:15:3 (N:P:K). Up to 14l is 1 tab, 45l is 4 tabs | NZTA P39: 2013, 3.13 | Site Records/photos | Each Area | I | SE
4.3 | MULCHING
4.3.1 | Mulch Spreading | Correct mulch application on flat sites | On sites flatter than a 1:3 grade (1.0m high by 3.0m metres long), mulch shall be spread evenly to a depth of 80-100mm after settlement, over the planted area, creating an inverted cone hollow around each plant stem with a maximum 25mm depth around plant stems. | NZTA P39: 2013, Section G | Site Records / As Built Survey | Each Area | I | SE
4.4 | BENTOSURE LINER
4.4.1 | Pre Bentosure liner inspection | inspect before installing bentosure liner | Ensure subgrade is smooth, compacted, and free of sharp objects, debris. Confirm BentoSure rolls are delivered intact, labeled, and stored properly (off the ground, covered). Confirm panel layout plan and anchor trench dimensions are per specifications. | Refer to installation guide | Visual Inspection/Check list | For all liner areas | HP | SE
4.4.2 | Bentosure Liner key Footing | Anchorage for Bentosure | 600mm Deep/400mm wide Anchorage key in footing | Refer to installation guide | Site Records/photos | For all liner | I | SE
4.4.3 | Bentosure liner laps | longitude and latitude overlaps | Longitude 300mm/Latitude 500mm overlaps minimum | Refer to installation guide | Site Records/photos | Each Area | I | SE
4.4.4 | Post Bentosure liner inspection | Post inspection - after bentosure has been laid and before any topsoil is placed on top | Verify panels lie flat without wrinkles or folds.Check seam overlaps Inspect anchor trench dimensions and proper backfilling.Confirm cover soil is free of sharp objects and is at least 300mm thick.Inspect for tears, punctures, or wrinkles; repair as needed with 300mm overlap and bentonite application. | Refer to installation guide | Visual Inspection/Check list | For all liner areas | HP | SE
4.4.5 | Bentosure Liner key Footing | Anchorage for Bentosure | 600mm Deep/400mm wide Anchorage key in footing | Refer to installation guide | Site Records/photos | For all liner | I | SE
4.5 | WEED MAT
4.5.1 | Weed mat laps | Lap joints | On slopes steeper than 1:3 biodegradeable matting shall over lap 100mm between adjacent rolls and 500mm longitudinally | NZTA P39: 2013, Section G | Site Records/photos | Each Area | I | SE
4.5.2 | Weed mat keys | Key in edges | On slopes steeper than 1:3 edges shall be keyed in to topsoil 150mm x 150mm | NZTA P39: 2013, Section G | Site Records/photos | Each Area | I | SE
4.5.3 | Weed mat pins | Freqency of pins | On slopes steeper than 1:3 biodegradeable matting shall be pinned with frequency of 2 per m2 min. | NZTA P39: 2013, Section G | Site Records/photos | Each Area | I | SE
4.6 | GRASSING
4.6.1 | Establishment of sown areas | Apply grass seed as soon as practical after area is prepped. Protect newly established grass areas. | Newly established grass shall be protected from damage by pedestrian and vehicular traffic until grass has reached a self-sustaining state. Newly grassed areas shall be maintained with regular mowing (90mm-30mm) ensuring that all clippings are removed from adjacent hard surfaces. | NZTA P39: 2013, Section G | Site Records/Photos | Each Area | I | SE
SECTION 5 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
5.1 | AS-BUILTS
5.1 | As-Builts/ Red pen markup | As-Built records and drawings shall accurately record the layout and extents of all the work. | Record of work completed | PS 16.7.6 | Red pen markups | During Earthworks | D | SV