## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-010 ITP Landscaping & Urban design | itp |  |  |  |  | DN1210-010 ITP Landscaping & Urban design Rev 2
section | SECTION 3 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 3.1.1 - Wetland & Landscaping Methodology
label | Detail - The Contractor shall submit the construction and QA methodology, for each element of Wetland & Landscaping including, testing, inspection and hold points for review and approval prior to works.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Approved Methodology
label | Testing Quantity Required (based from schedule qtys) - Prior to Earthworks
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Bentosure geosynthetic Clay liner
label | Detail - Permeability value of bentosure liner
label | ○ Liner Approved for use
label | Acceptance / Conformance Criteria - permeability value of 1 × 10⁻⁹ m/s
label | Standard / Specification - Refer to installation guide
label | Verifying Document - Delivery dockets
label | Testing Quantity Required (based from schedule qtys) - Once per source - prior to commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.3 - Geotextile Fabric
label | Detail - Geotextile fabric approval
label | Acceptance / Conformance Criteria - Class D geotextile fabric
label | Standard / Specification - PS 21.5.15
label | Verifying Document - Engineers Approval
label | Testing Quantity Required (based from schedule qtys) - Once prior to commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.4 - Topsoil Analysis
label | Detail - Testing of on-site and imported topsoil for quality.
label | Acceptance / Conformance Criteria - Topsoil must meet the criteria specified in the project standards.
label | Standard / Specification - NZTA P39: 2013, Section F
label | Verifying Document - Soil Testing Report
label | Testing Quantity Required (based from schedule qtys) - Once per source
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.5 - Mulch Material Verification
label | Detail - Verify that the mulch used meets the specified criteria (e.g., pallet mulch, arborist mulch).
label | Acceptance / Conformance Criteria - Mulch material should be free of contaminants, sufficiently aged, and appropriate to site and slope conditions
label | Standard / Specification - NZTA P39: 2013 Section 3.9
label | Verifying Document - Mulch Material Certification
label | Testing Quantity Required (based from schedule qtys) - 100% of mulch used
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.6 - Biodegradeable Weed Mat
label | Detail - Biodegradeable weed mat approval
label | Acceptance / Conformance Criteria - 450 GSM, 7mm thick, biodegradeable weed mat
label | Standard / Specification - PS 27.3.8
label | Verifying Document - Weed Mat Approval
label | Testing Quantity Required (based from schedule qtys) - Once prior to commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.7 - Rock Rip Rap Approval - Grading
label | Detail - D50=150mm Grading Approval D50=250mm Grading Approval
label | Acceptance / Conformance Criteria -
label | — — — — — — —
label | TABLE 21.3: D50 = 150mm Riprap Grading
label | Aperture Size (mm) ¦¦ Percentage Passing
label | — — — — — — —
label | 230 ¦¦ 85
label | 150 ¦¦ 50
label | 95 ¦¦ 15
label | — — — — — — —
label | TABLE 21.4: D50 = 250mm Riprap Grading
label | Aperture Size (mm) ¦¦ Percentage Passing
label | — — — — — — —
label | 380 ¦¦ 85
label | 250 ¦¦ 50
label | 160 ¦¦ 15
label | — — — — — — —
label | Standard / Specification - PS 21.5.14
label | Verifying Document - Engineers Approval
label | Testing Quantity Required (based from schedule qtys) - Once prior to commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.8 - Rock Rip Rap Approval-Weathering
label | Detail - Weathering Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA to CA
label | Standard / Specification - PS 21.7.4
label | Verifying Document - Engineers Approval
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.9 - Rock Rip Rap Approval-Crushing resistance
label | Detail - Crushing Resistance of Course Aggregate
label | Acceptance / Conformance Criteria - >150kN
label | Standard / Specification - PS 21.7.4
label | Verifying Document - Engineers Approval
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.10 - Rock Rip Rap Approval-Solid density
label | Detail - Solid Density of Aggregate
label | Acceptance / Conformance Criteria - >2.65 tonnes per m3
label | Standard / Specification - PS 21.7.4
label | Verifying Document - Engineers Approval
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.11 - Rock Rip Rap Approval - UCS
label | Detail - 1 per 1000m3 AS4133.4.2.1 >30 MPa
label | Acceptance / Conformance Criteria - >30 MPa
label | Standard / Specification - PS 21.7.4
label | Verifying Document - Engineers Approval
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.12 - Rock Rip Rap Approval-Point load
label | Detail - Point Load Strength
label | Acceptance / Conformance Criteria - > 1.5 Mpa
label | Standard / Specification - PS 21.7.4
label | Verifying Document - Engineers Approval
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.13 - Hydro-seeding
label | Detail - Grass mix approved
label | Acceptance / Conformance Criteria - Send seed mix to engineer for approval
label | Standard / Specification - NZTA P39: 2013, Section F
label | Verifying Document - Seed Mix
label | Testing Quantity Required (based from schedule qtys) - Once prior to commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 – CONSTRUCTION ACTIVITY
checkpoint | 4.1.1 - Setting out Notice
label | Detail - Confirm that the site has been marked out according to the project plans and specifications before planting of trees begins.
label | Acceptance / Conformance Criteria - The Contractor shall provide written notice to the Engineer, at least two days prior to Setting out.
label | Standard / Specification - PS 27.3.2
label | Verifying Document - Setting Out Notice Report
label | Testing Quantity Required (based from schedule qtys) - Before each stage
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.2 - Site Grading
label | Detail - Grading for planting areas to ensure drainage.
label | Acceptance / Conformance Criteria - Smooth, flowing contours with proper drainage.
label | Standard / Specification - NZTA P39: 2013, Section G, PS 16.6.3
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - 100% of areas
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.2.1 - Pre Planting site walk over
label | Detail - Confirm setout and ensure site is free from debris and is ready for Planting
label | Acceptance / Conformance Criteria - 1. Confirm planting set out is acceptable as per design drawings
label | 2. Confirm herbicide has been applied before planting
label | 3. Confirm delivery of Plants and Trees is correct
label | 4. Site mostly clear from vegetation and debris or rubbish
label | Standard / Specification - NZTA P39:2013 Section C and PS 27.3.2
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Once Per Establishment
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.2 - Confirm planting layout / pattern
label | Detail - Layout a sample section of plants in the pattern and density as shown on the design as per WSP-DR-UDL set and confirm this is acceptable before planting.
label | Acceptance / Conformance Criteria - For planting areas less than 2000m2: the sample area should a minimuim of 5% of entire area
label | ○ For planting areas more than 2000m2: sample area should be a minimum of 2% of the entire area.
label | Standard / Specification - PS 27.3.8 section b and NZTA P39:2013 Section B
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Once per planting type mix
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.3 - Planting Density
label | Detail - Plants shall be spaces as specified in the drawings. Either 500mm c/c or 1000mm c/c.
label | Acceptance / Conformance Criteria - Plants designed to be 500mm c/c should be between 350mm-750mm apart.
label | ○ Plants designed to be 1000mm c/c should be between 750mm-1250mm apart.
label | ○ This allows for a slightly varied pattern to look natural.
label | ○ Avoid a grid pattern if possible.
label | Standard / Specification - UDL 250 - UDL 253
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Once Per Establishment
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 4.2.4 - Tree Pit Excavation
label | Detail - Excavation of tree pits according to specified dimensions.
label | Acceptance / Conformance Criteria -
label | — — — — — — —
label | TABLE 1
label | PLANT SIZE (LITRE / PB) ¦¦ NO. OF STAKES ¦¦ TREE PIT SIZE
label | — — — — — — —
label | LESS THAN 15LT / PB28 ¦¦ 1 ¦¦ 2X SIZE OF ROOT BALL
label | 45LT / PB95 ¦¦ 3 ¦¦ 1000x1000x1000 mm
label | — — — — — — —
label | Standard / Specification - 2-32735.02-WSP-DR-UDL 0402 Rev 1
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Per tree pit
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.2.5 - Timber Stakes
label | Detail - Timber stakes used for landscaping must be of specified type, treated to prevent decay, and meet size and quality requirements.
label | ○ 50mmx50mmx1500mm H4 Treated Pine Stakes
label | Acceptance / Conformance Criteria -
label | — — — — — — —
label | TABLE 1
label | PLANT SIZE (LITRE / PB) ¦¦ NO. OF STAKES ¦¦ TREE PIT SIZE
label | — — — — — — —
label | LESS THAN 15LT / PB28 ¦¦ 1 ¦¦ 2X SIZE OF ROOT BALL
label | 45LT / PB95 ¦¦ 3 ¦¦ 1000x1000x1000 mm
label | — — — — — — —
label | Standard / Specification - NZTA P39: 2013, Section I
label | Verifying Document - Material Dockets
label | Testing Quantity Required (based from schedule qtys) - Per order
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.2.6 - Fertilising
label | Detail - All plantings shall have two-year slow-release fertilizer tablets installed at the time of planting.
label | Acceptance / Conformance Criteria - Fertiliser tablet placed in bottom of hole before planting. Fertiliser composition: 6:15:3 (N:P:K). Up to 14l is 1 tab, 45l is 4 tabs
label | Standard / Specification - NZTA P39: 2013, 3.13
label | Verifying Document - Site Records/photos
label | Testing Quantity Required (based from schedule qtys) - Each Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.3.1 - Mulch Spreading
label | Detail - Correct mulch application on flat sites
label | Acceptance / Conformance Criteria - On sites flatter than a 1:3 grade (1.0m high by 3.0m metres long), mulch shall be spread evenly to a depth of 80-100mm after settlement, over the planted area, creating an inverted cone hollow around each plant stem with a maximum 25mm depth around plant stems.
label | Standard / Specification - NZTA P39: 2013, Section G
label | Verifying Document - Site Records / As Built Survey
label | Testing Quantity Required (based from schedule qtys) - Each Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.4.1 - Pre Bentosure liner inspection
label | Detail - inspect before installing bentosure liner
label | Acceptance / Conformance Criteria - Ensure subgrade is smooth, compacted, and free of sharp objects, debris. Confirm BentoSure rolls are delivered intact, labeled, and stored properly (off the ground, covered). Confirm panel layout plan and anchor trench dimensions are per specifications.
label | Standard / Specification - Refer to installation guide
label | Verifying Document - Visual Inspection/Check list
label | Testing Quantity Required (based from schedule qtys) - For all liner areas
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4.2 - Bentosure Liner key Footing
label | Detail - Anchorage for Bentosure
label | Acceptance / Conformance Criteria - 600mm Deep/400mm wide Anchorage key in footing
label | Standard / Specification - Refer to installation guide
label | Verifying Document - Site Records/photos
label | Testing Quantity Required (based from schedule qtys) - For all liner
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.4.3 - Bentosure liner laps
label | Detail - longitude and latitude overlaps
label | Acceptance / Conformance Criteria - Longitude 300mm/Latitude 500mm overlaps minimum
label | Standard / Specification - Refer to installation guide
label | Verifying Document - Site Records/photos
label | Testing Quantity Required (based from schedule qtys) - Each Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.4.4 - Post Bentosure liner inspection
label | Detail - Post inspection - after bentosure has been laid and before any topsoil is placed on top
label | Acceptance / Conformance Criteria - Verify panels lie flat without wrinkles or folds.Check seam overlaps Inspect anchor trench dimensions and proper backfilling.Confirm cover soil is free of sharp objects and is at least 300mm thick.Inspect for tears, punctures, or wrinkles; repair as needed with 300mm overlap and bentonite application.
label | Standard / Specification - Refer to installation guide
label | Verifying Document - Visual Inspection/Check list
label | Testing Quantity Required (based from schedule qtys) - For all liner areas
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4.5 - Bentosure Liner key Footing
label | Detail - Anchorage for Bentosure
label | Acceptance / Conformance Criteria - 600mm Deep/400mm wide Anchorage key in footing
label | Standard / Specification - Refer to installation guide
label | Verifying Document - Site Records/photos
label | Testing Quantity Required (based from schedule qtys) - For all liner
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.5.1 - Weed mat laps
label | Detail - Lap joints
label | Acceptance / Conformance Criteria - On slopes steeper than 1:3 biodegradeable matting shall over lap 100mm between adjacent rolls and 500mm longitudinally
label | Standard / Specification - NZTA P39: 2013, Section G
label | Verifying Document - Site Records/photos
label | Testing Quantity Required (based from schedule qtys) - Each Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.5.2 - Weed mat keys
label | Detail - Key in edges
label | Acceptance / Conformance Criteria - On slopes steeper than 1:3 edges shall be keyed in to topsoil 150mm x 150mm
label | Standard / Specification - NZTA P39: 2013, Section G
label | Verifying Document - Site Records/photos
label | Testing Quantity Required (based from schedule qtys) - Each Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.5.3 - Weed mat pins
label | Detail - Freqency of pins
label | Acceptance / Conformance Criteria - On slopes steeper than 1:3 biodegradeable matting shall be pinned with frequency of 2 per m2 min.
label | Standard / Specification - NZTA P39: 2013, Section G
label | Verifying Document - Site Records/photos
label | Testing Quantity Required (based from schedule qtys) - Each Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.6.1 - Establishment of sown areas
label | Detail - Apply grass seed as soon as practical after area is prepped. Protect newly established grass areas.
label | Acceptance / Conformance Criteria - Newly established grass shall be protected from damage by pedestrian and vehicular traffic until grass has reached a self-sustaining state. Newly grassed areas shall be maintained with regular mowing (90mm-30mm) ensuring that all clippings are removed from adjacent hard surfaces.
label | Standard / Specification - NZTA P39: 2013, Section G
label | Verifying Document - Site Records/Photos
label | Testing Quantity Required (based from schedule qtys) - Each Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 5 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 5.1 - As-Builts/ Red pen markup
label | Detail - As-Built records and drawings shall accurately record the layout and extents of all the work.
label | Acceptance / Conformance Criteria - Record of work completed
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Red pen markups
label | Testing Quantity Required (based from schedule qtys) - During Earthworks
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1210-SP2-006-006 ITP Vehicle, Pedestrian, Pram & Cycle drop kerb crossing | itp |  |  |  |  | DN1210-SP2-006-006 ITP Vehicle, Pedestrian, Pram & Cycle drop kerb crossing Rev 2
section | SECTION 3 – PRE-CONSTRUCTION - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
checkpoint | 3.1 - Crushing Resistance AP40-1
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - < 10% fines passing 2.36mm under a load of 130kN
label | Standard / Specification - Project Specifications 20.9 TCC-IDC IT-4.8 table 4.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Soaked CBR AP40-1
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - >80%
label | Standard / Specification - Project Specifications 20.9 TCC-IDC IT-4.8 table 4.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Accelerated Weathering AP40-1
label | Detail - NZTAT/20 Ethylene Glycol Accelerated Weathering Test
label | Acceptance / Conformance Criteria - ≤ 30% increase in fines
label | Standard / Specification - Project Specifications 20.9 TCC-IDC IT-4.8 table 4.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Weathering Resistance AP40-1
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB or CA
label | Standard / Specification - Project Specifications 20.9 TCC-IDC IT-4.8 table 4.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Particle Size Distribution AP40-1
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 37.5mm ¦¦ 100% passing
label | 19.0mm ¦¦ 60-75% passing
label | 9.5mm ¦¦ 37-50% passing
label | 4.75mm ¦¦ 20-35% passing
label | 2.36mm ¦¦ 12-28% passing
label | 1.18mm ¦¦ 9-20% passing
label | 0.600mm ¦¦ 7-12% Passing
label | 0.300mm ¦¦ 3-10% Passing
label | 0.150mm ¦¦ 0-5% passing
label | 0.075mm ¦¦ 0-5% passing
label | Standard / Specification - Project Specifications 20.9 TCC-IDC IT-4.8 table 4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | 0-400 - 2 tests
label | 400-1,500 - 3 tests
label | 1,500-4,000 - 4 tests
label | >4,000 - 1 test for each additional 1,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Shape Control AP40-1
label | Detail - Tolerance allowed from approved grading curve (%)
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Tolerance
label | 37.5 – 9.5 ¦¦ 28-48%
label | 19.0 – 4.75 ¦¦ 14-34%
label | 9.5 – 2.36 ¦¦ 7-27%
label | 4.75 – 1.18 ¦¦ 6-22%
label | 2.36 – 0.6 ¦¦ 2-20%
label | 1.18 – 0.3 ¦¦ 5-19%
label | 0.6 – 0.15 ¦¦ 2-14%
label | Standard / Specification - Project Specifications 20.9 TCC-IDC IT-4..8 table 4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | 0-400 - 2 tests
label | 400-1,500 - 3 tests
label | 1,500-4,000 - 4 tests
label | >4,000 - 1 test for each additional 1,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Sand Equivalent AP40-1
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent
label | Acceptance / Conformance Criteria - ≥ 40
label | Standard / Specification - Project Specifications 20.9 TCC-IDC IT-4.8 table 4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Plasticity Index AP40-1
label | Detail - NZS4407:2015, Test 3.4 Plasticity Index
label | Acceptance / Conformance Criteria - Plasticity Index ≤ 8
label | Standard / Specification - Project Specifications 20.9 TCC-IDC IT-4.8 table 4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9 - Cone Penetrometer Limit AP40-1
label | Detail - NZS4407:2015, Test 3.2 Cone Penetration
label | Acceptance / Conformance Criteria - Cone Penetrometer ≤ 30
label | Standard / Specification - PS 20.9 TCC-IDC IT-4.8 table 4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.10 - Clay Index AP40-1
label | Detail - NZS4407:2015, Test 3.5 - Clay Index Test Report
label | Acceptance / Conformance Criteria - ≤ 5
label | Standard / Specification - Project Specifications 20.9 TCC-IDC IT-4.8 table 4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.11 - Maximum Dry Density and Optimum Water Content AP40-1
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4402:1986 Test 4.1.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.12 - Reinforcing Mesh
label | Detail - 661 Reinforcing mesh (Commerical Vehicle Crossing)
label | Acceptance / Conformance Criteria - 661 Reinforcing mesh (Commerical Vehicle Crossing)
label | Standard / Specification - 232735.02-WSP-DR-RSA-0305
label | Verifying Document - Material Data Sheet Engineer's Approval
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.13 - Reinforcing Ties
label | Detail - R6 Ties (For commercial crossing only)
label | Acceptance / Conformance Criteria - R6 Ties at 600 centres with 60 mm (For commercial crossing only)
label | Standard / Specification - 232735.02-WSP-DR-RSA-0305
label | Verifying Document - Material Data Sheet Engineer's Approval
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.14 - Reinforcing Bars
label | Detail - 4-D12 Bars (For commerical crossing only)
label | Acceptance / Conformance Criteria - 4-D12 Bars with 50 mm Cover (For commerical crossing only)
label | Standard / Specification - 232735.02-WSP-DR-RSA-0305
label | Verifying Document - Material Data Sheet Engineer's Approval
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.15 - Concrete Mix Design
label | Detail - 20.0 MPA concrete. 4kg/m3 black oxide (2.5%)
label | Acceptance / Conformance Criteria - 28 days concrete strength test of 20MPA
label | Standard / Specification - 232735.02-WSP-DR-UDL 0405
label | Verifying Document - Material Data Sheet Engineer's Approval
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1 - Cut Subgrade Testing - Cohesive Soil Shear Vane
label | Detail - NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test
label | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
label | Acceptance / Conformance Criteria - Average Minimum SU: > 60kPa
label | ○ CBR: >3
label | ○ Single Test Minimum SU: >50kPa
label | Standard / Specification - Project Specifications Appendix XVIII
label | Verifying Document - Shear Vane Report
label | Testing Quantity Required (based from schedule qtys) - 1 test per 100m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.2 - Cut Subgrade Testing - Granular Scala Penetrometer
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material
label | Acceptance / Conformance Criteria - Minimum 3 blows per 100mm penetration
label | Standard / Specification - Project Specifications Appendix XVIII
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.3 - Proof Roll Subgrade
label | Detail - Visual Inspection of Proof Roll
label | Acceptance / Conformance Criteria - Visual Inspection
label | Standard / Specification - Project Specifications Appendix XVIII
label | Verifying Document - Visual Inspection/Photos
label | Testing Quantity Required (based from schedule qtys) - Across Finished Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.4 - Hold point
label | Detail - Subgrade signoff
label | Acceptance / Conformance Criteria - Conqa signoff
label | Standard / Specification -
label | Verifying Document - Conqa signoff
label | Testing Quantity Required (based from schedule qtys) - Each area
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.1 - Stringlines or equivalent Basecourse (AP40)
label | Detail - Stringlines or equivalent to check finished height of surface
label | Acceptance / Conformance Criteria - Height +15mm/0mm
label | ○ Width –20 mm +100 mm
label | Standard / Specification - NZTA B/06 8.2.2 - Table 3
label | Verifying Document - Surveyor Records
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.2 - Compaction - Clegg Hammer Basecourse (AP40)
label | Detail - ASTM D5874-16:2016 Clegg Hammer Testing
label | Acceptance / Conformance Criteria - Min CIV 18
label | ○ Ave CIV 20
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.3 - Compaction - NDM Basecourse (AP40)
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | ○ Min >92% of MDD
label | Standard / Specification - NZTA B/02 7.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) 1000m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.4 - Hold point Basecourse (AP40)
label | Detail - Basecourse signoff
label | Acceptance / Conformance Criteria - Conqa signoff
label | Standard / Specification -
label | Verifying Document - Conqa signoff
label | Testing Quantity Required (based from schedule qtys) - Each area
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5 - Surveyor check FORMWORK
label | Detail - Equivalent to check the position of the formwork
label | Acceptance / Conformance Criteria - +\- 100mm of design
label | Standard / Specification - Project Specifications 27.4.5 (b)
label | Verifying Document - Surveyor Records
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres 1 set = 5 tests
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.6 - Surveyor check FORMWORK
label | Detail - Equivalent to check finished height of framework
label | Acceptance / Conformance Criteria - +\- 10mm of design
label | Standard / Specification - Project Specifications 27.4.5 (b)
label | Verifying Document - Surveyor Records
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres 1 set = 5 tests
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.7 - Reinforcing Mesh Check
label | Detail - 661 Reinforcing mesh (Commerical Vehicle Crossing)
label | Acceptance / Conformance Criteria - 661 Reinforcing mesh (Commerical Vehicle Crossing)
label | Standard / Specification - 232735.02-WSP-DR-RSA-0305
label | Verifying Document - Delivery Dockets
label | ○ Visual Inspection/Photos
label | Testing Quantity Required (based from schedule qtys) - Before Pour, During Construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.8 - Reinforcing Mesh
label | Detail - Ensure that overlap and cover above and beneath mesh
label | Acceptance / Conformance Criteria - Reinforcing mesh to be placed centrally in the concrete layer
label | Standard / Specification - 232735.02-WSP-DR-RSA-0305
label | Verifying Document - Visual Inspection/Photos
label | Testing Quantity Required (based from schedule qtys) - Before Pour, During Construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.9 - Reinforcing Ties -REINFORCING STEEL (COMMERICAL VEHICLE CROSSING ONLY)
label | Detail - R6 Ties at 600 centres with 60 mm (For commercial crossing only)
label | Acceptance / Conformance Criteria - R6 Ties at 600 centres with 60 mm (For commercial crossing only)
label | Standard / Specification - 232735.02-WSP-DR-RSA-0305
label | Verifying Document - Delivery Dockets, Visual Inspection/Photos
label | Testing Quantity Required (based from schedule qtys) - Before Pour, During Construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.10 - Reinforcing Bars - REINFORCING STEEL (COMMERICAL VEHICLE CROSSING ONLY)
label | Detail - 4-D12 Bars with 50 mm Cover (For commerical crossing only)
label | Acceptance / Conformance Criteria - 4-D12 Bars with 50 mm Cover (For commerical crossing only)
label | Standard / Specification - 232735.02-WSP-DR-RSA-0305
label | Verifying Document - Delivery Dockets, Visual Inspection/Photos
label | Testing Quantity Required (based from schedule qtys) - Before Pour, During Construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.11 - Concrete
label | Detail - 20.0 MPA concrete. 4kg/m3 black oxide (2.5%)
label | Acceptance / Conformance Criteria - 28 days concrete strength test of 20MPA
label | Standard / Specification - 232735.02-WSP-DR-UDL 0405
label | Verifying Document - Concrete Delivery Dockets, Test Results
label | Testing Quantity Required (based from schedule qtys) - Before Pour, During Construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.12 - Concrete Layer Thickness
label | Detail - Concrete layer thickness to be 150 mm for Residential Vehicle Crossings
label | ○ Concrete layer thickness to be 200 mm for Commerical Vehicle Crossings
label | Acceptance / Conformance Criteria - Concrete layer thickness to be 150 mm for Residential Vehicle Crossings
label | ○ Concrete layer thickness to be 200 mm for Commerical Vehicle Crossings
label | Standard / Specification - 232735.02-WSP-DR-RSA-0305
label | Verifying Document - Pre-Pour CheckSheet
label | Testing Quantity Required (based from schedule qtys) - Before Pour
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.13 - Final Finish
label | Detail - Rough broom finish
label | Acceptance / Conformance Criteria - U5
label | Standard / Specification - 232735.02-WSP-DR-UDL 0405
label | Verifying Document - Post-Pour CheckSheet
label | Testing Quantity Required (based from schedule qtys) - After Pour
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.14 - Saw Cuts
label | Detail - Saw cut expansion joints at 4m centres maximum each way
label | Acceptance / Conformance Criteria - Saw cut expansion joints at 4m centres maximum each way
label | Standard / Specification - 232735.02-WSP-DR-RSA-0305
label | Verifying Document - Post-Pour CheckSheet
label | Testing Quantity Required (based from schedule qtys) - After Pour
label | Verification Activity: Activity - D
label | Verification Activity: By - SE
checkpoint | 6.1 - Stringlines or equivalent Basecourse (AP40)
label | Detail - Stringlines or equivalent to check finished height of surface
label | Acceptance / Conformance Criteria - Height +15mm/0mm
label | ○ Width –20 mm +100 mm
label | Standard / Specification - NZTA B/06 8.2.2 - Table 3
label | Verifying Document - Surveyor Records
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.2 - Compaction - Clegg Hammer Basecourse (AP40)
label | Detail - ASTM D5874-16:2016 Clegg Hammer Testing
label | Acceptance / Conformance Criteria - Min CIV 18
label | ○ Ave CIV 20
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.3 - Hold point Basecourse (AP40)
label | Detail - Basecourse signoff
label | Acceptance / Conformance Criteria - Conqa signoff
label | Standard / Specification -
label | Verifying Document - Conqa signoff
label | Testing Quantity Required (based from schedule qtys) - Each area
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.4 - Concrete Layer Thickness
label | Detail - 100 mm thick concrete
label | Acceptance / Conformance Criteria - 100 mm thick concrete
label | Standard / Specification - 232735.02-WSP-DR-RSA-0304
label | Verifying Document - Pre-Pour checksheet
label | Testing Quantity Required (based from schedule qtys) - After pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.5 - Final Finish
label | Detail - Rough broom finish
label | Acceptance / Conformance Criteria - U5
label | Standard / Specification - 232735.02-WSP-DR-UDL 0405
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - After pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.6 - Cycle Entry Ramp Detail
label | Detail -
label | Acceptance / Conformance Criteria - Maximum 1 in 10 Grade
label | ○ 1200 mm wide cycle entry ramp detail
label | ○ 45 degree angle from the travel lane in the horizontal plane
label | Standard / Specification - 232735.02-WSP-DR-RSA-0304
label | Verifying Document - Photos, Measurements
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 6.7 - Cycle Exit Ramp Detail
label | Detail -
label | Acceptance / Conformance Criteria - Maximum 1 in 10 Grade
label | ○ 1200 mm wide cycle entry ramp detail
label | ○ 20 degree angle from the travel lane in the horizontal plane
label | Standard / Specification - 232735.02-WSP-DR-RSA-0304
label | Verifying Document - Photos, Measurements
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 6.8 - Bedding TACTILE PAVERS (PEDESTRIAN CROSSINGS)
label | Detail - 40 mm thick 2:1 sand/cement bed
label | Acceptance / Conformance Criteria - 40 mm thick 2:1 sand/cement bed
label | Standard / Specification - 232735.02-WSP-DR-RSA-0304
label | Verifying Document - Delivery Dockets, Check sheet
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 6.9 - Warning Indicators TACTILE PAVERS (PEDESTRIAN CROSSINGS)
label | Detail - 300 mm square
label | ○ 60mm thick
label | ○ Shall be aligned with the intended direction of travel of the pedestrian
label | Acceptance / Conformance Criteria - LTNZ RTS14 STANDARD
label | Standard / Specification - 232735.02-WSP-DR-RSA-0304
label | Verifying Document - Delivery Dockets, Check sheet
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 6.10 - Directional Indicators TACTILE PAVERS (PEDESTRIAN CROSSINGS)
label | Detail - 300 mm square
label | ○ Shall be aligned with the intended direction of travel of the pedestrian
label | Acceptance / Conformance Criteria - LTNZ RTS14 STANDARD
label | Standard / Specification - 232735.02-WSP-DR-RSA-0304
label | Verifying Document - Delivery Dockets, Check sheet
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
section | SECTION 7 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 7.1 - Final Inspection
label | Detail - Final inspection of all concrete work.
label | Acceptance / Conformance Criteria - All works meet project specifications and standards.
label | Standard / Specification - NZTA P39: 2013
label | Verifying Document - Final inspection report
label | Testing Quantity Required (based from schedule qtys) - 100% Completion of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.2 - As-Builts
label | Detail - Final inspection of all concrete work.
label | ○ Red Pen Mark up
label | Acceptance / Conformance Criteria - All works meet project specifications and standards. any changes to be noted on redpen markuProject Specifications
label | Standard / Specification - Project Specifications 16.7.6
label | Verifying Document - Red Pen Markup
label | Testing Quantity Required (based from schedule qtys) - 100% Completion of works
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1210-024 ITP Permanent Line Marking | itp |  |  |  |  | DN1210-024 ITP Permanent Line Marking REV 0
section | SECTION 3 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
checkpoint | 3.1.1 - Paint
label | Detail / Activity - comply to TNZ M/7, TNZ M/20 and TNZ M/24 requirements as applicable. It also must be the brand and type currently approved for use on State Highways.
label | Acceptance / Conformance Criteria - Engineer approval
label | Standard / Specification - PS-26.4.4
label | Verifying Document - Data Sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to Procurement
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Glass Beads
label | Detail / Activity - As per NZTA P/12:the Glass Beads must comply with the AS2009:1991
label | Acceptance / Conformance Criteria - As Per Specification Requirements and NZTA P/12
label | Standard / Specification - PS-26.4.4
label | Verifying Document - Data Sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to Procurement
label | Verification Activity: Activity - H
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - SE
checkpoint | 3.1.4 - Paint Applicator Testing
label | Detail / Activity - All applicator plant/equipment shall comply to requirements of the NZTA specification T/8 and must have a certificate of Compliance as per TNZ P/12 Specification
label | Acceptance / Conformance Criteria - As Per Project Specification
label | Standard / Specification - PS-26.4.4
label | Verifying Document - Test Certificate
label | Testing Quantity Required (based from schedule qtys) - Once per paint applicator
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 – CONSTRUCTION ACTIVITY
checkpoint | 4.1.1 - Survey Set Outs
label | Detail / Activity - Survey to set out edge,centre line at 20m interval on straight sections and 10m intervals on curves. Ensure setout is from the latest CAD file.
label | Acceptance / Conformance Criteria - Prior to commencement of line marking.
label | Standard / Specification - IFC Drawings
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - For each shift
label | Verification Activity: Activity - W
label | Review of text reports/records or other evidence of compliance
label | Verification Activity: By - ENG
checkpoint | 4.1.2 - Paint Marking tolerances
label | Detail / Activity - Paint marking tolerances shall be accordence with the section 10 of P12 requirements. and as per PS26.4.6 for transverse location +-20mm, Longitudinal location +-50mm
label | Acceptance / Conformance Criteria - Picture
label | Standard / Specification - NZTA P12
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - For each shift
label | Verification Activity: Activity - V
label | Visual Verification
label | Verification Activity: By - SE
checkpoint | 4.1.3 - Features, Arrows and Letters
label | Detail / Activity - Painting of Features, Arrows, Symbols, Letters etc shall be in accordance with industry best practice. Works shall conform with the requirement of TNZ P/12 specification.
label | Acceptance / Conformance Criteria - Paint Marking meeting the project specification and NZTA P/12
label | Standard / Specification - Detail as per IFC Drawing following PS 24.4.3
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - For each shift
label | Verification Activity: Activity - V
label | Visual Verification
label | Verification Activity: By - SE
checkpoint | 4.1.4 - Application Rates
label | Detail / Activity - For paint the finished dry film thickness shall be 150microns or greater. Film thickness is measured on steel plates
label | Acceptance / Conformance Criteria - Paint Marking meeting the project specification and NZTA P/12
label | Standard / Specification - PS-26.4.4
label | Verifying Document - Visual Inspection / Test Plate Certificate
label | Testing Quantity Required (based from schedule qtys) - Min of 2 per day after pressure or speed settings are changed.
label | Verification Activity: Activity - V
label | Visual Verification
label | Verification Activity: By - SE
checkpoint | 4.1.5 - Thinners
label | Detail / Activity - Thinners, when used in conjunction with paint application, shall be added according to the manufacturer's instruction.
label | Acceptance / Conformance Criteria - As Per Specification Requirements and NZTA P/12
label | Standard / Specification - PS-26.4.4
label | Verifying Document - sub-contractor's QA Record
label | Testing Quantity Required (based from schedule qtys) - As required
label | Verification Activity: Activity - M
label | Monitor
label | Verification Activity: By - SE
checkpoint | 4.1.6 - Road Reflectorised Pavement Markings (RRPM)
label | Detail / Activity - RRPM's for lane lines and edge lines shall be monodirectional, while RRPM's for centerlines and flush median border lines shall be bidirectional, as per MOTSAM requirements
label | Acceptance / Conformance Criteria - Paint Marking meeting the project specification and NZTA P/22
label | Standard / Specification - PS-26.4.4 (I)
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - As per DWG, RSA-0333,0334
label | Verification Activity: Activity - V
label | Visual Verification
label | Verification Activity: By - SE
checkpoint | 4.1.6 - Dry Reflectivity
label | Detail / Activity - The reflectivity is measured using a suitable photometer or reflectometer. 5 readings are taken and the results are avereged.
label | Acceptance / Conformance Criteria - Paint Marking meeting the project specification and NZTA P/22
label | Standard / Specification - PS-26.4.4
label | Verifying Document - Visual Inspection / Test Certificate
label | Testing Quantity Required (based from schedule qtys) - 1 test per 1km to a maximum of 5 tests
label | Verification Activity: Activity - I
label | Inspection
label | (Formal inspection activity to be undertaken and recorded)
label | Verification Activity: By - SE
section | SECTION 5 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 5.1.1 - Post Line Marking Inspection
label | Detail / Activity - Complete visual inspection of linemarking
label | Acceptance / Conformance Criteria - Accepted by the engineers representative that it is visually appealing
label | Standard / Specification - Project Specifications
label | Verifying Document - Site Instruction
label | Testing Quantity Required (based from schedule qtys) - Post works completion of a lot
label | Verification Activity: Activity - H
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - SE
checkpoint | 5.1.2 - Survey As-Builts
label | Detail / Activity - As built records of the finished line marking
label | Acceptance / Conformance Criteria - Meets spec as per drawings and capture any NCR or change to design.
label | Standard / Specification - Project Specifications
label | Verifying Document - Red pen markup
label | Testing Quantity Required (based from schedule qtys) - Post works completion of a lot
label | Verification Activity: Activity - R
label | Review Redpen markup
label | Verification Activity: By - SE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature