## GR Page 1
Contact Details
Project: |  |  |  | Contact:
Address: |  |  |  | Mobile:
Run Number: |  | Location Description:
Set out, Instruction, Issues, confirmation (Circle)
Start and Finish Points Located? |  | Yes | No | Did services affect the installation? |  |  | Yes | No
Face of Barrier Located? |  | Yes | No | Did rock affect the installation (drilled)? |  |  | Yes | No | (±✓
Service Location works completed? |  | Yes | No | Are fixed tie in points at the correct height? (Concrete Barriers, Bridge Barrier, etc) |  |  | Yes | No
Services clearly marked out? |  | Yes | No
Quantities Installed
Intermediate Barrier | Terminals |  |  | Motorcycle Protection |  | Additionals
Ezyguard 4/S | ET-SS TL2 |  |  | Hiasa Rubrail |  | Delineators
Ezyguard HC | ET-SS TL3 |  |  | Ingal MPR |  | Directional Decals
Ramshield | MSKT TL2 |  |  | Bikershield
Ramshield HC | MSKT TL3 |  |  | ET2000 Cover |  | Rocketbloc
G4 (Public Domain) | Terminal 1 (Melt) |  |  | ET-SS Cover |  | Ezy-Lift
G9 (Public Domain) | Terminal 2 (DET) |  |  | MSKT Cover |  | Abraham Blocks
Ezyguard LDS | Transition 1 (8m) |  |  | Ezy Post Caps |  | Trend Median
Ramshield Edge | Transition 2 (6m) |  |  | Ramshield Post Cap |  | X-Tension Median
| Ingal RBT |  |  | Terminal Post Caps |  | Ezy Bridge Barrier
Baseplated (BP), Drilling, Misc
Were any posts baseplated? How many and what type
Were any posts drilled? How many, diametre and depth
Inspection and Test Results
Testing Activity |  | Process of activity |  |  | Pass/Fail | Comments
Post heights |  | Check with tape at regular intervals
Post Verticallity |  | Check with level at regular intervals
Rail directional lapping |  | Does it flow with traffic? Check supplier
Rail heights |  | Check with tape at regular intervals
Rail and Post Bolts |  | Shake test or physically check each bolt
Terminal Impact Head |  | Check sitting correctly and secured
Terminal Anchor Cables |  | Check has been tightened
Up/Down Smoothing |  | Visual inspection, stay within tolerances
Batch Numbers |  | Read and Record back page
Compromised Galvanising |  | Cold Gal Spray to any areas needed
Directional Decals |  | Check facing correct way and clean
Delineation (Type) |  | Delineators correct colour?
Delineation (Direction) |  | Facing towards traffic?
Delineation (Spacing) |  | Correct spacing? Check MRTS14
Housekeeping |  | Your waste, rubbish, excess material
I confirm that the above works have been installed in accordance with main or local road authority specifications and manufacturers recommendations. Any alterations have been under instruction by those detailed in Daily Diary document.
Signature |  |  |  |  | Date
ECM Leading Hand |  |  |  |  | / /
Client Contact |  |  |  |  | / /
ECM Manager |  |  |  |  | / /

## GR Page 2
Barrier measurements and tolerances (INFORMATION SHEET)
Product | Post Type | Post Height | Height Tolerance | Rail Lap | Rail Type
Ezyguard 4 | 1650mm Z Post | 777mm | +25/-50mm | Traffic Flow | W-Beam
Ezyguard HC | 2000mm Z Post | 970mm | ±20mm | Traffic Flow | Thrie-Beam
Ezyguard LDS | 2000mm Z Post | 970mm | ±20mm | Traffic Flow | Thrie-Beam
Ramshield | 1560mm C Post | 750mm | ±20mm | Traffic Flow | W-Beam
Ramshield HC | 1860mm C Post | 970mm | ±20mm | Traffic Flow | Thrie-Beam
Ramshield Edge | 1860mm C Post | 970mm | ±20mm | Traffic Flow | Thrie-Beam
G4 (Public Domain) | 1850mm C Post | 750mm | ±10mm | Traffic Flow | W-Beam
G9 (Public Domain) | 2150mm C Post | 845mm | ±10mm | Traffic Flow | Thrie-Beam
ET-SS TL2 | 1830mm I Beam | 813mm | ±20mm | As an Approach | W-Beam
ET-SS TL3 | 1830mm I Beam | 813mm | ±20mm | As an Approach | W-Beam
MSKT TL2 | 1830mm I Beam | 810mm | ±20mm | Traffic Flow | W-Beam
MSKT TL3 | 1830mm I Beam | 810mm | ±20mm | Traffic Flow | W-Beam
Max-Tension TL2 | 1830mm I Beam | 810mm | Not Specified | Traffic Flow | W-Beam
Max-Tension TL3 | 1830mm I Beam | 810mm | Not Specified | Traffic Flow | W-Beam
X350 | 1830mm I Beam | 750mm | ±10mm | As an Approach | W-Beam
Terminal 1 (Melt) | 1850mm I and C Mix | 750mm | ±10mm | Traffic Flow | W-Beam
Terminal 2 (DET) | 1850mm C Posts | 750mm | ±10mm | Traffic Flow | W-Beam
Transition 1 (8m) | 2150mm C Posts | 845mm | ±10mm | Traffic Flow | Thrie-Beam
Transition 2 (6m) | 2150mm C Posts | 845mm | ±10mm | Traffic Flow | Thrie-Beam
Ingal RBT | 1830mm I Beam | 852mm | Not Specified | Traffic Flow | Thrie-Beam
Motorcycle Protection Products
Product | Roadsurface to bottom of rail |  | Rail Height | Rail Lap | Supplier
Hiasa Rubrail | Not Specified |  | Gov by top rail | Traffic Flow | SafeDirection
Ingal MPR | 60mm ±20 |  | =350mm | Traffic Flow | Ingal
Bikershield | 30mm (Nom) |  | Gov by top rail | Traffic Flow | SafeDirection

## GR Page 3
Contact Details
Project: |  |  | Contact:
Address: |  |  | Mobile:
Run Number: |  | Location Description:
Set out, Instruction, Issues, confirmation (Circle)
Design & Height |  |  | Batch Numbers - Should match steel certificates
Barrier Layout | Post Height | Post Verticality (✓) | Rail | Post | Block (If Applicable) | (±✓
Signature |  |  |  | Date
ECM Leading Hand |  |  |  | / /

## WR Page 1
Contact Details
Project: |  |  |  | Contact:
Address: |  |  |  | Mobile:
Run Number: |  | Location Description:
Set out, Instruction, Issues, confirmation (Circle)
Start and Finish Points Located? |  | Yes | No | Did services affect the installation? |  |  | Yes | No
Face of Barrier Located? |  | Yes | No | Did rock affect the installation (drilled)? |  |  | Yes | No | (±✓
Service Location works completed? |  | Yes | No | Issues?_____________________________________________________________________\ |  |  | Yes | No
Services clearly marked out? |  | Yes | No
Quantities Installed
Barrier Length (m) | How many posts? |  |  | Barrier Anchors |  | Additionals
Flexfence | Flexfence |  |  | Flexfence Anchors |  | Yellow Delineators
Mashflex | Mashflex |  |  | Mashflex Anchors |  | Red Delineators
Sentryline-M | Sentryline-M |  |  | Sentryline Anchors
Brifen | Brifen |  |  | Brifen Anchors
Baseplated (BP), Drilling, Misc
Were any posts baseplated? How many and what type
diametre and depth of holes drilled
Inspection and Test Results
Testing Activity |  | Process of activity |  |  | Pass/Fail | Comments
Post heights |  | Check with tape at regular intervals
Post Verticallity |  | Check with level at regular intervals
Post Direction |  | Does it flow with traffic? Check supplier
Wire Rope Height |  | Check with tape at regular intervals
Anchor bolts, shackles, Check Ropes |  | Physically check each
Anchor Dimensions |  | Check dimensions with tape
Barrier allignment |  | Check barrier is within setout marks
Anchor Finish |  | Concrete Anchors broom finished
Post Finish |  | Concrete Posts smooth finish
Compromised Galvanising |  | Cold Gal Spray to any areas needed
Directional Decals |  | Check facing correct way and clean
Delineation (Type) |  | Delineators correct colour?
Delineation (Direction) |  | Facing towards traffic?
Delineation (Spacing) |  | Correct spacing? Check MRTS14
Housekeeping |  | Your waste, rubbish, excess material
I confirm that the above works have been installed in accordance with main or local road authority specifications and manufacturers recommendations. Any alterations have been under instruction by those detailed in Daily Diary document.
Signature |  |  |  |  | Date
ECM Leading Hand |  |  |  |  | / /
Client Contact |  |  |  |  | / /
ECM Manager |  |  |  |  | / /

## WR Page 2
Barrier measurements and tolerances (INFORMATION SHEET)
Product | Post Footing | Post Height | Height Tolerance | Tension Tolerance | Post Direction
Flexfence | 300 x 600mm | 780mm | -10 / + 30mm | - 1kN / +2kN | Traffic Flow
Mashflex | 300 x 600mm | 880mm | -10 / + 30mm | - 1kN / +2kN | Traffic Flow
Sentryline-M | 300 x 600mm | 900mm | ± 25 | Not Specified | Traffic Flow
Brifen | 300 x 600mm | 970mm | ± 25 | Not Specified | Traffic Flow
Anchor measurements and tolerances (INFORMATION SHEET)
Product | Anchor Length | Anchor Width | Anchor Depth | Anchor Fitting | Footing Options?
Flexfence | 2500mm | 1000mm | 1500mm | Check Ropes | Yes
Mashflex | 2600mm | 1000mm | 1500mm | 300mm Bolt | Yes
Sentryline-M | 2300mm | 1500mm | 1000mm | Trigger Post | No
Brifen | 3000mm | 1500mm | 1000mm | Check Ropes | No
Barrier Post Spacing, Post Options, (INFORMATION SHEET)
Product | Post Spacing | Baseplate Posts | Driven Posts | Point of Need | Supplier
Flexfence | 2.5m or 3m | Yes | Yes | 8800mm | Ingal Civil Products
Mashflex | 2.5m or 3m | Yes | Yes | 8800mm | Ingal Civil Products
Sentryline-M | 3m | No | No | 13500mm | Safedirection
Brifen | 3m | No | No | 11250mm | Safedirection

## CC Page 1
Contact Details
Project: |  |  |  | Contact:
Address: |  |  |  | Mobile:
Run Number: |  | Location Description:
Set out, Instruction, Issues, confirmation (Circle)
Concrete Foundation Installed? |  | Yes | No | Steel occurred during drlling? |  |  | Yes | No
Foundation appears correct? |  | Yes | No | Is this unit a Tension Strut? |  |  | Yes | No | (±✓
Transitions to Barrier Required? |  | Yes | No | Is this unit a Concrete Backup? |  |  | Yes | No
If so, is foundation square with barrier? |  | Yes | No |  |  |  | Yes | No
Product Installed
Ingal Civil Products | Safedirection |  |  | Temporary Crash Cushions |  | Additionals
Quadguard | TAU-XR |  |  | Quadguards |  | Delineators
Quadguard M10 | Universal TAU-M |  |  | TAU Cushion |  | Directional Decals
Quadguard Elite | Hercules |  |  | Absorb-M |  | BG800 Med Gate
QuadG- Elite M10 |  |  |  | BG800
Additional
Crash Cushion Bays? | LHS Transition |  |  | RHS Transition |  | Endshoes
Epoxy Tubes | Anchors Installed |  |  | Drill bit diametre |  | Drill depth
Inspection and Test Results
Testing Activity |  | Process of activity |  |  | Pass/Fail | Comments
Foundation Height |  | Check concrete foundation matches road
Crash Cushion positioning |  | Check placed in the correct position
Anchor Diametre & Length |  | Check Anchors meet specification
Concrete Drilling |  | Check drilled to suitable dia/depth
Excess Thread |  | Check suitable thread exposed
Epoxy volume |  | Check signs of epoxy overflow
Anchor, bolts and cable tension |  | Check with appropriate tightening tools
Travel Bolts |  | Check travel bolts are removed
Batch Numbers |  | Read and Record back page
Compromised Galvanising |  | Cold Gal Spray to any areas needed
Directional Decals |  | Check facing correct way and clean
Housekeeping |  | Your waste, rubbish, excess material
Functionality (Gates) |  | Check gate opens and closes correctly
I confirm that the above works have been installed in accordance with main or local road authority specifications and manufacturers recommendations. Any alterations have been under instruction by those detailed in Daily Diary document.
Signature |  |  |  |  | Date
ECM Leading Hand |  |  |  |  | / /
Client Contact |  |  |  |  | / /
ECM Manager |  |  |  |  | / /