## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | XXXXXXXXXXX – Shift Report | [5 empty] | Shift Report
section | Details
checkpoint | Shift Report
textbox | Job ID:
textbox | PO#:
textbox | Location:
textbox | Summary of Works:
date | Date Completed:
textbox | Time started / finished: |  |  | XX:XX – XX:XX
button | Permit Acceptor: | Not required,Required
textbox | ECM Progress Claim:
label | Upload Photos (before / after)
checklist | 1. ECM - CC | itp |  |  |  |  | 1. ECM - CC
section | Set out, Instruction, Issues, confirmation
checkpoint | Concrete Foundation Installed?
checkpoint | Foundation appears correct?
checkpoint | Transitions to Barrier Required?
checkpoint | If so, is foundation square with barrier?
checkpoint | Steel occurred during drlling?
checkpoint | Is this unit a Tension Strut?
checkpoint | Is this unit a Concrete Backup?
section | Product Installed
checkpoint-no-status | Ingal Civil Products
textbox | Quadguard
textbox | Quadguard M10
textbox | Quadguard Elite
textbox | QuadG- Elite M10
checkpoint-no-status | Safedirection
textbox | TAU-XR
textbox | Universal TAU-M
textbox | Hercules
checkpoint-no-status | Temporary Crash Cushions
textbox | Quadguards
textbox | TAU Cushion
textbox | Absorb-M
textbox | BG800
checkpoint-no-status | Additionals
textbox | Delineators
textbox | Directional Decals
textbox | BG800 Med Gate
section | Additional
checkpoint-no-status | Additional
textbox | Crash Cushion Bays?
textbox | Epoxy Tubes
textbox | LHS Transition
textbox | Anchors Installed
textbox | RHS Transition
textbox | Drill bit Diameter
textbox | Endshoes
textbox | Drill depth
section | Inspection and Test Results
checkpoint | Foundation Height
label | Process of activity: Check concrete foundation matches road
checkpoint | Crash Cushion positioning
label | Process of activity: Check placed in the correct position
checkpoint | Anchor Diameter & Length
label | Process of activity: Check Anchors meet specification
checkpoint | Concrete Drilling
label | Process of activity: Check drilled to suitable dia/depth
checkpoint | Excess Thread
label | Process of activity: Check suitable thread exposed
checkpoint | Epoxy volume
label | Process of activity: Check signs of epoxy overflow
checkpoint | Anchor, bolts and cable tension
label | Process of activity: Check with appropriate tightening tools
checkpoint | Travel Bolts
label | Process of activity: Check travel bolts are removed
checkpoint | Batch Numbers
label | Process of activity: Read and Record back page
checkpoint | Compromised Galvanising
label | Process of activity: Cold Gal Spray to any areas needed
checkpoint | Directional Decals
label | Process of activity: Check facing correct way and clean
checkpoint | Housekeeping
label | Process of activity: Your waste, rubbish, excess material
checkpoint | Functionality (Gates)
label | Process of activity: Check gate opens and closes correctly
checkpoint | I confirm that the above works have been installed in accordance with main or local road authority specifications and manufacturers recommendations. Any alterations have been under instruction by those detailed in Daily Diary document.
holdpoint | Signature - ECM Leading Hand / Client Contact / ECM Manager
checklist | 1. ECM - GR | itp |  |  |  |  | 1. ECM - GR
section | Set out, Instruction, Issues, confirmation
checkpoint | Start and Finish Points Located?
checkpoint | Face of Barrier Located?
checkpoint | Service Location works completed?
checkpoint | Services clearly marked out?
checkpoint | Did services affect the installation?
checkpoint | Did rock affect the installation (drilled)?
checkpoint | Are fixed tie in points at the correct height? (Concrete Barriers, Bridge Barrier, etc)
checkpoint-no-status | Design & Height
textbox | Barrier Layout
textbox | Post Height
bool | Post Verticality (✓)
checkpoint-no-status | Batch Numbers - Should match steel certificates
textbox | Rail
textbox | Post
bool | Block (If Applicable)
checkpoint | Signature
holdpoint | ECM Leading Hand
section | Quantities Installed
checkpoint-no-status | Intermediate Barrier
textbox | Ezyguard 4/S
textbox | Ezyguard HC
textbox | Ramshield
textbox | Ramshield HC
textbox | G4 (Public Domain)
textbox | G9 (Public Domain)
textbox | Ezyguard LDS
textbox | Ramshield Edge
checkpoint-no-status | Terminals
textbox | ET-SS TL2
textbox | ET-SS TL3
textbox | MSKT TL2
textbox | MSKT TL3
textbox | Terminal 1 (Melt)
textbox | Terminal 2 (DET)
textbox | Transition 1 (8m)
textbox | Transition 2 (6m)
textbox | Ingal RBT
checkpoint-no-status | Motorcycle Protection
textbox | Hiasa Rubrail
textbox | Ingal MPR
textbox | Bikershield
textbox | ET2000 Cover
textbox | ET-SS Cover
textbox | MSKT Cover
textbox | Ezy Post Caps
textbox | Ramshield Post Cap
textbox | Terminal Post Caps
checkpoint-no-status | Additionals
textbox | Delineators
textbox | Directional Decals
textbox | Rocketbloc
textbox | Ezy-Lift
textbox | Abraham Blocks
textbox | Trend Median
textbox | X-Tension Median
textbox | Ezy Bridge Barrier
section | Baseplated (BP), Drilling, Misc
checkpoint | Were any posts baseplated?
textbox | How many and what type:
checkpoint | Were any posts drilled?
textbox | How many, Diameter and depth
section | Inspection and Test Results
checkpoint | Post heights
label | Process of activity: Check with tape at regular intervals
checkpoint | Post Verticallity
label | Process of activity: Check with level at regular intervals
checkpoint | Rail directional lapping
label | Process of activity: Does it flow with traffic? Check supplier
checkpoint | Rail heights
label | Process of activity: Check with tape at regular intervals
checkpoint | Rail and Post Bolts
label | Process of activity: Shake test or physically check each bolt
checkpoint | Terminal Impact Head
label | Process of activity: Check sitting correctly and secured
checkpoint | Terminal Anchor Cables
label | Process of activity: Check has been tightened
checkpoint | Up/Down Smoothing
label | Process of activity: Visual inspection, stay within tolerances
checkpoint | Batch Numbers
label | Process of activity: Read and Record back page
checkpoint | Compromised Galvanising
label | Process of activity: Cold Gal Spray to any areas needed
checkpoint | Directional Decals
label | Process of activity: Check facing correct way and clean
checkpoint | Delineation (Type)
label | Process of activity: Delineators correct colour?
checkpoint | Delineation (Direction)
label | Process of activity: Facing towards traffic?
checkpoint | Delineation (Spacing)
label | Process of activity: Correct spacing? Check MRTS14
checkpoint | Housekeeping
label | Process of activity: Your waste, rubbish, excess material
checkpoint | I confirm that the above works have been installed in accordance with main or local road authority specifications and manufacturers recommendations. Any alterations have been under instruction by those detailed in Daily Diary document.
holdpoint | Signature - ECM Leading Hand / Client Contact / ECM Manager
section | Barrier measurements and tolerances / Motorcycle Protection Products
checkpoint-no-status | Barrier measurements and tolerances (INFORMATION SHEET)
label | Product ¦ Post Type ¦ Post Height ¦ Height Tolerance ¦ Rail Lap ¦ Rail Type
label | — — — — — — — — —
label | Ezyguard 4 ¦ 1650mm Z Post ¦ 777mm ¦ +25/-50mm ¦ Traffic Flow ¦ W-Beam
label | Ezyguard HC ¦ 2000mm Z Post ¦ 970mm ¦ ±20mm ¦ Traffic Flow ¦ Thrie-Beam
label | Ezyguard LDS ¦ 2000mm Z Post ¦ 970mm ¦ ±20mm ¦ Traffic Flow ¦ Thrie-Beam
label | Ramshield ¦ 1560mm C Post ¦ 750mm ¦ ±20mm ¦ Traffic Flow ¦ W-Beam
label | Ramshield HC ¦ 1860mm C Post ¦ 970mm ¦ ±20mm ¦ Traffic Flow ¦ Thrie-Beam
label | Ramshield Edge ¦ 1860mm C Post ¦ 970mm ¦ ±20mm ¦ Traffic Flow ¦ Thrie-Beam
label | G4 (Public Domain) ¦ 1850mm C Post ¦ 750mm ¦ ±10mm ¦ Traffic Flow ¦ W-Beam
label | G9 (Public Domain) ¦ 2150mm C Post ¦ 845mm ¦ ±10mm ¦ Traffic Flow ¦ Thrie-Beam
label | ET-SS TL2 ¦ 1830mm I Beam ¦ 813mm ¦ ±20mm ¦ As an Approach ¦ W-Beam
label | ET-SS TL3 ¦ 1830mm I Beam ¦ 813mm ¦ ±20mm ¦ As an Approach ¦ W-Beam
label | MSKT TL2 ¦ 1830mm I Beam ¦ 810mm ¦ ±20mm ¦ Traffic Flow ¦ W-Beam
label | MSKT TL3 ¦ 1830mm I Beam ¦ 810mm ¦ ±20mm ¦ Traffic Flow ¦ W-Beam
label | Max-Tension TL2 ¦ 1830mm I Beam ¦ 810mm ¦ Not Specified ¦ Traffic Flow ¦ W-Beam
label | Max-Tension TL3 ¦ 1830mm I Beam ¦ 810mm ¦ Not Specified ¦ Traffic Flow ¦ W-Beam
label | X350 ¦ 1830mm I Beam ¦ 750mm ¦ ±10mm ¦ As an Approach ¦ W-Beam
label | Terminal 1 (Melt) ¦ 1850mm I and C Mix ¦ 750mm ¦ ±10mm ¦ Traffic Flow ¦ W-Beam
label | Terminal 2 (DET) ¦ 1850mm C Posts ¦ 750mm ¦ ±10mm ¦ Traffic Flow ¦ W-Beam
label | Transition 1 (8m) ¦ 2150mm C Posts ¦ 845mm ¦ ±10mm ¦ Traffic Flow ¦ Thrie-Beam
label | Transition 2 (6m) ¦ 2150mm C Posts ¦ 845mm ¦ ±10mm ¦ Traffic Flow ¦ Thrie-Beam
label | Ingal RBT ¦ 1830mm I Beam ¦ 852mm ¦ Not Specified ¦ Traffic Flow ¦ Thrie-Beam
checkpoint-no-status | Motorcycle Protection Products
label | Product ¦ Roadsurface to bottom of rail ¦ Rail Height ¦ Rail Lap ¦ Supplier
label | — — — — — — — — —
label | Hiasa Rubrail ¦ Not Specified ¦ ¦ Gov by top rail ¦ Traffic Flow ¦ SafeDirection
label | Ingal MPR ¦ 60mm ±20 ¦ ¦ =350mm ¦ Traffic Flow ¦ Ingal
label | Bikershield ¦ 30mm (Nom) ¦ ¦ Gov by top rail ¦ Traffic Flow ¦ SafeDirection
checklist | 1. ECM - WR | itp |  |  |  |  | 1. ECM - WR
section | Set out, Instruction, Issues, confirmation
checkpoint | Start and Finish Points Located?
checkpoint | Face of Barrier Located?
checkpoint | Service Location works completed?
checkpoint | Services clearly marked out?
checkpoint | Did services affect the installation?
checkpoint | Did rock affect the installation (drilled)?
checkpoint | Issues?
textbox | Issues:
section | Quantities Installed
checkpoint-no-status | Barrier Length (m)
textbox | Flexfence
textbox | Mashflex
textbox | Sentryline-M
textbox | Brifen
checkpoint-no-status | How many posts?
textbox | Flexfence
textbox | Mashflex
textbox | Sentryline-M
textbox | Brifen
checkpoint-no-status | Barrier Anchors
textbox | Flexfence Anchors
textbox | Mashflex Anchors
textbox | Sentryline Anchors
textbox | Brifen Anchors
checkpoint-no-status | Additionals
textbox | Yellow Delineators
textbox | Red Delineators
section | Baseplated (BP), Drilling, Misc
checkpoint | Were any posts baseplated?
textbox | How many and what type
textbox | Diameter and depth of holes drilled
section | Inspection and Test Results
checkpoint | Post heights
label | Process of activity: Check with tape at regular intervals
checkpoint | Post Verticallity
label | Process of activity: Check with level at regular intervals
checkpoint | Post Direction
label | Process of activity: Does it flow with traffic? Check supplier
checkpoint | Wire Rope Height
label | Process of activity: Check with tape at regular intervals
checkpoint | Anchor bolts, shackles, Check Ropes
label | Process of activity: Physically check each
checkpoint | Anchor Dimensions
label | Process of activity: Check dimensions with tape
checkpoint | Barrier allignment
label | Process of activity: Check barrier is within setout marks
checkpoint | Anchor Finish
label | Process of activity: Concrete Anchors broom finished
checkpoint | Post Finish
label | Process of activity: Concrete Posts smooth finish
checkpoint | Compromised Galvanising
label | Process of activity: Cold Gal Spray to any areas needed
checkpoint | Directional Decals
label | Process of activity: Check facing correct way and clean
checkpoint | Delineation (Type)
label | Process of activity: Delineators correct colour?
checkpoint | Delineation (Direction)
label | Process of activity: Facing towards traffic?
checkpoint | Delineation (Spacing)
label | Process of activity: Correct spacing? Check MRTS14
checkpoint | Housekeeping
label | Process of activity: Your waste, rubbish, excess material
checkpoint | I confirm that the above works have been installed in accordance with main or local road authority specifications and manufacturers recommendations. Any alterations have been under instruction by those detailed in Daily Diary document.
holdpoint | Signature - ECM Leading Hand / Client Contact / ECM Manager
section | Barrier measurements and tolerances / Anchor measurements and tolerances / Barrier Post Spacing, Post Options
checkpoint-no-status | Barrier measurements and tolerances (INFORMATION SHEET)
label | Product ¦ Post Footing ¦ Post Height ¦ Height Tolerance ¦ Tension Tolerance ¦ Post Direction
label | — — — — — — — — —
label | Flexfence ¦ 300 x 600mm ¦ 780mm ¦ -10 / + 30mm ¦ - 1kN / +2kN ¦ Traffic Flow
label | Mashflex ¦ 300 x 600mm ¦ 880mm ¦ -10 / + 30mm ¦ - 1kN / +2kN ¦ Traffic Flow
label | Sentryline-M ¦ 300 x 600mm ¦ 900mm ¦ ± 25 ¦ Not Specified ¦ Traffic Flow
label | Brifen ¦ 300 x 600mm ¦ 970mm ¦ ± 25 ¦ Not Specified ¦ Traffic Flow
checkpoint-no-status | Anchor measurements and tolerances (INFORMATION SHEET)
label | Product ¦ Anchor Length ¦ Anchor Width ¦ Anchor Depth ¦ Anchor Fitting ¦ Footing Options?
label | — — — — — — — — —
label | Flexfence ¦ 2500mm ¦ 1000mm ¦ 1500mm ¦ Check Ropes ¦ Yes
label | Mashflex ¦ 2600mm ¦ 1000mm ¦ 1500mm ¦ 300mm Bolt ¦ Yes
label | Sentryline-M ¦ 2300mm ¦ 1500mm ¦ 1000mm ¦ Trigger Post ¦ No
label | Brifen ¦ 3000mm ¦ 1500mm ¦ 1000mm ¦ Check Ropes ¦ No
checkpoint-no-status | Barrier Post Spacing, Post Options (INFORMATION SHEET)
label | Product ¦ Post Spacing ¦ Baseplate Posts ¦ Driven Posts ¦ Point of Need ¦ Supplier
label | — — — — — — — — —
label | Flexfence ¦ 2.5m or 3m ¦ Yes ¦ Yes ¦ 8800mm ¦ Ingal Civil Products
label | Mashflex ¦ 2.5m or 3m ¦ Yes ¦ Yes ¦ 8800mm ¦ Ingal Civil Products
label | Sentryline-M ¦ 3m ¦ No ¦ No ¦ 13500mm ¦ Safedirection
label | Brifen ¦ 3m ¦ No ¦ No ¦ 11250mm ¦ Safedirection
checklist | 2. Guardrail | itp |  |  |  |  | 2. Guardrail
section | Set out, Instruction, Issues, confirmation
checkpoint | Start and Finish Points Located?
checkpoint | Face of Barrier Located?
checkpoint | Service Location works completed?
checkpoint | Services clearly marked out?
checkpoint | Did services affect the installation?
checkpoint | Did rock affect the installation (drilled)?
checkpoint | Are fixed tie in points at the correct height? (Concrete Barriers, Bridge Barrier, etc)
checkpoint-no-status | Design & Height
textbox | Barrier Layout
textbox | Post Height
bool | Post Verticality (✓)
checkpoint-no-status | Batch Numbers - Should match steel certificates
textbox | Rail
textbox | Post
bool | Block (If Applicable)
checkpoint | Signature
holdpoint | ECM Leading Hand
section | Quantities Installed
checkpoint-no-status | Intermediate Barrier
textbox | Ezyguard 4/S
textbox | Ezyguard HC
textbox | Ramshield
textbox | Ramshield HC
textbox | G4 (Public Domain)
textbox | G9 (Public Domain)
textbox | Ezyguard LDS
textbox | Ramshield Edge
checkpoint-no-status | Terminals
textbox | ET-SS TL2
textbox | ET-SS TL3
textbox | MSKT TL2
textbox | MSKT TL3
textbox | Terminal 1 (Melt)
textbox | Terminal 2 (DET)
textbox | Transition 1 (8m)
textbox | Transition 2 (6m)
textbox | Ingal RBT
checkpoint-no-status | Motorcycle Protection
textbox | Hiasa Rubrail
textbox | Ingal MPR
textbox | Bikershield
textbox | ET2000 Cover
textbox | ET-SS Cover
textbox | MSKT Cover
textbox | Ezy Post Caps
textbox | Ramshield Post Cap
textbox | Terminal Post Caps
checkpoint-no-status | Motorcycle Protection
textbox | Delineators
textbox | Directional Decals
textbox | Rocketbloc
textbox | Ezy-Lift
textbox | Abraham Blocks
textbox | Trend Median
textbox | X-Tension Median
textbox | Ezy Bridge Barrier
section | Baseplated (BP), Drilling, Misc
checkpoint | Were any posts baseplated?
textbox | How many and what type
checkpoint | Were any posts drilled?
textbox | How many, Diameter and depth
section | Inspection and Test Results
checkpoint | Post heights
label | Process of activity: Check with tape at regular intervals
checkpoint | Post Verticallity
label | Process of activity: Check with level at regular intervals
checkpoint | Rail directional lapping
label | Process of activity: Does it flow with traffic? Check supplier
checkpoint | Rail heights
label | Process of activity: Check with tape at regular intervals
checkpoint | Rail and Post Bolts
label | Process of activity: Shake test or physically check each bolt
checkpoint | Terminal Impact Head
label | Process of activity: Check sitting correctly and secured
checkpoint | Terminal Anchor Cables
label | Process of activity: Check has been tightened
checkpoint | Up/Down Smoothing
label | Process of activity: Visual inspection, stay within tolerances
checkpoint | Batch Numbers
label | Process of activity: Read and Record back page
checkpoint | Compromised Galvanising
label | Process of activity: Cold Gal Spray to any areas needed
checkpoint | Directional Decals
label | Process of activity: Check facing correct way and clean
checkpoint | Delineation (Type)
label | Process of activity: Delineators correct colour?
checkpoint | Delineation (Direction)
label | Process of activity: Facing towards traffic?
checkpoint | Delineation (Spacing)
label | Process of activity: Correct spacing? Check MRTS14
checkpoint | Housekeeping
label | Process of activity: Your waste, rubbish, excess material
checkpoint | I confirm that the above works have been installed in accordance with main or local road authority specifications and manufacturers recommendations. Any alterations have been under instruction by those detailed in Daily Diary document.
holdpoint | Signature - ECM Leading Hand / Client Contact / ECM Manager
section | Barrier measurements and tolerances / Motorcycle Protection Products
checkpoint-no-status | Barrier measurements and tolerances (INFORMATION SHEET)
label | Product ¦ Post Type ¦ Post Height ¦ Height Tolerance ¦ Rail Lap ¦ Rail Type
label | — — — — — — — — —
label | Ezyguard 4 ¦ 1650mm Z Post ¦ 777mm ¦ +25/-50mm ¦ Traffic Flow ¦ W-Beam
label | Ezyguard HC ¦ 2000mm Z Post ¦ 970mm ¦ ±20mm ¦ Traffic Flow ¦ Thrie-Beam
label | Ezyguard LDS ¦ 2000mm Z Post ¦ 970mm ¦ ±20mm ¦ Traffic Flow ¦ Thrie-Beam
label | Ramshield ¦ 1560mm C Post ¦ 750mm ¦ ±20mm ¦ Traffic Flow ¦ W-Beam
label | Ramshield HC ¦ 1860mm C Post ¦ 970mm ¦ ±20mm ¦ Traffic Flow ¦ Thrie-Beam
label | Ramshield Edge ¦ 1860mm C Post ¦ 970mm ¦ ±20mm ¦ Traffic Flow ¦ Thrie-Beam
label | G4 (Public Domain) ¦ 1850mm C Post ¦ 750mm ¦ ±10mm ¦ Traffic Flow ¦ W-Beam
label | G9 (Public Domain) ¦ 2150mm C Post ¦ 845mm ¦ ±10mm ¦ Traffic Flow ¦ Thrie-Beam
label | ET-SS TL2 ¦ 1830mm I Beam ¦ 813mm ¦ ±20mm ¦ As an Approach ¦ W-Beam
label | ET-SS TL3 ¦ 1830mm I Beam ¦ 813mm ¦ ±20mm ¦ As an Approach ¦ W-Beam
label | MSKT TL2 ¦ 1830mm I Beam ¦ 810mm ¦ ±20mm ¦ Traffic Flow ¦ W-Beam
label | MSKT TL3 ¦ 1830mm I Beam ¦ 810mm ¦ ±20mm ¦ Traffic Flow ¦ W-Beam
label | Max-Tension TL2 ¦ 1830mm I Beam ¦ 810mm ¦ Not Specified ¦ Traffic Flow ¦ W-Beam
label | Max-Tension TL3 ¦ 1830mm I Beam ¦ 810mm ¦ Not Specified ¦ Traffic Flow ¦ W-Beam
label | X350 ¦ 1830mm I Beam ¦ 750mm ¦ ±10mm ¦ As an Approach ¦ W-Beam
label | Terminal 1 (Melt) ¦ 1850mm I and C Mix ¦ 750mm ¦ ±10mm ¦ Traffic Flow ¦ W-Beam
label | Terminal 2 (DET) ¦ 1850mm C Posts ¦ 750mm ¦ ±10mm ¦ Traffic Flow ¦ W-Beam
label | Transition 1 (8m) ¦ 2150mm C Posts ¦ 845mm ¦ ±10mm ¦ Traffic Flow ¦ Thrie-Beam
label | Transition 2 (6m) ¦ 2150mm C Posts ¦ 845mm ¦ ±10mm ¦ Traffic Flow ¦ Thrie-Beam
label | Ingal RBT ¦ 1830mm I Beam ¦ 852mm ¦ Not Specified ¦ Traffic Flow ¦ Thrie-Beam
checkpoint-no-status | Motorcycle Protection Products
label | Product ¦ Roadsurface to bottom of rail ¦ ¦ Rail Height ¦ Rail Lap ¦ Supplier
label | — — — — — — — — —
label | Hiasa Rubrail ¦ Not Specified ¦ Gov by top rail ¦ Traffic Flow ¦ SafeDirection
label | Ingal MPR ¦ 60mm ±20 ¦ =350mm ¦ Traffic Flow ¦ Ingal
label | Bikershield ¦ 30mm (Nom) ¦ Gov by top rail ¦ Traffic Flow ¦ SafeDirection
checklist | 3. Wirerope | itp |  |  |  |  | 3. Wirerope
section | Set out, Instruction, Issues, confirmation
checkpoint | Start and Finish Points Located?
checkpoint | Face of Barrier Located?
checkpoint | Service Location works completed?
checkpoint | Services clearly marked out?
checkpoint | Did services affect the installation?
checkpoint | Did rock affect the installation (drilled)?
checkpoint | Issues?
textbox | Issues:
section | Quantities Installed
checkpoint-no-status | Barrier Length (m)
textbox | Flexfence
textbox | Mashflex
textbox | Sentryline-M
textbox | Brifen
checkpoint-no-status | How many posts?
textbox | Flexfence
textbox | Mashflex
textbox | Sentryline-M
textbox | Brifen
checkpoint-no-status | Barrier Anchors
textbox | Flexfence Anchors
textbox | Mashflex Anchors
textbox | Sentryline Anchors
textbox | Brifen Anchors
checkpoint-no-status | Additionals
textbox | Yellow Delineators
textbox | Red Delineators
section | Baseplated (BP), Drilling, Misc
checkpoint | Were any posts baseplated?
textbox | How many and what type
textbox | Diameter and depth of holes drilled
section | Inspection and Test Results
checkpoint | Post heights
label | Process of activity: Check with tape at regular intervals
checkpoint | Post Verticallity
label | Process of activity: Check with level at regular intervals
checkpoint | Post Direction
label | Process of activity: Does it flow with traffic? Check supplier
checkpoint | Wire Rope Height
label | Process of activity: Check with tape at regular intervals
checkpoint | Anchor bolts, shackles, Check Ropes
label | Process of activity: Physically check each
checkpoint | Anchor Dimensions
label | Process of activity: Check dimensions with tape
checkpoint | Barrier allignment
label | Process of activity: Check barrier is within setout marks
checkpoint | Anchor Finish
label | Process of activity: Concrete Anchors broom finished
checkpoint | Post Finish
label | Process of activity: Concrete Posts smooth finish
checkpoint | Compromised Galvanising
label | Process of activity: Cold Gal Spray to any areas needed
checkpoint | Directional Decals
label | Process of activity: Check facing correct way and clean
checkpoint | Delineation (Type)
label | Process of activity: Delineators correct colour?
checkpoint | Delineation (Direction)
label | Process of activity: Facing towards traffic?
checkpoint | Delineation (Spacing)
label | Process of activity: Correct spacing? Check MRTS14
checkpoint | Housekeeping
label | Process of activity: Your waste, rubbish, excess material
checkpoint | I confirm that the above works have been installed in accordance with main or local road authority specifications and manufacturers recommendations. Any alterations have been under instruction by those detailed in Daily Diary document.
holdpoint | Signature - ECM Leading Hand / Client Contact / ECM Manager
section | Barrier measurements and tolerances / Anchor measurements and tolerances / Barrier Post Spacing, Post Options
checkpoint-no-status | Barrier measurements and tolerances (INFORMATION SHEET)
label | Product ¦ Post Footing ¦ Post Height ¦ Height Tolerance ¦ Tension Tolerance ¦ Post Direction
label | — — — — — — — — —
label | Flexfence ¦ 300 x 600mm ¦ 780mm ¦ -10 / + 30mm ¦ - 1kN / +2kN ¦ Traffic Flow
label | Mashflex ¦ 300 x 600mm ¦ 880mm ¦ -10 / + 30mm ¦ - 1kN / +2kN ¦ Traffic Flow
label | Sentryline-M ¦ 300 x 600mm ¦ 900mm ¦ ± 25 ¦ Not Specified ¦ Traffic Flow
label | Brifen ¦ 300 x 600mm ¦ 970mm ¦ ± 25 ¦ Not Specified ¦ Traffic Flow
checkpoint-no-status | Anchor measurements and tolerances (INFORMATION SHEET)
label | Product ¦ Anchor Length ¦ Anchor Width ¦ Anchor Depth ¦ Anchor Fitting ¦ Footing Options?
label | — — — — — — — — —
label | Flexfence ¦ 2500mm ¦ 1000mm ¦ 1500mm ¦ Check Ropes ¦ Yes
label | Mashflex ¦ 2600mm ¦ 1000mm ¦ 1500mm ¦ 300mm Bolt ¦ Yes
label | Sentryline-M ¦ 2300mm ¦ 1500mm ¦ 1000mm ¦ Trigger Post ¦ No
label | Brifen ¦ 3000mm ¦ 1500mm ¦ 1000mm ¦ Check Ropes ¦ No
checkpoint-no-status | Barrier Post Spacing, Post Options (INFORMATION SHEET)
label | Product ¦ Post Spacing ¦ Baseplate Posts ¦ Driven Posts ¦ Point of Need ¦ Supplier
label | — — — — — — — — —
label | Flexfence ¦ 2.5m or 3m ¦ Yes ¦ Yes ¦ 8800mm ¦ Ingal Civil Products
label | Mashflex ¦ 2.5m or 3m ¦ Yes ¦ Yes ¦ 8800mm ¦ Ingal Civil Products
label | Sentryline-M ¦ 3m ¦ No ¦ No ¦ 13500mm ¦ Safedirection
label | Brifen ¦ 3m ¦ No ¦ No ¦ 11250mm ¦ Safedirection
checklist | 4. Crash Cushion | itp |  |  |  |  | 4. Crash Cushion
section | Set out, Instruction, Issues, confirmation
checkpoint | Concrete Foundation Installed?
checkpoint | Foundation appears correct?
checkpoint | Transitions to Barrier Required?
checkpoint | If so, is foundation square with barrier?
checkpoint | Steel occurred during drlling?
checkpoint | Is this unit a Tension Strut?
checkpoint | Is this unit a Concrete Backup?
section | Product Installed
checkpoint-no-status | Ingal Civil Products
textbox | Quadguard
textbox | Quadguard M10
textbox | Quadguard Elite
textbox | QuadG- Elite M10
checkpoint-no-status | Safedirection
textbox | TAU-XR
textbox | Universal TAU-M
textbox | Hercules
checkpoint-no-status | Temporary Crash Cushions
textbox | Quadguards
textbox | TAU Cushion
textbox | Absorb-M
textbox | BG800
checkpoint-no-status | Additionals
textbox | Delineators
textbox | Directional Decals
textbox | BG800 Med Gate
section | Additional
checkpoint-no-status | Additional
textbox | Crash Cushion Bays?
textbox | Epoxy Tubes
textbox | LHS Transition
textbox | Anchors Installed
textbox | RHS Transition
textbox | Drill bit diametre
textbox | Endshoes
textbox | Drill depth
section | Inspection and Test Results
checkpoint | Foundation Height
label | Process of activity: Check concrete foundation matches road
checkpoint | Crash Cushion positioning
label | Process of activity: Check placed in the correct position
checkpoint | Anchor Diametre & Length
label | Process of activity: Check Anchors meet specification
checkpoint | Concrete Drilling
label | Process of activity: Check drilled to suitable dia/depth
checkpoint | Excess Thread
label | Process of activity: Check suitable thread exposed
checkpoint | Epoxy volume
label | Process of activity: Check signs of epoxy overflow
checkpoint | Anchor, bolts and cable tension
label | Process of activity: Check with appropriate tightening tools
checkpoint | Travel Bolts
label | Process of activity: Check travel bolts are removed
checkpoint | Batch Numbers
label | Process of activity: Read and Record back page
checkpoint | Compromised Galvanising
label | Process of activity: Cold Gal Spray to any areas needed
checkpoint | Directional Decals
label | Process of activity: Check facing correct way and clean
checkpoint | Housekeeping
label | Process of activity: Your waste, rubbish, excess material
checkpoint | Functionality (Gates)
label | Process of activity: Check gate opens and closes correctly
checkpoint | I confirm that the above works have been installed in accordance with main or local road authority specifications and manufacturers recommendations. Any alterations have been under instruction by those detailed in Daily Diary document.
holdpoint | Signature - ECM Leading Hand / Client Contact / ECM Manager