## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-293-CIV-SSB-Landscaping-Ground Preparation & Planting
ITP Description: |  | Landscaping-Ground Preparation & Planting
Discipline (e.g. CIV/STR/RAIL): |  | CIV
Revision Number: |  | 0
Revision Date: |  | 2025-07-18
ITP created by: |  | Ali Rajad
ITP approved for use by: |  | Sandy Escalona
Special Notes to ConQA Team : |  | ITP for SSB Project Only
Inspection & Test Plan - Landscaping-Ground Preparation & Planting
|  |  | Document No.: ITP-293-CIV-SSB-Landscaping-Ground Preparation & Planting | [5 empty] | Revision: | 0
[9 empty] | Date: | 2025-07-18
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads 720 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.2 | Non Dependent | AS 4454 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.3 | Non Dependent | AS 4419 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.4 | Non Dependent | IFC Drawings | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | Preliminaries-Materials
2.1 | Submission and records | VicRoads Spec: -Cl. 720.03 | Samples, records and certificates shall be provided to the Nominated Authority (NA) at least 10 working days prior to bulk delivery. Following information shall be provided to the NA: Samples -Mulch -Imported topsoil Records -Details of suppliers -Soil tests on imported topsoil -Copies/Photos of fertiliser labels Attach: Records and Certs into Hold Point inTeamBinder and write the Reference No. | Document Review | Prior to Commencement of works | HP | NA | ConQA HP Release
2.2 | Supply of topsoil | VicRoads Spec: -Cl.720.04 -Table 720.042 IFC Drawings | Site won topsoil to be tested to establish what soil amendments and macro and micro nutreints are required to be added to the top soil if required by planting subcontractor. Where imported topsoil is used, the topsoil must conform to the properties specified in Table 720.042 and align with IFC Drawings. Attach: Material Conformance Docs / Test Reports as Material Approval onto TeamBinder and write the Reference No. | Verify, Doc. Review if applicable | Prior to Commencement of works | HP | NA | ConQA HP Release
2.3 | Supply of Mulch | VicRoads Spec: -Cl.720.04 -Table 720.044 AS4454 IFC Drawings | Site mulch available from the chipping of on-site indigenous or non-weed vegetation shall be used where possible, otherwise approved mulch stated on IFC drawings. All wood mulch to be spread in accordance to AS 4454 and conform to required depth stated in IFC drawings . Imported Wood Mulch shall comply with Table 720.044. Attach: Material Conformance Docs / Test Reports as Material Approvasl onto TeamBinder and write the Reference No. | Verify, Doc. Review if applicable | Prior to Commencement of works | HP | NA | ConQA HP Release
2.4 | Supply of Plant | VicRoads Spec: -Cl.720.04 -Table 720.041 | All Plants have been inspected and comply with Sec 720.041 Attach: Landscape Architect Approval | Verify | Each Lot | HP | NA | ConQA HP Release
2.5 | Supply of grass seed | VicRoads Spec. -Cl.720.04 -Table 720.045 | Grass seed shall comply with Table 720.045 Attach: Material Conformance Docs / Test Reports as Material Approvasl onto TeamBinder and write the Reference No. | Verify | Prior to Commencing works | HP | NA | ConQA HP Release
3 | Preliminaries-Documents
3.1 | Check for correct documentation | Drawings and drawing registers | Ensure that all employees and subcontractors are: - Using the correct and complete set of IFC drawings - All drawings are the latest revision | Document Review | Prior to Commencement of works | IP | SE/PE | ITP Signed Off
3.2 | Subcontractor ITP | Subcontractor ITP | Subcontractor ITP to be reviewed and approved by MRPA. | Document Review | Each Lot | WP | SE/PE | ITP Signed Off
4 | Ground Preparation
4.1 | Soil Additives | VicRoads Spec: -Cl. 720.07 (a) -AS 4419 | Refer to Subcontractor ITP | Document Review | Each Lot | IP | SE/PE | Sign ITP Attach Test Report Attached Delivery Docket (if applicable)
4.2 | Ripping of subsoil | VicRoads Spec: -Cl. 720.07 -Table 720.071 | Rip Subsoil to min 250mm at 500mm spacing Do not proceed until the NA inspects and acknowledges requirements for ripping have been met. | Verify | Each Applicable Lot | HP | SE/NA | Sign ITP Attach Lot Map/Marked Up Area Inspected
4.3 | Topsoil application | VicRoads Spec: -Cl. 720.07 | Topsoil to be installed at 150mm depth with no air pockets, weeds, rocks, and other debris. Finish surface should be smooth and uniform | Verify | Each Applicable Lot | IP | SE/Site Supervisor | Subcontractor ITP
4.4 | Mulching | IFC Drawings VicRoads Spec: -Cl. 720.08(a) | Mulch to be installed at 100mm and to finish 50mm below pavement. | Verify | Each Applicable Lot | IP | SE/Site Supervisor | Subcontractor ITP Attach Delivery Dockets
4.5 | Weed and Erosion Control Mat | IFC Drawings VicRoads Spec: -Cl. 720.04(i) | Refer to Subcontractor ITP | Verify | Each Applicable Lot | IP | SE/Site Supervisor | Subcontractor ITP Attach Delivery Dockets
4.6 | Jute Matting Installation | IFC Drawings VicRoads Spec: -Table 720.071 | Pre-slit Jute Matt installed as per specification Lay Matting into a trench of min 150mm wide and depth, pin and backfill | Verify | Each Applicable Lot | IP | SE/Site Supervisor | Subcontractor ITP Attach Delivery Dockets
5 | Planting
5.1 | Plant Installation | IFC Drawings VicRoads Spec: -Table 720.041 | Plants to be removed from Pot and Roots Tickled Ensure Mulch does not overly cover stem of plant Ensure plants to be watered within the same day | Verify | Each Applicable Lot | IP | SE, Site Supervisor | Subcontractor ITP Attach Delivery Dockets
5.2 | Fertiliser Application | IFC Drawings VicRoads Spec: -Table 720.041 | Tubestock: 10gms (approx. 1 teaspoon) of fertiliser been added to base of plant 15-30cm Pots: 40gms (approx. 4 teaspoons) of fertiliser been added to base of plant 45L Trees: 80gms (approx. 8 teaspoons) of fertiliser been added to top of root ball | Verify | Each Applicable Lot | IP | SE, Site Supervisor | Subcontractor ITP Attach Delivery Dockets
5.3 | Tree Installation | IFC Drawings VicRoads Spec: -Table 720.041 | Installation on Grade: - Hole to be 100mm deeper and 600mm wider than pot size - Three 50mm x 50mm x 2400mm Hardwood Stakes driven min 600mm into ground outside rootball Installation on Garden Beds/Turf: - Tree Pit Inspected and Minimum 3 times the root ball width - Three 50mm x 50mm x 2400mm Hardwood Stakes driven min 600mm into ground outside rootball | Verify | Each Applicable Lot | IP | SE, Site Supervisor | Subcontractor ITP Attach Delivery Dockets
5.4 | Soil Installation | IFC Drawings | 75mm depth topsoil & 100mm min in swales consolidated as approved | Verify | Each Applicable Lot | IP | SE, Site Supervisor | Subcontractor ITP Attach Delivery Dockets
6 | Post Construction
6.1 | NCR Closeout | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot/element/Work Area that this ITP covers, have been closed | Document Review | Once, prior to closure of this lot/element/work area | HP* | SE/PE/SPE | ITP Signed Off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /