## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-293-CIV-SSB-Landscaping-Ground Preparation and Planting | itp |  |  |  |  | ITP-293-CIV-SSB-Landscaping-Ground Preparation and Planting Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-293-CIV-SSB-Landscaping-Ground Preparation & Planting
label | ITP Description: Landscaping-Ground Preparation & Planting
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 18/07/2025
label | ITP created by: Ali Rajad
label | ITP approved for use by: Sandy Escalona
label | 1.1 Non Dependent
label | Reference: VicRoads 720
label | 1.2 Non Dependent
label | Reference: AS 4454
label | 1.3 Non Dependent
label | Reference: AS 4419
label | 1.4 Non Dependent
label | Reference: IFC Drawings
section | Preliminaries-Materials
checkpoint | 2.1 Submission and records
label | REFERENCE: VicRoads Spec:
label | — Cl. 720.03
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Samples, records and certificates shall be provided to the Nominated Authority (NA) at least 10 working days prior to bulk delivery.
label | Following information shall be provided to the NA:
label | Samples
label | — Mulch
label | — Imported topsoil
label | Records
label | — Details of suppliers
label | — Soil tests on imported topsoil
label | — Copies/Photos of fertiliser labels
label | ○ Attach: Records and Certs into Hold Point inTeamBinder and write the Reference No.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to Commencement of works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: NA
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Supply of topsoil
label | REFERENCE: VicRoads Spec:
label | — Cl.720.04
label | — Table 720.042
label | ○ IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Site won topsoil to be tested to establish what soil amendments and macro and micro nutreints are required to be added to the top soil if required by planting subcontractor.
label | ○ Where imported topsoil is used, the topsoil must conform to the properties specified in Table 720.042 and align with IFC Drawings.
label | ○ Attach: Material Conformance Docs / Test Reports as Material Approval onto TeamBinder and write the Reference No.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify, Doc. Review if applicable
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to Commencement of works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: NA
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Supply of Mulch
label | REFERENCE: VicRoads Spec:
label | — Cl.720.04
label | — Table 720.044
label | ○ AS4454
label | ○ IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Site mulch available from the chipping of on-site indigenous or non-weed vegetation shall be used where possible, otherwise approved mulch stated on IFC drawings.
label | ○ All wood mulch to be spread in accordance to AS 4454 and conform to required depth stated in IFC drawings .
label | ○ Imported Wood Mulch shall comply with Table 720.044.
label | ○ Attach: Material Conformance Docs / Test Reports as Material Approvasl onto TeamBinder and write the Reference No.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify, Doc. Review if applicable
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to Commencement of works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: NA
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 Supply of Plant
label | REFERENCE: VicRoads Spec:
label | — Cl.720.04
label | — Table 720.041
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All Plants have been inspected and comply with Sec 720.041
label | ○ Attach: Landscape Architect Approval
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: NA
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 Supply of grass seed
label | REFERENCE: VicRoads Spec.
label | — Cl.720.04
label | — Table 720.045
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Grass seed shall comply with Table 720.045
label | ○ Attach: Material Conformance Docs / Test Reports as Material Approvasl onto TeamBinder and write the Reference No.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to Commencing works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: NA
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Preliminaries-Documents
checkpoint | 3.1 Check for correct documentation
label | REFERENCE: Drawings and drawing registers
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — Using the correct and complete set of IFC drawings
label | — All drawings are the latest revision
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to Commencement of works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ITP Signed Off
date | Date Completed:
checkpoint | 3.2 Subcontractor ITP
label | REFERENCE: Subcontractor ITP
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Subcontractor ITP to be reviewed and approved by MRPA.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: WP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ITP Signed Off
date | Date Completed:
section | Ground Preparation
checkpoint | 4.1 Soil Additives
label | REFERENCE: VicRoads Spec:
label | — Cl. 720.07 (a)
label | — AS 4419
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Refer to Subcontractor ITP
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
label | ○ Attach Test Report
label | ○ Attached Delivery Docket (if applicable)
date | Date Completed:
checkpoint | 4.2 Ripping of subsoil
label | REFERENCE: VicRoads Spec:
label | — Cl. 720.07
label | — Table 720.071
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Rip Subsoil to min 250mm at 500mm spacing
label | ○ Do not proceed until the NA inspects and acknowledges requirements for ripping have been met.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Applicable Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/NA
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
label | ○ Attach Lot Map/Marked Up Area Inspected
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 Topsoil application
label | REFERENCE: VicRoads Spec:
label | — Cl. 720.07
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Topsoil to be installed at 150mm depth with no air pockets, weeds, rocks, and other debris. Finish surface should be smooth and uniform
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Applicable Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Subcontractor ITP
date | Date Completed:
checkpoint | 4.4 Mulching
label | REFERENCE: IFC Drawings
label | VicRoads Spec:
label | — Cl. 720.08(a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Mulch to be installed at 100mm and to finish 50mm below pavement.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Applicable Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Subcontractor ITP
label | ○ Attach Delivery Dockets
date | Date Completed:
checkpoint | 4.5 Weed and Erosion Control Mat
label | REFERENCE: IFC Drawings
label | VicRoads Spec:
label | — Cl. 720.04(i)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Refer to Subcontractor ITP
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Applicable Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Subcontractor ITP
label | ○ Attach Delivery Dockets
date | Date Completed:
checkpoint | 4.6 Jute Matting Installation
label | REFERENCE: IFC Drawings
label | VicRoads Spec:
label | — Table 720.071
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Pre-slit Jute Matt installed as per specification
label | ○ Lay Matting into a trench of min 150mm wide and depth, pin and backfill
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Applicable Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Subcontractor ITP
label | ○ Attach Delivery Dockets
date | Date Completed:
section | Planting
checkpoint | 5.1 Plant Installation
label | REFERENCE: IFC Drawings
label | VicRoads Spec:
label | — Table 720.041
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Plants to be removed from Pot and Roots Tickled
label | ○ Ensure Mulch does not overly cover stem of plant
label | ○ Ensure plants to be watered within the same day
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Applicable Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE, Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Subcontractor ITP
label | ○ Attach Delivery Dockets
date | Date Completed:
checkpoint | 5.2 Fertiliser Application
label | REFERENCE: IFC Drawings
label | VicRoads Spec:
label | — Table 720.041
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Tubestock: 10gms (approx. 1 teaspoon) of fertiliser been added to base of plant
label | ○ 15-30cm Pots: 40gms (approx. 4 teaspoons) of fertiliser been added to base of plant
label | ○ 45L Trees: 80gms (approx. 8 teaspoons) of fertiliser been added to top of root ball
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Applicable Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE, Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Subcontractor ITP
label | ○ Attach Delivery Dockets
date | Date Completed:
checkpoint | 5.3 Tree Installation
label | REFERENCE: IFC Drawings
label | VicRoads Spec:
label | — Table 720.041
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Installation on Grade:
label | — Hole to be 100mm deeper and 600mm wider than pot size
label | — Three 50mm x 50mm x 2400mm Hardwood Stakes driven min 600mm into ground outside rootball
label | Installation on Garden Beds/Turf:
label | — Tree Pit Inspected and Minimum 3 times the root ball width
label | — Three 50mm x 50mm x 2400mm Hardwood Stakes driven min 600mm into ground outside rootball
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Applicable Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE, Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Subcontractor ITP
label | ○ Attach Delivery Dockets
date | Date Completed:
checkpoint | 5.4 Soil Installation
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: 75mm depth topsoil & 100mm min in swales consolidated as approved
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Applicable Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE, Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Subcontractor ITP
label | ○ Attach Delivery Dockets
date | Date Completed:
section | Post Construction
checkpoint | 6.1 NCR Closeout
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot/element/Work Area that this ITP covers, have been closed
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to closure of this lot/element/work area
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ITP Signed Off
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP