## Master List Templates
Id | Type | Name | Values | Prompting Name
8c253716-b068-4463-864a-a3ae084d0e6b | checklist | Add Site Visit Checklist |  | Site Visit Date:
4729aca8-cc4e-4c3b-9d0d-a415b9052b42 | checkpoint | Details entered
c3a4ba6a-1e39-5d18-880b-bcdc67943f1e | textbox | Site visit performed by
4c7c7e47-fb8f-57a7-b263-468dc7b66dfc | textbox | Site visit completed with / attendees
ab920d2f-11ad-511e-b608-b814391e07d9 | textbox | Description of area
2ebdfd27-7e28-4565-8eee-4f24e4f57fca | checkpoint | Photos taken
83fe08c2-8d6e-434f-bf70-eb85b3f4bb73 | checkpoint | General observations and comments
4394ccfc-826d-4325-b3ea-75b1f92f751f | checklist | Add Variation |  | Variation Details -
5812f9c1-031f-4ef4-8377-40218f3be5b5 | checkpoint | Variation Details Approved
a1dcf207-c630-5a69-87a0-3ffad882385e | textbox | Reference/Drawing/Instruction Number
e72912a4-382e-5a1d-b596-ca10ca275739 | textbox | Variation Area
b09de357-4c7d-5c81-b481-e02733600b27 | textbox | Materials & labour breakdown
42639ab8-ba44-4321-b193-ffa3b389b783 | signoff | Request Variation Acknowledgement
5720f4c5-8810-49b3-8227-164f7f441f37 | checkpoint | Variation Completed
743190f8-163d-40f9-995b-87adf468e9f5 | signoff | Request Variation Signoff
2aa2a7ed-2364-4deb-ba20-22d94b115844 | checklist | Document Attach |  | Document:
12c8ad85-0133-4af1-948a-ad327307b0f9 | checkpoint | Document Attached

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
e33f3829-a897-4c86-8289-fbe864aa34dd | checklist | Bituthene 3000 Checklist |  | Bituthene 3000
3ea99a68-0395-4dac-b825-e71070128d3e | section | Details
dd9301d5-471e-4fb8-8939-2647411ff061 | checkpoint | Surfaces are structurally sound and free of voids, spalled areas, loose aggregate and sharp protrusions. Pass/Fail/NA – Photo
0db80df8-9b18-487e-8c14-16fba4405240 | checkpoint | Apply Bituthene Adhesive Primer B2. Pass/Fail/NA – Photo
13278d41-d415-41d9-821c-37a840cb45b0 | checkpoint | Install Bituthene 3000 membrane as per manufacturer’s requirements. Pass/Fail/NA – Photo
b580267d-5403-4b96-8181-d4a6f874ed97 | checkpoint | Penetration Detail. Pass/Fail/NA – Photo
ad05ac26-6b3b-4794-b789-60a7eee7d8f6 | checkpoint | Termination Detail. Pass/Fail/NA – Photo
83f9d4e0-ec14-4fc2-a80e-776d73ce04d0 | checkpoint | Patch tears and adequate lapped seams. Pass/Fail/NA – Photo
a5dde8b4-ef7d-4d5a-9564-8561947e3aa6 | checkpoint | Install Membrane Protection. Pass/Fail/NA – Photo
ebecd5eb-6426-4987-85f3-a2fe3846387e | section | Sign off
1c293841-bc4d-4453-aeb1-cd11dea34622 | checkpoint | Main Contractor Representative
6bf56ab4-8b81-42d8-8951-ce7f1388f921 | signoff | Sign off
4257fe2c-7e29-4b9b-9e18-841f68188a0b | checkpoint | Sansom Representative
f6df5799-5aa7-4b90-8e2f-3edf283de907 | signoff | Sign off
6c110f08-f9ff-47c4-80af-99e653b4d293 | checklist | Preprufe 300R Checklist |  | Preprufe 300R Checklist
d4514aa6-4e4a-42f1-a608-7d1ca1959531 | section | Details
6ae18deb-6163-4d0f-a7bd-27dcd88b3295 | checkpoint | 1) Substrate Inspection completed.
d08a7573-63ff-5b74-bdb8-19f1c024158a | note | Upload document
38d44a4e-71c5-4f58-b9f5-a687c1feed31 | checkpoint | 2. Lot numbers of all materials used
2cf0b368-51d3-4a5d-b147-bf94bd313266 | checkpoint | 3) Prepfufe 300R Installed and lapped as per manufacturers specification.
4320be24-8d00-5a7f-a767-65793679271b | tickbox | Release Film
38b2c120-d35b-5866-bad7-81efd5a64902 | tickbox | Selvedge Edge
d3b16476-d62b-54e0-bad3-4df169432f4e | tickbox | End Laps
d76e3d04-0e32-54ab-bf9a-7da46d3c01db | tickbox | Cut Edges
cb01ed7d-e996-53da-871a-9b0ac02bfd93 | tickbox | Corners
d1595c00-0c28-4901-874f-c73bf1af019f | checkpoint | 4) All fastener penetrations have been patched using 100mm x 100mm patches of Preprufe® Tape
1a37425d-8a59-4e5b-a100-111241a59d2a | checkpoint | 5) All penetrations are detailed and sealed using Preprufe® Tape and Bituthene® LM.
4298f86d-f3e7-48f3-90d0-7af8e87eb6bd | checkpoint | 6) Expansion joint waterstops are located as per specification requirements, undamaged, firmly bonded to the Preprufe® membrane
1906e8c8-9142-4622-aa3a-31f8c44495d2 | checkpoint | 7) Construction joint waterstops are located as per specification requirements, undamaged and firmly fixed to substrate.
1042ae7b-dfac-4c8c-b3a8-8424d997308e | checkpoint | 8) Any membrane damage sustained has been repaired using Preprufe® 300R and Preprufe® Tape.
3e3eeea6-20b4-4a67-83d2-f4d662d1bc01 | checkpoint | Sansom Representative
3abd9ee0-9e02-4876-9182-8ee4fb2aa352 | signoff | Sign off
a512b564-d639-4ed3-b741-3900c9b19776 | checkpoint | Main Contractor Representative
11552e29-4b2f-4cf1-9a27-4aad3cb498a4 | signoff | Sign off
84fad1f4-5ed0-4985-a97f-ed32f9580efd | checklist | Substrate Inspection for Preprufe/Bituthene Checklist |  | Substrate Inspection for Preprufe/Bituthene Checklist
7c5220c4-fcea-4a20-beca-0168c27bcbe5 | section | Details
50335f40-157c-4b3a-add3-07d7265cde35 | checkpoint | 1. Application Area
f6ea16e0-458e-5f9f-b1ea-58963cbf1396 | textbox
f61cc749-f872-4c34-ae66-033a0441aa0d | checkpoint | 2. Horizontal Blinding completed
68a9bf37-a2dc-4bf6-8d2b-d3be2eeeec74 | checkpoint | 3. Vectical Formwork completed
aea176bc-3c3e-42b2-91bb-e958b2ab4201 | checkpoint | 4. Substrate is regular, smooth, and stable
b3385cf2-28d6-42ba-adef-1f46c2e1d377 | checkpoint | 5. Substrates have no gaps, voids, or irregularities > 12mm wide or 12mm deep
69995179-35bd-4846-a328-729a128b6bdc | checkpoint | 6. Substrate is free of loose aggregate and sharp protrusions
6b8f5e24-592b-485b-bdbc-597d71db62cd | checkpoint | 7. No Standing water
6626bb50-2d67-427c-8fd3-69031e4c5a7f | checkpoint | 8. Substrate Penetration grouted
9fc512c2-cc17-46a0-a9fc-c65a8d47e646 | checkpoint | 9. Piles extended min. 150 mm above substrate and profiled to suit substrate requirements
d21936b3-692f-409c-8b03-0e72b06d30d5 | section | Sign off
c58f2873-b972-4c71-a4e9-5758c7ca576d | checkpoint | Sansom Representative
9009e192-100d-436e-ac60-cd2906085ec6 | signoff | Sign off
80bec970-1c98-45b7-adbf-9f1063a4b832 | checkpoint | Main Contractor Representative
69508efb-fbaf-4aa1-ad61-ebdfd74cc49e | signoff | Sign off