## Sheet1
1 | Lot Boundries | MRTS 04 Cl 5.6 | Check and Verify | 1 - Lot Boundries | Acceptance Criteria - Lot Number established with the Lot boundaries of the works clearly defined for traceability within the works | Reference - MRTS 04 Cl 5.6 | Item Check - Check and Verify | 1 - Lot Boundries
| Lot Number established with the Lot boundaries of the works clearly defined for traceability within the works | [6 empty] | Acceptance Criteria - Lot Number established with the Lot boundaries of the works clearly defined for traceability within the works
2 | Subgrade Level | MRTS 04 Cl 13.3.2.1 | HOLD POINT | 2 - Subgrade Level | Acceptance Criteria - When the level of excavation has reached Subgrade Level plus a nominal allowance determined by the Contractor, the Contractor shall carry out the requirements of the relevant provisions of Clause 18.3.3 and cease excavation until the Subgrade treatment type has been determined in accordance with Clause 18.3.3. | Reference - MRTS 04 Cl 13.3.2.1 | Item Check - HOLD POINT | Reference - MRTS 04 Cl 5.6
| When the level of excavation has reached Subgrade Level plus a nominal allowance determined by the Contractor, the Contractor shall carry out the requirements of the relevant provisions of Clause 18.3.3 and cease excavation until the Subgrade treatment type has been determined in accordance with Clause 18.3.3. | [6 empty] | Item Check - Check and Verify
3 | Proof Roll | MRTS 04 Cl 18.3.2 | Witness Point | 3 - Proof Roll | Acceptance Criteria - At the completion of earthworks to Subgrade Level, the Contractor shall test for perceptible surface deformation by undertaking proof rolling. Witness Point 8 | Reference - MRTS 04 Cl 18.3.2 | Item Check - Witness Point | 2 - Subgrade Level
| At the completion of earthworks to Subgrade Level, the Contractor shall test for perceptible surface deformation by undertaking proof rolling. Witness Point 8 | [6 empty] | Acceptance Criteria - When the level of excavation has reached Subgrade Level plus a nominal allowance determined by the Contractor, the Contractor shall carry out the requirements of the relevant provisions of Clause 18.3.3 and cease excavation until the Subgrade treatment type has been determined in accordance with Clause 18.3.3.
5 | Subgrade Treament | MRTS 04 Cl 18.3.3 | HOLD POINT | 5 - Subgrade Treament | Acceptance Criteria - Subgrade Treatment Ordered: ____________________ | Reference - MRTS 04 Cl 18.3.3 | Item Check - HOLD POINT | Reference - MRTS 04 Cl 13.3.2.1
| Subgrade Treatment Ordered: ____________________ | [6 empty] | Item Check - HOLD POINT
6 | Subgrade Treament Type A | MRTS 04 Cl 18.3.3 | Check and Verify | 6 - Subgrade Treament Type A | Acceptance Criteria - For Subgrade treatment Type A, excavation shall be completed to Subgrade Level in accordance with Clause 13.3.1. The material below Subgrade Level shall be compacted as specified in Clause 15.3 to a characteristic value of compaction as specified in Table 15.3(b). The depth of compaction shall be as specified in Clause 12.3 of Annexure MRTS04.1 to this Technical Specification or, where no such depth is specified, to a depth of 150 mm. | Reference - MRTS 04 Cl 18.3.3 | Item Check - Check and Verify | 3 - Proof Roll
| For Subgrade treatment Type A, excavation shall be completed to Subgrade Level in accordance with Clause 13.3.1. The material below Subgrade Level shall be compacted as specified in Clause 15.3 to a characteristic value of compaction as specified in Table 15.3(b). The depth of compaction shall be as specified in Clause 12.3 of Annexure MRTS04.1 to this Technical Specification or, where no such depth is specified, to a depth of 150 mm. | [6 empty] | Acceptance Criteria - At the completion of earthworks to Subgrade Level, the Contractor shall test for perceptible surface deformation by undertaking proof rolling. Witness Point 8
7 | Subgrade Treatment Type C | MRTS 04 Cl 18.3.3 | Check and Verify | 7 - Subgrade Treatment Type C | Acceptance Criteria - For Subgrade treatment Type C, excavation shall be continued to a depth below Subgrade Level as specified in Clause 12.3 of Annexure MRTS04.1 to this Technical Specification or, where no such depth is specified, to a depth of 150 mm. Excavation shall comply with the requirements of Clause 13.3.1. The excavation shall be backfilled to Subgrade Level with unbound granular material, in accordance with Clause 18.2.2, and shall be constructed as specified in MRTS05 Unbound Pavements to a characteristic value of compaction of not less than that specified in Table 15.3(b). | Reference - MRTS 04 Cl 18.3.3 | Item Check - Check and Verify | Reference - MRTS 04 Cl 18.3.2
| For Subgrade treatment Type C, excavation shall be continued to a depth below Subgrade Level as specified in Clause 12.3 of Annexure MRTS04.1 to this Technical Specification or, where no such depth is specified, to a depth of 150 mm. Excavation shall comply with the requirements of Clause 13.3.1. The excavation shall be backfilled to Subgrade Level with unbound granular material, in accordance with Clause 18.2.2, and shall be constructed as specified in MRTS05 Unbound Pavements to a characteristic value of compaction of not less than that specified in Table 15.3(b). | [6 empty] | Item Check - Witness Point
8 | Testing - Compaction | MRTS 04 Table A.2 - 2.1 | Test Reports 1 per 500m2 4 per Lot | 8 - Testing - Compaction | Acceptance Criteria - Compaction - depth as per Clause 13.5 of Annexure MRTS04.1 | Reference - MRTS 04 Table A.2 - 2.1 | Item Check - Test Reports 1 per 500m2 4 per Lot | 5 - Subgrade Treament
| Compaction - depth as per Clause 13.5 of Annexure MRTS04.1 | [6 empty] | Acceptance Criteria - Subgrade Treatment Ordered: ____________________
8 | Geometrics - Straight Edge | MRTS 04 Table A.2 - 2.1 | Test Reports 1 Per 20m | 8 - Geometrics - Straight Edge | Acceptance Criteria - The gap beneath a three metre-long straight-edge placed anywhere on the surface at Subgrade Level shall not exceed 25 mm, due allowance being made for design shape where relevant. | Reference - MRTS 04 Table A.2 - 2.1 | Item Check - Test Reports 1 Per 20m | Reference - MRTS 04 Cl 18.3.3
| The gap beneath a three metre-long straight-edge placed anywhere on the surface at Subgrade Level shall not exceed 25 mm, due allowance being made for design shape where relevant. | [6 empty] | Item Check - HOLD POINT
8 | Geometrics - Survey | MRTS 04 Table A.2 - 2.1 | Survey 20m Iintervals | 8 - Geometrics - Survey | Acceptance Criteria - The heights of earthworks measured anywhere on a layer surface shall not vary from those shown on the drawings, or calculated in accordance with Clause 6.1, by more than the tolerance stated in Table 6.3.1 unless specified otherwise. Subgrade Level (Individual Results): ± 25mm Subrade Level (Average): ± 10 | Reference - MRTS 04 Table A.2 - 2.1 | Item Check - Survey 20m Iintervals | 6 - Subgrade Treament Type A
| The heights of earthworks measured anywhere on a layer surface shall not vary from those shown on the drawings, or calculated in accordance with Clause 6.1, by more than the tolerance stated in Table 6.3.1 unless specified otherwise. Subgrade Level (Individual Results): ± 25mm Subrade Level (Average): ± 10 | [6 empty] | Acceptance Criteria - For Subgrade treatment Type A, excavation shall be completed to Subgrade Level in accordance with Clause 13.3.1. The material below Subgrade Level shall be compacted as specified in Clause 15.3 to a characteristic value of compaction as specified in Table 15.3(b). The depth of compaction shall be as specified in Clause 12.3 of Annexure MRTS04.1 to this Technical Specification or, where no such depth is specified, to a depth of 150 mm.
Reference - MRTS 04 Cl 18.3.3
Item Check - Check and Verify
7 - Subgrade Treatment Type C
Acceptance Criteria - For Subgrade treatment Type C, excavation shall be continued to a depth below Subgrade Level as specified in Clause 12.3 of Annexure MRTS04.1 to this Technical Specification or, where no such depth is specified, to a depth of 150 mm. Excavation shall comply with the requirements of Clause 13.3.1. The excavation shall be backfilled to Subgrade Level with unbound granular material, in accordance with Clause 18.2.2, and shall be constructed as specified in MRTS05 Unbound Pavements to a characteristic value of compaction of not less than that specified in Table 15.3(b).
Reference - MRTS 04 Cl 18.3.3
Item Check - Check and Verify
8 - Testing - Compaction
Acceptance Criteria - Compaction - depth as per Clause 13.5 of Annexure MRTS04.1
Reference - MRTS 04 Table A.2 - 2.1
Item Check - Test Reports 1 per 500m2 4 per Lot
8 - Geometrics - Straight Edge
Acceptance Criteria - The gap beneath a three metre-long straight-edge placed anywhere on the surface at Subgrade Level shall not exceed 25 mm, due allowance being made for design shape where relevant.
Reference - MRTS 04 Table A.2 - 2.1
Item Check - Test Reports 1 Per 20m
8 - Geometrics - Survey
Acceptance Criteria - The heights of earthworks measured anywhere on a layer surface shall not vary from those shown on the drawings, or calculated in accordance with Clause 6.1, by more than the tolerance stated in Table 6.3.1 unless specified otherwise. Subgrade Level (Individual Results): ± 25mm Subrade Level (Average): ± 10
Reference - MRTS 04 Table A.2 - 2.1
Item Check - Survey 20m Iintervals