## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-042-CIV-Brunt-Subgrade Prep for Embankment Fill
ITP Description: |  | Subgrade Prep for Embankment Fill
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | 2023-06-13
ITP created by: |  | Jason Lee
ITP approved for use by: |  | Jon De Castro
Special Notes to ConQA Team : |  | ITP for Brunt Road Project Only
Inspection & Test Plan - Subgrade Preparation
|  |  | Document No.: | [5 empty] | Revision: | 0
[9 empty] | Date: | 2023-06-13
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 204 (Dec 2015) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VicRoads Section 173 (Oct 2008) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | IFC Drawings | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Non Dependent | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
3 | Preliminaries - Procedures & Documentation
3.1 | Non Dependent | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
4 | Pre-construction Activities
4.1 | Survey Set-Out | IFC Drawings | The Area of Excavation has been set out in accordance with the drawings. Attach: IFC Drawings with lots marked-up (Lot Maps) | Verify | Prior to Commencement of Excavation | IP | PE/SE/Surveyor | This ITP Signed Off
5 | Construction Activities
5.1 | Excavation to Subgrade | Section 204.06 Section 204.07 (b) | In situ material within 400mm of cut floor level to be consistent with IFC Drawings. Assigned CBR not less than Type A material and shall have swell less than 2.5%. If parameters are met, rip and re-compact to a depth of 150mm. If the material have an assigned CBR less than Type A material, it shall be removed to a depth of 400 mm below Cut Floor Level and replaced with conforming Type A Material. Attach: Laboratory Test Results | Verify - Document Review | Each Lot | HP | Nominated Authority | Conqa HP Release
5.2 | Acceptance of Rock Subgrade (where applicable) | Section 204.06 (f) | Material shall be excavated to a depth of not less than 150mm below subgrade level in all areas on which pavement is to be placed and all loose material and soil shall be removed from the rock floor. If any depressions lower than 150mm below subgrade is visible, it shall be cleaned of loose material and backfilled with 20mm Class 3, 3% Cement Treated Crushed Rock and compacted. A regulating Layer of Class 4, 20mm Crushed Rock shall then be placed above the rock to subgrade level in lieu of specified capping or selected material, in layers not exceeding thickness of 150mm. Attach: Delivery Dockets for verifications. | Site Inspection/ Document Review | Prior Construction of the regulating layer | HP | Nominated Authority | Conqa HP Release
5.3 | Groundwater (where applicable) | Section 204.06 (h) | Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater. Attach: TeamBinder Approval Reference No. | Visual Inspection | Each Lot | HP | Nominated Authority | Conqa HP Release
5.4 | Geotech Inspection | IFC Drawings | Excavation is required until natural clay is exposed wiIh a minimum shear strength of 75 kPa, to be inspected by CMW prior to fill placement. | Visual Inspection | Each lot | IP | SE/PE/SPE | This ITP Signed Off
5.5 | Proof Roll | Section 173 | Each Layer shall be proof rolled with a superintendent present. Compliance with the proof rolling requirements shall be when an area withstands proof rolling without visible deformation or springing. The plant for use in proof roll to comply with the following requirements: (i) Static smooth steel wheeled rollers shall have a mass of not less than 12 tonnes and a load intensity under either the front or rear wheels of not less than 6 tonnes per metre width of wheel. (ii) Pneumatic tyred plant shall have a mass of not less than 20 tonne and shall have a ground contact pressure under either the front or rear wheels of not less than 450 kPa per tyre. The area over which this ground contact pressure shall be applied shall not be less than 0.035 m2 per tyre. | Visual Inspection Test Roll as per 173.03 | Each Lot/Layer | HP | Nominated Authority | Conqa HP Release
5.6 | Compaction & Moisture Content Testing | Table 204.131 Table 204.142 | Compaction Requirement to be Scale B: Characteristic Density Ratio 98%. (6 tests per lot) Once three consecutive lots of like material have achieved the requirements in the first test, minimum testing frequency can be seek with the Superintendent agreement. Minimum Testing Frequency: Every second lot Lot size Type A Material - the lesser of one day's production or 5000sqm Attach: Compaction & Moisture Content Test Results | Review Document | Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work | IP | SE/PE/SPE | This ITP Signed Off
5.7 | Post Compaction Material Property Testing - Type A Replacement Fill (where applicable) | Table 204.131 IFC Drawings | Material Properties: CBR ≥ 8% and Swell ≤ 1.5% (Applicable for Type A Replacement Material) Max Permeability = 5E-9 m/s Grading: 75.0mm 100% 4.75mm 40-80% 0.075mm 10-40% Max. PI x%Passing 0.425mm = 1000 , PI = 6-25 Scale B: 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability. Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed. Attach: Post Compaction Material Property Test Results | Review Document | Each Lot/Reduced Testing Frequency Refer to Section 204 | IP | SE/PE/SPE | This ITP Signed Off
5.8 | Post Compaction Material Property Testing - Natural Ground (where applicable) | IFC Drawing Table 204.141 | Material Properties (Not Applicable for Scale C): CBR ≥ 2% (Applicable for Natural Ground) Max Permeability = N/A Scale B: 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability. Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed. Attach: Post Compaction Material Property Test Results | Review Document | Each Lot | IP | SE/PE/SPE | Sign ITP Attach Material Property Test Report
6 | Post-construction Activities
6.1 | Survey Conformance | Table 204.031 | Level tolerances (Scale B): Range Mean = +5, -25mm Max Standard Deviation = 15 mm 40 measurements per lot Attach: Survey Conformance Report | Review Document | Top of Type A | IP | SE/PE/ Surveyor | This ITP Signed Off
6.2 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP Signed Off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /