## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-042-CIV-Brunt-Subgrade Prep for Embankment Fill | itp |  |  |  | Yes | ITP-042-CIV-Brunt-Subgrade Prep for Embankment Fill
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-042-CIV-Brunt-Subgrade Prep for Embankment Fill
label | ITP Description: Subgrade Prep for Embankment Fill
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 13/06/2023
label | ITP created by: Jason Lee
label | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Non Dependent
label | Reference - VicRoads Section 204 (Dec 2015)
checkpoint | 1.2 - Non Dependent
label | Reference - VicRoads Section 173 (Oct 2008)
checkpoint | 1.3 - Non Dependent
label | Reference - IFC Drawings
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Non Dependent
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Non Dependent
section | 4. Pre-construction Activities
checkpoint | 4.1 - Survey Set-Out
note | Reference - IFC Drawings
note | Acceptance Criteria - The Area of Excavation has been set out in accordance with the drawings.
note | • Attach: IFC Drawings with lots marked-up (Lot Maps)
note | Method - Verify
note | Frequency - Prior to Commencement of Excavation
note | Category - IP
note | Responsible person - PE/SE/Surveyor
note | Verifying Documents - This ITP Signed Off
section | 5. Construction Activities
checkpoint | 5.1 - Excavation to Subgrade
note | Reference - Section 204.06, Section 204.07 (b)
note | Acceptance Criteria - In situ material within 400mm of cut floor level to be consistent with IFC Drawings. Assigned CBR not less than Type A material and shall have swell less than 2.5%. If parameters are met, rip and re-compact to a depth of 150mm.
note | • If the material have an assigned CBR less than Type A material, it shall be removed to a depth of 400 mm below Cut Floor Level and replaced with conforming Type A Material.
note | • Attach: Laboratory Test Results
note | Method - Verify - Document Review
note | Frequency - Each Lot
note | Category - HP
note | Responsible person - Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Acceptance of Rock Subgrade (where applicable)
note | Reference - Section 204.06 (f)
note | Acceptance Criteria - Material shall be excavated to a depth of not less than 150mm below subgrade level in all areas on which pavement is to be placed and all loose material and soil shall be removed from the rock floor.
note | • If any depressions lower than 150mm below subgrade is visible, it shall be cleaned of loose material and backfilled with 20mm Class 3, 3% Cement Treated Crushed Rock and compacted.
note | • A regulating Layer of Class 4, 20mm Crushed Rock shall then be placed above the rock to subgrade level in lieu of specified capping or selected material, in layers not exceeding thickness of 150mm.
note | • Attach: Delivery Dockets for verifications.
note | Method - Site Inspection/Document Review
note | Frequency - Prior Construction of the regulating layer
note | Category - HP
note | Responsible person - Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Groundwater (where applicable)
note | Reference - Section 204.06 (h)
note | Acceptance Criteria - Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review.
note | • The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
note | • Attach: TeamBinder Approval Reference No.
note | Method - Visual Inspection
note | Frequency - Each Lot
note | Category - HP
note | Responsible person - Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 - Geotech Inspection
note | Reference - IFC Drawings
note | Acceptance Criteria - Excavation is required until natural clay is exposed wiIh a minimum shear strength of 75 kPa, to be inspected by CMW prior to fill placement.
note | Method - Visual Inspection
note | Frequency - Each lot
note | Category - IP
note | Responsible person - SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.5 - Proof Roll
note | Reference - Section 173
note | Acceptance Criteria - Each Layer shall be proof rolled with a superintendent present. Compliance with the proof rolling requirements shall be when an area withstands proof rolling without visible deformation or springing.
note | • The plant for use in proof roll to comply with the following requirements:
note | (i) Static smooth steel wheeled rollers shall have a mass of not less than 12 tonnes and a load intensity under either the front or rear wheels of not less than 6 tonnes per metre width of wheel.
note | (ii) Pneumatic tyred plant shall have a mass of not less than 20 tonne and shall have a ground contact pressure under either the front or rear wheels of not less than 450 kPa per tyre. The area over which this ground contact pressure shall be applied shall not be less than 0.035 m2 per tyre.
note | Method - Visual Inspection, Test Roll as per 173.03
note | Frequency - Each Lot/Layer
note | Category - HP
note | Responsible person - Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.6 - Compaction & Moisture Content Testing
note | Reference - Table 204.131, Table 204.142
note | Acceptance Criteria - Compaction Requirement to be Scale B: Characteristic Density Ratio 98%. (6 tests per lot)
note | Once three consecutive lots of like material have achieved the requirements in the first test, minimum testing frequency can be seek with the Superintendent agreement.
note | • Minimum Testing Frequency: Every second lot
note | ○ Lot size
note | • Type A Material - the lesser of one day's production or 5000sqm
note | • Attach: Compaction & Moisture Content Test Results
note | Method - Review Document
note | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
note | Category - IP
note | Responsible person - SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.7 - Post Compaction Material Property Testing - Type A Replacement Fill (where applicable)
note | Reference - Table 204.131 IFC Drawings
note | Acceptance Criteria - Material Properties:
note | • CBR ≥ 8% and Swell ≤ 1.5% (Applicable for Type A Replacement Material)
note | • Max Permeability = 5E-9 m/s
note | ○ Grading:
note | • 75.0mm 100%
note | • 4.75mm 40-80%
note | • 0.075mm 10-40%
note | • Max. PI x%Passing 0.425mm = 1000 , PI = 6-25
note | ○ Scale B:
note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
note | • Attach: Post Compaction Material Property Test Results
note | Method - Review Document
note | Frequency - Each Lot/Reduced Testing Frequency Refer to Section 204
note | Category - IP
note | Responsible person - SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.8 - Post Compaction Material Property Testing - Natural Ground (where applicable)
note | Reference - IFC Drawing Table 204.141
note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
note | • CBR ≥ 2% (Applicable for Natural Ground)
note | • Max Permeability = N/A
note | ○ Scale B:
note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
note | • Attach: Post Compaction Material Property Test Results
note | Method - Review Document
note | Frequency - Each Lot
note | Category - IP
note | Responsible person - SE/PE/SPE
note | Verifying Documents - Sign ITP, Attach Material Property Test Report
section | 6. Post-construction Activities
checkpoint | 6.1 - Survey Conformance
note | Reference - Table 204.031
note | Acceptance Criteria - Level tolerances (Scale B):
note | • Range Mean = +5, -25mm
note | • Max Standard Deviation = 15 mm
note | • 40 measurements per lot
note | • Attach: Survey Conformance Report
note | Method - Review Document
note | Frequency - Top of Type A
note | Category - IP
note | Responsible person - SE/PE/Surveyor
note | Verifying Documents - This ITP Signed Off
checkpoint | 6.1 - Non-conformance Report (NCR) Closure
note | Reference - MRPA Quality Management Plan
note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
note | Method - Document Review
note | Frequency - Once, prior to closure of this lot / element / Work area
note | Category - HP*
note | Responsible person - SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP