## PAVEMENT RENEWALS – Unbound Gra
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH87 Heeney Creek Rehabilitation (SH87 Heeny Creek RS82/RP3550 - RP3790) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
PAVEMENT RENEWALS – Unbound Granular |  |  | NZTA F/2, NZTA M/3, NZS 4407:1991 Solid Density Test 3.7,TNZ B/2: 2005, NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005, NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005, NZS 4402: 1986 MDD and W/C Test 4.1.3 TNZ B/2: 2005, TNZ M/4:2006, TNZ C/20: 2003, NZTA T15 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER/KELSO | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Preliminary and General | [11 empty] | W & I | Supplier
1.1 | Construction Program Completion |  | Project Manager | Best Practice Contract Specific MMP | Before work Commence | Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date. | YES | W | R | H
1.2 | Approved RQP |  | NZTA Maintenance Contact Manager | Contract Specification | Before work Commence | Principal Acceptance according to guidelines in appendix 6.3 | YES | H | R | H
1.3 | Traffic Management/TMP |  | Project Manager | CoPTTM | Before Traffic Management Setup | TMP checked and approved Plans approved Current EED (if applicable) | YES | H | R | H
1.4 | Notification of intention to start work |  | Project Manager | Notification | Before work commences | Letter drop to local residents. Where required and defined by SWAMP, VMS, social media/media advertising | YES | H | R | H
2 | Setout/Site Preparation
2.1 | Setout/Survey |  | Project Manager | Best Practice | Per installation | Survey Records | YES | W | R | H
2.2 | Permit to dig/Authority to Work/close approach permits |  | Construction Foreman | Downer Permit to work or Equvilent | Before work commences | Organisational approval | YES | H | R | H
2.3 | Cultural/Heritage Risk Assessment |  | Project Manager | WK Cultural & Heritage Risk Model | Before work commences | Local kiwi has been notified of intent to start work | YES | H | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 18/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH87 Heeney Creek Rehabilitation (SH87 Heeny Creek RS82/RP3550 - RP3790) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
PAVEMENT RENEWALS – Unbound Granular |  |  | NZTA F/2, NZTA M/3, NZS 4407:1991 Solid Density Test 3.7,TNZ B/2: 2005, NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005, NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005, NZS 4402: 1986 MDD and W/C Test 4.1.3 TNZ B/2: 2005, TNZ M/4:2006, TNZ C/20: 2003, NZTA T15 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER/KELSO | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | SUB-CON | OTHER |  | W(5%) | Sub Supervisor
2.4 | Archaeological Risk |  | Project Manager | WK Cultural & Heritage Risk Model | Before work commences | Toolbox meeting held covering accidental discovery protocol | YES | H | R | H |  |  | W & I | Supplier
2.5 | Traffic Management Setup |  | Construction Foreman/STMS | Traffic Management Plan | Before work commences each day | Traffic management complies with TMP | YES | H | R | H
2.6 | Machine Control Survey Control |  | Construction Foreman | On Site/Measurement | Before using machine control | Verification of survey control points and setup | YES | H | R | H
2.7 | Machine Control Accuracy Verification |  | Construction Foreman | On Site/Measurement | Before using machine control | Verification of survey control points and setup | YES | H | R | H
2.8 | Prepare String Sheet (Digital) |  | Project Manager | On Site/Measurement | Before using machine control | Digital design set-out data is consistent with on site marks | YES | H | R | H
3 | Preparatory Work
3.1 | Earthwork and Stripping
3.1.1 | Shoulder Stripping |  | Construction Foreman | On site/Visual Check |  | Shoulder stripping completed | YES | W | R | H
3.1.2 | Cut/Excavation |  | Project Manager | On Site/Measurement | Tape measure from set-out or existing CL, as per design | Meets design drawings of cross-sectional extent | YES | H | R | H
3.2 | Drainage Structure
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 18/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH87 Heeney Creek Rehabilitation (SH87 Heeny Creek RS82/RP3550 - RP3790) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
PAVEMENT RENEWALS – Unbound Granular |  |  | NZTA F/2, NZTA M/3, NZS 4407:1991 Solid Density Test 3.7,TNZ B/2: 2005, NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005, NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005, NZS 4402: 1986 MDD and W/C Test 4.1.3 TNZ B/2: 2005, TNZ M/4:2006, TNZ C/20: 2003, NZTA T15 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER/KELSO | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | SUB-CON | OTHER |  | W(5%) | Sub Supervisor
3.2.1 | Other Structures |  | Project Manager | On site/Visual Check | Continues | Constructed to design drawings and relevant standards | YES | H | R | H |  |  | W & I | Supplier
3.3 | Ancillary Work
3.3.1 | Ancillary Items as per design Example: - Rock Benching - Signage - Vegetation/Trees - Kerb and Channel - Underground Services - Service Covers |  | Project Manager | Visual Check | Once | Constructed to design drawings and relevant standards | YES | H | R | H
3.4 | SubSoil Drainage
3.4.1 | Subsoil Drain Construction |  | Construction Foreman | Visual Check | each site | As per design drawings and/or NZTA F/2 Specification (if required or specified) | YES | W | R | H
3.4.2 | Inlets/Outlets |  | Construction Foreman | Visual Check |  | Connect to sump/catchpit, Concrete Apron, Open Channel, Inspection Eyes. | YES | W | R | H
3.5 | Pavement Widening and Digouts
3.5.1 | Excavation |  | Construction Foreman | Onsite/Scala Test | Scala Test at each Chainage (L & R Shoulders) | Subgrade CBR to be valiodated with design report. See section 5.4 refer to existing depth | YES | H | R | H
3.5.2 | Subbase Material Properties |  | Project Manager | TNZ M/3. 1986 (Lab Testing where instructed as part of M/3 Guidance) | Once | Meet speeding design requirements or NZTA M/3 guidance | YES | H | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 18/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH87 Heeney Creek Rehabilitation (SH87 Heeny Creek RS82/RP3550 - RP3790) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
PAVEMENT RENEWALS – Unbound Granular |  |  | NZTA F/2, NZTA M/3, NZS 4407:1991 Solid Density Test 3.7,TNZ B/2: 2005, NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005, NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005, NZS 4402: 1986 MDD and W/C Test 4.1.3 TNZ B/2: 2005, TNZ M/4:2006, TNZ C/20: 2003, NZTA T15 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER/KELSO | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | SUB-CON | OTHER |  | W(5%) | Sub Supervisor
3.5.3 | Density Lab testing in accordance with B/2. Only required if new subbase construction is within the carriageway line. If no compaction testing under sealed shoulders. |  | Project Manager | OWC as determined in the lab. | The lesser of: a) 1 test per stockpile or new seam b) 1 test every 5000m2 (in place) | NZS 4407:1991 Solid Density Test 3.7 TNZ B/2: 2005 | YES | H | R | H |  |  | W & I | Supplier
|  |  |  | When sampling stockpile for lab, take NDM for W/C offset. Record moisture content and take sample from beneath NDM to dry in the oven. (Two W/C readings and samples) |  | NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005
|  |  |  | MDD as the higher of the two results from lab and field Ensure plateau test is done at OWC from Lab Value and with NDM moisture offset |  | NZS 4402: 1986 MDD and W/C Test 4.1.3 TNZ B/2: 2005
3.5.4 | Construction only required when new construction is in carriageway lane. If no compaction testig under sealed shoulders |  | Project Manager | Subbase : Average ≥ 95% MDD Minimum ≥ 92% MDD | 5 test per homogenious lot of upto 1000m2 of laid pavement | NZS 4407: 1991 Test 4.2.2. TNZ B/2: 2005 | YES | H | R | H
4 | Pavement Including Sealed Shoulders
4.1 | Imported Basecourse Material Testing
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 18/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH87 Heeney Creek Rehabilitation (SH87 Heeny Creek RS82/RP3550 - RP3790) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
PAVEMENT RENEWALS – Unbound Granular |  |  | NZTA F/2, NZTA M/3, NZS 4407:1991 Solid Density Test 3.7,TNZ B/2: 2005, NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005, NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005, NZS 4402: 1986 MDD and W/C Test 4.1.3 TNZ B/2: 2005, TNZ M/4:2006, TNZ C/20: 2003, NZTA T15 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER/KELSO | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | SUB-CON | OTHER |  | W(5%) | Sub Supervisor
4.1.1 | Production Properties Note: Running course to be produced from the same type and source of material as the basecourse. |  | Project Manager | 1 - 400m3 – 2 tests 400 - 1500m3 - 3 tests 1500 - 4000m3 – 4 tests >4000m3 – 1 test per 1000m3 | TNZ M/4: Cl.4.2.3 | TNZ M/4:2006 NZS 4407 :1991 Test 3.8.1 | YES | H | R | H |  |  | W & I | Supplier
[5 empty] | Aggregate broken face content in each of the three aggregate fractions between 37.5mm and 4.75mm ≥ 70% by weight and has 2 or more broken faces | TNZ M/4: 2006 NZS 4407 :1991 Test 3.14 | YES | H | R | H
[5 empty] | Sand equivalent > 40 | TNZ M/4: 2006 NZS 4407 :1991 Test 3.6 | YES | H | R | H
[5 empty] | NB Downer Policy that only SE compliant basecourse allowed unless stabilised | TNZ M/4: 2006 NZS 4407 :1991 Test 3.6 | YES | H | R | H
[5 empty] | PI ≤ 5 | TNZ M/4: 2006/NZS 4407:1991 Test 3.4 | YES | H | R | H
4.1.2 | B/02 Lab Testing |  | Project Manager | The lesser of: a) 1 test per stockpile or new seam b) 1 test every 5000m2 (in place) | OWC as determined in the lab. | NZS 4407:1991 Solid Density Test 3.7 TNZ B/2: 2005 | YES | H | R | H
[5 empty] | When sampling stockpile for lab, take NDM for W/C offset. Record moisture content and take sample from beneath NDM to dry in the oven. (Two W/C readings and samples) | NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005 | YES | H | R | H
[7 empty] | YES | H | R | H
[5 empty] | MDD as the higher of the two results from lab and field Ensure plateau test is done at OWC from Lab Value and with NDM moisture offset | NZS 4402: 1986 MDD and W/C Test 4.1.3 TNZ B/2: 2005 | YES | H | R | H
[7 empty] | YES | H | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 18/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH87 Heeney Creek Rehabilitation (SH87 Heeny Creek RS82/RP3550 - RP3790) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
PAVEMENT RENEWALS – Unbound Granular |  |  | NZTA F/2, NZTA M/3, NZS 4407:1991 Solid Density Test 3.7,TNZ B/2: 2005, NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005, NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005, NZS 4402: 1986 MDD and W/C Test 4.1.3 TNZ B/2: 2005, TNZ M/4:2006, TNZ C/20: 2003, NZTA T15 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER/KELSO | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | SUB-CON | OTHER |  | W(5%) | Sub Supervisor
4.1.3 | Source Properties Note: Running course to be produced from the same type and source of material as the basecourse |  | Project Manager | Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve | 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | TNZ M/4: 2006 NZS 4407 :1991 Test 3.10 | YES | H | R | H
|  |  |  | Soaked CBR ≥ 80% when compacted/tested in accordance with both tests |  | NZS 4402: 1986 Test 4.13 | YES
|  |  |  | Must have quality index of AA, AB, AC, BA, BB or CA |  | NZS 4407: 1991 Test CBR 3.15 | YES
|  |  |  | T15 Specification |  | TNZ M/4: 2006 | YES
[6 empty] | TNZ M/4:2006 | YES
[6 empty] | NZTA T15 | YES
4.2 | Construction QA
4.2.1 | Pavement Surface Scarification |  | Project Manager | Overview of underlying defects that may required digout/replace | Visual Inspection after milling | Photographic condition of surface condition and visual inspection record | YES | H | R | H
4.2.2 | Pavement Surface Milling |  | Project Manager | Depth gauge every 60m. Sample record of cement by weight every 60m. | Visual Inspection during/after milling | Photographic record of milled surface, data records of cement spread and milling depth. Cement 5% by weight (20.52kg/m²). Milling Depth 180mm. | YES | H | R | H
4.2.3 | Compaction |  | Project Manager | Basecourse : Average ≥ 98% MDD Minimum ≥ 95% MDD | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | NZS 4407: 1991 Test 4.2.2. TNZ B/2: 2005 | YES | H | R | H
| Degree of Saturation (DOS) |  |  | Subbase: Average ≥ 95% MDD Minimum ≥ 92% MDD | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | NZS 4407: 1991 Test 4.2.2. TNZ B/2: 2005 | YES | H | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 18/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH87 Heeney Creek Rehabilitation (SH87 Heeny Creek RS82/RP3550 - RP3790) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
PAVEMENT RENEWALS – Unbound Granular |  |  | NZTA F/2, NZTA M/3, NZS 4407:1991 Solid Density Test 3.7,TNZ B/2: 2005, NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005, NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005, NZS 4402: 1986 MDD and W/C Test 4.1.3 TNZ B/2: 2005, TNZ M/4:2006, TNZ C/20: 2003, NZTA T15 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER/KELSO | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | SUB-CON | OTHER |  | W(5%) | Sub Supervisor
4.2.4 | Surface shape/profile Layer thickness |  | Project Manager | Visual inspection Cut/fill tolerance check Straight edge | 1 test per 60m | ≤10mm variance from 3m straight edge. | YES | H | R | H
[6 empty] | Gradual deviations | YES
[6 empty] | No ponding if crossfall > 1% | YES
[6 empty] | Overlay Thickness meets design but not >200mm OHS | YES
[6 empty] | Finished crossfall between any 2 points more than 2m apart transverse to centreline ±0.5% of design | YES
[6 empty] | Where lift pegs are used: -5mm +15mm or ±5mm at lip of concrete channel OR GPS level controlled grader | YES
| Tolerances: width unconstrained |  |  | (-20mm / -100mm) | 2 at every lift peg or per 180 m2 | Confirm offset from lift pegs | YES
| Tolerances: width constrained |  |  | Zero | 3 at every lift peg or per 180 m2 | Stringline or Topo Survey from Leveling system on Grader/lift pegs | YES
| Visual appearance |  |  | No Loose Chip Remaining | Immediately prior to sealing | Stringline or Topo Survey from Leveling system on Grader/lift pegs | YES
5 | Shoulder and addition Surfacing Preparation
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 11/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH87 Heeney Creek Rehabilitation (SH87 Heeny Creek RS82/RP3550 - RP3790) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
PAVEMENT RENEWALS – Unbound Granular |  |  | NZTA F/2, NZTA M/3, NZS 4407:1991 Solid Density Test 3.7,TNZ B/2: 2005, NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005, NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005, NZS 4402: 1986 MDD and W/C Test 4.1.3 TNZ B/2: 2005, TNZ M/4:2006, TNZ C/20: 2003, NZTA T15 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER/KELSO | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | SUB-CON | OTHER |  | W(5%) | Sub Supervisor
5.1 | Slope |  | Project Manager | Slopes consistent and is at 20% (1:5) grade |  | Visual inspection with smart level | YES | H | R | H
5.2 | Compaction |  |  | Vehicles can drive on shoulders without significant indentation/soft surface | All shoulders | Drive over 4T, check wheeltracks | YES |  | R
5.3 | Additional Surfacing Preparation - Side Roads - Accesses - Driveways - Dish Channels - High Shoulders |  | Project Manager | Have all areas of additional surfacing on the design been prepared and marked for sealing? | Before/During Sealing | Per Design | YES | H | R | H
5.4 | Soiling |  | Construction Foreman | Soiling has been done where required | All areas requiring grassing |  | YES | W | R | H
5.5 | Grassing |  | Construction Foreman | Grassing has been done where required | All areas requiring grassing |  | YES | W | R | H
6 | Pavement finishing and Surfacing
6.1 | Completed construction pavement surface = Mosaic surface, Pre-sealing walkover and checks |  | NZTA Maintenance Contact Manager | The large aggregate is held in place by a matrix of smaller aggregates The smaller aggregate is held firmly in place by fine material The matrix does not displace under normal trafficking or sweeping | Overview of site for tight mosaic surface | A clean macro texture with a tight mosaic surface as per Chapter 7 Chipsealing in NZ | YES | H | R | H
|  |  |  | All other necessary checks have been done & accepted | Before sealing |  | YES
|  |  |  | See Sealing ITP |  |  | YES
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 18/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH87 Heeney Creek Rehabilitation (SH87 Heeny Creek RS82/RP3550 - RP3790) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
PAVEMENT RENEWALS – Unbound Granular |  |  | NZTA F/2, NZTA M/3, NZS 4407:1991 Solid Density Test 3.7,TNZ B/2: 2005, NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005, NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005, NZS 4402: 1986 MDD and W/C Test 4.1.3 TNZ B/2: 2005, TNZ M/4:2006, TNZ C/20: 2003, NZTA T15 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER/KELSO | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | SUB-CON | OTHER |  | W(5%) | Sub Supervisor
6.2 | Pre-seal Area Check |  | NZTA Maintenance Contact Manager | Check prepared and marked area for sealing against design to check whether full area of design ready for surfacing | Before sealing | On Site tape-measure | YES | H | R | H
6.3 | Sealing TMP and aftercare process |  | Sealing Manager | See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site |  |  | YES | W | R | H
6.4 | Sweeping of Sealing works and handover to Roadmarkers |  | Sealing Manager | Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor. |  |  | YES | H | R | H
6.5 | Post-seal Area Check |  | NZTA Maintenance Contact Manager | Check sealed area meets design | After Surfacing | On Site tape-measure | YES | W | R | H
7 | Improvements
7.1 | Improvement guardrails singnage footpaths |  | Project Manager | Replaced in same position, height etc | All signs/marker | Visual inspection/TNZ C/20: 2003 | YES | H | R | H
8 | Site Reinstatement/Clearance
8.1 | Roadmarking |  | Project Manager | Visual Inspection | All markings | Replaced in same position, or per design/MOTSAM | YES | H | R | H
8.2 | Traffic Services | Marker pegs/ Signs/Markings/RRPMs Replaced | Construction Foreman | Visual inspection | All signs/markers | Replaced in same position, height etc/TNZ C/20: 2003 | YES | H | R | H
8.3 | Draine Cleared |  | Construction Foreman | Visual inspection | All drains, after all other works | Drains are cleared and culvert ends and side (accessway) culverts installed or reinstated | YES | W | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 18/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 620185 ITP V1.0 | Rev.: | 1 |  | H | Client Rep
|  | Project: | SH87 Heeney Creek Rehabilitation (SH87 Heeny Creek RS82/RP3550 - RP3790) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
PAVEMENT RENEWALS – Unbound Granular |  |  | NZTA F/2, NZTA M/3, NZS 4407:1991 Solid Density Test 3.7,TNZ B/2: 2005, NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005, NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005, NZS 4402: 1986 MDD and W/C Test 4.1.3 TNZ B/2: 2005, TNZ M/4:2006, TNZ C/20: 2003, NZTA T15 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER/KELSO | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | SUB-CON | OTHER |  | W(5%) | Sub Supervisor
8.4 | Envirnomental Controls Removed |  | Construction Foreman | Visual check | All installed measures | Any silt fences or other controls are removed | YES | W | R | H
8.5 | Traffic Management Removed |  | Construction Foreman | Visual check | When safe, after all physical works completed | All traffic management removed from site safely | YES | W | R | H
8.6 | Site left clean & tidy |  | Construction Foreman | Visual check | After vacating site | Stockpiles removed, Plant removed, Litter cleared from site | YES | W | R | H
9 | As Built Records
9.1 | Collect asset data |  | Renewal Enginerr |  | During construction | All relevant as built information collected. SHDOM (SM050) | YES | W | R | H
9.2 | Enter asset data into RAMM and/or register(s) |  | Asset Information Manager | RAMM | At completion of work. | All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.SHDOM (SM050) | YES | W | R | H
9.3 | Construction Completion Report |  | Project Manager/Renewal Manager | Contract Specification | At completion of work. | Checked and approved | YES | W | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Tim Joss |  | Rowan Tumai
DATE: 18/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client