## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - CONOC Construction (Heeney Creek Rehabilitation) - PAVEMENT RENEWALS - Unbound Granular | itp |  |  |  |  | ITP - CONOC Construction (Heeney Creek Rehabilitation) - PAVEMENT RENEWALS - Unbound Granular
section | 1 - Preliminary and General
checkpoint | 1.1 - Construction Program Completion
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Best Practice Contract Specific MMP
label | Frequency Of Inspection Or Test - Before work Commence
label | Spec. Ref, Procedure Or Method Statement - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date.
label | Records Required - YES
label | DOWNER ENGINEER - W
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Approved RQP
label | Controlled By : (Position) - NZTA Maintenance Contact Manager
label | Accept / Reject Criteria - Contract Specification
label | Frequency Of Inspection Or Test - Before work Commence
label | Spec. Ref, Procedure Or Method Statement - Principal Acceptance according to guidelines in appendix 6.3
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Traffic Management/TMP
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - CoPTTM
label | Frequency Of Inspection Or Test - Before Traffic Management Setup
label | Spec. Ref, Procedure Or Method Statement - TMP checked and approved, Plans approved, Current EED (if applicable)
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Notification of intention to start work
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Notification
label | Frequency Of Inspection Or Test - Before work commences
label | Spec. Ref, Procedure Or Method Statement - Letter drop to local residents. Where required and defined by SWAMP, VMS, social media/media advertising
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Setout/Site Preparation
checkpoint | 2.1 - Setout/Survey
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Best Practice
label | Frequency Of Inspection Or Test - Per installation
label | Spec. Ref, Procedure Or Method Statement - Survey Records
label | Records Required - YES
label | DOWNER ENGINEER - W
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Permit to dig/Authority to Work/close approach permits
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Downer Permit to work or Equvilent
label | Frequency Of Inspection Or Test - Before work commences
label | Spec. Ref, Procedure Or Method Statement - Organisational approval
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Cultural/Heritage Risk Assessment
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - WK Cultural & Heritage Risk Model
label | Frequency Of Inspection Or Test - Before work commences
label | Spec. Ref, Procedure Or Method Statement - Local kiwi has been notified of intent to start work
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Archaeological Risk
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - WK Cultural & Heritage Risk Model
label | Frequency Of Inspection Or Test - Before work commences
label | Spec. Ref, Procedure Or Method Statement - Toolbox meeting held covering accidental discovery protocol
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Traffic Management Setup
label | Controlled By : (Position) - Construction Foreman/STMS
label | Accept / Reject Criteria - Traffic Management Plan
label | Frequency Of Inspection Or Test - Before work commences each day
label | Spec. Ref, Procedure Or Method Statement - Traffic management complies with TMP
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Machine Control Survey Control
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - On Site/Measurement
label | Frequency Of Inspection Or Test - Before using machine control
label | Spec. Ref, Procedure Or Method Statement - Verification of survey control points and setup
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Machine Control Accuracy Verification
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - On Site/Measurement
label | Frequency Of Inspection Or Test - Before using machine control
label | Spec. Ref, Procedure Or Method Statement - Verification of survey control points and setup
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Prepare String Sheet (Digital)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - On Site/Measurement
label | Frequency Of Inspection Or Test - Before using machine control
label | Spec. Ref, Procedure Or Method Statement - Digital design set-out data is consistent with on site marks
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Preparatory Work (3.1 - Earthwork and Stripping)
checkpoint | 3.1.1 - Shoulder Stripping
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - On site/Visual Check
label | Spec. Ref, Procedure Or Method Statement - Shoulder stripping completed
label | Records Required - YES
label | DOWNER ENGINEER - W
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Cut/Excavation
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - On Site/Measurement
label | Frequency Of Inspection Or Test - Tape measure from set-out or existing CL, as per design
label | Spec. Ref, Procedure Or Method Statement - Meets design drawings of cross-sectional extent
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Preparatory Work (3.2 - Drainage Structure)
checkpoint | 3.2.1 - Other Structures
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - On site/Visual Check
label | Frequency Of Inspection Or Test - Continues
label | Spec. Ref, Procedure Or Method Statement - Constructed to design drawings and relevant standards
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Preparatory Work (3.3 - Ancillary Work)
checkpoint | 3.3.1 - Ancillary Items as per design
label | Example:
label | – Rock Benching
label | – Signage
label | – Vegetation/Trees
label | – Kerb and Channel
label | – Underground Services
label | – Service Covers
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Visual Check
label | Frequency Of Inspection Or Test - Once
label | Spec. Ref, Procedure Or Method Statement - Constructed to design drawings and relevant standards
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Preparatory Work (3.4 - SubSoil Drainage)
checkpoint | 3.4.1 - Subsoil Drain Construction
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Visual Check
label | Frequency Of Inspection Or Test - each site
label | Spec. Ref, Procedure Or Method Statement - As per design drawings and/or NZTA F/2 Specification (if required or specified)
label | Records Required - YES
label | DOWNER ENGINEER - W
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4.2 - Inlets/Outlets
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Visual Check
label | Spec. Ref, Procedure Or Method Statement - Connect to sump/catchpit, Concrete Apron, Open Channel, Inspection Eyes.
label | Records Required - YES
label | DOWNER ENGINEER - W
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Preparatory Work (3.5 - Pavement Widening and Digouts)
checkpoint | 3.5.1 - Excavation
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Onsite/Scala Test
label | Frequency Of Inspection Or Test - Scala Test at each Chainage (L & R Shoulders)
label | Spec. Ref, Procedure Or Method Statement - Subgrade CBR to be valiodated with design report. See section 5.4 refer to existing depth
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5.2 - Subbase Material Properties
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - TNZ M/3. 1986 (Lab Testing where instructed as part of M/3 Guidance)
label | Frequency Of Inspection Or Test - Once
label | Spec. Ref, Procedure Or Method Statement - Meet speeding design requirements or NZTA M/3 guidance
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5.3 - Density Lab testing in accordance with B/2. Only required if new subbase construction is within the carriageway line. If no compaction testing under sealed shoulders. (1)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - OWC as determined in the lab.
label | Frequency Of Inspection Or Test - The lesser of:
label | a) 1 test per stockpile or new seam
label | b) 1 test every 5000m2 (in place)
label | Spec. Ref, Procedure Or Method Statement - NZS 4407:1991 Solid Density Test 3.7, TNZ B/2: 2005
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5.3 - Density Lab testing in accordance with B/2. Only required if new subbase construction is within the carriageway line. If no compaction testing under sealed shoulders. (2)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - When sampling stockpile for lab, take NDM for W/C offset. Record moisture content and take sample from beneath NDM to dry in the oven. (Two W/C readings and samples)
label | Frequency Of Inspection Or Test - The lesser of:
label | a) 1 test per stockpile or new seam
label | b) 1 test every 5000m2 (in place)
label | Spec. Ref, Procedure Or Method Statement - NZS 4407:1991 W/C Test 3.7, TNZ B/2: 2005
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5.3 - Density Lab testing in accordance with B/2. Only required if new subbase construction is within the carriageway line. If no compaction testing under sealed shoulders. (3)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - MDD as the higher of the two results from lab and field. Ensure plateau test is done at OWC from Lab Value and with NDM moisture offset.
label | Frequency Of Inspection Or Test - The lesser of:
label | a) 1 test per stockpile or new seam
label | b) 1 test every 5000m2 (in place)
label | Spec. Ref, Procedure Or Method Statement - NZS 4402: 1986 MDD and W/C Test 4.1.3, TNZ B/2: 2005
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5.4 - Construction only required when new construction is in carriageway lane. If no compaction testig under sealed shoulders
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Subbase:
label | ○ Average ≥ 95% MDD
label | ○ Minimum ≥ 92% MDD
label | Frequency Of Inspection Or Test - 5 test per homogenious lot of upto 1000m2 of laid pavement
label | Spec. Ref, Procedure Or Method Statement - NZS 4407: 1991 Test 4.2.2. TNZ B/2: 2005
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 4 - Pavement Including Sealed Shoulders (4.1 - Imported Basecourse Material Testing)
checkpoint | 4.1.1 - Production Properties - Note: Running course to be produced from the same type and source of material as the basecourse. (1)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - 1 - 400m3 – 2 tests
label | ○ 400 - 1500m3 - 3 tests
label | ○ 1500 - 4000m3 – 4 tests
label | ○ >4000m3 – 1 test per 1000m3
label | Frequency Of Inspection Or Test - TNZ M/4: Cl.4.2.3
label | Spec. Ref, Procedure Or Method Statement - TNZ M/4:2006, NZS 4407 :1991 Test 3.8.1
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.1 - Production Properties - Note: Running course to be produced from the same type and source of material as the basecourse. (2)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - 1 - 400m3 – 2 tests
label | ○ 400 - 1500m3 - 3 tests
label | ○ 1500 - 4000m3 – 4 tests
label | ○ >4000m3 – 1 test per 1000m3
label | Frequency Of Inspection Or Test - Aggregate broken face content in each of the three aggregate fractions between 37.5mm and 4.75mm ≥ 70% by weight and has 2 or more broken faces
label | Spec. Ref, Procedure Or Method Statement - TNZ M/4: 2006, NZS 4407 :1991 Test 3.14
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.1 - Production Properties - Note: Running course to be produced from the same type and source of material as the basecourse. (3)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - 1 - 400m3 – 2 tests
label | ○ 400 - 1500m3 - 3 tests
label | ○ 1500 - 4000m3 – 4 tests
label | ○ >4000m3 – 1 test per 1000m3
label | Frequency Of Inspection Or Test - Sand equivalent > 40
label | Spec. Ref, Procedure Or Method Statement - TNZ M/4: 2006, NZS 4407 :1991 Test 3.6
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.1 - Production Properties - Note: Running course to be produced from the same type and source of material as the basecourse. (4)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - 1 - 400m3 – 2 tests
label | ○ 400 - 1500m3 - 3 tests
label | ○ 1500 - 4000m3 – 4 tests
label | ○ >4000m3 – 1 test per 1000m3
label | Frequency Of Inspection Or Test - NB Downer Policy that only SE compliant basecourse allowed unless stabilised
label | Spec. Ref, Procedure Or Method Statement - TNZ M/4: 2006, NZS 4407 :1991 Test 3.6
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.1 - Production Properties - Note: Running course to be produced from the same type and source of material as the basecourse. (5)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - 1 - 400m3 – 2 tests
label | ○ 400 - 1500m3 - 3 tests
label | ○ 1500 - 4000m3 – 4 tests
label | ○ >4000m3 – 1 test per 1000m3
label | Frequency Of Inspection Or Test - PI ≤ 5
label | Spec. Ref, Procedure Or Method Statement - TNZ M/4: 2006/NZS 4407:1991 Test 3.4
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.2 - B/02 Lab Testing (1)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - The lesser of:
label | a) 1 test per stockpile or new seam
label | b) 1 test every 5000m2 (in place)
label | Frequency Of Inspection Or Test - OWC as determined in the lab.
label | Spec. Ref, Procedure Or Method Statement - NZS 4407:1991 Solid Density Test 3.7, TNZ B/2: 2005
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.2 - B/02 Lab Testing (2)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - The lesser of:
label | a) 1 test per stockpile or new seam
label | b) 1 test every 5000m2 (in place)
label | Frequency Of Inspection Or Test - When sampling stockpile for lab, take NDM for W/C offset. Record moisture content and take sample from beneath NDM to dry in the oven. (Two W/C readings and samples)
label | Spec. Ref, Procedure Or Method Statement - NZS 4407:1991 W/C Test 3.7 TNZ B/2: 2005
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.2 - B/02 Lab Testing (3)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - The lesser of:
label | a) 1 test per stockpile or new seam
label | b) 1 test every 5000m2 (in place)
label | Frequency Of Inspection Or Test - MDD as the higher of the two results from lab and field Ensure plateau test is done at OWC from Lab Value and with NDM moisture offset
label | Spec. Ref, Procedure Or Method Statement - NZS 4402: 1986 MDD and W/C Test 4.1.3 TNZ B/2: 2005
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.3 - Source Properties Note: Running course to be produced from the same type and source of material as the basecourse (1)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve
label | Frequency Of Inspection Or Test - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | Spec. Ref, Procedure Or Method Statement - TNZ M/4: 2006, NZS 4407 :1991 Test 3.10
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.3 - Source Properties Note: Running course to be produced from the same type and source of material as the basecourse (2)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Soaked CBR ≥ 80% when compacted/tested in accordance with both tests
label | Frequency Of Inspection Or Test - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | Spec. Ref, Procedure Or Method Statement - NZS 4402: 1986 Test 4.13
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.3 - Source Properties Note: Running course to be produced from the same type and source of material as the basecourse (3)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Must have quality index of AA, AB, AC, BA, BB or CA
label | Frequency Of Inspection Or Test - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | Spec. Ref, Procedure Or Method Statement - NZS 4407: 1991 Test CBR 3.15
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.3 - Source Properties Note: Running course to be produced from the same type and source of material as the basecourse (4)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - T15 Specification
label | Frequency Of Inspection Or Test - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | Spec. Ref, Procedure Or Method Statement - TNZ M/4: 2006
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.3 - Source Properties Note: Running course to be produced from the same type and source of material as the basecourse (5)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - T15 Specification
label | Frequency Of Inspection Or Test - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | Spec. Ref, Procedure Or Method Statement - TNZ M/4:2006
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 4 - Pavement Including Sealed Shoulders (4.2 - Construction QA)
checkpoint | 4.2.1 - Pavement Surface Scarification
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Overview of underlying defects that may required digout/replace
label | Frequency Of Inspection Or Test - Visual Inspection after milling
label | Spec. Ref, Procedure Or Method Statement - Photographic condition of surface condition and visual inspection record
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.2 - Pavement Surface Milling
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Depth gauge every 60m. Sample record of cement by weight every 60m.
label | Frequency Of Inspection Or Test - Visual Inspection during/after milling
label | Spec. Ref, Procedure Or Method Statement - Photographic record of milled surface, data records of cement spread and milling depth. Cement 5% by weight (20.52kg/m²). Milling Depth 180mm.
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.3 - Compaction
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Basecourse:
label | ○ Average ≥ 98% MDD
label | ○ Minimum ≥ 95% MDD
label | Frequency Of Inspection Or Test - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | Spec. Ref, Procedure Or Method Statement - NZS 4407: 1991 Test 4.2.2. TNZ B/2: 2005
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.3 - Degree of Saturation (DOS)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Subbase:
label | ○ Average ≥ 95% MDD
label | ○ Minimum ≥ 92% MDD
label | Frequency Of Inspection Or Test - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | Spec. Ref, Procedure Or Method Statement - NZS 4407: 1991 Test 4.2.2. TNZ B/2: 2005
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.4 - Surface shape/profile Layer thickness (1)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Visual inspection, Cut/fill tolerance check, Straight edge
label | Frequency Of Inspection Or Test - 1 test per 60m
label | Spec. Ref, Procedure Or Method Statement - ≤10mm variance from 3m straight edge.
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.4 - Surface shape/profile Layer thickness (2)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Visual inspection, Cut/fill tolerance check, Straight edge
label | Frequency Of Inspection Or Test - 1 test per 60m
label | Spec. Ref, Procedure Or Method Statement - Gradual deviations
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.4 - Surface shape/profile Layer thickness (3)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Visual inspection, Cut/fill tolerance check, Straight edge
label | Frequency Of Inspection Or Test - 1 test per 60m
label | Spec. Ref, Procedure Or Method Statement - No ponding if crossfall > 1%
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.4 - Surface shape/profile Layer thickness (4)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Visual inspection, Cut/fill tolerance check, Straight edge
label | Frequency Of Inspection Or Test - 1 test per 60m
label | Spec. Ref, Procedure Or Method Statement - Overlay Thickness meets design but not >200mm OHS
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.4 - Surface shape/profile Layer thickness (5)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Visual inspection, Cut/fill tolerance check, Straight edge
label | Frequency Of Inspection Or Test - 1 test per 60m
label | Spec. Ref, Procedure Or Method Statement - Finished crossfall between any 2 points more than 2m apart transverse to centreline ±0.5% of design
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.4 - Surface shape/profile Layer thickness (6)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Visual inspection, Cut/fill tolerance check, Straight edge
label | Frequency Of Inspection Or Test - 1 test per 60m
label | Spec. Ref, Procedure Or Method Statement - Where lift pegs are used: -5mm +15mm or ±5mm at lip of concrete channel OR GPS level controlled grader
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.4 - Tolerances: width unconstrained
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - (-20mm / -100mm)
label | Frequency Of Inspection Or Test - 2 at every lift peg or per 180 m2
label | Spec. Ref, Procedure Or Method Statement - Confirm offset from lift pegs
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.4 - Tolerances: width constrained
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Zero
label | Frequency Of Inspection Or Test - 3 at every lift peg or per 180 m2
label | Spec. Ref, Procedure Or Method Statement - Stringline or Topo Survey from Leveling system on Grader/lift pegs
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.4 - Visual appearance
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - No Loose Chip Remaining
label | Frequency Of Inspection Or Test - Immediately prior to sealing
label | Spec. Ref, Procedure Or Method Statement - Stringline or Topo Survey from Leveling system on Grader/lift pegs
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 5 - Shoulder and addition Surfacing Preparation
checkpoint | 5.1 - Slope
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Slopes consistent and is at 20% (1:5) grade
label | Spec. Ref, Procedure Or Method Statement - Visual inspection with smart level
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Compaction
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Vehicles can drive on shoulders without significant indentation/soft surface
label | Frequency Of Inspection Or Test - All shoulders
label | Spec. Ref, Procedure Or Method Statement - Drive over 4T, check wheeltracks
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Additional Surfacing Preparation
label | – Side Roads
label | – Accesses
label | – Driveways
label | – Dish Channels
label | – High Shoulders
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Have all areas of additional surfacing on the design been prepared and marked for sealing?
label | Frequency Of Inspection Or Test - Before/During Sealing
label | Spec. Ref, Procedure Or Method Statement - Per Design
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 - Soiling
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Soiling has been done where required
label | Frequency Of Inspection Or Test - All areas requiring grassing
label | Records Required - YES
label | DOWNER ENGINEER - W
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5 - Grassing
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Grassing has been done where required
label | Frequency Of Inspection Or Test - All areas requiring grassing
label | Records Required - YES
label | DOWNER ENGINEER - W
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 6 - Pavement finishing and Surfacing
checkpoint | 6.1 - Completed construction pavement surface = Mosaic surface, Pre-sealing walkover and checks (1)
label | Controlled By : (Position) - NZTA Maintenance Contact Manager
label | Accept / Reject Criteria - The large aggregate is held in place by a matrix of smaller aggregates. The smaller aggregate is held firmly in place by fine material. The matrix does not displace under normal trafficking or sweeping.
label | Frequency Of Inspection Or Test - Overview of site for tight mosaic surface
label | Spec. Ref, Procedure Or Method Statement - A clean macro texture with a tight mosaic surface as per Chapter 7 Chipsealing in NZ
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.1 - Completed construction pavement surface = Mosaic surface, Pre-sealing walkover and checks (2)
label | Controlled By : (Position) - NZTA Maintenance Contact Manager
label | Accept / Reject Criteria - All other necessary checks have been done & accepted
label | Frequency Of Inspection Or Test - Before sealing
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.1 - Completed construction pavement surface = Mosaic surface, Pre-sealing walkover and checks (3)
label | Controlled By : (Position) - NZTA Maintenance Contact Manager
label | Accept / Reject Criteria - See Sealing ITP
label | Frequency Of Inspection Or Test - See Sealing ITP
label | Spec. Ref, Procedure Or Method Statement - See Sealing ITP
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2 - Pre-seal Area Check
label | Controlled By : (Position) - NZTA Maintenance Contact Manager
label | Accept / Reject Criteria - Check prepared and marked area for sealing against design to check whether full area of design ready for surfacing
label | Frequency Of Inspection Or Test - Before sealing
label | Spec. Ref, Procedure Or Method Statement - On Site tape-measure
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.3 - Sealing TMP and aftercare process
label | Controlled By : (Position) - Sealing Manager
label | Accept / Reject Criteria - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | Frequency Of Inspection Or Test - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | Spec. Ref, Procedure Or Method Statement - See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site
label | Records Required - YES
label | DOWNER ENGINEER - W
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.4 - Sweeping of Sealing works and handover to Roadmarkers
label | Controlled By : (Position) - Sealing Manager
label | Accept / Reject Criteria - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | Frequency Of Inspection Or Test - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | Spec. Ref, Procedure Or Method Statement - Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor.
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.5 - Post-seal Area Check
label | Controlled By : (Position) - NZTA Maintenance Contact Manager
label | Accept / Reject Criteria - Check sealed area meets design
label | Frequency Of Inspection Or Test - After Surfacing
label | Spec. Ref, Procedure Or Method Statement - On Site tape-measure
label | Records Required - YES
label | DOWNER ENGINEER - W
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 7 - Improvements
checkpoint | 7.1 - Improvement guardrails singnage footpaths
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Replaced in same position, height etc
label | Frequency Of Inspection Or Test - All signs/marker
label | Spec. Ref, Procedure Or Method Statement - Visual inspection/TNZ C/20: 2003
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 8 - Site Reinstatement/Clearance
checkpoint | 8.1 - Roadmarking
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - Visual Inspection
label | Frequency Of Inspection Or Test - All markings
label | Spec. Ref, Procedure Or Method Statement - Replaced in same position, or per design/MOTSAM
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.2 - Traffic Services, Marker pegs/ Signs/Markings/RRPMs Replaced
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Visual inspection
label | Frequency Of Inspection Or Test - All signs/markers
label | Spec. Ref, Procedure Or Method Statement - Replaced in same position, height etc/TNZ C/20: 2003
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.3 - Draine Cleared
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Visual inspection
label | Frequency Of Inspection Or Test - All drains, after all other works
label | Spec. Ref, Procedure Or Method Statement - Drains are cleared and culvert ends and side (accessway) culverts installed or reinstated
label | Records Required - YES
label | DOWNER ENGINEER - W
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.4 - Envirnomental Controls Removed
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Visual check
label | Frequency Of Inspection Or Test - All installed measures
label | Spec. Ref, Procedure Or Method Statement - Any silt fences or other controls are removed
label | Records Required - YES
label | DOWNER ENGINEER - W
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.5 - Traffic Management Removed
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Visual check
label | Frequency Of Inspection Or Test - When safe, after all physical works completed
label | Spec. Ref, Procedure Or Method Statement - All traffic management removed from site safely
label | Records Required - YES
label | DOWNER ENGINEER - W
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.6 - Site left clean & tidy
label | Controlled By : (Position) - Construction Foreman
label | Accept / Reject Criteria - Visual check
label | Frequency Of Inspection Or Test - After vacating site
label | Spec. Ref, Procedure Or Method Statement - Stockpiles removed, Plant removed, Litter cleared from site
label | Records Required - YES
label | DOWNER ENGINEER - W
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 9 - As Built Records
checkpoint | 9.1 - Collect asset data
label | Controlled By : (Position) - Renewal Enginerr
label | Frequency Of Inspection Or Test - During construction
label | Spec. Ref, Procedure Or Method Statement - All relevant as built information collected. SHDOM (SM050)
label | Records Required - YES
label | DOWNER ENGINEER - W
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9.2 - Enter asset data into RAMM and/or register(s)
label | Controlled By : (Position) - Asset Information Manager
label | Accept / Reject Criteria - RAMM
label | Frequency Of Inspection Or Test - At completion of work.
label | Spec. Ref, Procedure Or Method Statement - All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.SHDOM (SM050)
label | Records Required - YES
label | DOWNER ENGINEER - W
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9.3 - Construction Completion Report
label | Controlled By : (Position) - Project Manager/Renewal Manager
label | Accept / Reject Criteria - Contract Specification
label | Frequency Of Inspection Or Test - At completion of work.
label | Spec. Ref, Procedure Or Method Statement - Checked and approved
label | Records Required - YES
label | DOWNER ENGINEER - W
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT