## DN-GD-GP032
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Shallow Pothole Repair in a sealed Pavement - Premixe Method - QPR |  |  | DN-GD-GP032 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/SOUTH ROADS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare Hole |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP032 | NO | R | R | H |  |  | W & I | Supplier
2 | Filling Hole |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP032 | NO | R | R | H
3 | Blinding |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP032 | NO | R | R | H
4 | Test and Check |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP032 | NO | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 11/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## DN-GD-GP033
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Deep Pothole Repair in a Sealed Pavement Premix Method |  |  | DN-GD-GP033 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/SOUTH ROADS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare Hole |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP033 | NO | R | R | H |  |  | W & I | Supplier
2 | Filling Hole |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP033 | NO | R | R | H
3 | Blinding |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP033 | NO | R | R | H
4 | Test and Check |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP033 | NO | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 11/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## DN-GD-GP034
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Pothole repair using a Broom Road Patch (BRP) |  |  | DN-GD-GP034 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/SOUTH ROADS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare Hole |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP034 | NO | R | R | H |  |  | W & I | Supplier
2 | Apply RS1 Tack Coat Emulsion |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP034 | NO | R | R | H
3 | Attach BRP |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP034 | NO | R | R | H
4 | Blinding |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP034 | NO | R | R | H
5 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP034 | NO | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 11/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## DN-GD-GP035
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Adjust a Surface Box - Not a Manhole |  |  | DN-GD-GP035 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/SOUTH ROADS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP035 | NO | R | R | H |  |  | W & I | Supplier
2 | Excavation |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP035 | NO | W(10%) | R | H
3 | Replace Risers |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP035 | NO | W(10%) | R | H
4 | Backfill around the Riser (Clegg Hammer) |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP035 | YES | W(10%) | R | H
5 | Final Shape and Trim |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP035 | NO | W(10%) | R | H
6 | Surfacing |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP035 | NO | W(10%) | R | H
7 | Surface Cover Painting |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP035 | NO | W(10%) | R | H
8 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP035 | NO | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 11/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## DN-GD-GP036
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Edgebreak Repair - Formed Shoulder (Manual Premix Method) |  |  | DN-GD-GP036 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/SOUTH ROADS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepre Site |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP036 | NO | R | R | H
2 | Prepare Shoulder |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP036 | NO | W(10%) | R | H
3 | Filling the Edge Break |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP036 | NO | W(10%) | R | H
4 | Reconstruction Supporting Shoulder |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP036 | YES | W(10%) | R | H
5 | Blinding |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP036 | NO | W(10%) | R | H
6 | Test and Check |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP036 | NO | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 11/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -

## DN-GD-GP037
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Repair Low Shoulder - Grading |  |  | DN-GD-GP037 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/SOUTH ROADS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP037 | NO | R | R | H |  |  | W & I | Supplier
2 | Remove EMP |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP037 | NO | R | R | H
3 | Initial Cut and Grader Steup |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP037 | NO | R | R | H
4 | Final Shape and Trim |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP037 | NO | W(10%) | R | H
5 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP037 | NO | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 11/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## DN-GD-GP038
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Repair Low Shoulder-Material Replacement |  |  | DN-GD-GP038 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/SOUTH ROADS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP038 | NO | R | R | H |  |  | W & I | Supplier
2 | Scarify |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP038 | NO | R | R | H
3 | Spread Makeup Metal |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP038 | NO | W(10%) | R | H
4 | Fianl Shape and Trim |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP038 | NO | W(10%) | R | H
5 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP038 | NO | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 11/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## DN-GD-GP039
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Repair Surface Depression – Hand Premix |  |  | DN-GD-GP039 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/SOUTH ROADS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP039 | NO | R | R | H |  |  | W & I | Supplier
2 | Application of Blinder (Tack Coat) |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP039 | YES | W(10%) | R | H
3 | Spreding Premix Material |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP039 | NO | W(10%) | R | H
4 | Final Shape and Trim |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP039 | NO | W(10%) | R | H
5 | Blinding |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP039 | NO | W(10%) | R | H
6 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP039 | NO | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 11/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## DN-GD-GP040
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Repair Surface Depression - Machine Premix Method |  |  | DN-GD-GP040 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/SOUTH ROADS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP040 | NO | R | R | H |  |  | W & I | Supplier
2 | Milling |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP040 | NO | W(10%) | R | H
3 | Application of Binder ( Tack Coat) |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP040 | NO | W(10%) | R | H
4 | Base Levelling |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP040 | NO | W(10%) | R | H
5 | layer Premix Material |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP040 | NO | W(10%) | R | H
6 | Final Compaction |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP040 | NO | W(10%) | R | H
7 | Blinding |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP040 | NO | W(10%) | R | H
8 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP040 | NO | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 11/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## DN-GD-GP042
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Repair Surface Depression - Rip and Remake Method |  |  | DN-GD-GP042 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/SOUTH ROADS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP042 | NO | R | R | H |  |  | W & I | Supplier
2 | Pavement Layer |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP042 | NO | R | R | H
3 | Final Shape and Trim |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP042 | NO | R | R | H
4 | Surfacing |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP042 | YES | W(10%) | R | H
5 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP042 | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 11/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## DN-GD-GP043
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Repair of Bleeding - Flushing Binder Applying Additional Chip |  |  | DN-GD-GP043 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/SOUTH ROADS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP043 | NO | R | R | H |  |  | W & I | Supplier
2 | Solvent Spraying |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP043 | YES | R | R | H
3 | Chip Application |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP043 | YES | W(10%) | R | H
4 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP043 | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 11/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## DN-GD-GP044
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Crack Seal Repairs (5-15mm) Reservoir and Overband Methods |  |  | DN-GD-GP044 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/SOUTH ROADS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Materail |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP044 | NO | R | R | H |  |  | W & I | Supplier
2 | Weather |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP044 | NO | R | R | H
3 | Preparation |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP044 | NO | W(10%) | R | H
4 | Cleaning and Drying |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP044 | NO | W(10%) | R | H
5 | Application of Sealer/Filler |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP044 | NO | W(10%) | R | H
6 | Finishing |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP044 | NO | W(10%) | R | H
7 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP044 | NO | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 11/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client