## DN-GD-GP045
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Repair of Stripping or Scabbing: Applying Additional Chip |  |  | DN-GD-GP045 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/SOUTH ROADS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP045 | NO | R | R | H |  |  | W & I | Supplier
2 | Solvent and Chip Method |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP045 | YES | W(10%) | R | H
3 | Emulsion and Chip Method |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP045 | YES | W(10%) | R | H
4 | Test and Check |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP045 | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 11/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## DN-GD-GP047
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
First Coat – Two Coat Chip Seal (Hand Spray Method) |  |  | DN-GD-GP047 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/SOUTH ROADS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Weather |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP047 | NO | R | R | H |  |  | W & I | Supplier
2 | Site Preparation |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP047 | NO | R | R | H
3 | Binder Spray - First Coat |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP047 | YES | W(10%) | R | H
4 | Spreading Chip first Coat |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP047 | YES | W(10%) | R | H
5 | Prepare for Second Coat |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP047 | YES | W(10%) | R | H
6 | Second Coat |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP047 | YES | W(10%) | R | H
7 | Site Monitoring |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP047 | NO | W(10%) | R | H
8 | Sweeping and Marking |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP047 | NO | W(10%) | R | H
9 | Test and Check |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP047 | NO | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 12/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## DN-GD-GP060
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Grading Unsealed Road - Light |  |  | DN-GD-GP060 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/SOUTH ROADS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP060 | NO | R | R | H |  |  | W & I | Supplier
2 | Grader Operation |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP060 | NO | R | R | H
3 | Grader Set-up |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP060 | NO | R | R | H
4 | Super Elevation on Corners |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP060 | YES | W(10%) | R | H
5 | Fisrt Pass |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP060 | NO | W(10%) | R | H
6 | Second Pass |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP060 | NO | W(10%) | R | H
7 | Third Cutting Pass (Optional depending on width of road) |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP060 | NO | W(10%) | R | H
8 | Spreading Pass 1-2 |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP060 | NO | W(10%) | R | H
9 | Things to Watch for |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP060 | NO | R | R | H
10 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP060 | NO | W | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 12/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## DN-GD-GP061
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Grading Unsealed Road - Medium |  |  | DN-GD-GP061 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/SOUTH ROADS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP061 | NO | R | R | H |  |  | W & I | Supplier
2 | Grader Operation |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP061 | NO | R | R | H
3 | Grader Set-up |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP061 | NO | R | R | H
4 | Super Elevation on Corners |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP061 | YES | W(10%) | R | H
5 | First Pass |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP061 | NO | W(10%) | R | H
6 | Second Pass |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP061 | NO | W(10%) | R | H
7 | Cut outs |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP061 | NO | W(10%) | R | H
8 | Third Pass |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP061 | NO | W(10%) | R | H
9 | Fourth Pass |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP061 | NO | W(10%) | R | H
10 | Extra Pass |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP061 | NO | W(10%) | R | H
11 | Spreading Passes 1-2 |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP061 | NO | W(10%) | R | H
12 | Issues |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP061 | NO | W(10%) | R | H
13 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP061 | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 12/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## DN-GD-GP062
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Grading Unsealed Road - Heavy |  |  | DN-GD-GP062 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/SOUTH ROADS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP062 | NO | R | R | H
2 | Grader Operation |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP062 | NO | R | R | H
3 | Grader Set-up |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP062 | NO | R | R | H
4 | Super Elevation on Corners |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP062 | YES | W(10%) | R | H
5 | First Pass |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP062 | NO | W(10%) | R | H
6 | Second Pass |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP062 | NO | W(10%) | R | H
7 | Cut outs |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP062 | NO | W(10%) | R | H
8 | Third Pass Grader Set-up |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP062 | NO | W(10%) | R | H
9 | Fourth Pass |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP062 | NO | W(10%) | R | H
10 | Extra Pass |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP062 | NO | W(10%) | R | H
11 | Spreading Passes 1-2 |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP062 | NO | W(10%) | R | H
12 | Compaction |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP062 | YES | W(10%) | R | H
13 | Issues |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP062 | NO | W(10%) | R | H
14 | Test and Check |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP062 | YES | W(10%) | R | H
11 | Spreading Passes 1-2 |  | XXX |  |  |  |  | - | - | - | -
12 | Test and Check |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 12/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -

## DN-GD-GP063
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Unsealed Pavement – Repair a Pothole |  |  | DN-GD-GP063 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/SOUTH ROADS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Selecating Patchiong Material |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP063 | NO | R | R | H |  |  | W & I | Supplier
2 | Short Term Repair |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP063 | NO | R | R | H
3 | Long Term Repair |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP063 | NO | R | R | H
4 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP063 | NO | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 12/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## DN-GD-GP064
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Unsealed Pavement - Digout Repair |  |  | DN-GD-GP064 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/SOUTH ROADS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP064 | NO | R | R | H |  |  | W & I | Supplier
2 | Drainage |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP064 | NO | R | R | H
3 | Excavation |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP064 | YES | W(10%) | R | H
4 | Filter Fabric |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP064 | YES | W(10%) | R | H
5 | Subsoil Drainage |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP064 | YES | W(10%) | R | H
6 | Backfill and Compaction |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP064 | YES | W(10%) | R | H
7 | Running Course |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP064 | NO | W(10%) | R | H
8 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP064 | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 12/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## DN-GD-GP065
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Unsealed Road: Laying Metal Using a Tip Truck (or Bottom Dumper) |  |  | DN-GD-GP065 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/SOUTH ROADS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP065 | NO | R | R | H |  |  | W & I | Supplier
2 | Base Preparation |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP065 | NO | R | R | H
3 | Metal Spreading |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP065 | NO | R | R | H
4 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP065 | NO | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 12/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## DN-GD-GP066
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Unsealed Roads-Construct an Unsealed Pavement |  |  | DN-GD-GP066 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/SOUTH ROADS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP066 | NO | R | R | H |  |  | W & I | Supplier
2 | Base Preparation |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP066 | NO | R | R | H
3 | Metal Spreading |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP066 | NO | W(10%) | R | H
4 | Moisture Content |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP066 | YES | W(10%) | R | H
5 | Compaction |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP066 | YES | W(10%) | R | H
6 | Running Course |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP066 | YES | W(10%) | R | H
7 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP066 | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 12/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## DN-GD-GP081
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Construct a Sandbag Weir |  |  | DN-GD-GP081 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/SOUTH ROADS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare the Site |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP081 | NO | R | R | H |  |  | W & I | Supplier
2 | Setting Out |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP081 | NO | R | R | H
3 | Prepapre Base |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP081 | NO | W(10%) | R | H
4 | Sandbag Filling |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP081 | NO | W(10%) | R | H
5 | Sandbag Placing |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP081 | NO | W(10%) | R | H
6 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP081 | NO | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 12/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## DN-GD-GP083
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Install a Culvert Headwall Constructed of Dry Concrete Sand Bags |  |  | DN-GD-GP083 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/SOUTH ROADS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare the Site |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP083 | NO | R | R | H |  |  | W & I | Supplier
2 | Setting Out |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP083 | NO | R | R | H
3 | Prepare Base |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP083 | NO | W(10%) | R | H
4 | Fill Sandbags |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP083 | NO | W(10%) | R | H
5 | Place Sandbags |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP083 | NO | W(10%) | R | H
6 | Sight Rail |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP083 | NO | W(10%) | R | H
7 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP083 | NO | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 12/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client