## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - CONOC Operations (Heavy and Light Maintenance) - Shallow Pothole Repair in a sealed Pavement - Premixe Method - QPR | itp |  |  |  |  | ITP - CONOC Operations (Heavy and Light Maintenance) - Shallow Pothole Repair in a sealed Pavement - Premixe Method - QPR
checkpoint | 1 - Prepare Hole
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP032
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Filling Hole
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP032
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Blinding
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP032
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP032
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations (Heavy and Light Maintenance) - Deep Pothole Repair in a Sealed Pavement Premix Method | itp |  |  |  |  | ITP - CONOC Operations (Heavy and Light Maintenance) - Deep Pothole Repair in a Sealed Pavement Premix Method
checkpoint | 1 - Prepare Hole
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP033
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Filling Hole
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP033
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Blinding
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP033
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP033
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations (Heavy and Light Maintenance) - Pothole repair using a Broom Road Patch (BRP) | itp |  |  |  |  | ITP - CONOC Operations (Heavy and Light Maintenance) - Pothole repair using a Broom Road Patch (BRP)
checkpoint | 1 - Prepare Hole
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP034
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Apply RS1 Tack Coat Emulsion
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP034
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Attach BRP
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP034
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Blinding
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP034
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP034
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations (Heavy and Light Maintenance) - Adjust a Surface Box - Not a Manhole | itp |  |  |  |  | ITP - CONOC Operations (Heavy and Light Maintenance) - Adjust a Surface Box - Not a Manhole
checkpoint | 1 - Prepare
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP035
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Excavation
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP035
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Replace Risers
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP035
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Backfill around the Riser (Clegg Hammer)
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP035
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Final Shape and Trim
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP035
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Surfacing
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP035
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Surface Cover Painting
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP035
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP035
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations (Heavy and Light Maintenance) - Edgebreak Repair - Formed Shoulder (Manual Premix Method) | itp |  |  |  |  | ITP - CONOC Operations (Heavy and Light Maintenance) - Edgebreak Repair - Formed Shoulder (Manual Premix Method)
checkpoint | 1 - Prepare Site
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP036
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Prepare Shoulder
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP036
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Filling the Edge Break
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP036
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Reconstruction Supporting Shoulder
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP036
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Blinding
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP036
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP036
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair Low Shoulder - Grading | itp |  |  |  |  | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair Low Shoulder - Grading
checkpoint | 1 - Prepare
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP037
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Remove EMP
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP037
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Initial Cut and Grader Steup
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP037
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Final Shape and Trim
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP037
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP037
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair Low Shoulder - Material Replacement | itp |  |  |  |  | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair Low Shoulder - Material Replacement
checkpoint | 1 - Prepare
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP038
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Scarify
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP038
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Spread Makeup Metal
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP038
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Fianl Shape and Trim
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP038
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP038
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair Surface Depression - Hand Premix | itp |  |  |  |  | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair Surface Depression - Hand Premix
checkpoint | 1 - Prepare
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP039
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Application of Blinder (Tack Coat)
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP039
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Spreding Premix Material
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP039
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Final Shape and Trim
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP039
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Blinding
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP039
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP039
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair Surface Depression - Machine Premix Method | itp |  |  |  |  | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair Surface Depression - Machine Premix Method
checkpoint | 1 - Prepare
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP040
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Milling
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP040
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Application of Binder (Tack Coat)
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP040
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Base Levelling
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP040
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Layer Premix Material
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP040
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Final Compaction
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP040
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Blinding
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP040
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP040
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair Surface Depression - Rip and Remake Method | itp |  |  |  |  | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair Surface Depression - Rip and Remake Method
checkpoint | 1 - Prepare
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP042
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Pavement Layer
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP042
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Final Shape and Trim
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP042
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Surfacing
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP042
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP042
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair of Bleeding - Flushing Binder Applying Additional Chip | itp |  |  |  |  | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair of Bleeding - Flushing Binder Applying Additional Chip
checkpoint | 1 - Prepare
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP043
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Solvent Spraying
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP043
label | Records Required - YES
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Chip Application
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP043
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP043
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations (Heavy and Light Maintenance) - Crack Seal Repairs (5-15mm) Reservoir and Overband Methods | itp |  |  |  |  | ITP - CONOC Operations (Heavy and Light Maintenance) - Crack Seal Repairs (5-15mm) Reservoir and Overband Methods
checkpoint | 1 - Materail
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP044
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Weather
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP044
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Preparation
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP044
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Cleaning and Drying
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP044
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Application of Sealer/Filler
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP044
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Finishing
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP044
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP044
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT