## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair of Stripping or Scabbing: Applying Additional Chip | itp |  |  |  |  | ITP - CONOC Operations (Heavy and Light Maintenance) - Repair of Stripping or Scabbing: Applying Additional Chip
checkpoint | 1 - Prepare
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP045
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Solvent and Chip Method
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP045
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Emulsion and Chip Method
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP045
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP045
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations (Heavy and Light Maintenance) - First Coat - Two Coat Chip Seal (Hand Spray Method) | itp |  |  |  |  | ITP - CONOC Operations (Heavy and Light Maintenance) - First Coat - Two Coat Chip Seal (Hand Spray Method)
checkpoint | 1 - Weather
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP047
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Site Preparation
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP047
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Binder Spray - First Coat
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP047
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Spreading Chip first Coat
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP047
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Prepare for Second Coat
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP047
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Second Coat
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP047
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Site Monitoring
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP047
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Sweeping and Marking
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP047
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP047
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations (Heavy and Light Maintenance) - Grading Unsealed Road - Light | itp |  |  |  |  | ITP - CONOC Operations (Heavy and Light Maintenance) - Grading Unsealed Road - Light
checkpoint | 1 - Prepare
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP060
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Grader Operation
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP060
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Grader Set-up
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP060
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Super Elevation on Corners
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP060
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Fisrt Pass
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP060
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Second Pass
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP060
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Third Cutting Pass (Optional depending on width of road)
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP060
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Spreading Pass 1-2
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP060
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Things to Watch for
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP060
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP060
label | Records Required - NO
label | DOWNER ENGINEER - W
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations (Heavy and Light Maintenance) - Grading Unsealed Road - Medium | itp |  |  |  |  | ITP - CONOC Operations (Heavy and Light Maintenance) - Grading Unsealed Road - Medium
checkpoint | 1 - Prepare
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Grader Operation
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Grader Set-up
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Super Elevation on Corners
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - First Pass
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Second Pass
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Cut outs
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Third Pass
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Fourth Pass
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Extra Pass
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Spreading Passes 1-2
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR -
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Issues
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP061
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations (Heavy and Light Maintenance) - Grading Unsealed Road - Heavy | itp |  |  |  |  | ITP - CONOC Operations (Heavy and Light Maintenance) - Grading Unsealed Road - Heavy
checkpoint | 1 - Prepare
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Grader Operation
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Grader Set-up
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - In- process
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Super Elevation on Corners
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - First Pass
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Second Pass
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Cut outs
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Third Pass Grader Set-up
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Fourth Pass
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Extra Pass
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Spreading Passes 1-2
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Compaction
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Issues
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP062
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations (Heavy and Light Maintenance) - Unsealed Pavement - Repair a Pothole | itp |  |  |  |  | ITP - CONOC Operations (Heavy and Light Maintenance) - Unsealed Pavement - Repair a Pothole
checkpoint | 1 - Selecating Patching Material
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP063
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Short Term Repair
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP063
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Long Term Repair
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP063
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP063
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations (Heavy and Light Maintenance) - Unsealed Pavement - Digout Repair | itp |  |  |  |  | ITP - CONOC Operations (Heavy and Light Maintenance) - Unsealed Pavement - Digout Repair
checkpoint | 1 - Prepare
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP064
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Drainage
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP064
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Excavation
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP064
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Filter Fabric
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP064
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Subsoil Drainage
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP064
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Backfill and Compaction
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP064
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Running Course
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP064
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP064
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations (Heavy and Light Maintenance) - Unsealed Road: Laying Metal Using a Tip Truck (or Bottom Dumper) | itp |  |  |  |  | ITP - CONOC Operations (Heavy and Light Maintenance) - Unsealed Road: Laying Metal Using a Tip Truck (or Bottom Dumper)
checkpoint | 1 - Prepare
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP065
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Base Preparation
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP065
label | Records Required - DN-GD-GP065
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Metal Spreading
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP065
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP065
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations (Heavy and Light Maintenance) - Unsealed Roads - Construct an Unsealed Pavement | itp |  |  |  |  | ITP - CONOC Operations (Heavy and Light Maintenance) - Unsealed Roads - Construct an Unsealed Pavement
checkpoint | 1 - Prepare
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP066
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Base Preparation
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP066
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Metal Spreading
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP066
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Moisture Content
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP066
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Compaction
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP066
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Running Course
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP066
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP066
label | Records Required - YES
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations (Heavy and Light Maintenance) - Construct a Sandbag Weir | itp |  |  |  |  | ITP - CONOC Operations (Heavy and Light Maintenance) - Construct a Sandbag Weir
checkpoint | 1 - Prepare the Site
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP081
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Setting Out
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP081
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Prepare Base
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP081
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Sandbag Filling
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP081
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Sandbag Placing
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP081
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP081
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations (Heavy and Light Maintenance) - Install a Culvert Headwall Constructed of Dry Concrete Sand Bags | itp |  |  |  |  | ITP - CONOC Operations (Heavy and Light Maintenance) - Install a Culvert Headwall Constructed of Dry Concrete Sand Bags
checkpoint | 1 - Prepare the Site
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP083
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Setting Out
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP083
label | Records Required - NO
label | DOWNER ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Prepare Base
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP083
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Fill Sandbags
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP083
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Place Sandbags
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP083
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Sight Rail
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP083
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP083
label | Records Required - NO
label | DOWNER ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT