## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Demo Work - Jack Arch Demo |  |  |  |  | Yes | Demo Work - Jack Arch Demo | 3058e558-8f43-4585-ad92-f0e031e1e4cc
checkpoint-status |  |  | checkpoint | Check using latest version of drawings.
label | 02f10cfa-f88a-57e8-add4-61a21975cf2b |  | note | Mark Up - Jack Arch Demo - LG & GF (Including JA on hold).pdf
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Workers signed the following:
label | 5485249c-300a-5be7-9ce7-a024f3ae664b |  | note | SWMS (Simpli)
label | 976f491e-0d39-58b6-afd3-e15ae6d4c1fd |  | note | Methodology
label | b6d26c0c-14fd-5fef-b6d0-9c1ecf2ebec1 |  | note | Workers positively communicated loading limits of floors
label | 63f6259d-1de5-5b55-af86-9327771ac228 |  | note | Workers positively communicated loading elements that need protecting
label | 2ecb8aa2-53e9-5c90-bf78-5c0f36a6bcf6 |  | note | Management Plans
label | 787176fe-d3b8-561d-a860-5366fb369aad |  | note | Manual Handling SOP
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Equipment Test and Tag
checkpoint-status |  |  | checkpoint | FFE Tagged
checkpoint-status |  |  | checkpoint | Mobile Scaffold has been built to manufacturer spec and has appropriate handrail and access ladder;
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Plywood protection installed on floors and is stable
checkpoint-status |  |  | checkpoint | Heritage elements and walls protected by vertical plywood is suitable
checkpoint-status |  |  | checkpoint | Vibration Monitors in-place
checkpoint-status |  |  | checkpoint | Air Monitors in-place
checkpoint-status |  |  | checkpoint | Exclusion Zones Setup with Hard Barriers and Signage
checkpoint-status |  |  | checkpoint | Ventilation is adequate and as per methodology;
checkpoint-status |  |  | checkpoint | Light is adequate
checkpoint-status |  |  | checkpoint | Plastic bubble installed is adequate
checkpoint-status |  |  | checkpoint | BOH material excavation material bench level.
checkpoint-status |  |  | checkpoint | Bench is suitably constructed
checkpoint-status |  |  | checkpoint | Sawcuts at 450mm depth at a time along marked Set Out 100mm from wall (first half of wall);
checkpoint-status |  |  | checkpoint | Footing trimmed down to 450 level.
checkpoint-status |  |  | checkpoint | Additional Sawcut for second drop to req.
text | e057ff64-00d9-5496-aebc-9fa10d990130 |  | textbox | Trimmed Height
checkpoint-status |  |  | checkpoint | Footing trimmed down to req. level.
checkpoint-status |  |  | checkpoint | Client to verify extent of demolition is complete as per scope
holdpoint |  |  | signoff | Signed by Delta Group & Built
checklist-sectioned |  |  | checklist | ITP003 - Hoist Base |  |  |  |  | Yes | ITP003 - Hoist Base | 4ce2cb4f-eb70-4be0-a6cc-272d8b455430
checkpoint-group |  |  | section | Pre-Construction
checkpoint-status |  |  | checkpoint | Structural & Architectural Drawings: Issued for Construction (IFC) Drawings
label | 3c6b8339-6672-55ba-a942-23f744c63f8b |  | note | 191482-TTW-SK-S-03-A- Hoist Base Footing
label | 458ff95b-a8d6-5509-b1f8-f970101275f6 |  | note | Hoist Pit Excavation_HW_2.12.21
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Concrete Mix Design - Approved: Concrete mix design submitted to & approved by Design Engineer (Taylor Thomson Whitting).
text | ada3f8f3-6d72-55a9-b8ee-9977b317f2d1 |  | textbox | Approved Mix Design
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Surveyor set out in accordance with above IFC drawings:
text | 5815fbdf-e4d4-5914-91b6-3f9f4563c91c |  | textbox | Top of Concrete:
text | f12404e7-e8b4-59ee-971c-a1af9894c0aa |  | textbox | Footing Depth:
text | 0f80f406-990d-532d-9288-41c853524e02 |  | textbox | Blinding:
text | fe437af6-f7eb-5a49-87a1-3a71c78104b7 |  | textbox | Excavation RL:
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Base to be socketed into min 1,500 kPa sandstone for lateral. Bearing pressure of sandstone assumed to be min. 1500 kPa.
text | 17b8a2b5-3572-5757-978c-0b7005b17f91 |  | textbox | Depth of Test:
text | b3c9a1d1-86bd-5018-a7a7-b957371c59bc |  | textbox | Assessment:
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Surveyor to provide as-built survey confirming extent of excavation prior to reinforcement.
text | 8d7b3f8e-1ea6-5fa0-ba98-f19b819e7e19 |  | textbox | Depth of Excavation:
text | 7f332398-16f4-52b1-b5b2-026478715729 |  | textbox | Excavation Extent Achieved:
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Blinding Layer of concrete to be installed at base of excavation.
text | 7bd6d55e-9eab-5c51-98e7-29c6b4095c1a |  | textbox | Blinding Strength & Thickness:
text | a41fc952-73e2-5135-b520-b798833928be |  | textbox | Top of Blinding RL:
checkpoint-group |  |  | section | Formwork, Reinforcement & Concrete Pour
checkpoint-status |  |  | checkpoint | Sacrificial ply (& timber where required) shutters to be installed prior to concrete pour
checkpoint-status |  |  | checkpoint | Reinforcement reviewed against drawings & confirmed correct quantity, diameter & dimensions of bars have been provided:
checkpoint-status |  |  | checkpoint | Footing reinforcement has been installed as per IFC drawings:
label | a3b5cb1b-8722-589d-993e-e10a7ef4cac9 |  | note | Reinforcement Details:
text | 4b7bc946-7bf9-5196-b336-99d80948cc7c |  | textbox | Bar Qty & Dia:
text | 5e7f5dfa-8ed1-5351-a890-15207699357e |  | textbox | Main Bar Dimensions:
text | 5e964450-8982-55cd-97bf-0d1e4da0778f |  | textbox | Side Bar Dimensions:
text | 9c51591a-9658-5ad8-9401-323f65d9be36 |  | textbox | Lap/Cog Lengths:
text | 1f3d99e5-04c3-52b9-a1b8-4826f500cf18 |  | textbox | Bar Chairs:
text | e45499a7-0016-521a-a41d-f1f2cf243d03 |  | textbox | Concrete Cover:
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Delivered Concrete Mix as per approved Mix Design.
checkpoint-status |  |  | checkpoint | Concrete Samples taken as per AS 1379.
checkpoint-status |  |  | checkpoint | Concrete Strength testing as per AS1012.1.
text | 7a7f3e19-c061-5a62-9bed-6b990c9283b5 |  | textbox | Test Results MPa @ & Days
checkpoint-status |  |  | checkpoint | Concrete installed within tolerance ±10mm.
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Surveyor to provide As built confirming final dimensions & location of foundation structure.
holdpoint |  |  | signoff | Signed by Delta Group & Built
checklist-sectioned |  |  | checklist | ITP007 - Demolition - Lift 1 & 2 |  |  |  |  | Yes | ITP007 - Demolition - Lift 1 & 2 | 5e451321-1a1a-4391-8f64-f49ae8c4c081
checkpoint-group |  |  | section | Pre-Works – Documentation
checkpoint-status |  |  | checkpoint | Architectural Drawings: Issued for Construction (IFC) Drawings:
label | 8ebac0a0-e3f1-596d-863c-9d09a3ad8847 |  | note | SP-L-A-03xx-REV-X – Demolition Plans
label | 6c5a1a50-343e-5081-81d9-206808fc2fba |  | note | SP-L-A-050x-REV-X – Soft Strip Plans
label | 12e6d92d-8c17-5c9f-9292-a3af0dc493d7 |  | note | SP-L-A-032x-REV-X – Demolition Reflected Ceiling Plans
label | 546e1242-a443-528f-b7ef-e6bd6f15d08d |  | note | SP-L-A-034x-REV-X – Demolition Elevations
label | a0323f1d-b1bd-5c9b-b6f9-16821262cd81 |  | note | SP-L-A-036x-REV-X – Demolition Details
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Structural Drawings: Issued for Construction (IFC) Drawings:
label | aa071278-f914-5a2e-a537-1a76d15abfb6 |  | note | SP-L-ST-2xx1 [X] – Level – Temporary Works & Demolition Plans
label | 26466828-b822-5fc1-aaae-0ba60ca8f840 |  | note | SP-L-ST-290x [X] – Demolition Elevations
label | 3b1e133b-a1b9-51d0-84e4-bbf978aad97d |  | note | SP-L-ST-295x [X] – Temporary Works & Demolition Details
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Architectural Schedule: Strip out works to be completed in accordance with the Heritage Architects heritage strip out schedule:
label | 3a565d3b-3960-52ca-80ce-de205a760c0f |  | note | 20211117 - SP-L-HA-8001-REV-B - Heritage Strip Out Schedule
checkpoint-group |  |  | section | Completion of Works – Strip Out & Demolition
checkpoint-status |  |  | checkpoint | Soft Strip out works have been completed in line with Soft Demolition / Strip extents & Notes on architectural drawings:
label | 6b3f52fb-698a-57a0-a26c-9291ef075073 |  | note | Refer to Appendix A below for specific items.
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Demolition works have been completed in accordance with Architectural & Structural Demolition Drawings & Notes:
label | 37da2821-3fc5-51b6-9edb-23636849a384 |  | note | Refer to Appendix B below for specific items
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Soft Strip out works have been completed in line with Heritage Strip Out Schedule.
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-group |  |  | section | Completion of Works – Permanent Openings
checkpoint-status |  |  | checkpoint | Permanent openings have been set out by a surveyor in line with the architectural demolition set out drawings:
label | 97f6afcd-1a9d-559d-b527-bff4a8f9a028 |  | note | SP-L-A-0360 [A*] – Lower Ground Detail Demolition
label | d0f86e24-064d-52aa-b814-6f3b2f08acc1 |  | note | SP-L-A-0365 [A*] – Level 03 Detail Demolition
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Set out dimensions as follows:
label | 314ac893-c257-57c1-b78d-9a017181924c |  | note | Western Opening:
text | 659f86c3-d9ad-505c-83ae-da453f13acee |  | textbox | Width:
text | 0bd9ceae-de32-5930-9f7b-bb5938417367 |  | textbox | Height:
text | 6e941501-82bf-5481-b7db-911ba025d143 |  | textbox | Grid offset / Location:
label | be7c1f3f-6244-5573-93f4-0e8b6511d611 |  | note | Eastern Opening:
text | c6e235ac-35ec-5060-9b10-f5ff13f221f6 |  | textbox | Width:
text | 046bab74-3a78-54a7-a12c-e9b7b61f6f47 |  | textbox | Height:
text | f39402de-05be-5244-820f-db4fb4dd4838 |  | textbox | Grid offset / Location:
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Temporary Works as documented within Methodology have been installed & certified by relevant Engineer:
label | 16293118-5c30-547b-9694-df7db8a0978f |  | note | 2 x 100 PFC Spreaders clamped to wall:
label | 9d47d6ea-2ad7-591b-9384-605862a81c0c |  | note | PFC Length: 600mm
label | 88af83d1-76c3-560e-bdec-06881ca6ce9b |  | note | 3 x M16 Through-bolts & HILTI HIT HY 170
label | ad7e8765-36cd-5c5a-a3ca-bd1b0f7d1ae0 |  | note | Plate bridges across opening infill
label | d0d754a5-edaf-5819-a4c4-6b5107a115e6 |  | note | 20 kN Push-Pull Prop Installed
label | 69e6b246-9768-5308-8117-22442efe0fc7 |  | note | 1 x M20 + HIT 170 Epoxy Fixing into Floor
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Temporary Lintels have been installed as per relevant temporary works plan / methodology:
label | 5c8b77b9-ee59-56eb-9009-90704d3859c1 |  | note | N1-421 - Lands - Demolition Methodology - Rev.14 - Lifts 1 & 2
label | 2207c28e-a126-599f-a042-f75cab845dcb |  | note | Lintel Member: 100 x 100 x 10 EA Each side
label | e98050cc-9b26-508e-8b50-4c90517ee3e3 |  | note | Bearing: 150 mm Each End
label | 66b5037b-62c5-50db-b554-81a8340251b6 |  | note | 20 MPa Grout installed on bearing surfaces
label | 7f9901fc-25d5-5306-81e0-983fdc35cfd9 |  | note | M16 Anchors + HILTI HIT HY 170 @ 500 mm c/c
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Temporary Lintel installation has been certified by 3rd Party Structural Engineer (TWES).
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Permanent Lintels have been installed as per Structural Drawings:
label | bbb7f03b-8e87-5390-a054-88202de1b14b |  | note | SP-L-A-ST-2906 [C] – Demolition Elevations – Sheet 6 – Section L
label | 132402cf-9cb9-56a2-86db-8de8e141cbf3 |  | note | Lintel: 110 x 170 Ultra Lintel (Qty: 3 per opening)
label | 27f46f6c-6c4e-570a-8aeb-7f36bba859ed |  | note | Bearing: 150 mm Each End
label | c09c8d7d-060a-560c-979d-faa2dead10fc |  | note | Rough surface facing up
label | bd253b10-bed5-5fab-8b3e-b3e858313dbb |  | note | 20 MPa Grout installed on bearing surfaces
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Permanent Lintel installation has been certified by Permanent Works Structural Engineer (TTW).
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Permanent Openings have been demolished in line with Architectural Demolition Drawings:
label | 702435d3-c687-5828-a7e2-a8a5cca6d052 |  | note | SP-L-A-0360 [A*] – Lower Ground Detail Demolition
label | 4d1ed22e-45c4-5588-a747-feb28a0a636b |  | note | SP-L-A-0365 [A*] – Level 03 Detail Demolition
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Opening Extents as measured:
label | c2d6cee5-0dfa-5eec-93ec-fc8e12f7819c |  | note | Western Opening:
text | 64280510-6ab8-5afc-aa82-b521e9a056a7 |  | textbox | Width:
text | 5808ac4e-f3fd-574a-a006-02065166a0a9 |  | textbox | Height:
text | 523483ca-bbeb-59b1-8c52-fc84ac0d2e02 |  | textbox | Grid offset / Location:
label | 9b7d6ab9-fecc-50ae-85a1-addeaf916323 |  | note | Eastern Opening:
text | e0e62ec8-8941-5a00-8918-a06062b9b223 |  | textbox | Width:
text | ccc43880-400d-55aa-8532-97dddb2f8e7b |  | textbox | Height:
text | fd247602-a615-5400-b67b-27b594e608cd |  | textbox | Grid offset / Location:
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Temporary Lintels have been removed, and masonry slots patched with 20 MPa non-shrink grout.
checkpoint-group |  |  | section | Reference: SP-L-A-050x-REV-X – Soft Strip Plans
checkpoint-status |  |  | checkpoint | Remove all built-in cabinetry including within kitchens and bathrooms
checkpoint-status |  |  | checkpoint | Terminate and cap supply, remove non-historic building services and surface mounted conduit (e.G. Fan coil units and associated plinths, lighting, mechanical air conditioning and gas outlets)
checkpoint-status |  |  | checkpoint | Remove all power, data and light switches (floor, skirting and wall mounted) including casing, surface mounted wires, and conduits.
checkpoint-status |  |  | checkpoint | Terminate and cap off all non-historic essential services and surface mounted conduits or pipework (eg fire sprinklers, ewis speakers, smoke detectors etc)
checkpoint-status |  |  | checkpoint | Remove all wall mounted shelving, pin boards, signage, wall brackets and name plates, including fixings, wall plugs, hook etc
checkpoint-status |  |  | checkpoint | Remove all non-structural modern timber or metal stud framed and lined partitions
checkpoint-status |  |  | checkpoint | Remove non-structural, modern timber or metal stud framed and lined infill to existing internal openings including to fireplaces
checkpoint-status |  |  | checkpoint | Remove modern window coverings, blinds, tracks, pelmets and operators
checkpoint-status |  |  | checkpoint | Remove all non-original lowered ceilings and associated framework, battening or support structure.
checkpoint-status |  |  | checkpoint | Remove all non-original floor finishes including carpet, vinyl over original substrate - marble tiles/timber floorboards.
checkpoint-status |  |  | checkpoint | Remove miscellaneous or room specific item - refer table
checkpoint-status |  |  | checkpoint | Significant items to be retained and protected in existing location - refer schedule
checkpoint-status |  |  | checkpoint | Remove plant access walkways
checkpoint-status |  |  | checkpoint | Remove bird proofing and associated adhesives
checkpoint-group |  |  | section | Reference: SP-L-A-03xx-REV-X – Demolition Plans
checkpoint-status |  |  | checkpoint | Carefully remove roof and associated structure
checkpoint-status |  |  | checkpoint | Create opening in slab for new lift core/stair
checkpoint-status |  |  | checkpoint | Carefully demolish full or part slab/floor structure, including fill
checkpoint-status |  |  | checkpoint | Carefully remove jack arch - refer to structural engineer's documentation.
checkpoint-status |  |  | checkpoint | Carefully demolish wall or part wall.
checkpoint-status |  |  | checkpoint | Carefully demolish contemporary door set. Resell, recycle or dispose according to salvage methodology
checkpoint-status |  |  | checkpoint | Carefully remove contemporary window set. Resell, recycle or dispose according to salvage methodology
checkpoint-status |  |  | checkpoint | Carefully remove window glazing only.
checkpoint-status |  |  | checkpoint | Carefully remove ceiling or part ceiling
checkpoint-status |  |  | checkpoint | Carefully remove stair/core
checkpoint-status |  |  | checkpoint | Create new opening in existing wall - lintel to structural engineer documentation.
checkpoint-status |  |  | checkpoint | Create opening for new structure.
checkpoint-status |  |  | checkpoint | Create opening for new fire services.
checkpoint-status |  |  | checkpoint | Carefully remove amenities and associated non-original floor/joinery.
checkpoint-status |  |  | checkpoint | Carefully demolish external amenity blocks and associated structure.
checkpoint-status |  |  | checkpoint | Carefully remove redundant modern services, grilles and accessories.
checkpoint-status |  |  | checkpoint | Carefully demolish modern skylights.
checkpoint-status |  |  | checkpoint | Carefully remove mezzanine and associated structure.
checkpoint-status |  |  | checkpoint | Carefully remove lathe & plaster ceiling.
checkpoint-status |  |  | checkpoint | Demolish structural column - refer to structural engineer's documentation.
checkpoint-status |  |  | checkpoint | Carefully remove all exposed contemporary services from courtyard windows and elevations.
checkpoint-status |  |  | checkpoint | Carefully remove existing cast iron gantries.
checklist-sectioned |  |  | checklist | ITP009 - Demolition - Access Hatch Openings |  |  |  |  | Yes | ITP009 - Demolition - Access Hatch Openings | 755e5b45-7030-4284-b318-93862a1f3ac6
checkpoint-group |  |  | section | Pre-Works – Documentation
checkpoint-status |  |  | checkpoint | Architectural Drawings: Issued for Construction (IFC) Drawings:
label | 707fdad9-12b4-597b-bfff-cec7ef9e1065 |  | note | SP-L-A-03xx-REV-X – Demolition Plans
label | a966e55a-2b99-53ac-8fe6-76701ed1e2b7 |  | note | SP-L-A-036x-REV-X – Demolition Details
label | b4774e9e-ce5c-55ed-9e11-1cc732da06c6 |  | note | 20220618 - Lands - BUILT - Revised Access Hatch Locations - Phase 1.pdf
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Structural Drawings: Issued for Construction (IFC) Drawings:
label | acf85497-3cd6-570a-8d06-2f2f68417b41 |  | note | SP-L-ST-2xx1 [X] – Level xx – Temporary Works & Demolition Plans
label | 0e999c97-2a0c-5666-9c10-0e2c0ddad10c |  | note | SP-L-ST-295x [X] – Temporary Works & Demolition Details
label | f6d61e90-d20c-5d69-a962-59b15fb93a34 |  | note | SP-L-ST-6211 [X] – TYPICAL CORRIDOR VOID TIE DETAILS
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-group |  |  | section | Completion of Works – Permanent Openings
checkpoint-status |  |  | checkpoint | Permanent openings have been set out by Built.
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Structural Wall Ties have been installed where required:
label | 70839426-e587-5072-8e74-91473625a62d |  | note | SP-L-ST-6211 [D] – TYPICAL CORRIDOR VOID TIE DETAILS
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Permanent openings have been created by completing the nominated core hole detail.
text | e1cf8e3b-a2a2-522e-bf80-81a3b84d5c66 |  | textbox | Core Hole Diameter:
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Permanent openings have been made safe by installation of an engineer approved penetration cover:
label | f856ff40-449e-56de-9fec-0e9e909930fd |  | note | Install 20 mm Ply Cover
label | a0ee2b68-e119-5975-af99-d73445626e83 |  | note | Re-install Built Floor Protection Ply & Penetration Signage
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Installation of Phase 1 Permanent Openings have been completed for the nominated work area:
label | 49d9cfba-5b18-581c-abec-a137b33355cd |  | note | Refer Appendix A
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Wall Ties Installed
text | cd0a5143-c109-5cac-83cb-a5a4ea59ed82 |  | textbox | Core Hole Diameter
checkpoint-status |  |  | checkpoint | Penetration Cover Installed
checklist-sectioned |  |  | checklist | ITP003 - Civil Works- Shafts |  |  |  |  | Yes | ITP003 - Civil Works- Shafts | 7be0f6ec-a8e8-49a2-8bd0-e2bb4acd47b5
checkpoint-group |  |  | section | Pre-Excavation
checkpoint-status |  |  | checkpoint | Check using latest version of drawings.
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Workers to sign on the following:
label | 475ca1c8-9efd-5d17-bb5c-12bd16b749d6 |  | note | SWMS (Simpli)
label | b124a1a2-5a5f-5736-a068-3d586711b4d5 |  | note | Methodology
label | e2f116ca-01fd-581c-978d-cbaeea740f2d |  | note | Management Plans
label | c707ae05-8941-5459-a649-9c1cdbaa6b25 |  | note | Plant Inducted
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Exclusion Zones Setup with Hard Barriers and Signage
checkpoint-status |  |  | checkpoint | Air exhaust installed
checkpoint-status |  |  | checkpoint | Lights installed
checkpoint-status |  |  | checkpoint | Dust suppression in-place including plumbing to rock saw
checkpoint-status |  |  | checkpoint | Vibration Monitors in-place
checkpoint-status |  |  | checkpoint | Air Monitors in-place
checkpoint-status |  |  | checkpoint | Surveyor set out levels and offsets in accordance to latest drawings.
checkpoint-status |  |  | checkpoint | Plant Pre-start Complete
checkpoint-status |  |  | checkpoint | Equipment Test and Tag
checkpoint-status |  |  | checkpoint | FFE Tagged
checkpoint-status |  |  | checkpoint | Inspect saw.
checkpoint-status |  |  | checkpoint | Environmental Controls in place as per methodology
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-group |  |  | section | Excavation
checkpoint-status |  |  | checkpoint | Sawcut 450mm depth
checkpoint-status |  |  | checkpoint | Excavate to sawcut level and level checked
checkpoint-status |  |  | checkpoint | Excavation shall be completed to the depth and profile shown on the drawings. (First drop 750mm)
checkpoint-status |  |  | checkpoint | Additional sawcutting for final depth
text | f942228e-d79c-5ba6-918b-8f5b9f769efe |  | textbox | Final excavation RL as per drawings
text | 013039f9-7713-500e-874b-621465903869 |  | textbox | Surveyed final RL
checkpoint-status |  |  | checkpoint | Site ensure site is free from trip hazards.
checkpoint-status |  |  | checkpoint | Exclusion zones are maintained and secure.
checkpoint-status |  |  | checkpoint | Geotech Engineer to inspect cut face at each interface to provide advice.
checkpoint-status |  |  | checkpoint | Sign-off received on works.
checkpoint-status |  |  | checkpoint | As-built issued and works closed out
holdpoint |  |  | signoff | Signed by Delta Group & Built
checklist-sectioned |  |  | checklist | ITP002 - Strip Out |  |  |  |  | Yes | ITP002 - Strip Out | 88f649b8-c80d-4c95-b75b-dcde835fd2b1
checkpoint-group |  |  | section | Pre-Works
checkpoint-status |  |  | checkpoint | Architectural Drawings: Issued for Construction (IFC) Drawings:
label | fe7e6fe4-667d-5cfd-982f-0784e713daa7 |  | note | SP-L-A-0502-REV-A – Soft Strip Plans – Lower Ground Floor
label | e41f3286-2bab-55b7-8479-ec9f000581a8 |  | note | SP-L-A-0503-REV-A – Soft Strip Plans – Lower Ground Mezzanine
label | c596cadf-4e84-5074-93c4-b8b7c61276fb |  | note | SP-L-A-0504-REV-A – Soft Strip Plans – Ground Floor
label | 1c81426f-2d5d-5783-b8a2-f3ca98cff9c5 |  | note | SP-L-A-0505-REV-A – Soft Strip Plans – Level 01
label | 32e9c9dc-c4e3-5278-9a8f-c3156b34d22e |  | note | SP-L-A-0506-REV-A – Soft Strip Plans – Level 02
label | 3c391e33-313e-5038-99a6-83171565cf5c |  | note | SP-L-A-0507-REV-A – Soft Strip Plans – Level 03
label | c0eab496-7238-55bf-93ab-b4664247c90e |  | note | SP-L-A-0508-REV-A – Soft Strip Plans – Level 04
label | e4a87a53-86d3-56df-9cc6-3c0db920da3d |  | note | SP-L-A-0509-REV-A – Soft Strip Plans – Level 05 + Level 06
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Architectural Schedule: Strip out works to be completed in accordance with the Heritage Architects heritage strip out schedule:
label | 2738c076-8015-59d7-a67e-5c56d3befe68 |  | note | 20211117 - SP-L-HA-8001-REV-B - Heritage Strip Out Schedule
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-group |  |  | section | Completion of Works
checkpoint-status |  |  | checkpoint | Strip out works have been completed in line with extents as per reference drawings:
label | 9dacd959-be08-50fa-9f86-ad739ac589ea |  | note | Lightweight partitions/modern fabric to be demolished/removed.
label | f7c37b55-1a63-5a2a-8b7b-83219ae3feba |  | note | Lighting to be removed – refer schedule.
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Soft Strip out works have been completed in line with Soft Demolition / Strip Notes on architectural drawings:
label | 0f8572a7-808d-5503-9b66-658fc9f8b634 |  | note | Refer to Appendix A below for specific items.
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Soft Strip out works have been completed in line with Heritage Strip Out Schedule:
label | f260760a-d50a-5ab7-a8d0-34f403cff3fc |  | note | Refer to Appendix B below for specific items.
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-group |  |  | section | Reference: SP-L-A-0502-REV-A – Soft Strip Plans – Lower Ground Floor
checkpoint-status |  |  | checkpoint | Remove all built-in cabinetry including within kitchens and bathrooms
checkpoint-status |  |  | checkpoint | Terminate and cap supply, remove non-historic building services and surface mounted conduit (e.G. Fan coil units and associated plinths, lighting, mechanical air conditioning and gas outlets)
checkpoint-status |  |  | checkpoint | Remove all power, data and light switches (floor, skirting and wall mounted) including casing, surface mounted wires, and conduits.
checkpoint-status |  |  | checkpoint | Terminate and cap off all non-historic essential services and surface mounted conduits or pipework (eg fire sprinklers, ewis speakers, smoke detectors etc)
checkpoint-status |  |  | checkpoint | Remove all wall mounted shelving, pin boards, signage, wall brackets and name plates, including fixings, wall plugs, hook etc
checkpoint-status |  |  | checkpoint | Remove all non-structural modern timber or metal stud framed and lined partitions
checkpoint-status |  |  | checkpoint | Remove non-structural, modern timber or metal stud framed and lined infill to existing internal openings including to fireplaces
checkpoint-status |  |  | checkpoint | Remove modern window coverings, blinds, tracks, pelmets and operators
checkpoint-status |  |  | checkpoint | Remove all non-original lowered ceilings and associated framework, battening or support structure.
checkpoint-status |  |  | checkpoint | Remove all non-original floor finishes including carpet, vinyl over original substrate - marble tiles/timber floorboards. Note: carpet to some rooms had been removed prior to inspection
checkpoint-status |  |  | checkpoint | Remove miscellaneous or room specific item - refer table
checkpoint-status |  |  | checkpoint | Significant items to be retained and protected in existing location - refer schedule
checkpoint-status |  |  | checkpoint | Remove plant access walkways
checkpoint-status |  |  | checkpoint | Remove bird proofing and associated adhesives
checklist-sectioned |  |  | checklist | ITP006 - Completion of Works |  |  |  |  | Yes | ITP006 - Completion of Works | d0951048-6e17-4aad-a9c8-1242604a759c
checkpoint-group |  |  | section | Pre-Works – Documentation
checkpoint-status |  |  | checkpoint | Architectural Drawings: Issued for Construction (IFC) Drawings:
label | 23409c8f-429e-55cd-9a4a-779c98e071ff |  | note | SP-L-A-03xx-REV-X – Demolition Plans
label | ac9ad8d5-be69-54bc-9c48-72c2780c769e |  | note | SP-L-A-050x-REV-X – Soft Strip Plans
label | 3c2a83d1-67bd-5c7a-adee-4548d342b43d |  | note | SP-L-A-032x-REV-X – Demolition Reflected Ceiling Plans
label | 9d46ac9d-88b3-5390-8e20-a2d2d60d7f94 |  | note | SP-L-A-034x-REV-X – Demolition Elevations
label | 66fc4fcc-6de1-587c-8d26-a3adb9396a53 |  | note | SP-L-A-036x-REV-X – Demolition Details
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Architectural Schedule: Strip out works to be completed in accordance with the Heritage Architects heritage strip out schedule:
label | 6e68182b-9463-5ad6-b28b-1dd3f91859a6 |  | note | 20211117 - SP-L-HA-8001-REV-B - Heritage Strip Out Schedule
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Structural Drawings: Issued for Construction (IFC) Drawings:
label | cca08b91-bbdc-5f45-bbd1-a3d26ab5765a |  | note | SP-L-ST-2xx1 [X] – Level – Temporary Works & Demolition Plans
label | 4093aef4-cf4d-583b-b0a5-d4fd40fc4eac |  | note | SP-L-ST-290x [X] – Demolition Elevations
label | 0e9a8f2c-f5f8-5c38-88d4-c588563ce96f |  | note | SP-L-ST-295x [X] – Temporary Works & Demolition Details
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Hazmat Register: Hazmat Register & Destructive Hazmat Surveys available & reviewed
label | 8979dc5a-c9b7-57a6-a3d6-7f459ceb46cb |  | note | PRA HAZMAT Matrix 20211203
label | d8a56885-4887-518f-9942-79d2dd2cf1aa |  | note | PRJ000737_HBSA001_DoL_L4-6_2021_10_12_V1
label | a9f4888f-adc4-5573-a16f-965c9b07b7ae |  | note | PRJ000737_HBSA002_DoL_L3_2021_10_15_V1
label | e562d0ec-85f4-5d5e-a46b-d750442563eb |  | note | PRJ000737_HBSA003_DoL_Level_2_2021_11_01_V2
label | 8fed7ba3-c17d-57b8-9f11-d0fa72855804 |  | note | PRJ000737_HBSA004_DoL_Level_1_2021_11_06_V2
label | 1aaebc7f-25a0-53e9-9298-3b69e3ef5571 |  | note | PRJ000737_HBSA005_DoL_GroundFloor_2021_11_01_V1
label | 8e094cea-41d5-5ee1-a07e-0e48b1456fa1 |  | note | PRJ000737_HBSA006_DoL_LowerGroundFloor_2021_11_01_V1
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-group |  |  | section | Completion of Works – Hazmat
checkpoint-status |  |  | checkpoint | Identified Hazmat has been removed / remediated as per recommendations within Hazmat Surveys:
label | e0b5cfea-8576-5f91-9cca-77f2b8f16543 |  | note | Air Monitoring Reports
label | 59bcd1a9-22de-5240-ae56-a45897fde237 |  | note | Clearance Certificates
label | 00d8be3d-f91b-533e-8593-11472c906bf4 |  | note | Clearance Limitations – Noted
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-group |  |  | section | Completion of Works – Strip Out
checkpoint-status |  |  | checkpoint | Strip out works have been completed in line with extents as per reference drawings above.
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Soft Strip out works have been completed in line with Soft Demolition / Strip Notes on architectural drawings:
label | 4f979b07-a114-5283-b296-e850ef08f857 |  | note | Refer to Appendix A below for specific items.
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Soft Strip out works have been completed in line with Heritage Strip Out Schedule.
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-group |  |  | section | Completion of Works – Demolition
checkpoint-status |  |  | checkpoint | Demolition works have been completed in line with extents as per reference drawings above.
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Demolition works have been completed in accordance with the demolition notes on architectural Demolition Drawings:
label | 22e1c033-4662-55f9-8321-15ad365de567 |  | note | Refer to Appendix B below for specific items
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-group |  |  | section | Completion of Works – Scope Specific / Other
checkpoint-status |  |  | checkpoint | Works within the area have been completed in line with Scope of Works & any other contract documentation:
label | a4235f6b-a8d5-5554-a2d9-1d1b517a19da |  | note | Refer to Scope of Works
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-group |  |  | section | Reference: SP-L-A-050x-REV-X – Soft Strip Plans
checkpoint-status |  |  | checkpoint | Remove All Built-In Cabinetry Including Within Kitchens & Bathrooms
checkpoint-status |  |  | checkpoint | Terminate and cap supply, remove non-historic building services and surface mounted conduit (e.G. Fan coil units and associated plinths, lighting, mechanical air conditioning and gas outlets)
checkpoint-status |  |  | checkpoint | Remove all power, data and light switches (floor, skirting and wall mounted) including casing, surface mounted wires, and conduits.
checkpoint-status |  |  | checkpoint | Terminate and cap off all non-historic essential services and surface mounted conduits or pipework (eg fire sprinklers, ewis speakers, smoke detectors etc)
checkpoint-status |  |  | checkpoint | Remove all wall mounted shelving, pin boards, signage, wall brackets and name plates, including fixings, wall plugs, hook etc
checkpoint-status |  |  | checkpoint | Remove all non-structural modern timber or metal stud framed and lined partitions
checkpoint-status |  |  | checkpoint | Remove non-structural, modern timber or metal stud framed and lined infill to existing internal openings including to fireplaces
checkpoint-status |  |  | checkpoint | Remove modern window coverings, blinds, tracks, pelmets and operators
checkpoint-status |  |  | checkpoint | Remove all non-original lowered ceilings and associated framework, battening or support structure.
checkpoint-status |  |  | checkpoint | Remove all non-original floor finishes including carpet, vinyl over original substrate - marble tiles/timber floorboards.
checkpoint-status |  |  | checkpoint | Remove miscellaneous or room specific item - refer table
checkpoint-status |  |  | checkpoint | Significant items to be retained and protected in existing location - refer schedule
checkpoint-status |  |  | checkpoint | Remove plant access walkways
checkpoint-status |  |  | checkpoint | Remove bird proofing and associated adhesives
checkpoint-group |  |  | section | Reference: SP-L-A-03xx-REV-X – Demolition Plans
checkpoint-status |  |  | checkpoint | Carefully remove roof and associated structure
checkpoint-status |  |  | checkpoint | Create opening in slab for new lift core/stair
checkpoint-status |  |  | checkpoint | Carefully demolish full or part slab/floor structure, including fill
checkpoint-status |  |  | checkpoint | Carefully remove jack arch - refer to structural engineer's documentation.
checkpoint-status |  |  | checkpoint | Carefully demolish wall or part wall.
checkpoint-status |  |  | checkpoint | Carefully demolish contemporary door set. Resell, recycle or dispose according to salvage methodology
checkpoint-status |  |  | checkpoint | Carefully remove contemporary window set. Resell, recycle or dispose according to salvage methodology
checkpoint-status |  |  | checkpoint | Carefully remove window glazing only.
checkpoint-status |  |  | checkpoint | Carefully remove ceiling or part ceiling
checkpoint-status |  |  | checkpoint | Carefully remove stair/core
checkpoint-status |  |  | checkpoint | Create new opening in existing wall - lintel to structural engineer documentation.
checkpoint-status |  |  | checkpoint | Create opening for new structure.
checkpoint-status |  |  | checkpoint | Create opening for new fire services.
checkpoint-status |  |  | checkpoint | Carefully remove amenities and associated non-original floor/joinery.
checkpoint-status |  |  | checkpoint | Carefully demolish external amenity blocks and associated structure.
checkpoint-status |  |  | checkpoint | Carefully remove redundant modern services, grilles and accessories.
checkpoint-status |  |  | checkpoint | Carefully demolish modern skylights.
checkpoint-status |  |  | checkpoint | Carefully remove mezzanine and associated structure.
checkpoint-status |  |  | checkpoint | Carefully remove lathe & plaster ceiling.
checkpoint-status |  |  | checkpoint | Demolish structural column - refer to structural engineer's documentation.
checkpoint-status |  |  | checkpoint | Carefully remove all exposed contemporary services from courtyard windows and elevations.
checkpoint-status |  |  | checkpoint | Carefully remove existing cast iron gantries.
checklist-sectioned |  |  | checklist | ITP001 - Civil Works - Footing Trimming |  |  |  |  | Yes | ITP001 - Civil Works - Footing Trimming | ee6a9cc1-f2cc-4f7a-a215-ebf133518273
checkpoint-group |  |  | section | Prior to Starting Footing Trimming
checkpoint-status |  |  | checkpoint | Check using latest version of drawings.
label | 18eaf837-b2ef-502b-b755-09c397c33a77 |  | note | SP-L-BSK-TE-002-A
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Workers to sign on the following:
label | aa6a5872-616f-5157-834b-269427f51cb1 |  | note | SWMS (Simpli)
label | 03bce694-94bd-5459-b0e8-c700cc9e0555 |  | note | Methodology
label | 8262e9a4-fd77-5c12-aaeb-d3816ea00c5c |  | note | Management Plans
label | 98234652-6841-54e5-9488-180f09dde51b |  | note | Plant Inducted
checkpoint-status |  |  | checkpoint | Built to Set Out Extent of excavation
checkpoint-status |  |  | checkpoint | Mark 100mm offset along wall DL28
checkpoint-status |  |  | checkpoint | Exclusion Zones Setup with Hard Barriers and Signage
checkpoint-status |  |  | checkpoint | Air exhaust installed
checkpoint-status |  |  | checkpoint | Lights installed
checkpoint-status |  |  | checkpoint | Dust suppression in-place including plumbing to rock saw
checkpoint-status |  |  | checkpoint | Vibration Monitors in-place
checkpoint-status |  |  | checkpoint | Air Monitors in-place
checkpoint-status |  |  | checkpoint | Plant Pre-start Complete
checkpoint-status |  |  | checkpoint | Equipment Test and Tag
checkpoint-status |  |  | checkpoint | FFE Tagged
checkpoint-status |  |  | checkpoint | Inspect saw.
checkpoint-status |  |  | checkpoint | Environmental Controls in place as per methodology
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-group |  |  | section | Footing Trimming along DL26
checkpoint-status |  |  | checkpoint | BOH material excavation material bench level.
checkpoint-status |  |  | checkpoint | Bench is suitably constructed
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Sawcuts at 450mm depth at a time along marked Set Out 100mm from wall (first half of wall);
checkpoint-status |  |  | checkpoint | Footing trimmed down to 450 level.
checkpoint-status |  |  | checkpoint | Additional Sawcut for second drop to req.
text | 8621ccd8-96e3-5488-abe9-8f19b8f3d0ad |  | textbox | Trimmed Height
checkpoint-status |  |  | checkpoint | Footing trimmed down to req. level.
text | 98c756d9-92a6-5bdb-82e7-4fa2f6cd691a |  | textbox | Final trim RL required
text | 7f39bc0d-1e80-5e1b-a652-689bbfba0b71 |  | textbox | Measured RL
checkpoint-status |  |  | checkpoint | Site is free from trip hazards
checkpoint-group |  |  | section | Inspections
checkpoint-status |  |  | checkpoint | Geotech engineering & Structural Engineer to inspect face of DL26 cut face to confirm no stitching or strengthening works required
checkpoint-status |  |  | checkpoint | Sign-off received on works
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | As-built issued and works closed out
checklist-flat |  |  | checklist | ITP005 - Lead Paint & Mould |  |  |  |  | Yes | ITP005 - Lead Paint & Mould | efa1aac7-c736-4a2d-8107-a09f17934eef
checkpoint-status |  |  | checkpoint | Scope of Work Extent Reviewed
label | b4f7660d-0ddb-5878-8275-dcc2346ff1d0 |  | note | Refer to Contract Scope Documentation:
label | 89807019-0a66-51ba-8718-1c3cdfda6400 |  | note | Lead, Mould, Soft Strip Scope – P1 Rev B.pdf
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Encapsulate, seal and stabilise the existing lead paint on all walls, ceilings, doors, metal structures (stairs, walkways, balustrades etc.) and other surfaces which have been painted with lead paint within the areas shown, in accordance with Australian Standards.
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Clean, wipe down, vacuum and/or chemically treat all porous & nonporous surfaces which contain both surface level and penetrated mould.
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Hygienist has inspected the area and provided a report confirming lead paint has been remediated to a satisfactory extent.
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Following completion of works, Delta and Built have inspected the work area & accepted works as completed.
holdpoint |  |  | signoff | Signed by Delta Group & Built
checkpoint-status |  |  | checkpoint | Unsuitable Paint Removed
checkpoint-status |  |  | checkpoint | Encapsulation Installed
checkpoint-status |  |  | checkpoint | Mould Remediation Complete
holdpoint |  |  | signoff | Signed by Delta Group & Built