## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Waterproofing ITP |  |  |  |  | Yes | Waterproofing ITP | 509e8877-686c-4e14-a7f8-827d31bdc840
checkpoint-group |  |  | section | Specifications & Safety
checkpoint-status |  |  | checkpoint | Current manufacturer's product Specification and materials confirmed (RLA, Sika)
checkpoint-group |  |  | section | Verification of Preceding Works
checkpoint-status |  |  | checkpoint | Confirm substrate is clean and empty from any coating, sharp edges, rough concrete, oils, grease, spray marks and any other materials that will impact adhesion
checkpoint-status |  |  | checkpoint | Confirm base substrate is dry, clean, and smooth surfaces for application of membrane. Moisture content to meet the manufacturer’s recommendation and the material data sheet.
checkpoint-status |  |  | checkpoint | Confirm substrate details are as per drawing and specifications. i.e., falls to drains, flashing rebates, hobs, angles have been constructed properly to enable membrane systems to work as per manufacturer's specifications.
checkpoint-group |  |  | section | Hobs
checkpoint-status |  |  | checkpoint | Confirm substrate is clean and empty from any coating, sharp edges, rough concrete, oils, grease, spray marks and any other materials that will impact adhesion
checkpoint-status |  |  | checkpoint | Confirm base substrate is dry, clean, and smooth surfaces for application of membrane. Moisture content to meet the manufacturer’s recommendation and the material data sheet.
checkpoint-status |  |  | checkpoint | Confirm substrate details are as per drawing and specifications. i.e., falls to drains, flashing rebates, hobs, angles have been constructed properly to enable membrane systems to work as per manufacturer's specifications.
checkpoint-status |  |  | checkpoint | Checked Moisture content in concrete before waterproofing
checkpoint-status |  |  | checkpoint | Confirm application of two-part water-based (Moisture Seal Primer) to the floors.
checkpoint-status |  |  | checkpoint | Confirm application of 1st coat of RLA PU850 (oil base) to the floors
checkpoint-status |  |  | checkpoint | Confirm application of 2nd coat of RLA PU850 (oil base) to the floors
checkpoint-status |  |  | checkpoint | Membrane application as per manufacturer specifications and Australian Standards
checkpoint-status |  |  | checkpoint | Confirm membrane thickness is minimum 1000 microns
checkpoint-group |  |  | section | Bathrooms & Laundries
checkpoint-status |  |  | checkpoint | Confirm all joints are cleaned and sealed with coving/fillet between floor and wall junctions. Joints widths for sealing no more than 5mm
checkpoint-status |  |  | checkpoint | Checked Moisture content in concrete before waterproofing
checkpoint-status |  |  | checkpoint | Water stops (3mm) supply/install laser square as specified
checkpoint-status |  |  | checkpoint | Confirm application of two-part water-based (Moisture Seal Primer) to the floors.
checkpoint-status |  |  | checkpoint | Confirm application of primer (Uniprime) to the walls.
checkpoint-status |  |  | checkpoint | Confirm application of 1st coat & 2nd coat of RLA PU850 (oil base) to the floors
checkpoint-status |  |  | checkpoint | Confirm application of 1st coat & 2nd coat of RLA WPM (water base) to the walls.
checkpoint-status |  |  | checkpoint | Flood tested for 24 hours
checkpoint-status |  |  | checkpoint | Membrane application as per manufacturer specifications and Australian Standards
checkpoint-group |  |  | section | Balconies
checkpoint-status |  |  | checkpoint | Confirm all joints are cleaned and sealed with coving/fillet between floor and wall junctions. Joints widths for sealing no more than 5mm
checkpoint-status |  |  | checkpoint | Confirm membrane wall upturns are maximum 150mm and 100mm above FFL (floor finish level)
checkpoint-status |  |  | checkpoint | Confirm falls to drainage outlets in floor substrate 1:100 minimum
checkpoint-status |  |  | checkpoint | Checked Moisture content in concrete before waterproofing
checkpoint-status |  |  | checkpoint | Confirm application of two-part water-based (Moisture Seal Primer). Primer must be completely dry prior to application of sealant and membrane.
checkpoint-status |  |  | checkpoint | Confirm application of bond breaker single component (Sikaflex)
checkpoint-status |  |  | checkpoint | Confirm application of 1st coat & 2nd coat of RLA PU850 (oil base)
checkpoint-status |  |  | checkpoint | Membrane application as per manufacturer specifications and Australian Standards
checkpoint-status |  |  | checkpoint | Confirm application of Sikaflex to the sides.
checkpoint-status |  |  | checkpoint | Flood tested for 24 hours
checkpoint-status |  |  | checkpoint | Confirm edge to drip groove with the application of Moisture seal and 2 Part Cementitious
checkpoint-status |  |  | checkpoint | Confirm sand cement screed Waterproof on top of sand & cement with Moisture seal and 2 Part Cementitious
checkpoint-group |  |  | section | Planter Boxes
checkpoint-status |  |  | checkpoint | Pre-waterproofing surface preparation
checkpoint-status |  |  | checkpoint | Confirm the application of Moisture seal primer
checkpoint-status |  |  | checkpoint | Confirm the application of 2 Part membrane with bandage tape.
checkpoint-group |  |  | section | Hold Point
checkpoint-status |  |  | checkpoint | Confirm membrane thickness is minimum 1000 microns
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Day completion as per time stamped photos
holdpoint |  |  | signoff | Hold Point
checklist-sectioned |  |  | checklist | Tiling ITP |  |  |  |  | Yes | Tiling ITP | 5e4f484b-49e8-4da6-b9a9-1f64136592c2
checkpoint-group |  |  | section | Sand & Cement Bedding
checkpoint-status |  |  | checkpoint | Confirm set-out, step-downs and finish floor levels
checkpoint-status |  |  | checkpoint | Lay bedding as specified (40mm bed)
checkpoint-status |  |  | checkpoint | Confirm step-downs and falls are as per Australian Standards
checkpoint-group |  |  | section | Floor Tiling
checkpoint-status |  |  | checkpoint | Check waterproofing is applied to wet area floor
checkpoint-status |  |  | checkpoint | Lay tiles to set out as specified
checkpoint-status |  |  | checkpoint | Adhesive used is as specified
checkpoint-status |  |  | checkpoint | Tiles used are as specified
checkpoint-status |  |  | checkpoint | Grout colour and consistency
checkpoint-status |  |  | checkpoint | Falls to floor wastes are as per Australian Standards
checkpoint-status |  |  | checkpoint | Tiled areas are free of damaged tiles
checkpoint-status |  |  | checkpoint | All joints are sealed with silicon as specified
checkpoint-status |  |  | checkpoint | Floor wastes pipes are clean and block free from screed
checkpoint-status |  |  | checkpoint | Trims and Floor wastes as specified
checkpoint-group |  |  | section | Wall Tiling
checkpoint-status |  |  | checkpoint | Check walls are plumb and square
checkpoint-status |  |  | checkpoint | Check waterproofing applied to wet area walls
checkpoint-status |  |  | checkpoint | Confirm set-out for wall tiles
checkpoint-status |  |  | checkpoint | Adhesive used is a specified
checkpoint-status |  |  | checkpoint | Tiles used are as specified
checkpoint-status |  |  | checkpoint | Grout colour and consistency
checkpoint-status |  |  | checkpoint | Filed areas are free of damaged tiles.
checkpoint-status |  |  | checkpoint | All joints are sealed with silicon as specified
checkpoint-status |  |  | checkpoint | Notch trowel glue applied
checkpoint-status |  |  | checkpoint | Trim/Angles used are as specified
checkpoint-status |  |  | checkpoint | Final Review & Sign-off
holdpoint |  |  | signoff | Hold Point