## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP042 - AGL Shallow Base Cans | itp |  |  |  |  | FH-ZU2-QU-ITP042 - AGL Shallow Base Cans - Rev 0
section | 1.0 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are using the latest and complete set of drawings
label | Reference Documents - IFC Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - Drawings
label | IP
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing any activities
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is PSP, EMP, TMP, SWMS & WP.
label | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
label | Inspection/Test Method - Verify
label | Record of conformity - Site and office Inspection
label | HP*
label | Responsibility - Project Engineer / Site Supervisor
date | Date Completed:
checkpoint | 1.3 - Material/equipment approvals
label | Frequency - Prior to start
label | Acceptance Criteria - Materials and equipment that shall be used in the construction of the works as nominated on the Drawings.
label | Reference Documents - ZULU-BECA-001-SPC-00003 cl 2.3
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex reference(s)
label | HP*
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | 1.4 - Setting out for airfield luminaires
label | Frequency - Each Lot
label | Acceptance Criteria - HOLD POINT
label | ○ The Contractor shall survey the proposed light locations in conjunction with the new and existing line-marking to set out the proposed lights. A schedule of the proposed lights shall be produced and submitted to the Contract Administrator.
label | Reference Documents - ZULU- BECA-001-SPC-00003 cl 5.4
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex reference
label | HP
label | Responsibility - Project Engineer / Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 - Removal of Existing Can
checkpoint | 2.1 - Removal of existing AGL can
label | Frequency - Each lot
label | Acceptance Criteria -
label | Reference Documents - ZULU-BECA-024-DWG-07513
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed, Avionics Removal of Existing Can checklist
label | IP
label | Responsibility - Project Engineer
date | Date Completed:
section | 3.0 - Installation of Shallow Base Can
checkpoint | 3.1 - Inset luminaire base can
label | Frequency - Each lot
label | Acceptance Criteria -
label | Reference Documents - ZULU-BECA-024-DWG-07501, ZULU-BECA-024-DWG-07506-8
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed, Avionics Shallow Canister Installation checklist
label | IP
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: